## 00_Cover
HOMEOCENTRUM — WEB / UI / MOBILE / QA TASK REGISTERS
Split from Homeocentrum_Feature_Delivery_Task_Register.xlsx · Source PDF 29 August 2026 · Every original sub-task is in exactly one track
How the four teams work (read this before coding)
1. This file is the team split of the master sequential register. The master remains the programme source of truth. Do not skip a PDF feature — if it is not on your sheet, another track owns it (see Sister Tracks).
2. Each original sub-task is assigned to EXACTLY one track so work is not double-counted. Sum of Web + UI + Mobile + QA = all 1,000 master sub-tasks.
3. Develop strictly by Track Seq on your sequential sheet. Original Seq is the global programme order (Phase PRE → 0 → … → 19).
4. WEB owns: database, APIs, backend, security (login/RBAC/OTP/audit), payment gateway, SMS/video/push server, Account ledger, client decisions. Start here for every Main Task that has a Web sister.
5. UI owns: React web screens for Admin, Doctor, Reception, Account, Public website, Pharmacy console (Layer = Web SPA). Do not invent a second API — call Web APIs.
6. MOBILE owns: Patient iOS/Android and Doctor iOS/Android screens (Mobile UI / client / UX). Case-taking stays on Doctor web. Consume the same .NET 8 APIs.
7. QA owns: every Regression / QA layer row (acceptance, IDOR, parity, E2E). QA of a Main Task starts when that Main Task’s Web/UI/Mobile implementation rows are Done.
8. Column “Wait for other track” lists original Depends On IDs that are NOT on your sheet (usually a Web API). Do not start until those IDs are Done on the other sheet.
9. Column “Sister Tracks” lists other tracks that have sub-tasks under the same Main Task ID. Typical pattern: Web (DB+API) → UI (screen) → Mobile (app screen) → QA.
10. Work Type is unchanged from the master: Existing = keep/regression only; Existing Improvement = finish partial; Existing Modification = change behaviour; New = build; New Integration = vendor.
11. Status dropdown is the only column to edit daily. Owner defaults to the track name; assign people as needed.
12. Sheet 09_Traceability maps Original Seq → Track. If a master row is missing there, that is a defect — stop and fix the generator before coding.
Track counts (exclusive assignment)
Track | What you build | Sub tasks | Main tasks (with ≥1 sub) | Sheet to execute
Web | DB, API, backend, security, payments, integrations, PRE client gates | 378 | 196 | 01_Web_Sequential
UI | React SPA screens — Admin, Doctor, Reception, Account, Public, Pharmacy | 135 | 132 | 02_UI_Sequential
Mobile | Patient app + Doctor app (no case-taking on phone) | 209 | 72 | 03_Mobile_Sequential
QA | Regression packs, acceptance, IDOR, iOS/Android parity, E2E ecosystem proof | 278 | 274 | 04_QA_Sequential
Integrity: original sub-tasks = 1000 · assigned = 1000 · unique Main Task IDs in master = 280 · none dropped.
Work Type legend (same as master)
Existing | Live today. Keep. Do not rebuild.
Existing Improvement | Exists but stub, partial, or missing a role surface.
Existing Modification | Exists but behaviour must change.
New | Not in the three repos.
New Integration | Vendor/gateway (Razorpay, video SDK, SMS, FCM).
Configuration | Rates/flags/templates — not hardcoded.
Data Migration | Additive schema / backfill.
Client Decision | Blocks engineering until signed (Web PRE rows).
Regression | QA track — prove it still works.

## 01_Web_Sequential
WEB SEQUENTIAL BACKLOG — DB, API, backend, security, payments, integrations, PRE decisions. Execute top to bottom by Track Seq. Do not skip. UI/Mobile/QA of the same Main Task wait on your Done status.
Track Seq | Original Seq | Track | Phase | Phase Name | WBS | Main Task ID | Main Task | Sub Task ID | Sub Task | Work Type | Module / Area | PDF Section | PDF Feature (exact wording) | PDF Delivery Text | Application Surface | Layer | Frontend | Backend | Database | API | Mobile | Integration | Priority | Effort Band | Depends On (original) | Depends On (this track) | Sister Tracks (same Main Task) | Wait for other track | Existing Capability (AS-IS) | Gap / Change Required (TO-BE) | Acceptance Criteria | Status | Owner | Notes
1 | 1 | Web | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.1 | PRE-01 | Decide settlement model — Homeocentrum holds all money (food-delivery / quick-commerce pattern) | PRE-01.01 | Workshop with finance: confirm Homeocentrum is single merchant of record for consult + medicine + subscription | Client Decision | Finance | §9 + §8 | Every transaction passes through Homeocentrum | Built on the principle: every transaction passes through Homeocentrum, in the same way a food-delivery or quick-commerce platform holds all payments centrally. | Account / Gateway | Decision | No | No | No | No | No | No | P0 | S | — | — | — |  | Only doctor SaaS subscription via client-side Razorpay; no consult/medicine ledger | Written decision: platform-held funds + periodic NEFT (v1) vs Razorpay Route (v2) | Signed decision recorded; payout architecture unblocked | Not Started | Web
2 | 2 | Web | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.1 | PRE-01 | Decide settlement model — Homeocentrum holds all money (food-delivery / quick-commerce pattern) | PRE-01.02 | Choose v1 payout mechanic: Homeocentrum-held + NEFT/IMPS vs Razorpay Route / linked accounts | Client Decision | Finance | §9 + §8 | Every transaction passes through Homeocentrum | Built on the principle: every transaction passes through Homeocentrum, in the same way a food-delivery or quick-commerce platform holds all payments centrally. | Account / Gateway | Decision | No | No | No | No | No | Yes | P0 | S | PRE-01.01 | T-1 (PRE-01.01) | — |  | Only doctor SaaS subscription via client-side Razorpay; no consult/medicine ledger | Written decision: platform-held funds + periodic NEFT (v1) vs Razorpay Route (v2) | Signed decision recorded; payout architecture unblocked | Not Started | Web
3 | 3 | Web | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.1 | PRE-01 | Decide settlement model — Homeocentrum holds all money (food-delivery / quick-commerce pattern) | PRE-01.03 | Record decision in config (SettlementModel) — engineering must not hardcode a split model | Configuration | Finance | §9 + §8 | Every transaction passes through Homeocentrum | Built on the principle: every transaction passes through Homeocentrum, in the same way a food-delivery or quick-commerce platform holds all payments centrally. | Account / Gateway | Configuration | No | Yes | No | No | No | No | P0 | S | PRE-01.02 | T-2 (PRE-01.02) | — |  | Only doctor SaaS subscription via client-side Razorpay; no consult/medicine ledger | Written decision: platform-held funds + periodic NEFT (v1) vs Razorpay Route (v2) | Signed decision recorded; payout architecture unblocked | Not Started | Web
4 | 4 | Web | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.2 | PRE-02 | Decide reception cash policy — clinic retains vs remits to Homeocentrum | PRE-02.01 | OQ: cash collected at reception retained by clinic or remitted to Homeocentrum? | Client Decision | Finance / Reception | §9 | Reception payment collection | Cash, UPI, card or payment link with printed receipt | Account / Reception | Decision | No | No | No | No | No | No | P0 | S | — | — | — |  | No reception collection; no S3 ledger | Policy for cash/UPI at clinic: retain at clinic (still ledgered) or remit | Written policy; clinic collection view can be designed | Not Started | Web
5 | 5 | Web | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.2 | PRE-02 | Decide reception cash policy — clinic retains vs remits to Homeocentrum | PRE-02.02 | Document GST treatment on consult fee, platform fee, and medicine (on which amount, which GSTIN) | Client Decision | Finance / Reception | §9 | Reception payment collection | Cash, UPI, card or payment link with printed receipt | Account / Reception | Decision | No | No | No | No | No | No | P0 | S | PRE-02.01 | T-4 (PRE-02.01) | — |  | No reception collection; no S3 ledger | Policy for cash/UPI at clinic: retain at clinic (still ledgered) or remit | Written policy; clinic collection view can be designed | Not Started | Web
6 | 6 | Web | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.2 | PRE-02 | Decide reception cash policy — clinic retains vs remits to Homeocentrum | PRE-02.03 | Confirm commission %, settlement hold T+N days, invoice numbering series — configuration not code | Configuration | Finance / Reception | §9 | Reception payment collection | Cash, UPI, card or payment link with printed receipt | Account / Reception | Configuration | No | Yes | No | No | No | No | P0 | S | PRE-02.02 | T-5 (PRE-02.02) | — |  | No reception collection; no S3 ledger | Policy for cash/UPI at clinic: retain at clinic (still ledgered) or remit | Written policy; clinic collection view can be designed | Not Started | Web
7 | 7 | Web | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.3 | PRE-03 | Vendor and legal gates — video SDK, SMS, WhatsApp, push, DPDP copy | PRE-03.01 | Select in-browser + mobile video vendor (Agora / Twilio / Daily / WebRTC self-host) — required for §10 | Client Decision | Platform | §10 + §14 + §17 | Telemedicine + notifications + consent | Video consultation; SMS/WhatsApp/Push/Email; consent records | Shared | Decision | No | No | No | No | No | Yes | P0 | S | — | — | — |  | WhatsApp Meta Cloud partial; no video SDK; no SMS provider; no FCM; privacy/terms incomplete for DPDP/tele/pharmacy | Named vendors + DPDP-ready legal copy before those phases start | Vendors contracted or shortlisted; legal pages drafted | Not Started | Web
8 | 8 | Web | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.3 | PRE-03 | Vendor and legal gates — video SDK, SMS, WhatsApp, push, DPDP copy | PRE-03.02 | Select SMS provider (MSG91 / Twilio / etc.) and confirm DLT templates for appointment/OTP/cancel | Client Decision | Platform | §10 + §14 + §17 | Telemedicine + notifications + consent | Video consultation; SMS/WhatsApp/Push/Email; consent records | Shared | Decision | No | No | No | No | No | Yes | P0 | S | PRE-03.01 | T-7 (PRE-03.01) | — |  | WhatsApp Meta Cloud partial; no video SDK; no SMS provider; no FCM; privacy/terms incomplete for DPDP/tele/pharmacy | Named vendors + DPDP-ready legal copy before those phases start | Vendors contracted or shortlisted; legal pages drafted | Not Started | Web
9 | 9 | Web | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.3 | PRE-03 | Vendor and legal gates — video SDK, SMS, WhatsApp, push, DPDP copy | PRE-03.03 | Legal: privacy (data protection, recording, pharmacy consent) and terms (payments, refunds, telemedicine, medicine orders) drafted for §4 + §17 | Client Decision | Platform | §10 + §14 + §17 | Telemedicine + notifications + consent | Video consultation; SMS/WhatsApp/Push/Email; consent records | Shared | Legal | No | No | No | No | No | No | P0 | M | PRE-03.02 | T-8 (PRE-03.02) | — |  | WhatsApp Meta Cloud partial; no video SDK; no SMS provider; no FCM; privacy/terms incomplete for DPDP/tele/pharmacy | Named vendors + DPDP-ready legal copy before those phases start | Vendors contracted or shortlisted; legal pages drafted | Not Started | Web
10 | 10 | Web | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.3 | PRE-03 | Vendor and legal gates — video SDK, SMS, WhatsApp, push, DPDP copy | PRE-03.04 | OQ: unpaid-booking slot hold duration vs release immediately if patient does not pay | Client Decision | Platform | §10 + §14 + §17 | Telemedicine + notifications + consent | Video consultation; SMS/WhatsApp/Push/Email; consent records | Shared | Decision | No | No | No | No | No | No | P0 | S | PRE-03.03 | T-9 (PRE-03.03) | — |  | WhatsApp Meta Cloud partial; no video SDK; no SMS provider; no FCM; privacy/terms incomplete for DPDP/tele/pharmacy | Named vendors + DPDP-ready legal copy before those phases start | Vendors contracted or shortlisted; legal pages drafted | Not Started | Web
11 | 11 | Web | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.3 | PRE-03 | Vendor and legal gates — video SDK, SMS, WhatsApp, push, DPDP copy | PRE-03.05 | OQ: live-doctor credentialing backfill — auto-Approve existing doctors? Unverified doctors visible only to own clinic? | Client Decision | Platform | §10 + §14 + §17 | Telemedicine + notifications + consent | Video consultation; SMS/WhatsApp/Push/Email; consent records | Shared | Decision | No | No | No | No | No | No | P0 | S | PRE-03.04 | T-10 (PRE-03.04) | — |  | WhatsApp Meta Cloud partial; no video SDK; no SMS provider; no FCM; privacy/terms incomplete for DPDP/tele/pharmacy | Named vendors + DPDP-ready legal copy before those phases start | Vendors contracted or shortlisted; legal pages drafted | Not Started | Web
12 | 12 | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.1 | FND-01 | One connected ecosystem — shared keys so a patient, appointment, prescription and payment created anywhere are visible everywhere | FND-01.01 | Publish shared-key design (DoctorId, PatientId, PatientAppId, CaseId, ErxId, LedgerTxnId, MedicineOrderId) and event list (created/rescheduled/cancelled/paid/signed/accepted) | New | Platform | §1 | One connected ecosystem serving six types of users | A patient, an appointment, a prescription and a payment created anywhere in the system are visible everywhere else — there are no separate systems to reconcile. | Shared | Architecture | No | Yes | Yes | No | No | No | P0 | M | — | — | QA |  | Doctor/Admin/Reception web only; Patient, Account, Pharmacy roles do not exist; no shared payment or eRx keys | Canonical keys: UserId/DoctorId, PatientId, PatientAppId, CaseId, ErxId, LedgerTxnId, MedicineOrderId — used by every surface | Any write on one surface is readable on all authorised surfaces within SLA; no dual ledgers | Not Started | Web
13 | 13 | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.1 | FND-01 | One connected ecosystem — shared keys so a patient, appointment, prescription and payment created anywhere are visible everywhere | FND-01.02 | Add role enum values Patient, Account, PharmacyPartner alongside existing Admin/Doctor/Reception (keep unused Management/Supervisor/Inspector unused) | New | Platform | §1 | One connected ecosystem serving six types of users | A patient, an appointment, a prescription and a payment created anywhere in the system are visible everywhere else — there are no separate systems to reconcile. | Shared | Database + Auth | Yes | Yes | Yes | No | No | No | P0 | S | FND-01.01 | T-12 (FND-01.01) | QA |  | Doctor/Admin/Reception web only; Patient, Account, Pharmacy roles do not exist; no shared payment or eRx keys | Canonical keys: UserId/DoctorId, PatientId, PatientAppId, CaseId, ErxId, LedgerTxnId, MedicineOrderId — used by every surface | Any write on one surface is readable on all authorised surfaces within SLA; no dual ledgers | Not Started | Web
14 | 14 | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.1 | FND-01 | One connected ecosystem — shared keys so a patient, appointment, prescription and payment created anywhere are visible everywhere | FND-01.03 | All new domain modules on NigaHomeopathy-API (.NET 8); do not create a third API; classic API only where login/Rx-write/Razorpay already live until ported | Existing Modification | Platform | §1 | One connected ecosystem serving six types of users | A patient, an appointment, a prescription and a payment created anywhere in the system are visible everywhere else — there are no separate systems to reconcile. | Shared | Architecture | No | Yes | No | Yes | No | No | P0 | S | FND-01.02 | T-13 (FND-01.02) | QA |  | Dual API api.homeocentrum.com + api1.homeocentrum.com | New work on .NET 8; port Razorpay off classic OrderController as part of Phase 6 | Any write on one surface is readable on all authorised surfaces within SLA; no dual ledgers | Not Started | Web
15 | 19 | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.2 | FND-02 | Delivery footprint — 2 mobile apps · 5 web portals · payment · telemedicine · digital prescription · HomeoMeds (programme skeleton) | FND-02.04 | Document the five portals: Patient Website, Doctor Web Portal, Reception Portal, Admin Portal, Account Department (Pharmacy console is HomeoMeds, not a 6th portal in the PDF count) | New | Platform | §1 | Delivery covers | 2 mobile applications · 5 web portals · payment system · telemedicine · digital prescription · online medicine delivery. | Shared | Architecture | No | No | No | No | No | No | P0 | S | FND-02.03 | — | UI, Mobile | FND-02.03 | 1 web SPA (Admin/Doctor/Reception + marketing). No patient app, doctor app, Account portal, Pharmacy console | Repo/route skeleton: Patient Website, Doctor Web, Reception, Admin, Account (+ Pharmacy console under HomeoMeds); Patient + Doctor mobile later | Five web portal shells routable by role; mobile apps scheduled in Phases 16–17 not started here | Not Started | Web
16 | 20 | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.3 | SEC-01 | Secure login — protected credentials for every user type | SEC-01.01 | DB/Migration: hash existing UserMaster passwords (bcrypt/PBKDF2); never store new plaintext | Data Migration | Security | §17 | Secure login | Protected credentials for every user type | All web + later mobile | Database | No | Yes | Yes | No | No | No | P0 | M | — | — | UI, QA |  | POST /Account/Login on classic API; JWT in sessionStorage; doctor/user passwords compared plaintext; reception hashed on classic; fakeBackend() still mounted | Hashed passwords; Role claim on JWT; disable fake backend for production paths; Patient OTP login is Phase 8 (not password) | No plaintext password compare; every role including future Patient/Account/Pharmacy authenticates through a protected path | Not Started | Web
17 | 21 | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.3 | SEC-01 | Secure login — protected credentials for every user type | SEC-01.02 | API: Login verifies hash; embed Role + DoctorId claims; keep classic login URL until .NET 8 login is cut over | Existing Modification | Security | §17 | Secure login | Protected credentials for every user type | All web + later mobile | API | No | Yes | No | Yes | No | No | P0 | M | SEC-01.01 | T-16 (SEC-01.01) | UI, QA |  | POST /Account/Login on classic API; JWT in sessionStorage; doctor/user passwords compared plaintext; reception hashed on classic; fakeBackend() still mounted | Hashed passwords; Role claim on JWT; disable fake backend for production paths; Patient OTP login is Phase 8 (not password) | No plaintext password compare; every role including future Patient/Account/Pharmacy authenticates through a protected path | Not Started | Web
18 | 24 | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.4 | SEC-02 | Secure password reset — time-limited reset links (stop plaintext email + fake thunk) | SEC-02.01 | DB: PasswordResetToken (UserId, TokenHash, ExpiresAt, UsedAt) | New | Security | §17 | Secure password reset | Time-limited reset links | Admin / Doctor / Reception web | Database | No | Yes | Yes | No | No | No | P0 | S | — | — | UI, QA |  | /forgot-password UI exists; thunk uses fake/Firebase; POST /users/ForgetPassword emails plaintext password | Tokenised reset (hash, TTL); email contains link only; ChangePassword for logged-in user | Reset email never contains the password; token expires; used token cannot be reused | Not Started | Web
19 | 25 | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.4 | SEC-02 | Secure password reset — time-limited reset links (stop plaintext email + fake thunk) | SEC-02.02 | API: ForgotPassword sends reset link; ResetPassword consumes token; stop emailing plaintext; ChangePassword for authenticated user | Existing Modification | Security | §17 | Secure password reset | Time-limited reset links | Admin / Doctor / Reception web | API | No | Yes | No | Yes | No | No | P0 | M | SEC-02.01 | T-18 (SEC-02.01) | UI, QA |  | /forgot-password UI exists; thunk uses fake/Firebase; POST /users/ForgetPassword emails plaintext password | Tokenised reset (hash, TTL); email contains link only; ChangePassword for logged-in user | Reset email never contains the password; token expires; used token cannot be reused | Not Started | Web
20 | 28 | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.5 | SEC-03 | Session control — proper sign-out across web and mobile | SEC-03.01 | API: POST /Account/Logout; persist UserLoginStatus; optional denylist until token expiry | Existing Improvement | Security | §17 | Session control | Proper sign-out across web and mobile | All | API | No | Yes | Yes | Yes | No | No | P0 | S | — | — | UI, QA |  | Client clears sessionStorage; no server logout / token revoke; UserLoginStatus unused | POST Logout persists login status; optional token denylist; mobile will call the same API in Phase 16/17 | After logout the JWT cannot call protected APIs; board session cleared (already on client) | Not Started | Web
21 | 30 | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.5 | SEC-03 | Session control — proper sign-out across web and mobile | SEC-03.03 | Contract: mobile apps MUST use the same Logout endpoint (implemented in Phases 16–17) | New | Security | §17 | Session control | Proper sign-out across web and mobile | All | API contract | No | No | No | Yes | Yes | No | P0 | S | SEC-03.02 | — | UI, QA | SEC-03.02 | Client clears sessionStorage; no server logout / token revoke; UserLoginStatus unused | POST Logout persists login status; optional token denylist; mobile will call the same API in Phase 16/17 | After logout the JWT cannot call protected APIs; board session cleared (already on client) | Not Started | Web
22 | 32 | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.6 | SEC-04 | Role-based access — each role sees only what it is permitted to see | SEC-04.01 | Backend: restore GetMenuByRole; add role attributes on new money and PII APIs | Existing Improvement | Security | §17 | Role-based access | Each role sees only what it is permitted to see | Admin / All web | API | No | Yes | No | Yes | No | No | P0 | M | — | — | UI, QA |  | RoleMaster + RoleDetail + MenuMaster exist; GetMenuByRole commented out on .NET 8; no per-route frontend ACL — any authenticated URL works | Re-enable GetMenuByRole; AuthProtected deny-by-default; [Authorize(Roles=)] on money/clinical APIs; Account cannot edit repertory; Admin cannot approve payouts | Unknown URL for a role returns 403/redirect; admin menus match DB permissions | Not Started | Web
23 | 34 | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.6 | SEC-04 | Role-based access — each role sees only what it is permitted to see | SEC-04.03 | Separation of duties seed: Account role controls money; Admin controls platform and clinical data — neither can perform the other’s role (PDF §8) | New | Security | §17 | Role-based access | Each role sees only what it is permitted to see | Admin / All web | Configuration | No | Yes | Yes | No | No | No | P0 | S | SEC-04.02 | — | UI, QA | SEC-04.02 | RoleMaster + RoleDetail + MenuMaster exist; GetMenuByRole commented out on .NET 8; no per-route frontend ACL — any authenticated URL works | Re-enable GetMenuByRole; AuthProtected deny-by-default; [Authorize(Roles=)] on money/clinical APIs; Account cannot edit repertory; Admin cannot approve payouts | Unknown URL for a role returns 403/redirect; admin menus match DB permissions | Not Started | Web | PDF: 'the Account department controls money. Admin controls the platform and clinical data.'
24 | 36 | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.7 | SEC-05 | Patient data protection — health records restricted to the treating doctor and the patient | SEC-05.01 | API: enforce DoctorId ownership on Patient, Appointment, Case, Rx, notes, labs, board backup | Existing Improvement | Security | §17 | Patient data protection | Health records restricted to the treating doctor and the patient | API | API | No | Yes | No | Yes | No | No | P0 | L | — | — | QA |  | Many repertory APIs have [Authorize] commented; directory browsing enabled for /attachments and /Blogs; no patient-scoped ACL on case data | Every case/Rx/note/lab query filtered by treating DoctorId (or PatientId for patient token); disable directory browsing | Doctor A cannot read Doctor B’s patient board payload; unauthenticated attachment URLs fail | Not Started | Web
25 | 37 | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.7 | SEC-05 | Patient data protection — health records restricted to the treating doctor and the patient | SEC-05.02 | Disable directory browsing on /attachments and /Blogs; signed-URL or authorised download for documents | Existing Modification | Security | §17 | Patient data protection | Health records restricted to the treating doctor and the patient | API | API | No | Yes | No | No | No | No | P0 | S | SEC-05.01 | T-24 (SEC-05.01) | QA |  | Many repertory APIs have [Authorize] commented; directory browsing enabled for /attachments and /Blogs; no patient-scoped ACL on case data | Every case/Rx/note/lab query filtered by treating DoctorId (or PatientId for patient token); disable directory browsing | Doctor A cannot read Doctor B’s patient board payload; unauthenticated attachment URLs fail | Not Started | Web
26 | 39 | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.8 | SEC-06 | Consent records infrastructure — every consent captured, stored and reviewable | SEC-06.01 | DB: ConsentRecord + ConsentType master (Privacy, Booking, TeleRecording, PharmacyShare, Marketing, Caregiver) | New | Security / Trust | §17 | Consent records | Every consent captured, stored and reviewable | Shared | Database | No | Yes | Yes | No | No | No | P0 | S | — | — | QA |  | AudioCaseConsentLog exists for audio case taking only | ConsentRecord (PatientId, Type, Version, GrantedAt, WithdrawnAt, SourceSurface) covering privacy, booking, recording, pharmacy share, marketing | Any later feature that needs consent writes this table; withdrawal is queryable | Not Started | Web
27 | 40 | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.8 | SEC-06 | Consent records infrastructure — every consent captured, stored and reviewable | SEC-06.02 | API: Grant / Withdraw / List-mine / Admin-audit (no clinical content in the API response beyond type+time) | New | Security / Trust | §17 | Consent records | Every consent captured, stored and reviewable | Shared | API | No | Yes | No | Yes | No | No | P0 | M | SEC-06.01 | T-26 (SEC-06.01) | QA |  | AudioCaseConsentLog exists for audio case taking only | ConsentRecord (PatientId, Type, Version, GrantedAt, WithdrawnAt, SourceSurface) covering privacy, booking, recording, pharmacy share, marketing | Any later feature that needs consent writes this table; withdrawal is queryable | Not Started | Web
28 | 41 | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.8 | SEC-06 | Consent records infrastructure — every consent captured, stored and reviewable | SEC-06.03 | Reuse AudioCaseConsentLog pattern; do not fork a second consent model for telemedicine (Phase 11 will write TeleRecording into ConsentRecord) | Existing Improvement | Security / Trust | §17 | Consent records | Every consent captured, stored and reviewable | Shared | API | No | Yes | No | No | No | No | P0 | S | SEC-06.02 | T-27 (SEC-06.02) | QA |  | AudioCaseConsentLog exists for audio case taking only | ConsentRecord (PatientId, Type, Version, GrantedAt, WithdrawnAt, SourceSurface) covering privacy, booking, recording, pharmacy share, marketing | Any later feature that needs consent writes this table; withdrawal is queryable | Not Started | Web
29 | 43 | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.9 | SEC-07 | OTP verification infrastructure — applied to sensitive actions including payouts and pharmacy acceptance | SEC-07.01 | DB: OtpChallenge, OtpAuditLog (Action, EntityType, EntityId, ToMasked, Success, At) | New | Security | §17 + §8 + §12 | OTP verification | Applied to sensitive actions including payouts and pharmacy acceptance | Shared | Database | No | Yes | Yes | No | No | No | P0 | S | — | — | QA |  | No generic OTP control plane; patient OTP login does not exist | OtpChallenge + OtpAuditLog; Account/Admin can query who/when/entity/success without seeing card data | Payout and pharmacy-accept cannot complete without a successful OTP; failures are auditable | Not Started | Web
30 | 44 | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.9 | SEC-07 | OTP verification infrastructure — applied to sensitive actions including payouts and pharmacy acceptance | SEC-07.02 | API: RequestOtp / VerifyOtp (generic); rate-limit; lockout; SMS provider adapter stub until PRE-03 vendor is live | New | Security | §17 + §8 + §12 | OTP verification | Applied to sensitive actions including payouts and pharmacy acceptance | Shared | API | No | Yes | No | Yes | No | Yes | P0 | M | SEC-07.01 | T-29 (SEC-07.01) | QA |  | No generic OTP control plane; patient OTP login does not exist | OtpChallenge + OtpAuditLog; Account/Admin can query who/when/entity/success without seeing card data | Payout and pharmacy-accept cannot complete without a successful OTP; failures are auditable | Not Started | Web
31 | 45 | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.9 | SEC-07 | OTP verification infrastructure — applied to sensitive actions including payouts and pharmacy acceptance | SEC-07.03 | GET /api/Otp/Audit for Account and Admin (masked destination) | New | Security | §17 + §8 + §12 | OTP verification | Applied to sensitive actions including payouts and pharmacy acceptance | Shared | API | No | Yes | No | Yes | No | No | P0 | S | SEC-07.02 | T-30 (SEC-07.02) | QA |  | No generic OTP control plane; patient OTP login does not exist | OtpChallenge + OtpAuditLog; Account/Admin can query who/when/entity/success without seeing card data | Payout and pharmacy-accept cannot complete without a successful OTP; failures are auditable | Not Started | Web
32 | 47 | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.10 | SEC-08 | Complete audit trail — who did what and when across payments, prescriptions and approvals | SEC-08.01 | DB: AuditEvent (ActorUserId, Role, Action, Entity, OldJson, NewJson, At, CorrelationId) | New | Security | §17 + §9 | Complete audit trail | Who did what, and when, across payments, prescriptions and approvals / Every transaction traceable end to end by Homeocentrum | Shared | Database | No | Yes | Yes | No | No | No | P0 | S | — | — | QA |  | No platform-wide audit; no AppointmentChangeLog; no payment webhook store | Append-only AuditEvent for money, eRx sign, credentialing, payout, pharmacy accept; payments get a dedicated trail in Phase 6 | Account can reconstruct any sensitive action without calling a doctor | Not Started | Web
33 | 48 | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.10 | SEC-08 | Complete audit trail — who did what and when across payments, prescriptions and approvals | SEC-08.02 | API middleware: write audit on mutating money/Rx/approval endpoints (start with a helper used by later phases) | New | Security | §17 + §9 | Complete audit trail | Who did what, and when, across payments, prescriptions and approvals / Every transaction traceable end to end by Homeocentrum | Shared | API | No | Yes | No | No | No | No | P0 | M | SEC-08.01 | T-32 (SEC-08.01) | QA |  | No platform-wide audit; no AppointmentChangeLog; no payment webhook store | Append-only AuditEvent for money, eRx sign, credentialing, payout, pharmacy accept; payments get a dedicated trail in Phase 6 | Account can reconstruct any sensitive action without calling a doctor | Not Started | Web
34 | 50 | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.11 | SEC-09 | Secure documents — prescriptions, reports and uploads protected from unauthorised access | SEC-09.01 | DB: SecureDocument (OwnerType, OwnerId, BlobPath, Mime, Hash, CreatedBy) | New | Security | §17 | Secure documents | Prescriptions, reports and uploads protected from unauthorised access | Shared | Database | No | Yes | Yes | No | No | No | P1 | S | — | — | QA |  | Attachments served with directory browsing; no signed URLs; no patient upload module | Authorised download; virus-scan hook; patient uploads in Phase 15 use this store | Guessable URL does not leak a prescription PDF | Not Started | Web
35 | 51 | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.11 | SEC-09 | Secure documents — prescriptions, reports and uploads protected from unauthorised access | SEC-09.02 | API: upload (multipart) + authorised GET; no public folder listing | New | Security | §17 | Secure documents | Prescriptions, reports and uploads protected from unauthorised access | Shared | API | No | Yes | No | Yes | No | No | P1 | M | SEC-09.01 | T-34 (SEC-09.01) | QA |  | Attachments served with directory browsing; no signed URLs; no patient upload module | Authorised download; virus-scan hook; patient uploads in Phase 15 use this store | Guessable URL does not leak a prescription PDF | Not Started | Web
36 | 54 | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.1 | ADM-R01 | Keep and harden Admin Repertory sections (do not rebuild) | ADM-R01.02 | ACL: only Admin (and permitted roles) can mutate Repertory sections; Doctor is read-only consumer on Patient Board | Existing Improvement | Repertory | §7.1 | Repertory sections | Manage repertory sections | Admin Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | ADM-R01.01 | — | QA | ADM-R01.01 | Admin Repertory section CRUD live (pages/Admin/Repertory) | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Repertory sections still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | Web
37 | 55 | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.1 | ADM-R01 | Keep and harden Admin Repertory sections (do not rebuild) | ADM-R01.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Repertory sections; do not silently switch | Existing | Repertory | §7.1 | Repertory sections | Manage repertory sections | Admin Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | ADM-R01.02 | T-36 (ADM-R01.02) | QA |  | Admin Repertory section CRUD live (pages/Admin/Repertory) | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Repertory sections still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | Web
38 | 57 | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.2 | ADM-R02 | Keep and harden Admin Subsection & rubric tree (do not rebuild) | ADM-R02.02 | ACL: only Admin (and permitted roles) can mutate Subsection & rubric tree; Doctor is read-only consumer on Patient Board | Existing Improvement | Repertory | §7.1 | Subsection & rubric tree | Manage the full rubric hierarchy | Admin Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | ADM-R02.01 | — | QA | ADM-R02.01 | Hierarchical subsection/rubric tree + Excel import/export live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Subsection & rubric tree still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | Web
39 | 58 | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.2 | ADM-R02 | Keep and harden Admin Subsection & rubric tree (do not rebuild) | ADM-R02.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Subsection & rubric tree; do not silently switch | Existing | Repertory | §7.1 | Subsection & rubric tree | Manage the full rubric hierarchy | Admin Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | ADM-R02.02 | T-38 (ADM-R02.02) | QA |  | Hierarchical subsection/rubric tree + Excel import/export live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Subsection & rubric tree still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | Web
40 | 60 | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.3 | ADM-R03 | Keep and harden Admin Rubric–remedy mapping (do not rebuild) | ADM-R03.02 | ACL: only Admin (and permitted roles) can mutate Rubric–remedy mapping; Doctor is read-only consumer on Patient Board | Existing Improvement | Repertory | §7.1 | Rubric–remedy mapping | Map remedies to rubrics with author and grade | Admin Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | ADM-R03.01 | — | QA | ADM-R03.01 | Rubric-remedy mapping by author/grade live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Rubric–remedy mapping still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | Web
41 | 61 | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.3 | ADM-R03 | Keep and harden Admin Rubric–remedy mapping (do not rebuild) | ADM-R03.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Rubric–remedy mapping; do not silently switch | Existing | Repertory | §7.1 | Rubric–remedy mapping | Map remedies to rubrics with author and grade | Admin Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | ADM-R03.02 | T-40 (ADM-R03.02) | QA |  | Rubric-remedy mapping by author/grade live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Rubric–remedy mapping still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | Web
42 | 63 | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.4 | ADM-R04 | Keep and harden Admin Remedy-linked rubrics (do not rebuild) | ADM-R04.02 | ACL: only Admin (and permitted roles) can mutate Remedy-linked rubrics; Doctor is read-only consumer on Patient Board | Existing Improvement | Repertory | §7.1 | Remedy-linked rubrics | View all rubrics linked to a remedy | Admin Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | ADM-R04.01 | — | QA | ADM-R04.01 | Remedial-rubrics viewer live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Remedy-linked rubrics still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | Web
43 | 64 | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.4 | ADM-R04 | Keep and harden Admin Remedy-linked rubrics (do not rebuild) | ADM-R04.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Remedy-linked rubrics; do not silently switch | Existing | Repertory | §7.1 | Remedy-linked rubrics | View all rubrics linked to a remedy | Admin Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | ADM-R04.02 | T-42 (ADM-R04.02) | QA |  | Remedial-rubrics viewer live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Remedy-linked rubrics still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | Web
44 | 66 | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.5 | ADM-R05 | Keep and harden Admin Language master (do not rebuild) | ADM-R05.02 | ACL: only Admin (and permitted roles) can mutate Language master; Doctor is read-only consumer on Patient Board | Existing Improvement | Repertory | §7.1 | Language master | Manage languages | Admin Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | ADM-R05.01 | — | QA | ADM-R05.01 | Language master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Language master still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | Web
45 | 67 | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.5 | ADM-R05 | Keep and harden Admin Language master (do not rebuild) | ADM-R05.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Language master; do not silently switch | Existing | Repertory | §7.1 | Language master | Manage languages | Admin Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | ADM-R05.02 | T-44 (ADM-R05.02) | QA |  | Language master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Language master still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | Web
46 | 69 | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.6 | ADM-R06 | Keep and harden Admin Body part master (do not rebuild) | ADM-R06.02 | ACL: only Admin (and permitted roles) can mutate Body part master; Doctor is read-only consumer on Patient Board | Existing Improvement | Repertory | §7.1 | Body part master | Manage body parts | Admin Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | ADM-R06.01 | — | QA | ADM-R06.01 | Body part master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Body part master still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | Web
47 | 70 | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.6 | ADM-R06 | Keep and harden Admin Body part master (do not rebuild) | ADM-R06.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Body part master; do not silently switch | Existing | Repertory | §7.1 | Body part master | Manage body parts | Admin Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | ADM-R06.02 | T-46 (ADM-R06.02) | QA |  | Body part master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Body part master still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | Web
48 | 72 | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.7 | ADM-R07 | Keep and harden Admin Intensity master (do not rebuild) | ADM-R07.02 | ACL: only Admin (and permitted roles) can mutate Intensity master; Doctor is read-only consumer on Patient Board | Existing Improvement | Repertory | §7.1 | Intensity master | Manage intensity levels | Admin Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | ADM-R07.01 | — | QA | ADM-R07.01 | Intensity master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Intensity master still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | Web
49 | 73 | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.7 | ADM-R07 | Keep and harden Admin Intensity master (do not rebuild) | ADM-R07.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Intensity master; do not silently switch | Existing | Repertory | §7.1 | Intensity master | Manage intensity levels | Admin Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | ADM-R07.02 | T-48 (ADM-R07.02) | QA |  | Intensity master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Intensity master still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | Web
50 | 75 | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.8 | ADM-R08 | Keep and harden Admin Remedy master (do not rebuild) | ADM-R08.02 | ACL: only Admin (and permitted roles) can mutate Remedy master; Doctor is read-only consumer on Patient Board | Existing Improvement | Repertory | §7.1 | Remedy master | Manage the remedy library | Admin Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | ADM-R08.01 | — | QA | ADM-R08.01 | Remedy master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Remedy master still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | Web
51 | 76 | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.8 | ADM-R08 | Keep and harden Admin Remedy master (do not rebuild) | ADM-R08.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Remedy master; do not silently switch | Existing | Repertory | §7.1 | Remedy master | Manage the remedy library | Admin Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | ADM-R08.02 | T-50 (ADM-R08.02) | QA |  | Remedy master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Remedy master still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | Web
52 | 78 | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.9 | ADM-R09 | Keep and harden Admin Remedy grade master (do not rebuild) | ADM-R09.02 | ACL: only Admin (and permitted roles) can mutate Remedy grade master; Doctor is read-only consumer on Patient Board | Existing Improvement | Repertory | §7.1 | Remedy grade master | Manage remedy grading | Admin Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | ADM-R09.01 | — | QA | ADM-R09.01 | Remedy grade master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Remedy grade master still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | Web
53 | 79 | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.9 | ADM-R09 | Keep and harden Admin Remedy grade master (do not rebuild) | ADM-R09.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Remedy grade master; do not silently switch | Existing | Repertory | §7.1 | Remedy grade master | Manage remedy grading | Admin Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | ADM-R09.02 | T-52 (ADM-R09.02) | QA |  | Remedy grade master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Remedy grade master still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | Web
54 | 81 | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.10 | ADM-M01 | Keep and harden Admin Author master (do not rebuild) | ADM-M01.02 | ACL: only Admin (and permitted roles) can mutate Author master; Doctor is read-only consumer on Patient Board | Existing Improvement | Materia Medica | §7.1 | Author master | Manage materia medica authors | Admin Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | ADM-M01.01 | — | QA | ADM-M01.01 | Author master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Author master still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | Web
55 | 82 | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.10 | ADM-M01 | Keep and harden Admin Author master (do not rebuild) | ADM-M01.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Author master; do not silently switch | Existing | Materia Medica | §7.1 | Author master | Manage materia medica authors | Admin Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | ADM-M01.02 | T-54 (ADM-M01.02) | QA |  | Author master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Author master still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | Web
56 | 84 | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.11 | ADM-M02 | Keep and harden Admin Materia medica master (do not rebuild) | ADM-M02.02 | ACL: only Admin (and permitted roles) can mutate Materia medica master; Doctor is read-only consumer on Patient Board | Existing Improvement | Materia Medica | §7.1 | Materia medica master | Manage the materia medica library | Admin Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | ADM-M02.01 | — | QA | ADM-M02.01 | MM master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Materia medica master still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | Web
57 | 85 | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.11 | ADM-M02 | Keep and harden Admin Materia medica master (do not rebuild) | ADM-M02.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Materia medica master; do not silently switch | Existing | Materia Medica | §7.1 | Materia medica master | Manage the materia medica library | Admin Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | ADM-M02.02 | T-56 (ADM-M02.02) | QA |  | MM master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Materia medica master still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | Web
58 | 87 | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.12 | ADM-M03 | Keep and harden Admin Materia medica heads (do not rebuild) | ADM-M03.02 | ACL: only Admin (and permitted roles) can mutate Materia medica heads; Doctor is read-only consumer on Patient Board | Existing Improvement | Materia Medica | §7.1 | Materia medica heads | Manage chapter headings | Admin Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | ADM-M03.01 | — | QA | ADM-M03.01 | MM heads live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Materia medica heads still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | Web
59 | 88 | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.12 | ADM-M03 | Keep and harden Admin Materia medica heads (do not rebuild) | ADM-M03.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Materia medica heads; do not silently switch | Existing | Materia Medica | §7.1 | Materia medica heads | Manage chapter headings | Admin Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | ADM-M03.02 | T-58 (ADM-M03.02) | QA |  | MM heads live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Materia medica heads still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | Web
60 | 90 | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.13 | ADM-M04 | Keep and harden Admin Materia medica remedies (do not rebuild) | ADM-M04.02 | ACL: only Admin (and permitted roles) can mutate Materia medica remedies; Doctor is read-only consumer on Patient Board | Existing Improvement | Materia Medica | §7.1 | Materia medica remedies | View remedy-wise materia medica | Admin Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | ADM-M04.01 | — | QA | ADM-M04.01 | Remedy-wise MM viewer live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Materia medica remedies still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | Web
61 | 91 | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.13 | ADM-M04 | Keep and harden Admin Materia medica remedies (do not rebuild) | ADM-M04.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Materia medica remedies; do not silently switch | Existing | Materia Medica | §7.1 | Materia medica remedies | View remedy-wise materia medica | Admin Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | ADM-M04.02 | T-60 (ADM-M04.02) | QA |  | Remedy-wise MM viewer live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Materia medica remedies still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | Web
62 | 93 | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.14 | ADM-D01 | Keep and harden Admin Diagnosis system (do not rebuild) | ADM-D01.02 | ACL: only Admin (and permitted roles) can mutate Diagnosis system; Doctor is read-only consumer on Patient Board | Existing Improvement | Diagnosis | §7.1 | Diagnosis system | Manage diagnosis systems | Admin Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | ADM-D01.01 | — | QA | ADM-D01.01 | Diagnosis system CRUD live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Diagnosis system still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | Web
63 | 94 | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.14 | ADM-D01 | Keep and harden Admin Diagnosis system (do not rebuild) | ADM-D01.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Diagnosis system; do not silently switch | Existing | Diagnosis | §7.1 | Diagnosis system | Manage diagnosis systems | Admin Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | ADM-D01.02 | T-62 (ADM-D01.02) | QA |  | Diagnosis system CRUD live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Diagnosis system still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | Web
64 | 96 | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.15 | ADM-D02 | Keep and harden Admin Diagnosis therapeutics (do not rebuild) | ADM-D02.02 | ACL: only Admin (and permitted roles) can mutate Diagnosis therapeutics; Doctor is read-only consumer on Patient Board | Existing Improvement | Diagnosis | §7.1 | Diagnosis therapeutics | Manage therapeutics | Admin Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | ADM-D02.01 | — | QA | ADM-D02.01 | Therapeutics details live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Diagnosis therapeutics still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | Web
65 | 97 | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.15 | ADM-D02 | Keep and harden Admin Diagnosis therapeutics (do not rebuild) | ADM-D02.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Diagnosis therapeutics; do not silently switch | Existing | Diagnosis | §7.1 | Diagnosis therapeutics | Manage therapeutics | Admin Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | ADM-D02.02 | T-64 (ADM-D02.02) | QA |  | Therapeutics details live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Diagnosis therapeutics still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | Web
66 | 99 | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.16 | ADM-D03 | Keep and harden Admin Diagnosis conditions (do not rebuild) | ADM-D03.02 | ACL: only Admin (and permitted roles) can mutate Diagnosis conditions; Doctor is read-only consumer on Patient Board | Existing Improvement | Diagnosis | §7.1 | Diagnosis conditions | Manage conditions and linked rubrics | Admin Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | ADM-D03.01 | — | QA | ADM-D03.01 | Conditions + keyword→rubric live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Diagnosis conditions still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | Web
67 | 100 | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.16 | ADM-D03 | Keep and harden Admin Diagnosis conditions (do not rebuild) | ADM-D03.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Diagnosis conditions; do not silently switch | Existing | Diagnosis | §7.1 | Diagnosis conditions | Manage conditions and linked rubrics | Admin Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | ADM-D03.02 | T-66 (ADM-D03.02) | QA |  | Conditions + keyword→rubric live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Diagnosis conditions still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | Web
68 | 102 | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.17 | ADM-A01 | Keep and harden Admin Drug system (do not rebuild) | ADM-A01.02 | ACL: only Admin (and permitted roles) can mutate Drug system; Doctor is read-only consumer on Patient Board | Existing Improvement | Adverse Effect | §7.1 | Drug system | Manage conventional drug systems | Admin Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | ADM-A01.01 | — | QA | ADM-A01.01 | Drug system CRUD live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Drug system still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | Web
69 | 103 | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.17 | ADM-A01 | Keep and harden Admin Drug system (do not rebuild) | ADM-A01.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Drug system; do not silently switch | Existing | Adverse Effect | §7.1 | Drug system | Manage conventional drug systems | Admin Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | ADM-A01.02 | T-68 (ADM-A01.02) | QA |  | Drug system CRUD live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Drug system still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | Web
70 | 105 | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.18 | ADM-A02 | Keep and harden Admin Drug group (do not rebuild) | ADM-A02.02 | ACL: only Admin (and permitted roles) can mutate Drug group; Doctor is read-only consumer on Patient Board | Existing Improvement | Adverse Effect | §7.1 | Drug group | Manage drug groups | Admin Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | ADM-A02.01 | — | QA | ADM-A02.01 | Drug group CRUD live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Drug group still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | Web
71 | 106 | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.18 | ADM-A02 | Keep and harden Admin Drug group (do not rebuild) | ADM-A02.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Drug group; do not silently switch | Existing | Adverse Effect | §7.1 | Drug group | Manage drug groups | Admin Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | ADM-A02.02 | T-70 (ADM-A02.02) | QA |  | Drug group CRUD live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Drug group still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | Web
72 | 108 | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.19 | ADM-A03 | Keep and harden Admin Allopathic drug & side effects (do not rebuild) | ADM-A03.02 | ACL: only Admin (and permitted roles) can mutate Allopathic drug & side effects; Doctor is read-only consumer on Patient Board | Existing Improvement | Adverse Effect | §7.1 | Allopathic drug & side effects | Manage drugs with side effects and adverse reactions | Admin Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | ADM-A03.01 | — | QA | ADM-A03.01 | Allopathic drug + serious/other/adverse live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Allopathic drug & side effects still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | Web
73 | 109 | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.19 | ADM-A03 | Keep and harden Admin Allopathic drug & side effects (do not rebuild) | ADM-A03.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Allopathic drug & side effects; do not silently switch | Existing | Adverse Effect | §7.1 | Allopathic drug & side effects | Manage drugs with side effects and adverse reactions | Admin Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | ADM-A03.02 | T-72 (ADM-A03.02) | QA |  | Allopathic drug + serious/other/adverse live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Allopathic drug & side effects still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | Web
74 | 111 | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.20 | ADM-Q01 | Keep and harden Admin Question section, group & sub-group (do not rebuild) | ADM-Q01.02 | ACL: only Admin (and permitted roles) can mutate Question section, group & sub-group; Doctor is read-only consumer on Patient Board | Existing Improvement | Clinical Questions | §7.1 | Question section, group & sub-group | Manage the clinical questionnaire structure | Admin Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | ADM-Q01.01 | — | QA | ADM-Q01.01 | Existance / question group / subgroup CRUD live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Question section, group & sub-group still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | Web
75 | 112 | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.20 | ADM-Q01 | Keep and harden Admin Question section, group & sub-group (do not rebuild) | ADM-Q01.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Question section, group & sub-group; do not silently switch | Existing | Clinical Questions | §7.1 | Question section, group & sub-group | Manage the clinical questionnaire structure | Admin Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | ADM-Q01.02 | T-74 (ADM-Q01.02) | QA |  | Existance / question group / subgroup CRUD live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Question section, group & sub-group still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | Web
76 | 114 | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.21 | ADM-Q02 | Keep and harden Admin Clinical question mapping (do not rebuild) | ADM-Q02.02 | ACL: only Admin (and permitted roles) can mutate Clinical question mapping; Doctor is read-only consumer on Patient Board | Existing Improvement | Clinical Questions | §7.1 | Clinical question mapping | Map questions to body parts and rubrics | Admin Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | ADM-Q02.01 | — | QA | ADM-Q02.01 | Clinical questions mapped to body parts and rubrics live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Clinical question mapping still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | Web
77 | 115 | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.21 | ADM-Q02 | Keep and harden Admin Clinical question mapping (do not rebuild) | ADM-Q02.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Clinical question mapping; do not silently switch | Existing | Clinical Questions | §7.1 | Clinical question mapping | Map questions to body parts and rubrics | Admin Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | ADM-Q02.02 | T-76 (ADM-Q02.02) | QA |  | Clinical questions mapped to body parts and rubrics live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Clinical question mapping still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | Web
78 | 117 | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.22 | ADM-3D1 | Keep and harden Admin 3D mesh key master (do not rebuild) | ADM-3D1.02 | ACL: only Admin (and permitted roles) can mutate 3D mesh key master; Doctor is read-only consumer on Patient Board | Existing Improvement | 3D Body | §7.1 | 3D mesh key master | Manage 3D model references | Admin Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | ADM-3D1.01 | — | QA | ADM-3D1.01 | Mesh key master on .NET 8 live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | 3D mesh key master still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | Web
79 | 118 | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.22 | ADM-3D1 | Keep and harden Admin 3D mesh key master (do not rebuild) | ADM-3D1.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for 3D mesh key master; do not silently switch | Existing | 3D Body | §7.1 | 3D mesh key master | Manage 3D model references | Admin Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | ADM-3D1.02 | T-78 (ADM-3D1.02) | QA |  | Mesh key master on .NET 8 live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | 3D mesh key master still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | Web
80 | 120 | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.23 | ADM-3D2 | Keep and harden Admin 3D section master (do not rebuild) | ADM-3D2.02 | ACL: only Admin (and permitted roles) can mutate 3D section master; Doctor is read-only consumer on Patient Board | Existing Improvement | 3D Body | §7.1 | 3D section master | Manage 3D body sections | Admin Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | ADM-3D2.01 | — | QA | ADM-3D2.01 | 3D section master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | 3D section master still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | Web
81 | 121 | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.23 | ADM-3D2 | Keep and harden Admin 3D section master (do not rebuild) | ADM-3D2.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for 3D section master; do not silently switch | Existing | 3D Body | §7.1 | 3D section master | Manage 3D body sections | Admin Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | ADM-3D2.02 | T-80 (ADM-3D2.02) | QA |  | 3D section master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | 3D section master still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | Web
82 | 123 | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.24 | ADM-3D3 | Keep and harden Admin 3D hotspots (do not rebuild) | ADM-3D3.02 | ACL: only Admin (and permitted roles) can mutate 3D hotspots; Doctor is read-only consumer on Patient Board | Existing Improvement | 3D Body | §7.1 | 3D hotspots | Manage clickable points on the 3D model | Admin Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | ADM-3D3.01 | — | QA | ADM-3D3.01 | Hotspot master live; doctor viewer consumes them | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | 3D hotspots still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | Web
83 | 124 | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.24 | ADM-3D3 | Keep and harden Admin 3D hotspots (do not rebuild) | ADM-3D3.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for 3D hotspots; do not silently switch | Existing | 3D Body | §7.1 | 3D hotspots | Manage clickable points on the 3D model | Admin Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | ADM-3D3.02 | T-82 (ADM-3D3.02) | QA |  | Hotspot master live; doctor viewer consumes them | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | 3D hotspots still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | Web
84 | 126 | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.25 | ADM-B01 | Business Management — Doctor qualifications (existing, used later by credentialing) | ADM-B01.02 | ACL on qualification APIs | Existing Improvement | Business Management | §7.2 | Doctor qualifications | Manage the qualification list | Admin Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | ADM-B01.01 | — | QA | ADM-B01.01 | Qualifications CRUD on newer API live; used by RegisterDoctor | Keep; credentialing Phase 8 will reference QualificationId | Qualification list still drives doctor registration | Not Started | Web
85 | 127 | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.25 | ADM-B01 | Business Management — Doctor qualifications (existing, used later by credentialing) | ADM-B01.03 | Confirm UI uses newer API (not classic) for qualifications | Existing | Business Management | §7.2 | Doctor qualifications | Manage the qualification list | Admin Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | ADM-B01.02 | T-84 (ADM-B01.02) | QA |  | Qualifications CRUD on newer API live; used by RegisterDoctor | Keep; credentialing Phase 8 will reference QualificationId | Qualification list still drives doctor registration | Not Started | Web
86 | 129 | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.26 | ADM-B02 | Business Management — Lab & imaging test catalog (existing, used by eRx lab orders) | ADM-B02.02 | ACL on catalog mutate | Existing Improvement | Business Management | §7.2 | Lab & imaging test catalog | Manage the test catalogue | Admin Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | ADM-B02.01 | — | QA | ADM-B02.01 | Labs & imaging CRUD live; Patient Board orders from this catalogue | Keep; eRx Phase 10 continues to use the same catalogue | Doctor can still order a lab from the catalogue | Not Started | Web
87 | 130 | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.26 | ADM-B02 | Business Management — Lab & imaging test catalog (existing, used by eRx lab orders) | ADM-B02.03 | Confirm classic PatientLab APIs still read this catalogue | Existing | Business Management | §7.2 | Lab & imaging test catalog | Manage the test catalogue | Admin Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | ADM-B02.02 | T-86 (ADM-B02.02) | QA |  | Labs & imaging CRUD live; Patient Board orders from this catalogue | Keep; eRx Phase 10 continues to use the same catalogue | Doctor can still order a lab from the catalogue | Not Started | Web
88 | 132 | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.27 | ADM-B03 | Business Management — Subscription packages (existing S1 SaaS; later tied to Account ledger) | ADM-B03.02 | ACL on package mutate | Existing Improvement | Business Management | §7.2 | Subscription packages | Manage doctor subscription plans | Admin Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | ADM-B03.01 | — | QA | ADM-B03.01 | Package CRUD live; Razorpay buy/renew partial (no webhook) | Do not overload PackageEntryDetail for consult/medicine money; Phase 6 ports payment verification | Admin can still create/edit packages; doctor still sees plan flags | Not Started | Web
89 | 133 | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.27 | ADM-B03 | Business Management — Subscription packages (existing S1 SaaS; later tied to Account ledger) | ADM-B03.03 | Note in code: PackageEntryDetail is S1 only — never reuse for S2 consult or S5 medicine | Existing | Business Management | §7.2 | Subscription packages | Manage doctor subscription plans | Admin Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | ADM-B03.02 | T-88 (ADM-B03.02) | QA |  | Package CRUD live; Razorpay buy/renew partial (no webhook) | Do not overload PackageEntryDetail for consult/medicine money; Phase 6 ports payment verification | Admin can still create/edit packages; doctor still sees plan flags | Not Started | Web
90 | 134 | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.28 | ADM-B04 | Business Management — Roles & menu permissions (existing DB, runtime ACL leftover) | ADM-B04.01 | No schema change unless Account/Pharmacy/Patient roles need new MenuMaster rows — seed those menus | Existing Improvement | Business Management | §7.2 | Roles & menu permissions | Control exactly what each role can access | Admin Portal | Database | No | Yes | Yes | No | No | No | P1 | S | — | — | UI, QA |  | Role CRUD screens live; runtime GetMenuByRole commented; no frontend route ACL | This is the product surface for SEC-04; complete wiring here | Changing a role’s menu immediately hides those routes after refresh | Not Started | Web
91 | 135 | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.28 | ADM-B04 | Business Management — Roles & menu permissions (existing DB, runtime ACL leftover) | ADM-B04.02 | Restore GetMenuByRole on .NET 8; seed menus for Account and (later) Pharmacy | Existing Improvement | Business Management | §7.2 | Roles & menu permissions | Control exactly what each role can access | Admin Portal | API | No | Yes | Yes | Yes | No | No | P1 | M | ADM-B04.01 | T-90 (ADM-B04.01) | UI, QA |  | Role CRUD screens live; runtime GetMenuByRole commented; no frontend route ACL | This is the product surface for SEC-04; complete wiring here | Changing a role’s menu immediately hides those routes after refresh | Not Started | Web
92 | 139 | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.1 | CLN-01 | Clinical workspace — single screen for the entire consultation | CLN-01.02 | Do not split the board into multiple apps; mobile doctor app will NOT get case-taking (PDF §3) | Existing | Patient Board | §5.3 | Clinical workspace | Single screen for the entire consultation | Doctor Web Portal | Architecture | No | No | No | No | No | No | P1 | S | CLN-01.01 | — | UI, QA | CLN-01.01 | PatientBoard.js (~13.5k) is the workspace; ~90% — missing payment/tele/eRx header status | Keep one screen; add header chips for payment, tele session, signed eRx (chips light up as later phases land) | Doctor still opens one board per patient; new chips do not break tabs | Not Started | Web
93 | 142 | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.2 | CLN-02 | Manual case taking — structured case taking (keep) | CLN-02.02 | ACL: only treating doctor (not Reception) can run full case taking | Existing Improvement | Patient Board | §5.3 | Manual case taking | Structured case taking | Doctor Web Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | CLN-02.01 | — | QA | CLN-02.01 | Classic case-taking tabs live | Regression only; do not rebuild | Manual case taking still saves/restores | Not Started | Web
94 | 143 | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.2 | CLN-02 | Manual case taking — structured case taking (keep) | CLN-02.03 | Confirm clipboard/repertorization APIs still on the correct host | Existing | Patient Board | §5.3 | Manual case taking | Structured case taking | Doctor Web Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | CLN-02.02 | T-93 (CLN-02.02) | QA |  | Classic case-taking tabs live | Regression only; do not rebuild | Manual case taking still saves/restores | Not Started | Web
95 | 145 | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.3 | CLN-03 | Body parts & intensity selection (keep) | CLN-03.02 | ACL: doctor-only | Existing Improvement | Patient Board | §5.3 | Body parts & intensity selection | Select affected areas and severity | Doctor Web Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | CLN-03.01 | — | QA | CLN-03.01 | Body Parts tab + intensity chips live | Regression; intensity master from Phase 1 still drives chips | Selecting a body part + intensity still adds rubrics | Not Started | Web
96 | 146 | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.3 | CLN-03 | Body parts & intensity selection (keep) | CLN-03.03 | API host unchanged | Existing | Patient Board | §5.3 | Body parts & intensity selection | Select affected areas and severity | Doctor Web Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | CLN-03.02 | T-95 (CLN-03.02) | QA |  | Body Parts tab + intensity chips live | Regression; intensity master from Phase 1 still drives chips | Selecting a body part + intensity still adds rubrics | Not Started | Web
97 | 148 | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.4 | CLN-04 | Clinical questions — guided questions by section, group and sub-group (keep) | CLN-04.02 | ACL doctor-only | Existing Improvement | Patient Board | §5.3 | Clinical questions | Guided questions by section, group and sub-group | Doctor Web Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | CLN-04.01 | — | QA | CLN-04.01 | Questions tab loads Existance taxonomy live | Regression | Section → group → subgroup → keywords → rubrics still works | Not Started | Web
98 | 149 | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.4 | CLN-04 | Clinical questions — guided questions by section, group and sub-group (keep) | CLN-04.03 | API host unchanged | Existing | Patient Board | §5.3 | Clinical questions | Guided questions by section, group and sub-group | Doctor Web Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | CLN-04.02 | T-97 (CLN-04.02) | QA |  | Questions tab loads Existance taxonomy live | Regression | Section → group → subgroup → keywords → rubrics still works | Not Started | Web
99 | 151 | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.5 | CLN-05 | Diagnosis, therapeutics & pattern search (keep) | CLN-05.02 | ACL doctor-only | Existing Improvement | Patient Board | §5.3 | Diagnosis, therapeutics & pattern search | Search diagnoses and linked therapeutics | Doctor Web Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | CLN-05.01 | — | QA | CLN-05.01 | Clinical Pattern tab live (13 keyword tabs + therapeutics) | Regression | Diagnosis search still returns linked rubrics and therapeutics | Not Started | Web
100 | 152 | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.5 | CLN-05 | Diagnosis, therapeutics & pattern search (keep) | CLN-05.03 | API host unchanged | Existing | Patient Board | §5.3 | Diagnosis, therapeutics & pattern search | Search diagnoses and linked therapeutics | Doctor Web Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | CLN-05.02 | T-99 (CLN-05.02) | QA |  | Clinical Pattern tab live (13 keyword tabs + therapeutics) | Regression | Diagnosis search still returns linked rubrics and therapeutics | Not Started | Web
101 | 154 | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.6 | CLN-06 | Repertory rubric search & selection (keep) | CLN-06.02 | ACL doctor-only | Existing Improvement | Patient Board | §5.3 | Repertory rubric search & selection | Search and select from the full repertory | Doctor Web Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | CLN-06.01 | — | QA | CLN-06.01 | Repertory tree + search live | Regression; small UX polish allowed but not a rewrite | Search still adds to clipboard | Not Started | Web
102 | 155 | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.6 | CLN-06 | Repertory rubric search & selection (keep) | CLN-06.03 | Confirm subsection search host (newer vs classic) documented | Existing | Patient Board | §5.3 | Repertory rubric search & selection | Search and select from the full repertory | Doctor Web Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | CLN-06.02 | T-101 (CLN-06.02) | QA |  | Repertory tree + search live | Regression; small UX polish allowed but not a rewrite | Search still adds to clipboard | Not Started | Web
103 | 156 | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.7 | CLN-07 | Manage selected rubrics — review, edit and remove (remaining ~10%) | CLN-07.01 | No new table — clipboard already persisted via board backup / repertorization payload | Existing Improvement | Patient Board | §5.3 | Manage selected rubrics | Review, edit and remove selected rubrics | Doctor Web Portal | Database | No | Yes | Yes | No | No | No | P1 | S | — | — | UI, QA |  | Clipboard exists; confirm-delete / intensity-edit incomplete | Confirm delete; edit intensity on selected rubric; no accidental wipe | Doctor can remove one rubric without losing the rest | Not Started | Web
104 | 157 | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.7 | CLN-07 | Manage selected rubrics — review, edit and remove (remaining ~10%) | CLN-07.02 | If intensity-on-clipboard is client-only, persist it on backup payload | Existing Improvement | Patient Board | §5.3 | Manage selected rubrics | Review, edit and remove selected rubrics | Doctor Web Portal | API | No | Yes | Yes | Yes | No | No | P1 | M | CLN-07.01 | T-103 (CLN-07.01) | UI, QA |  | Clipboard exists; confirm-delete / intensity-edit incomplete | Confirm delete; edit intensity on selected rubric; no accidental wipe | Doctor can remove one rubric without losing the rest | Not Started | Web
105 | 161 | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.8 | CLN-08 | Audio case taking — record and receive suggested rubrics (keep engine; do not rebuild) | CLN-08.02 | Consent: audio consent continues to write AudioCaseConsentLog (later also ConsentRecord) | Existing Improvement | Audio AI | §5.3 | Audio case taking | Record the consultation and receive suggested rubrics automatically | Doctor Web Portal | Security | Yes | Yes | No | Yes | No | No | P1 | S | CLN-08.01 | — | QA | CLN-08.01 | Whisper + rubric engines + CaseTaking UI live on .NET 8 | Keep; follow existing AUDIO_CASE_TAKING_* docs; accuracy is the next task | Record/upload still produces suggested rubrics for approve/reject | Not Started | Web
106 | 162 | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.8 | CLN-08 | Audio case taking — record and receive suggested rubrics (keep engine; do not rebuild) | CLN-08.03 | Confirm audio queue/worker still healthy | Existing | Audio AI | §5.3 | Audio case taking | Record the consultation and receive suggested rubrics automatically | Doctor Web Portal | API hygiene | No | Yes | No | Yes | No | No | P1 | S | CLN-08.02 | T-105 (CLN-08.02) | QA |  | Whisper + rubric engines + CaseTaking UI live on .NET 8 | Keep; follow existing AUDIO_CASE_TAKING_* docs; accuracy is the next task | Record/upload still produces suggested rubrics for approve/reject | Not Started | Web
107 | 163 | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.9 | CLN-09 | Improved rubric accuracy — enhanced accuracy rules for audio-based rubric suggestions | CLN-09.01 | Follow AUDIO_CASE_TAKING_* docs: accuracy rules, aliases, metaphors, benchmark | Existing Improvement | Audio AI | §5.3 | Improved rubric accuracy | Enhanced accuracy rules for audio-based rubric suggestions | Doctor Web Portal + Admin intelligence | Backend | No | Yes | No | No | No | No | P1 | L | — | — | UI, QA |  | Engine + admin metaphors/aliases exist; accuracy rules still in progress (~50%) | Complete accuracy rules per AUDIO_CASE_TAKING_AI_ENGINE docs; metaphor/alias QA | Benchmark set meets agreed accuracy gate before calling this done | Not Started | Web
108 | 166 | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.10 | CLN-10 | Materia medica reference during consultation (remaining ~10%) | CLN-10.01 | No schema change | Existing Improvement | Patient Board | §5.3 | Materia medica reference | Browse materia medica during the consultation | Doctor Web Portal | Database | No | Yes | Yes | No | No | No | P2 | S | — | — | UI, QA |  | MM tab + repertorize differential accordion ~90% | Faster head navigation during case; do not rebuild MM masters | Doctor can open a remedy MM without leaving the board | Not Started | Web
109 | 167 | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.10 | CLN-10 | Materia medica reference during consultation (remaining ~10%) | CLN-10.02 | Existing MM APIs — add a lightweight get-by-remedy if chatty | Existing Improvement | Patient Board | §5.3 | Materia medica reference | Browse materia medica during the consultation | Doctor Web Portal | API | No | Yes | Yes | Yes | No | No | P2 | M | CLN-10.01 | T-108 (CLN-10.01) | UI, QA |  | MM tab + repertorize differential accordion ~90% | Faster head navigation during case; do not rebuild MM masters | Doctor can open a remedy MM without leaving the board | Not Started | Web
110 | 171 | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.11 | CLN-11 | Allopathic drug side-effect lookup (keep) | CLN-11.02 | ACL doctor-only | Existing Improvement | Patient Board | §5.3 | Allopathic drug side-effect lookup | Check side effects of conventional medicines | Doctor Web Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | CLN-11.01 | — | QA | CLN-11.01 | Adverse Effect tab live | Regression | Lookup still shows serious/other/adverse | Not Started | Web
111 | 172 | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.11 | CLN-11 | Allopathic drug side-effect lookup (keep) | CLN-11.03 | API host unchanged | Existing | Patient Board | §5.3 | Allopathic drug side-effect lookup | Check side effects of conventional medicines | Doctor Web Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | CLN-11.02 | T-110 (CLN-11.02) | QA |  | Adverse Effect tab live | Regression | Lookup still shows serious/other/adverse | Not Started | Web
112 | 173 | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.12 | CLN-12 | Repertorization & elimination (remaining ~10%) | CLN-12.01 | No schema change | Existing Improvement | Patient Board | §5.3 | Repertorization & elimination | Full repertorization with elimination | Doctor Web Portal | Database | No | Yes | Yes | No | No | No | P1 | S | — | — | UI, QA |  | Common/uncommon/elimination live ~90% | Stability polish; Center of Gravity is a NEW panel on the same rubrics (next task) | Elimination still ranks remedies from selected rubrics | Not Started | Web
113 | 174 | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.12 | CLN-12 | Repertorization & elimination (remaining ~10%) | CLN-12.02 | Keep existing repertorization APIs; fix any known scoring edge cases | Existing Improvement | Patient Board | §5.3 | Repertorization & elimination | Full repertorization with elimination | Doctor Web Portal | API | No | Yes | Yes | Yes | No | No | P1 | M | CLN-12.01 | T-112 (CLN-12.01) | UI, QA |  | Common/uncommon/elimination live ~90% | Stability polish; Center of Gravity is a NEW panel on the same rubrics (next task) | Elimination still ranks remedies from selected rubrics | Not Started | Web
114 | 177 | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.13 | CLN-13 | Center of Gravity — new analysis identifying the central remedy of the case, with reasoning shown | CLN-13.01 | No mandatory new table (algorithm on selected rubrics); optional CogRun log for support | New | Repertorization | §5.3 | Center of Gravity | New analysis identifying the central remedy of the case, with reasoning shown | Doctor Web Portal | Database | No | Yes | Yes | No | No | No | P1 | S | — | — | UI, QA |  | Does not exist | POST /api/Repertorization/CenterOfGravity from selected rubric ids + intensities; UI panel with explainability | COG returns ranked central remedies plus contribution reasons the doctor can read | Not Started | Web
115 | 178 | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.13 | CLN-13 | Center of Gravity — new analysis identifying the central remedy of the case, with reasoning shown | CLN-13.02 | POST /api/Repertorization/CenterOfGravity — input rubric ids + intensities; output ranked remedies + reasons | New | Repertorization | §5.3 | Center of Gravity | New analysis identifying the central remedy of the case, with reasoning shown | Doctor Web Portal | API | No | Yes | Yes | Yes | No | No | P1 | M | CLN-13.01 | T-114 (CLN-13.01) | UI, QA |  | Does not exist | POST /api/Repertorization/CenterOfGravity from selected rubric ids + intensities; UI panel with explainability | COG returns ranked central remedies plus contribution reasons the doctor can read | Not Started | Web
116 | 182 | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.14 | CLN-14 | Lab orders & lab entries (keep; later also sit on eRx) | CLN-14.02 | ACL doctor-only | Existing Improvement | Patient Board | §5.3 + §11 | Lab orders & lab entries | Order tests and record results / Tests ordered alongside the prescription | Doctor Web Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | CLN-14.01 | — | QA | CLN-14.01 | Lab order + result entry on prescription modal live | Keep; when eRx splits notes from Rx, labs stay on the prescription/eRx side | Order + result still save against the appointment | Not Started | Web
117 | 183 | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.14 | CLN-14 | Lab orders & lab entries (keep; later also sit on eRx) | CLN-14.03 | API: classic PatientLab still authoritative until ported | Existing | Patient Board | §5.3 + §11 | Lab orders & lab entries | Order tests and record results / Tests ordered alongside the prescription | Doctor Web Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | CLN-14.02 | T-116 (CLN-14.02) | QA |  | Lab order + result entry on prescription modal live | Keep; when eRx splits notes from Rx, labs stay on the prescription/eRx side | Order + result still save against the appointment | Not Started | Web
118 | 185 | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.15 | CLN-15 | Appointment history notes (keep; split from eRx in Phase 10) | CLN-15.02 | ACL doctor-only | Existing Improvement | Patient Board | §5.3 | Appointment history notes | Notes recorded against each visit | Doctor Web Portal | Security | Yes | Yes | No | Yes | No | No | P1 | S | CLN-15.01 | — | QA | CLN-15.01 | AppointmentHistoryNote APIs live (classic); currently mixed into Rx modal tabs | Keep save/get; Phase 10 moves UX outside Rx modal and adds NoteType / IsErxExcluded | Notes still save against PatientAppId | Not Started | Web
119 | 186 | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.15 | CLN-15 | Appointment history notes (keep; split from eRx in Phase 10) | CLN-15.03 | Do not dual-write; classic notes stay until Phase 10 extends them | Existing | Patient Board | §5.3 | Appointment history notes | Notes recorded against each visit | Doctor Web Portal | API hygiene | No | Yes | No | Yes | No | No | P1 | S | CLN-15.02 | T-118 (CLN-15.02) | QA |  | AppointmentHistoryNote APIs live (classic); currently mixed into Rx modal tabs | Keep save/get; Phase 10 moves UX outside Rx modal and adds NoteType / IsErxExcluded | Notes still save against PatientAppId | Not Started | Web
120 | 187 | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.16 | CLN-16 | Complaints & case details — wire Patient Board to existing SaveComplaints / SaveCaseDetails (~20% today) | CLN-16.01 | Use existing tables — no new schema unless fields are missing vs PDF | Existing Improvement | Patient Board | §5.3 | Complaints & case details | Capture and store complaints and case details | Doctor Web Portal | Database | No | Yes | Yes | No | No | No | P1 | S | — | — | UI, QA |  | Classic SaveComplaints / SaveCaseDetails APIs exist; Patient Board does not call them | Call the existing APIs from the board; Reception case-paper (Phase 5) uses a subset | Complaints and case details persist and reload on the board | Not Started | Web
121 | 188 | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.16 | CLN-16 | Complaints & case details — wire Patient Board to existing SaveComplaints / SaveCaseDetails (~20% today) | CLN-16.02 | Keep classic SaveComplaints / SaveCaseDetails; add GET if missing | Existing Improvement | Patient Board | §5.3 | Complaints & case details | Capture and store complaints and case details | Doctor Web Portal | API | No | Yes | Yes | Yes | No | No | P1 | M | CLN-16.01 | T-120 (CLN-16.01) | UI, QA |  | Classic SaveComplaints / SaveCaseDetails APIs exist; Patient Board does not call them | Call the existing APIs from the board; Reception case-paper (Phase 5) uses a subset | Complaints and case details persist and reload on the board | Not Started | Web
122 | 191 | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.17 | CLN-17 | Patient back history — complete history of visits, notes, prescriptions and payments | CLN-17.01 | No new table — compose from Appointment + notes + Rx + (later) ConsultPayment | Existing Improvement | Patient Board | §5.3 | Patient back history | Complete history of visits, notes, prescriptions and payments | Doctor Web Portal | Database | No | Yes | Yes | No | No | No | P1 | S | — | — | UI, QA |  | History panel ~70%; no payment line (payments do not exist yet) | Timeline: visits, notes, eRx, labs; payment row added when Phase 6 lands (placeholder now) | Doctor sees chronological visits with notes and Rx; payment appears after Phase 6 | Not Started | Web
123 | 192 | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.17 | CLN-17 | Patient back history — complete history of visits, notes, prescriptions and payments | CLN-17.02 | GET patient timeline DTO including payment status when column exists | Existing Improvement | Patient Board | §5.3 | Patient back history | Complete history of visits, notes, prescriptions and payments | Doctor Web Portal | API | No | Yes | Yes | Yes | No | No | P1 | M | CLN-17.01 | T-122 (CLN-17.01) | UI, QA |  | History panel ~70%; no payment line (payments do not exist yet) | Timeline: visits, notes, eRx, labs; payment row added when Phase 6 lands (placeholder now) | Doctor sees chronological visits with notes and Rx; payment appears after Phase 6 | Not Started | Web
124 | 195 | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.18 | CLN-18 | Export case data — download the full case in Excel or PDF | CLN-18.01 | Reuse ExportCasesToExcel; add PDF generation of the clinical case (doctor copy, includes notes) | Existing Improvement | Patient Board | §5.3 | Export case data | Download the full case in Excel or PDF | Doctor Web Portal | API | No | Yes | No | Yes | No | No | P1 | M | — | — | UI, QA |  | Newer ExportCasesToExcel exists; no Patient Board export UI; no PDF | Toolbar Excel + PDF using existing Excel API + new PDF renderer; exclude private notes from patient-facing PDF (eRx print is Phase 10) | Doctor downloads Excel and PDF of the case they own | Not Started | Web
125 | 199 | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.19 | CLN-19 | Session restore — continue exactly where the doctor left off, across multiple patients (keep) | CLN-19.02 | ACL: backup scoped to DoctorId | Existing Improvement | Patient Board | §5.3 | Session restore | Continue exactly where the doctor left off, across multiple patients | Doctor Web Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | CLN-19.01 | — | QA | CLN-19.01 | Up to 5 in-memory sessions + DoctorPatientBoardBackup live | Regression; header stack remains | Kill browser, login, restore last work | Not Started | Web
126 | 200 | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.19 | CLN-19 | Session restore — continue exactly where the doctor left off, across multiple patients (keep) | CLN-19.03 | API: PatientBoardBackup on .NET 8 unchanged | Existing | Patient Board | §5.3 | Session restore | Continue exactly where the doctor left off, across multiple patients | Doctor Web Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | CLN-19.02 | T-125 (CLN-19.02) | QA |  | Up to 5 in-memory sessions + DoctorPatientBoardBackup live | Regression; header stack remains | Kill browser, login, restore last work | Not Started | Web
127 | 201 | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.20 | CLN-20 | 3D anatomy viewer — interactive 3D body model linked to rubric search (remaining ~50%) | CLN-20.01 | No new tables — Mesh/Section/Hotspot masters already exist | Existing Improvement | Anatomy | §5.3 | 3D anatomy viewer | Interactive 3D body model linked to rubric search | Doctor Web Portal | Database | No | Yes | Yes | No | No | No | P2 | S | — | — | UI, QA |  | three.js viewer + hotspot→search live; incomplete mesh coverage / UX | Complete GLB/hotspot coverage; mobile fallback later; admin 3D masters already in Phase 1 | Every admin hotspot on the shipped models opens the correct rubric search | Not Started | Web
128 | 202 | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.20 | CLN-20 | 3D anatomy viewer — interactive 3D body model linked to rubric search (remaining ~50%) | CLN-20.02 | Fix hotspot mapping gaps on newer threeDBodyPart APIs | Existing Improvement | Anatomy | §5.3 | 3D anatomy viewer | Interactive 3D body model linked to rubric search | Doctor Web Portal | API | No | Yes | Yes | Yes | No | No | P2 | M | CLN-20.01 | T-127 (CLN-20.01) | UI, QA |  | three.js viewer + hotspot→search live; incomplete mesh coverage / UX | Complete GLB/hotspot coverage; mobile fallback later; admin 3D masters already in Phase 1 | Every admin hotspot on the shipped models opens the correct rubric search | Not Started | Web
129 | 205 | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.1 | DOC-01 | Doctor home dashboard — complete overview of the working day (remaining ~30%) | DOC-01.01 | No new dashboard table | Existing Improvement | Doctor Dashboard | §5.1 | Doctor home dashboard | Complete overview of the working day | Doctor Web Portal | Database | No | Yes | Yes | No | No | No | P1 | S | — | — | UI, QA |  | Widgets + BestSellingProducts ~70%; missing online toggle, tele queue, payment badges, follow-up due | Extend, do not replace; later phases light up tele/payment chips | Doctor sees today’s buckets plus placeholders for tele/payment that become live in Phases 6 and 11 | Not Started | Web
130 | 206 | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.1 | DOC-01 | Doctor home dashboard — complete overview of the working day (remaining ~30%) | DOC-01.02 | Extend dashboard DTOs with paymentStatus / tele flags when columns exist (nullable until Phase 6/11) | Existing Improvement | Doctor Dashboard | §5.1 | Doctor home dashboard | Complete overview of the working day | Doctor Web Portal | API | No | Yes | Yes | Yes | No | No | P1 | M | DOC-01.01 | T-129 (DOC-01.01) | UI, QA |  | Widgets + BestSellingProducts ~70%; missing online toggle, tele queue, payment badges, follow-up due | Extend, do not replace; later phases light up tele/payment chips | Doctor sees today’s buckets plus placeholders for tele/payment that become live in Phases 6 and 11 | Not Started | Web
131 | 210 | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.2 | DOC-02 | Patient counts & waiting list — live counts by status with quick actions (keep; extend paid/unpaid) | DOC-02.02 | Reception sharing this view is OK until Phase 5 splits chrome | Existing Improvement | Doctor Dashboard | §5.1 | Patient counts & waiting list | Live counts by status with quick actions | Doctor Web Portal | Security | Yes | Yes | No | Yes | No | No | P1 | S | DOC-02.01 | — | QA | DOC-02.01 | Status buckets WAITING, WALK-IN, NOT ARRIVED, E-CONSULT, REMAINING, COMPLETED live | Keep; add CANCELLED in Phase 4; paid/unpaid badge in Phase 6 | Counts still match appointment list | Not Started | Web
132 | 211 | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.2 | DOC-02 | Patient counts & waiting list — live counts by status with quick actions (keep; extend paid/unpaid) | DOC-02.03 | API: existing dashboard count endpoints | Existing | Doctor Dashboard | §5.1 | Patient counts & waiting list | Live counts by status with quick actions | Doctor Web Portal | API hygiene | No | Yes | No | Yes | No | No | P1 | S | DOC-02.02 | T-131 (DOC-02.02) | QA |  | Status buckets WAITING, WALK-IN, NOT ARRIVED, E-CONSULT, REMAINING, COMPLETED live | Keep; add CANCELLED in Phase 4; paid/unpaid badge in Phase 6 | Counts still match appointment list | Not Started | Web
133 | 212 | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.3 | DOC-03 | Patient search, list & open case (remaining ~10%) | DOC-03.01 | Use existing Patient + Appointment — add DTO fields | Existing Improvement | Doctor Dashboard | §5.1 | Patient search, list & open case | Find any patient and open their case instantly | Doctor Web Portal | Database | No | Yes | Yes | No | No | No | P1 | S | — | — | UI, QA |  | Search/list/open ~90%; missing last visit, unpaid, family filters | Add last-visit column; unpaid/family after those modules exist | Search still opens Patient Board; last visit visible | Not Started | Web
134 | 213 | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.3 | DOC-03 | Patient search, list & open case (remaining ~10%) | DOC-03.02 | Search DTO includes lastVisitAt | Existing Improvement | Doctor Dashboard | §5.1 | Patient search, list & open case | Find any patient and open their case instantly | Doctor Web Portal | API | No | Yes | Yes | Yes | No | No | P1 | M | DOC-03.01 | T-133 (DOC-03.01) | UI, QA |  | Search/list/open ~90%; missing last visit, unpaid, family filters | Add last-visit column; unpaid/family after those modules exist | Search still opens Patient Board; last visit visible | Not Started | Web
135 | 217 | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.4 | DOC-04 | Add new patient — register a patient in seconds (keep) | DOC-04.02 | ACL: doctor/reception of that clinic only | Existing Improvement | Patients | §5.1 | Add new patient | Register a patient in seconds | Doctor Web Portal | Security | Yes | Yes | No | Yes | No | No | P1 | S | DOC-04.01 | — | QA | DOC-04.01 | Create patient live | Regression; public self-registration is a different Patient identity in Phase 9 | Doctor can still create a clinic patient | Not Started | Web
136 | 218 | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.4 | DOC-04 | Add new patient — register a patient in seconds (keep) | DOC-04.03 | API unchanged | Existing | Patients | §5.1 | Add new patient | Register a patient in seconds | Doctor Web Portal | API hygiene | No | Yes | No | Yes | No | No | P1 | S | DOC-04.02 | T-135 (DOC-04.02) | QA |  | Create patient live | Regression; public self-registration is a different Patient identity in Phase 9 | Doctor can still create a clinic patient | Not Started | Web
137 | 220 | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.5 | DOC-05 | Import patients — bring existing patient records in bulk (keep) | DOC-05.02 | ACL doctor-only (or reception if already allowed) | Existing Improvement | Patients | §5.1 | Import patients | Bring existing patient records in bulk | Doctor Web Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | DOC-05.01 | — | QA | DOC-05.01 | Import live | Regression | Import still creates patients for this doctor | Not Started | Web
138 | 221 | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.5 | DOC-05 | Import patients — bring existing patient records in bulk (keep) | DOC-05.03 | API unchanged | Existing | Patients | §5.1 | Import patients | Bring existing patient records in bulk | Doctor Web Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | DOC-05.02 | T-137 (DOC-05.02) | QA |  | Import live | Regression | Import still creates patients for this doctor | Not Started | Web
139 | 222 | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.6 | DOC-06 | Export patients — download patient data in Excel, CSV or PDF (keep) | DOC-06.01 | Audit current export formats; add PDF if only Excel/CSV exist today | Existing Improvement | Patients | §5.1 | Export patients | Download patient data in Excel, CSV or PDF | Doctor Web Portal | API | No | Yes | No | Yes | No | No | P2 | S | — | — | UI, QA |  | Export live (confirm PDF vs Excel/CSV in QA) | If PDF is missing, add it as Existing Improvement; do not skip the PDF wording in the PDF | Excel, CSV and PDF each download this doctor’s patients only | Not Started | Web
140 | 226 | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.7 | DOC-07 | Recent activity panel (keep) | DOC-07.02 | ACL scoped to doctor | Existing Improvement | Doctor Dashboard | §5.1 | Recent activity panel | Everything that happened recently, at a glance | Doctor Web Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | DOC-07.01 | — | QA | DOC-07.01 | Recent activity live | Regression; later include payment/tele events when those exist | Panel still lists recent actions | Not Started | Web
141 | 227 | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.7 | DOC-07 | Recent activity panel (keep) | DOC-07.03 | API unchanged | Existing | Doctor Dashboard | §5.1 | Recent activity panel | Everything that happened recently, at a glance | Doctor Web Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | DOC-07.02 | T-140 (DOC-07.02) | QA |  | Recent activity live | Regression; later include payment/tele events when those exist | Panel still lists recent actions | Not Started | Web
142 | 229 | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.8 | DOC-08 | Patient statistics charts (keep; foundation for clinic performance in Phase 18) | DOC-08.02 | ACL doctor-only | Existing Improvement | Doctor Dashboard | §5.1 | Patient statistics charts | Visual practice statistics | Doctor Web Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | DOC-08.01 | — | QA | DOC-08.01 | GetPatientStats / GetPatientStatsCharts + ApexCharts live | Keep; clinic performance report extends this in Phase 18 | Charts still render for the doctor | Not Started | Web
143 | 230 | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.8 | DOC-08 | Patient statistics charts (keep; foundation for clinic performance in Phase 18) | DOC-08.03 | API unchanged | Existing | Doctor Dashboard | §5.1 | Patient statistics charts | Visual practice statistics | Doctor Web Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | DOC-08.02 | T-142 (DOC-08.02) | QA |  | GetPatientStats / GetPatientStatsCharts + ApexCharts live | Keep; clinic performance report extends this in Phase 18 | Charts still render for the doctor | Not Started | Web
144 | 231 | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.9 | DOC-09 | Manage reception staff — add, edit and remove reception users (backend done, UI absent) | DOC-09.01 | No new API — authorise that the doctor owns the staff record on existing CRUD | Existing Improvement | Staff | §5.1 | Manage reception staff | Add, edit and remove reception users | Doctor Web Portal | API | No | Yes | No | Yes | No | No | P1 | S | — | — | UI, QA |  | .NET 8 api/ReceptionStaff CRUD exists; no SPA page | List/add/edit/disable at /doctor/reception-staff; doctor owns the staff record | Doctor can create a reception user who logs in to that DoctorId | Not Started | Web
145 | 234 | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.10 | DOC-10 | Doctor profile — clinic details, consultation fee, photo, qualifications, working hours, bank details | DOC-10.01 | Extend Doctor / add DoctorPayeeKyc fields (bank, PAN) used later by Account; ConsultFeeConfig may wait until Phase 6 — store fee on profile now if simpler | Existing Improvement | Doctor Profile | §5.1 | Doctor profile | Clinic details, consultation fee, photo, qualifications, working hours, bank details | Doctor Web Portal | Database | No | Yes | Yes | No | No | No | P0 | S | — | — | UI, QA |  | /profile is Velzon first_name only (~20%); credentials sit on Doctor entity; no fee/KYC UI | Real doctor profile: clinic, photo, qualifications, consult fee (feeds Phase 6), hours (feeds schedule), bank KYC (feeds Account payees) | Doctor can save clinic, photo, qualifications, fee, hours, bank details; verification status visible | Not Started | Web
146 | 235 | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.10 | DOC-10 | Doctor profile — clinic details, consultation fee, photo, qualifications, working hours, bank details | DOC-10.02 | GET/PUT /api/Profile/Me (doctor DTO); POST photo multipart; do not allow role escalation | Existing Improvement | Doctor Profile | §5.1 | Doctor profile | Clinic details, consultation fee, photo, qualifications, working hours, bank details | Doctor Web Portal | API | No | Yes | Yes | Yes | No | No | P0 | M | DOC-10.01 | T-145 (DOC-10.01) | UI, QA |  | /profile is Velzon first_name only (~20%); credentials sit on Doctor entity; no fee/KYC UI | Real doctor profile: clinic, photo, qualifications, consult fee (feeds Phase 6), hours (feeds schedule), bank KYC (feeds Account payees) | Doctor can save clinic, photo, qualifications, fee, hours, bank details; verification status visible | Not Started | Web
147 | 239 | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.1 | APT-01 | Appointment list & waiting patients — full day view with live status (keep; later payment/tele) | APT-01.02 | ACL doctor/reception of that DoctorId | Existing Improvement | Appointments | §5.2 | Appointment list & waiting patients | Full day view with live status | Doctor Web Portal | Security | Yes | Yes | No | Yes | No | No | P1 | S | APT-01.01 | — | QA | APT-01.01 | Day list + status live | Keep; reschedule/cancel/payment attach to this list | Day view still lists today’s appointments | Not Started | Web
148 | 240 | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.1 | APT-01 | Appointment list & waiting patients — full day view with live status (keep; later payment/tele) | APT-01.03 | API unchanged | Existing | Appointments | §5.2 | Appointment list & waiting patients | Full day view with live status | Doctor Web Portal | API hygiene | No | Yes | No | Yes | No | No | P1 | S | APT-01.02 | T-147 (APT-01.02) | QA |  | Day list + status live | Keep; reschedule/cancel/payment attach to this list | Day view still lists today’s appointments | Not Started | Web
149 | 241 | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.2 | APT-02 | Create new appointment — persist visit type, consultation mode and fee | APT-02.01 | DB: PatientAppointment.VisitType, ConsultMode; migrate existing rows VisitType=First (do not infer retrospectively) | Existing Improvement | Appointments | §5.2 | Create new appointment | Book with visit type, consultation mode and fee | Doctor Web Portal | Database | No | Yes | Yes | No | No | No | P0 | S | — | — | UI, QA |  | Create appointment ~90%; Formik modal has no VisitType / ConsultMode / fee | VisitType First/Follow-up; ConsultMode In-clinic / E-Consult; fee display from doctor profile / ConsultFeeConfig | New appointments persist visit type, mode and fee; filters/analytics can use them | Not Started | Web
150 | 242 | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.2 | APT-02 | Create new appointment — persist visit type, consultation mode and fee | APT-02.02 | API: create/update appointment accepts the new fields; PATCH VisitType | Existing Improvement | Appointments | §5.2 | Create new appointment | Book with visit type, consultation mode and fee | Doctor Web Portal | API | No | Yes | Yes | Yes | No | No | P0 | M | APT-02.01 | T-149 (APT-02.01) | UI, QA |  | Create appointment ~90%; Formik modal has no VisitType / ConsultMode / fee | VisitType First/Follow-up; ConsultMode In-clinic / E-Consult; fee display from doctor profile / ConsultFeeConfig | New appointments persist visit type, mode and fee; filters/analytics can use them | Not Started | Web
151 | 246 | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.3 | APT-03 | Appointment status update — move patients through the visit stages (keep) | APT-03.02 | ACL doctor/reception | Existing Improvement | Appointments | §5.2 | Appointment status update | Move patients through the visit stages | Doctor Web Portal | Security | Yes | Yes | No | Yes | No | No | P1 | S | APT-03.01 | — | QA | APT-03.01 | Status transitions live | Keep; add CANCELLED in APT-06; do not reuse DeleteStatus as cancel | Status still updates and buckets refresh | Not Started | Web
152 | 247 | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.3 | APT-03 | Appointment status update — move patients through the visit stages (keep) | APT-03.03 | API unchanged | Existing | Appointments | §5.2 | Appointment status update | Move patients through the visit stages | Doctor Web Portal | API hygiene | No | Yes | No | Yes | No | No | P1 | S | APT-03.02 | T-151 (APT-03.02) | QA |  | Status transitions live | Keep; add CANCELLED in APT-06; do not reuse DeleteStatus as cancel | Status still updates and buckets refresh | Not Started | Web
153 | 249 | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.4 | APT-04 | Appointment time update — adjust timings as the day runs (keep; distinct from formal reschedule) | APT-04.02 | Document in UI that Reschedule is the patient-notified path | Existing Improvement | Appointments | §5.2 | Appointment time update | Adjust timings as the day runs | Doctor Web Portal | Security | Yes | Yes | No | Yes | No | No | P1 | S | APT-04.01 | — | QA | APT-04.01 | UpdateAppointmentTime live — changes a time only; no audit/notify | Keep same-day time tweak; formal reschedule (old→new, notify, conflict) is APT-05 | Same-day time change still works; does not silently replace Reschedule | Not Started | Web
154 | 250 | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.4 | APT-04 | Appointment time update — adjust timings as the day runs (keep; distinct from formal reschedule) | APT-04.03 | API: keep UpdateAppointmentTime; Reschedule wraps it | Existing | Appointments | §5.2 | Appointment time update | Adjust timings as the day runs | Doctor Web Portal | API hygiene | No | Yes | No | Yes | No | No | P1 | S | APT-04.02 | T-153 (APT-04.02) | QA |  | UpdateAppointmentTime live — changes a time only; no audit/notify | Keep same-day time tweak; formal reschedule (old→new, notify, conflict) is APT-05 | Same-day time change still works; does not silently replace Reschedule | Not Started | Web
155 | 251 | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.5 | APT-05 | Reschedule appointment — move to a new slot with automatic patient notification (NEW — not a rename of UpdateAppointmentTime) | APT-05.01 | DB: AppointmentChangeLog (PatientAppId, Action, OldValue, NewValue, ByUserId, ByRole, At) + indexes | New | Appointments | §5.2 + §2.3 + §6 | Reschedule appointment | Move to a new slot with automatic patient notification / Move to another slot without calling the clinic | Doctor Web + Reception + later Patient | Database | No | Yes | Yes | No | No | No | P0 | S | — | — | UI, QA |  | Time can be edited; no formal Reschedule (audit, notify, old→new confirm) | POST RescheduleAppointment; AppointmentChangeLog; conflict 409 with alternatives; SMS/WhatsApp fan-out (notify failure must not roll back) | Every reschedule is in the change log; patient notified; old slot released; reception uses the same API | Not Started | Web
156 | 252 | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.5 | APT-05 | Reschedule appointment — move to a new slot with automatic patient notification (NEW — not a rename of UpdateAppointmentTime) | APT-05.02 | API: POST /api/PatientAppointment/RescheduleAppointment — validate schedule, bookings, not in the past; 409 with alternatives; wrap UpdateAppointmentTime; GET ChangeLog/{id} | New | Appointments | §5.2 + §2.3 + §6 | Reschedule appointment | Move to a new slot with automatic patient notification / Move to another slot without calling the clinic | Doctor Web + Reception + later Patient | API | No | Yes | Yes | Yes | No | No | P0 | M | APT-05.01 | T-155 (APT-05.01) | UI, QA |  | Time can be edited; no formal Reschedule (audit, notify, old→new confirm) | POST RescheduleAppointment; AppointmentChangeLog; conflict 409 with alternatives; SMS/WhatsApp fan-out (notify failure must not roll back) | Every reschedule is in the change log; patient notified; old slot released; reception uses the same API | Not Started | Web
157 | 254 | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.5 | APT-05 | Reschedule appointment — move to a new slot with automatic patient notification (NEW — not a rename of UpdateAppointmentTime) | APT-05.04 | Notifications: SMS + WhatsApp + (later) push — old→new; must not block the transaction if notify fails | New Integration | Appointments | §5.2 + §2.3 + §6 | Reschedule appointment | Move to a new slot with automatic patient notification / Move to another slot without calling the clinic | Doctor Web + Reception + later Patient | Integration | No | Yes | No | Yes | No | Yes | P0 | M | APT-05.03 | — | UI, QA | APT-05.03 | Time can be edited; no formal Reschedule (audit, notify, old→new confirm) | POST RescheduleAppointment; AppointmentChangeLog; conflict 409 with alternatives; SMS/WhatsApp fan-out (notify failure must not roll back) | Every reschedule is in the change log; patient notified; old slot released; reception uses the same API | Not Started | Web
158 | 256 | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.6 | APT-06 | Cancel appointment — reason, free the slot, trigger refund where applicable (NEW CANCELLED status — do NOT reuse DeleteStatus) | APT-06.01 | DB: add CANCELLED to status set; CancelReasonCode, CancelReasonText, CancelledBy, CancelledAt; DeleteStatus remains administrative | New | Appointments | §5.2 + §2.3 + §6 | Cancel appointment | Cancel with reason, free the slot, trigger refund where applicable / Cancel with reason, refund handled per policy | Doctor Web + Reception + later Patient | Database | No | Yes | Yes | No | No | No | P0 | S | — | — | UI, QA |  | No CANCELLED; DeleteStatus is soft-delete only | CANCELLED + reason fields; free slot; waitlist hook; if PAID evaluate refund policy (Phase 6/7) | Cancelled appointments leave active buckets; slot immediately bookable; refund path triggered rather than silently keeping money | Not Started | Web
159 | 257 | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.6 | APT-06 | Cancel appointment — reason, free the slot, trigger refund where applicable (NEW CANCELLED status — do NOT reuse DeleteStatus) | APT-06.02 | API: POST /api/PatientAppointment/CancelAppointment — reason required (enum; text if Other); free slot; offer waitlist stub; if PAID enqueue refund policy | New | Appointments | §5.2 + §2.3 + §6 | Cancel appointment | Cancel with reason, free the slot, trigger refund where applicable / Cancel with reason, refund handled per policy | Doctor Web + Reception + later Patient | API | No | Yes | Yes | Yes | No | No | P0 | M | APT-06.01 | T-158 (APT-06.01) | UI, QA |  | No CANCELLED; DeleteStatus is soft-delete only | CANCELLED + reason fields; free slot; waitlist hook; if PAID evaluate refund policy (Phase 6/7) | Cancelled appointments leave active buckets; slot immediately bookable; refund path triggered rather than silently keeping money | Not Started | Web
160 | 259 | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.6 | APT-06 | Cancel appointment — reason, free the slot, trigger refund where applicable (NEW CANCELLED status — do NOT reuse DeleteStatus) | APT-06.04 | Waitlist worker stub: on cancel, offer freed slot (full waitlist capture is Phase 9 GST waitlist) | New Integration | Appointments | §5.2 + §2.3 + §6 | Cancel appointment | Cancel with reason, free the slot, trigger refund where applicable / Cancel with reason, refund handled per policy | Doctor Web + Reception + later Patient | Integration | No | Yes | No | Yes | No | Yes | P0 | M | APT-06.03 | — | UI, QA | APT-06.03 | No CANCELLED; DeleteStatus is soft-delete only | CANCELLED + reason fields; free slot; waitlist hook; if PAID evaluate refund policy (Phase 6/7) | Cancelled appointments leave active buckets; slot immediately bookable; refund path triggered rather than silently keeping money | Not Started | Web
161 | 262 | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.7 | APT-07 | Daily schedule setup — define working days, hours and break times (promote modal to first-class screen) | APT-07.02 | No new API unless validation (breaks, overlapping hours) is missing — add server-side validation | Existing Improvement | Scheduling | §5.2 | Daily schedule setup | Define working days, hours and break times | Doctor Web Portal | API | No | Yes | No | Yes | No | No | P0 | S | APT-07.01 | — | UI, QA | APT-07.01 | DailyScheduleSetupModal + GetDailySchedule / SaveDailySchedule exist; not a first-class screen (draft marked 0%) | Promote to /doctor/schedule with week grid and copy-day; reuse existing APIs — do not rebuild | Public booking slots (Phase 9) respect the saved schedule | Not Started | Web
162 | 265 | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.8 | APT-08 | Appointment slot grid — visual slot-by-slot view of the day (keep; public booking reuses this) | APT-08.02 | ACL doctor/reception | Existing Improvement | Scheduling | §5.2 | Appointment slot grid | Visual slot-by-slot view of the day | Doctor Web Portal | Security | Yes | Yes | No | Yes | No | No | P0 | S | APT-08.01 | — | QA | APT-08.01 | Slot picker / grid live | Keep; Phase 9 public APIs reuse the same slot engine | Grid matches saved daily schedule | Not Started | Web
163 | 266 | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.8 | APT-08 | Appointment slot grid — visual slot-by-slot view of the day (keep; public booking reuses this) | APT-08.03 | Document GetAppointmentSlots as the public-booking engine — do not fork a second slot calculator | Existing | Scheduling | §5.2 | Appointment slot grid | Visual slot-by-slot view of the day | Doctor Web Portal | API hygiene | No | Yes | No | Yes | No | No | P0 | S | APT-08.02 | T-162 (APT-08.02) | QA |  | Slot picker / grid live | Keep; Phase 9 public APIs reuse the same slot engine | Grid matches saved daily schedule | Not Started | Web
164 | 267 | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.9 | APT-09 | Consultation payment status on every appointment (schema now; values live in Phase 6) | APT-09.01 | DB: PatientAppointment.PaymentStatus, PaymentMethod, PayAtClinicAllowed; default UNPAID | New | Appointments | §5.2 + §9 | Consultation payment status | See paid, unpaid or pay-at-clinic on every appointment / Doctor, reception and patient all see the same payment status | Doctor Web Portal | Database | No | Yes | Yes | No | No | No | P0 | S | — | — | UI, QA |  | No PaymentStatus on appointment | Add PaymentStatus UNPAID / PENDING / PAID / FAILED / PAY_AT_CLINIC / REFUNDED; UI badge; source of truth is webhook in Phase 6 not the client screen | Every appointment row can show a payment badge; until Phase 6 all show UNPAID/PAY_AT_CLINIC as configured | Not Started | Web
165 | 268 | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.9 | APT-09 | Consultation payment status on every appointment (schema now; values live in Phase 6) | APT-09.02 | API: include PaymentStatus on all appointment DTOs (doctor, reception, later public/patient) | New | Appointments | §5.2 + §9 | Consultation payment status | See paid, unpaid or pay-at-clinic on every appointment / Doctor, reception and patient all see the same payment status | Doctor Web Portal | API | No | Yes | No | Yes | No | No | P0 | S | APT-09.01 | T-164 (APT-09.01) | UI, QA |  | No PaymentStatus on appointment | Add PaymentStatus UNPAID / PENDING / PAID / FAILED / PAY_AT_CLINIC / REFUNDED; UI badge; source of truth is webhook in Phase 6 not the client screen | Every appointment row can show a payment badge; until Phase 6 all show UNPAID/PAY_AT_CLINIC as configured | Not Started | Web
166 | 272 | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.1 | REC-01 | Reception login — secure staff access (keep) | REC-01.02 | Disabled staff cannot login (after DOC-09) | Existing Improvement | Reception | §6 | Reception login | Secure staff access | Reception Portal | Security | Yes | Yes | No | Yes | No | No | P1 | S | REC-01.01 | — | QA | REC-01.01 | Reception logs in via Account; JWT includes DoctorID; uses doctor dashboard layout | Keep login; Phase 0 hashing applies; later dedicated reception chrome | Reception user still logs in and lands on front-desk home | Not Started | Web
167 | 273 | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.1 | REC-01 | Reception login — secure staff access (keep) | REC-01.03 | Same Login API as doctor | Existing | Reception | §6 | Reception login | Secure staff access | Reception Portal | API hygiene | No | Yes | No | Yes | No | No | P1 | S | REC-01.02 | T-166 (REC-01.02) | QA |  | Reception logs in via Account; JWT includes DoctorID; uses doctor dashboard layout | Keep login; Phase 0 hashing applies; later dedicated reception chrome | Reception user still logs in and lands on front-desk home | Not Started | Web
168 | 274 | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.2 | REC-02 | Reception profile — manage own profile details (0% today) | REC-02.01 | Reuse Profile/Me with role=Reception DTO (no new table if UserMaster suffices) | New | Reception | §6 | Reception profile | Manage own profile details | Reception Portal | Database | No | Yes | Yes | No | No | No | P1 | S | — | — | UI, QA |  | No reception-specific profile; shared Velzon /profile | Name, mobile, attached doctor (read-only); cannot edit doctor bank/fee | Reception can update own name/mobile; cannot change DoctorId | Not Started | Web
169 | 275 | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.2 | REC-02 | Reception profile — manage own profile details (0% today) | REC-02.02 | GET/PUT profile fields allowed for reception; ignore clinic fee/bank | New | Reception | §6 | Reception profile | Manage own profile details | Reception Portal | API | No | Yes | Yes | Yes | No | No | P1 | M | REC-02.01 | T-168 (REC-02.01) | UI, QA |  | No reception-specific profile; shared Velzon /profile | Name, mobile, attached doctor (read-only); cannot edit doctor bank/fee | Reception can update own name/mobile; cannot change DoctorId | Not Started | Web
170 | 282 | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.4 | REC-04 | Create patient — register a walk-in patient quickly (keep) | REC-04.02 | ACL: own doctor only | Existing Improvement | Reception | §6 | Create patient | Register a walk-in patient quickly | Reception Portal | Security | Yes | Yes | No | Yes | No | No | P1 | S | REC-04.01 | — | QA | REC-04.01 | Create patient live on shared dashboard | Keep on reception chrome | Walk-in patient created under the JWT DoctorId | Not Started | Web
171 | 283 | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.4 | REC-04 | Create patient — register a walk-in patient quickly (keep) | REC-04.03 | Same create-patient API | Existing | Reception | §6 | Create patient | Register a walk-in patient quickly | Reception Portal | API hygiene | No | Yes | No | Yes | No | No | P1 | S | REC-04.02 | T-170 (REC-04.02) | QA |  | Create patient live on shared dashboard | Keep on reception chrome | Walk-in patient created under the JWT DoctorId | Not Started | Web
172 | 285 | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.5 | REC-05 | Patient search & list — find any patient instantly (keep) | REC-05.02 | Opening a row goes to case paper or appointment, not full repertory | Existing Improvement | Reception | §6 | Patient search & list | Find any patient instantly | Reception Portal | Security | Yes | Yes | No | Yes | No | No | P1 | S | REC-05.01 | — | QA | REC-05.01 | Search live | Keep; no opening full clinical board | Search returns this doctor’s patients only | Not Started | Web
173 | 286 | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.5 | REC-05 | Patient search & list — find any patient instantly (keep) | REC-05.03 | API unchanged | Existing | Reception | §6 | Patient search & list | Find any patient instantly | Reception Portal | API hygiene | No | Yes | No | Yes | No | No | P1 | S | REC-05.02 | T-172 (REC-05.02) | QA |  | Search live | Keep; no opening full clinical board | Search returns this doctor’s patients only | Not Started | Web
174 | 287 | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.6 | REC-06 | Create & manage appointments — full appointment management (keep; plus reschedule/cancel from Phase 4) | REC-06.01 | Authorise Reception for Reschedule and Cancel for its own doctor's appointments only | New | Reception | §6 | Create & manage appointments | Full appointment management | Reception Portal | API + SPA | Yes | Yes | No | Yes | No | No | P0 | S | — | — | UI, QA |  | Create/status/time live; reschedule/cancel missing until Phase 4 APIs | Enable RescheduleAppointment and CancelAppointment for JWT DoctorId; isReceptionUser must not block | Reception acts only for its doctor; permission tests pass | Not Started | Web
175 | 292 | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.8 | REC-08 | Waiting queue management — manage the live queue and call the next patient | REC-08.01 | No new table required if status+order suffice; optional QueuePosition | Existing Improvement | Reception | §6 | Waiting queue management | Manage the live queue and call the next patient | Reception Portal | Database | No | Yes | Yes | No | No | No | P1 | S | — | — | UI, QA |  | Status buckets ~60%; no dedicated queue UX / call-next | Dedicated queue: walk-in vs tele; payment state; Call next; notify patient (later push) | Reception can call next; status moves; patient can be notified when Phase 12 exists | Not Started | Web
176 | 293 | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.8 | REC-08 | Waiting queue management — manage the live queue and call the next patient | REC-08.02 | Optional CallNext API that sets status and timestamp | Existing Improvement | Reception | §6 | Waiting queue management | Manage the live queue and call the next patient | Reception Portal | API | No | Yes | Yes | Yes | No | No | P1 | M | REC-08.01 | T-175 (REC-08.01) | UI, QA |  | Status buckets ~60%; no dedicated queue UX / call-next | Dedicated queue: walk-in vs tele; payment state; Call next; notify patient (later push) | Reception can call next; status moves; patient can be notified when Phase 12 exists | Not Started | Web
177 | 297 | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.9 | REC-09 | Appointment status update (reception) — update as patients arrive and are seen (keep) | REC-09.02 | ACL own doctor | Existing Improvement | Reception | §6 | Appointment status update | Update as patients arrive and are seen | Reception Portal | Security | Yes | Yes | No | Yes | No | No | P1 | S | REC-09.01 | — | QA | REC-09.01 | Status update live | Keep on reception chrome | Arrived / seen transitions still work | Not Started | Web
178 | 298 | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.9 | REC-09 | Appointment status update (reception) — update as patients arrive and are seen (keep) | REC-09.03 | Same status API as doctor | Existing | Reception | §6 | Appointment status update | Update as patients arrive and are seen | Reception Portal | API hygiene | No | Yes | No | Yes | No | No | P1 | S | REC-09.02 | T-177 (REC-09.02) | QA |  | Status update live | Keep on reception chrome | Arrived / seen transitions still work | Not Started | Web
179 | 300 | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.10 | REC-10 | Appointment time update (reception) — adjust timings through the day (keep) | REC-10.02 | ACL own doctor | Existing Improvement | Reception | §6 | Appointment time update | Adjust timings through the day | Reception Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | REC-10.01 | — | QA | REC-10.01 | Time update live | Keep; formal reschedule remains REC-06 | Same-day time tweak from reception works | Not Started | Web
180 | 301 | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.10 | REC-10 | Appointment time update (reception) — adjust timings through the day (keep) | REC-10.03 | Same API | Existing | Reception | §6 | Appointment time update | Adjust timings through the day | Reception Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | REC-10.02 | T-179 (REC-10.02) | QA |  | Time update live | Keep; formal reschedule remains REC-06 | Same-day time tweak from reception works | Not Started | Web
181 | 304 | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.12 | REC-12 | Log case paper / chief complaint — record the reason for visit before the consultation | REC-12.01 | Reuse complaints table; add CreatedByRole=Reception | New | Reception | §6 | Log case paper / chief complaint | Record the reason for visit before the consultation | Reception Portal | Database | No | Yes | Yes | No | No | No | P1 | S | — | — | UI, QA |  | Missing; SaveComplaints exists but board is doctor-only | Restricted case-paper form (chief complaint only — no repertory/Rx); audit reception author | Chief complaint visible to doctor on Patient Board; reception cannot repertorize | Not Started | Web
182 | 305 | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.12 | REC-12 | Log case paper / chief complaint — record the reason for visit before the consultation | REC-12.02 | POST case-paper subset of SaveComplaints; GET on board | New | Reception | §6 | Log case paper / chief complaint | Record the reason for visit before the consultation | Reception Portal | API | No | Yes | Yes | Yes | No | No | P1 | M | REC-12.01 | T-181 (REC-12.01) | UI, QA |  | Missing; SaveComplaints exists but board is doctor-only | Restricted case-paper form (chief complaint only — no repertory/Rx); audit reception author | Chief complaint visible to doctor on Patient Board; reception cannot repertorize | Not Started | Web
183 | 309 | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.13 | REC-13 | Collect consultation payment — cash, UPI, card or payment link and issue a receipt (API in Phase 6; UI shell now) | REC-13.02 | Do not write PaymentStatus=PAID from the client — Account/webhook is source of truth (Phase 6) | New | Reception | §6 + §9 | Collect consultation payment | Take cash, UPI, card or payment link and issue a receipt | Reception Portal | Architecture | No | Yes | No | No | No | No | P0 | S | REC-13.01 | — | UI | REC-13.01 | Does not exist | UI modal ready; CollectAtReception API lands with payment spine in Phase 6 — do not fake a paid status here | Modal exists but cannot mark PAID until Phase 6 webhook/ledger path is live — or land UI in Phase 6 with PAY-06. Prefer implement fully in Phase 6; this task is the reception UX that Phase 6 must include | Not Started | Web | Implement with PAY-02 in Phase 6; listed here so PDF §6 is not skipped in the Reception phase map
184 | 310 | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.1 | PAY-01 | Consultation fee configuration — each doctor’s fee set and displayed to patients | PAY-01.01 | DB: ConsultFeeConfig (DoctorId, InClinicFee, TeleFee, InstantSurcharge, Currency, PayAtClinicEnabled, EffectiveFrom) | New | Payments | §9 | Consultation fee configuration | Each doctor’s fee set and displayed to patients | Doctor profile + Public + Admin | Database | No | Yes | Yes | No | No | No | P0 | S | — | — | UI, QA |  | No ConsultFeeConfig; doctor profile work in DOC-10 may have stored a fee field | ConsultFeeConfig (InClinic, EConsult, optional Instant surcharge, PayAtClinicEnabled, GST flags) | Fee shown to patients matches what checkout charges; admin/doctor can update | Not Started | Web
185 | 311 | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.1 | PAY-01 | Consultation fee configuration — each doctor’s fee set and displayed to patients | PAY-01.02 | API: GET public fee; PUT doctor/admin; history of changes in audit | New | Payments | §9 | Consultation fee configuration | Each doctor’s fee set and displayed to patients | Doctor profile + Public + Admin | API | No | Yes | Yes | Yes | No | No | P0 | M | PAY-01.01 | T-184 (PAY-01.01) | UI, QA |  | No ConsultFeeConfig; doctor profile work in DOC-10 may have stored a fee field | ConsultFeeConfig (InClinic, EConsult, optional Instant surcharge, PayAtClinicEnabled, GST flags) | Fee shown to patients matches what checkout charges; admin/doctor can update | Not Started | Web
186 | 314 | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.2 | PAY-02 | Automatic payment verification — bank/webhook is source of truth, not the patient’s screen | PAY-02.01 | DB: PaymentOrder, PaymentEvent (raw webhook), idempotency key on payment_id | New | Payments | §9 | Automatic payment verification | Payments confirmed by the bank, not by the patient’s screen — nothing is lost if the app or browser closes | Shared | Database | No | Yes | Yes | No | No | No | P0 | M | — | — | QA |  | Razorpay checkout for S1 subscription only; no webhook; no signature verify on server | Port Razorpay to .NET 8; keys in config; POST /api/Payments/Webhook/Razorpay anonymous + signature verify; PaymentOrder table | Kill browser after pay → webhook still marks PAID; client callback alone never marks PAID | Not Started | Web
187 | 315 | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.2 | PAY-02 | Automatic payment verification — bank/webhook is source of truth, not the patient’s screen | PAY-02.02 | Port Order/GenerateOrderId pattern to .NET 8; move keys to configuration; do not commit secrets | New Integration | Payments | §9 | Automatic payment verification | Payments confirmed by the bank, not by the patient’s screen — nothing is lost if the app or browser closes | Shared | API | No | Yes | No | Yes | No | Yes | P0 | L | PAY-02.01 | T-186 (PAY-02.01) | QA |  | Razorpay checkout for S1 subscription only; no webhook; no signature verify on server | Port Razorpay to .NET 8; keys in config; POST /api/Payments/Webhook/Razorpay anonymous + signature verify; PaymentOrder table | Kill browser after pay → webhook still marks PAID; client callback alone never marks PAID | Not Started | Web
188 | 316 | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.2 | PAY-02 | Automatic payment verification — bank/webhook is source of truth, not the patient’s screen | PAY-02.03 | Webhook handler payment.captured / payment.failed; signature verify; never trust client-only success | New Integration | Payments | §9 | Automatic payment verification | Payments confirmed by the bank, not by the patient’s screen — nothing is lost if the app or browser closes | Shared | API | No | Yes | No | Yes | No | Yes | P0 | M | PAY-02.02 | T-187 (PAY-02.02) | QA |  | Razorpay checkout for S1 subscription only; no webhook; no signature verify on server | Port Razorpay to .NET 8; keys in config; POST /api/Payments/Webhook/Razorpay anonymous + signature verify; PaymentOrder table | Kill browser after pay → webhook still marks PAID; client callback alone never marks PAID | Not Started | Web
189 | 318 | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.3 | PAY-03 | Online consultation payment — patient pays by card, UPI, netbanking or wallet | PAY-03.01 | DB: ConsultPayment linked to PaymentOrder + PatientAppId — NOT PackageEntryDetail | New | Payments | §9 + §4 + §2.3 | Online consultation payment | Patient pays by card, UPI, netbanking or wallet / Pay the consultation fee at the time of booking / Pay the consultation fee inside the app | Public web + later Patient app | Database | No | Yes | Yes | No | No | No | P0 | S | — | — | UI, QA |  | Does not exist (only S1 SaaS) | CreateConsultOrder attached to PatientAppId; Razorpay Checkout; webhook sets PAID; do not overload PackageEntryDetail | Paid appointment unlocks tele queue rules; doctor sees PAID; Account sees ledger row (Phase 7) | Not Started | Web
190 | 319 | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.3 | PAY-03 | Online consultation payment — patient pays by card, UPI, netbanking or wallet | PAY-03.02 | API: CreateConsultOrder, Verify (optional), status by appointment; amount from ConsultFeeConfig | New | Payments | §9 + §4 + §2.3 | Online consultation payment | Patient pays by card, UPI, netbanking or wallet / Pay the consultation fee at the time of booking / Pay the consultation fee inside the app | Public web + later Patient app | API | No | Yes | Yes | Yes | No | No | P0 | M | PAY-03.01 | T-189 (PAY-03.01) | UI, QA |  | Does not exist (only S1 SaaS) | CreateConsultOrder attached to PatientAppId; Razorpay Checkout; webhook sets PAID; do not overload PackageEntryDetail | Paid appointment unlocks tele queue rules; doctor sees PAID; Account sees ledger row (Phase 7) | Not Started | Web
191 | 321 | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.3 | PAY-03 | Online consultation payment — patient pays by card, UPI, netbanking or wallet | PAY-03.04 | Razorpay Checkout methods: card, UPI, netbanking, wallet as enabled on the account | New Integration | Payments | §9 + §4 + §2.3 | Online consultation payment | Patient pays by card, UPI, netbanking or wallet / Pay the consultation fee at the time of booking / Pay the consultation fee inside the app | Public web + later Patient app | Integration | No | Yes | No | Yes | No | Yes | P0 | M | PAY-03.03 | — | UI, QA | PAY-03.03 | Does not exist (only S1 SaaS) | CreateConsultOrder attached to PatientAppId; Razorpay Checkout; webhook sets PAID; do not overload PackageEntryDetail | Paid appointment unlocks tele queue rules; doctor sees PAID; Account sees ledger row (Phase 7) | Not Started | Web
192 | 323 | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.4 | PAY-04 | Reception payment collection — cash, UPI, card or payment link with printed receipt | PAY-04.01 | Reuse PaymentOrder + ConsultPayment with Method=CASH/UPI_OFFLINE/CARD_POS/PAY_LINK | New | Payments | §9 + §6 | Reception payment collection | Cash, UPI, card or payment link with printed receipt | Reception Portal | Database | No | Yes | Yes | No | No | No | P0 | S | — | — | UI, QA |  | Does not exist | CollectAtReception writes ledger S3; print receipt; payment-link uses same Razorpay order as online | Cash still creates an immutable ledger row; receipt printable; status matches doctor list | Not Started | Web
193 | 324 | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.4 | PAY-04 | Reception payment collection — cash, UPI, card or payment link with printed receipt | PAY-04.02 | API: CollectAtReception; generate pay-link; print receipt payload | New | Payments | §9 + §6 | Reception payment collection | Cash, UPI, card or payment link with printed receipt | Reception Portal | API | No | Yes | Yes | Yes | No | No | P0 | M | PAY-04.01 | T-192 (PAY-04.01) | UI, QA |  | Does not exist | CollectAtReception writes ledger S3; print receipt; payment-link uses same Razorpay order as online | Cash still creates an immutable ledger row; receipt printable; status matches doctor list | Not Started | Web
194 | 326 | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.4 | PAY-04 | Reception payment collection — cash, UPI, card or payment link with printed receipt | PAY-04.04 | Pay-link SMS/WhatsApp optional (Phase 12); must still ledger if notify fails | New Integration | Payments | §9 + §6 | Reception payment collection | Cash, UPI, card or payment link with printed receipt | Reception Portal | Integration | No | Yes | No | Yes | No | Yes | P0 | M | PAY-04.03 | — | UI, QA | PAY-04.03 | Does not exist | CollectAtReception writes ledger S3; print receipt; payment-link uses same Razorpay order as online | Cash still creates an immutable ledger row; receipt printable; status matches doctor list | Not Started | Web
195 | 328 | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.5 | PAY-05 | Pay-at-clinic option — book now, pay at the clinic where the doctor allows it | PAY-05.01 | Honor PayAtClinicEnabled on public create-booking and checkout | New | Payments | §9 | Pay-at-clinic option | Book now, pay at the clinic where the doctor allows it | Public + Doctor + Reception | API | No | Yes | No | Yes | No | No | P1 | S | — | — | UI, QA |  | Does not exist | PayAtClinicEnabled on fee config; appointment PaymentStatus=PAY_AT_CLINIC; tele queue may still require PAID (policy) | If doctor disables pay-at-clinic, public checkout requires online pay | Not Started | Web
196 | 331 | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.6 | PAY-06 | Doctor subscription payment — buy and renew subscription packages (complete remaining ~30%) | PAY-06.01 | Reuse PAY-02 webhook for S1 orders; link PackageEntryDetail as S1 only | Existing Improvement | Payments | §9 | Doctor subscription payment | Buy and renew subscription packages | Doctor Web Portal | API | No | Yes | No | No | No | Yes | P1 | M | — | — | UI, QA |  | Checkout works ~70%; no webhook, refund, invoice, GST, Account ledger | Same webhook spine; write S1 ledger; invoice; failed pay UX; PackageEntryDetail shape UNCHANGED | SaaS pay verified by webhook; doctor plan flags update without trusting client callback alone | Not Started | Web
197 | 334 | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.7 | PAY-07 | Medicine payment — pay online or cash on delivery (API contract now; HomeoMeds Phase 14 implements orders) | PAY-07.01 | Extend PaymentOrder with Stream=CONSULT¦SUBSCRIPTION¦MEDICINE so Phase 14 can attach without schema rewrite | New | Payments | §9 + §12 | Medicine payment | Pay online or choose cash on delivery / Both options supported, with status tracking | Shared | Database | No | Yes | Yes | No | No | No | P1 | S | — | — | QA |  | Does not exist | PaymentOrder.Stream=MEDICINE; COD_PENDING until pharmacy confirms collection; do not mix with consult money | A medicine PaymentOrder cannot be summarised as consult GMV | Not Started | Web
198 | 335 | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.7 | PAY-07 | Medicine payment — pay online or cash on delivery (API contract now; HomeoMeds Phase 14 implements orders) | PAY-07.02 | API stub: CreateMedicineOrder payment + COD status enum — implemented fully in Phase 14 | New | Payments | §9 + §12 | Medicine payment | Pay online or choose cash on delivery / Both options supported, with status tracking | Shared | API | No | Yes | No | Yes | No | No | P1 | S | PAY-07.01 | T-197 (PAY-07.01) | QA |  | Does not exist | PaymentOrder.Stream=MEDICINE; COD_PENDING until pharmacy confirms collection; do not mix with consult money | A medicine PaymentOrder cannot be summarised as consult GMV | Not Started | Web
199 | 337 | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.8 | PAY-08 | Payment status everywhere — doctor, reception and patient all see the same payment status | PAY-08.01 | Single source: PaymentOrder/ConsultPayment → Appointment.PaymentStatus updated only by webhook or CollectAtReception | New | Payments | §9 | Payment status everywhere | Doctor, reception and patient all see the same payment status | All | API | No | Yes | No | No | No | No | P0 | M | — | — | UI, QA |  | No shared status | Single PaymentStatus on appointment/order; all DTOs read it; never a second client-only flag | Doctor list, reception queue, public booking confirmation, later patient app show identical status for the same id | Not Started | Web
200 | 340 | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.9 | PAY-09 | Refunds — processed and tracked against the original payment | PAY-09.01 | DB: Refund (PaymentOrderId, Amount, Reason, Status, GatewayRefundId, ByUserId, At) | New | Payments | §9 + §8 + §2.8 | Refunds | Processed and tracked against the original payment / Issue and track refunds | Account + Patient | Database | No | Yes | Yes | No | No | No | P0 | S | — | — | UI, QA |  | Does not exist | Refund entity against original PaymentOrder; Razorpay refund API; cancel-appointment hook; patient sees status | Refund cannot exceed captured amount; original payment remains visible; appointment status REFUNDED/partial as designed | Not Started | Web
201 | 341 | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.9 | PAY-09 | Refunds — processed and tracked against the original payment | PAY-09.02 | API: create refund (Account); webhook refund.processed; cancel-appointment policy engine (full/partial/none) | New | Payments | §9 + §8 + §2.8 | Refunds | Processed and tracked against the original payment / Issue and track refunds | Account + Patient | API | No | Yes | Yes | Yes | No | No | P0 | M | PAY-09.01 | T-200 (PAY-09.01) | UI, QA |  | Does not exist | Refund entity against original PaymentOrder; Razorpay refund API; cancel-appointment hook; patient sees status | Refund cannot exceed captured amount; original payment remains visible; appointment status REFUNDED/partial as designed | Not Started | Web
202 | 343 | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.9 | PAY-09 | Refunds — processed and tracked against the original payment | PAY-09.04 | Razorpay refund API + webhook | New Integration | Payments | §9 + §8 + §2.8 | Refunds | Processed and tracked against the original payment / Issue and track refunds | Account + Patient | Integration | No | Yes | No | Yes | No | Yes | P0 | M | PAY-09.03 | — | UI, QA | PAY-09.03 | Does not exist | Refund entity against original PaymentOrder; Razorpay refund API; cancel-appointment hook; patient sees status | Refund cannot exceed captured amount; original payment remains visible; appointment status REFUNDED/partial as designed | Not Started | Web
203 | 345 | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.10 | PAY-10 | Payment receipts & invoices — issued for every transaction | PAY-10.01 | DB: Invoice (Number, Series, Stream, PaymentOrderId, GstBreakup, PdfPath) | New | Payments | §9 + §8 | Payment receipts & invoices | Issued for every transaction / Invoice numbering and tax reporting | All | Database | No | Yes | Yes | No | No | No | P1 | S | — | — | UI, QA |  | No invoice entity | Invoice numbering series from PRE-02; PDF receipt; GST fields; email in Phase 12 | Every PAID consult/subscription/medicine has a retrievable receipt number | Not Started | Web
204 | 346 | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.10 | PAY-10 | Payment receipts & invoices — issued for every transaction | PAY-10.02 | API: get invoice by payment; generate PDF via SecureDocument | New | Payments | §9 + §8 | Payment receipts & invoices | Issued for every transaction / Invoice numbering and tax reporting | All | API | No | Yes | Yes | Yes | No | No | P1 | M | PAY-10.01 | T-203 (PAY-10.01) | UI, QA |  | No invoice entity | Invoice numbering series from PRE-02; PDF receipt; GST fields; email in Phase 12 | Every PAID consult/subscription/medicine has a retrievable receipt number | Not Started | Web
205 | 349 | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.11 | PAY-11 | Complete payment audit trail — every transaction traceable end to end by Homeocentrum | PAY-11.01 | Persist raw webhook JSON; correlation id on Appointment and Ledger | New | Payments | §9 + §17 | Complete audit trail | Every transaction traceable end to end by Homeocentrum | Account | Database | No | Yes | Yes | No | No | No | P0 | S | — | — | QA |  | No webhook store | PaymentEvent raw payloads + AuditEvent + OtpAudit for payouts; Account can reconstruct without Razorpay dashboard | Given a PatientAppId, Account retrieves order, events, invoice, refunds | Not Started | Web
206 | 350 | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.11 | PAY-11 | Complete payment audit trail — every transaction traceable end to end by Homeocentrum | PAY-11.02 | Account query API: trail by appointment / payment / doctor (Phase 7 UI) | New | Payments | §9 + §17 | Complete audit trail | Every transaction traceable end to end by Homeocentrum | Account | API | No | Yes | No | Yes | No | No | P0 | M | PAY-11.01 | T-205 (PAY-11.01) | QA |  | No webhook store | PaymentEvent raw payloads + AuditEvent + OtpAudit for payouts; Account can reconstruct without Razorpay dashboard | Given a PatientAppId, Account retrieves order, events, invoice, refunds | Not Started | Web
207 | 352 | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.1 | FIN-01 | Unified transaction ledger — every rupee that moves through the platform, in one record | FIN-01.01 | DB: LedgerEntry (Stream, Direction, Amount, Gst, Commission, EntityType, EntityId, PaymentOrderId, At) immutable | New | Account | §8 | Unified transaction ledger | Every rupee that moves through the platform, in one record | Account Portal | Database | No | Yes | Yes | No | No | No | P0 | S | — | — | UI, QA |  | Does not exist | Append-only LedgerEntry for S1–S7; filters; OTP audit link; Admin may view, Account owns movement | No money movement without a ledger row; rows are immutable | Not Started | Web
208 | 353 | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.1 | FIN-01 | Unified transaction ledger — every rupee that moves through the platform, in one record | FIN-01.02 | API: GET /account/ledger filters; export; write-only from payment/settlement services | New | Account | §8 | Unified transaction ledger | Every rupee that moves through the platform, in one record | Account Portal | API | No | Yes | Yes | Yes | No | No | P0 | M | FIN-01.01 | T-207 (FIN-01.01) | UI, QA |  | Does not exist | Append-only LedgerEntry for S1–S7; filters; OTP audit link; Admin may view, Account owns movement | No money movement without a ledger row; rows are immutable | Not Started | Web
209 | 356 | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.2 | FIN-02 | Consultation payment reconciliation — online payments and reception collections matched and verified | FIN-02.01 | Reuse ConsultPayment + Appointment; reconciliation query | New | Account | §8 + §7.2 + §16 | Consultation payment reconciliation | Online payments and reception collections matched and verified / Match every booking against every payment | Account + Admin | Database | No | Yes | Yes | No | No | No | P0 | S | — | — | UI, QA |  | Does not exist | Join booking ↔ payment ↔ appointment; KPI collected/pending/failed/refunded; CSV | Every paid booking has exactly one captured consult payment or an exception | Not Started | Web
210 | 357 | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.2 | FIN-02 | Consultation payment reconciliation — online payments and reception collections matched and verified | FIN-02.02 | GET Admin/Account reconciliation + aggregates | New | Account | §8 + §7.2 + §16 | Consultation payment reconciliation | Online payments and reception collections matched and verified / Match every booking against every payment | Account + Admin | API | No | Yes | Yes | Yes | No | No | P0 | M | FIN-02.01 | T-209 (FIN-02.01) | UI, QA |  | Does not exist | Join booking ↔ payment ↔ appointment; KPI collected/pending/failed/refunded; CSV | Every paid booking has exactly one captured consult payment or an exception | Not Started | Web
211 | 360 | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.3 | FIN-03 | Medicine ledger — medicine money tracked separately from consultation money | FIN-03.01 | LedgerEntry stream MEDICINE with SplitSeller/SplitPlatform/SplitDelivery | New | Account | §8 + §12 | Medicine ledger | Medicine money tracked separately from consultation money / Seller, platform and delivery shares recorded separately from consultation money | Account Portal | Database | No | Yes | Yes | No | No | No | P1 | S | — | — | UI, QA |  | Does not exist | /account/medicine-ledger; Stream=MEDICINE; seller/platform/delivery split columns; filled in Phase 14 | Medicine GMV query cannot include consult fees | Not Started | Web
212 | 361 | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.3 | FIN-03 | Medicine ledger — medicine money tracked separately from consultation money | FIN-03.02 | GET /account/medicine-ledger | New | Account | §8 + §12 | Medicine ledger | Medicine money tracked separately from consultation money / Seller, platform and delivery shares recorded separately from consultation money | Account Portal | API | No | Yes | Yes | Yes | No | No | P1 | M | FIN-03.01 | T-211 (FIN-03.01) | UI, QA |  | Does not exist | /account/medicine-ledger; Stream=MEDICINE; seller/platform/delivery split columns; filled in Phase 14 | Medicine GMV query cannot include consult fees | Not Started | Web
213 | 364 | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.4 | FIN-04 | Settlement runs — scheduled settlement of amounts due to doctors and pharmacies | FIN-04.01 | DB: SettlementRun, SettlementLine | New | Account | §8 + §16 | Settlement runs | Scheduled settlement of amounts due to doctors and pharmacies | Account Portal | Database | No | Yes | Yes | No | No | No | P0 | S | — | — | UI, QA |  | Does not exist | SettlementRun job T+N hold; net of commission/GST/refunds; pharmacies after Phase 14 | A settlement run is replayable and lists included transactions | Not Started | Web
214 | 365 | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.4 | FIN-04 | Settlement runs — scheduled settlement of amounts due to doctors and pharmacies | FIN-04.02 | API: create run (dry-run + commit); list; detail | New | Account | §8 + §16 | Settlement runs | Scheduled settlement of amounts due to doctors and pharmacies | Account Portal | API | No | Yes | Yes | Yes | No | No | P0 | M | FIN-04.01 | T-213 (FIN-04.01) | UI, QA |  | Does not exist | SettlementRun job T+N hold; net of commission/GST/refunds; pharmacies after Phase 14 | A settlement run is replayable and lists included transactions | Not Started | Web
215 | 368 | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.5 | FIN-05 | Payout approval — payouts released only after OTP-verified approval | FIN-05.01 | DB: Payout (PayeeType Doctor¦Pharmacy, Amount, Status, SettlementRunId) | New | Account | §8 + §17 | Payout approval | Payouts released only after OTP-verified approval | Account Portal | Database | No | Yes | Yes | No | No | No | P0 | S | — | — | UI, QA |  | Does not exist | ApprovePayout requires SEC-07 OTP; Admin cannot approve; NEFT/file or gateway per PRE-01 | Payout without OTP fails; audit shows who approved | Not Started | Web
216 | 369 | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.5 | FIN-05 | Payout approval — payouts released only after OTP-verified approval | FIN-05.02 | API: ApprovePayout with OTP; reject | New | Account | §8 + §17 | Payout approval | Payouts released only after OTP-verified approval | Account Portal | API | No | Yes | Yes | Yes | No | No | P0 | M | FIN-05.01 | T-215 (FIN-05.01) | UI, QA |  | Does not exist | ApprovePayout requires SEC-07 OTP; Admin cannot approve; NEFT/file or gateway per PRE-01 | Payout without OTP fails; audit shows who approved | Not Started | Web
217 | 371 | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.5 | FIN-05 | Payout approval — payouts released only after OTP-verified approval | FIN-05.04 | Bank file / Razorpay payout adapter per PRE-01 | New Integration | Account | §8 + §17 | Payout approval | Payouts released only after OTP-verified approval | Account Portal | Integration | No | Yes | No | Yes | No | Yes | P0 | M | FIN-05.03 | — | UI, QA | FIN-05.03 | Does not exist | ApprovePayout requires SEC-07 OTP; Admin cannot approve; NEFT/file or gateway per PRE-01 | Payout without OTP fails; audit shows who approved | Not Started | Web
218 | 374 | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.6 | FIN-06 | Refund processing — Account issues and tracks refunds (uses PAY-09) | FIN-06.02 | Ledger reverse entries on successful refund | New | Account | §8 | Refund processing | Issue and track refunds | Account Portal | API | No | Yes | No | No | No | No | P0 | S | FIN-06.01 | — | UI, QA | FIN-06.01 | Does not exist | /account/refunds UI on PAY-09 APIs; OTP if policy requires | Account can issue refund; patient status updates; ledger reverses | Not Started | Web
219 | 376 | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.7 | FIN-07 | Payment exception handling — investigate and resolve every failed or disputed payment | FIN-07.01 | DB: PaymentException state machine | New | Account | §8 + §7.2 | Payment exception handling | Investigate and resolve every failed or disputed payment / Every failed or mismatched payment surfaced for action | Account + Admin | Database | No | Yes | Yes | No | No | No | P0 | S | — | — | UI, QA |  | Does not exist | Exception queue Failed/Partial/Webhook-mismatch/Refund-pending; retry/resolve with OTP on manual reconcile | Nothing failed is silent; resolve writes audit | Not Started | Web
220 | 377 | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.7 | FIN-07 | Payment exception handling — investigate and resolve every failed or disputed payment | FIN-07.02 | API: list/detail/retry/resolve; created by webhook mismatches | New | Account | §8 + §7.2 | Payment exception handling | Investigate and resolve every failed or disputed payment / Every failed or mismatched payment surfaced for action | Account + Admin | API | No | Yes | Yes | Yes | No | No | P0 | M | FIN-07.01 | T-219 (FIN-07.01) | UI, QA |  | Does not exist | Exception queue Failed/Partial/Webhook-mismatch/Refund-pending; retry/resolve with OTP on manual reconcile | Nothing failed is silent; resolve writes audit | Not Started | Web
221 | 380 | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.8 | FIN-08 | GST & invoice reports — invoice numbering and tax reporting | FIN-08.01 | Reuse Invoice; tax config table (GstRate, treatment flags) | New | Account | §8 + §16 | GST & invoice reports | Invoice numbering and tax reporting | Account Portal | Database | No | Yes | Yes | No | No | No | P1 | S | — | — | UI, QA |  | Does not exist | /account/tax export using Invoice table and PRE-02 GST treatment — configuration not hardcoded | Date-range GST report matches invoices issued | Not Started | Web
222 | 381 | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.8 | FIN-08 | GST & invoice reports — invoice numbering and tax reporting | FIN-08.02 | GET tax report + CSV | New | Account | §8 + §16 | GST & invoice reports | Invoice numbering and tax reporting | Account Portal | API | No | Yes | Yes | Yes | No | No | P1 | M | FIN-08.01 | T-221 (FIN-08.01) | UI, QA |  | Does not exist | /account/tax export using Invoice table and PRE-02 GST treatment — configuration not hardcoded | Date-range GST report matches invoices issued | Not Started | Web
223 | 384 | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.9 | FIN-09 | Payee records — bank and KYC details for doctors and pharmacies | FIN-09.01 | DB: Payee (DoctorId/PharmacyId, Bank, PAN, KYC status) | New | Account | §8 | Payee records | Bank and KYC details for doctors and pharmacies | Account Portal | Database | No | Yes | Yes | No | No | No | P1 | S | — | — | UI, QA |  | Doctor bank fields added in DOC-10; no Account UI; no pharmacy | /account/payees; OTP on doctor KYC change (fraud); pharmacies after Phase 14 | Payout cannot run to a payee missing KYC | Not Started | Web
224 | 385 | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.9 | FIN-09 | Payee records — bank and KYC details for doctors and pharmacies | FIN-09.02 | API: list/update; OTP on bank change | New | Account | §8 | Payee records | Bank and KYC details for doctors and pharmacies | Account Portal | API | No | Yes | Yes | Yes | No | No | P1 | M | FIN-09.01 | T-223 (FIN-09.01) | UI, QA |  | Doctor bank fields added in DOC-10; no Account UI; no pharmacy | /account/payees; OTP on doctor KYC change (fraud); pharmacies after Phase 14 | Payout cannot run to a payee missing KYC | Not Started | Web
225 | 388 | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.10 | FIN-10 | Clinic collection view — cash and UPI collected at reception, per clinic and per day | FIN-10.01 | Query ConsultPayment Method in CASH/UPI_OFFLINE grouped by DoctorId/date | New | Account | §8 | Clinic collection view | Cash and UPI collected at reception, per clinic and per day | Account Portal | Database | No | Yes | Yes | No | No | No | P1 | S | — | — | UI, QA |  | Does not exist | /account/clinic-collections from CollectAtReception rows; respect PRE-02 retain vs remit | Per clinic per day cash/UPI totals match reception receipts | Not Started | Web
226 | 389 | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.10 | FIN-10 | Clinic collection view — cash and UPI collected at reception, per clinic and per day | FIN-10.02 | GET clinic-collections | New | Account | §8 | Clinic collection view | Cash and UPI collected at reception, per clinic and per day | Account Portal | API | No | Yes | Yes | Yes | No | No | P1 | M | FIN-10.01 | T-225 (FIN-10.01) | UI, QA |  | Does not exist | /account/clinic-collections from CollectAtReception rows; respect PRE-02 retain vs remit | Per clinic per day cash/UPI totals match reception receipts | Not Started | Web
227 | 392 | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.11 | FIN-11 | Separation of duties — Account controls money; Admin controls platform and clinical data | FIN-11.01 | Seed Account role menus: ledger, recon, medicine ledger, exceptions, settlements, payouts, refunds, tax, payees, clinic collections | New | Account | §8 | Separation of duties | The Account department controls money. Admin controls the platform and clinical data. Neither can perform the other’s role, which protects both. | Admin + Account | Configuration | Yes | Yes | Yes | No | No | No | P0 | M | — | — | QA |  | Account role does not exist | Enforce in RBAC: Admin cannot ApprovePayout; Account cannot edit repertory/users’ clinical masters | Automated tests for both forbidden directions | Not Started | Web
228 | 394 | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.1 | TRU-01 | Doctor credentialing — doctors upload qualification and registration documents for review | TRU-01.01 | DB: DoctorVerification (Pending/Approved/Rejected/NeedsInfo), DoctorCredentialDocument | New | Trust | §13 + §7.2 | Doctor credentialing | Doctors upload qualification and registration documents for review | Doctor Web + Admin | Database | No | Yes | Yes | No | No | No | P0 | S | — | — | UI, QA |  | RegisterDoctor activates immediately; PassingUniversity/CertNo/QualificationId exist; no document store/queue | DoctorCredentialDocument + VerificationStatus Pending; do not auto-activate practice for public directory | New registrations sit in Pending with documents; existing doctors backfill per PRE-03 | Not Started | Web
229 | 395 | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.1 | TRU-01 | Doctor credentialing — doctors upload qualification and registration documents for review | TRU-01.02 | API: upload documents; MyStatus; RegisterDoctor modified to VerificationStatus=Pending (not auto-practice) | New | Trust | §13 + §7.2 | Doctor credentialing | Doctors upload qualification and registration documents for review | Doctor Web + Admin | API | No | Yes | Yes | Yes | No | No | P0 | M | TRU-01.01 | T-228 (TRU-01.01) | UI, QA |  | RegisterDoctor activates immediately; PassingUniversity/CertNo/QualificationId exist; no document store/queue | DoctorCredentialDocument + VerificationStatus Pending; do not auto-activate practice for public directory | New registrations sit in Pending with documents; existing doctors backfill per PRE-03 | Not Started | Web
230 | 398 | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.2 | TRU-02 | Verification review — Admin approves, rejects or requests further information | TRU-02.01 | Reuse DoctorVerification | New | Trust | §13 + §7.2 | Verification review | Admin approves, rejects or requests more information before they can practise on the platform | Admin Portal | Database | No | Yes | Yes | No | No | No | P0 | S | — | — | UI, QA |  | Does not exist | /admin/doctor-credentialing list + detail; email notify doctor | Approve/reject/request-info all audited; doctor sees status | Not Started | Web
231 | 399 | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.2 | TRU-02 | Verification review — Admin approves, rejects or requests further information | TRU-02.02 | API: Queue, {id}, Approve, Reject, RequestInfo | New | Trust | §13 + §7.2 | Verification review | Admin approves, rejects or requests more information before they can practise on the platform | Admin Portal | API | No | Yes | Yes | Yes | No | No | P0 | M | TRU-02.01 | T-230 (TRU-02.01) | UI, QA |  | Does not exist | /admin/doctor-credentialing list + detail; email notify doctor | Approve/reject/request-info all audited; doctor sees status | Not Started | Web
232 | 401 | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.2 | TRU-02 | Verification review — Admin approves, rejects or requests further information | TRU-02.04 | Email notify (Phase 12 SMTP already used for activation) | New Integration | Trust | §13 + §7.2 | Verification review | Admin approves, rejects or requests more information before they can practise on the platform | Admin Portal | Integration | No | Yes | No | Yes | No | Yes | P0 | M | TRU-02.03 | — | UI, QA | TRU-02.03 | Does not exist | /admin/doctor-credentialing list + detail; email notify doctor | Approve/reject/request-info all audited; doctor sees status | Not Started | Web
233 | 403 | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.3 | TRU-03 | Verified badge — patients see which doctors have been verified | TRU-03.01 | Public doctor DTO includes isVerified | New | Trust | §13 + §2.2 | Verified badge / Credentials & verification | Patients see which doctors have been verified / Verified badge showing the doctor’s credentials are checked | Public + Patient app | API | No | Yes | No | Yes | No | No | P0 | S | — | — | UI, QA |  | Does not exist | Badge on public doctor card and profile from VerificationStatus=Approved | Unverified doctors never show a verified badge | Not Started | Web
234 | 406 | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.4 | TRU-04 | Practice gate — only verified doctors appear to patients and take paid consultations | TRU-04.01 | Public doctor list filter VerificationStatus=Approved | New | Trust | §13 | Practice gate | Only verified doctors appear to patients and take paid consultations | Public + Payments | API | No | Yes | No | Yes | No | No | P0 | S | — | — | QA |  | Any activated doctor could theoretically be listed; no public list yet | Public search and CreateConsultOrder require Approved; own-clinic staff booking may still work per PRE-03 | Unverified doctor absent from /book; paid public consult blocked | Not Started | Web
235 | 407 | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.4 | TRU-04 | Practice gate — only verified doctors appear to patients and take paid consultations | TRU-04.02 | CreateConsultOrder rejects unverified doctor for patient-originated bookings | New | Trust | §13 | Practice gate | Only verified doctors appear to patients and take paid consultations | Public + Payments | API | No | Yes | No | Yes | No | No | P0 | S | TRU-04.01 | T-234 (TRU-04.01) | QA |  | Any activated doctor could theoretically be listed; no public list yet | Public search and CreateConsultOrder require Approved; own-clinic staff booking may still work per PRE-03 | Unverified doctor absent from /book; paid public consult blocked | Not Started | Web
236 | 409 | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.5 | TRU-05 | Patient reviews — patients rate and review consultations | TRU-05.01 | DB: Review (PatientAppId, Rating, Text, Status, At) | New | Trust | §13 + §2.8 | Patient reviews / Write a review | Patients rate and review consultations / Rate and review the consultation | Patient + Public | Database | No | Yes | Yes | No | No | No | P1 | S | — | — | UI, QA |  | Does not exist | Review linked to PatientAppId; one review per visit; moderation flag optional | Review only after completed consult; doctor cannot write self-reviews | Not Started | Web
237 | 410 | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.5 | TRU-05 | Patient reviews — patients rate and review consultations | TRU-05.02 | API: create (patient), list by doctor (public approved), doctor list own | New | Trust | §13 + §2.8 | Patient reviews / Write a review | Patients rate and review consultations / Rate and review the consultation | Patient + Public | API | No | Yes | Yes | Yes | No | No | P1 | M | TRU-05.01 | T-236 (TRU-05.01) | UI, QA |  | Does not exist | Review linked to PatientAppId; one review per visit; moderation flag optional | Review only after completed consult; doctor cannot write self-reviews | Not Started | Web
238 | 413 | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.6 | TRU-06 | Review appeal — doctors can appeal a review; patients manage reviews and raise an appeal | TRU-06.01 | DB: ReviewAppeal | New | Trust | §13 + §2.8 | Review appeal / My reviews & appeal | Doctors can appeal a review / Manage reviews and raise an appeal | Doctor + Patient + Admin | Database | No | Yes | Yes | No | No | No | P2 | S | — | — | UI, QA |  | Does not exist | Appeal entity; admin resolves; patient my-reviews list | Appealed review hidden or marked pending per policy; admin decision audited | Not Started | Web
239 | 414 | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.6 | TRU-06 | Review appeal — doctors can appeal a review; patients manage reviews and raise an appeal | TRU-06.02 | API: doctor appeal; patient list/mine; admin resolve | New | Trust | §13 + §2.8 | Review appeal / My reviews & appeal | Doctors can appeal a review / Manage reviews and raise an appeal | Doctor + Patient + Admin | API | No | Yes | Yes | Yes | No | No | P2 | M | TRU-06.01 | T-238 (TRU-06.01) | UI, QA |  | Does not exist | Appeal entity; admin resolves; patient my-reviews list | Appealed review hidden or marked pending per policy; admin decision audited | Not Started | Web
240 | 417 | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.7 | TRU-07 | Ranking transparency — patients are shown why doctors are ranked as they are | TRU-07.01 | Ranking config (weights) — not a black box hardcoded sort | New | Trust | §13 + §2.2 | Ranking transparency / Ranking explanation | Patients are shown why doctors are ranked as they are / Transparent explanation of why doctors appear in a given order | Public + Patient app | Database | No | Yes | Yes | No | No | No | P1 | S | — | — | UI, QA |  | Does not exist | Documented ranking factors (verified, availability, fee, reviews, experience) + explain API/UI | Each search result has an explain link that matches the sort order | Not Started | Web
241 | 418 | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.7 | TRU-07 | Ranking transparency — patients are shown why doctors are ranked as they are | TRU-07.02 | GET doctors + GET ranking-explain/{doctorId} | New | Trust | §13 + §2.2 | Ranking transparency / Ranking explanation | Patients are shown why doctors are ranked as they are / Transparent explanation of why doctors appear in a given order | Public + Patient app | API | No | Yes | Yes | Yes | No | No | P1 | M | TRU-07.01 | T-240 (TRU-07.01) | UI, QA |  | Does not exist | Documented ranking factors (verified, availability, fee, reviews, experience) + explain API/UI | Each search result has an explain link that matches the sort order | Not Started | Web
242 | 421 | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.1 | WEB-01 | Product home page — complete public website presenting the service | WEB-01.01 | No schema | Existing Improvement | Patient Website | §4 | Product home page | Complete public website presenting the service | Patient Website | Database | No | Yes | Yes | No | No | No | P1 | S | — | — | UI, QA |  | HomeoJobLanding ~50%; Velzon leftovers; CTAs incomplete for book/trust/apps | Book CTA, verified doctors, consult+SaaS pricing teaser, app download placeholders | Unauthenticated user can go Home → Book without calling the clinic | Not Started | Web
243 | 422 | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.1 | WEB-01 | Product home page — complete public website presenting the service | WEB-01.02 | Reuse public doctor/fee APIs when live | Existing Improvement | Patient Website | §4 | Product home page | Complete public website presenting the service | Patient Website | API | No | Yes | Yes | Yes | No | No | P1 | M | WEB-01.01 | T-242 (WEB-01.01) | UI, QA |  | HomeoJobLanding ~50%; Velzon leftovers; CTAs incomplete for book/trust/apps | Book CTA, verified doctors, consult+SaaS pricing teaser, app download placeholders | Unauthenticated user can go Home → Book without calling the clinic | Not Started | Web
244 | 428 | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.3 | WEB-03 | Doctor discovery — browse and search verified doctors | WEB-03.01 | Public doctor search indexes (from Doctor + verification + fee + schedule) | New | Patient Website | §4 + §2.2 | Doctor discovery | Browse and search verified doctors | Patient Website | Database | No | Yes | Yes | No | No | No | P0 | S | — | — | UI, QA |  | Does not exist as a patient product (marketing only) | /book search: name, condition, category; filters availability, fee, experience, language, location | Only verified doctors; ranking explanation available (TRU-07) | Not Started | Web
245 | 429 | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.3 | WEB-03 | Doctor discovery — browse and search verified doctors | WEB-03.02 | GET /api/Public/Doctors + filters + profile | New | Patient Website | §4 + §2.2 | Doctor discovery | Browse and search verified doctors | Patient Website | API | No | Yes | Yes | Yes | No | No | P0 | M | WEB-03.01 | T-244 (WEB-03.01) | UI, QA |  | Does not exist as a patient product (marketing only) | /book search: name, condition, category; filters availability, fee, experience, language, location | Only verified doctors; ranking explanation available (TRU-07) | Not Started | Web
246 | 432 | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.4 | WEB-04 | Self-service booking — book an appointment online without calling the clinic | WEB-04.01 | Reuse Patient + Appointment; BookingToken; PatientAuth OTP | New | Patient Website | §4 + §2.3 | Self-service booking | Book an appointment online without calling the clinic | Patient Website | Database | No | Yes | Yes | No | No | No | P0 | S | — | — | UI, QA |  | Staff-only appointments | Funnel /book/:id/slots → review+consent → create Patient+Appointment; OTP; rate-limit; respect schedule + unpaid hold policy PRE-03 | Slot no longer free after confirmed booking; consent written to ConsentRecord | Not Started | Web
247 | 433 | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.4 | WEB-04 | Self-service booking — book an appointment online without calling the clinic | WEB-04.02 | Public: Doctors/{id}/Slots, Create, {bookingToken}; POST PatientAuth RequestOtp/VerifyOtp | New | Patient Website | §4 + §2.3 | Self-service booking | Book an appointment online without calling the clinic | Patient Website | API | No | Yes | Yes | Yes | No | No | P0 | M | WEB-04.01 | T-246 (WEB-04.01) | UI, QA |  | Staff-only appointments | Funnel /book/:id/slots → review+consent → create Patient+Appointment; OTP; rate-limit; respect schedule + unpaid hold policy PRE-03 | Slot no longer free after confirmed booking; consent written to ConsentRecord | Not Started | Web
248 | 438 | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.6 | WEB-06 | Contact & enquiry form — enquiries reach the admin team and are tracked | WEB-06.01 | Reuse EnquiryDetail; add Status/AssignedTo if missing | Existing Improvement | Patient Website | §4 + §15 | Contact & enquiry form | Enquiries reach the admin team and are tracked | Patient Website + Admin | Database | No | Yes | Yes | No | No | No | P1 | S | — | — | UI, QA |  | EnquiryDetail API exists; public form partial; admin inbox screen missing | Confirmation + enquiry id; /admin/enquiries inbox; optional convert to SupportTicket | Every website enquiry is visible to admin with status | Not Started | Web
249 | 439 | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.6 | WEB-06 | Contact & enquiry form — enquiries reach the admin team and are tracked | WEB-06.02 | Existing enquiry POST; admin list API if missing | Existing Improvement | Patient Website | §4 + §15 | Contact & enquiry form | Enquiries reach the admin team and are tracked | Patient Website + Admin | API | No | Yes | Yes | Yes | No | No | P1 | M | WEB-06.01 | T-248 (WEB-06.01) | UI, QA |  | EnquiryDetail API exists; public form partial; admin inbox screen missing | Confirmation + enquiry id; /admin/enquiries inbox; optional convert to SupportTicket | Every website enquiry is visible to admin with status | Not Started | Web
250 | 446 | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.9 | WEB-09 | Doctor self-registration — doctors apply to join the platform online | WEB-09.01 | Documents via TRU-01 tables | Existing Improvement | Patient Website | §4 | Doctor self-registration | Doctors apply to join the platform online | Public | Database | No | Yes | Yes | No | No | No | P0 | S | — | — | UI, QA |  | RegisterDoctor ~90%; activates immediately; no document upload | Document upload; pending-verification message; TRU-01 status Pending | New doctor cannot take paid public consults until Approved | Not Started | Web
251 | 447 | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.9 | WEB-09 | Doctor self-registration — doctors apply to join the platform online | WEB-09.02 | RegisterDoctor sets Pending; does not auto-activate practice for directory | Existing Improvement | Patient Website | §4 | Doctor self-registration | Doctors apply to join the platform online | Public | API | No | Yes | Yes | Yes | No | No | P0 | M | WEB-09.01 | T-250 (WEB-09.01) | UI, QA |  | RegisterDoctor ~90%; activates immediately; no document upload | Document upload; pending-verification message; TRU-01 status Pending | New doctor cannot take paid public consults until Approved | Not Started | Web
252 | 450 | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.10 | WEB-10 | Email activation — secure account activation by email link | WEB-10.01 | Activation token TTL if missing | Existing Improvement | Auth | §4 | Email activation | Secure account activation by email link | Public | Database | No | Yes | Yes | No | No | No | P1 | S | — | — | UI, QA |  | ActivateUser via /login?UserId= ~90%; align with verification; expiry/resend incomplete | Token expiry, resend, align with credentialing (activation ≠ verified practice) | Expired link fails; resend works; activated unverified still not in directory | Not Started | Web
253 | 451 | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.10 | WEB-10 | Email activation — secure account activation by email link | WEB-10.02 | Resend activation; do not treat activation as TRU-04 gate | Existing Improvement | Auth | §4 | Email activation | Secure account activation by email link | Public | API | No | Yes | Yes | Yes | No | No | P1 | M | WEB-10.01 | T-252 (WEB-10.01) | UI, QA |  | ActivateUser via /login?UserId= ~90%; align with verification; expiry/resend incomplete | Token expiry, resend, align with credentialing (activation ≠ verified practice) | Expired link fails; resend works; activated unverified still not in directory | Not Started | Web
254 | 454 | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.11 | WEB-11 | Waitlist offer — get offered a slot when one is freed by a cancellation (patient website + later app) | WEB-11.01 | DB: BookingWaitlist | New | Booking | §2.3 | Waitlist offer | Get offered a slot when one is freed by a cancellation | Patient Website + App | Database | No | Yes | Yes | No | No | No | P2 | S | — | — | UI, QA |  | Cancel hook stub in Phase 4; no waitlist records | BookingWaitlist; on cancel, offer FIFO; timeout | Cancelled slot offered to waitlisted patient before returning to open search | Not Started | Web
255 | 455 | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.11 | WEB-11 | Waitlist offer — get offered a slot when one is freed by a cancellation (patient website + later app) | WEB-11.02 | API: join waitlist; worker on CancelAppointment | New | Booking | §2.3 | Waitlist offer | Get offered a slot when one is freed by a cancellation | Patient Website + App | API | No | Yes | Yes | Yes | No | No | P2 | M | WEB-11.01 | T-254 (WEB-11.01) | UI, QA |  | Cancel hook stub in Phase 4; no waitlist records | BookingWaitlist; on cancel, offer FIFO; timeout | Cancelled slot offered to waitlisted patient before returning to open search | Not Started | Web
256 | 457 | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.11 | WEB-11 | Waitlist offer — get offered a slot when one is freed by a cancellation (patient website + later app) | WEB-11.04 | Notify SMS/push when Phase 12 exists | New Integration | Booking | §2.3 | Waitlist offer | Get offered a slot when one is freed by a cancellation | Patient Website + App | Integration | No | Yes | No | Yes | No | Yes | P2 | M | WEB-11.03 | — | UI, QA | WEB-11.03 | Cancel hook stub in Phase 4; no waitlist records | BookingWaitlist; on cancel, offer FIFO; timeout | Cancelled slot offered to waitlisted patient before returning to open search | Not Started | Web
257 | 461 | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.1 | ERX-01 | Potency module — every remedy carries a defined potency from a managed list, no free text | ERX-01.01 | DB: PotencyMaster; PrescriptionRemedyDetail.PotencyId | New | eRx | §11 | Potency module | Every remedy carries a defined potency, selected from a managed list — no free text | Doctor Web + Admin | Database | No | Yes | Yes | No | No | No | P0 | S | — | — | UI, QA |  | Dose saved as empty free-text dose: '' | PotencyMaster CRUD; PotencyId on PrescriptionRemedyDetail; stop empty Dose | Cannot sign eRx with missing potency | Not Started | Web
258 | 462 | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.1 | ERX-01 | Potency module — every remedy carries a defined potency from a managed list, no free text | ERX-01.02 | API: potency DDL; extend SavePrescriptionDetail | New | eRx | §11 | Potency module | Every remedy carries a defined potency, selected from a managed list — no free text | Doctor Web + Admin | API | No | Yes | Yes | Yes | No | No | P0 | M | ERX-01.01 | T-257 (ERX-01.01) | UI, QA |  | Dose saved as empty free-text dose: '' | PotencyMaster CRUD; PotencyId on PrescriptionRemedyDetail; stop empty Dose | Cannot sign eRx with missing potency | Not Started | Web
259 | 465 | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.2 | ERX-02 | Dosage details — frequency, duration and instructions recorded clearly | ERX-02.01 | DB: Frequency, Duration, Instructions on remedy line | New | eRx | §11 | Dosage details | Frequency, duration and instructions recorded clearly | Doctor Web Portal | Database | No | Yes | Yes | No | No | No | P0 | S | — | — | UI, QA |  | Unstructured/empty dose | Frequency, Duration, Instructions fields on each remedy line | Print/PDF shows frequency, duration, instructions | Not Started | Web
260 | 466 | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.2 | ERX-02 | Dosage details — frequency, duration and instructions recorded clearly | ERX-02.02 | Extend save/get Rx APIs | New | eRx | §11 | Dosage details | Frequency, duration and instructions recorded clearly | Doctor Web Portal | API | No | Yes | Yes | Yes | No | No | P0 | M | ERX-02.01 | T-259 (ERX-02.01) | UI, QA |  | Unstructured/empty dose | Frequency, Duration, Instructions fields on each remedy line | Print/PDF shows frequency, duration, instructions | Not Started | Web
261 | 469 | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.3 | ERX-03 | Visit notes kept separate from the prescription — private clinical notes never appear on the prescription given to the patient or pharmacy | ERX-03.01 | Extend AppointmentHistoryNote with NoteType, IsErxExcluded | New | eRx | §11 + §5.3 | Visit notes kept separate from the prescription | The doctor’s private clinical notes never appear on the prescription given to the patient or pharmacy | Doctor Web Portal | Database | No | Yes | Yes | No | No | No | P0 | S | — | — | UI, QA |  | History notes mixed into Rx modal tabs | Visit Notes panel outside Rx; NoteType; IsErxExcluded; eRx print has remedies+labs only | Patient PDF and pharmacy payload contain zero private note text | Not Started | Web
262 | 470 | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.3 | ERX-03 | Visit notes kept separate from the prescription — private clinical notes never appear on the prescription given to the patient or pharmacy | ERX-03.02 | GET /api/Erx/ByAppointment/{id} returns snapshot without notes | New | eRx | §11 + §5.3 | Visit notes kept separate from the prescription | The doctor’s private clinical notes never appear on the prescription given to the patient or pharmacy | Doctor Web Portal | API | No | Yes | Yes | Yes | No | No | P0 | M | ERX-03.01 | T-261 (ERX-03.01) | UI, QA |  | History notes mixed into Rx modal tabs | Visit Notes panel outside Rx; NoteType; IsErxExcluded; eRx print has remedies+labs only | Patient PDF and pharmacy payload contain zero private note text | Not Started | Web
263 | 473 | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.4 | ERX-04 | Signed digital prescription — issued and locked once signed, so it cannot be altered afterwards | ERX-04.01 | DB: ErxSnapshot, ErxSnapshotItem (codes+names stored; patient API returns codes until pharmacy accept) | New | eRx | §11 + §2.5 + §5.3 | Signed digital prescription | Issued and locked once signed, so it cannot be altered afterwards / Official prescription issued by the doctor | Doctor Web | Database | No | Yes | Yes | No | No | No | P0 | S | — | — | UI, QA |  | SavePrescriptionDetail overwritable; no lock/sign | ErxSnapshot immutable on sign; subsequent edits create a new unsigned draft not a silent mutate | Signed snapshot hash stable; UI cannot edit locked lines | Not Started | Web
264 | 474 | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.4 | ERX-04 | Signed digital prescription — issued and locked once signed, so it cannot be altered afterwards | ERX-04.02 | API: SignErx; GetErx; reject mutate of signed snapshot | New | eRx | §11 + §2.5 + §5.3 | Signed digital prescription | Issued and locked once signed, so it cannot be altered afterwards / Official prescription issued by the doctor | Doctor Web | API | No | Yes | Yes | Yes | No | No | P0 | M | ERX-04.01 | T-263 (ERX-04.01) | UI, QA |  | SavePrescriptionDetail overwritable; no lock/sign | ErxSnapshot immutable on sign; subsequent edits create a new unsigned draft not a silent mutate | Signed snapshot hash stable; UI cannot edit locked lines | Not Started | Web
265 | 477 | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.5 | ERX-05 | Prescription history — every prescription stored against the patient and visit | ERX-05.01 | GET history by patient; by appointment | New | eRx | §11 | Prescription history | Every prescription stored against the patient and visit | Doctor + Patient | API | No | Yes | No | Yes | No | No | P1 | S | — | — | UI, QA |  | Rx saved per appointment but no signed history product | List snapshots by PatientId; open past visit eRx | All signed eRx retrievable by patient and treating doctor | Not Started | Web
266 | 480 | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.6 | ERX-06 | Patient view of prescription in app — patient sees the prescription immediately (codes until pharmacy accept) | ERX-06.01 | Patient-authorised GET Erx; apply code protection ERX-08 | New | eRx | §11 + §2.5 | Patient view in app | Patient sees the prescription immediately in the app | Patient App + Website | API | No | Yes | No | Yes | No | No | P0 | S | — | — | UI, QA |  | No patient surface | Patient GET eRx by appointment; names redacted until Phase 14 accept; website optional view | Immediately after sign, patient API returns codes (or names if no HomeoMeds order required for in-clinic dispense policy — document) | Not Started | Web
267 | 483 | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.7 | ERX-07 | Print & PDF — printable and downloadable prescription | ERX-07.01 | PDF renderer from ErxSnapshot; store via SEC-09 | New | eRx | §11 | Print & PDF | Printable and downloadable prescription | Doctor + Patient | API | No | Yes | No | Yes | No | No | P1 | M | — | — | UI, QA |  | No eRx PDF | Patient copy without notes; doctor copy may include letterhead; SecureDocument store | PDF matches signed snapshot; notes absent on patient copy | Not Started | Web
268 | 486 | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.8 | ERX-08 | Remedy code protection — patient sees remedy codes rather than names until a licensed pharmacy accepts the order | ERX-08.01 | Assign stable remedy codes on snapshot items | New | eRx | §11 | Remedy code protection | The patient sees remedy codes rather than remedy names until a licensed pharmacy accepts the order | Patient | API | No | Yes | Yes | No | No | No | P0 | M | — | — | QA |  | Does not exist | Code map on snapshot items; patient serializer strips names; doctor always sees names | Patient JSON has no remedy name fields until PharmacyAccepted | Not Started | Web
269 | 488 | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.9 | ERX-09 | Reveal on pharmacy acceptance — names and price revealed; payment QR or link generated (implemented with HomeoMeds; contract now) | ERX-09.01 | API contract: AcceptOrder(OTP) → reveal names; Quote → PayQR | New | eRx | §11 + §12 | Reveal on pharmacy acceptance | Once a pharmacy accepts and verifies by OTP, the remedy names and price are revealed and a payment QR or link is generated | Patient + Pharmacy | API | No | Yes | No | Yes | No | No | P0 | S | — | — | — |  | Does not exist | Flag PharmacyAccepted on order; patient GET starts returning names; CreateMedicine payment link; full UI in Phase 14 | Names appear only after OTP accept; QR/link only after quote | Not Started | Web
270 | 489 | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.9 | ERX-09 | Reveal on pharmacy acceptance — names and price revealed; payment QR or link generated (implemented with HomeoMeds; contract now) | ERX-09.02 | Implement fully with MED-* in Phase 14 — do not reveal names from doctor sign alone | New | eRx | §11 + §12 | Reveal on pharmacy acceptance | Once a pharmacy accepts and verifies by OTP, the remedy names and price are revealed and a payment QR or link is generated | Patient + Pharmacy | Architecture | No | Yes | No | No | No | No | P0 | S | ERX-09.01 | T-269 (ERX-09.01) | — |  | Does not exist | Flag PharmacyAccepted on order; patient GET starts returning names; CreateMedicine payment link; full UI in Phase 14 | Names appear only after OTP accept; QR/link only after quote | Not Started | Web
271 | 490 | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.10 | ERX-10 | Repeat prescription / refill — patient requests; doctor approves or rejects from the mobile app (inbox on web too) | ERX-10.01 | DB: RefillRequest | New | eRx | §11 + §3 + §2.7 | Repeat prescription / refill | Patient requests a refill; doctor approves or rejects from the mobile app | Patient + Doctor mobile + Doctor web | Database | No | Yes | Yes | No | No | No | P1 | S | — | — | UI, QA |  | Does not exist | RefillRequest against ErxSnapshot; doctor inbox; no case-taking on mobile | Reject/approve audited; approved refill creates a new order draft not an editable old snapshot | Not Started | Web
272 | 491 | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.10 | ERX-10 | Repeat prescription / refill — patient requests; doctor approves or rejects from the mobile app (inbox on web too) | ERX-10.02 | API: patient request; doctor inbox; approve/reject | New | eRx | §11 + §3 + §2.7 | Repeat prescription / refill | Patient requests a refill; doctor approves or rejects from the mobile app | Patient + Doctor mobile + Doctor web | API | No | Yes | Yes | Yes | No | No | P1 | M | ERX-10.01 | T-271 (ERX-10.01) | UI, QA |  | Does not exist | RefillRequest against ErxSnapshot; doctor inbox; no case-taking on mobile | Reject/approve audited; approved refill creates a new order draft not an editable old snapshot | Not Started | Web
273 | 494 | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.11 | ERX-11 | Lab orders alongside the prescription (keep existing labs on eRx snapshot) | ERX-11.01 | Copy lab orders into ErxSnapshot on sign | Existing Improvement | eRx | §11 | Lab orders | Tests ordered alongside the prescription | Doctor Web | API | No | Yes | No | No | No | No | P1 | S | — | — | QA |  | Labs on Rx modal live | Include lab orders in signed snapshot; still not on private notes | Signed eRx PDF lists labs; results stay clinical-side | Not Started | Web
274 | 496 | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.1 | TEL-01 | Doctor availability — online or offline status and working hours | TEL-01.01 | DB: TeleAvailability (Online/Offline, LastHeartbeat) | New | Telemedicine | §10 + §3 | Doctor availability | Doctor sets online or offline status and working hours | Doctor Web + Doctor App | Database | No | Yes | Yes | No | No | No | P0 | S | — | — | UI, QA |  | E-CONSULT status + WhatsApp video stub only; no availability | TeleAvailability + heartbeat; working hours reuse daily schedule | Offline doctor cannot be offered instant consult | Not Started | Web
275 | 497 | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.1 | TEL-01 | Doctor availability — online or offline status and working hours | TEL-01.02 | API: SET/GET availability; public GET by doctorId | New | Telemedicine | §10 + §3 | Doctor availability | Doctor sets online or offline status and working hours | Doctor Web + Doctor App | API | No | Yes | Yes | Yes | No | No | P0 | M | TEL-01.01 | T-274 (TEL-01.01) | UI, QA |  | E-CONSULT status + WhatsApp video stub only; no availability | TeleAvailability + heartbeat; working hours reuse daily schedule | Offline doctor cannot be offered instant consult | Not Started | Web
276 | 500 | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.2 | TEL-02 | Telemedicine waiting queue — who is waiting, how long, whether they have paid | TEL-02.01 | Queue query on E-CONSULT + PaymentStatus + join time | New | Telemedicine | §10 + §3 | Telemedicine waiting queue | Doctor sees who is waiting, for how long, and whether they have paid | Doctor Web + App | Database | No | Yes | Yes | No | No | No | P0 | S | — | — | UI, QA |  | E-CONSULT list only | Queue by doctor + Online + paid/confirmed; wait time; Join | Unpaid patients do not join if policy requires PAID | Not Started | Web
277 | 501 | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.2 | TEL-02 | Telemedicine waiting queue — who is waiting, how long, whether they have paid | TEL-02.02 | GET Tele/Queue; POST start session | New | Telemedicine | §10 + §3 | Telemedicine waiting queue | Doctor sees who is waiting, for how long, and whether they have paid | Doctor Web + App | API | No | Yes | Yes | Yes | No | No | P0 | M | TEL-02.01 | T-276 (TEL-02.01) | UI, QA |  | E-CONSULT list only | Queue by doctor + Online + paid/confirmed; wait time; Join | Unpaid patients do not join if policy requires PAID | Not Started | Web
278 | 503 | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.2 | TEL-02 | Telemedicine waiting queue — who is waiting, how long, whether they have paid | TEL-02.04 | SignalR/poll | New Integration | Telemedicine | §10 + §3 | Telemedicine waiting queue | Doctor sees who is waiting, for how long, and whether they have paid | Doctor Web + App | Integration | No | Yes | No | Yes | No | Yes | P0 | M | TEL-02.03 | — | UI, QA | TEL-02.03 | E-CONSULT list only | Queue by doctor + Online + paid/confirmed; wait time; Join | Unpaid patients do not join if policy requires PAID | Not Started | Web
279 | 505 | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.3 | TEL-03 | Video consultation in browser — doctor consults directly from the web portal | TEL-03.01 | DB: TeleSession (PatientAppId, RoomId, Status) | New | Telemedicine | §10 | Video consultation in browser | Doctor consults directly from the web portal | Doctor Web Portal | Database | No | Yes | Yes | No | No | No | P0 | S | — | — | UI, QA |  | SweetAlert WhatsApp stub | /teleconsult/:sessionId in-browser video; replace stub; vendor from PRE-03 | Doctor and patient in same room linked to PatientAppId | Not Started | Web
280 | 506 | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.3 | TEL-03 | Video consultation in browser — doctor consults directly from the web portal | TEL-03.02 | API: create/end session; vendor tokens | New | Telemedicine | §10 | Video consultation in browser | Doctor consults directly from the web portal | Doctor Web Portal | API | No | Yes | Yes | Yes | No | No | P0 | M | TEL-03.01 | T-279 (TEL-03.01) | UI, QA |  | SweetAlert WhatsApp stub | /teleconsult/:sessionId in-browser video; replace stub; vendor from PRE-03 | Doctor and patient in same room linked to PatientAppId | Not Started | Web
281 | 508 | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.3 | TEL-03 | Video consultation in browser — doctor consults directly from the web portal | TEL-03.04 | Video SDK (Agora/Twilio/Daily) | New Integration | Telemedicine | §10 | Video consultation in browser | Doctor consults directly from the web portal | Doctor Web Portal | Integration | No | Yes | No | Yes | No | Yes | P0 | M | TEL-03.03 | — | UI, QA | TEL-03.03 | SweetAlert WhatsApp stub | /teleconsult/:sessionId in-browser video; replace stub; vendor from PRE-03 | Doctor and patient in same room linked to PatientAppId | Not Started | Web
282 | 510 | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.4 | TEL-04 | Video consultation on mobile — doctor and patient both consult from the app (apps in 16–17; same session tokens) | TEL-04.01 | Token API must be client-agnostic (web and mobile) | New | Telemedicine | §10 + §2.4 + §3 | Video consultation on mobile | Doctor and patient both consult from the app / Face-to-face consultation from home / Start the video or audio consultation from the phone | Patient App + Doctor App | API | No | Yes | No | Yes | Yes | No | P0 | S | — | — | QA |  | No apps | Same TeleSession tokens; mobile join implemented in Phases 16–17 against this API | Web doctor + mobile patient in one session | Not Started | Web
283 | 514 | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.6 | TEL-06 | Waiting room — patient waits with live status until the doctor joins | TEL-06.01 | Session status events | New | Telemedicine | §10 + §2.4 | Waiting room | Patient waits with live status / Wait with live status until the doctor joins | Patient | Database | No | Yes | Yes | No | No | No | P1 | S | — | — | UI, QA |  | Does not exist | Waiting room page: position, doctor online, paid, estimated wait | Status updates without refresh (poll/SignalR) | Not Started | Web
284 | 515 | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.6 | TEL-06 | Waiting room — patient waits with live status until the doctor joins | TEL-06.02 | GET session status for patient token | New | Telemedicine | §10 + §2.4 | Waiting room | Patient waits with live status / Wait with live status until the doctor joins | Patient | API | No | Yes | Yes | Yes | No | No | P1 | M | TEL-06.01 | T-283 (TEL-06.01) | UI, QA |  | Does not exist | Waiting room page: position, doctor online, paid, estimated wait | Status updates without refresh (poll/SignalR) | Not Started | Web
285 | 518 | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.7 | TEL-07 | Recording consent — consent captured before the consultation; no recording without it | TEL-07.01 | Write ConsentRecord TeleRecording; TeleConsentLog events | New | Telemedicine | §10 + §2.4 + §17 | Recording consent | Consent captured before the consultation; no recording without it / Explicit consent requested before any recording | Patient + Doctor | Database | No | Yes | Yes | No | No | No | P0 | S | — | — | UI, QA |  | AudioCaseConsentLog only for audio case taking | ConsentRecord type TeleRecording; block record if declined; both sides see status | Recording pipeline cannot start if consent denied | Not Started | Web
286 | 519 | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.7 | TEL-07 | Recording consent — consent captured before the consultation; no recording without it | TEL-07.02 | API: capture consent; session.recordAllowed | New | Telemedicine | §10 + §2.4 + §17 | Recording consent | Consent captured before the consultation; no recording without it / Explicit consent requested before any recording | Patient + Doctor | API | No | Yes | Yes | Yes | No | No | P0 | M | TEL-07.01 | T-285 (TEL-07.01) | UI, QA |  | AudioCaseConsentLog only for audio case taking | ConsentRecord type TeleRecording; block record if declined; both sides see status | Recording pipeline cannot start if consent denied | Not Started | Web
287 | 522 | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.8 | TEL-08 | Rejoin after dropped call — either side can rejoin the same consultation | TEL-08.01 | API: Rejoin issues token if Status=Active | New | Telemedicine | §10 + §2.4 | Rejoin after dropped call | Either side can rejoin the same consultation / Rejoin the same consultation if the connection drops | Doctor + Patient | API | No | Yes | No | Yes | No | No | P0 | S | — | — | UI, QA |  | Does not exist | Session Active until End; rejoin tokens; dashboard Rejoin | Drop and rejoin same PatientAppId session; End prevents rejoin | Not Started | Web
288 | 525 | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.9 | TEL-09 | Join failure handling — clear fallback if the call cannot connect, with options to retry | TEL-09.01 | Standardise join error codes; log TeleSessionEvent | New | Telemedicine | §10 + §2.4 | Join failure handling / Fallback & join failure handling | Clear fallback if the call cannot connect / Clear guidance if the call fails, with options to retry | Doctor + Patient | API | No | Yes | No | No | No | No | P1 | S | — | — | UI, QA |  | Does not exist | Error codes; retry; support ticket deep link later; do not silently fail | Every join failure has a user-visible next action | Not Started | Web
289 | 528 | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.10 | TEL-10 | Case-linked chat — chat attached to the consultation record, not a loose message thread | TEL-10.01 | DB: TeleChatMessage (SessionId, PatientAppId, Body, At) | New | Telemedicine | §10 + §2.4 | Case-linked chat | Chat attached to the consultation record / Chat tied to the consultation, not a loose message thread | Doctor + Patient | Database | No | Yes | Yes | No | No | No | P1 | S | — | — | UI, QA |  | Does not exist | Messages keyed by TeleSession/PatientAppId; retained with the case | Chat not visible on a different appointment | Not Started | Web
290 | 529 | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.10 | TEL-10 | Case-linked chat — chat attached to the consultation record, not a loose message thread | TEL-10.02 | API: post/list; doctor and patient only | New | Telemedicine | §10 + §2.4 | Case-linked chat | Chat attached to the consultation record / Chat tied to the consultation, not a loose message thread | Doctor + Patient | API | No | Yes | Yes | Yes | No | No | P1 | M | TEL-10.01 | T-289 (TEL-10.01) | UI, QA |  | Does not exist | Messages keyed by TeleSession/PatientAppId; retained with the case | Chat not visible on a different appointment | Not Started | Web
291 | 532 | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.11 | TEL-11 | Consultation summary — issued to the patient at the end of the call | TEL-11.01 | DB: ConsultationSummary (PatientAppId, Text, At) | New | Telemedicine | §10 + §2.4 | Consultation summary | Issued to the patient at the end of the call / Written summary available immediately after the call | Patient + Doctor | Database | No | Yes | Yes | No | No | No | P1 | S | — | — | UI, QA |  | Does not exist | Doctor submits summary (not private notes); patient sees immediately; may share eRx id | Summary available without waiting for signed eRx if doctor issues it first | Not Started | Web
292 | 533 | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.11 | TEL-11 | Consultation summary — issued to the patient at the end of the call | TEL-11.02 | API: doctor PUT; patient GET | New | Telemedicine | §10 + §2.4 | Consultation summary | Issued to the patient at the end of the call / Written summary available immediately after the call | Patient + Doctor | API | No | Yes | Yes | Yes | No | No | P1 | M | TEL-11.01 | T-291 (TEL-11.01) | UI, QA |  | Does not exist | Doctor submits summary (not private notes); patient sees immediately; may share eRx id | Summary available without waiting for signed eRx if doctor issues it first | Not Started | Web
293 | 536 | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.12 | TEL-12 | Instant consultation — patient requests an immediate consultation with an available doctor | TEL-12.01 | DB: InstantConsultRequest, DoctorOffer | New | Telemedicine | §10 + §2.3 | Instant consultation / Instant consult request / Queue & doctor offer | Patient can request an immediate consultation with an available doctor / See position in queue and accept an offered doctor | Patient + Doctor | Database | No | Yes | Yes | No | No | No | P1 | S | — | — | UI, QA |  | Does not exist | Instant request pool; offer doctor; patient accepts; optional surcharge from fee config | Offline doctors never offered; patient can decline an offered doctor | Not Started | Web
294 | 537 | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.12 | TEL-12 | Instant consultation — patient requests an immediate consultation with an available doctor | TEL-12.02 | API: request, match, offer, accept, queue position | New | Telemedicine | §10 + §2.3 | Instant consultation / Instant consult request / Queue & doctor offer | Patient can request an immediate consultation with an available doctor / See position in queue and accept an offered doctor | Patient + Doctor | API | No | Yes | Yes | Yes | No | No | P1 | M | TEL-12.01 | T-293 (TEL-12.01) | UI, QA |  | Does not exist | Instant request pool; offer doctor; patient accepts; optional surcharge from fee config | Offline doctors never offered; patient can decline an offered doctor | Not Started | Web
295 | 540 | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.1 | COM-01 | SMS — appointment confirmation, registration confirmation, doctor-unavailable, OTP, reschedule and cancellation | COM-01.01 | DB: SmsTemplate, SmsMessageLog; Patient.SmsOptOut | New | Notifications | §14 | SMS | Appointment confirmation, registration confirmation, doctor-unavailable notice, OTP, reschedule and cancellation alerts | Shared | Database | No | Yes | Yes | No | No | No | P0 | S | — | — | UI, QA |  | No SMS provider; WhatsApp exists separately | SmsProvider + templates + DLT; event hooks; DND/opt-out on Patient | Each listed event can send SMS; notify failure does not roll back the business transaction | Not Started | Web
296 | 541 | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.1 | COM-01 | SMS — appointment confirmation, registration confirmation, doctor-unavailable, OTP, reschedule and cancellation | COM-01.02 | API: Templates CRUD; Send; History; event worker | New | Notifications | §14 | SMS | Appointment confirmation, registration confirmation, doctor-unavailable notice, OTP, reschedule and cancellation alerts | Shared | API | No | Yes | Yes | Yes | No | No | P0 | M | COM-01.01 | T-295 (COM-01.01) | UI, QA |  | No SMS provider; WhatsApp exists separately | SmsProvider + templates + DLT; event hooks; DND/opt-out on Patient | Each listed event can send SMS; notify failure does not roll back the business transaction | Not Started | Web
297 | 543 | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.1 | COM-01 | SMS — appointment confirmation, registration confirmation, doctor-unavailable, OTP, reschedule and cancellation | COM-01.04 | MSG91/Twilio/etc. from PRE-03 | New Integration | Notifications | §14 | SMS | Appointment confirmation, registration confirmation, doctor-unavailable notice, OTP, reschedule and cancellation alerts | Shared | Integration | No | Yes | No | Yes | No | Yes | P0 | M | COM-01.03 | — | UI, QA | COM-01.03 | No SMS provider; WhatsApp exists separately | SmsProvider + templates + DLT; event hooks; DND/opt-out on Patient | Each listed event can send SMS; notify failure does not roll back the business transaction | Not Started | Web
298 | 545 | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.2 | COM-02 | WhatsApp — templates, offers, health tips and bulk messaging with delivery reports and opt-out (complete remaining ~50%) | COM-02.01 | Extend WhatsApp log if delivery receipts not stored | Existing Improvement | Notifications | §14 | WhatsApp | Templates, offers, health tips and bulk messaging to patients, with delivery reports and opt-out | Doctor Web | Database | No | Yes | Yes | No | No | No | P1 | S | — | — | UI, QA |  | Meta Cloud send/templates/campaigns live; bulk/opt-in/analytics incomplete | Finish bulk queue UX, template approval states, delivery reports, opt-out | Bulk campaign shows delivered/failed; opted-out patients excluded | Not Started | Web
299 | 546 | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.2 | COM-02 | WhatsApp — templates, offers, health tips and bulk messaging with delivery reports and opt-out (complete remaining ~50%) | COM-02.02 | Finish bulk worker + receipt webhook | Existing Improvement | Notifications | §14 | WhatsApp | Templates, offers, health tips and bulk messaging to patients, with delivery reports and opt-out | Doctor Web | API | No | Yes | Yes | Yes | No | No | P1 | M | COM-02.01 | T-298 (COM-02.01) | UI, QA |  | Meta Cloud send/templates/campaigns live; bulk/opt-in/analytics incomplete | Finish bulk queue UX, template approval states, delivery reports, opt-out | Bulk campaign shows delivered/failed; opted-out patients excluded | Not Started | Web
300 | 549 | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.3 | COM-03 | Push notifications — booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests | COM-03.01 | DB: DeviceToken, AppNotification | New | Notifications | §14 + §2.9 + §3 | Push notifications | Booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests / Patient waiting, new booking, reschedule, cancellation, refill request, payment received | Patient App + Doctor App | Database | No | Yes | Yes | No | No | No | P0 | S | — | — | UI, QA |  | Does not exist | DeviceToken + FCM/APNs; event fan-out; apps register tokens in Phases 16–17 | Each listed event has a template; unregister on logout | Not Started | Web
301 | 550 | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.3 | COM-03 | Push notifications — booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests | COM-03.02 | API: Devices/Register; Notifications/Send; list | New | Notifications | §14 + §2.9 + §3 | Push notifications | Booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests / Patient waiting, new booking, reschedule, cancellation, refill request, payment received | Patient App + Doctor App | API | No | Yes | Yes | Yes | No | No | P0 | M | COM-03.01 | T-300 (COM-03.01) | UI, QA |  | Does not exist | DeviceToken + FCM/APNs; event fan-out; apps register tokens in Phases 16–17 | Each listed event has a template; unregister on logout | Not Started | Web
302 | 552 | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.3 | COM-03 | Push notifications — booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests | COM-03.04 | FCM + APNs | New Integration | Notifications | §14 + §2.9 + §3 | Push notifications | Booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests / Patient waiting, new booking, reschedule, cancellation, refill request, payment received | Patient App + Doctor App | Integration | No | Yes | No | Yes | No | Yes | P0 | M | COM-03.03 | — | UI, QA | COM-03.03 | Does not exist | DeviceToken + FCM/APNs; event fan-out; apps register tokens in Phases 16–17 | Each listed event has a template; unregister on logout | Not Started | Web
303 | 554 | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.4 | COM-04 | Email — registration, activation, password reset, invoices and receipts | COM-04.01 | EmailMessageLog if missing | Existing Improvement | Notifications | §14 | Email | Registration, activation, password reset, invoices and receipts | Shared | Database | No | Yes | Yes | No | No | No | P1 | S | — | — | UI, QA |  | SMTP used for activation/forgot (plaintext issue fixed in Phase 0); no invoice email | Template emails for listed events; invoice PDF attach via SEC-09 | Each listed event has an email; bounce logged | Not Started | Web
304 | 555 | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.4 | COM-04 | Email — registration, activation, password reset, invoices and receipts | COM-04.02 | Send invoice/receipt email on PAID; keep activation/reset | Existing Improvement | Notifications | §14 | Email | Registration, activation, password reset, invoices and receipts | Shared | API | No | Yes | Yes | Yes | No | No | P1 | M | COM-04.01 | T-303 (COM-04.01) | UI, QA |  | SMTP used for activation/forgot (plaintext issue fixed in Phase 0); no invoice email | Template emails for listed events; invoice PDF attach via SEC-09 | Each listed event has an email; bounce logged | Not Started | Web
305 | 558 | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.5 | COM-05 | In-app notification centre — all alerts collected in one place for patients and doctors | COM-05.01 | Reuse AppNotification | New | Notifications | §14 + §2.8 | In-app notification centre / Notifications centre | All alerts collected in one place for patients and doctors / All alerts in one place | Patient App + Doctor Web/App | Database | No | Yes | Yes | No | No | No | P1 | S | — | — | UI, QA |  | Does not exist (Velzon notification demo is not product) | AppNotification inbox; mark read; do not use Velzon demo notifications | Same events as push appear in-app if push is denied | Not Started | Web
306 | 559 | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.5 | COM-05 | In-app notification centre — all alerts collected in one place for patients and doctors | COM-05.02 | GET/PATCH notifications | New | Notifications | §14 + §2.8 | In-app notification centre / Notifications centre | All alerts collected in one place for patients and doctors / All alerts in one place | Patient App + Doctor Web/App | API | No | Yes | Yes | Yes | No | No | P1 | M | COM-05.01 | T-305 (COM-05.01) | UI, QA |  | Does not exist (Velzon notification demo is not product) | AppNotification inbox; mark read; do not use Velzon demo notifications | Same events as push appear in-app if push is denied | Not Started | Web
307 | 562 | Web | 13 | Phase 13 — Support & help desk (PDF §15) | 13.1 | SUP-01 | Patient support tickets — patients raise issues from the app and track them | SUP-01.01 | DB: SupportTicket, SupportTicketMessage, SupportTicketAttachment | New | Support | §15 + §2.9 | Patient support tickets / Help centre & support tickets | Patients raise issues from the app and track them to resolution | Patient App + Admin | Database | No | Yes | Yes | No | No | No | P1 | S | — | — | UI, QA |  | Does not exist; EnquiryDetail is not tickets; Velzon tickets demo ignore | SupportTicket reporter=Patient; status track; not Enquiry, not Velzon /apps-tickets-* | Patient sees status changes; cannot see other patients’ tickets | Not Started | Web
308 | 563 | Web | 13 | Phase 13 — Support & help desk (PDF §15) | 13.1 | SUP-01 | Patient support tickets — patients raise issues from the app and track them | SUP-01.02 | API: create/list/mine for patient | New | Support | §15 + §2.9 | Patient support tickets / Help centre & support tickets | Patients raise issues from the app and track them to resolution | Patient App + Admin | API | No | Yes | Yes | Yes | No | No | P1 | M | SUP-01.01 | T-307 (SUP-01.01) | UI, QA |  | Does not exist; EnquiryDetail is not tickets; Velzon tickets demo ignore | SupportTicket reporter=Patient; status track; not Enquiry, not Velzon /apps-tickets-* | Patient sees status changes; cannot see other patients’ tickets | Not Started | Web
309 | 566 | Web | 13 | Phase 13 — Support & help desk (PDF §15) | 13.2 | SUP-02 | Doctor support tickets — doctors raise issues from the portal | SUP-02.01 | Reuse SupportTicket with ReporterRole=Doctor | New | Support | §15 | Doctor support tickets | Doctors raise issues from the portal | Doctor Web + Admin | API | No | Yes | No | Yes | No | No | P1 | S | — | — | UI, QA |  | Does not exist | Same ticket tables; reporter=Doctor | Doctor portal has Raise issue; tracks to resolution | Not Started | Web
310 | 569 | Web | 13 | Phase 13 — Support & help desk (PDF §15) | 13.3 | SUP-03 | Admin issue queue — all issues in one queue with priority, assignment and status | SUP-03.01 | Extend ticket with Priority, Assignee, SLA | New | Support | §15 + §7.2 | Admin issue queue / Support ticket queue | All issues in one queue with priority, assignment and status / All patient and doctor issues in one queue with assignment and resolution | Admin Portal | Database | No | Yes | Yes | No | No | No | P1 | S | — | — | UI, QA |  | Does not exist | /admin/support-tickets; SLA timestamps; assign | Patient and doctor tickets in one queue; assignable | Not Started | Web
311 | 570 | Web | 13 | Phase 13 — Support & help desk (PDF §15) | 13.3 | SUP-03 | Admin issue queue — all issues in one queue with priority, assignment and status | SUP-03.02 | Admin list/filter/assign/status | New | Support | §15 + §7.2 | Admin issue queue / Support ticket queue | All issues in one queue with priority, assignment and status / All patient and doctor issues in one queue with assignment and resolution | Admin Portal | API | No | Yes | Yes | Yes | No | No | P1 | M | SUP-03.01 | T-310 (SUP-03.01) | UI, QA |  | Does not exist | /admin/support-tickets; SLA timestamps; assign | Patient and doctor tickets in one queue; assignable | Not Started | Web
312 | 573 | Web | 13 | Phase 13 — Support & help desk (PDF §15) | 13.4 | SUP-04 | Ticket conversation — full message thread with attachments | SUP-04.01 | API: messages CRUD + attachment | New | Support | §15 | Ticket conversation | Full message thread with attachments | Admin + Doctor + Patient | API | No | Yes | No | Yes | No | No | P1 | M | — | — | UI, QA |  | Does not exist | Threaded messages + SEC-09 attachments | Both sides see the same thread order | Not Started | Web
313 | 578 | Web | 13 | Phase 13 — Support & help desk (PDF §15) | 13.6 | SUP-06 | Help centre — self-service help content for patients | SUP-06.01 | HelpArticle table or reuse blog category=help | New | Support | §15 + §2.9 | Help centre | Self-service help content for patients | Patient Website + App | Database | No | Yes | Yes | No | No | No | P2 | S | — | — | UI, QA |  | Does not exist | CMS articles or static help; searchable | Patient can open help without raising a ticket | Not Started | Web
314 | 579 | Web | 13 | Phase 13 — Support & help desk (PDF §15) | 13.6 | SUP-06 | Help centre — self-service help content for patients | SUP-06.02 | Public GET help articles | New | Support | §15 + §2.9 | Help centre | Self-service help content for patients | Patient Website + App | API | No | Yes | Yes | Yes | No | No | P2 | M | SUP-06.01 | T-313 (SUP-06.01) | UI, QA |  | Does not exist | CMS articles or static help; searchable | Patient can open help without raising a ticket | Not Started | Web
315 | 582 | Web | 13 | Phase 13 — Support & help desk (PDF §15) | 13.7 | SUP-07 | Assisted booking — help for patients who need support booking | SUP-07.01 | Flag BookingChannel=Assisted; AssistedRequest ticket type | New | Support | §15 + §2.9 | Assisted booking | Support for patients who need help booking / Help for patients who need support booking | Support + Reception + Patient | Database | No | Yes | Yes | No | No | No | P2 | S | — | — | UI, QA |  | Does not exist | Staff (admin/support/reception) can complete public booking on behalf of a patient with audit; patient app CTA to request assistance | Assisted booking appears in audit as staff-created; patient still owns the appointment | Not Started | Web
316 | 583 | Web | 13 | Phase 13 — Support & help desk (PDF §15) | 13.7 | SUP-07 | Assisted booking — help for patients who need support booking | SUP-07.02 | API: request assistance; staff completes WEB-04 create on behalf | New | Support | §15 + §2.9 | Assisted booking | Support for patients who need help booking / Help for patients who need support booking | Support + Reception + Patient | API | No | Yes | Yes | Yes | No | No | P2 | M | SUP-07.01 | T-315 (SUP-07.01) | UI, QA |  | Does not exist | Staff (admin/support/reception) can complete public booking on behalf of a patient with audit; patient app CTA to request assistance | Assisted booking appears in audit as staff-created; patient still owns the appointment | Not Started | Web
317 | 586 | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.1 | MED-01 | Pharmacy partner onboarding — licensed premises, licence records, activation checklist | MED-01.01 | DB: PharmacyPartner, PharmacyLicence, activation checklist fields | New | HomeoMeds | §12 + §7.2 | Pharmacy partner onboarding / Pharmacy partner management | Licensed premises registered with licence records and an activation checklist / Onboard and activate licensed pharmacies | Pharmacy + Admin | Database | No | Yes | Yes | No | No | No | P0 | S | — | — | UI, QA |  | Does not exist | PharmacyPartner + licences; admin activation; pharmacy console login | Unactivated pharmacy cannot receive orders | Not Started | Web
318 | 587 | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.1 | MED-01 | Pharmacy partner onboarding — licensed premises, licence records, activation checklist | MED-01.02 | API: onboard, admin activate, pharmacy login role | New | HomeoMeds | §12 + §7.2 | Pharmacy partner onboarding / Pharmacy partner management | Licensed premises registered with licence records and an activation checklist / Onboard and activate licensed pharmacies | Pharmacy + Admin | API | No | Yes | Yes | Yes | No | No | P0 | M | MED-01.01 | T-317 (MED-01.01) | UI, QA |  | Does not exist | PharmacyPartner + licences; admin activation; pharmacy console login | Unactivated pharmacy cannot receive orders | Not Started | Web
319 | 590 | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.2 | MED-02 | Licence gating — expired or suspended licences blocked automatically from receiving orders | MED-02.01 | Job: mark licence expired/suspended; exclude from routing | New | HomeoMeds | §12 | Licence gating | Pharmacies with expired or suspended licences are blocked automatically from receiving orders | Backend | Backend | No | Yes | Yes | No | No | No | P0 | M | — | — | UI, QA |  | Does not exist | Scheduler; routing skip; banner on pharmacy console | Expired licence receives zero new orders the next minute | Not Started | Web
320 | 593 | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.3 | MED-03 | Fulfilment consent & pharmacy selection — patient chooses the seller and consents before the prescription is shared | MED-03.01 | Consent + selected PharmacyPartnerId on MedicineOrder | New | HomeoMeds | §12 + §2.7 | Fulfilment consent & pharmacy selection | The patient chooses the seller and consents before the prescription is shared | Patient | Database | No | Yes | Yes | No | No | No | P0 | S | — | — | UI, QA |  | Does not exist | ConsentRecord PharmacyShare; patient picks from routed sellers; share only after consent | No pharmacy sees names until patient consents and seller is selected (codes still protected until accept+OTP) | Not Started | Web
321 | 594 | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.3 | MED-03 | Fulfilment consent & pharmacy selection — patient chooses the seller and consents before the prescription is shared | MED-03.02 | API: list sellers; select; grant consent | New | HomeoMeds | §12 + §2.7 | Fulfilment consent & pharmacy selection | The patient chooses the seller and consents before the prescription is shared | Patient | API | No | Yes | Yes | Yes | No | No | P0 | M | MED-03.01 | T-320 (MED-03.01) | UI, QA |  | Does not exist | ConsentRecord PharmacyShare; patient picks from routed sellers; share only after consent | No pharmacy sees names until patient consents and seller is selected (codes still protected until accept+OTP) | Not Started | Web
322 | 597 | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.4 | MED-04 | Prescription handoff — signed prescription becomes the order directly — no re-entry, no transcription errors | MED-04.01 | DB: MedicineOrder, MedicineOrderItem from ErxSnapshot | New | HomeoMeds | §12 + §2.7 | Prescription handoff / Order start | The signed prescription becomes the order directly — no re-entry, no transcription errors / Start an order directly from the prescription | Patient + Pharmacy | Database | No | Yes | Yes | No | No | No | P0 | S | — | — | UI, QA |  | Does not exist | MedicineOrder copied from ErxSnapshot items (codes); pharmacy never types remedies | Order lines == snapshot lines; pharmacy cannot add a different remedy | Not Started | Web
323 | 598 | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.4 | MED-04 | Prescription handoff — signed prescription becomes the order directly — no re-entry, no transcription errors | MED-04.02 | API: POST order from ErxId | New | HomeoMeds | §12 + §2.7 | Prescription handoff / Order start | The signed prescription becomes the order directly — no re-entry, no transcription errors / Start an order directly from the prescription | Patient + Pharmacy | API | No | Yes | Yes | Yes | No | No | P0 | M | MED-04.01 | T-322 (MED-04.01) | UI, QA |  | Does not exist | MedicineOrder copied from ErxSnapshot items (codes); pharmacy never types remedies | Order lines == snapshot lines; pharmacy cannot add a different remedy | Not Started | Web
324 | 601 | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.5 | MED-05 | Rule-based seller routing — licence validity, service area, working hours and capacity | MED-05.01 | DB: SellerRoutingRule (area, hours, capacity) | New | HomeoMeds | §12 | Rule-based seller routing | Orders routed by licence validity, service area, working hours and capacity | Backend | Database | No | Yes | Yes | No | No | No | P0 | S | — | — | UI, QA |  | Does not exist | SellerRoutingRule engine | Out-of-area pharmacy never listed | Not Started | Web
325 | 602 | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.5 | MED-05 | Rule-based seller routing — licence validity, service area, working hours and capacity | MED-05.02 | Routing service used by seller list API | New | HomeoMeds | §12 | Rule-based seller routing | Orders routed by licence validity, service area, working hours and capacity | Backend | API | No | Yes | Yes | Yes | No | No | P0 | M | MED-05.01 | T-324 (MED-05.01) | UI, QA |  | Does not exist | SellerRoutingRule engine | Out-of-area pharmacy never listed | Not Started | Web
326 | 605 | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.6 | MED-06 | Manual stock confirmation — pharmacy confirms availability — no live inventory integration required | MED-06.01 | Accept payload includes stock confirmation; reject reason OUT_OF_STOCK | New | HomeoMeds | §12 | Manual stock confirmation | The pharmacy confirms availability — no live inventory integration required | Pharmacy console | API | No | Yes | No | Yes | No | No | P0 | S | — | — | UI, QA |  | Does not exist | Accept/reject with stock flag; do not build inventory master | Reject for out-of-stock routes to next seller or exception queue | Not Started | Web
327 | 608 | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.7 | MED-07 | Pharmacy console — accept or reject, enter price quote, mark ready and dispatched | MED-07.01 | Order status machine: Offered/Accepted/Rejected/Quoted/Paid/Ready/Dispatched/Delivered | New | HomeoMeds | §12 | Pharmacy console | Accept or reject orders, enter the price quote, mark ready and dispatched | Pharmacy console | Database | No | Yes | Yes | No | No | No | P0 | S | — | — | UI, QA |  | Does not exist | /pharmacy/orders list+detail; OTP accept (SEC-07); quote; ready; dispatched | OTP required on accept; status visible to patient | Not Started | Web
328 | 609 | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.7 | MED-07 | Pharmacy console — accept or reject, enter price quote, mark ready and dispatched | MED-07.02 | API: accept(OTP), reject, quote, ready, dispatch | New | HomeoMeds | §12 | Pharmacy console | Accept or reject orders, enter the price quote, mark ready and dispatched | Pharmacy console | API | No | Yes | Yes | Yes | No | No | P0 | M | MED-07.01 | T-327 (MED-07.01) | UI, QA |  | Does not exist | /pharmacy/orders list+detail; OTP accept (SEC-07); quote; ready; dispatched | OTP required on accept; status visible to patient | Not Started | Web
329 | 611 | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.7 | MED-07 | Pharmacy console — accept or reject, enter price quote, mark ready and dispatched | MED-07.04 | OTP on accept | New Integration | HomeoMeds | §12 | Pharmacy console | Accept or reject orders, enter the price quote, mark ready and dispatched | Pharmacy console | Integration | No | Yes | No | Yes | No | Yes | P0 | M | MED-07.03 | — | UI, QA | MED-07.03 | Does not exist | /pharmacy/orders list+detail; OTP accept (SEC-07); quote; ready; dispatched | OTP required on accept; status visible to patient | Not Started | Web
330 | 613 | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.8 | MED-08 | Quote before payment — the patient always sees the price before paying | MED-08.01 | DB: MedicineQuote | New | HomeoMeds | §12 + §2.7 | Quote before payment / Pharmacy selection & quote | The patient always sees the price before paying / Choose a licensed pharmacy and see the price before paying | Patient | Database | No | Yes | Yes | No | No | No | P0 | S | — | — | UI, QA |  | Does not exist | MedicineQuote; patient must confirm quote; then PAY-07 | Payment API rejects if quote not accepted by patient | Not Started | Web
331 | 614 | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.8 | MED-08 | Quote before payment — the patient always sees the price before paying | MED-08.02 | API: quote, patient accept quote, then create medicine payment | New | HomeoMeds | §12 + §2.7 | Quote before payment / Pharmacy selection & quote | The patient always sees the price before paying / Choose a licensed pharmacy and see the price before paying | Patient | API | No | Yes | Yes | Yes | No | No | P0 | M | MED-08.01 | T-330 (MED-08.01) | UI, QA |  | Does not exist | MedicineQuote; patient must confirm quote; then PAY-07 | Payment API rejects if quote not accepted by patient | Not Started | Web
332 | 617 | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.9 | MED-09 | Payment or cash on delivery — both options, with status tracking | MED-09.01 | Wire PAY-07 CreateMedicineOrder; COD status enum | New | HomeoMeds | §12 + §9 | Payment or cash on delivery | Both options supported, with status tracking | Patient | API | No | Yes | No | Yes | No | Yes | P0 | M | — | — | UI, QA |  | Stream MEDICINE stub in Phase 6 | Online pay via PAY-02; COD_PENDING until pharmacy confirms collection | COD does not mark Stream MEDICINE as captured until collection confirmed | Not Started | Web
333 | 620 | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.10 | MED-10 | Order tracking — live status for the patient at every stage | MED-10.01 | DB: MedicineOrderEvent | New | HomeoMeds | §12 + §2.7 | Order tracking | Live status for the patient at every stage / Live status from accepted to delivered | Patient | Database | No | Yes | Yes | No | No | No | P1 | S | — | — | UI, QA |  | Does not exist | Status timeline events; push updates COM-03 | Every status change visible; never silent skip | Not Started | Web
334 | 621 | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.10 | MED-10 | Order tracking — live status for the patient at every stage | MED-10.02 | GET tracking by order id (patient) | New | HomeoMeds | §12 + §2.7 | Order tracking | Live status for the patient at every stage / Live status from accepted to delivered | Patient | API | No | Yes | Yes | Yes | No | No | P1 | M | MED-10.01 | T-333 (MED-10.01) | UI, QA |  | Does not exist | Status timeline events; push updates COM-03 | Every status change visible; never silent skip | Not Started | Web
335 | 623 | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.10 | MED-10 | Order tracking — live status for the patient at every stage | MED-10.04 | Push on status change | New Integration | HomeoMeds | §12 + §2.7 | Order tracking | Live status for the patient at every stage / Live status from accepted to delivered | Patient | Integration | No | Yes | No | Yes | No | Yes | P1 | M | MED-10.03 | — | UI, QA | MED-10.03 | Does not exist | Status timeline events; push updates COM-03 | Every status change visible; never silent skip | Not Started | Web
336 | 625 | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.11 | MED-11 | Medicine ledger shares — seller, platform and delivery recorded (FIN-03 live fill) | MED-11.01 | On captured medicine payment write three-share ledger lines | New | HomeoMeds | §12 + §8 | Medicine ledger | Seller, platform and delivery shares recorded separately from consultation money | Account | API | No | Yes | Yes | No | No | No | P0 | M | — | — | QA |  | Empty medicine ledger screen from Phase 7 | On pay/COD collect, write SplitSeller/Platform/Delivery from config | Account medicine ledger shows real rows after first order | Not Started | Web
337 | 627 | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.12 | MED-12 | Order exception queue — stuck, rejected or failed orders always surfaced — never silent | MED-12.01 | Exception rows for medicine orders | New | HomeoMeds | §12 | Order exception queue | Stuck, rejected or failed orders are always surfaced to the operations team — never silent | Admin + Account | Database | No | Yes | Yes | No | No | No | P0 | S | — | — | UI, QA |  | Does not exist | HomeoMeds exception queue; SLA; never drop | Rejected-by-all-sellers appears in queue within worker SLA | Not Started | Web
338 | 628 | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.12 | MED-12 | Order exception queue — stuck, rejected or failed orders always surfaced — never silent | MED-12.02 | Admin/ops list/detail/retry re-route | New | HomeoMeds | §12 | Order exception queue | Stuck, rejected or failed orders are always surfaced to the operations team — never silent | Admin + Account | API | No | Yes | Yes | Yes | No | No | P0 | M | MED-12.01 | T-337 (MED-12.01) | UI, QA |  | Does not exist | HomeoMeds exception queue; SLA; never drop | Rejected-by-all-sellers appears in queue within worker SLA | Not Started | Web
339 | 631 | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.13 | MED-13 | OTP-based control — key actions verified by OTP so Homeocentrum can monitor and trace every transaction | MED-13.01 | Bind OTP actions: PharmacyAccept, (optional) QuoteLock, Payout already FIN-05 | New | HomeoMeds | §12 + §17 | OTP-based control | Key actions verified by OTP so Homeocentrum can monitor and trace every transaction | Pharmacy + Account | API | No | Yes | No | Yes | No | No | P0 | S | — | — | QA |  | SEC-07 infrastructure exists | OTP on pharmacy accept (and other high-risk); OtpAudit queryable | Accept without OTP fails; audit lists the action | Not Started | Web
340 | 633 | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.14 | MED-14 | Refill orders — repeat orders raised from an existing prescription | MED-14.01 | On doctor approve, clone order from snapshot; patient one-tap | New | HomeoMeds | §12 + §2.7 + §11 | Refill orders / Order detail & refill | Repeat orders raised from an existing prescription / Full order history and one-tap refill request | Patient + Doctor | API | No | Yes | No | Yes | No | No | P1 | M | — | — | UI, QA |  | ERX-10 refill request exists | Approved refill creates a new MedicineOrder from the same snapshot; one-tap patient | Refill does not mutate the original signed snapshot | Not Started | Web
341 | 638 | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.16 | MED-16 | Medicines tab — all medicine orders in one place (API now; app UI in Phase 16) | MED-16.01 | GET /api/Patient/MedicineOrders | New | HomeoMeds | §2.7 | Medicines tab | All medicine orders in one place | Patient | API | No | Yes | No | Yes | No | No | P1 | S | — | — | UI, QA |  | Does not exist | GET my orders; website optional list; app tab Phase 16 | Patient sees all orders for their PatientId only | Not Started | Web
342 | 641 | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.1 | CON-01 | Family members — add family members under one account | CON-01.01 | DB: FamilyMember | New | Patient identity | §2.1 | Family members | Add family members under one account | Patient App (API now) | Database | No | Yes | Yes | No | No | No | P0 | S | — | — | UI, QA |  | Does not exist | FamilyMember under Patient account; bookings can be for a member | Member has own PatientId or MemberId linked; records isolated correctly | Not Started | Web
343 | 642 | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.1 | CON-01 | Family members — add family members under one account | CON-01.02 | API: CRUD family; book-as-member | New | Patient identity | §2.1 | Family members | Add family members under one account | Patient App (API now) | API | No | Yes | Yes | Yes | No | No | P0 | M | CON-01.01 | T-342 (CON-01.01) | UI, QA |  | Does not exist | FamilyMember under Patient account; bookings can be for a member | Member has own PatientId or MemberId linked; records isolated correctly | Not Started | Web
344 | 645 | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.2 | CON-02 | Caregiver authorization — let a family member book and manage on their behalf | CON-02.01 | DB: CaregiverAuth | New | Patient identity | §2.1 | Caregiver authorization | Let a family member book and manage on their behalf | Patient App (API now) | Database | No | Yes | Yes | No | No | No | P0 | S | — | — | UI, QA |  | Does not exist | CaregiverAuth with scopes; OTP; withdrawable via consent centre | Caregiver cannot exceed granted scopes; withdrawal immediate | Not Started | Web
345 | 646 | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.2 | CON-02 | Caregiver authorization — let a family member book and manage on their behalf | CON-02.02 | API: grant/revoke/list; booking authorisation check | New | Patient identity | §2.1 | Caregiver authorization | Let a family member book and manage on their behalf | Patient App (API now) | API | No | Yes | Yes | Yes | No | No | P0 | M | CON-02.01 | T-344 (CON-02.01) | UI, QA |  | Does not exist | CaregiverAuth with scopes; OTP; withdrawable via consent centre | Caregiver cannot exceed granted scopes; withdrawal immediate | Not Started | Web
346 | 648 | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.2 | CON-02 | Caregiver authorization — let a family member book and manage on their behalf | CON-02.04 | OTP on grant | New Integration | Patient identity | §2.1 | Caregiver authorization | Let a family member book and manage on their behalf | Patient App (API now) | Integration | No | Yes | No | Yes | No | Yes | P0 | M | CON-02.03 | — | UI, QA | CON-02.03 | Does not exist | CaregiverAuth with scopes; OTP; withdrawable via consent centre | Caregiver cannot exceed granted scopes; withdrawal immediate | Not Started | Web
347 | 650 | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.3 | CON-03 | Records timeline + consultation note + document upload APIs | CON-03.01 | Reuse appointments + summary + eRx + SecureDocument | New | Patient records | §2.5 | Records timeline / Consultation note / Document upload | Complete visit history in date order / Doctor’s notes for each visit / Upload reports, scans and previous prescriptions | Patient App (API now) | Database | No | Yes | Yes | No | No | No | P0 | S | — | — | UI, QA |  | Doctor history exists; no patient timeline; no patient upload | Patient timeline DTO (visits, summary, eRx codes, labs); consultation note = TEL-11 summary not private notes; uploads via SEC-09 | Private doctor notes never in patient timeline; uploads listed | Not Started | Web
348 | 651 | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.3 | CON-03 | Records timeline + consultation note + document upload APIs | CON-03.02 | GET timeline; GET consultation note (summary); POST documents | New | Patient records | §2.5 | Records timeline / Consultation note / Document upload | Complete visit history in date order / Doctor’s notes for each visit / Upload reports, scans and previous prescriptions | Patient App (API now) | API | No | Yes | Yes | Yes | No | No | P0 | M | CON-03.01 | T-347 (CON-03.01) | UI, QA |  | Doctor history exists; no patient timeline; no patient upload | Patient timeline DTO (visits, summary, eRx codes, labs); consultation note = TEL-11 summary not private notes; uploads via SEC-09 | Private doctor notes never in patient timeline; uploads listed | Not Started | Web
349 | 654 | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.4 | CON-04 | Follow-up plan & tasks — clear next steps after each consultation | CON-04.01 | DB: FollowUpPlan, FollowUpTask | New | Continuity | §2.6 | Follow-up plan & tasks | Clear next steps after each consultation | Doctor Web + Patient | Database | No | Yes | Yes | No | No | No | P1 | S | — | — | UI, QA |  | Does not exist (follow-up option in notes does not save) | FollowUpTask created by doctor; patient sees tasks | Tasks persist against PatientAppId; due dates drive Phase 18 follow-up analysis | Not Started | Web
350 | 655 | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.4 | CON-04 | Follow-up plan & tasks — clear next steps after each consultation | CON-04.02 | API: doctor set; patient list/complete | New | Continuity | §2.6 | Follow-up plan & tasks | Clear next steps after each consultation | Doctor Web + Patient | API | No | Yes | Yes | Yes | No | No | P1 | M | CON-04.01 | T-349 (CON-04.01) | UI, QA |  | Does not exist (follow-up option in notes does not save) | FollowUpTask created by doctor; patient sees tasks | Tasks persist against PatientAppId; due dates drive Phase 18 follow-up analysis | Not Started | Web
351 | 658 | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.5 | CON-05 | Symptom diary — record symptoms between visits | CON-05.01 | DB: SymptomDiary | New | Continuity | §2.6 | Symptom diary | Record symptoms between visits | Patient App (API now) | Database | No | Yes | Yes | No | No | No | P1 | S | — | — | UI, QA |  | Does not exist | SymptomDiary entries; doctor can read on board | Entries dated; treating doctor can read; other doctors 403 | Not Started | Web
352 | 659 | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.5 | CON-05 | Symptom diary — record symptoms between visits | CON-05.02 | API: patient CRUD; doctor GET by patient | New | Continuity | §2.6 | Symptom diary | Record symptoms between visits | Patient App (API now) | API | No | Yes | Yes | Yes | No | No | P1 | M | CON-05.01 | T-351 (CON-05.01) | UI, QA |  | Does not exist | SymptomDiary entries; doctor can read on board | Entries dated; treating doctor can read; other doctors 403 | Not Started | Web
353 | 662 | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.6 | CON-06 | Progress tracking — see improvement over time across visits | CON-06.01 | Derived API from diary + appointments | New | Continuity | §2.6 | Progress tracking | See improvement over time across visits | Patient + Doctor | Database | No | Yes | Yes | No | No | No | P2 | S | — | — | UI, QA |  | Does not exist | Progress series from diary + visit outcomes; not a fake chart | Empty state for new patients; series uses real diary/visit data | Not Started | Web
354 | 663 | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.6 | CON-06 | Progress tracking — see improvement over time across visits | CON-06.02 | GET progress series | New | Continuity | §2.6 | Progress tracking | See improvement over time across visits | Patient + Doctor | API | No | Yes | Yes | Yes | No | No | P2 | M | CON-06.01 | T-353 (CON-06.01) | UI, QA |  | Does not exist | Progress series from diary + visit outcomes; not a fake chart | Empty state for new patients; series uses real diary/visit data | Not Started | Web
355 | 666 | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.7 | CON-07 | Consent centre & data rights — view, manage and withdraw consents; request data | CON-07.01 | Reuse ConsentRecord; DataRequest table | New | Privacy | §17 + §2.8 | Consent centre & data rights | Patients can view, manage and withdraw consent / View, manage and withdraw consents; request data | Patient App (API now) | Database | No | Yes | Yes | No | No | No | P0 | S | — | — | UI, QA |  | ConsentRecord from Phase 0 | Patient list/withdraw; data export request (DPDP); deletion request workflow | Withdraw tele-recording prevents future recording; export request ticketed | Not Started | Web
356 | 667 | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.7 | CON-07 | Consent centre & data rights — view, manage and withdraw consents; request data | CON-07.02 | API: list/withdraw; request export/delete | New | Privacy | §17 + §2.8 | Consent centre & data rights | Patients can view, manage and withdraw consent / View, manage and withdraw consents; request data | Patient App (API now) | API | No | Yes | Yes | Yes | No | No | P0 | M | CON-07.01 | T-355 (CON-07.01) | UI, QA |  | ConsentRecord from Phase 0 | Patient list/withdraw; data export request (DPDP); deletion request workflow | Withdraw tele-recording prevents future recording; export request ticketed | Not Started | Web
357 | 670 | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.8 | CON-08 | Patient payments & refunds read model | CON-08.01 | GET /api/Patient/Payments | New | Patient money | §2.8 | Payments & refunds | Full payment history and refund status | Patient App (API now) | API | No | Yes | No | Yes | No | No | P1 | M | — | — | QA |  | Ledger exists for Account | Patient-safe DTO of own consult+medicine payments and refunds — no other patients, no commission internals | Patient sees status matching PAY-08; no Account-only fields leaked | Not Started | Web
358 | 672 | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.9 | CON-09 | Physical clinic appointment — book an in-person visit as well as online | CON-09.01 | Public/patient create booking accepts ConsultMode=In-clinic; uses in-clinic fee | Existing Improvement | Booking | §2.9 + §5.2 | Physical clinic appointment | Book an in-person visit as well as online | Patient | API | No | Yes | No | Yes | No | No | P1 | S | — | — | QA |  | ConsultMode added in APT-02; public booking in WEB-04 | Ensure public/patient booking supports In-clinic as first-class, not tele-only | Patient can book in-clinic slot where doctor offers it | Not Started | Web
359 | 674 | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.10 | CON-10 | Patient profile setup API — name, age, gender, contact and health basics | CON-10.01 | Extend Patient with health-basics JSON/columns | New | Patient identity | §2.1 | Profile setup | Name, age, gender, contact and health basics | Patient App (API now) | Database | No | Yes | Yes | No | No | No | P0 | S | — | — | UI, QA |  | Clinic-created Patient exists; no self-serve profile product | Patient profile fields + health basics; used by OTP-verified patient token | Profile required before first paid booking (or soft-gate documented) | Not Started | Web
360 | 675 | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.10 | CON-10 | Patient profile setup API — name, age, gender, contact and health basics | CON-10.02 | GET/PUT /api/Patient/Profile | New | Patient identity | §2.1 | Profile setup | Name, age, gender, contact and health basics | Patient App (API now) | API | No | Yes | Yes | Yes | No | No | P0 | M | CON-10.01 | T-359 (CON-10.01) | UI, QA |  | Clinic-created Patient exists; no self-serve profile product | Patient profile fields + health basics; used by OTP-verified patient token | Profile required before first paid booking (or soft-gate documented) | Not Started | Web
361 | 957 | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.1 | RPT-01 | Admin overview dashboard — platform-wide activity at a glance (replace Velzon ecommerce) | RPT-01.01 | No ecommerce tables | Existing Improvement | Reports | §16 + §7.2 | Admin overview dashboard / Admin dashboard | Platform-wide activity at a glance / Live overview of the whole platform | Admin Portal | Database | No | Yes | Yes | No | No | No | P0 | S | — | — | UI, QA |  | Velzon ecommerce dashboard 0% product; login lands /dashboard | True /admin/dashboard KPIs: doctors, credentialing, bookings, GMV, failed payments, tickets, HomeoMeds exceptions; redirect /dashboard away from StoreVisits | Admin home is product KPIs, not Velzon Revenue/StoreVisits | Not Started | Web
362 | 958 | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.1 | RPT-01 | Admin overview dashboard — platform-wide activity at a glance (replace Velzon ecommerce) | RPT-01.02 | GET /api/AdminDashboard/Overview | Existing Improvement | Reports | §16 + §7.2 | Admin overview dashboard / Admin dashboard | Platform-wide activity at a glance / Live overview of the whole platform | Admin Portal | API | No | Yes | Yes | Yes | No | No | P0 | M | RPT-01.01 | T-361 (RPT-01.01) | UI, QA |  | Velzon ecommerce dashboard 0% product; login lands /dashboard | True /admin/dashboard KPIs: doctors, credentialing, bookings, GMV, failed payments, tickets, HomeoMeds exceptions; redirect /dashboard away from StoreVisits | Admin home is product KPIs, not Velzon Revenue/StoreVisits | Not Started | Web
363 | 961 | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.2 | RPT-02 | Doctor practice statistics — patient and consultation trends (extend existing charts) | RPT-02.01 | No new warehouse required for v1 | Existing Improvement | Reports | §16 + §5.1 | Doctor practice statistics | Patient and consultation trends | Doctor Web | Database | No | Yes | Yes | No | No | No | P1 | S | — | — | UI, QA |  | Patient stats charts live | Keep as foundation; ensure visit type/mode included after APT-02 | Trends include first vs follow-up when VisitType exists | Not Started | Web
364 | 962 | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.2 | RPT-02 | Doctor practice statistics — patient and consultation trends (extend existing charts) | RPT-02.02 | Extend GetPatientStatsCharts with VisitType/ConsultMode | Existing Improvement | Reports | §16 + §5.1 | Doctor practice statistics | Patient and consultation trends | Doctor Web | API | No | Yes | Yes | Yes | No | No | P1 | M | RPT-02.01 | T-363 (RPT-02.01) | UI, QA |  | Patient stats charts live | Keep as foundation; ensure visit type/mode included after APT-02 | Trends include first vs follow-up when VisitType exists | Not Started | Web
365 | 965 | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.3 | RPT-03 | Follow-up analysis — due/overdue patients and follow-up conversion | RPT-03.01 | Queries on VisitType + FollowUpTask | New | Reports | §16 | Follow-up analysis | Which patients are due or overdue for follow-up, and follow-up conversion | Doctor Web | Database | No | Yes | Yes | No | No | No | P1 | S | — | — | UI, QA |  | Does not exist; follow-up option in notes does not save | /doctor/follow-up-analysis from VisitType + CON-04 tasks | Due list and conversion first-visit → follow-up are real counts | Not Started | Web
366 | 966 | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.3 | RPT-03 | Follow-up analysis — due/overdue patients and follow-up conversion | RPT-03.02 | GET FollowUpDue, FollowUpSummary | New | Reports | §16 | Follow-up analysis | Which patients are due or overdue for follow-up, and follow-up conversion | Doctor Web | API | No | Yes | Yes | Yes | No | No | P1 | M | RPT-03.01 | T-365 (RPT-03.01) | UI, QA |  | Does not exist; follow-up option in notes does not save | /doctor/follow-up-analysis from VisitType + CON-04 tasks | Due list and conversion first-visit → follow-up are real counts | Not Started | Web
367 | 969 | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.4 | RPT-04 | Clinic performance analysis — appointments, slot utilisation, no-shows, cancellations, waiting time and revenue | RPT-04.01 | Aggregate APIs beyond GetPatientStatsCharts | New | Reports | §16 | Clinic performance analysis | Appointments, slot utilisation, no-shows, cancellations, waiting time and revenue | Doctor Web | Database | No | Yes | Yes | No | No | No | P1 | S | — | — | UI, QA |  | Does not exist | /doctor/clinic-performance including payment collected and tele duration if timed | Each KPI has a definition note on the screen (no silent formula) | Not Started | Web
368 | 970 | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.4 | RPT-04 | Clinic performance analysis — appointments, slot utilisation, no-shows, cancellations, waiting time and revenue | RPT-04.02 | GET ClinicPerformance | New | Reports | §16 | Clinic performance analysis | Appointments, slot utilisation, no-shows, cancellations, waiting time and revenue | Doctor Web | API | No | Yes | Yes | Yes | No | No | P1 | M | RPT-04.01 | T-367 (RPT-04.01) | UI, QA |  | Does not exist | /doctor/clinic-performance including payment collected and tele duration if timed | Each KPI has a definition note on the screen (no silent formula) | Not Started | Web
369 | 973 | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.5 | RPT-05 | Payment reconciliation report — bookings matched against payments | RPT-05.01 | CSV/PDF export of FIN-02 query | New | Reports | §16 + §7.2 | Payment reconciliation report / Consult booking & payment reconciliation | Bookings matched against payments / Match every booking against every payment | Admin + Account | API | No | Yes | No | Yes | No | No | P1 | S | — | — | UI, QA |  | FIN-02 built the queue; this is the report/export | Exportable report from the same reconciliation query | CSV totals match on-screen KPIs | Not Started | Web
370 | 976 | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.6 | RPT-06 | Settlement & payout reports — amounts due and paid to doctors and pharmacies | RPT-06.01 | Export settlement runs + payout register | New | Reports | §16 + §8 | Settlement & payout reports | Amounts due and paid to doctors and pharmacies | Account | API | No | Yes | No | Yes | No | No | P1 | S | — | — | UI, QA |  | FIN-04/05 exist as ops screens | Formal report/export of runs and payouts | Paid vs due columns reconcile to ledger | Not Started | Web
371 | 979 | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.7 | RPT-07 | GST & invoice reports (reporting surface of FIN-08) | RPT-07.01 | Confirm CA format; implement export if not already in FIN-08 | New | Reports | §16 + §8 | GST & invoice reports | Tax reporting | Account | API | No | Yes | No | No | No | No | P1 | M | — | — | QA |  | FIN-08 built tax screen | Confirm report pack (GSTR-style export as agreed with CA) — configuration | Invoice list export matches FIN-08 | Not Started | Web
372 | 981 | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.8 | RPT-08 | Doctor earnings summary — daily, weekly and monthly earnings with payout status (web + same API as DMO-10) | RPT-08.01 | Reuse earnings API | New | Reports | §16 + §3 | Doctor earnings summary | Daily, weekly and monthly earnings with payout status | Doctor Web + App | Database | No | Yes | Yes | No | No | No | P1 | S | — | — | UI, QA |  | Does not exist | Web earnings page using same API as doctor app | Web and app match | Not Started | Web
373 | 982 | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.8 | RPT-08 | Doctor earnings summary — daily, weekly and monthly earnings with payout status (web + same API as DMO-10) | RPT-08.02 | GET Earnings/Summary already for app — add if missing date buckets | New | Reports | §16 + §3 | Doctor earnings summary | Daily, weekly and monthly earnings with payout status | Doctor Web + App | API | No | Yes | Yes | Yes | No | No | P1 | M | RPT-08.01 | T-372 (RPT-08.01) | UI, QA |  | Does not exist | Web earnings page using same API as doctor app | Web and app match | Not Started | Web
374 | 985 | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.9 | RPT-09 | Medicine order reports — order volumes, fulfilment and exceptions | RPT-09.01 | Aggregates on MedicineOrder | New | Reports | §16 + §12 | Medicine order reports | Order volumes, fulfilment and exceptions | Admin + Account | Database | No | Yes | Yes | No | No | No | P1 | S | — | — | UI, QA |  | Does not exist | Volumes, SLA, exception counts from HomeoMeds | Exception count matches MED-12 queue | Not Started | Web
375 | 986 | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.9 | RPT-09 | Medicine order reports — order volumes, fulfilment and exceptions | RPT-09.02 | GET medicine order report | New | Reports | §16 + §12 | Medicine order reports | Order volumes, fulfilment and exceptions | Admin + Account | API | No | Yes | Yes | Yes | No | No | P1 | M | RPT-09.01 | T-374 (RPT-09.01) | UI, QA |  | Does not exist | Volumes, SLA, exception counts from HomeoMeds | Exception count matches MED-12 queue | Not Started | Web
376 | 989 | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.10 | RPT-10 | Platform users remaining 20% — import, export and activation control | RPT-10.01 | VerificationStatus on user/doctor list DTO | Existing Improvement | Admin | §7.2 | Platform users | Manage all users with import, export and activation control | Admin Portal | Database | No | Yes | Yes | No | No | No | P1 | S | — | — | UI, QA |  | List/Add/Edit live; Import/Export buttons dead; no verification column | Wire Import/Export; verification column; activate/lock; link credentialing | Import/Export work; unverified visible; lock prevents login | Not Started | Web
377 | 990 | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.10 | RPT-10 | Platform users remaining 20% — import, export and activation control | RPT-10.02 | User import/export APIs if missing | Existing Improvement | Admin | §7.2 | Platform users | Manage all users with import, export and activation control | Admin Portal | API | No | Yes | Yes | Yes | No | No | P1 | M | RPT-10.01 | T-376 (RPT-10.01) | UI, QA |  | List/Add/Edit live; Import/Export buttons dead; no verification column | Wire Import/Export; verification column; activate/lock; link credentialing | Import/Export work; unverified visible; lock prevents login | Not Started | Web
378 | 998 | Web | 19 | Phase 19 — Cross-surface QA, NFR, delivery summary gate (PDF §1 + §18) | 19.3 | NFR-01 | NFR — performance, low-data, reliability, secrets, dual-API freeze | NFR-01.01 | Rotate API secrets; keys in config/KeyVault; directory browsing remains off | Existing Modification | NFR | §2.9 + §3 + §17 | Low-data mode / Reliability monitoring / Secure login | Works on slow connections; failures reported automatically; credentials protected | All | Security | No | Yes | No | No | No | No | P0 | M | — | — | QA |  | Known risks: plaintext passwords (fixed P0), secrets in appsettings, dual API drift | Rotate secrets; no new third API; patient low-data verified; doctor reliability SDK live | Load test on booking+webhook; secrets not in git; dual-API map documented | Not Started | Web

## 02_UI_Sequential
UI SEQUENTIAL BACKLOG — React SPA screens (Admin, Doctor, Reception, Account, Public, Pharmacy). Execute by Track Seq. If Wait for other track lists a Web API ID, that API must be Done first.
Track Seq | Original Seq | Track | Phase | Phase Name | WBS | Main Task ID | Main Task | Sub Task ID | Sub Task | Work Type | Module / Area | PDF Section | PDF Feature (exact wording) | PDF Delivery Text | Application Surface | Layer | Frontend | Backend | Database | API | Mobile | Integration | Priority | Effort Band | Depends On (original) | Depends On (this track) | Sister Tracks (same Main Task) | Wait for other track | Existing Capability (AS-IS) | Gap / Change Required (TO-BE) | Acceptance Criteria | Status | Owner | Notes
1 | 16 | UI | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.2 | FND-02 | Delivery footprint — 2 mobile apps · 5 web portals · payment · telemedicine · digital prescription · HomeoMeds (programme skeleton) | FND-02.01 | Web: add Account layout + home redirect; Pharmacy layout stub; do not build screens yet | New | Platform | §1 | Delivery covers | 2 mobile applications · 5 web portals · payment system · telemedicine · digital prescription · online medicine delivery. | Shared | Web SPA | Yes | No | No | No | No | No | P0 | M | — | — | Web, Mobile |  | 1 web SPA (Admin/Doctor/Reception + marketing). No patient app, doctor app, Account portal, Pharmacy console | Repo/route skeleton: Patient Website, Doctor Web, Reception, Admin, Account (+ Pharmacy console under HomeoMeds); Patient + Doctor mobile later | Five web portal shells routable by role; mobile apps scheduled in Phases 16–17 not started here | Not Started | UI
2 | 17 | UI | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.2 | FND-02 | Delivery footprint — 2 mobile apps · 5 web portals · payment · telemedicine · digital prescription · HomeoMeds (programme skeleton) | FND-02.02 | Extend roles.js and AuthProtected with per-route ACL skeleton (deny-by-default for new routes) | Existing Improvement | Platform | §1 | Delivery covers | 2 mobile applications · 5 web portals · payment system · telemedicine · digital prescription · online medicine delivery. | Shared | Web SPA | Yes | No | No | No | No | No | P0 | M | FND-02.01 | T-1 (FND-02.01) | Web, Mobile |  | 1 web SPA (Admin/Doctor/Reception + marketing). No patient app, doctor app, Account portal, Pharmacy console | Repo/route skeleton: Patient Website, Doctor Web, Reception, Admin, Account (+ Pharmacy console under HomeoMeds); Patient + Doctor mobile later | Five web portal shells routable by role; mobile apps scheduled in Phases 16–17 not started here | Not Started | UI
3 | 22 | UI | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.3 | SEC-01 | Secure login — protected credentials for every user type | SEC-01.03 | UI: remove fakeBackend() from App.js production path; login still Formik/Yup | Existing Modification | Security | §17 | Secure login | Protected credentials for every user type | All web + later mobile | Web SPA | Yes | No | No | No | No | No | P0 | S | SEC-01.02 | — | Web, QA | SEC-01.02 | POST /Account/Login on classic API; JWT in sessionStorage; doctor/user passwords compared plaintext; reception hashed on classic; fakeBackend() still mounted | Hashed passwords; Role claim on JWT; disable fake backend for production paths; Patient OTP login is Phase 8 (not password) | No plaintext password compare; every role including future Patient/Account/Pharmacy authenticates through a protected path | Not Started | UI
4 | 26 | UI | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.4 | SEC-02 | Secure password reset — time-limited reset links (stop plaintext email + fake thunk) | SEC-02.03 | UI: replace slices/auth/forgetpwd fake/Firebase with real APIs; /reset-password/:token success/expiry states | Existing Improvement | Security | §17 | Secure password reset | Time-limited reset links | Admin / Doctor / Reception web | Web SPA | Yes | No | No | Yes | No | No | P0 | M | SEC-02.02 | — | Web, QA | SEC-02.02 | /forgot-password UI exists; thunk uses fake/Firebase; POST /users/ForgetPassword emails plaintext password | Tokenised reset (hash, TTL); email contains link only; ChangePassword for logged-in user | Reset email never contains the password; token expires; used token cannot be reused | Not Started | UI
5 | 29 | UI | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.5 | SEC-03 | Session control — proper sign-out across web and mobile | SEC-03.02 | Web: Logout.js calls API then clears authUser + patient-board session (keep existing board clear) | Existing Improvement | Security | §17 | Session control | Proper sign-out across web and mobile | All | Web SPA | Yes | No | No | Yes | No | No | P0 | S | SEC-03.01 | — | Web, QA | SEC-03.01 | Client clears sessionStorage; no server logout / token revoke; UserLoginStatus unused | POST Logout persists login status; optional token denylist; mobile will call the same API in Phase 16/17 | After logout the JWT cannot call protected APIs; board session cleared (already on client) | Not Started | UI
6 | 33 | UI | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.6 | SEC-04 | Role-based access — each role sees only what it is permitted to see | SEC-04.02 | Frontend: hide routes the role cannot view; keep Velzon demo routes out of production menus | Existing Improvement | Security | §17 | Role-based access | Each role sees only what it is permitted to see | Admin / All web | Web SPA | Yes | No | No | No | No | No | P0 | M | SEC-04.01 | — | Web, QA | SEC-04.01 | RoleMaster + RoleDetail + MenuMaster exist; GetMenuByRole commented out on .NET 8; no per-route frontend ACL — any authenticated URL works | Re-enable GetMenuByRole; AuthProtected deny-by-default; [Authorize(Roles=)] on money/clinical APIs; Account cannot edit repertory; Admin cannot approve payouts | Unknown URL for a role returns 403/redirect; admin menus match DB permissions | Not Started | UI
7 | 136 | UI | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.28 | ADM-B04 | Business Management — Roles & menu permissions (existing DB, runtime ACL leftover) | ADM-B04.03 | Admin role pages remain; frontend consumes menu API instead of hard-coded LayoutMenuData for domain items | Existing Improvement | Business Management | §7.2 | Roles & menu permissions | Control exactly what each role can access | Admin Portal | Web SPA | Yes | No | No | Yes | No | No | P1 | M | ADM-B04.02 | — | Web, QA | ADM-B04.02 | Role CRUD screens live; runtime GetMenuByRole commented; no frontend route ACL | This is the product surface for SEC-04; complete wiring here | Changing a role’s menu immediately hides those routes after refresh | Not Started | UI
8 | 138 | UI | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.1 | CLN-01 | Clinical workspace — single screen for the entire consultation | CLN-01.01 | UI: Patient Board header shows appointment, visit type, consult mode placeholders (wired in Phases 4 and 6) | Existing Improvement | Patient Board | §5.3 | Clinical workspace | Single screen for the entire consultation | Doctor Web Portal | Web SPA | Yes | No | No | No | No | No | P1 | S | — | — | Web, QA |  | PatientBoard.js (~13.5k) is the workspace; ~90% — missing payment/tele/eRx header status | Keep one screen; add header chips for payment, tele session, signed eRx (chips light up as later phases land) | Doctor still opens one board per patient; new chips do not break tabs | Not Started | UI
9 | 158 | UI | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.7 | CLN-07 | Manage selected rubrics — review, edit and remove (remaining ~10%) | CLN-07.03 | Clipboard UX: confirm delete; intensity edit; count badge | Existing Improvement | Patient Board | §5.3 | Manage selected rubrics | Review, edit and remove selected rubrics | Doctor Web Portal | Web SPA | Yes | No | No | Yes | No | No | P1 | M | CLN-07.02 | — | Web, QA | CLN-07.02 | Clipboard exists; confirm-delete / intensity-edit incomplete | Confirm delete; edit intensity on selected rubric; no accidental wipe | Doctor can remove one rubric without losing the rest | Not Started | UI
10 | 164 | UI | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.9 | CLN-09 | Improved rubric accuracy — enhanced accuracy rules for audio-based rubric suggestions | CLN-09.02 | Admin: metaphor/alias approve-reject remaining UX | Existing Improvement | Audio AI | §5.3 | Improved rubric accuracy | Enhanced accuracy rules for audio-based rubric suggestions | Doctor Web Portal + Admin intelligence | Web SPA | Yes | No | No | Yes | No | No | P1 | M | CLN-09.01 | — | Web, QA | CLN-09.01 | Engine + admin metaphors/aliases exist; accuracy rules still in progress (~50%) | Complete accuracy rules per AUDIO_CASE_TAKING_AI_ENGINE docs; metaphor/alias QA | Benchmark set meets agreed accuracy gate before calling this done | Not Started | UI
11 | 168 | UI | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.10 | CLN-10 | Materia medica reference during consultation (remaining ~10%) | CLN-10.03 | MM tab: faster head navigation / keep place in case | Existing Improvement | Patient Board | §5.3 | Materia medica reference | Browse materia medica during the consultation | Doctor Web Portal | Web SPA | Yes | No | No | Yes | No | No | P2 | M | CLN-10.02 | — | Web, QA | CLN-10.02 | MM tab + repertorize differential accordion ~90% | Faster head navigation during case; do not rebuild MM masters | Doctor can open a remedy MM without leaving the board | Not Started | UI
12 | 175 | UI | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.12 | CLN-12 | Repertorization & elimination (remaining ~10%) | CLN-12.03 | Repertorize tab stability; then COG sits beside it | Existing Improvement | Patient Board | §5.3 | Repertorization & elimination | Full repertorization with elimination | Doctor Web Portal | Web SPA | Yes | No | No | Yes | No | No | P1 | M | CLN-12.02 | — | Web, QA | CLN-12.02 | Common/uncommon/elimination live ~90% | Stability polish; Center of Gravity is a NEW panel on the same rubrics (next task) | Elimination still ranks remedies from selected rubrics | Not Started | UI
13 | 179 | UI | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.13 | CLN-13 | Center of Gravity — new analysis identifying the central remedy of the case, with reasoning shown | CLN-13.03 | Patient Board → Repertorize tab → Center of Gravity sub-panel (toggle vs classic elimination) | New | Repertorization | §5.3 | Center of Gravity | New analysis identifying the central remedy of the case, with reasoning shown | Doctor Web Portal | Web SPA | Yes | No | No | Yes | No | No | P1 | M | CLN-13.02 | — | Web, QA | CLN-13.02 | Does not exist | POST /api/Repertorization/CenterOfGravity from selected rubric ids + intensities; UI panel with explainability | COG returns ranked central remedies plus contribution reasons the doctor can read | Not Started | UI
14 | 189 | UI | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.16 | CLN-16 | Complaints & case details — wire Patient Board to existing SaveComplaints / SaveCaseDetails (~20% today) | CLN-16.03 | Patient Board: complaints + case details form that actually POSTs | Existing Improvement | Patient Board | §5.3 | Complaints & case details | Capture and store complaints and case details | Doctor Web Portal | Web SPA | Yes | No | No | Yes | No | No | P1 | M | CLN-16.02 | — | Web, QA | CLN-16.02 | Classic SaveComplaints / SaveCaseDetails APIs exist; Patient Board does not call them | Call the existing APIs from the board; Reception case-paper (Phase 5) uses a subset | Complaints and case details persist and reload on the board | Not Started | UI
15 | 193 | UI | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.17 | CLN-17 | Patient back history — complete history of visits, notes, prescriptions and payments | CLN-17.03 | History panel: date-ordered visits; open past eRx; payment badge placeholder | Existing Improvement | Patient Board | §5.3 | Patient back history | Complete history of visits, notes, prescriptions and payments | Doctor Web Portal | Web SPA | Yes | No | No | Yes | No | No | P1 | M | CLN-17.02 | — | Web, QA | CLN-17.02 | History panel ~70%; no payment line (payments do not exist yet) | Timeline: visits, notes, eRx, labs; payment row added when Phase 6 lands (placeholder now) | Doctor sees chronological visits with notes and Rx; payment appears after Phase 6 | Not Started | UI
16 | 196 | UI | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.18 | CLN-18 | Export case data — download the full case in Excel or PDF | CLN-18.02 | Patient Board toolbar: Export Excel / Export PDF | New | Patient Board | §5.3 | Export case data | Download the full case in Excel or PDF | Doctor Web Portal | Web SPA | Yes | No | No | Yes | No | No | P1 | S | CLN-18.01 | — | Web, QA | CLN-18.01 | Newer ExportCasesToExcel exists; no Patient Board export UI; no PDF | Toolbar Excel + PDF using existing Excel API + new PDF renderer; exclude private notes from patient-facing PDF (eRx print is Phase 10) | Doctor downloads Excel and PDF of the case they own | Not Started | UI
17 | 203 | UI | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.20 | CLN-20 | 3D anatomy viewer — interactive 3D body model linked to rubric search (remaining ~50%) | CLN-20.03 | Viewer UX: incomplete regions, loading, fallback message | Existing Improvement | Anatomy | §5.3 | 3D anatomy viewer | Interactive 3D body model linked to rubric search | Doctor Web Portal | Web SPA | Yes | No | No | Yes | No | No | P2 | M | CLN-20.02 | — | Web, QA | CLN-20.02 | three.js viewer + hotspot→search live; incomplete mesh coverage / UX | Complete GLB/hotspot coverage; mobile fallback later; admin 3D masters already in Phase 1 | Every admin hotspot on the shipped models opens the correct rubric search | Not Started | UI
18 | 207 | UI | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.1 | DOC-01 | Doctor home dashboard — complete overview of the working day (remaining ~30%) | DOC-01.03 | Dashboard chrome: keep counts; add slots for Online toggle, tele queue, unpaid badge | Existing Improvement | Doctor Dashboard | §5.1 | Doctor home dashboard | Complete overview of the working day | Doctor Web Portal | Web SPA | Yes | No | No | Yes | No | No | P1 | M | DOC-01.02 | — | Web, QA | DOC-01.02 | Widgets + BestSellingProducts ~70%; missing online toggle, tele queue, payment badges, follow-up due | Extend, do not replace; later phases light up tele/payment chips | Doctor sees today’s buckets plus placeholders for tele/payment that become live in Phases 6 and 11 | Not Started | UI
19 | 214 | UI | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.3 | DOC-03 | Patient search, list & open case (remaining ~10%) | DOC-03.03 | List columns: last visit; later payment/family | Existing Improvement | Doctor Dashboard | §5.1 | Patient search, list & open case | Find any patient and open their case instantly | Doctor Web Portal | Web SPA | Yes | No | No | Yes | No | No | P1 | M | DOC-03.02 | — | Web, QA | DOC-03.02 | Search/list/open ~90%; missing last visit, unpaid, family filters | Add last-visit column; unpaid/family after those modules exist | Search still opens Patient Board; last visit visible | Not Started | UI
20 | 223 | UI | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.6 | DOC-06 | Export patients — download patient data in Excel, CSV or PDF (keep) | DOC-06.02 | UI: Excel / CSV / PDF actions labelled as in the delivery document | Existing Improvement | Patients | §5.1 | Export patients | Download patient data in Excel, CSV or PDF | Doctor Web Portal | Web SPA | Yes | No | No | No | No | No | P2 | S | DOC-06.01 | — | Web, QA | DOC-06.01 | Export live (confirm PDF vs Excel/CSV in QA) | If PDF is missing, add it as Existing Improvement; do not skip the PDF wording in the PDF | Excel, CSV and PDF each download this doctor’s patients only | Not Started | UI
21 | 232 | UI | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.9 | DOC-09 | Manage reception staff — add, edit and remove reception users (backend done, UI absent) | DOC-09.02 | Build /doctor/reception-staff list, add, edit, disable pages; menu entry in doctor chrome | Existing Improvement | Staff | §5.1 | Manage reception staff | Add, edit and remove reception users | Doctor Web Portal | Web SPA | Yes | No | No | Yes | No | No | P1 | M | DOC-09.01 | — | Web, QA | DOC-09.01 | .NET 8 api/ReceptionStaff CRUD exists; no SPA page | List/add/edit/disable at /doctor/reception-staff; doctor owns the staff record | Doctor can create a reception user who logs in to that DoctorId | Not Started | UI
22 | 236 | UI | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.10 | DOC-10 | Doctor profile — clinic details, consultation fee, photo, qualifications, working hours, bank details | DOC-10.03 | Replace Velzon /profile for doctor role with clinic/fee/photo/qualifications/hours/bank tabs | Existing Improvement | Doctor Profile | §5.1 | Doctor profile | Clinic details, consultation fee, photo, qualifications, working hours, bank details | Doctor Web Portal | Web SPA | Yes | No | No | Yes | No | No | P0 | M | DOC-10.02 | — | Web, QA | DOC-10.02 | /profile is Velzon first_name only (~20%); credentials sit on Doctor entity; no fee/KYC UI | Real doctor profile: clinic, photo, qualifications, consult fee (feeds Phase 6), hours (feeds schedule), bank KYC (feeds Account payees) | Doctor can save clinic, photo, qualifications, fee, hours, bank details; verification status visible | Not Started | UI
23 | 243 | UI | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.2 | APT-02 | Create new appointment — persist visit type, consultation mode and fee | APT-02.03 | Doctor/Reception new-appointment modal: visit type, consult mode, fee (placeholder until Phase 6 config) | Existing Improvement | Appointments | §5.2 | Create new appointment | Book with visit type, consultation mode and fee | Doctor Web Portal | Web SPA | Yes | No | No | Yes | No | No | P0 | M | APT-02.02 | — | Web, QA | APT-02.02 | Create appointment ~90%; Formik modal has no VisitType / ConsultMode / fee | VisitType First/Follow-up; ConsultMode In-clinic / E-Consult; fee display from doctor profile / ConsultFeeConfig | New appointments persist visit type, mode and fee; filters/analytics can use them | Not Started | UI
24 | 253 | UI | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.5 | APT-05 | Reschedule appointment — move to a new slot with automatic patient notification (NEW — not a rename of UpdateAppointmentTime) | APT-05.03 | UI: RescheduleModal shared by Doctor and Reception — old date/time + new slot picker; reason optional | New | Appointments | §5.2 + §2.3 + §6 | Reschedule appointment | Move to a new slot with automatic patient notification / Move to another slot without calling the clinic | Doctor Web + Reception + later Patient | Web SPA | Yes | No | No | Yes | No | No | P0 | M | APT-05.02 | — | Web, QA | APT-05.02 | Time can be edited; no formal Reschedule (audit, notify, old→new confirm) | POST RescheduleAppointment; AppointmentChangeLog; conflict 409 with alternatives; SMS/WhatsApp fan-out (notify failure must not roll back) | Every reschedule is in the change log; patient notified; old slot released; reception uses the same API | Not Started | UI
25 | 258 | UI | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.6 | APT-06 | Cancel appointment — reason, free the slot, trigger refund where applicable (NEW CANCELLED status — do NOT reuse DeleteStatus) | APT-06.03 | UI: CancelAppointmentModal shared by Doctor and Reception; dashboard Cancelled filter | New | Appointments | §5.2 + §2.3 + §6 | Cancel appointment | Cancel with reason, free the slot, trigger refund where applicable / Cancel with reason, refund handled per policy | Doctor Web + Reception + later Patient | Web SPA | Yes | No | No | Yes | No | No | P0 | M | APT-06.02 | — | Web, QA | APT-06.02 | No CANCELLED; DeleteStatus is soft-delete only | CANCELLED + reason fields; free slot; waitlist hook; if PAID evaluate refund policy (Phase 6/7) | Cancelled appointments leave active buckets; slot immediately bookable; refund path triggered rather than silently keeping money | Not Started | UI
26 | 261 | UI | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.7 | APT-07 | Daily schedule setup — define working days, hours and break times (promote modal to first-class screen) | APT-07.01 | Promote DailyScheduleSetupModal to /doctor/schedule; week grid; copy-day; reuse Get/SaveDailySchedule | Existing Improvement | Scheduling | §5.2 | Daily schedule setup | Define working days, hours and break times | Doctor Web Portal | Web SPA | Yes | No | No | Yes | No | No | P0 | M | — | — | Web, QA |  | DailyScheduleSetupModal + GetDailySchedule / SaveDailySchedule exist; not a first-class screen (draft marked 0%) | Promote to /doctor/schedule with week grid and copy-day; reuse existing APIs — do not rebuild | Public booking slots (Phase 9) respect the saved schedule | Not Started | UI
27 | 269 | UI | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.9 | APT-09 | Consultation payment status on every appointment (schema now; values live in Phase 6) | APT-09.03 | UI: Paid / Unpaid / Pay-at-clinic / Failed badges on doctor appointment list | New | Appointments | §5.2 + §9 | Consultation payment status | See paid, unpaid or pay-at-clinic on every appointment / Doctor, reception and patient all see the same payment status | Doctor Web Portal | Web SPA | Yes | No | No | No | No | No | P0 | S | APT-09.02 | — | Web, QA | APT-09.02 | No PaymentStatus on appointment | Add PaymentStatus UNPAID / PENDING / PAID / FAILED / PAY_AT_CLINIC / REFUNDED; UI badge; source of truth is webhook in Phase 6 not the client screen | Every appointment row can show a payment badge; until Phase 6 all show UNPAID/PAY_AT_CLINIC as configured | Not Started | UI
28 | 276 | UI | 5 | Phase 5 — Reception portal (PDF §6) | 5.2 | REC-02 | Reception profile — manage own profile details (0% today) | REC-02.03 | /profile reception variant | New | Reception | §6 | Reception profile | Manage own profile details | Reception Portal | Web SPA | Yes | No | No | Yes | No | No | P1 | M | REC-02.02 | — | Web, QA | REC-02.02 | No reception-specific profile; shared Velzon /profile | Name, mobile, attached doctor (read-only); cannot edit doctor bank/fee | Reception can update own name/mobile; cannot change DoctorId | Not Started | UI
29 | 278 | UI | 5 | Phase 5 — Reception portal (PDF §6) | 5.3 | REC-03 | Reception home dashboard — purpose-built front-desk dashboard (not only hidden doctor actions) | REC-03.01 | Route /reception (or role-based chrome on existing dashboard) hiding clinical tabs | Existing Improvement | Reception | §6 | Reception home dashboard | Purpose-built front-desk dashboard | Reception Portal | Web SPA | Yes | No | No | No | No | No | P1 | M | — | — | QA |  | Same /doctordashboard with some clinical actions disabled ~90% | Reception-first chrome: queue, collect pay, case paper, no repertory/Rx; optional /reception home route | Reception never sees repertorize/audio/COG; sees queue and collect-pay | Not Started | UI
30 | 279 | UI | 5 | Phase 5 — Reception portal (PDF §6) | 5.3 | REC-03 | Reception home dashboard — purpose-built front-desk dashboard (not only hidden doctor actions) | REC-03.02 | Quick actions: new patient, new appointment, collect payment, case paper, schedule | Existing Improvement | Reception | §6 | Reception home dashboard | Purpose-built front-desk dashboard | Reception Portal | Web SPA | Yes | No | No | No | No | No | P1 | S | REC-03.01 | T-29 (REC-03.01) | QA |  | Same /doctordashboard with some clinical actions disabled ~90% | Reception-first chrome: queue, collect pay, case paper, no repertory/Rx; optional /reception home route | Reception never sees repertorize/audio/COG; sees queue and collect-pay | Not Started | UI
31 | 288 | UI | 5 | Phase 5 — Reception portal (PDF §6) | 5.6 | REC-06 | Create & manage appointments — full appointment management (keep; plus reschedule/cancel from Phase 4) | REC-06.02 | Reception UI uses the same Reschedule/Cancel modals as doctor | New | Reception | §6 | Create & manage appointments | Full appointment management | Reception Portal | Web SPA | Yes | No | No | No | No | No | P0 | S | REC-06.01 | — | Web, QA | REC-06.01 | Create/status/time live; reschedule/cancel missing until Phase 4 APIs | Enable RescheduleAppointment and CancelAppointment for JWT DoctorId; isReceptionUser must not block | Reception acts only for its doctor; permission tests pass | Not Started | UI
32 | 290 | UI | 5 | Phase 5 — Reception portal (PDF §6) | 5.7 | REC-07 | New appointment — book on behalf of the patient (keep; same VisitType/ConsultMode/fee as APT-02) | REC-07.01 | Share the extended new-appointment modal with reception chrome | Existing Improvement | Reception | §6 | New appointment | Book on behalf of the patient | Reception Portal | Web SPA | Yes | No | No | No | No | No | P1 | S | — | — | QA |  | New appointment modal live; fields incomplete until APT-02 | Same modal fields as doctor so public booking later matches staff-created rows | Reception-created appointments have visit type, mode, fee | Not Started | UI
33 | 294 | UI | 5 | Phase 5 — Reception portal (PDF §6) | 5.8 | REC-08 | Waiting queue management — manage the live queue and call the next patient | REC-08.03 | Queue panel: order, wait time, paid/unpaid, Call next | Existing Improvement | Reception | §6 | Waiting queue management | Manage the live queue and call the next patient | Reception Portal | Web SPA | Yes | No | No | Yes | No | No | P1 | M | REC-08.02 | — | Web, QA | REC-08.02 | Status buckets ~60%; no dedicated queue UX / call-next | Dedicated queue: walk-in vs tele; payment state; Call next; notify patient (later push) | Reception can call next; status moves; patient can be notified when Phase 12 exists | Not Started | UI
34 | 302 | UI | 5 | Phase 5 — Reception portal (PDF §6) | 5.11 | REC-11 | View doctor schedule — see the doctor’s working schedule (read-only) | REC-11.01 | Frontend only over existing GetDailySchedule — /reception/schedule read-only | New | Reception | §6 | View doctor schedule | See the doctor’s working schedule | Reception Portal | Web SPA | Yes | No | No | Yes | No | No | P1 | S | — | — | QA |  | GetDailySchedule exists; no reception view | Read-only /reception/schedule using DoctorID from JWT | Reception views hours; cannot edit clinical schedule unless authorised | Not Started | UI
35 | 306 | UI | 5 | Phase 5 — Reception portal (PDF §6) | 5.12 | REC-12 | Log case paper / chief complaint — record the reason for visit before the consultation | REC-12.03 | /reception/case-paper or limited board | New | Reception | §6 | Log case paper / chief complaint | Record the reason for visit before the consultation | Reception Portal | Web SPA | Yes | No | No | Yes | No | No | P1 | M | REC-12.02 | — | Web, QA | REC-12.02 | Missing; SaveComplaints exists but board is doctor-only | Restricted case-paper form (chief complaint only — no repertory/Rx); audit reception author | Chief complaint visible to doctor on Patient Board; reception cannot repertorize | Not Started | UI
36 | 308 | UI | 5 | Phase 5 — Reception portal (PDF §6) | 5.13 | REC-13 | Collect consultation payment — cash, UPI, card or payment link and issue a receipt (API in Phase 6; UI shell now) | REC-13.01 | Specify receipt fields (amount, method, appointment, GST placeholder) for Phase 6 implementation | New | Reception | §6 + §9 | Collect consultation payment | Take cash, UPI, card or payment link and issue a receipt | Reception Portal | Design | Yes | No | No | No | No | No | P0 | S | — | — | Web |  | Does not exist | UI modal ready; CollectAtReception API lands with payment spine in Phase 6 — do not fake a paid status here | Modal exists but cannot mark PAID until Phase 6 webhook/ledger path is live — or land UI in Phase 6 with PAY-06. Prefer implement fully in Phase 6; this task is the reception UX that Phase 6 must include | Not Started | UI | Implement with PAY-02 in Phase 6; listed here so PDF §6 is not skipped in the Reception phase map
37 | 312 | UI | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.1 | PAY-01 | Consultation fee configuration — each doctor’s fee set and displayed to patients | PAY-01.03 | Doctor profile fee tab + later public doctor card | New | Payments | §9 | Consultation fee configuration | Each doctor’s fee set and displayed to patients | Doctor profile + Public + Admin | Web SPA | Yes | No | No | Yes | No | No | P0 | M | PAY-01.02 | — | Web, QA | PAY-01.02 | No ConsultFeeConfig; doctor profile work in DOC-10 may have stored a fee field | ConsultFeeConfig (InClinic, EConsult, optional Instant surcharge, PayAtClinicEnabled, GST flags) | Fee shown to patients matches what checkout charges; admin/doctor can update | Not Started | UI
38 | 320 | UI | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.3 | PAY-03 | Online consultation payment — patient pays by card, UPI, netbanking or wallet | PAY-03.03 | Public /book/pay/:bookingId using Razorpay pattern from Widgets.js but consult order API | New | Payments | §9 + §4 + §2.3 | Online consultation payment | Patient pays by card, UPI, netbanking or wallet / Pay the consultation fee at the time of booking / Pay the consultation fee inside the app | Public web + later Patient app | Web SPA | Yes | No | No | Yes | No | No | P0 | M | PAY-03.02 | — | Web, QA | PAY-03.02 | Does not exist (only S1 SaaS) | CreateConsultOrder attached to PatientAppId; Razorpay Checkout; webhook sets PAID; do not overload PackageEntryDetail | Paid appointment unlocks tele queue rules; doctor sees PAID; Account sees ledger row (Phase 7) | Not Started | UI
39 | 325 | UI | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.4 | PAY-04 | Reception payment collection — cash, UPI, card or payment link with printed receipt | PAY-04.03 | Reception collect modal: amount, method, GST placeholder, print receipt | New | Payments | §9 + §6 | Reception payment collection | Cash, UPI, card or payment link with printed receipt | Reception Portal | Web SPA | Yes | No | No | Yes | No | No | P0 | M | PAY-04.02 | — | Web, QA | PAY-04.02 | Does not exist | CollectAtReception writes ledger S3; print receipt; payment-link uses same Razorpay order as online | Cash still creates an immutable ledger row; receipt printable; status matches doctor list | Not Started | UI
40 | 329 | UI | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.5 | PAY-05 | Pay-at-clinic option — book now, pay at the clinic where the doctor allows it | PAY-05.02 | UI: public booking shows Pay at clinic vs Pay now; doctor list badge | New | Payments | §9 | Pay-at-clinic option | Book now, pay at the clinic where the doctor allows it | Public + Doctor + Reception | Web SPA | Yes | No | No | No | No | No | P1 | S | PAY-05.01 | — | Web, QA | PAY-05.01 | Does not exist | PayAtClinicEnabled on fee config; appointment PaymentStatus=PAY_AT_CLINIC; tele queue may still require PAID (policy) | If doctor disables pay-at-clinic, public checkout requires online pay | Not Started | UI
41 | 332 | UI | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.6 | PAY-06 | Doctor subscription payment — buy and renew subscription packages (complete remaining ~30%) | PAY-06.02 | Widgets.js: handle failed pay; show invoice when Phase 7 invoice exists | Existing Improvement | Payments | §9 | Doctor subscription payment | Buy and renew subscription packages | Doctor Web Portal | Web SPA | Yes | No | No | No | No | No | P1 | S | PAY-06.01 | — | Web, QA | PAY-06.01 | Checkout works ~70%; no webhook, refund, invoice, GST, Account ledger | Same webhook spine; write S1 ledger; invoice; failed pay UX; PackageEntryDetail shape UNCHANGED | SaaS pay verified by webhook; doctor plan flags update without trusting client callback alone | Not Started | UI
42 | 338 | UI | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.8 | PAY-08 | Payment status everywhere — doctor, reception and patient all see the same payment status | PAY-08.02 | Surface badges: doctor, reception; public confirmation page; patient app in Phase 16 consumes same API | New | Payments | §9 | Payment status everywhere | Doctor, reception and patient all see the same payment status | All | Web SPA | Yes | No | No | No | No | No | P0 | S | PAY-08.01 | — | Web, QA | PAY-08.01 | No shared status | Single PaymentStatus on appointment/order; all DTOs read it; never a second client-only flag | Doctor list, reception queue, public booking confirmation, later patient app show identical status for the same id | Not Started | UI
43 | 342 | UI | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.9 | PAY-09 | Refunds — processed and tracked against the original payment | PAY-09.03 | Account refund screen in Phase 7; patient payments list in Phase 16 | New | Payments | §9 + §8 + §2.8 | Refunds | Processed and tracked against the original payment / Issue and track refunds | Account + Patient | Web SPA | Yes | No | No | Yes | No | No | P0 | M | PAY-09.02 | — | Web, QA | PAY-09.02 | Does not exist | Refund entity against original PaymentOrder; Razorpay refund API; cancel-appointment hook; patient sees status | Refund cannot exceed captured amount; original payment remains visible; appointment status REFUNDED/partial as designed | Not Started | UI
44 | 347 | UI | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.10 | PAY-10 | Payment receipts & invoices — issued for every transaction | PAY-10.03 | Print/download on reception, doctor (subscription), later patient app | New | Payments | §9 + §8 | Payment receipts & invoices | Issued for every transaction / Invoice numbering and tax reporting | All | Web SPA | Yes | No | No | Yes | No | No | P1 | M | PAY-10.02 | — | Web, QA | PAY-10.02 | No invoice entity | Invoice numbering series from PRE-02; PDF receipt; GST fields; email in Phase 12 | Every PAID consult/subscription/medicine has a retrievable receipt number | Not Started | UI
45 | 354 | UI | 7 | Phase 7 — Account & finance department (PDF §8) | 7.1 | FIN-01 | Unified transaction ledger — every rupee that moves through the platform, in one record | FIN-01.03 | /account/ledger UI — Account layout sidebar Finance | New | Account | §8 | Unified transaction ledger | Every rupee that moves through the platform, in one record | Account Portal | Web SPA | Yes | No | No | Yes | No | No | P0 | M | FIN-01.02 | — | Web, QA | FIN-01.02 | Does not exist | Append-only LedgerEntry for S1–S7; filters; OTP audit link; Admin may view, Account owns movement | No money movement without a ledger row; rows are immutable | Not Started | UI
46 | 358 | UI | 7 | Phase 7 — Account & finance department (PDF §8) | 7.2 | FIN-02 | Consultation payment reconciliation — online payments and reception collections matched and verified | FIN-02.03 | /account/consult-recon and /admin/consult-payments (same data, Account owns, Admin views) | New | Account | §8 + §7.2 + §16 | Consultation payment reconciliation | Online payments and reception collections matched and verified / Match every booking against every payment | Account + Admin | Web SPA | Yes | No | No | Yes | No | No | P0 | M | FIN-02.02 | — | Web, QA | FIN-02.02 | Does not exist | Join booking ↔ payment ↔ appointment; KPI collected/pending/failed/refunded; CSV | Every paid booking has exactly one captured consult payment or an exception | Not Started | UI
47 | 362 | UI | 7 | Phase 7 — Account & finance department (PDF §8) | 7.3 | FIN-03 | Medicine ledger — medicine money tracked separately from consultation money | FIN-03.03 | /account/medicine-ledger UI (empty until HomeoMeds orders exist — still ship the screen) | New | Account | §8 + §12 | Medicine ledger | Medicine money tracked separately from consultation money / Seller, platform and delivery shares recorded separately from consultation money | Account Portal | Web SPA | Yes | No | No | Yes | No | No | P1 | M | FIN-03.02 | — | Web, QA | FIN-03.02 | Does not exist | /account/medicine-ledger; Stream=MEDICINE; seller/platform/delivery split columns; filled in Phase 14 | Medicine GMV query cannot include consult fees | Not Started | UI
48 | 366 | UI | 7 | Phase 7 — Account & finance department (PDF §8) | 7.4 | FIN-04 | Settlement runs — scheduled settlement of amounts due to doctors and pharmacies | FIN-04.03 | /account/settlements | New | Account | §8 + §16 | Settlement runs | Scheduled settlement of amounts due to doctors and pharmacies | Account Portal | Web SPA | Yes | No | No | Yes | No | No | P0 | M | FIN-04.02 | — | Web, QA | FIN-04.02 | Does not exist | SettlementRun job T+N hold; net of commission/GST/refunds; pharmacies after Phase 14 | A settlement run is replayable and lists included transactions | Not Started | UI
49 | 370 | UI | 7 | Phase 7 — Account & finance department (PDF §8) | 7.5 | FIN-05 | Payout approval — payouts released only after OTP-verified approval | FIN-05.03 | /account/payouts | New | Account | §8 + §17 | Payout approval | Payouts released only after OTP-verified approval | Account Portal | Web SPA | Yes | No | No | Yes | No | No | P0 | M | FIN-05.02 | — | Web, QA | FIN-05.02 | Does not exist | ApprovePayout requires SEC-07 OTP; Admin cannot approve; NEFT/file or gateway per PRE-01 | Payout without OTP fails; audit shows who approved | Not Started | UI
50 | 373 | UI | 7 | Phase 7 — Account & finance department (PDF §8) | 7.6 | FIN-06 | Refund processing — Account issues and tracks refunds (uses PAY-09) | FIN-06.01 | UI /account/refunds: original payment, amount, reason, status | New | Account | §8 | Refund processing | Issue and track refunds | Account Portal | Web SPA | Yes | No | No | Yes | No | No | P0 | M | — | — | Web, QA |  | Does not exist | /account/refunds UI on PAY-09 APIs; OTP if policy requires | Account can issue refund; patient status updates; ledger reverses | Not Started | UI
51 | 378 | UI | 7 | Phase 7 — Account & finance department (PDF §8) | 7.7 | FIN-07 | Payment exception handling — investigate and resolve every failed or disputed payment | FIN-07.03 | /account/exceptions and /admin/payment-exceptions (same queue) | New | Account | §8 + §7.2 | Payment exception handling | Investigate and resolve every failed or disputed payment / Every failed or mismatched payment surfaced for action | Account + Admin | Web SPA | Yes | No | No | Yes | No | No | P0 | M | FIN-07.02 | — | Web, QA | FIN-07.02 | Does not exist | Exception queue Failed/Partial/Webhook-mismatch/Refund-pending; retry/resolve with OTP on manual reconcile | Nothing failed is silent; resolve writes audit | Not Started | UI
52 | 382 | UI | 7 | Phase 7 — Account & finance department (PDF §8) | 7.8 | FIN-08 | GST & invoice reports — invoice numbering and tax reporting | FIN-08.03 | /account/tax | New | Account | §8 + §16 | GST & invoice reports | Invoice numbering and tax reporting | Account Portal | Web SPA | Yes | No | No | Yes | No | No | P1 | M | FIN-08.02 | — | Web, QA | FIN-08.02 | Does not exist | /account/tax export using Invoice table and PRE-02 GST treatment — configuration not hardcoded | Date-range GST report matches invoices issued | Not Started | UI
53 | 386 | UI | 7 | Phase 7 — Account & finance department (PDF §8) | 7.9 | FIN-09 | Payee records — bank and KYC details for doctors and pharmacies | FIN-09.03 | /account/payees | New | Account | §8 | Payee records | Bank and KYC details for doctors and pharmacies | Account Portal | Web SPA | Yes | No | No | Yes | No | No | P1 | M | FIN-09.02 | — | Web, QA | FIN-09.02 | Doctor bank fields added in DOC-10; no Account UI; no pharmacy | /account/payees; OTP on doctor KYC change (fraud); pharmacies after Phase 14 | Payout cannot run to a payee missing KYC | Not Started | UI
54 | 390 | UI | 7 | Phase 7 — Account & finance department (PDF §8) | 7.10 | FIN-10 | Clinic collection view — cash and UPI collected at reception, per clinic and per day | FIN-10.03 | /account/clinic-collections | New | Account | §8 | Clinic collection view | Cash and UPI collected at reception, per clinic and per day | Account Portal | Web SPA | Yes | No | No | Yes | No | No | P1 | M | FIN-10.02 | — | Web, QA | FIN-10.02 | Does not exist | /account/clinic-collections from CollectAtReception rows; respect PRE-02 retain vs remit | Per clinic per day cash/UPI totals match reception receipts | Not Started | UI
55 | 396 | UI | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.1 | TRU-01 | Doctor credentialing — doctors upload qualification and registration documents for review | TRU-01.03 | Doctor profile credentials tab + document upload | New | Trust | §13 + §7.2 | Doctor credentialing | Doctors upload qualification and registration documents for review | Doctor Web + Admin | Web SPA | Yes | No | No | Yes | No | No | P0 | M | TRU-01.02 | — | Web, QA | TRU-01.02 | RegisterDoctor activates immediately; PassingUniversity/CertNo/QualificationId exist; no document store/queue | DoctorCredentialDocument + VerificationStatus Pending; do not auto-activate practice for public directory | New registrations sit in Pending with documents; existing doctors backfill per PRE-03 | Not Started | UI
56 | 400 | UI | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.2 | TRU-02 | Verification review — Admin approves, rejects or requests further information | TRU-02.03 | /admin/doctor-credentialing and /:doctorId; verification column on users list | New | Trust | §13 + §7.2 | Verification review | Admin approves, rejects or requests more information before they can practise on the platform | Admin Portal | Web SPA | Yes | No | No | Yes | No | No | P0 | M | TRU-02.02 | — | Web, QA | TRU-02.02 | Does not exist | /admin/doctor-credentialing list + detail; email notify doctor | Approve/reject/request-info all audited; doctor sees status | Not Started | UI
57 | 404 | UI | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.3 | TRU-03 | Verified badge — patients see which doctors have been verified | TRU-03.02 | Badge component for website (Phase 9) and patient app (Phase 16) | New | Trust | §13 + §2.2 | Verified badge / Credentials & verification | Patients see which doctors have been verified / Verified badge showing the doctor’s credentials are checked | Public + Patient app | Web SPA | Yes | No | No | No | No | No | P0 | S | TRU-03.01 | — | Web, QA | TRU-03.01 | Does not exist | Badge on public doctor card and profile from VerificationStatus=Approved | Unverified doctors never show a verified badge | Not Started | UI
58 | 411 | UI | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.5 | TRU-05 | Patient reviews — patients rate and review consultations | TRU-05.03 | Public doctor profile reviews; patient app write flow Phase 16 | New | Trust | §13 + §2.8 | Patient reviews / Write a review | Patients rate and review consultations / Rate and review the consultation | Patient + Public | Web SPA | Yes | No | No | Yes | No | No | P1 | M | TRU-05.02 | — | Web, QA | TRU-05.02 | Does not exist | Review linked to PatientAppId; one review per visit; moderation flag optional | Review only after completed consult; doctor cannot write self-reviews | Not Started | UI
59 | 415 | UI | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.6 | TRU-06 | Review appeal — doctors can appeal a review; patients manage reviews and raise an appeal | TRU-06.03 | Doctor dashboard my-reviews; admin queue | New | Trust | §13 + §2.8 | Review appeal / My reviews & appeal | Doctors can appeal a review / Manage reviews and raise an appeal | Doctor + Patient + Admin | Web SPA | Yes | No | No | Yes | No | No | P2 | M | TRU-06.02 | — | Web, QA | TRU-06.02 | Does not exist | Appeal entity; admin resolves; patient my-reviews list | Appealed review hidden or marked pending per policy; admin decision audited | Not Started | UI
60 | 419 | UI | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.7 | TRU-07 | Ranking transparency — patients are shown why doctors are ranked as they are | TRU-07.03 | Search results: Why this order? panel | New | Trust | §13 + §2.2 | Ranking transparency / Ranking explanation | Patients are shown why doctors are ranked as they are / Transparent explanation of why doctors appear in a given order | Public + Patient app | Web SPA | Yes | No | No | Yes | No | No | P1 | M | TRU-07.02 | — | Web, QA | TRU-07.02 | Does not exist | Documented ranking factors (verified, availability, fee, reviews, experience) + explain API/UI | Each search result has an explain link that matches the sort order | Not Started | UI
61 | 423 | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.1 | WEB-01 | Product home page — complete public website presenting the service | WEB-01.03 | HomeLandingPage: book, verified doctors, pricing teaser, store badges; strip leftover job-board feel | Existing Improvement | Patient Website | §4 | Product home page | Complete public website presenting the service | Patient Website | Web SPA | Yes | No | No | Yes | No | No | P1 | M | WEB-01.02 | — | Web, QA | WEB-01.02 | HomeoJobLanding ~50%; Velzon leftovers; CTAs incomplete for book/trust/apps | Book CTA, verified doctors, consult+SaaS pricing teaser, app download placeholders | Unauthenticated user can go Home → Book without calling the clinic | Not Started | UI
62 | 425 | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.2 | WEB-02 | Consultation & subscription pricing — transparent pricing display | WEB-02.01 | Public doctor card shows in-clinic and tele fee | Existing Improvement | Patient Website | §4 | Consultation & subscription pricing | Transparent pricing display | Patient Website | Web SPA | Yes | No | No | Yes | No | No | P1 | S | — | — | QA |  | SaaS package marketing /pricing exists; no consult fee display per doctor | Keep SaaS pricing; add consult fee on doctor cards from ConsultFeeConfig | Patient sees consult fee before booking; doctor SaaS pricing still shown for doctors buying plans | Not Started | UI
63 | 426 | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.2 | WEB-02 | Consultation & subscription pricing — transparent pricing display | WEB-02.02 | /pricing remains SaaS packages for doctors; label it clearly vs patient consult fees | Existing Improvement | Patient Website | §4 | Consultation & subscription pricing | Transparent pricing display | Patient Website | Web SPA | Yes | No | No | No | No | No | P1 | S | WEB-02.01 | T-62 (WEB-02.01) | QA |  | SaaS package marketing /pricing exists; no consult fee display per doctor | Keep SaaS pricing; add consult fee on doctor cards from ConsultFeeConfig | Patient sees consult fee before booking; doctor SaaS pricing still shown for doctors buying plans | Not Started | UI
64 | 430 | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.3 | WEB-03 | Doctor discovery — browse and search verified doctors | WEB-03.03 | /book list + filters + doctor profile page | New | Patient Website | §4 + §2.2 | Doctor discovery | Browse and search verified doctors | Patient Website | Web SPA | Yes | No | No | Yes | No | No | P0 | M | WEB-03.02 | — | Web, QA | WEB-03.02 | Does not exist as a patient product (marketing only) | /book search: name, condition, category; filters availability, fee, experience, language, location | Only verified doctors; ranking explanation available (TRU-07) | Not Started | UI
65 | 434 | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.4 | WEB-04 | Self-service booking — book an appointment online without calling the clinic | WEB-04.03 | /book/:doctorId/slots; /book/confirm; booking success | New | Patient Website | §4 + §2.3 | Self-service booking | Book an appointment online without calling the clinic | Patient Website | Web SPA | Yes | No | No | Yes | No | No | P0 | M | WEB-04.02 | — | Web, QA | WEB-04.02 | Staff-only appointments | Funnel /book/:id/slots → review+consent → create Patient+Appointment; OTP; rate-limit; respect schedule + unpaid hold policy PRE-03 | Slot no longer free after confirmed booking; consent written to ConsentRecord | Not Started | UI
66 | 436 | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.5 | WEB-05 | Online consultation payment on website — pay the fee at the time of booking | WEB-05.01 | /book/pay/:bookingId + success/failure pages | New | Patient Website | §4 + §9 | Online consultation payment | Pay the consultation fee at the time of booking | Patient Website | Web SPA | Yes | No | No | Yes | No | Yes | P0 | M | — | — | QA |  | Does not exist | Checkout uses PAY-03; success/fail pages; pay-at-clinic branch from PAY-05 | Closing the tab does not lose a captured payment (PAY-02) | Not Started | UI
67 | 440 | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.6 | WEB-06 | Contact & enquiry form — enquiries reach the admin team and are tracked | WEB-06.03 | /contact confirmation; /admin/enquiries inbox (not Velzon mailbox) | Existing Improvement | Patient Website | §4 + §15 | Contact & enquiry form | Enquiries reach the admin team and are tracked | Patient Website + Admin | Web SPA | Yes | No | No | Yes | No | No | P1 | M | WEB-06.02 | — | Web, QA | WEB-06.02 | EnquiryDetail API exists; public form partial; admin inbox screen missing | Confirmation + enquiry id; /admin/enquiries inbox; optional convert to SupportTicket | Every website enquiry is visible to admin with status | Not Started | UI
68 | 442 | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.7 | WEB-07 | Privacy policy — covering data protection, recording and pharmacy consent | WEB-07.01 | Replace /privacy content with signed legal copy; store PolicyVersion | Existing Improvement | Legal | §4 + §17 | Privacy policy | Covering data protection, recording and pharmacy consent | Patient Website | Web SPA | Yes | No | Yes | No | No | No | P0 | S | — | — | QA |  | Privacy page partial; not DPDP/tele/pharmacy complete | Publish PRE-03 legal copy: DPDP, recording, pharmacy, data-rights, family/caregiver | Versioned policy; booking consent references this version | Not Started | UI
69 | 444 | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.8 | WEB-08 | Terms of service — covering payments, refunds, telemedicine and medicine orders | WEB-08.01 | Replace /terms with signed copy; version stamp on booking/payment | Existing Improvement | Legal | §4 | Terms of service | Covering payments, refunds, telemedicine and medicine orders | Patient Website | Web SPA | Yes | No | Yes | No | No | No | P0 | S | — | — | QA |  | Terms partial | Payments, refunds, telemedicine, HomeoMeds, codes-before-names | Checkout cannot complete without accepted terms version | Not Started | UI
70 | 448 | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.9 | WEB-09 | Doctor self-registration — doctors apply to join the platform online | WEB-09.03 | /register multipart docs; pending message; status page | Existing Improvement | Patient Website | §4 | Doctor self-registration | Doctors apply to join the platform online | Public | Web SPA | Yes | No | No | Yes | No | No | P0 | M | WEB-09.02 | — | Web, QA | WEB-09.02 | RegisterDoctor ~90%; activates immediately; no document upload | Document upload; pending-verification message; TRU-01 status Pending | New doctor cannot take paid public consults until Approved | Not Started | UI
71 | 452 | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.10 | WEB-10 | Email activation — secure account activation by email link | WEB-10.03 | Login activation query param UX + expiry copy | Existing Improvement | Auth | §4 | Email activation | Secure account activation by email link | Public | Web SPA | Yes | No | No | Yes | No | No | P1 | M | WEB-10.02 | — | Web, QA | WEB-10.02 | ActivateUser via /login?UserId= ~90%; align with verification; expiry/resend incomplete | Token expiry, resend, align with credentialing (activation ≠ verified practice) | Expired link fails; resend works; activated unverified still not in directory | Not Started | UI
72 | 456 | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.11 | WEB-11 | Waitlist offer — get offered a slot when one is freed by a cancellation (patient website + later app) | WEB-11.03 | Public waitlist CTA on full days | New | Booking | §2.3 | Waitlist offer | Get offered a slot when one is freed by a cancellation | Patient Website + App | Web SPA | Yes | No | No | Yes | No | No | P2 | M | WEB-11.02 | — | Web, QA | WEB-11.02 | Cancel hook stub in Phase 4; no waitlist records | BookingWaitlist; on cancel, offer FIFO; timeout | Cancelled slot offered to waitlisted patient before returning to open search | Not Started | UI
73 | 459 | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.12 | WEB-12 | Health articles — educational content to build trust and engagement | WEB-12.01 | Public articles list/detail from existing blog/news APIs | Existing Improvement | Patient Website | §2.2 | Health articles | Educational content to build trust and engagement | Patient Website + App | Web SPA | Yes | No | No | Yes | No | No | P2 | S | — | — | QA |  | Blog/news APIs on classic exist for marketing | Reuse blog/news as health articles on public site and later patient app; admin already has news/blog | Published articles appear on public site; draft does not | Not Started | UI
74 | 463 | UI | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.1 | ERX-01 | Potency module — every remedy carries a defined potency from a managed list, no free text | ERX-01.03 | Rx modal potency picker (6C, 30C, 200C, 1M…) | New | eRx | §11 | Potency module | Every remedy carries a defined potency, selected from a managed list — no free text | Doctor Web + Admin | Web SPA | Yes | No | No | Yes | No | No | P0 | M | ERX-01.02 | — | Web, QA | ERX-01.02 | Dose saved as empty free-text dose: '' | PotencyMaster CRUD; PotencyId on PrescriptionRemedyDetail; stop empty Dose | Cannot sign eRx with missing potency | Not Started | UI
75 | 467 | UI | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.2 | ERX-02 | Dosage details — frequency, duration and instructions recorded clearly | ERX-02.03 | Rx row UI for the three fields | New | eRx | §11 | Dosage details | Frequency, duration and instructions recorded clearly | Doctor Web Portal | Web SPA | Yes | No | No | Yes | No | No | P0 | M | ERX-02.02 | — | Web, QA | ERX-02.02 | Unstructured/empty dose | Frequency, Duration, Instructions fields on each remedy line | Print/PDF shows frequency, duration, instructions | Not Started | UI
76 | 471 | UI | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.3 | ERX-03 | Visit notes kept separate from the prescription — private clinical notes never appear on the prescription given to the patient or pharmacy | ERX-03.03 | Move History Notes out of Rx modal; note types Chief complaint / Follow-up / General | New | eRx | §11 + §5.3 | Visit notes kept separate from the prescription | The doctor’s private clinical notes never appear on the prescription given to the patient or pharmacy | Doctor Web Portal | Web SPA | Yes | No | No | Yes | No | No | P0 | M | ERX-03.02 | — | Web, QA | ERX-03.02 | History notes mixed into Rx modal tabs | Visit Notes panel outside Rx; NoteType; IsErxExcluded; eRx print has remedies+labs only | Patient PDF and pharmacy payload contain zero private note text | Not Started | UI
77 | 475 | UI | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.4 | ERX-04 | Signed digital prescription — issued and locked once signed, so it cannot be altered afterwards | ERX-04.03 | Sign button; locked badge on board header | New | eRx | §11 + §2.5 + §5.3 | Signed digital prescription | Issued and locked once signed, so it cannot be altered afterwards / Official prescription issued by the doctor | Doctor Web | Web SPA | Yes | No | No | Yes | No | No | P0 | M | ERX-04.02 | — | Web, QA | ERX-04.02 | SavePrescriptionDetail overwritable; no lock/sign | ErxSnapshot immutable on sign; subsequent edits create a new unsigned draft not a silent mutate | Signed snapshot hash stable; UI cannot edit locked lines | Not Started | UI
78 | 478 | UI | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.5 | ERX-05 | Prescription history — every prescription stored against the patient and visit | ERX-05.02 | Doctor history panel lists signed eRx; patient timeline in Phase 16 | New | eRx | §11 | Prescription history | Every prescription stored against the patient and visit | Doctor + Patient | Web SPA | Yes | No | No | No | No | No | P1 | S | ERX-05.01 | — | Web, QA | ERX-05.01 | Rx saved per appointment but no signed history product | List snapshots by PatientId; open past visit eRx | All signed eRx retrievable by patient and treating doctor | Not Started | UI
79 | 481 | UI | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.6 | ERX-06 | Patient view of prescription in app — patient sees the prescription immediately (codes until pharmacy accept) | ERX-06.02 | Web confirmation/records page can show the same payload before the app exists | New | eRx | §11 + §2.5 | Patient view in app | Patient sees the prescription immediately in the app | Patient App + Website | Web SPA | Yes | No | No | No | No | No | P0 | S | ERX-06.01 | — | Web, QA | ERX-06.01 | No patient surface | Patient GET eRx by appointment; names redacted until Phase 14 accept; website optional view | Immediately after sign, patient API returns codes (or names if no HomeoMeds order required for in-clinic dispense policy — document) | Not Started | UI
80 | 484 | UI | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.7 | ERX-07 | Print & PDF — printable and downloadable prescription | ERX-07.02 | Print/Download on doctor board and later patient app | New | eRx | §11 | Print & PDF | Printable and downloadable prescription | Doctor + Patient | Web SPA | Yes | No | No | No | No | No | P1 | S | ERX-07.01 | — | Web, QA | ERX-07.01 | No eRx PDF | Patient copy without notes; doctor copy may include letterhead; SecureDocument store | PDF matches signed snapshot; notes absent on patient copy | Not Started | UI
81 | 492 | UI | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.10 | ERX-10 | Repeat prescription / refill — patient requests; doctor approves or rejects from the mobile app (inbox on web too) | ERX-10.03 | Doctor web inbox; doctor app in Phase 17; patient app in Phase 16 | New | eRx | §11 + §3 + §2.7 | Repeat prescription / refill | Patient requests a refill; doctor approves or rejects from the mobile app | Patient + Doctor mobile + Doctor web | Web SPA | Yes | No | No | Yes | No | No | P1 | M | ERX-10.02 | — | Web, QA | ERX-10.02 | Does not exist | RefillRequest against ErxSnapshot; doctor inbox; no case-taking on mobile | Reject/approve audited; approved refill creates a new order draft not an editable old snapshot | Not Started | UI
82 | 498 | UI | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.1 | TEL-01 | Doctor availability — online or offline status and working hours | TEL-01.03 | Dashboard toggle Online for teleconsult | New | Telemedicine | §10 + §3 | Doctor availability | Doctor sets online or offline status and working hours | Doctor Web + Doctor App | Web SPA | Yes | No | No | Yes | No | No | P0 | M | TEL-01.02 | — | Web, QA | TEL-01.02 | E-CONSULT status + WhatsApp video stub only; no availability | TeleAvailability + heartbeat; working hours reuse daily schedule | Offline doctor cannot be offered instant consult | Not Started | UI
83 | 502 | UI | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.2 | TEL-02 | Telemedicine waiting queue — who is waiting, how long, whether they have paid | TEL-02.03 | Dedicated Tele queue on dashboard (beyond E-CONSULT list) | New | Telemedicine | §10 + §3 | Telemedicine waiting queue | Doctor sees who is waiting, for how long, and whether they have paid | Doctor Web + App | Web SPA | Yes | No | No | Yes | No | No | P0 | M | TEL-02.02 | — | Web, QA | TEL-02.02 | E-CONSULT list only | Queue by doctor + Online + paid/confirmed; wait time; Join | Unpaid patients do not join if policy requires PAID | Not Started | UI
84 | 507 | UI | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.3 | TEL-03 | Video consultation in browser — doctor consults directly from the web portal | TEL-03.03 | Full-page video room mute/end | New | Telemedicine | §10 | Video consultation in browser | Doctor consults directly from the web portal | Doctor Web Portal | Web SPA | Yes | No | No | Yes | No | No | P0 | M | TEL-03.02 | — | Web, QA | TEL-03.02 | SweetAlert WhatsApp stub | /teleconsult/:sessionId in-browser video; replace stub; vendor from PRE-03 | Doctor and patient in same room linked to PatientAppId | Not Started | UI
85 | 512 | UI | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.5 | TEL-05 | Device check — camera, microphone and connection tested before joining | TEL-05.01 | Shared device-check component (web); mobile equivalent in Phase 16 | New | Telemedicine | §10 + §2.4 | Device check | Camera, microphone and connection tested before joining | Doctor Web + Patient | Web SPA | Yes | No | No | No | No | No | P1 | M | — | — | QA |  | Does not exist | Pre-join device/network check UI; block join on hard fail with guidance | User sees camera/mic/network result before entering the room | Not Started | UI
86 | 516 | UI | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.6 | TEL-06 | Waiting room — patient waits with live status until the doctor joins | TEL-06.03 | Waiting room UI on web (and app later) | New | Telemedicine | §10 + §2.4 | Waiting room | Patient waits with live status / Wait with live status until the doctor joins | Patient | Web SPA | Yes | No | No | Yes | No | No | P1 | M | TEL-06.02 | — | Web, QA | TEL-06.02 | Does not exist | Waiting room page: position, doctor online, paid, estimated wait | Status updates without refresh (poll/SignalR) | Not Started | UI
87 | 520 | UI | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.7 | TEL-07 | Recording consent — consent captured before the consultation; no recording without it | TEL-07.03 | Pre-join modal both sides | New | Telemedicine | §10 + §2.4 + §17 | Recording consent | Consent captured before the consultation; no recording without it / Explicit consent requested before any recording | Patient + Doctor | Web SPA | Yes | No | No | Yes | No | No | P0 | M | TEL-07.02 | — | Web, QA | TEL-07.02 | AudioCaseConsentLog only for audio case taking | ConsentRecord type TeleRecording; block record if declined; both sides see status | Recording pipeline cannot start if consent denied | Not Started | UI
88 | 523 | UI | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.8 | TEL-08 | Rejoin after dropped call — either side can rejoin the same consultation | TEL-08.02 | UI Rejoin on doctor dashboard and patient waiting/call fail | New | Telemedicine | §10 + §2.4 | Rejoin after dropped call | Either side can rejoin the same consultation / Rejoin the same consultation if the connection drops | Doctor + Patient | Web SPA | Yes | No | No | No | No | No | P0 | S | TEL-08.01 | — | Web, QA | TEL-08.01 | Does not exist | Session Active until End; rejoin tokens; dashboard Rejoin | Drop and rejoin same PatientAppId session; End prevents rejoin | Not Started | UI
89 | 526 | UI | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.9 | TEL-09 | Join failure handling — clear fallback if the call cannot connect, with options to retry | TEL-09.02 | Fallback UI: retry, rejoin, contact support | New | Telemedicine | §10 + §2.4 | Join failure handling / Fallback & join failure handling | Clear fallback if the call cannot connect / Clear guidance if the call fails, with options to retry | Doctor + Patient | Web SPA | Yes | No | No | No | No | No | P1 | S | TEL-09.01 | — | Web, QA | TEL-09.01 | Does not exist | Error codes; retry; support ticket deep link later; do not silently fail | Every join failure has a user-visible next action | Not Started | UI
90 | 530 | UI | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.10 | TEL-10 | Case-linked chat — chat attached to the consultation record, not a loose message thread | TEL-10.03 | In-room chat panel | New | Telemedicine | §10 + §2.4 | Case-linked chat | Chat attached to the consultation record / Chat tied to the consultation, not a loose message thread | Doctor + Patient | Web SPA | Yes | No | No | Yes | No | No | P1 | M | TEL-10.02 | — | Web, QA | TEL-10.02 | Does not exist | Messages keyed by TeleSession/PatientAppId; retained with the case | Chat not visible on a different appointment | Not Started | UI
91 | 534 | UI | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.11 | TEL-11 | Consultation summary — issued to the patient at the end of the call | TEL-11.03 | Post-call summary form; patient view | New | Telemedicine | §10 + §2.4 | Consultation summary | Issued to the patient at the end of the call / Written summary available immediately after the call | Patient + Doctor | Web SPA | Yes | No | No | Yes | No | No | P1 | M | TEL-11.02 | — | Web, QA | TEL-11.02 | Does not exist | Doctor submits summary (not private notes); patient sees immediately; may share eRx id | Summary available without waiting for signed eRx if doctor issues it first | Not Started | UI
92 | 538 | UI | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.12 | TEL-12 | Instant consultation — patient requests an immediate consultation with an available doctor | TEL-12.03 | Patient instant CTA; doctor offer banner | New | Telemedicine | §10 + §2.3 | Instant consultation / Instant consult request / Queue & doctor offer | Patient can request an immediate consultation with an available doctor / See position in queue and accept an offered doctor | Patient + Doctor | Web SPA | Yes | No | No | Yes | No | No | P1 | M | TEL-12.02 | — | Web, QA | TEL-12.02 | Does not exist | Instant request pool; offer doctor; patient accepts; optional surcharge from fee config | Offline doctors never offered; patient can decline an offered doctor | Not Started | UI
93 | 542 | UI | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.1 | COM-01 | SMS — appointment confirmation, registration confirmation, doctor-unavailable, OTP, reschedule and cancellation | COM-01.03 | Doctor /doctor/sms enable-per-event; admin templates | New | Notifications | §14 | SMS | Appointment confirmation, registration confirmation, doctor-unavailable notice, OTP, reschedule and cancellation alerts | Shared | Web SPA | Yes | No | No | Yes | No | No | P0 | M | COM-01.02 | — | Web, QA | COM-01.02 | No SMS provider; WhatsApp exists separately | SmsProvider + templates + DLT; event hooks; DND/opt-out on Patient | Each listed event can send SMS; notify failure does not roll back the business transaction | Not Started | UI
94 | 547 | UI | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.2 | COM-02 | WhatsApp — templates, offers, health tips and bulk messaging with delivery reports and opt-out (complete remaining ~50%) | COM-02.03 | WhatsAppModal: campaign status, failures, opt-out | Existing Improvement | Notifications | §14 | WhatsApp | Templates, offers, health tips and bulk messaging to patients, with delivery reports and opt-out | Doctor Web | Web SPA | Yes | No | No | Yes | No | No | P1 | M | COM-02.02 | — | Web, QA | COM-02.02 | Meta Cloud send/templates/campaigns live; bulk/opt-in/analytics incomplete | Finish bulk queue UX, template approval states, delivery reports, opt-out | Bulk campaign shows delivered/failed; opted-out patients excluded | Not Started | UI
95 | 551 | UI | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.3 | COM-03 | Push notifications — booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests | COM-03.03 | Server event hooks (apps consume in 16–17) | New | Notifications | §14 + §2.9 + §3 | Push notifications | Booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests / Patient waiting, new booking, reschedule, cancellation, refill request, payment received | Patient App + Doctor App | Web SPA | Yes | No | No | Yes | No | No | P0 | M | COM-03.02 | — | Web, QA | COM-03.02 | Does not exist | DeviceToken + FCM/APNs; event fan-out; apps register tokens in Phases 16–17 | Each listed event has a template; unregister on logout | Not Started | UI
96 | 556 | UI | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.4 | COM-04 | Email — registration, activation, password reset, invoices and receipts | COM-04.03 | No new public page — transactional only | Existing Improvement | Notifications | §14 | Email | Registration, activation, password reset, invoices and receipts | Shared | Web SPA | Yes | No | No | Yes | No | No | P1 | M | COM-04.02 | — | Web, QA | COM-04.02 | SMTP used for activation/forgot (plaintext issue fixed in Phase 0); no invoice email | Template emails for listed events; invoice PDF attach via SEC-09 | Each listed event has an email; bounce logged | Not Started | UI
97 | 560 | UI | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.5 | COM-05 | In-app notification centre — all alerts collected in one place for patients and doctors | COM-05.03 | Doctor web bell; patient/doctor app centres in 16–17 | New | Notifications | §14 + §2.8 | In-app notification centre / Notifications centre | All alerts collected in one place for patients and doctors / All alerts in one place | Patient App + Doctor Web/App | Web SPA | Yes | No | No | Yes | No | No | P1 | M | COM-05.02 | — | Web, QA | COM-05.02 | Does not exist (Velzon notification demo is not product) | AppNotification inbox; mark read; do not use Velzon demo notifications | Same events as push appear in-app if push is denied | Not Started | UI
98 | 564 | UI | 13 | Phase 13 — Support & help desk (PDF §15) | 13.1 | SUP-01 | Patient support tickets — patients raise issues from the app and track them | SUP-01.03 | Patient app screens in Phase 16; web help optional | New | Support | §15 + §2.9 | Patient support tickets / Help centre & support tickets | Patients raise issues from the app and track them to resolution | Patient App + Admin | Web SPA | Yes | No | No | Yes | No | No | P1 | M | SUP-01.02 | — | Web, QA | SUP-01.02 | Does not exist; EnquiryDetail is not tickets; Velzon tickets demo ignore | SupportTicket reporter=Patient; status track; not Enquiry, not Velzon /apps-tickets-* | Patient sees status changes; cannot see other patients’ tickets | Not Started | UI
99 | 567 | UI | 13 | Phase 13 — Support & help desk (PDF §15) | 13.2 | SUP-02 | Doctor support tickets — doctors raise issues from the portal | SUP-02.02 | /doctor/support list/create/detail | New | Support | §15 | Doctor support tickets | Doctors raise issues from the portal | Doctor Web + Admin | Web SPA | Yes | No | No | No | No | No | P1 | M | SUP-02.01 | — | Web, QA | SUP-02.01 | Does not exist | Same ticket tables; reporter=Doctor | Doctor portal has Raise issue; tracks to resolution | Not Started | UI
100 | 571 | UI | 13 | Phase 13 — Support & help desk (PDF §15) | 13.3 | SUP-03 | Admin issue queue — all issues in one queue with priority, assignment and status | SUP-03.03 | /admin/support-tickets and /:id | New | Support | §15 + §7.2 | Admin issue queue / Support ticket queue | All issues in one queue with priority, assignment and status / All patient and doctor issues in one queue with assignment and resolution | Admin Portal | Web SPA | Yes | No | No | Yes | No | No | P1 | M | SUP-03.02 | — | Web, QA | SUP-03.02 | Does not exist | /admin/support-tickets; SLA timestamps; assign | Patient and doctor tickets in one queue; assignable | Not Started | UI
101 | 574 | UI | 13 | Phase 13 — Support & help desk (PDF §15) | 13.4 | SUP-04 | Ticket conversation — full message thread with attachments | SUP-04.02 | Detail UI thread | New | Support | §15 | Ticket conversation | Full message thread with attachments | Admin + Doctor + Patient | Web SPA | Yes | No | No | No | No | No | P1 | M | SUP-04.01 | — | Web, QA | SUP-04.01 | Does not exist | Threaded messages + SEC-09 attachments | Both sides see the same thread order | Not Started | UI
102 | 576 | UI | 13 | Phase 13 — Support & help desk (PDF §15) | 13.5 | SUP-05 | Enquiry management — website enquiries tracked (ties WEB-06) | SUP-05.01 | Admin enquiry inbox SLA fields | Existing Improvement | Support | §15 + §4 | Enquiry management | Website enquiries reach the admin team and are tracked | Admin Portal | Web SPA | Yes | No | No | Yes | No | No | P1 | S | — | — | QA |  | API exists; inbox missing | Complete WEB-06 admin inbox if not already; convert enquiry → ticket optional | No enquiry is only in email | Not Started | UI
103 | 580 | UI | 13 | Phase 13 — Support & help desk (PDF §15) | 13.6 | SUP-06 | Help centre — self-service help content for patients | SUP-06.03 | Help centre list/detail | New | Support | §15 + §2.9 | Help centre | Self-service help content for patients | Patient Website + App | Web SPA | Yes | No | No | Yes | No | No | P2 | M | SUP-06.02 | — | Web, QA | SUP-06.02 | Does not exist | CMS articles or static help; searchable | Patient can open help without raising a ticket | Not Started | UI
104 | 584 | UI | 13 | Phase 13 — Support & help desk (PDF §15) | 13.7 | SUP-07 | Assisted booking — help for patients who need support booking | SUP-07.03 | Patient CTA; admin/reception assisted-book wizard | New | Support | §15 + §2.9 | Assisted booking | Support for patients who need help booking / Help for patients who need support booking | Support + Reception + Patient | Web SPA | Yes | No | No | Yes | No | No | P2 | M | SUP-07.02 | — | Web, QA | SUP-07.02 | Does not exist | Staff (admin/support/reception) can complete public booking on behalf of a patient with audit; patient app CTA to request assistance | Assisted booking appears in audit as staff-created; patient still owns the appointment | Not Started | UI
105 | 588 | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.1 | MED-01 | Pharmacy partner onboarding — licensed premises, licence records, activation checklist | MED-01.03 | /pharmacy/onboard; /admin pharmacy partners | New | HomeoMeds | §12 + §7.2 | Pharmacy partner onboarding / Pharmacy partner management | Licensed premises registered with licence records and an activation checklist / Onboard and activate licensed pharmacies | Pharmacy + Admin | Web SPA | Yes | No | No | Yes | No | No | P0 | M | MED-01.02 | — | Web, QA | MED-01.02 | Does not exist | PharmacyPartner + licences; admin activation; pharmacy console login | Unactivated pharmacy cannot receive orders | Not Started | UI
106 | 591 | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.2 | MED-02 | Licence gating — expired or suspended licences blocked automatically from receiving orders | MED-02.02 | Pharmacy console status banner | New | HomeoMeds | §12 | Licence gating | Pharmacies with expired or suspended licences are blocked automatically from receiving orders | Backend | Web SPA | Yes | No | No | No | No | No | P0 | S | MED-02.01 | — | Web, QA | MED-02.01 | Does not exist | Scheduler; routing skip; banner on pharmacy console | Expired licence receives zero new orders the next minute | Not Started | UI
107 | 595 | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.3 | MED-03 | Fulfilment consent & pharmacy selection — patient chooses the seller and consents before the prescription is shared | MED-03.03 | Patient pharmacy pick UI (web optional + app Phase 16) | New | HomeoMeds | §12 + §2.7 | Fulfilment consent & pharmacy selection | The patient chooses the seller and consents before the prescription is shared | Patient | Web SPA | Yes | No | No | Yes | No | No | P0 | M | MED-03.02 | — | Web, QA | MED-03.02 | Does not exist | ConsentRecord PharmacyShare; patient picks from routed sellers; share only after consent | No pharmacy sees names until patient consents and seller is selected (codes still protected until accept+OTP) | Not Started | UI
108 | 599 | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.4 | MED-04 | Prescription handoff — signed prescription becomes the order directly — no re-entry, no transcription errors | MED-04.03 | Order start from patient eRx screen | New | HomeoMeds | §12 + §2.7 | Prescription handoff / Order start | The signed prescription becomes the order directly — no re-entry, no transcription errors / Start an order directly from the prescription | Patient + Pharmacy | Web SPA | Yes | No | No | Yes | No | No | P0 | M | MED-04.02 | — | Web, QA | MED-04.02 | Does not exist | MedicineOrder copied from ErxSnapshot items (codes); pharmacy never types remedies | Order lines == snapshot lines; pharmacy cannot add a different remedy | Not Started | UI
109 | 603 | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.5 | MED-05 | Rule-based seller routing — licence validity, service area, working hours and capacity | MED-05.03 | Admin/pharmacy hours and area config UI | New | HomeoMeds | §12 | Rule-based seller routing | Orders routed by licence validity, service area, working hours and capacity | Backend | Web SPA | Yes | No | No | Yes | No | No | P0 | M | MED-05.02 | — | Web, QA | MED-05.02 | Does not exist | SellerRoutingRule engine | Out-of-area pharmacy never listed | Not Started | UI
110 | 606 | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.6 | MED-06 | Manual stock confirmation — pharmacy confirms availability — no live inventory integration required | MED-06.02 | Pharmacy UI confirm availability | New | HomeoMeds | §12 | Manual stock confirmation | The pharmacy confirms availability — no live inventory integration required | Pharmacy console | Web SPA | Yes | No | No | No | No | No | P0 | S | MED-06.01 | — | Web, QA | MED-06.01 | Does not exist | Accept/reject with stock flag; do not build inventory master | Reject for out-of-stock routes to next seller or exception queue | Not Started | UI
111 | 610 | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.7 | MED-07 | Pharmacy console — accept or reject, enter price quote, mark ready and dispatched | MED-07.03 | /pharmacy/orders and detail | New | HomeoMeds | §12 | Pharmacy console | Accept or reject orders, enter the price quote, mark ready and dispatched | Pharmacy console | Web SPA | Yes | No | No | Yes | No | No | P0 | M | MED-07.02 | — | Web, QA | MED-07.02 | Does not exist | /pharmacy/orders list+detail; OTP accept (SEC-07); quote; ready; dispatched | OTP required on accept; status visible to patient | Not Started | UI
112 | 615 | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.8 | MED-08 | Quote before payment — the patient always sees the price before paying | MED-08.03 | Patient quote screen | New | HomeoMeds | §12 + §2.7 | Quote before payment / Pharmacy selection & quote | The patient always sees the price before paying / Choose a licensed pharmacy and see the price before paying | Patient | Web SPA | Yes | No | No | Yes | No | No | P0 | M | MED-08.02 | — | Web, QA | MED-08.02 | Does not exist | MedicineQuote; patient must confirm quote; then PAY-07 | Payment API rejects if quote not accepted by patient | Not Started | UI
113 | 618 | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.9 | MED-09 | Payment or cash on delivery — both options, with status tracking | MED-09.02 | Patient pay vs COD UI | New | HomeoMeds | §12 + §9 | Payment or cash on delivery | Both options supported, with status tracking | Patient | Web SPA | Yes | No | No | No | Yes | No | P0 | M | MED-09.01 | — | Web, QA | MED-09.01 | Stream MEDICINE stub in Phase 6 | Online pay via PAY-02; COD_PENDING until pharmacy confirms collection | COD does not mark Stream MEDICINE as captured until collection confirmed | Not Started | UI
114 | 622 | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.10 | MED-10 | Order tracking — live status for the patient at every stage | MED-10.03 | Tracking UI | New | HomeoMeds | §12 + §2.7 | Order tracking | Live status for the patient at every stage / Live status from accepted to delivered | Patient | Web SPA | Yes | No | No | Yes | No | No | P1 | M | MED-10.02 | — | Web, QA | MED-10.02 | Does not exist | Status timeline events; push updates COM-03 | Every status change visible; never silent skip | Not Started | UI
115 | 629 | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.12 | MED-12 | Order exception queue — stuck, rejected or failed orders always surfaced — never silent | MED-12.03 | /admin/homemeds-exceptions | New | HomeoMeds | §12 | Order exception queue | Stuck, rejected or failed orders are always surfaced to the operations team — never silent | Admin + Account | Web SPA | Yes | No | No | Yes | No | No | P0 | M | MED-12.02 | — | Web, QA | MED-12.02 | Does not exist | HomeoMeds exception queue; SLA; never drop | Rejected-by-all-sellers appears in queue within worker SLA | Not Started | UI
116 | 634 | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.14 | MED-14 | Refill orders — repeat orders raised from an existing prescription | MED-14.02 | Patient order detail + refill CTA | New | HomeoMeds | §12 + §2.7 + §11 | Refill orders / Order detail & refill | Repeat orders raised from an existing prescription / Full order history and one-tap refill request | Patient + Doctor | Web SPA | Yes | No | No | No | Yes | No | P1 | S | MED-14.01 | — | Web, QA | MED-14.01 | ERX-10 refill request exists | Approved refill creates a new MedicineOrder from the same snapshot; one-tap patient | Refill does not mutate the original signed snapshot | Not Started | UI
117 | 636 | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.15 | MED-15 | Order review & consent (patient) — confirm and consent before the prescription is shared | MED-15.01 | Patient review screen before handoff | New | HomeoMeds | §2.7 | Order review & consent | Confirm and consent before the prescription is shared | Patient | Web SPA | Yes | No | No | Yes | Yes | No | P0 | M | — | — | QA |  | Covered by MED-03; explicit review screen still required | Review screen listing codes (not names) + pharmacy + consent checkbox | Share does not occur until review confirmed | Not Started | UI
118 | 639 | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.16 | MED-16 | Medicines tab — all medicine orders in one place (API now; app UI in Phase 16) | MED-16.02 | Optional web list; mobile tab later | New | HomeoMeds | §2.7 | Medicines tab | All medicine orders in one place | Patient | Web SPA | Yes | No | No | No | No | No | P1 | S | MED-16.01 | — | Web, QA | MED-16.01 | Does not exist | GET my orders; website optional list; app tab Phase 16 | Patient sees all orders for their PatientId only | Not Started | UI
119 | 643 | UI | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.1 | CON-01 | Family members — add family members under one account | CON-01.03 | Consumed in Phase 16 | New | Patient identity | §2.1 | Family members | Add family members under one account | Patient App (API now) | Web SPA | Yes | No | No | Yes | No | No | P0 | M | CON-01.02 | — | Web, QA | CON-01.02 | Does not exist | FamilyMember under Patient account; bookings can be for a member | Member has own PatientId or MemberId linked; records isolated correctly | Not Started | UI
120 | 647 | UI | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.2 | CON-02 | Caregiver authorization — let a family member book and manage on their behalf | CON-02.03 | Consumed in Phase 16 | New | Patient identity | §2.1 | Caregiver authorization | Let a family member book and manage on their behalf | Patient App (API now) | Web SPA | Yes | No | No | Yes | No | No | P0 | M | CON-02.02 | — | Web, QA | CON-02.02 | Does not exist | CaregiverAuth with scopes; OTP; withdrawable via consent centre | Caregiver cannot exceed granted scopes; withdrawal immediate | Not Started | UI
121 | 652 | UI | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.3 | CON-03 | Records timeline + consultation note + document upload APIs | CON-03.03 | Consumed in Phase 16 | New | Patient records | §2.5 | Records timeline / Consultation note / Document upload | Complete visit history in date order / Doctor’s notes for each visit / Upload reports, scans and previous prescriptions | Patient App (API now) | Web SPA | Yes | No | No | Yes | No | No | P0 | M | CON-03.02 | — | Web, QA | CON-03.02 | Doctor history exists; no patient timeline; no patient upload | Patient timeline DTO (visits, summary, eRx codes, labs); consultation note = TEL-11 summary not private notes; uploads via SEC-09 | Private doctor notes never in patient timeline; uploads listed | Not Started | UI
122 | 656 | UI | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.4 | CON-04 | Follow-up plan & tasks — clear next steps after each consultation | CON-04.03 | Doctor board follow-up panel; app in Phase 16 | New | Continuity | §2.6 | Follow-up plan & tasks | Clear next steps after each consultation | Doctor Web + Patient | Web SPA | Yes | No | No | Yes | No | No | P1 | M | CON-04.02 | — | Web, QA | CON-04.02 | Does not exist (follow-up option in notes does not save) | FollowUpTask created by doctor; patient sees tasks | Tasks persist against PatientAppId; due dates drive Phase 18 follow-up analysis | Not Started | UI
123 | 660 | UI | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.5 | CON-05 | Symptom diary — record symptoms between visits | CON-05.03 | Doctor board read-only; app write Phase 16 | New | Continuity | §2.6 | Symptom diary | Record symptoms between visits | Patient App (API now) | Web SPA | Yes | No | No | Yes | No | No | P1 | M | CON-05.02 | — | Web, QA | CON-05.02 | Does not exist | SymptomDiary entries; doctor can read on board | Entries dated; treating doctor can read; other doctors 403 | Not Started | UI
124 | 664 | UI | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.6 | CON-06 | Progress tracking — see improvement over time across visits | CON-06.03 | Consumed in Phase 16 | New | Continuity | §2.6 | Progress tracking | See improvement over time across visits | Patient + Doctor | Web SPA | Yes | No | No | Yes | No | No | P2 | M | CON-06.02 | — | Web, QA | CON-06.02 | Does not exist | Progress series from diary + visit outcomes; not a fake chart | Empty state for new patients; series uses real diary/visit data | Not Started | UI
125 | 668 | UI | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.7 | CON-07 | Consent centre & data rights — view, manage and withdraw consents; request data | CON-07.03 | Consumed in Phase 16 | New | Privacy | §17 + §2.8 | Consent centre & data rights | Patients can view, manage and withdraw consent / View, manage and withdraw consents; request data | Patient App (API now) | Web SPA | Yes | No | No | Yes | No | No | P0 | M | CON-07.02 | — | Web, QA | CON-07.02 | ConsentRecord from Phase 0 | Patient list/withdraw; data export request (DPDP); deletion request workflow | Withdraw tele-recording prevents future recording; export request ticketed | Not Started | UI
126 | 676 | UI | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.10 | CON-10 | Patient profile setup API — name, age, gender, contact and health basics | CON-10.03 | Consumed in Phase 16 | New | Patient identity | §2.1 | Profile setup | Name, age, gender, contact and health basics | Patient App (API now) | Web SPA | Yes | No | No | Yes | No | No | P0 | M | CON-10.02 | — | Web, QA | CON-10.02 | Clinic-created Patient exists; no self-serve profile product | Patient profile fields + health basics; used by OTP-verified patient token | Profile required before first paid booking (or soft-gate documented) | Not Started | UI
127 | 959 | UI | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.1 | RPT-01 | Admin overview dashboard — platform-wide activity at a glance (replace Velzon ecommerce) | RPT-01.03 | Replace pages/Admin/Dashboard; getHomeDashboardPath → /admin/dashboard | Existing Improvement | Reports | §16 + §7.2 | Admin overview dashboard / Admin dashboard | Platform-wide activity at a glance / Live overview of the whole platform | Admin Portal | Web SPA | Yes | No | No | Yes | No | No | P0 | M | RPT-01.02 | — | Web, QA | RPT-01.02 | Velzon ecommerce dashboard 0% product; login lands /dashboard | True /admin/dashboard KPIs: doctors, credentialing, bookings, GMV, failed payments, tickets, HomeoMeds exceptions; redirect /dashboard away from StoreVisits | Admin home is product KPIs, not Velzon Revenue/StoreVisits | Not Started | UI
128 | 963 | UI | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.2 | RPT-02 | Doctor practice statistics — patient and consultation trends (extend existing charts) | RPT-02.03 | Dashboard charts consume new series | Existing Improvement | Reports | §16 + §5.1 | Doctor practice statistics | Patient and consultation trends | Doctor Web | Web SPA | Yes | No | No | Yes | No | No | P1 | M | RPT-02.02 | — | Web, QA | RPT-02.02 | Patient stats charts live | Keep as foundation; ensure visit type/mode included after APT-02 | Trends include first vs follow-up when VisitType exists | Not Started | UI
129 | 967 | UI | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.3 | RPT-03 | Follow-up analysis — due/overdue patients and follow-up conversion | RPT-03.03 | /doctor/follow-up-analysis | New | Reports | §16 | Follow-up analysis | Which patients are due or overdue for follow-up, and follow-up conversion | Doctor Web | Web SPA | Yes | No | No | Yes | No | No | P1 | M | RPT-03.02 | — | Web, QA | RPT-03.02 | Does not exist; follow-up option in notes does not save | /doctor/follow-up-analysis from VisitType + CON-04 tasks | Due list and conversion first-visit → follow-up are real counts | Not Started | UI
130 | 971 | UI | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.4 | RPT-04 | Clinic performance analysis — appointments, slot utilisation, no-shows, cancellations, waiting time and revenue | RPT-04.03 | /doctor/clinic-performance | New | Reports | §16 | Clinic performance analysis | Appointments, slot utilisation, no-shows, cancellations, waiting time and revenue | Doctor Web | Web SPA | Yes | No | No | Yes | No | No | P1 | M | RPT-04.02 | — | Web, QA | RPT-04.02 | Does not exist | /doctor/clinic-performance including payment collected and tele duration if timed | Each KPI has a definition note on the screen (no silent formula) | Not Started | UI
131 | 974 | UI | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.5 | RPT-05 | Payment reconciliation report — bookings matched against payments | RPT-05.02 | Report UI on admin/account recon screens | New | Reports | §16 + §7.2 | Payment reconciliation report / Consult booking & payment reconciliation | Bookings matched against payments / Match every booking against every payment | Admin + Account | Web SPA | Yes | No | No | No | No | No | P1 | S | RPT-05.01 | — | Web, QA | RPT-05.01 | FIN-02 built the queue; this is the report/export | Exportable report from the same reconciliation query | CSV totals match on-screen KPIs | Not Started | UI
132 | 977 | UI | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.6 | RPT-06 | Settlement & payout reports — amounts due and paid to doctors and pharmacies | RPT-06.02 | Report UI | New | Reports | §16 + §8 | Settlement & payout reports | Amounts due and paid to doctors and pharmacies | Account | Web SPA | Yes | No | No | No | No | No | P1 | S | RPT-06.01 | — | Web, QA | RPT-06.01 | FIN-04/05 exist as ops screens | Formal report/export of runs and payouts | Paid vs due columns reconcile to ledger | Not Started | UI
133 | 983 | UI | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.8 | RPT-08 | Doctor earnings summary — daily, weekly and monthly earnings with payout status (web + same API as DMO-10) | RPT-08.03 | /doctor/earnings | New | Reports | §16 + §3 | Doctor earnings summary | Daily, weekly and monthly earnings with payout status | Doctor Web + App | Web SPA | Yes | No | No | Yes | No | No | P1 | M | RPT-08.02 | — | Web, QA | RPT-08.02 | Does not exist | Web earnings page using same API as doctor app | Web and app match | Not Started | UI
134 | 987 | UI | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.9 | RPT-09 | Medicine order reports — order volumes, fulfilment and exceptions | RPT-09.03 | Admin/account report page | New | Reports | §16 + §12 | Medicine order reports | Order volumes, fulfilment and exceptions | Admin + Account | Web SPA | Yes | No | No | Yes | No | No | P1 | M | RPT-09.02 | — | Web, QA | RPT-09.02 | Does not exist | Volumes, SLA, exception counts from HomeoMeds | Exception count matches MED-12 queue | Not Started | UI
135 | 991 | UI | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.10 | RPT-10 | Platform users remaining 20% — import, export and activation control | RPT-10.03 | ListUser.js wire dead buttons; verification column | Existing Improvement | Admin | §7.2 | Platform users | Manage all users with import, export and activation control | Admin Portal | Web SPA | Yes | No | No | Yes | No | No | P1 | M | RPT-10.02 | — | Web, QA | RPT-10.02 | List/Add/Edit live; Import/Export buttons dead; no verification column | Wire Import/Export; verification column; activate/lock; link credentialing | Import/Export work; unverified visible; lock prevents login | Not Started | UI

## 03_Mobile_Sequential
MOBILE SEQUENTIAL BACKLOG — Patient iOS/Android then Doctor iOS/Android. No case-taking on phone. Execute by Track Seq. Consume .NET 8 APIs already built on the Web track.
Track Seq | Original Seq | Track | Phase | Phase Name | WBS | Main Task ID | Main Task | Sub Task ID | Sub Task | Work Type | Module / Area | PDF Section | PDF Feature (exact wording) | PDF Delivery Text | Application Surface | Layer | Frontend | Backend | Database | API | Mobile | Integration | Priority | Effort Band | Depends On (original) | Depends On (this track) | Sister Tracks (same Main Task) | Wait for other track | Existing Capability (AS-IS) | Gap / Change Required (TO-BE) | Acceptance Criteria | Status | Owner | Notes
1 | 18 | Mobile | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.2 | FND-02 | Delivery footprint — 2 mobile apps · 5 web portals · payment · telemedicine · digital prescription · HomeoMeds (programme skeleton) | FND-02.03 | Mobile: create Patient app and Doctor app repository/bootstrap (React Native or agreed stack) — empty shells only | New | Platform | §1 | Delivery covers | 2 mobile applications · 5 web portals · payment system · telemedicine · digital prescription · online medicine delivery. | Shared | Mobile | No | No | No | No | Yes | No | P0 | L | FND-02.02 | — | Web, UI | FND-02.02 | 1 web SPA (Admin/Doctor/Reception + marketing). No patient app, doctor app, Account portal, Pharmacy console | Repo/route skeleton: Patient Website, Doctor Web, Reception, Admin, Account (+ Pharmacy console under HomeoMeds); Patient + Doctor mobile later | Five web portal shells routable by role; mobile apps scheduled in Phases 16–17 not started here | Not Started | Mobile
2 | 678 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.1 | PAT-01 | Patient app — language selection on first open | PAT-01.01 | UI: Language selection screens (empty, loading, error, offline) | New | Patient Mobile | §2.1 | Language selection | Choose preferred language on first open | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | — | — | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Choose preferred language on first open | Not Started | Mobile
3 | 679 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.1 | PAT-01 | Patient app — language selection on first open | PAT-01.02 | Wire to the Phase 8–15 API for: Language selection | New | Patient Mobile | §2.1 | Language selection | Choose preferred language on first open | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-01.01 | T-2 (PAT-01.01) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Choose preferred language on first open | Not Started | Mobile
4 | 680 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.1 | PAT-01 | Patient app — language selection on first open | PAT-01.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.1 | Language selection | Choose preferred language on first open | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-01.02 | T-3 (PAT-01.02) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Choose preferred language on first open | Not Started | Mobile
5 | 682 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.2 | PAT-02 | Patient app — welcome and introduction | PAT-02.01 | UI: Welcome & introduction screens (empty, loading, error, offline) | New | Patient Mobile | §2.1 | Welcome & introduction | Guided introduction to the app | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | — | — | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Guided introduction to the app | Not Started | Mobile
6 | 683 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.2 | PAT-02 | Patient app — welcome and introduction | PAT-02.02 | Wire to the Phase 8–15 API for: Welcome & introduction | New | Patient Mobile | §2.1 | Welcome & introduction | Guided introduction to the app | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-02.01 | T-5 (PAT-02.01) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Guided introduction to the app | Not Started | Mobile
7 | 684 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.2 | PAT-02 | Patient app — welcome and introduction | PAT-02.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.1 | Welcome & introduction | Guided introduction to the app | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-02.02 | T-6 (PAT-02.02) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Guided introduction to the app | Not Started | Mobile
8 | 686 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.3 | PAT-03 | Patient app — mobile number + OTP login (PatientAuth) | PAT-03.01 | UI: Mobile number + OTP login screens (empty, loading, error, offline) | New | Patient Mobile | §2.1 | Mobile number + OTP login | Secure sign-in with no password to remember | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | WEB-04 | — | QA | WEB-04 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Secure sign-in with no password to remember | Not Started | Mobile
9 | 687 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.3 | PAT-03 | Patient app — mobile number + OTP login (PatientAuth) | PAT-03.02 | Wire to the Phase 8–15 API for: Mobile number + OTP login | New | Patient Mobile | §2.1 | Mobile number + OTP login | Secure sign-in with no password to remember | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-03.01 | T-8 (PAT-03.01) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Secure sign-in with no password to remember | Not Started | Mobile
10 | 688 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.3 | PAT-03 | Patient app — mobile number + OTP login (PatientAuth) | PAT-03.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.1 | Mobile number + OTP login | Secure sign-in with no password to remember | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-03.02 | T-9 (PAT-03.02) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Secure sign-in with no password to remember | Not Started | Mobile
11 | 690 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.4 | PAT-04 | Patient app — profile setup | PAT-04.01 | UI: Profile setup screens (empty, loading, error, offline) | New | Patient Mobile | §2.1 | Profile setup | Name, age, gender, contact and health basics | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | CON-10 | — | QA | CON-10 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Name, age, gender, contact and health basics | Not Started | Mobile
12 | 691 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.4 | PAT-04 | Patient app — profile setup | PAT-04.02 | Wire to the Phase 8–15 API for: Profile setup | New | Patient Mobile | §2.1 | Profile setup | Name, age, gender, contact and health basics | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-04.01 | T-11 (PAT-04.01) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Name, age, gender, contact and health basics | Not Started | Mobile
13 | 692 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.4 | PAT-04 | Patient app — profile setup | PAT-04.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.1 | Profile setup | Name, age, gender, contact and health basics | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-04.02 | T-12 (PAT-04.02) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Name, age, gender, contact and health basics | Not Started | Mobile
14 | 694 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.5 | PAT-05 | Patient app — privacy consent before data stored | PAT-05.01 | UI: Privacy consent screens (empty, loading, error, offline) | New | Patient Mobile | §2.1 | Privacy consent | Clear consent before any personal data is stored | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | SEC-06 | — | QA | SEC-06 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Clear consent before any personal data is stored | Not Started | Mobile
15 | 695 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.5 | PAT-05 | Patient app — privacy consent before data stored | PAT-05.02 | Wire to the Phase 8–15 API for: Privacy consent | New | Patient Mobile | §2.1 | Privacy consent | Clear consent before any personal data is stored | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-05.01 | T-14 (PAT-05.01) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Clear consent before any personal data is stored | Not Started | Mobile
16 | 696 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.5 | PAT-05 | Patient app — privacy consent before data stored | PAT-05.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.1 | Privacy consent | Clear consent before any personal data is stored | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-05.02 | T-15 (PAT-05.02) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Clear consent before any personal data is stored | Not Started | Mobile
17 | 698 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.6 | PAT-06 | Patient app — family members | PAT-06.01 | UI: Family members screens (empty, loading, error, offline) | New | Patient Mobile | §2.1 | Family members | Add family members under one account | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | CON-01 | — | QA | CON-01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Add family members under one account | Not Started | Mobile
18 | 699 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.6 | PAT-06 | Patient app — family members | PAT-06.02 | Wire to the Phase 8–15 API for: Family members | New | Patient Mobile | §2.1 | Family members | Add family members under one account | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-06.01 | T-17 (PAT-06.01) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Add family members under one account | Not Started | Mobile
19 | 700 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.6 | PAT-06 | Patient app — family members | PAT-06.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.1 | Family members | Add family members under one account | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-06.02 | T-18 (PAT-06.02) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Add family members under one account | Not Started | Mobile
20 | 702 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.7 | PAT-07 | Patient app — caregiver authorization | PAT-07.01 | UI: Caregiver authorization screens (empty, loading, error, offline) | New | Patient Mobile | §2.1 | Caregiver authorization | Let a family member book and manage on their behalf | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | CON-02 | — | QA | CON-02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Let a family member book and manage on their behalf | Not Started | Mobile
21 | 703 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.7 | PAT-07 | Patient app — caregiver authorization | PAT-07.02 | Wire to the Phase 8–15 API for: Caregiver authorization | New | Patient Mobile | §2.1 | Caregiver authorization | Let a family member book and manage on their behalf | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-07.01 | T-20 (PAT-07.01) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Let a family member book and manage on their behalf | Not Started | Mobile
22 | 704 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.7 | PAT-07 | Patient app — caregiver authorization | PAT-07.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.1 | Caregiver authorization | Let a family member book and manage on their behalf | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-07.02 | T-21 (PAT-07.02) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Let a family member book and manage on their behalf | Not Started | Mobile
23 | 706 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.8 | PAT-08 | Patient app — home dashboard | PAT-08.01 | UI: Home dashboard screens (empty, loading, error, offline) | New | Patient Mobile | §2.2 | Home dashboard | Personalised home with upcoming visits and quick actions | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | — | — | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Personalised home with upcoming visits and quick actions | Not Started | Mobile
24 | 707 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.8 | PAT-08 | Patient app — home dashboard | PAT-08.02 | Wire to the Phase 8–15 API for: Home dashboard | New | Patient Mobile | §2.2 | Home dashboard | Personalised home with upcoming visits and quick actions | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-08.01 | T-23 (PAT-08.01) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Personalised home with upcoming visits and quick actions | Not Started | Mobile
25 | 708 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.8 | PAT-08 | Patient app — home dashboard | PAT-08.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.2 | Home dashboard | Personalised home with upcoming visits and quick actions | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-08.02 | T-24 (PAT-08.02) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Personalised home with upcoming visits and quick actions | Not Started | Mobile
26 | 710 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.9 | PAT-09 | Patient app — search and care categories | PAT-09.01 | UI: Search & care categories screens (empty, loading, error, offline) | New | Patient Mobile | §2.2 | Search & care categories | Search by name, condition or category of care | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | WEB-03 | — | QA | WEB-03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Search by name, condition or category of care | Not Started | Mobile
27 | 711 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.9 | PAT-09 | Patient app — search and care categories | PAT-09.02 | Wire to the Phase 8–15 API for: Search & care categories | New | Patient Mobile | §2.2 | Search & care categories | Search by name, condition or category of care | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-09.01 | T-26 (PAT-09.01) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Search by name, condition or category of care | Not Started | Mobile
28 | 712 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.9 | PAT-09 | Patient app — search and care categories | PAT-09.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.2 | Search & care categories | Search by name, condition or category of care | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-09.02 | T-27 (PAT-09.02) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Search by name, condition or category of care | Not Started | Mobile
29 | 714 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.10 | PAT-10 | Patient app — search results | PAT-10.01 | UI: Search results screens (empty, loading, error, offline) | New | Patient Mobile | §2.2 | Search results | Clear list of available doctors | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | WEB-03 | — | QA | WEB-03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Clear list of available doctors | Not Started | Mobile
30 | 715 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.10 | PAT-10 | Patient app — search results | PAT-10.02 | Wire to the Phase 8–15 API for: Search results | New | Patient Mobile | §2.2 | Search results | Clear list of available doctors | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-10.01 | T-29 (PAT-10.01) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Clear list of available doctors | Not Started | Mobile
31 | 716 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.10 | PAT-10 | Patient app — search results | PAT-10.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.2 | Search results | Clear list of available doctors | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-10.02 | T-30 (PAT-10.02) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Clear list of available doctors | Not Started | Mobile
32 | 718 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.11 | PAT-11 | Patient app — discovery filters | PAT-11.01 | UI: Filters screens (empty, loading, error, offline) | New | Patient Mobile | §2.2 | Filters | Narrow by availability, fee, experience, language and location | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | WEB-03 | — | QA | WEB-03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Narrow by availability, fee, experience, language and location | Not Started | Mobile
33 | 719 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.11 | PAT-11 | Patient app — discovery filters | PAT-11.02 | Wire to the Phase 8–15 API for: Filters | New | Patient Mobile | §2.2 | Filters | Narrow by availability, fee, experience, language and location | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-11.01 | T-32 (PAT-11.01) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Narrow by availability, fee, experience, language and location | Not Started | Mobile
34 | 720 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.11 | PAT-11 | Patient app — discovery filters | PAT-11.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.2 | Filters | Narrow by availability, fee, experience, language and location | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-11.02 | T-33 (PAT-11.02) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Narrow by availability, fee, experience, language and location | Not Started | Mobile
35 | 722 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.12 | PAT-12 | Patient app — doctor profile | PAT-12.01 | UI: Doctor profile screens (empty, loading, error, offline) | New | Patient Mobile | §2.2 | Doctor profile | Full profile with qualifications, experience and consultation fee | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | WEB-03 | — | QA | WEB-03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Full profile with qualifications, experience and consultation fee | Not Started | Mobile
36 | 723 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.12 | PAT-12 | Patient app — doctor profile | PAT-12.02 | Wire to the Phase 8–15 API for: Doctor profile | New | Patient Mobile | §2.2 | Doctor profile | Full profile with qualifications, experience and consultation fee | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-12.01 | T-35 (PAT-12.01) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Full profile with qualifications, experience and consultation fee | Not Started | Mobile
37 | 724 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.12 | PAT-12 | Patient app — doctor profile | PAT-12.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.2 | Doctor profile | Full profile with qualifications, experience and consultation fee | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-12.02 | T-36 (PAT-12.02) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Full profile with qualifications, experience and consultation fee | Not Started | Mobile
38 | 726 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.13 | PAT-13 | Patient app — verified badge on doctor | PAT-13.01 | UI: Credentials & verification screens (empty, loading, error, offline) | New | Patient Mobile | §2.2 | Credentials & verification | Verified badge showing the doctor’s credentials are checked | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | TRU-03 | — | QA | TRU-03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Verified badge showing the doctor’s credentials are checked | Not Started | Mobile
39 | 727 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.13 | PAT-13 | Patient app — verified badge on doctor | PAT-13.02 | Wire to the Phase 8–15 API for: Credentials & verification | New | Patient Mobile | §2.2 | Credentials & verification | Verified badge showing the doctor’s credentials are checked | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-13.01 | T-38 (PAT-13.01) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Verified badge showing the doctor’s credentials are checked | Not Started | Mobile
40 | 728 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.13 | PAT-13 | Patient app — verified badge on doctor | PAT-13.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.2 | Credentials & verification | Verified badge showing the doctor’s credentials are checked | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-13.02 | T-39 (PAT-13.02) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Verified badge showing the doctor’s credentials are checked | Not Started | Mobile
41 | 730 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.14 | PAT-14 | Patient app — ranking explanation | PAT-14.01 | UI: Ranking explanation screens (empty, loading, error, offline) | New | Patient Mobile | §2.2 | Ranking explanation | Transparent explanation of why doctors appear in a given order | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | TRU-07 | — | QA | TRU-07 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Transparent explanation of why doctors appear in a given order | Not Started | Mobile
42 | 731 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.14 | PAT-14 | Patient app — ranking explanation | PAT-14.02 | Wire to the Phase 8–15 API for: Ranking explanation | New | Patient Mobile | §2.2 | Ranking explanation | Transparent explanation of why doctors appear in a given order | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-14.01 | T-41 (PAT-14.01) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Transparent explanation of why doctors appear in a given order | Not Started | Mobile
43 | 732 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.14 | PAT-14 | Patient app — ranking explanation | PAT-14.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.2 | Ranking explanation | Transparent explanation of why doctors appear in a given order | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-14.02 | T-42 (PAT-14.02) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Transparent explanation of why doctors appear in a given order | Not Started | Mobile
44 | 734 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.15 | PAT-15 | Patient app — health articles | PAT-15.01 | UI: Health articles screens (empty, loading, error, offline) | New | Patient Mobile | §2.2 | Health articles | Educational content to build trust and engagement | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | WEB-12 | — | QA | WEB-12 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Educational content to build trust and engagement | Not Started | Mobile
45 | 735 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.15 | PAT-15 | Patient app — health articles | PAT-15.02 | Wire to the Phase 8–15 API for: Health articles | New | Patient Mobile | §2.2 | Health articles | Educational content to build trust and engagement | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-15.01 | T-44 (PAT-15.01) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Educational content to build trust and engagement | Not Started | Mobile
46 | 736 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.15 | PAT-15 | Patient app — health articles | PAT-15.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.2 | Health articles | Educational content to build trust and engagement | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-15.02 | T-45 (PAT-15.02) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Educational content to build trust and engagement | Not Started | Mobile
47 | 738 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.16 | PAT-16 | Patient app — slot picker | PAT-16.01 | UI: Slot picker screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Slot picker | See real available time slots and choose one | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | APT-08 | — | QA | APT-08 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: See real available time slots and choose one | Not Started | Mobile
48 | 739 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.16 | PAT-16 | Patient app — slot picker | PAT-16.02 | Wire to the Phase 8–15 API for: Slot picker | New | Patient Mobile | §2.3 | Slot picker | See real available time slots and choose one | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-16.01 | T-47 (PAT-16.01) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: See real available time slots and choose one | Not Started | Mobile
49 | 740 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.16 | PAT-16 | Patient app — slot picker | PAT-16.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Slot picker | See real available time slots and choose one | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-16.02 | T-48 (PAT-16.02) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: See real available time slots and choose one | Not Started | Mobile
50 | 742 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.17 | PAT-17 | Patient app — booking review and consent | PAT-17.01 | UI: Booking review & consent screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Booking review & consent | Confirm details and consent before booking | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | WEB-04 | — | QA | WEB-04 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Confirm details and consent before booking | Not Started | Mobile
51 | 743 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.17 | PAT-17 | Patient app — booking review and consent | PAT-17.02 | Wire to the Phase 8–15 API for: Booking review & consent | New | Patient Mobile | §2.3 | Booking review & consent | Confirm details and consent before booking | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-17.01 | T-50 (PAT-17.01) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Confirm details and consent before booking | Not Started | Mobile
52 | 744 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.17 | PAT-17 | Patient app — booking review and consent | PAT-17.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Booking review & consent | Confirm details and consent before booking | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-17.02 | T-51 (PAT-17.02) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Confirm details and consent before booking | Not Started | Mobile
53 | 746 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.18 | PAT-18 | Patient app — checkout | PAT-18.01 | UI: Checkout screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Checkout | Pay the consultation fee inside the app | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | PAY-03 | — | QA | PAY-03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Pay the consultation fee inside the app | Not Started | Mobile
54 | 747 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.18 | PAT-18 | Patient app — checkout | PAT-18.02 | Wire to the Phase 8–15 API for: Checkout | New | Patient Mobile | §2.3 | Checkout | Pay the consultation fee inside the app | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-18.01 | T-53 (PAT-18.01) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Pay the consultation fee inside the app | Not Started | Mobile
55 | 748 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.18 | PAT-18 | Patient app — checkout | PAT-18.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Checkout | Pay the consultation fee inside the app | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-18.02 | T-54 (PAT-18.02) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Pay the consultation fee inside the app | Not Started | Mobile
56 | 750 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.19 | PAT-19 | Patient app — payment status | PAT-19.01 | UI: Payment status screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Payment status | Immediate confirmation of paid, pending or failed | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | PAY-08 | — | QA | PAY-08 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Immediate confirmation of paid, pending or failed | Not Started | Mobile
57 | 751 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.19 | PAT-19 | Patient app — payment status | PAT-19.02 | Wire to the Phase 8–15 API for: Payment status | New | Patient Mobile | §2.3 | Payment status | Immediate confirmation of paid, pending or failed | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-19.01 | T-56 (PAT-19.01) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Immediate confirmation of paid, pending or failed | Not Started | Mobile
58 | 752 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.19 | PAT-19 | Patient app — payment status | PAT-19.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Payment status | Immediate confirmation of paid, pending or failed | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-19.02 | T-57 (PAT-19.02) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Immediate confirmation of paid, pending or failed | Not Started | Mobile
59 | 754 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.20 | PAT-20 | Patient app — appointment detail | PAT-20.01 | UI: Appointment detail screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Appointment detail | Full booking details in one place | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | — | — | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Full booking details in one place | Not Started | Mobile
60 | 755 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.20 | PAT-20 | Patient app — appointment detail | PAT-20.02 | Wire to the Phase 8–15 API for: Appointment detail | New | Patient Mobile | §2.3 | Appointment detail | Full booking details in one place | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-20.01 | T-59 (PAT-20.01) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Full booking details in one place | Not Started | Mobile
61 | 756 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.20 | PAT-20 | Patient app — appointment detail | PAT-20.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Appointment detail | Full booking details in one place | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-20.02 | T-60 (PAT-20.02) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Full booking details in one place | Not Started | Mobile
62 | 758 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.21 | PAT-21 | Patient app — reschedule | PAT-21.01 | UI: Reschedule appointment screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Reschedule appointment | Move to another slot without calling the clinic | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | APT-05 | — | QA | APT-05 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Move to another slot without calling the clinic | Not Started | Mobile
63 | 759 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.21 | PAT-21 | Patient app — reschedule | PAT-21.02 | Wire to the Phase 8–15 API for: Reschedule appointment | New | Patient Mobile | §2.3 | Reschedule appointment | Move to another slot without calling the clinic | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-21.01 | T-62 (PAT-21.01) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Move to another slot without calling the clinic | Not Started | Mobile
64 | 760 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.21 | PAT-21 | Patient app — reschedule | PAT-21.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Reschedule appointment | Move to another slot without calling the clinic | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-21.02 | T-63 (PAT-21.02) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Move to another slot without calling the clinic | Not Started | Mobile
65 | 762 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.22 | PAT-22 | Patient app — cancel | PAT-22.01 | UI: Cancel appointment screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Cancel appointment | Cancel with reason, refund handled per policy | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | APT-06 | — | QA | APT-06 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Cancel with reason, refund handled per policy | Not Started | Mobile
66 | 763 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.22 | PAT-22 | Patient app — cancel | PAT-22.02 | Wire to the Phase 8–15 API for: Cancel appointment | New | Patient Mobile | §2.3 | Cancel appointment | Cancel with reason, refund handled per policy | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-22.01 | T-65 (PAT-22.01) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Cancel with reason, refund handled per policy | Not Started | Mobile
67 | 764 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.22 | PAT-22 | Patient app — cancel | PAT-22.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Cancel appointment | Cancel with reason, refund handled per policy | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-22.02 | T-66 (PAT-22.02) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Cancel with reason, refund handled per policy | Not Started | Mobile
68 | 766 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.23 | PAT-23 | Patient app — waitlist offer | PAT-23.01 | UI: Waitlist offer screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Waitlist offer | Get offered a slot when one is freed by a cancellation | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | WEB-11 | — | QA | WEB-11 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Get offered a slot when one is freed by a cancellation | Not Started | Mobile
69 | 767 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.23 | PAT-23 | Patient app — waitlist offer | PAT-23.02 | Wire to the Phase 8–15 API for: Waitlist offer | New | Patient Mobile | §2.3 | Waitlist offer | Get offered a slot when one is freed by a cancellation | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-23.01 | T-68 (PAT-23.01) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Get offered a slot when one is freed by a cancellation | Not Started | Mobile
70 | 768 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.23 | PAT-23 | Patient app — waitlist offer | PAT-23.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Waitlist offer | Get offered a slot when one is freed by a cancellation | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-23.02 | T-69 (PAT-23.02) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Get offered a slot when one is freed by a cancellation | Not Started | Mobile
71 | 770 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.24 | PAT-24 | Patient app — instant consult request | PAT-24.01 | UI: Instant consult request screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Instant consult request | Request an immediate consultation with an available doctor | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | TEL-12 | — | QA | TEL-12 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Request an immediate consultation with an available doctor | Not Started | Mobile
72 | 771 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.24 | PAT-24 | Patient app — instant consult request | PAT-24.02 | Wire to the Phase 8–15 API for: Instant consult request | New | Patient Mobile | §2.3 | Instant consult request | Request an immediate consultation with an available doctor | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-24.01 | T-71 (PAT-24.01) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Request an immediate consultation with an available doctor | Not Started | Mobile
73 | 772 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.24 | PAT-24 | Patient app — instant consult request | PAT-24.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Instant consult request | Request an immediate consultation with an available doctor | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-24.02 | T-72 (PAT-24.02) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Request an immediate consultation with an available doctor | Not Started | Mobile
74 | 774 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.25 | PAT-25 | Patient app — queue and doctor offer | PAT-25.01 | UI: Queue & doctor offer screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Queue & doctor offer | See position in queue and accept an offered doctor | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | TEL-12 | — | QA | TEL-12 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: See position in queue and accept an offered doctor | Not Started | Mobile
75 | 775 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.25 | PAT-25 | Patient app — queue and doctor offer | PAT-25.02 | Wire to the Phase 8–15 API for: Queue & doctor offer | New | Patient Mobile | §2.3 | Queue & doctor offer | See position in queue and accept an offered doctor | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-25.01 | T-74 (PAT-25.01) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: See position in queue and accept an offered doctor | Not Started | Mobile
76 | 776 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.25 | PAT-25 | Patient app — queue and doctor offer | PAT-25.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Queue & doctor offer | See position in queue and accept an offered doctor | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-25.02 | T-75 (PAT-25.02) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: See position in queue and accept an offered doctor | Not Started | Mobile
77 | 778 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.26 | PAT-26 | Patient app — device check | PAT-26.01 | UI: Device check screens (empty, loading, error, offline) | New | Patient Mobile | §2.4 | Device check | Camera, microphone and network checked before the call | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | TEL-05 | — | QA | TEL-05 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Camera, microphone and network checked before the call | Not Started | Mobile
78 | 779 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.26 | PAT-26 | Patient app — device check | PAT-26.02 | Wire to the Phase 8–15 API for: Device check | New | Patient Mobile | §2.4 | Device check | Camera, microphone and network checked before the call | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-26.01 | T-77 (PAT-26.01) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Camera, microphone and network checked before the call | Not Started | Mobile
79 | 780 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.26 | PAT-26 | Patient app — device check | PAT-26.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.4 | Device check | Camera, microphone and network checked before the call | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-26.02 | T-78 (PAT-26.02) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Camera, microphone and network checked before the call | Not Started | Mobile
80 | 782 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.27 | PAT-27 | Patient app — waiting room | PAT-27.01 | UI: Waiting room screens (empty, loading, error, offline) | New | Patient Mobile | §2.4 | Waiting room | Wait with live status until the doctor joins | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | TEL-06 | — | QA | TEL-06 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Wait with live status until the doctor joins | Not Started | Mobile
81 | 783 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.27 | PAT-27 | Patient app — waiting room | PAT-27.02 | Wire to the Phase 8–15 API for: Waiting room | New | Patient Mobile | §2.4 | Waiting room | Wait with live status until the doctor joins | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-27.01 | T-80 (PAT-27.01) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Wait with live status until the doctor joins | Not Started | Mobile
82 | 784 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.27 | PAT-27 | Patient app — waiting room | PAT-27.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.4 | Waiting room | Wait with live status until the doctor joins | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-27.02 | T-81 (PAT-27.02) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Wait with live status until the doctor joins | Not Started | Mobile
83 | 786 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.28 | PAT-28 | Patient app — live video | PAT-28.01 | UI: Live video consultation screens (empty, loading, error, offline) | New | Patient Mobile | §2.4 | Live video consultation | Face-to-face consultation from home | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | TEL-04 | — | QA | TEL-04 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Face-to-face consultation from home | Not Started | Mobile
84 | 787 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.28 | PAT-28 | Patient app — live video | PAT-28.02 | Wire to the Phase 8–15 API for: Live video consultation | New | Patient Mobile | §2.4 | Live video consultation | Face-to-face consultation from home | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-28.01 | T-83 (PAT-28.01) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Face-to-face consultation from home | Not Started | Mobile
85 | 788 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.28 | PAT-28 | Patient app — live video | PAT-28.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.4 | Live video consultation | Face-to-face consultation from home | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-28.02 | T-84 (PAT-28.02) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Face-to-face consultation from home | Not Started | Mobile
86 | 790 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.29 | PAT-29 | Patient app — recording consent | PAT-29.01 | UI: Recording consent screens (empty, loading, error, offline) | New | Patient Mobile | §2.4 | Recording consent | Explicit consent requested before any recording | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | TEL-07 | — | QA | TEL-07 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Explicit consent requested before any recording | Not Started | Mobile
87 | 791 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.29 | PAT-29 | Patient app — recording consent | PAT-29.02 | Wire to the Phase 8–15 API for: Recording consent | New | Patient Mobile | §2.4 | Recording consent | Explicit consent requested before any recording | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-29.01 | T-86 (PAT-29.01) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Explicit consent requested before any recording | Not Started | Mobile
88 | 792 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.29 | PAT-29 | Patient app — recording consent | PAT-29.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.4 | Recording consent | Explicit consent requested before any recording | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-29.02 | T-87 (PAT-29.02) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Explicit consent requested before any recording | Not Started | Mobile
89 | 794 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.30 | PAT-30 | Patient app — join failure fallback | PAT-30.01 | UI: Fallback & join failure handling screens (empty, loading, error, offline) | New | Patient Mobile | §2.4 | Fallback & join failure handling | Clear guidance if the call fails, with options to retry | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | TEL-09 | — | QA | TEL-09 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Clear guidance if the call fails, with options to retry | Not Started | Mobile
90 | 795 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.30 | PAT-30 | Patient app — join failure fallback | PAT-30.02 | Wire to the Phase 8–15 API for: Fallback & join failure handling | New | Patient Mobile | §2.4 | Fallback & join failure handling | Clear guidance if the call fails, with options to retry | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-30.01 | T-89 (PAT-30.01) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Clear guidance if the call fails, with options to retry | Not Started | Mobile
91 | 796 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.30 | PAT-30 | Patient app — join failure fallback | PAT-30.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.4 | Fallback & join failure handling | Clear guidance if the call fails, with options to retry | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-30.02 | T-90 (PAT-30.02) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Clear guidance if the call fails, with options to retry | Not Started | Mobile
92 | 798 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.31 | PAT-31 | Patient app — case-linked chat | PAT-31.01 | UI: Case-linked chat screens (empty, loading, error, offline) | New | Patient Mobile | §2.4 | Case-linked chat | Chat tied to the consultation, not a loose message thread | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | TEL-10 | — | QA | TEL-10 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Chat tied to the consultation, not a loose message thread | Not Started | Mobile
93 | 799 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.31 | PAT-31 | Patient app — case-linked chat | PAT-31.02 | Wire to the Phase 8–15 API for: Case-linked chat | New | Patient Mobile | §2.4 | Case-linked chat | Chat tied to the consultation, not a loose message thread | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-31.01 | T-92 (PAT-31.01) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Chat tied to the consultation, not a loose message thread | Not Started | Mobile
94 | 800 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.31 | PAT-31 | Patient app — case-linked chat | PAT-31.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.4 | Case-linked chat | Chat tied to the consultation, not a loose message thread | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-31.02 | T-93 (PAT-31.02) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Chat tied to the consultation, not a loose message thread | Not Started | Mobile
95 | 802 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.32 | PAT-32 | Patient app — consultation summary | PAT-32.01 | UI: Consultation summary screens (empty, loading, error, offline) | New | Patient Mobile | §2.4 | Consultation summary | Written summary available immediately after the call | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | TEL-11 | — | QA | TEL-11 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Written summary available immediately after the call | Not Started | Mobile
96 | 803 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.32 | PAT-32 | Patient app — consultation summary | PAT-32.02 | Wire to the Phase 8–15 API for: Consultation summary | New | Patient Mobile | §2.4 | Consultation summary | Written summary available immediately after the call | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-32.01 | T-95 (PAT-32.01) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Written summary available immediately after the call | Not Started | Mobile
97 | 804 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.32 | PAT-32 | Patient app — consultation summary | PAT-32.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.4 | Consultation summary | Written summary available immediately after the call | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-32.02 | T-96 (PAT-32.02) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Written summary available immediately after the call | Not Started | Mobile
98 | 806 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.33 | PAT-33 | Patient app — rejoin | PAT-33.01 | UI: Rejoin after dropped call screens (empty, loading, error, offline) | New | Patient Mobile | §2.4 | Rejoin after dropped call | Rejoin the same consultation if the connection drops | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | TEL-08 | — | QA | TEL-08 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Rejoin the same consultation if the connection drops | Not Started | Mobile
99 | 807 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.33 | PAT-33 | Patient app — rejoin | PAT-33.02 | Wire to the Phase 8–15 API for: Rejoin after dropped call | New | Patient Mobile | §2.4 | Rejoin after dropped call | Rejoin the same consultation if the connection drops | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-33.01 | T-98 (PAT-33.01) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Rejoin the same consultation if the connection drops | Not Started | Mobile
100 | 808 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.33 | PAT-33 | Patient app — rejoin | PAT-33.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.4 | Rejoin after dropped call | Rejoin the same consultation if the connection drops | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-33.02 | T-99 (PAT-33.02) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Rejoin the same consultation if the connection drops | Not Started | Mobile
101 | 810 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.34 | PAT-34 | Patient app — records timeline | PAT-34.01 | UI: Records timeline screens (empty, loading, error, offline) | New | Patient Mobile | §2.5 | Records timeline | Complete visit history in date order | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | CON-03 | — | QA | CON-03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Complete visit history in date order | Not Started | Mobile
102 | 811 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.34 | PAT-34 | Patient app — records timeline | PAT-34.02 | Wire to the Phase 8–15 API for: Records timeline | New | Patient Mobile | §2.5 | Records timeline | Complete visit history in date order | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-34.01 | T-101 (PAT-34.01) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Complete visit history in date order | Not Started | Mobile
103 | 812 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.34 | PAT-34 | Patient app — records timeline | PAT-34.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.5 | Records timeline | Complete visit history in date order | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-34.02 | T-102 (PAT-34.02) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Complete visit history in date order | Not Started | Mobile
104 | 814 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.35 | PAT-35 | Patient app — consultation note (summary, not private notes) | PAT-35.01 | UI: Consultation note screens (empty, loading, error, offline) | New | Patient Mobile | §2.5 | Consultation note | Doctor’s notes for each visit | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | CON-03 | — | QA | CON-03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Doctor’s notes for each visit | Not Started | Mobile
105 | 815 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.35 | PAT-35 | Patient app — consultation note (summary, not private notes) | PAT-35.02 | Wire to the Phase 8–15 API for: Consultation note | New | Patient Mobile | §2.5 | Consultation note | Doctor’s notes for each visit | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-35.01 | T-104 (PAT-35.01) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Doctor’s notes for each visit | Not Started | Mobile
106 | 816 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.35 | PAT-35 | Patient app — consultation note (summary, not private notes) | PAT-35.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.5 | Consultation note | Doctor’s notes for each visit | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-35.02 | T-105 (PAT-35.02) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Doctor’s notes for each visit | Not Started | Mobile
107 | 818 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.36 | PAT-36 | Patient app — signed eRx (codes until pharmacy accept) | PAT-36.01 | UI: Signed digital prescription screens (empty, loading, error, offline) | New | Patient Mobile | §2.5 | Signed digital prescription | Official prescription issued by the doctor | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | ERX-06 | — | QA | ERX-06 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Official prescription issued by the doctor | Not Started | Mobile
108 | 819 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.36 | PAT-36 | Patient app — signed eRx (codes until pharmacy accept) | PAT-36.02 | Wire to the Phase 8–15 API for: Signed digital prescription | New | Patient Mobile | §2.5 | Signed digital prescription | Official prescription issued by the doctor | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-36.01 | T-107 (PAT-36.01) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Official prescription issued by the doctor | Not Started | Mobile
109 | 820 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.36 | PAT-36 | Patient app — signed eRx (codes until pharmacy accept) | PAT-36.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.5 | Signed digital prescription | Official prescription issued by the doctor | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-36.02 | T-108 (PAT-36.02) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Official prescription issued by the doctor | Not Started | Mobile
110 | 822 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.37 | PAT-37 | Patient app — document upload | PAT-37.01 | UI: Document upload screens (empty, loading, error, offline) | New | Patient Mobile | §2.5 | Document upload | Upload reports, scans and previous prescriptions | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | CON-03 | — | QA | CON-03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Upload reports, scans and previous prescriptions | Not Started | Mobile
111 | 823 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.37 | PAT-37 | Patient app — document upload | PAT-37.02 | Wire to the Phase 8–15 API for: Document upload | New | Patient Mobile | §2.5 | Document upload | Upload reports, scans and previous prescriptions | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-37.01 | T-110 (PAT-37.01) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Upload reports, scans and previous prescriptions | Not Started | Mobile
112 | 824 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.37 | PAT-37 | Patient app — document upload | PAT-37.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.5 | Document upload | Upload reports, scans and previous prescriptions | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-37.02 | T-111 (PAT-37.02) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Upload reports, scans and previous prescriptions | Not Started | Mobile
113 | 826 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.38 | PAT-38 | Patient app — follow-up plan and tasks | PAT-38.01 | UI: Follow-up plan & tasks screens (empty, loading, error, offline) | New | Patient Mobile | §2.6 | Follow-up plan & tasks | Clear next steps after each consultation | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | CON-04 | — | QA | CON-04 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Clear next steps after each consultation | Not Started | Mobile
114 | 827 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.38 | PAT-38 | Patient app — follow-up plan and tasks | PAT-38.02 | Wire to the Phase 8–15 API for: Follow-up plan & tasks | New | Patient Mobile | §2.6 | Follow-up plan & tasks | Clear next steps after each consultation | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-38.01 | T-113 (PAT-38.01) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Clear next steps after each consultation | Not Started | Mobile
115 | 828 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.38 | PAT-38 | Patient app — follow-up plan and tasks | PAT-38.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.6 | Follow-up plan & tasks | Clear next steps after each consultation | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-38.02 | T-114 (PAT-38.02) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Clear next steps after each consultation | Not Started | Mobile
116 | 830 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.39 | PAT-39 | Patient app — symptom diary | PAT-39.01 | UI: Symptom diary screens (empty, loading, error, offline) | New | Patient Mobile | §2.6 | Symptom diary | Record symptoms between visits | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | CON-05 | — | QA | CON-05 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Record symptoms between visits | Not Started | Mobile
117 | 831 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.39 | PAT-39 | Patient app — symptom diary | PAT-39.02 | Wire to the Phase 8–15 API for: Symptom diary | New | Patient Mobile | §2.6 | Symptom diary | Record symptoms between visits | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-39.01 | T-116 (PAT-39.01) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Record symptoms between visits | Not Started | Mobile
118 | 832 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.39 | PAT-39 | Patient app — symptom diary | PAT-39.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.6 | Symptom diary | Record symptoms between visits | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-39.02 | T-117 (PAT-39.02) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Record symptoms between visits | Not Started | Mobile
119 | 834 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.40 | PAT-40 | Patient app — progress tracking | PAT-40.01 | UI: Progress tracking screens (empty, loading, error, offline) | New | Patient Mobile | §2.6 | Progress tracking | See improvement over time across visits | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | CON-06 | — | QA | CON-06 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: See improvement over time across visits | Not Started | Mobile
120 | 835 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.40 | PAT-40 | Patient app — progress tracking | PAT-40.02 | Wire to the Phase 8–15 API for: Progress tracking | New | Patient Mobile | §2.6 | Progress tracking | See improvement over time across visits | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-40.01 | T-119 (PAT-40.01) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: See improvement over time across visits | Not Started | Mobile
121 | 836 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.40 | PAT-40 | Patient app — progress tracking | PAT-40.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.6 | Progress tracking | See improvement over time across visits | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-40.02 | T-120 (PAT-40.02) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: See improvement over time across visits | Not Started | Mobile
122 | 838 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.41 | PAT-41 | Patient app — medicines tab | PAT-41.01 | UI: Medicines tab screens (empty, loading, error, offline) | New | Patient Mobile | §2.7 | Medicines tab | All medicine orders in one place | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | MED-16 | — | QA | MED-16 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: All medicine orders in one place | Not Started | Mobile
123 | 839 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.41 | PAT-41 | Patient app — medicines tab | PAT-41.02 | Wire to the Phase 8–15 API for: Medicines tab | New | Patient Mobile | §2.7 | Medicines tab | All medicine orders in one place | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-41.01 | T-122 (PAT-41.01) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: All medicine orders in one place | Not Started | Mobile
124 | 840 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.41 | PAT-41 | Patient app — medicines tab | PAT-41.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.7 | Medicines tab | All medicine orders in one place | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-41.02 | T-123 (PAT-41.02) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: All medicine orders in one place | Not Started | Mobile
125 | 842 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.42 | PAT-42 | Patient app — start HomeoMeds order from eRx | PAT-42.01 | UI: Order start screens (empty, loading, error, offline) | New | Patient Mobile | §2.7 | Order start | Start an order directly from the prescription | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | MED-04 | — | QA | MED-04 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Start an order directly from the prescription | Not Started | Mobile
126 | 843 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.42 | PAT-42 | Patient app — start HomeoMeds order from eRx | PAT-42.02 | Wire to the Phase 8–15 API for: Order start | New | Patient Mobile | §2.7 | Order start | Start an order directly from the prescription | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-42.01 | T-125 (PAT-42.01) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Start an order directly from the prescription | Not Started | Mobile
127 | 844 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.42 | PAT-42 | Patient app — start HomeoMeds order from eRx | PAT-42.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.7 | Order start | Start an order directly from the prescription | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-42.02 | T-126 (PAT-42.02) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Start an order directly from the prescription | Not Started | Mobile
128 | 846 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.43 | PAT-43 | Patient app — pharmacy selection and quote | PAT-43.01 | UI: Pharmacy selection & quote screens (empty, loading, error, offline) | New | Patient Mobile | §2.7 | Pharmacy selection & quote | Choose a licensed pharmacy and see the price before paying | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | MED-08 | — | QA | MED-08 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Choose a licensed pharmacy and see the price before paying | Not Started | Mobile
129 | 847 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.43 | PAT-43 | Patient app — pharmacy selection and quote | PAT-43.02 | Wire to the Phase 8–15 API for: Pharmacy selection & quote | New | Patient Mobile | §2.7 | Pharmacy selection & quote | Choose a licensed pharmacy and see the price before paying | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-43.01 | T-128 (PAT-43.01) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Choose a licensed pharmacy and see the price before paying | Not Started | Mobile
130 | 848 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.43 | PAT-43 | Patient app — pharmacy selection and quote | PAT-43.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.7 | Pharmacy selection & quote | Choose a licensed pharmacy and see the price before paying | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-43.02 | T-129 (PAT-43.02) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Choose a licensed pharmacy and see the price before paying | Not Started | Mobile
131 | 850 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.44 | PAT-44 | Patient app — order review and consent | PAT-44.01 | UI: Order review & consent screens (empty, loading, error, offline) | New | Patient Mobile | §2.7 | Order review & consent | Confirm and consent before the prescription is shared | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | MED-15 | — | QA | MED-15 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Confirm and consent before the prescription is shared | Not Started | Mobile
132 | 851 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.44 | PAT-44 | Patient app — order review and consent | PAT-44.02 | Wire to the Phase 8–15 API for: Order review & consent | New | Patient Mobile | §2.7 | Order review & consent | Confirm and consent before the prescription is shared | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-44.01 | T-131 (PAT-44.01) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Confirm and consent before the prescription is shared | Not Started | Mobile
133 | 852 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.44 | PAT-44 | Patient app — order review and consent | PAT-44.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.7 | Order review & consent | Confirm and consent before the prescription is shared | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-44.02 | T-132 (PAT-44.02) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Confirm and consent before the prescription is shared | Not Started | Mobile
134 | 854 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.45 | PAT-45 | Patient app — order tracking | PAT-45.01 | UI: Order tracking screens (empty, loading, error, offline) | New | Patient Mobile | §2.7 | Order tracking | Live status from accepted to delivered | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | MED-10 | — | QA | MED-10 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Live status from accepted to delivered | Not Started | Mobile
135 | 855 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.45 | PAT-45 | Patient app — order tracking | PAT-45.02 | Wire to the Phase 8–15 API for: Order tracking | New | Patient Mobile | §2.7 | Order tracking | Live status from accepted to delivered | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-45.01 | T-134 (PAT-45.01) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Live status from accepted to delivered | Not Started | Mobile
136 | 856 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.45 | PAT-45 | Patient app — order tracking | PAT-45.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.7 | Order tracking | Live status from accepted to delivered | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-45.02 | T-135 (PAT-45.02) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Live status from accepted to delivered | Not Started | Mobile
137 | 858 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.46 | PAT-46 | Patient app — order detail and refill | PAT-46.01 | UI: Order detail & refill screens (empty, loading, error, offline) | New | Patient Mobile | §2.7 | Order detail & refill | Full order history and one-tap refill request | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | MED-14 | — | QA | MED-14 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Full order history and one-tap refill request | Not Started | Mobile
138 | 859 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.46 | PAT-46 | Patient app — order detail and refill | PAT-46.02 | Wire to the Phase 8–15 API for: Order detail & refill | New | Patient Mobile | §2.7 | Order detail & refill | Full order history and one-tap refill request | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-46.01 | T-137 (PAT-46.01) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Full order history and one-tap refill request | Not Started | Mobile
139 | 860 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.46 | PAT-46 | Patient app — order detail and refill | PAT-46.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.7 | Order detail & refill | Full order history and one-tap refill request | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-46.02 | T-138 (PAT-46.02) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Full order history and one-tap refill request | Not Started | Mobile
140 | 862 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.47 | PAT-47 | Patient app — write a review | PAT-47.01 | UI: Write a review screens (empty, loading, error, offline) | New | Patient Mobile | §2.8 | Write a review | Rate and review the consultation | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | TRU-05 | — | QA | TRU-05 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Rate and review the consultation | Not Started | Mobile
141 | 863 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.47 | PAT-47 | Patient app — write a review | PAT-47.02 | Wire to the Phase 8–15 API for: Write a review | New | Patient Mobile | §2.8 | Write a review | Rate and review the consultation | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-47.01 | T-140 (PAT-47.01) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Rate and review the consultation | Not Started | Mobile
142 | 864 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.47 | PAT-47 | Patient app — write a review | PAT-47.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.8 | Write a review | Rate and review the consultation | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-47.02 | T-141 (PAT-47.02) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Rate and review the consultation | Not Started | Mobile
143 | 866 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.48 | PAT-48 | Patient app — my reviews and appeal | PAT-48.01 | UI: My reviews & appeal screens (empty, loading, error, offline) | New | Patient Mobile | §2.8 | My reviews & appeal | Manage reviews and raise an appeal | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | TRU-06 | — | QA | TRU-06 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Manage reviews and raise an appeal | Not Started | Mobile
144 | 867 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.48 | PAT-48 | Patient app — my reviews and appeal | PAT-48.02 | Wire to the Phase 8–15 API for: My reviews & appeal | New | Patient Mobile | §2.8 | My reviews & appeal | Manage reviews and raise an appeal | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-48.01 | T-143 (PAT-48.01) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Manage reviews and raise an appeal | Not Started | Mobile
145 | 868 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.48 | PAT-48 | Patient app — my reviews and appeal | PAT-48.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.8 | My reviews & appeal | Manage reviews and raise an appeal | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-48.02 | T-144 (PAT-48.02) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Manage reviews and raise an appeal | Not Started | Mobile
146 | 870 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.49 | PAT-49 | Patient app — payments and refunds | PAT-49.01 | UI: Payments & refunds screens (empty, loading, error, offline) | New | Patient Mobile | §2.8 | Payments & refunds | Full payment history and refund status | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | CON-08 | — | QA | CON-08 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Full payment history and refund status | Not Started | Mobile
147 | 871 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.49 | PAT-49 | Patient app — payments and refunds | PAT-49.02 | Wire to the Phase 8–15 API for: Payments & refunds | New | Patient Mobile | §2.8 | Payments & refunds | Full payment history and refund status | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-49.01 | T-146 (PAT-49.01) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Full payment history and refund status | Not Started | Mobile
148 | 872 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.49 | PAT-49 | Patient app — payments and refunds | PAT-49.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.8 | Payments & refunds | Full payment history and refund status | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-49.02 | T-147 (PAT-49.02) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Full payment history and refund status | Not Started | Mobile
149 | 874 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.50 | PAT-50 | Patient app — profile and settings | PAT-50.01 | UI: Profile & settings screens (empty, loading, error, offline) | New | Patient Mobile | §2.8 | Profile & settings | Manage personal details and preferences | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | CON-10 | — | QA | CON-10 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Manage personal details and preferences | Not Started | Mobile
150 | 875 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.50 | PAT-50 | Patient app — profile and settings | PAT-50.02 | Wire to the Phase 8–15 API for: Profile & settings | New | Patient Mobile | §2.8 | Profile & settings | Manage personal details and preferences | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-50.01 | T-149 (PAT-50.01) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Manage personal details and preferences | Not Started | Mobile
151 | 876 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.50 | PAT-50 | Patient app — profile and settings | PAT-50.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.8 | Profile & settings | Manage personal details and preferences | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-50.02 | T-150 (PAT-50.02) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Manage personal details and preferences | Not Started | Mobile
152 | 878 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.51 | PAT-51 | Patient app — consent centre and data rights | PAT-51.01 | UI: Consent centre & data rights screens (empty, loading, error, offline) | New | Patient Mobile | §2.8 | Consent centre & data rights | View, manage and withdraw consents; request data | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | CON-07 | — | QA | CON-07 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: View, manage and withdraw consents; request data | Not Started | Mobile
153 | 879 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.51 | PAT-51 | Patient app — consent centre and data rights | PAT-51.02 | Wire to the Phase 8–15 API for: Consent centre & data rights | New | Patient Mobile | §2.8 | Consent centre & data rights | View, manage and withdraw consents; request data | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-51.01 | T-152 (PAT-51.01) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: View, manage and withdraw consents; request data | Not Started | Mobile
154 | 880 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.51 | PAT-51 | Patient app — consent centre and data rights | PAT-51.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.8 | Consent centre & data rights | View, manage and withdraw consents; request data | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-51.02 | T-153 (PAT-51.02) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: View, manage and withdraw consents; request data | Not Started | Mobile
155 | 882 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.52 | PAT-52 | Patient app — notifications centre | PAT-52.01 | UI: Notifications centre screens (empty, loading, error, offline) | New | Patient Mobile | §2.8 | Notifications centre | All alerts in one place | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | COM-05 | — | QA | COM-05 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: All alerts in one place | Not Started | Mobile
156 | 883 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.52 | PAT-52 | Patient app — notifications centre | PAT-52.02 | Wire to the Phase 8–15 API for: Notifications centre | New | Patient Mobile | §2.8 | Notifications centre | All alerts in one place | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-52.01 | T-155 (PAT-52.01) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: All alerts in one place | Not Started | Mobile
157 | 884 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.52 | PAT-52 | Patient app — notifications centre | PAT-52.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.8 | Notifications centre | All alerts in one place | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-52.02 | T-156 (PAT-52.02) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: All alerts in one place | Not Started | Mobile
158 | 886 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.53 | PAT-53 | Patient app — help centre and tickets | PAT-53.01 | UI: Help centre & support tickets screens (empty, loading, error, offline) | New | Patient Mobile | §2.9 | Help centre & support tickets | Raise an issue and track it to resolution | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | SUP-01 | — | QA | SUP-01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Raise an issue and track it to resolution | Not Started | Mobile
159 | 887 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.53 | PAT-53 | Patient app — help centre and tickets | PAT-53.02 | Wire to the Phase 8–15 API for: Help centre & support tickets | New | Patient Mobile | §2.9 | Help centre & support tickets | Raise an issue and track it to resolution | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-53.01 | T-158 (PAT-53.01) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Raise an issue and track it to resolution | Not Started | Mobile
160 | 888 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.53 | PAT-53 | Patient app — help centre and tickets | PAT-53.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.9 | Help centre & support tickets | Raise an issue and track it to resolution | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-53.02 | T-159 (PAT-53.02) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Raise an issue and track it to resolution | Not Started | Mobile
161 | 890 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.54 | PAT-54 | Patient app — physical clinic booking | PAT-54.01 | UI: Physical clinic appointment screens (empty, loading, error, offline) | New | Patient Mobile | §2.9 | Physical clinic appointment | Book an in-person visit as well as online | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | CON-09 | — | QA | CON-09 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Book an in-person visit as well as online | Not Started | Mobile
162 | 891 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.54 | PAT-54 | Patient app — physical clinic booking | PAT-54.02 | Wire to the Phase 8–15 API for: Physical clinic appointment | New | Patient Mobile | §2.9 | Physical clinic appointment | Book an in-person visit as well as online | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-54.01 | T-161 (PAT-54.01) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Book an in-person visit as well as online | Not Started | Mobile
163 | 892 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.54 | PAT-54 | Patient app — physical clinic booking | PAT-54.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.9 | Physical clinic appointment | Book an in-person visit as well as online | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-54.02 | T-162 (PAT-54.02) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Book an in-person visit as well as online | Not Started | Mobile
164 | 894 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.55 | PAT-55 | Patient app — assisted booking request | PAT-55.01 | UI: Assisted booking screens (empty, loading, error, offline) | New | Patient Mobile | §2.9 | Assisted booking | Help for patients who need support booking | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | SUP-07 | — | QA | SUP-07 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Help for patients who need support booking | Not Started | Mobile
165 | 895 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.55 | PAT-55 | Patient app — assisted booking request | PAT-55.02 | Wire to the Phase 8–15 API for: Assisted booking | New | Patient Mobile | §2.9 | Assisted booking | Help for patients who need support booking | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-55.01 | T-164 (PAT-55.01) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Help for patients who need support booking | Not Started | Mobile
166 | 896 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.55 | PAT-55 | Patient app — assisted booking request | PAT-55.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.9 | Assisted booking | Help for patients who need support booking | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-55.02 | T-165 (PAT-55.02) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Help for patients who need support booking | Not Started | Mobile
167 | 898 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.56 | PAT-56 | Patient app — low-data mode | PAT-56.01 | UI: Low-data mode screens (empty, loading, error, offline) | New | Patient Mobile | §2.9 | Low-data mode | Works on slow or limited connections | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | — | — | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Works on slow or limited connections | Not Started | Mobile
168 | 899 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.56 | PAT-56 | Patient app — low-data mode | PAT-56.02 | Wire to the Phase 8–15 API for: Low-data mode | New | Patient Mobile | §2.9 | Low-data mode | Works on slow or limited connections | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-56.01 | T-167 (PAT-56.01) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Works on slow or limited connections | Not Started | Mobile
169 | 900 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.56 | PAT-56 | Patient app — low-data mode | PAT-56.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.9 | Low-data mode | Works on slow or limited connections | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-56.02 | T-168 (PAT-56.02) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Works on slow or limited connections | Not Started | Mobile
170 | 902 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.57 | PAT-57 | Patient app — push notifications | PAT-57.01 | UI: Push notifications screens (empty, loading, error, offline) | New | Patient Mobile | §2.9 | Push notifications | Booking confirmations, reminders, doctor ready, prescription issued, order updates | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | COM-03 | — | QA | COM-03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Booking confirmations, reminders, doctor ready, prescription issued, order updates | Not Started | Mobile
171 | 903 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.57 | PAT-57 | Patient app — push notifications | PAT-57.02 | Wire to the Phase 8–15 API for: Push notifications | New | Patient Mobile | §2.9 | Push notifications | Booking confirmations, reminders, doctor ready, prescription issued, order updates | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-57.01 | T-170 (PAT-57.01) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Booking confirmations, reminders, doctor ready, prescription issued, order updates | Not Started | Mobile
172 | 904 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.57 | PAT-57 | Patient app — push notifications | PAT-57.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.9 | Push notifications | Booking confirmations, reminders, doctor ready, prescription issued, order updates | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-57.02 | T-171 (PAT-57.02) | QA |  | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Booking confirmations, reminders, doctor ready, prescription issued, order updates | Not Started | Mobile
173 | 906 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.58 | PAT-58 | Patient app — iOS and Android store release, device matrix, and parity QA | PAT-58.01 | CI: iOS + Android release builds; env pointing to .NET 8 | New | Patient Mobile | §2 + §18 | Patient mobile app iOS and Android | iOS and Android — onboarding, discovery, booking, payment, video consultation, records, prescriptions, follow-up, medicines, reviews, support, notifications | Patient Mobile App | Mobile | No | No | No | No | Yes | No | P0 | L | — | — | QA |  | No app | Store builds; crash-free join; feature parity checklist against every §2 row | Parity matrix signed: every §2 feature works on both OS | Not Started | Mobile
174 | 908 | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.58 | PAT-58 | Patient app — iOS and Android store release, device matrix, and parity QA | PAT-58.03 | Crashlytics/Sentry equivalent for patient app | New Integration | Patient Mobile | §2 + §18 | Patient mobile app iOS and Android | iOS and Android — onboarding, discovery, booking, payment, video consultation, records, prescriptions, follow-up, medicines, reviews, support, notifications | Patient Mobile App | Mobile | No | No | No | No | Yes | Yes | P0 | S | PAT-58.02 | — | QA | PAT-58.02 | No app | Store builds; crash-free join; feature parity checklist against every §2 row | Parity matrix signed: every §2 feature works on both OS | Not Started | Mobile
175 | 909 | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.1 | DMO-01 | Doctor app — login & identity (same login and same account as the web portal) | DMO-01.01 | Login screen (password or OTP-to-registered mobile) | New | Doctor Mobile | §3 | Login & identity | Same login and same account as the web portal | Doctor Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P0 | M | — | — | QA |  | No doctor app | Same Account login + DoctorId; bind device; no separate doctor identity | Web and app show the same queue for the same DoctorId | Not Started | Mobile
176 | 910 | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.1 | DMO-01 | Doctor app — login & identity (same login and same account as the web portal) | DMO-01.02 | Call same Login API; store JWT securely (Keychain/Keystore) | New | Doctor Mobile | §3 | Login & identity | Same login and same account as the web portal | Doctor Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P0 | M | DMO-01.01 | T-175 (DMO-01.01) | QA |  | No doctor app | Same Account login + DoctorId; bind device; no separate doctor identity | Web and app show the same queue for the same DoctorId | Not Started | Mobile
177 | 911 | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.1 | DMO-01 | Doctor app — login & identity (same login and same account as the web portal) | DMO-01.03 | Expired session → re-login; no case-taking entry point | New | Doctor Mobile | §3 | Login & identity | Same login and same account as the web portal | Doctor Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P0 | S | DMO-01.02 | T-176 (DMO-01.02) | QA |  | No doctor app | Same Account login + DoctorId; bind device; no separate doctor identity | Web and app show the same queue for the same DoctorId | Not Started | Mobile
178 | 913 | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.2 | DMO-02 | Doctor app — first-run onboarding (guided setup, number confirmation and permissions) | DMO-02.01 | Onboarding screens | New | Doctor Mobile | §3 | First-run onboarding | Guided setup, number confirmation and permissions | Doctor Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | — | — | QA |  | No app | Confirm registered mobile; permission primer | Onboarding cannot be skipped past permission explanation for mic/camera/push | Not Started | Mobile
179 | 914 | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.2 | DMO-02 | Doctor app — first-run onboarding (guided setup, number confirmation and permissions) | DMO-02.02 | Confirm number against profile | New | Doctor Mobile | §3 | First-run onboarding | Guided setup, number confirmation and permissions | Doctor Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | DMO-02.01 | T-178 (DMO-02.01) | QA |  | No app | Confirm registered mobile; permission primer | Onboarding cannot be skipped past permission explanation for mic/camera/push | Not Started | Mobile
180 | 915 | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.2 | DMO-02 | Doctor app — first-run onboarding (guided setup, number confirmation and permissions) | DMO-02.03 | Skip vs required steps documented | New | Doctor Mobile | §3 | First-run onboarding | Guided setup, number confirmation and permissions | Doctor Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | DMO-02.02 | T-179 (DMO-02.02) | QA |  | No app | Confirm registered mobile; permission primer | Onboarding cannot be skipped past permission explanation for mic/camera/push | Not Started | Mobile
181 | 917 | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.3 | DMO-03 | Doctor app — notification permissions (push, microphone and camera handled properly) | DMO-03.01 | Permission primer + settings CTA | New | Doctor Mobile | §3 | Notification permissions | Push, microphone and camera permissions handled properly | Doctor Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P0 | M | — | — | QA |  | No app | OS permission flows; settings deep link if denied | Denied camera still allows queue viewing; join explains why it cannot start | Not Started | Mobile
182 | 918 | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.3 | DMO-03 | Doctor app — notification permissions (push, microphone and camera handled properly) | DMO-03.02 | Register FCM/APNs token (COM-03) | New | Doctor Mobile | §3 | Notification permissions | Push, microphone and camera permissions handled properly | Doctor Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P0 | M | DMO-03.01 | T-181 (DMO-03.01) | QA |  | No app | OS permission flows; settings deep link if denied | Denied camera still allows queue viewing; join explains why it cannot start | Not Started | Mobile
183 | 919 | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.3 | DMO-03 | Doctor app — notification permissions (push, microphone and camera handled properly) | DMO-03.03 | Denied-state UX | New | Doctor Mobile | §3 | Notification permissions | Push, microphone and camera permissions handled properly | Doctor Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P0 | S | DMO-03.02 | T-182 (DMO-03.02) | QA |  | No app | OS permission flows; settings deep link if denied | Denied camera still allows queue viewing; join explains why it cannot start | Not Started | Mobile
184 | 921 | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.4 | DMO-04 | Doctor app — today’s queue & schedule (the full day at a glance) | DMO-04.01 | TodayQueue screen | New | Doctor Mobile | §3 | Today’s queue & schedule | The full day at a glance | Doctor Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P0 | M | — | — | QA |  | No app | Appointment list APIs; payment + tele flags; no Patient Board | Matches web dashboard buckets for today | Not Started | Mobile
185 | 922 | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.4 | DMO-04 | Doctor app — today’s queue & schedule (the full day at a glance) | DMO-04.02 | Existing appointment list APIs | New | Doctor Mobile | §3 | Today’s queue & schedule | The full day at a glance | Doctor Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P0 | M | DMO-04.01 | T-184 (DMO-04.01) | QA |  | No app | Appointment list APIs; payment + tele flags; no Patient Board | Matches web dashboard buckets for today | Not Started | Mobile
186 | 923 | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.4 | DMO-04 | Doctor app — today’s queue & schedule (the full day at a glance) | DMO-04.03 | Pull-to-refresh; empty Sunday | New | Doctor Mobile | §3 | Today’s queue & schedule | The full day at a glance | Doctor Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P0 | S | DMO-04.02 | T-185 (DMO-04.02) | QA |  | No app | Appointment list APIs; payment + tele flags; no Patient Board | Matches web dashboard buckets for today | Not Started | Mobile
187 | 925 | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.5 | DMO-05 | Doctor app — availability toggle (go online or offline, set working hours) | DMO-05.01 | Availability + hours screens | New | Doctor Mobile | §3 | Availability toggle | Go online or offline, set working hours | Doctor Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P0 | M | — | — | QA |  | No app | Same TeleAvailability + schedule APIs as web | Toggle on app updates web and patient instant matching | Not Started | Mobile
188 | 926 | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.5 | DMO-05 | Doctor app — availability toggle (go online or offline, set working hours) | DMO-05.02 | TEL-01 + APT-07 APIs (hours read/edit policy: edit hours may stay web-only if product decides — PDF says set working hours so include) | New | Doctor Mobile | §3 | Availability toggle | Go online or offline, set working hours | Doctor Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P0 | M | DMO-05.01 | T-187 (DMO-05.01) | QA |  | No app | Same TeleAvailability + schedule APIs as web | Toggle on app updates web and patient instant matching | Not Started | Mobile
189 | 927 | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.5 | DMO-05 | Doctor app — availability toggle (go online or offline, set working hours) | DMO-05.03 | Offline banner | New | Doctor Mobile | §3 | Availability toggle | Go online or offline, set working hours | Doctor Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P0 | S | DMO-05.02 | T-188 (DMO-05.02) | QA |  | No app | Same TeleAvailability + schedule APIs as web | Toggle on app updates web and patient instant matching | Not Started | Mobile
190 | 929 | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.6 | DMO-06 | Doctor app — push notifications (waiting, booking, reschedule, cancellation, refill, payment received) | DMO-06.01 | Notification handling + deep links into queue/refill/join | New | Doctor Mobile | §3 | Push notifications | Patient waiting, new booking, reschedule, cancellation, refill request, payment received | Doctor Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P0 | M | — | — | QA |  | No app | Consume COM-03 doctor templates | Each listed event delivers a push when permission granted | Not Started | Mobile
191 | 930 | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.6 | DMO-06 | Doctor app — push notifications (waiting, booking, reschedule, cancellation, refill, payment received) | DMO-06.02 | Device register | New | Doctor Mobile | §3 | Push notifications | Patient waiting, new booking, reschedule, cancellation, refill request, payment received | Doctor Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P0 | M | DMO-06.01 | T-190 (DMO-06.01) | QA |  | No app | Consume COM-03 doctor templates | Each listed event delivers a push when permission granted | Not Started | Mobile
192 | 931 | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.6 | DMO-06 | Doctor app — push notifications (waiting, booking, reschedule, cancellation, refill, payment received) | DMO-06.03 | Foreground in-app banner | New | Doctor Mobile | §3 | Push notifications | Patient waiting, new booking, reschedule, cancellation, refill request, payment received | Doctor Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P0 | S | DMO-06.02 | T-191 (DMO-06.02) | QA |  | No app | Consume COM-03 doctor templates | Each listed event delivers a push when permission granted | Not Started | Mobile
193 | 933 | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.7 | DMO-07 | Doctor app — patient context card (name, age, chief complaint and last visit) — NO case-taking | DMO-07.01 | PatientCard read-only | New | Doctor Mobile | §3 | Patient context card | Name, age, chief complaint and last visit before joining | Doctor Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P0 | M | — | — | QA |  | No app; PDF: detailed case-taking stays on the web portal | Read-only card; explicitly no repertory/audio/Rx compose | No path to Patient Board clinical tools from the app | Not Started | Mobile
194 | 934 | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.7 | DMO-07 | Doctor app — patient context card (name, age, chief complaint and last visit) — NO case-taking | DMO-07.02 | Context API (name, age, CC, last visit, payment, tele) | New | Doctor Mobile | §3 | Patient context card | Name, age, chief complaint and last visit before joining | Doctor Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P0 | M | DMO-07.01 | T-193 (DMO-07.01) | QA |  | No app; PDF: detailed case-taking stays on the web portal | Read-only card; explicitly no repertory/audio/Rx compose | No path to Patient Board clinical tools from the app | Not Started | Mobile
195 | 935 | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.7 | DMO-07 | Doctor app — patient context card (name, age, chief complaint and last visit) — NO case-taking | DMO-07.03 | Do not ship case-taking tabs | New | Doctor Mobile | §3 | Patient context card | Name, age, chief complaint and last visit before joining | Doctor Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P0 | S | DMO-07.02 | T-194 (DMO-07.02) | QA |  | No app; PDF: detailed case-taking stays on the web portal | Read-only card; explicitly no repertory/audio/Rx compose | No path to Patient Board clinical tools from the app | Not Started | Mobile
196 | 937 | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.8 | DMO-08 | Doctor app — join consultation (video or audio from the phone) | DMO-08.01 | VideoRoom | New | Doctor Mobile | §3 | Join consultation | Start the video or audio consultation from the phone | Doctor Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P0 | M | — | — | QA |  | No app | Same session tokens as TEL-03/04 | Join same room as web patient or mobile patient | Not Started | Mobile
197 | 938 | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.8 | DMO-08 | Doctor app — join consultation (video or audio from the phone) | DMO-08.02 | Tele session tokens | New | Doctor Mobile | §3 | Join consultation | Start the video or audio consultation from the phone | Doctor Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P0 | M | DMO-08.01 | T-196 (DMO-08.01) | QA |  | No app | Same session tokens as TEL-03/04 | Join same room as web patient or mobile patient | Not Started | Mobile
198 | 939 | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.8 | DMO-08 | Doctor app — join consultation (video or audio from the phone) | DMO-08.03 | Audio-only fallback | New | Doctor Mobile | §3 | Join consultation | Start the video or audio consultation from the phone | Doctor Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P0 | S | DMO-08.02 | T-197 (DMO-08.02) | QA |  | No app | Same session tokens as TEL-03/04 | Join same room as web patient or mobile patient | Not Started | Mobile
199 | 941 | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.9 | DMO-09 | Doctor app — refill approval (approve or reject repeat prescription requests) | DMO-09.01 | RefillInbox + RefillDetail | New | Doctor Mobile | §3 + §11 | Refill approval | Approve or reject repeat prescription requests | Doctor Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P0 | M | — | — | QA |  | No app | ERX-10 inbox; approve only — Patient Board remains web | Approve/reject from phone writes the same RefillRequest as web | Not Started | Mobile
200 | 942 | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.9 | DMO-09 | Doctor app — refill approval (approve or reject repeat prescription requests) | DMO-09.02 | Approve/Reject APIs | New | Doctor Mobile | §3 + §11 | Refill approval | Approve or reject repeat prescription requests | Doctor Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P0 | M | DMO-09.01 | T-199 (DMO-09.01) | QA |  | No app | ERX-10 inbox; approve only — Patient Board remains web | Approve/reject from phone writes the same RefillRequest as web | Not Started | Mobile
201 | 943 | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.9 | DMO-09 | Doctor app — refill approval (approve or reject repeat prescription requests) | DMO-09.03 | Show codes vs names per policy (doctor sees names) | New | Doctor Mobile | §3 + §11 | Refill approval | Approve or reject repeat prescription requests | Doctor Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P0 | S | DMO-09.02 | T-200 (DMO-09.02) | QA |  | No app | ERX-10 inbox; approve only — Patient Board remains web | Approve/reject from phone writes the same RefillRequest as web | Not Started | Mobile
202 | 945 | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.10 | DMO-10 | Doctor app — earnings summary (today, this week, this month, with payout status) | DMO-10.01 | Earnings screens | New | Doctor Mobile | §3 + §16 | Earnings summary | Today, this week and this month, with payout status | Doctor Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | — | — | QA |  | No app | Account ledger read model for this DoctorId — not a second money system | Figures match Account settlement for that doctor | Not Started | Mobile
203 | 946 | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.10 | DMO-10 | Doctor app — earnings summary (today, this week, this month, with payout status) | DMO-10.02 | GET Earnings/Summary | New | Doctor Mobile | §3 + §16 | Earnings summary | Today, this week and this month, with payout status | Doctor Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | DMO-10.01 | T-202 (DMO-10.01) | QA |  | No app | Account ledger read model for this DoctorId — not a second money system | Figures match Account settlement for that doctor | Not Started | Mobile
204 | 947 | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.10 | DMO-10 | Doctor app — earnings summary (today, this week, this month, with payout status) | DMO-10.03 | Empty first week | New | Doctor Mobile | §3 + §16 | Earnings summary | Today, this week and this month, with payout status | Doctor Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | DMO-10.02 | T-203 (DMO-10.02) | QA |  | No app | Account ledger read model for this DoctorId — not a second money system | Figures match Account settlement for that doctor | Not Started | Mobile
205 | 949 | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.11 | DMO-11 | Doctor app — offline handling (weak connection or expired session) | DMO-11.01 | Offline/error screens | New | Doctor Mobile | §3 | Offline handling | Clear behaviour on weak connection or expired session | Doctor Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | — | — | QA |  | No app | Queued actions policy (do not fake join); session expiry uses SEC-03 | Expired JWT cannot join video; user is told to re-login | Not Started | Mobile
206 | 950 | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.11 | DMO-11 | Doctor app — offline handling (weak connection or expired session) | DMO-11.02 | 401 interceptor → logout API | New | Doctor Mobile | §3 | Offline handling | Clear behaviour on weak connection or expired session | Doctor Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | DMO-11.01 | T-205 (DMO-11.01) | QA |  | No app | Queued actions policy (do not fake join); session expiry uses SEC-03 | Expired JWT cannot join video; user is told to re-login | Not Started | Mobile
207 | 951 | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.11 | DMO-11 | Doctor app — offline handling (weak connection or expired session) | DMO-11.03 | No silent retry of payments | New | Doctor Mobile | §3 | Offline handling | Clear behaviour on weak connection or expired session | Doctor Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | DMO-11.02 | T-206 (DMO-11.02) | QA |  | No app | Queued actions policy (do not fake join); session expiry uses SEC-03 | Expired JWT cannot join video; user is told to re-login | Not Started | Mobile
208 | 953 | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.12 | DMO-12 | Doctor app — reliability monitoring (failures reported automatically) | DMO-12.01 | Integrate Crashlytics/Sentry; map to doctorId hashed | New Integration | Doctor Mobile | §3 | Reliability monitoring | Failures are reported automatically, not left to a phone call | Doctor Mobile App | Mobile | No | No | No | No | Yes | Yes | P1 | S | — | — | QA |  | No app | Crash/error SDK; join failures also as TeleSessionEvent | A forced crash appears in the monitoring tool within SLA | Not Started | Mobile
209 | 955 | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.13 | DMO-13 | Doctor app — iOS and Android parity QA (queue, availability, notifications, context, video, refill, earnings) | DMO-13.01 | Release builds both OS | New | Doctor Mobile | §3 + §18 | Doctor mobile app iOS and Android | iOS and Android — queue, availability, notifications, patient context, video consultation, refill approval, earnings | Doctor Mobile App | Mobile | No | No | No | No | Yes | No | P0 | L | — | — | QA |  | No app | Parity checklist for every §3 row on both OS | Parity matrix signed | Not Started | Mobile

## 04_QA_Sequential
QA SEQUENTIAL BACKLOG — every Regression / acceptance / IDOR / parity / E2E row from the master. Execute by Track Seq. Start a Main Task’s QA when its Web/UI/Mobile implementation rows are Done.
Track Seq | Original Seq | Track | Phase | Phase Name | WBS | Main Task ID | Main Task | Sub Task ID | Sub Task | Work Type | Module / Area | PDF Section | PDF Feature (exact wording) | PDF Delivery Text | Application Surface | Layer | Frontend | Backend | Database | API | Mobile | Integration | Priority | Effort Band | Depends On (original) | Depends On (this track) | Sister Tracks (same Main Task) | Wait for other track | Existing Capability (AS-IS) | Gap / Change Required (TO-BE) | Acceptance Criteria | Status | Owner | Notes
1 | 15 | QA | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.1 | FND-01 | One connected ecosystem — shared keys so a patient, appointment, prescription and payment created anywhere are visible everywhere | FND-01.04 | QA: create appointment on Reception → visible on Doctor web; pay on Patient web → same PaymentStatus on Doctor and Account (after Phase 6) | Regression | Platform | §1 | One connected ecosystem serving six types of users | A patient, an appointment, a prescription and a payment created anywhere in the system are visible everywhere else — there are no separate systems to reconcile. | Shared | QA | Yes | Yes | No | Yes | No | No | P2 | S | FND-01.03 | — | Web | FND-01.03 | Doctor/Admin/Reception web only; Patient, Account, Pharmacy roles do not exist; no shared payment or eRx keys | Canonical keys: UserId/DoctorId, PatientId, PatientAppId, CaseId, ErxId, LedgerTxnId, MedicineOrderId — used by every surface | Any write on one surface is readable on all authorised surfaces within SLA; no dual ledgers | Not Started | QA
2 | 23 | QA | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.3 | SEC-01 | Secure login — protected credentials for every user type | SEC-01.04 | QA: Admin, Doctor, Reception login; invalid password; deactivated user; SQL injection/brute-force rate limit | Regression | Security | §17 | Secure login | Protected credentials for every user type | All web + later mobile | QA | Yes | Yes | No | Yes | No | No | P0 | S | SEC-01.03 | — | Web, UI | SEC-01.03 | POST /Account/Login on classic API; JWT in sessionStorage; doctor/user passwords compared plaintext; reception hashed on classic; fakeBackend() still mounted | Hashed passwords; Role claim on JWT; disable fake backend for production paths; Patient OTP login is Phase 8 (not password) | No plaintext password compare; every role including future Patient/Account/Pharmacy authenticates through a protected path | Not Started | QA
3 | 27 | QA | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.4 | SEC-02 | Secure password reset — time-limited reset links (stop plaintext email + fake thunk) | SEC-02.04 | QA: expired token, reused token, unknown email (no user enumeration), logged-in change password | Regression | Security | §17 | Secure password reset | Time-limited reset links | Admin / Doctor / Reception web | QA | Yes | Yes | No | No | No | No | P0 | S | SEC-02.03 | — | Web, UI | SEC-02.03 | /forgot-password UI exists; thunk uses fake/Firebase; POST /users/ForgetPassword emails plaintext password | Tokenised reset (hash, TTL); email contains link only; ChangePassword for logged-in user | Reset email never contains the password; token expires; used token cannot be reused | Not Started | QA
4 | 31 | QA | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.5 | SEC-03 | Session control — proper sign-out across web and mobile | SEC-03.04 | QA: logout on one tab; expired session message; 401 interceptor | Regression | Security | §17 | Session control | Proper sign-out across web and mobile | All | QA | Yes | Yes | No | No | No | No | P0 | S | SEC-03.03 | — | Web, UI | SEC-03.03 | Client clears sessionStorage; no server logout / token revoke; UserLoginStatus unused | POST Logout persists login status; optional token denylist; mobile will call the same API in Phase 16/17 | After logout the JWT cannot call protected APIs; board session cleared (already on client) | Not Started | QA
5 | 35 | QA | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.6 | SEC-04 | Role-based access — each role sees only what it is permitted to see | SEC-04.04 | QA: Reception cannot open repertory masters; Account cannot edit diagnosis; Doctor cannot see platform-wide ledger | Regression | Security | §17 | Role-based access | Each role sees only what it is permitted to see | Admin / All web | QA | Yes | Yes | No | No | No | No | P0 | S | SEC-04.03 | — | Web, UI | SEC-04.03 | RoleMaster + RoleDetail + MenuMaster exist; GetMenuByRole commented out on .NET 8; no per-route frontend ACL — any authenticated URL works | Re-enable GetMenuByRole; AuthProtected deny-by-default; [Authorize(Roles=)] on money/clinical APIs; Account cannot edit repertory; Admin cannot approve payouts | Unknown URL for a role returns 403/redirect; admin menus match DB permissions | Not Started | QA
6 | 38 | QA | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.7 | SEC-05 | Patient data protection — health records restricted to the treating doctor and the patient | SEC-05.03 | QA: IDOR tests (swap PatientAppId / CaseId in requests) | Regression | Security | §17 | Patient data protection | Health records restricted to the treating doctor and the patient | API | QA | No | Yes | No | Yes | No | No | P0 | M | SEC-05.02 | — | Web | SEC-05.02 | Many repertory APIs have [Authorize] commented; directory browsing enabled for /attachments and /Blogs; no patient-scoped ACL on case data | Every case/Rx/note/lab query filtered by treating DoctorId (or PatientId for patient token); disable directory browsing | Doctor A cannot read Doctor B’s patient board payload; unauthenticated attachment URLs fail | Not Started | QA
7 | 42 | QA | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.8 | SEC-06 | Consent records infrastructure — every consent captured, stored and reviewable | SEC-06.04 | QA: grant, withdraw, re-grant; audit log immutable | Regression | Security / Trust | §17 | Consent records | Every consent captured, stored and reviewable | Shared | QA | No | Yes | No | No | No | No | P0 | S | SEC-06.03 | — | Web | SEC-06.03 | AudioCaseConsentLog exists for audio case taking only | ConsentRecord (PatientId, Type, Version, GrantedAt, WithdrawnAt, SourceSurface) covering privacy, booking, recording, pharmacy share, marketing | Any later feature that needs consent writes this table; withdrawal is queryable | Not Started | QA
8 | 46 | QA | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.9 | SEC-07 | OTP verification infrastructure — applied to sensitive actions including payouts and pharmacy acceptance | SEC-07.04 | QA: replay OTP, expiry, max attempts, audit completeness | Regression | Security | §17 + §8 + §12 | OTP verification | Applied to sensitive actions including payouts and pharmacy acceptance | Shared | QA | No | Yes | No | No | No | No | P0 | S | SEC-07.03 | — | Web | SEC-07.03 | No generic OTP control plane; patient OTP login does not exist | OtpChallenge + OtpAuditLog; Account/Admin can query who/when/entity/success without seeing card data | Payout and pharmacy-accept cannot complete without a successful OTP; failures are auditable | Not Started | QA
9 | 49 | QA | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.10 | SEC-08 | Complete audit trail — who did what and when across payments, prescriptions and approvals | SEC-08.03 | QA: sample sign-prescription / approve-payout (when those exist) produce audit rows | Regression | Security | §17 + §9 | Complete audit trail | Who did what, and when, across payments, prescriptions and approvals / Every transaction traceable end to end by Homeocentrum | Shared | QA | No | Yes | No | No | No | No | P2 | S | SEC-08.02 | — | Web | SEC-08.02 | No platform-wide audit; no AppointmentChangeLog; no payment webhook store | Append-only AuditEvent for money, eRx sign, credentialing, payout, pharmacy accept; payments get a dedicated trail in Phase 6 | Account can reconstruct any sensitive action without calling a doctor | Not Started | QA
10 | 52 | QA | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.11 | SEC-09 | Secure documents — prescriptions, reports and uploads protected from unauthorised access | SEC-09.03 | QA: doctor of record can download; other doctor 403; anonymous 401 | Regression | Security | §17 | Secure documents | Prescriptions, reports and uploads protected from unauthorised access | Shared | QA | No | Yes | No | No | No | No | P1 | S | SEC-09.02 | — | Web | SEC-09.02 | Attachments served with directory browsing; no signed URLs; no patient upload module | Authorised download; virus-scan hook; patient uploads in Phase 15 use this store | Guessable URL does not leak a prescription PDF | Not Started | QA
11 | 53 | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.1 | ADM-R01 | Keep and harden Admin Repertory sections (do not rebuild) | ADM-R01.01 | Regression: list / add / edit / (import-export if present) for Repertory sections | Existing | Repertory | §7.1 | Repertory sections | Manage repertory sections | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | — | Web |  | Admin Repertory section CRUD live (pages/Admin/Repertory) | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Repertory sections still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | QA
12 | 56 | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.2 | ADM-R02 | Keep and harden Admin Subsection & rubric tree (do not rebuild) | ADM-R02.01 | Regression: list / add / edit / (import-export if present) for Subsection & rubric tree | Existing | Repertory | §7.1 | Subsection & rubric tree | Manage the full rubric hierarchy | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | — | Web |  | Hierarchical subsection/rubric tree + Excel import/export live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Subsection & rubric tree still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | QA
13 | 59 | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.3 | ADM-R03 | Keep and harden Admin Rubric–remedy mapping (do not rebuild) | ADM-R03.01 | Regression: list / add / edit / (import-export if present) for Rubric–remedy mapping | Existing | Repertory | §7.1 | Rubric–remedy mapping | Map remedies to rubrics with author and grade | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | — | Web |  | Rubric-remedy mapping by author/grade live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Rubric–remedy mapping still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | QA
14 | 62 | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.4 | ADM-R04 | Keep and harden Admin Remedy-linked rubrics (do not rebuild) | ADM-R04.01 | Regression: list / add / edit / (import-export if present) for Remedy-linked rubrics | Existing | Repertory | §7.1 | Remedy-linked rubrics | View all rubrics linked to a remedy | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | — | Web |  | Remedial-rubrics viewer live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Remedy-linked rubrics still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | QA
15 | 65 | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.5 | ADM-R05 | Keep and harden Admin Language master (do not rebuild) | ADM-R05.01 | Regression: list / add / edit / (import-export if present) for Language master | Existing | Repertory | §7.1 | Language master | Manage languages | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | — | Web |  | Language master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Language master still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | QA
16 | 68 | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.6 | ADM-R06 | Keep and harden Admin Body part master (do not rebuild) | ADM-R06.01 | Regression: list / add / edit / (import-export if present) for Body part master | Existing | Repertory | §7.1 | Body part master | Manage body parts | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | — | Web |  | Body part master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Body part master still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | QA
17 | 71 | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.7 | ADM-R07 | Keep and harden Admin Intensity master (do not rebuild) | ADM-R07.01 | Regression: list / add / edit / (import-export if present) for Intensity master | Existing | Repertory | §7.1 | Intensity master | Manage intensity levels | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | — | Web |  | Intensity master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Intensity master still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | QA
18 | 74 | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.8 | ADM-R08 | Keep and harden Admin Remedy master (do not rebuild) | ADM-R08.01 | Regression: list / add / edit / (import-export if present) for Remedy master | Existing | Repertory | §7.1 | Remedy master | Manage the remedy library | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | — | Web |  | Remedy master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Remedy master still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | QA
19 | 77 | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.9 | ADM-R09 | Keep and harden Admin Remedy grade master (do not rebuild) | ADM-R09.01 | Regression: list / add / edit / (import-export if present) for Remedy grade master | Existing | Repertory | §7.1 | Remedy grade master | Manage remedy grading | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | — | Web |  | Remedy grade master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Remedy grade master still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | QA
20 | 80 | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.10 | ADM-M01 | Keep and harden Admin Author master (do not rebuild) | ADM-M01.01 | Regression: list / add / edit / (import-export if present) for Author master | Existing | Materia Medica | §7.1 | Author master | Manage materia medica authors | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | — | Web |  | Author master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Author master still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | QA
21 | 83 | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.11 | ADM-M02 | Keep and harden Admin Materia medica master (do not rebuild) | ADM-M02.01 | Regression: list / add / edit / (import-export if present) for Materia medica master | Existing | Materia Medica | §7.1 | Materia medica master | Manage the materia medica library | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | — | Web |  | MM master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Materia medica master still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | QA
22 | 86 | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.12 | ADM-M03 | Keep and harden Admin Materia medica heads (do not rebuild) | ADM-M03.01 | Regression: list / add / edit / (import-export if present) for Materia medica heads | Existing | Materia Medica | §7.1 | Materia medica heads | Manage chapter headings | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | — | Web |  | MM heads live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Materia medica heads still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | QA
23 | 89 | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.13 | ADM-M04 | Keep and harden Admin Materia medica remedies (do not rebuild) | ADM-M04.01 | Regression: list / add / edit / (import-export if present) for Materia medica remedies | Existing | Materia Medica | §7.1 | Materia medica remedies | View remedy-wise materia medica | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | — | Web |  | Remedy-wise MM viewer live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Materia medica remedies still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | QA
24 | 92 | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.14 | ADM-D01 | Keep and harden Admin Diagnosis system (do not rebuild) | ADM-D01.01 | Regression: list / add / edit / (import-export if present) for Diagnosis system | Existing | Diagnosis | §7.1 | Diagnosis system | Manage diagnosis systems | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | — | Web |  | Diagnosis system CRUD live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Diagnosis system still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | QA
25 | 95 | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.15 | ADM-D02 | Keep and harden Admin Diagnosis therapeutics (do not rebuild) | ADM-D02.01 | Regression: list / add / edit / (import-export if present) for Diagnosis therapeutics | Existing | Diagnosis | §7.1 | Diagnosis therapeutics | Manage therapeutics | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | — | Web |  | Therapeutics details live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Diagnosis therapeutics still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | QA
26 | 98 | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.16 | ADM-D03 | Keep and harden Admin Diagnosis conditions (do not rebuild) | ADM-D03.01 | Regression: list / add / edit / (import-export if present) for Diagnosis conditions | Existing | Diagnosis | §7.1 | Diagnosis conditions | Manage conditions and linked rubrics | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | — | Web |  | Conditions + keyword→rubric live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Diagnosis conditions still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | QA
27 | 101 | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.17 | ADM-A01 | Keep and harden Admin Drug system (do not rebuild) | ADM-A01.01 | Regression: list / add / edit / (import-export if present) for Drug system | Existing | Adverse Effect | §7.1 | Drug system | Manage conventional drug systems | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | — | Web |  | Drug system CRUD live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Drug system still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | QA
28 | 104 | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.18 | ADM-A02 | Keep and harden Admin Drug group (do not rebuild) | ADM-A02.01 | Regression: list / add / edit / (import-export if present) for Drug group | Existing | Adverse Effect | §7.1 | Drug group | Manage drug groups | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | — | Web |  | Drug group CRUD live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Drug group still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | QA
29 | 107 | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.19 | ADM-A03 | Keep and harden Admin Allopathic drug & side effects (do not rebuild) | ADM-A03.01 | Regression: list / add / edit / (import-export if present) for Allopathic drug & side effects | Existing | Adverse Effect | §7.1 | Allopathic drug & side effects | Manage drugs with side effects and adverse reactions | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | — | Web |  | Allopathic drug + serious/other/adverse live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Allopathic drug & side effects still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | QA
30 | 110 | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.20 | ADM-Q01 | Keep and harden Admin Question section, group & sub-group (do not rebuild) | ADM-Q01.01 | Regression: list / add / edit / (import-export if present) for Question section, group & sub-group | Existing | Clinical Questions | §7.1 | Question section, group & sub-group | Manage the clinical questionnaire structure | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | — | Web |  | Existance / question group / subgroup CRUD live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Question section, group & sub-group still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | QA
31 | 113 | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.21 | ADM-Q02 | Keep and harden Admin Clinical question mapping (do not rebuild) | ADM-Q02.01 | Regression: list / add / edit / (import-export if present) for Clinical question mapping | Existing | Clinical Questions | §7.1 | Clinical question mapping | Map questions to body parts and rubrics | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | — | Web |  | Clinical questions mapped to body parts and rubrics live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Clinical question mapping still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | QA
32 | 116 | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.22 | ADM-3D1 | Keep and harden Admin 3D mesh key master (do not rebuild) | ADM-3D1.01 | Regression: list / add / edit / (import-export if present) for 3D mesh key master | Existing | 3D Body | §7.1 | 3D mesh key master | Manage 3D model references | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | — | Web |  | Mesh key master on .NET 8 live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | 3D mesh key master still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | QA
33 | 119 | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.23 | ADM-3D2 | Keep and harden Admin 3D section master (do not rebuild) | ADM-3D2.01 | Regression: list / add / edit / (import-export if present) for 3D section master | Existing | 3D Body | §7.1 | 3D section master | Manage 3D body sections | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | — | Web |  | 3D section master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | 3D section master still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | QA
34 | 122 | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.24 | ADM-3D3 | Keep and harden Admin 3D hotspots (do not rebuild) | ADM-3D3.01 | Regression: list / add / edit / (import-export if present) for 3D hotspots | Existing | 3D Body | §7.1 | 3D hotspots | Manage clickable points on the 3D model | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | — | Web |  | Hotspot master live; doctor viewer consumes them | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | 3D hotspots still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started | QA
35 | 125 | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.25 | ADM-B01 | Business Management — Doctor qualifications (existing, used later by credentialing) | ADM-B01.01 | Regression: qualifications list/add/edit | Existing | Business Management | §7.2 | Doctor qualifications | Manage the qualification list | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | — | Web |  | Qualifications CRUD on newer API live; used by RegisterDoctor | Keep; credentialing Phase 8 will reference QualificationId | Qualification list still drives doctor registration | Not Started | QA
36 | 128 | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.26 | ADM-B02 | Business Management — Lab & imaging test catalog (existing, used by eRx lab orders) | ADM-B02.01 | Regression: lab catalog CRUD and doctor order pick-list | Existing | Business Management | §7.2 | Lab & imaging test catalog | Manage the test catalogue | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | — | Web |  | Labs & imaging CRUD live; Patient Board orders from this catalogue | Keep; eRx Phase 10 continues to use the same catalogue | Doctor can still order a lab from the catalogue | Not Started | QA
37 | 131 | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.27 | ADM-B03 | Business Management — Subscription packages (existing S1 SaaS; later tied to Account ledger) | ADM-B03.01 | Regression: package list/add/edit; doctor Widgets still reads packages | Existing | Business Management | §7.2 | Subscription packages | Manage doctor subscription plans | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | — | Web |  | Package CRUD live; Razorpay buy/renew partial (no webhook) | Do not overload PackageEntryDetail for consult/medicine money; Phase 6 ports payment verification | Admin can still create/edit packages; doctor still sees plan flags | Not Started | QA
38 | 137 | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.28 | ADM-B04 | Business Management — Roles & menu permissions (existing DB, runtime ACL leftover) | ADM-B04.04 | QA: edit role menu → user of that role no longer sees the item | Regression | Business Management | §7.2 | Roles & menu permissions | Control exactly what each role can access | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P1 | S | ADM-B04.03 | — | Web, UI | ADM-B04.03 | Role CRUD screens live; runtime GetMenuByRole commented; no frontend route ACL | This is the product surface for SEC-04; complete wiring here | Changing a role’s menu immediately hides those routes after refresh | Not Started | QA
39 | 140 | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.1 | CLN-01 | Clinical workspace — single screen for the entire consultation | CLN-01.03 | Regression: open case from dashboard still remounts via PatientBoardRoute | Regression | Patient Board | §5.3 | Clinical workspace | Single screen for the entire consultation | Doctor Web Portal | QA | Yes | No | No | No | No | No | P1 | S | CLN-01.02 | — | Web, UI | CLN-01.02 | PatientBoard.js (~13.5k) is the workspace; ~90% — missing payment/tele/eRx header status | Keep one screen; add header chips for payment, tele session, signed eRx (chips light up as later phases land) | Doctor still opens one board per patient; new chips do not break tabs | Not Started | QA
40 | 141 | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.2 | CLN-02 | Manual case taking — structured case taking (keep) | CLN-02.01 | Regression: create case, add rubrics via manual path, repertorize | Existing | Patient Board | §5.3 | Manual case taking | Structured case taking | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | — | Web |  | Classic case-taking tabs live | Regression only; do not rebuild | Manual case taking still saves/restores | Not Started | QA
41 | 144 | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.3 | CLN-03 | Body parts & intensity selection (keep) | CLN-03.01 | Regression: body part → rubrics; intensity chip | Existing | Patient Board | §5.3 | Body parts & intensity selection | Select affected areas and severity | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | — | Web |  | Body Parts tab + intensity chips live | Regression; intensity master from Phase 1 still drives chips | Selecting a body part + intensity still adds rubrics | Not Started | QA
42 | 147 | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.4 | CLN-04 | Clinical questions — guided questions by section, group and sub-group (keep) | CLN-04.01 | Regression: full question drill-down | Existing | Patient Board | §5.3 | Clinical questions | Guided questions by section, group and sub-group | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | — | Web |  | Questions tab loads Existance taxonomy live | Regression | Section → group → subgroup → keywords → rubrics still works | Not Started | QA
43 | 150 | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.5 | CLN-05 | Diagnosis, therapeutics & pattern search (keep) | CLN-05.01 | Regression: diagnosis search + therapeutics | Existing | Patient Board | §5.3 | Diagnosis, therapeutics & pattern search | Search diagnoses and linked therapeutics | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | — | Web |  | Clinical Pattern tab live (13 keyword tabs + therapeutics) | Regression | Diagnosis search still returns linked rubrics and therapeutics | Not Started | QA
44 | 153 | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.6 | CLN-06 | Repertory rubric search & selection (keep) | CLN-06.01 | Regression: tree + search + add to clipboard | Existing | Patient Board | §5.3 | Repertory rubric search & selection | Search and select from the full repertory | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | — | Web |  | Repertory tree + search live | Regression; small UX polish allowed but not a rewrite | Search still adds to clipboard | Not Started | QA
45 | 159 | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.7 | CLN-07 | Manage selected rubrics — review, edit and remove (remaining ~10%) | CLN-07.04 | QA: remove, undo-not-required, backup restore still has remaining rubrics | Regression | Patient Board | §5.3 | Manage selected rubrics | Review, edit and remove selected rubrics | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P1 | S | CLN-07.03 | — | Web, UI | CLN-07.03 | Clipboard exists; confirm-delete / intensity-edit incomplete | Confirm delete; edit intensity on selected rubric; no accidental wipe | Doctor can remove one rubric without losing the rest | Not Started | QA
46 | 160 | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.8 | CLN-08 | Audio case taking — record and receive suggested rubrics (keep engine; do not rebuild) | CLN-08.01 | Regression: record, poll, approve/reject suggested rubrics | Existing | Audio AI | §5.3 | Audio case taking | Record the consultation and receive suggested rubrics automatically | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P1 | S | — | — | Web |  | Whisper + rubric engines + CaseTaking UI live on .NET 8 | Keep; follow existing AUDIO_CASE_TAKING_* docs; accuracy is the next task | Record/upload still produces suggested rubrics for approve/reject | Not Started | QA
47 | 165 | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.9 | CLN-09 | Improved rubric accuracy — enhanced accuracy rules for audio-based rubric suggestions | CLN-09.03 | QA: golden transcripts → expected rubric IDs within tolerance | Regression | Audio AI | §5.3 | Improved rubric accuracy | Enhanced accuracy rules for audio-based rubric suggestions | Doctor Web Portal + Admin intelligence | QA | No | Yes | No | No | No | No | P1 | M | CLN-09.02 | — | Web, UI | CLN-09.02 | Engine + admin metaphors/aliases exist; accuracy rules still in progress (~50%) | Complete accuracy rules per AUDIO_CASE_TAKING_AI_ENGINE docs; metaphor/alias QA | Benchmark set meets agreed accuracy gate before calling this done | Not Started | QA
48 | 169 | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.10 | CLN-10 | Materia medica reference during consultation (remaining ~10%) | CLN-10.04 | QA: open MM for a repertorized remedy | Regression | Patient Board | §5.3 | Materia medica reference | Browse materia medica during the consultation | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | CLN-10.03 | — | Web, UI | CLN-10.03 | MM tab + repertorize differential accordion ~90% | Faster head navigation during case; do not rebuild MM masters | Doctor can open a remedy MM without leaving the board | Not Started | QA
49 | 170 | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.11 | CLN-11 | Allopathic drug side-effect lookup (keep) | CLN-11.01 | Regression: search drug → side effects | Existing | Patient Board | §5.3 | Allopathic drug side-effect lookup | Check side effects of conventional medicines | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | — | Web |  | Adverse Effect tab live | Regression | Lookup still shows serious/other/adverse | Not Started | QA
50 | 176 | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.12 | CLN-12 | Repertorization & elimination (remaining ~10%) | CLN-12.04 | QA: known case → expected top remedies | Regression | Patient Board | §5.3 | Repertorization & elimination | Full repertorization with elimination | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P1 | S | CLN-12.03 | — | Web, UI | CLN-12.03 | Common/uncommon/elimination live ~90% | Stability polish; Center of Gravity is a NEW panel on the same rubrics (next task) | Elimination still ranks remedies from selected rubrics | Not Started | QA
51 | 180 | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.13 | CLN-13 | Center of Gravity — new analysis identifying the central remedy of the case, with reasoning shown | CLN-13.04 | QA: same clipboard as classic repertorize; COG reasons cite contributing rubrics; empty clipboard → clear empty state | Regression | Repertorization | §5.3 | Center of Gravity | New analysis identifying the central remedy of the case, with reasoning shown | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P1 | S | CLN-13.03 | — | Web, UI | CLN-13.03 | Does not exist | POST /api/Repertorization/CenterOfGravity from selected rubric ids + intensities; UI panel with explainability | COG returns ranked central remedies plus contribution reasons the doctor can read | Not Started | QA
52 | 181 | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.14 | CLN-14 | Lab orders & lab entries (keep; later also sit on eRx) | CLN-14.01 | Regression: order lab from catalogue; enter result | Existing | Patient Board | §5.3 + §11 | Lab orders & lab entries | Order tests and record results / Tests ordered alongside the prescription | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | — | Web |  | Lab order + result entry on prescription modal live | Keep; when eRx splits notes from Rx, labs stay on the prescription/eRx side | Order + result still save against the appointment | Not Started | QA
53 | 184 | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.15 | CLN-15 | Appointment history notes (keep; split from eRx in Phase 10) | CLN-15.01 | Regression: add/list notes on a visit | Existing | Patient Board | §5.3 | Appointment history notes | Notes recorded against each visit | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P1 | S | — | — | Web |  | AppointmentHistoryNote APIs live (classic); currently mixed into Rx modal tabs | Keep save/get; Phase 10 moves UX outside Rx modal and adds NoteType / IsErxExcluded | Notes still save against PatientAppId | Not Started | QA
54 | 190 | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.16 | CLN-16 | Complaints & case details — wire Patient Board to existing SaveComplaints / SaveCaseDetails (~20% today) | CLN-16.04 | QA: save, reload, second doctor cannot read | Regression | Patient Board | §5.3 | Complaints & case details | Capture and store complaints and case details | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P1 | S | CLN-16.03 | — | Web, UI | CLN-16.03 | Classic SaveComplaints / SaveCaseDetails APIs exist; Patient Board does not call them | Call the existing APIs from the board; Reception case-paper (Phase 5) uses a subset | Complaints and case details persist and reload on the board | Not Started | QA
55 | 194 | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.17 | CLN-17 | Patient back history — complete history of visits, notes, prescriptions and payments | CLN-17.04 | QA: multi-visit patient; empty new patient | Regression | Patient Board | §5.3 | Patient back history | Complete history of visits, notes, prescriptions and payments | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P1 | S | CLN-17.03 | — | Web, UI | CLN-17.03 | History panel ~70%; no payment line (payments do not exist yet) | Timeline: visits, notes, eRx, labs; payment row added when Phase 6 lands (placeholder now) | Doctor sees chronological visits with notes and Rx; payment appears after Phase 6 | Not Started | QA
56 | 197 | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.18 | CLN-18 | Export case data — download the full case in Excel or PDF | CLN-18.03 | QA: export matches on-screen rubrics + Rx; unauthorised doctor 403 | Regression | Patient Board | §5.3 | Export case data | Download the full case in Excel or PDF | Doctor Web Portal | QA | Yes | Yes | No | No | No | No | P1 | S | CLN-18.02 | — | Web, UI | CLN-18.02 | Newer ExportCasesToExcel exists; no Patient Board export UI; no PDF | Toolbar Excel + PDF using existing Excel API + new PDF renderer; exclude private notes from patient-facing PDF (eRx print is Phase 10) | Doctor downloads Excel and PDF of the case they own | Not Started | QA
57 | 198 | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.19 | CLN-19 | Session restore — continue exactly where the doctor left off, across multiple patients (keep) | CLN-19.01 | Regression: backup, restore, 5-session stack | Existing | Patient Board | §5.3 | Session restore | Continue exactly where the doctor left off, across multiple patients | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | — | Web |  | Up to 5 in-memory sessions + DoctorPatientBoardBackup live | Regression; header stack remains | Kill browser, login, restore last work | Not Started | QA
58 | 204 | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.20 | CLN-20 | 3D anatomy viewer — interactive 3D body model linked to rubric search (remaining ~50%) | CLN-20.04 | QA: click hotspot → subsection search results | Regression | Anatomy | §5.3 | 3D anatomy viewer | Interactive 3D body model linked to rubric search | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | CLN-20.03 | — | Web, UI | CLN-20.03 | three.js viewer + hotspot→search live; incomplete mesh coverage / UX | Complete GLB/hotspot coverage; mobile fallback later; admin 3D masters already in Phase 1 | Every admin hotspot on the shipped models opens the correct rubric search | Not Started | QA
59 | 208 | QA | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.1 | DOC-01 | Doctor home dashboard — complete overview of the working day (remaining ~30%) | DOC-01.04 | QA: existing buckets still populate; reception still shares layout until Phase 5 reception chrome | Regression | Doctor Dashboard | §5.1 | Doctor home dashboard | Complete overview of the working day | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P1 | S | DOC-01.03 | — | Web, UI | DOC-01.03 | Widgets + BestSellingProducts ~70%; missing online toggle, tele queue, payment badges, follow-up due | Extend, do not replace; later phases light up tele/payment chips | Doctor sees today’s buckets plus placeholders for tele/payment that become live in Phases 6 and 11 | Not Started | QA
60 | 209 | QA | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.2 | DOC-02 | Patient counts & waiting list — live counts by status with quick actions (keep; extend paid/unpaid) | DOC-02.01 | Regression: each bucket count and click-through | Existing | Doctor Dashboard | §5.1 | Patient counts & waiting list | Live counts by status with quick actions | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P1 | S | — | — | Web |  | Status buckets WAITING, WALK-IN, NOT ARRIVED, E-CONSULT, REMAINING, COMPLETED live | Keep; add CANCELLED in Phase 4; paid/unpaid badge in Phase 6 | Counts still match appointment list | Not Started | QA
61 | 215 | QA | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.3 | DOC-03 | Patient search, list & open case (remaining ~10%) | DOC-03.04 | QA: search by name/mobile; open case | Regression | Doctor Dashboard | §5.1 | Patient search, list & open case | Find any patient and open their case instantly | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P1 | S | DOC-03.03 | — | Web, UI | DOC-03.03 | Search/list/open ~90%; missing last visit, unpaid, family filters | Add last-visit column; unpaid/family after those modules exist | Search still opens Patient Board; last visit visible | Not Started | QA
62 | 216 | QA | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.4 | DOC-04 | Add new patient — register a patient in seconds (keep) | DOC-04.01 | Regression: add patient validation and save | Existing | Patients | §5.1 | Add new patient | Register a patient in seconds | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P1 | S | — | — | Web |  | Create patient live | Regression; public self-registration is a different Patient identity in Phase 9 | Doctor can still create a clinic patient | Not Started | QA
63 | 219 | QA | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.5 | DOC-05 | Import patients — bring existing patient records in bulk (keep) | DOC-05.01 | Regression: template + import + error rows | Existing | Patients | §5.1 | Import patients | Bring existing patient records in bulk | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | — | Web |  | Import live | Regression | Import still creates patients for this doctor | Not Started | QA
64 | 224 | QA | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.6 | DOC-06 | Export patients — download patient data in Excel, CSV or PDF (keep) | DOC-06.03 | QA: another doctor cannot export this list | Regression | Patients | §5.1 | Export patients | Download patient data in Excel, CSV or PDF | Doctor Web Portal | QA | Yes | Yes | No | No | No | No | P2 | S | DOC-06.02 | — | Web, UI | DOC-06.02 | Export live (confirm PDF vs Excel/CSV in QA) | If PDF is missing, add it as Existing Improvement; do not skip the PDF wording in the PDF | Excel, CSV and PDF each download this doctor’s patients only | Not Started | QA
65 | 225 | QA | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.7 | DOC-07 | Recent activity panel (keep) | DOC-07.01 | Regression: activity loads | Existing | Doctor Dashboard | §5.1 | Recent activity panel | Everything that happened recently, at a glance | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | — | Web |  | Recent activity live | Regression; later include payment/tele events when those exist | Panel still lists recent actions | Not Started | QA
66 | 228 | QA | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.8 | DOC-08 | Patient statistics charts (keep; foundation for clinic performance in Phase 18) | DOC-08.01 | Regression: stats charts date range | Existing | Doctor Dashboard | §5.1 | Patient statistics charts | Visual practice statistics | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | — | Web |  | GetPatientStats / GetPatientStatsCharts + ApexCharts live | Keep; clinic performance report extends this in Phase 18 | Charts still render for the doctor | Not Started | QA
67 | 233 | QA | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.9 | DOC-09 | Manage reception staff — add, edit and remove reception users (backend done, UI absent) | DOC-09.03 | QA: reception user cannot manage other doctors’ staff; disable prevents login | Regression | Staff | §5.1 | Manage reception staff | Add, edit and remove reception users | Doctor Web Portal | QA | Yes | Yes | No | No | No | No | P1 | S | DOC-09.02 | — | Web, UI | DOC-09.02 | .NET 8 api/ReceptionStaff CRUD exists; no SPA page | List/add/edit/disable at /doctor/reception-staff; doctor owns the staff record | Doctor can create a reception user who logs in to that DoctorId | Not Started | QA
68 | 237 | QA | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.10 | DOC-10 | Doctor profile — clinic details, consultation fee, photo, qualifications, working hours, bank details | DOC-10.04 | QA: reception cannot edit doctor bank details; photo displays on public profile later | Regression | Doctor Profile | §5.1 | Doctor profile | Clinic details, consultation fee, photo, qualifications, working hours, bank details | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P0 | S | DOC-10.03 | — | Web, UI | DOC-10.03 | /profile is Velzon first_name only (~20%); credentials sit on Doctor entity; no fee/KYC UI | Real doctor profile: clinic, photo, qualifications, consult fee (feeds Phase 6), hours (feeds schedule), bank KYC (feeds Account payees) | Doctor can save clinic, photo, qualifications, fee, hours, bank details; verification status visible | Not Started | QA
69 | 238 | QA | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.1 | APT-01 | Appointment list & waiting patients — full day view with live status (keep; later payment/tele) | APT-01.01 | Regression: day list, status colour, open patient | Existing | Appointments | §5.2 | Appointment list & waiting patients | Full day view with live status | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P1 | S | — | — | Web |  | Day list + status live | Keep; reschedule/cancel/payment attach to this list | Day view still lists today’s appointments | Not Started | QA
70 | 244 | QA | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.2 | APT-02 | Create new appointment — persist visit type, consultation mode and fee | APT-02.04 | QA: staff-created appointments carry the same fields public booking will use in Phase 9 | Regression | Appointments | §5.2 | Create new appointment | Book with visit type, consultation mode and fee | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P0 | S | APT-02.03 | — | Web, UI | APT-02.03 | Create appointment ~90%; Formik modal has no VisitType / ConsultMode / fee | VisitType First/Follow-up; ConsultMode In-clinic / E-Consult; fee display from doctor profile / ConsultFeeConfig | New appointments persist visit type, mode and fee; filters/analytics can use them | Not Started | QA
71 | 245 | QA | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.3 | APT-03 | Appointment status update — move patients through the visit stages (keep) | APT-03.01 | Regression: each status transition | Existing | Appointments | §5.2 | Appointment status update | Move patients through the visit stages | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P1 | S | — | — | Web |  | Status transitions live | Keep; add CANCELLED in APT-06; do not reuse DeleteStatus as cancel | Status still updates and buckets refresh | Not Started | QA
72 | 248 | QA | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.4 | APT-04 | Appointment time update — adjust timings as the day runs (keep; distinct from formal reschedule) | APT-04.01 | Regression: UpdateAppointmentTime on dashboard | Existing | Appointments | §5.2 | Appointment time update | Adjust timings as the day runs | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P1 | S | — | — | Web |  | UpdateAppointmentTime live — changes a time only; no audit/notify | Keep same-day time tweak; formal reschedule (old→new, notify, conflict) is APT-05 | Same-day time change still works; does not silently replace Reschedule | Not Started | QA
73 | 255 | QA | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.5 | APT-05 | Reschedule appointment — move to a new slot with automatic patient notification (NEW — not a rename of UpdateAppointmentTime) | APT-05.05 | QA: slot taken → 409; patient already booked elsewhere; across a schedule change; reception authorised for own DoctorId only | Regression | Appointments | §5.2 + §2.3 + §6 | Reschedule appointment | Move to a new slot with automatic patient notification / Move to another slot without calling the clinic | Doctor Web + Reception + later Patient | QA | Yes | Yes | No | Yes | No | No | P0 | S | APT-05.04 | — | Web, UI | APT-05.04 | Time can be edited; no formal Reschedule (audit, notify, old→new confirm) | POST RescheduleAppointment; AppointmentChangeLog; conflict 409 with alternatives; SMS/WhatsApp fan-out (notify failure must not roll back) | Every reschedule is in the change log; patient notified; old slot released; reception uses the same API | Not Started | QA
74 | 260 | QA | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.6 | APT-06 | Cancel appointment — reason, free the slot, trigger refund where applicable (NEW CANCELLED status — do NOT reuse DeleteStatus) | APT-06.05 | QA: reason mandatory; all three roles (later Patient) cancel with correct authorisation; freed slot bookable | Regression | Appointments | §5.2 + §2.3 + §6 | Cancel appointment | Cancel with reason, free the slot, trigger refund where applicable / Cancel with reason, refund handled per policy | Doctor Web + Reception + later Patient | QA | Yes | Yes | No | Yes | No | No | P0 | S | APT-06.04 | — | Web, UI | APT-06.04 | No CANCELLED; DeleteStatus is soft-delete only | CANCELLED + reason fields; free slot; waitlist hook; if PAID evaluate refund policy (Phase 6/7) | Cancelled appointments leave active buckets; slot immediately bookable; refund path triggered rather than silently keeping money | Not Started | QA
75 | 263 | QA | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.7 | APT-07 | Daily schedule setup — define working days, hours and break times (promote modal to first-class screen) | APT-07.03 | QA: save week; public slot generator (Phase 9) uses this data; reception read-only is Phase 5 | Regression | Scheduling | §5.2 | Daily schedule setup | Define working days, hours and break times | Doctor Web Portal | QA | Yes | Yes | No | No | No | No | P0 | S | APT-07.02 | — | Web, UI | APT-07.02 | DailyScheduleSetupModal + GetDailySchedule / SaveDailySchedule exist; not a first-class screen (draft marked 0%) | Promote to /doctor/schedule with week grid and copy-day; reuse existing APIs — do not rebuild | Public booking slots (Phase 9) respect the saved schedule | Not Started | QA
76 | 264 | QA | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.8 | APT-08 | Appointment slot grid — visual slot-by-slot view of the day (keep; public booking reuses this) | APT-08.01 | Regression: slot grid vs schedule | Existing | Scheduling | §5.2 | Appointment slot grid | Visual slot-by-slot view of the day | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P0 | S | — | — | Web |  | Slot picker / grid live | Keep; Phase 9 public APIs reuse the same slot engine | Grid matches saved daily schedule | Not Started | QA
77 | 270 | QA | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.9 | APT-09 | Consultation payment status on every appointment (schema now; values live in Phase 6) | APT-09.04 | QA: same appointment shows the same badge on doctor and reception | Regression | Appointments | §5.2 + §9 | Consultation payment status | See paid, unpaid or pay-at-clinic on every appointment / Doctor, reception and patient all see the same payment status | Doctor Web Portal | QA | Yes | No | No | No | No | No | P0 | S | APT-09.03 | — | Web, UI | APT-09.03 | No PaymentStatus on appointment | Add PaymentStatus UNPAID / PENDING / PAID / FAILED / PAY_AT_CLINIC / REFUNDED; UI badge; source of truth is webhook in Phase 6 not the client screen | Every appointment row can show a payment badge; until Phase 6 all show UNPAID/PAY_AT_CLINIC as configured | Not Started | QA
78 | 271 | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.1 | REC-01 | Reception login — secure staff access (keep) | REC-01.01 | Regression: reception login with DoctorID claim | Existing | Reception | §6 | Reception login | Secure staff access | Reception Portal | QA | Yes | Yes | No | Yes | No | No | P1 | S | — | — | Web |  | Reception logs in via Account; JWT includes DoctorID; uses doctor dashboard layout | Keep login; Phase 0 hashing applies; later dedicated reception chrome | Reception user still logs in and lands on front-desk home | Not Started | QA
79 | 277 | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.2 | REC-02 | Reception profile — manage own profile details (0% today) | REC-02.04 | QA: cannot edit doctor qualifications or fee | Regression | Reception | §6 | Reception profile | Manage own profile details | Reception Portal | QA | Yes | Yes | No | Yes | No | No | P1 | S | REC-02.03 | — | Web, UI | REC-02.03 | No reception-specific profile; shared Velzon /profile | Name, mobile, attached doctor (read-only); cannot edit doctor bank/fee | Reception can update own name/mobile; cannot change DoctorId | Not Started | QA
80 | 280 | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.3 | REC-03 | Reception home dashboard — purpose-built front-desk dashboard (not only hidden doctor actions) | REC-03.03 | QA: deep-link to Patient Board full clinical URL is 403 for reception | Regression | Reception | §6 | Reception home dashboard | Purpose-built front-desk dashboard | Reception Portal | QA | Yes | Yes | No | No | No | No | P1 | S | REC-03.02 | — | UI | REC-03.02 | Same /doctordashboard with some clinical actions disabled ~90% | Reception-first chrome: queue, collect pay, case paper, no repertory/Rx; optional /reception home route | Reception never sees repertorize/audio/COG; sees queue and collect-pay | Not Started | QA
81 | 281 | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.4 | REC-04 | Create patient — register a walk-in patient quickly (keep) | REC-04.01 | Regression: reception create patient | Existing | Reception | §6 | Create patient | Register a walk-in patient quickly | Reception Portal | QA | Yes | Yes | No | Yes | No | No | P1 | S | — | — | Web |  | Create patient live on shared dashboard | Keep on reception chrome | Walk-in patient created under the JWT DoctorId | Not Started | QA
82 | 284 | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.5 | REC-05 | Patient search & list — find any patient instantly (keep) | REC-05.01 | Regression: search by name/mobile | Existing | Reception | §6 | Patient search & list | Find any patient instantly | Reception Portal | QA | Yes | Yes | No | Yes | No | No | P1 | S | — | — | Web |  | Search live | Keep; no opening full clinical board | Search returns this doctor’s patients only | Not Started | QA
83 | 289 | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.6 | REC-06 | Create & manage appointments — full appointment management (keep; plus reschedule/cancel from Phase 4) | REC-06.03 | QA: cannot cancel another clinic’s appointment | Regression | Reception | §6 | Create & manage appointments | Full appointment management | Reception Portal | QA | Yes | Yes | No | No | No | No | P0 | S | REC-06.02 | — | Web, UI | REC-06.02 | Create/status/time live; reschedule/cancel missing until Phase 4 APIs | Enable RescheduleAppointment and CancelAppointment for JWT DoctorId; isReceptionUser must not block | Reception acts only for its doctor; permission tests pass | Not Started | QA
84 | 291 | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.7 | REC-07 | New appointment — book on behalf of the patient (keep; same VisitType/ConsultMode/fee as APT-02) | REC-07.02 | QA: in-clinic vs E-Consult both creatable from reception | Regression | Reception | §6 | New appointment | Book on behalf of the patient | Reception Portal | QA | Yes | No | No | No | No | No | P1 | S | REC-07.01 | — | UI | REC-07.01 | New appointment modal live; fields incomplete until APT-02 | Same modal fields as doctor so public booking later matches staff-created rows | Reception-created appointments have visit type, mode, fee | Not Started | QA
85 | 295 | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.8 | REC-08 | Waiting queue management — manage the live queue and call the next patient | REC-08.04 | QA: two waiting patients; call next picks the right one | Regression | Reception | §6 | Waiting queue management | Manage the live queue and call the next patient | Reception Portal | QA | Yes | Yes | No | Yes | No | No | P1 | S | REC-08.03 | — | Web, UI | REC-08.03 | Status buckets ~60%; no dedicated queue UX / call-next | Dedicated queue: walk-in vs tele; payment state; Call next; notify patient (later push) | Reception can call next; status moves; patient can be notified when Phase 12 exists | Not Started | QA
86 | 296 | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.9 | REC-09 | Appointment status update (reception) — update as patients arrive and are seen (keep) | REC-09.01 | Regression: reception status update | Existing | Reception | §6 | Appointment status update | Update as patients arrive and are seen | Reception Portal | QA | Yes | Yes | No | Yes | No | No | P1 | S | — | — | Web |  | Status update live | Keep on reception chrome | Arrived / seen transitions still work | Not Started | QA
87 | 299 | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.10 | REC-10 | Appointment time update (reception) — adjust timings through the day (keep) | REC-10.01 | Regression: reception UpdateAppointmentTime | Existing | Reception | §6 | Appointment time update | Adjust timings through the day | Reception Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | — | Web |  | Time update live | Keep; formal reschedule remains REC-06 | Same-day time tweak from reception works | Not Started | QA
88 | 303 | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.11 | REC-11 | View doctor schedule — see the doctor’s working schedule (read-only) | REC-11.02 | QA: edit buttons hidden; doctor can still edit on /doctor/schedule | Regression | Reception | §6 | View doctor schedule | See the doctor’s working schedule | Reception Portal | QA | Yes | No | No | No | No | No | P1 | S | REC-11.01 | — | UI | REC-11.01 | GetDailySchedule exists; no reception view | Read-only /reception/schedule using DoctorID from JWT | Reception views hours; cannot edit clinical schedule unless authorised | Not Started | QA
89 | 307 | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.12 | REC-12 | Log case paper / chief complaint — record the reason for visit before the consultation | REC-12.04 | QA: doctor sees CC; reception 403 on repertory APIs | Regression | Reception | §6 | Log case paper / chief complaint | Record the reason for visit before the consultation | Reception Portal | QA | Yes | Yes | No | Yes | No | No | P1 | S | REC-12.03 | — | Web, UI | REC-12.03 | Missing; SaveComplaints exists but board is doctor-only | Restricted case-paper form (chief complaint only — no repertory/Rx); audit reception author | Chief complaint visible to doctor on Patient Board; reception cannot repertorize | Not Started | QA
90 | 313 | QA | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.1 | PAY-01 | Consultation fee configuration — each doctor’s fee set and displayed to patients | PAY-01.04 | QA: changing fee does not alter already-created unpaid orders without a rule (document the rule) | Regression | Payments | §9 | Consultation fee configuration | Each doctor’s fee set and displayed to patients | Doctor profile + Public + Admin | QA | Yes | Yes | No | Yes | No | No | P0 | S | PAY-01.03 | — | Web, UI | PAY-01.03 | No ConsultFeeConfig; doctor profile work in DOC-10 may have stored a fee field | ConsultFeeConfig (InClinic, EConsult, optional Instant surcharge, PayAtClinicEnabled, GST flags) | Fee shown to patients matches what checkout charges; admin/doctor can update | Not Started | QA
91 | 317 | QA | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.2 | PAY-02 | Automatic payment verification — bank/webhook is source of truth, not the patient’s screen | PAY-02.04 | QA: duplicate webhook; delayed webhook; failed capture; app closed mid-checkout | Regression | Payments | §9 | Automatic payment verification | Payments confirmed by the bank, not by the patient’s screen — nothing is lost if the app or browser closes | Shared | QA | No | Yes | No | No | No | Yes | P0 | M | PAY-02.03 | — | Web | PAY-02.03 | Razorpay checkout for S1 subscription only; no webhook; no signature verify on server | Port Razorpay to .NET 8; keys in config; POST /api/Payments/Webhook/Razorpay anonymous + signature verify; PaymentOrder table | Kill browser after pay → webhook still marks PAID; client callback alone never marks PAID | Not Started | QA
92 | 322 | QA | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.3 | PAY-03 | Online consultation payment — patient pays by card, UPI, netbanking or wallet | PAY-03.05 | QA: success, failure, pending, double-click create order idempotent | Regression | Payments | §9 + §4 + §2.3 | Online consultation payment | Patient pays by card, UPI, netbanking or wallet / Pay the consultation fee at the time of booking / Pay the consultation fee inside the app | Public web + later Patient app | QA | Yes | Yes | No | Yes | No | No | P0 | S | PAY-03.04 | — | Web, UI | PAY-03.04 | Does not exist (only S1 SaaS) | CreateConsultOrder attached to PatientAppId; Razorpay Checkout; webhook sets PAID; do not overload PackageEntryDetail | Paid appointment unlocks tele queue rules; doctor sees PAID; Account sees ledger row (Phase 7) | Not Started | QA
93 | 327 | QA | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.4 | PAY-04 | Reception payment collection — cash, UPI, card or payment link with printed receipt | PAY-04.05 | QA: cash collection visible in clinic collection view after Phase 7; cannot mark PAID without this API | Regression | Payments | §9 + §6 | Reception payment collection | Cash, UPI, card or payment link with printed receipt | Reception Portal | QA | Yes | Yes | No | Yes | No | No | P0 | S | PAY-04.04 | — | Web, UI | PAY-04.04 | Does not exist | CollectAtReception writes ledger S3; print receipt; payment-link uses same Razorpay order as online | Cash still creates an immutable ledger row; receipt printable; status matches doctor list | Not Started | QA
94 | 330 | QA | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.5 | PAY-05 | Pay-at-clinic option — book now, pay at the clinic where the doctor allows it | PAY-05.03 | QA: doctor flag off → pay-at-clinic hidden; reception can still collect | Regression | Payments | §9 | Pay-at-clinic option | Book now, pay at the clinic where the doctor allows it | Public + Doctor + Reception | QA | Yes | Yes | No | No | No | No | P1 | S | PAY-05.02 | — | Web, UI | PAY-05.02 | Does not exist | PayAtClinicEnabled on fee config; appointment PaymentStatus=PAY_AT_CLINIC; tele queue may still require PAID (policy) | If doctor disables pay-at-clinic, public checkout requires online pay | Not Started | QA
95 | 333 | QA | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.6 | PAY-06 | Doctor subscription payment — buy and renew subscription packages (complete remaining ~30%) | PAY-06.03 | QA: renew, fail, webhook delay, last-5-days warning still works | Regression | Payments | §9 | Doctor subscription payment | Buy and renew subscription packages | Doctor Web Portal | QA | Yes | Yes | No | No | No | No | P1 | S | PAY-06.02 | — | Web, UI | PAY-06.02 | Checkout works ~70%; no webhook, refund, invoice, GST, Account ledger | Same webhook spine; write S1 ledger; invoice; failed pay UX; PackageEntryDetail shape UNCHANGED | SaaS pay verified by webhook; doctor plan flags update without trusting client callback alone | Not Started | QA
96 | 336 | QA | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.7 | PAY-07 | Medicine payment — pay online or cash on delivery (API contract now; HomeoMeds Phase 14 implements orders) | PAY-07.03 | QA: stream isolation query (consult vs medicine totals differ) | Regression | Payments | §9 + §12 | Medicine payment | Pay online or choose cash on delivery / Both options supported, with status tracking | Shared | QA | No | Yes | No | No | No | No | P2 | S | PAY-07.02 | — | Web | PAY-07.02 | Does not exist | PaymentOrder.Stream=MEDICINE; COD_PENDING until pharmacy confirms collection; do not mix with consult money | A medicine PaymentOrder cannot be summarised as consult GMV | Not Started | QA
97 | 339 | QA | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.8 | PAY-08 | Payment status everywhere — doctor, reception and patient all see the same payment status | PAY-08.03 | QA: three roles, one appointment, same enum value | Regression | Payments | §9 | Payment status everywhere | Doctor, reception and patient all see the same payment status | All | QA | Yes | Yes | No | No | No | No | P0 | S | PAY-08.02 | — | Web, UI | PAY-08.02 | No shared status | Single PaymentStatus on appointment/order; all DTOs read it; never a second client-only flag | Doctor list, reception queue, public booking confirmation, later patient app show identical status for the same id | Not Started | QA
98 | 344 | QA | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.9 | PAY-09 | Refunds — processed and tracked against the original payment | PAY-09.05 | QA: double refund blocked; cash collection refund is ledger-only per PRE-02 policy | Regression | Payments | §9 + §8 + §2.8 | Refunds | Processed and tracked against the original payment / Issue and track refunds | Account + Patient | QA | Yes | Yes | No | Yes | No | No | P0 | S | PAY-09.04 | — | Web, UI | PAY-09.04 | Does not exist | Refund entity against original PaymentOrder; Razorpay refund API; cancel-appointment hook; patient sees status | Refund cannot exceed captured amount; original payment remains visible; appointment status REFUNDED/partial as designed | Not Started | QA
99 | 348 | QA | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.10 | PAY-10 | Payment receipts & invoices — issued for every transaction | PAY-10.04 | QA: unique invoice numbers; cancelled invoice not reused | Regression | Payments | §9 + §8 | Payment receipts & invoices | Issued for every transaction / Invoice numbering and tax reporting | All | QA | Yes | Yes | No | Yes | No | No | P1 | S | PAY-10.03 | — | Web, UI | PAY-10.03 | No invoice entity | Invoice numbering series from PRE-02; PDF receipt; GST fields; email in Phase 12 | Every PAID consult/subscription/medicine has a retrievable receipt number | Not Started | QA
100 | 351 | QA | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.11 | PAY-11 | Complete payment audit trail — every transaction traceable end to end by Homeocentrum | PAY-11.03 | QA: missing webhook still shows PENDING not PAID | Regression | Payments | §9 + §17 | Complete audit trail | Every transaction traceable end to end by Homeocentrum | Account | QA | No | Yes | No | No | No | No | P0 | S | PAY-11.02 | — | Web | PAY-11.02 | No webhook store | PaymentEvent raw payloads + AuditEvent + OtpAudit for payouts; Account can reconstruct without Razorpay dashboard | Given a PatientAppId, Account retrieves order, events, invoice, refunds | Not Started | QA
101 | 355 | QA | 7 | Phase 7 — Account & finance department (PDF §8) | 7.1 | FIN-01 | Unified transaction ledger — every rupee that moves through the platform, in one record | FIN-01.04 | QA: consult pay writes S2; subscription writes S1; they never share one row | Regression | Account | §8 | Unified transaction ledger | Every rupee that moves through the platform, in one record | Account Portal | QA | Yes | Yes | No | Yes | No | No | P0 | S | FIN-01.03 | — | Web, UI | FIN-01.03 | Does not exist | Append-only LedgerEntry for S1–S7; filters; OTP audit link; Admin may view, Account owns movement | No money movement without a ledger row; rows are immutable | Not Started | QA
102 | 359 | QA | 7 | Phase 7 — Account & finance department (PDF §8) | 7.2 | FIN-02 | Consultation payment reconciliation — online payments and reception collections matched and verified | FIN-02.04 | QA: unmatched payment appears in exception queue not silent | Regression | Account | §8 + §7.2 + §16 | Consultation payment reconciliation | Online payments and reception collections matched and verified / Match every booking against every payment | Account + Admin | QA | Yes | Yes | No | Yes | No | No | P0 | S | FIN-02.03 | — | Web, UI | FIN-02.03 | Does not exist | Join booking ↔ payment ↔ appointment; KPI collected/pending/failed/refunded; CSV | Every paid booking has exactly one captured consult payment or an exception | Not Started | QA
103 | 363 | QA | 7 | Phase 7 — Account & finance department (PDF §8) | 7.3 | FIN-03 | Medicine ledger — medicine money tracked separately from consultation money | FIN-03.04 | QA: S2 consult row never appears on this screen | Regression | Account | §8 + §12 | Medicine ledger | Medicine money tracked separately from consultation money / Seller, platform and delivery shares recorded separately from consultation money | Account Portal | QA | Yes | Yes | No | Yes | No | No | P1 | S | FIN-03.03 | — | Web, UI | FIN-03.03 | Does not exist | /account/medicine-ledger; Stream=MEDICINE; seller/platform/delivery split columns; filled in Phase 14 | Medicine GMV query cannot include consult fees | Not Started | QA
104 | 367 | QA | 7 | Phase 7 — Account & finance department (PDF §8) | 7.4 | FIN-04 | Settlement runs — scheduled settlement of amounts due to doctors and pharmacies | FIN-04.04 | QA: hold days exclude too-new captures; refunds net out | Regression | Account | §8 + §16 | Settlement runs | Scheduled settlement of amounts due to doctors and pharmacies | Account Portal | QA | Yes | Yes | No | Yes | No | No | P0 | S | FIN-04.03 | — | Web, UI | FIN-04.03 | Does not exist | SettlementRun job T+N hold; net of commission/GST/refunds; pharmacies after Phase 14 | A settlement run is replayable and lists included transactions | Not Started | QA
105 | 372 | QA | 7 | Phase 7 — Account & finance department (PDF §8) | 7.5 | FIN-05 | Payout approval — payouts released only after OTP-verified approval | FIN-05.05 | QA: Account role only; replay OTP; Admin 403 on approve | Regression | Account | §8 + §17 | Payout approval | Payouts released only after OTP-verified approval | Account Portal | QA | Yes | Yes | No | Yes | No | No | P0 | S | FIN-05.04 | — | Web, UI | FIN-05.04 | Does not exist | ApprovePayout requires SEC-07 OTP; Admin cannot approve; NEFT/file or gateway per PRE-01 | Payout without OTP fails; audit shows who approved | Not Started | QA
106 | 375 | QA | 7 | Phase 7 — Account & finance department (PDF §8) | 7.6 | FIN-06 | Refund processing — Account issues and tracks refunds (uses PAY-09) | FIN-06.03 | QA: partial refund; full refund; cash-policy path | Regression | Account | §8 | Refund processing | Issue and track refunds | Account Portal | QA | Yes | Yes | No | No | No | No | P0 | S | FIN-06.02 | — | Web, UI | FIN-06.02 | Does not exist | /account/refunds UI on PAY-09 APIs; OTP if policy requires | Account can issue refund; patient status updates; ledger reverses | Not Started | QA
107 | 379 | QA | 7 | Phase 7 — Account & finance department (PDF §8) | 7.7 | FIN-07 | Payment exception handling — investigate and resolve every failed or disputed payment | FIN-07.04 | QA: failed webhook creates exception; manual resolve requires Account role + OTP | Regression | Account | §8 + §7.2 | Payment exception handling | Investigate and resolve every failed or disputed payment / Every failed or mismatched payment surfaced for action | Account + Admin | QA | Yes | Yes | No | Yes | No | No | P0 | S | FIN-07.03 | — | Web, UI | FIN-07.03 | Does not exist | Exception queue Failed/Partial/Webhook-mismatch/Refund-pending; retry/resolve with OTP on manual reconcile | Nothing failed is silent; resolve writes audit | Not Started | QA
108 | 383 | QA | 7 | Phase 7 — Account & finance department (PDF §8) | 7.8 | FIN-08 | GST & invoice reports — invoice numbering and tax reporting | FIN-08.04 | QA: rates come from config; changing rate does not rewrite old invoices | Regression | Account | §8 + §16 | GST & invoice reports | Invoice numbering and tax reporting | Account Portal | QA | Yes | Yes | No | Yes | No | No | P1 | S | FIN-08.03 | — | Web, UI | FIN-08.03 | Does not exist | /account/tax export using Invoice table and PRE-02 GST treatment — configuration not hardcoded | Date-range GST report matches invoices issued | Not Started | QA
109 | 387 | QA | 7 | Phase 7 — Account & finance department (PDF §8) | 7.9 | FIN-09 | Payee records — bank and KYC details for doctors and pharmacies | FIN-09.04 | QA: missing KYC blocks FIN-05 | Regression | Account | §8 | Payee records | Bank and KYC details for doctors and pharmacies | Account Portal | QA | Yes | Yes | No | Yes | No | No | P1 | S | FIN-09.03 | — | Web, UI | FIN-09.03 | Doctor bank fields added in DOC-10; no Account UI; no pharmacy | /account/payees; OTP on doctor KYC change (fraud); pharmacies after Phase 14 | Payout cannot run to a payee missing KYC | Not Started | QA
110 | 391 | QA | 7 | Phase 7 — Account & finance department (PDF §8) | 7.10 | FIN-10 | Clinic collection view — cash and UPI collected at reception, per clinic and per day | FIN-10.04 | QA: online Razorpay consults do not appear as clinic cash | Regression | Account | §8 | Clinic collection view | Cash and UPI collected at reception, per clinic and per day | Account Portal | QA | Yes | Yes | No | Yes | No | No | P1 | S | FIN-10.03 | — | Web, UI | FIN-10.03 | Does not exist | /account/clinic-collections from CollectAtReception rows; respect PRE-02 retain vs remit | Per clinic per day cash/UPI totals match reception receipts | Not Started | QA
111 | 393 | QA | 7 | Phase 7 — Account & finance department (PDF §8) | 7.11 | FIN-11 | Separation of duties — Account controls money; Admin controls platform and clinical data | FIN-11.02 | Negative tests: Admin POST ApprovePayout → 403; Account POST repertory section → 403 | Regression | Account | §8 | Separation of duties | The Account department controls money. Admin controls the platform and clinical data. Neither can perform the other’s role, which protects both. | Admin + Account | QA | No | Yes | No | Yes | No | No | P0 | S | FIN-11.01 | — | Web | FIN-11.01 | Account role does not exist | Enforce in RBAC: Admin cannot ApprovePayout; Account cannot edit repertory/users’ clinical masters | Automated tests for both forbidden directions | Not Started | QA
112 | 397 | QA | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.1 | TRU-01 | Doctor credentialing — doctors upload qualification and registration documents for review | TRU-01.04 | QA: doctor without docs cannot appear in public directory (Phase 9) | Regression | Trust | §13 + §7.2 | Doctor credentialing | Doctors upload qualification and registration documents for review | Doctor Web + Admin | QA | Yes | Yes | No | Yes | No | No | P0 | S | TRU-01.03 | — | Web, UI | TRU-01.03 | RegisterDoctor activates immediately; PassingUniversity/CertNo/QualificationId exist; no document store/queue | DoctorCredentialDocument + VerificationStatus Pending; do not auto-activate practice for public directory | New registrations sit in Pending with documents; existing doctors backfill per PRE-03 | Not Started | QA
113 | 402 | QA | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.2 | TRU-02 | Verification review — Admin approves, rejects or requests further information | TRU-02.05 | QA: reject reason required; request-info reopens Pending | Regression | Trust | §13 + §7.2 | Verification review | Admin approves, rejects or requests more information before they can practise on the platform | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P0 | S | TRU-02.04 | — | Web, UI | TRU-02.04 | Does not exist | /admin/doctor-credentialing list + detail; email notify doctor | Approve/reject/request-info all audited; doctor sees status | Not Started | QA
114 | 405 | QA | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.3 | TRU-03 | Verified badge — patients see which doctors have been verified | TRU-03.03 | QA: pending doctor has no badge | Regression | Trust | §13 + §2.2 | Verified badge / Credentials & verification | Patients see which doctors have been verified / Verified badge showing the doctor’s credentials are checked | Public + Patient app | QA | Yes | No | No | No | No | No | P0 | S | TRU-03.02 | — | Web, UI | TRU-03.02 | Does not exist | Badge on public doctor card and profile from VerificationStatus=Approved | Unverified doctors never show a verified badge | Not Started | QA
115 | 408 | QA | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.4 | TRU-04 | Practice gate — only verified doctors appear to patients and take paid consultations | TRU-04.03 | QA: reception can still book own clinic patient for unverified doctor if PRE-03 allows | Regression | Trust | §13 | Practice gate | Only verified doctors appear to patients and take paid consultations | Public + Payments | QA | No | Yes | No | No | No | No | P0 | S | TRU-04.02 | — | Web | TRU-04.02 | Any activated doctor could theoretically be listed; no public list yet | Public search and CreateConsultOrder require Approved; own-clinic staff booking may still work per PRE-03 | Unverified doctor absent from /book; paid public consult blocked | Not Started | QA
116 | 412 | QA | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.5 | TRU-05 | Patient reviews — patients rate and review consultations | TRU-05.04 | QA: duplicate review blocked; incomplete visit blocked | Regression | Trust | §13 + §2.8 | Patient reviews / Write a review | Patients rate and review consultations / Rate and review the consultation | Patient + Public | QA | Yes | Yes | No | Yes | No | No | P1 | S | TRU-05.03 | — | Web, UI | TRU-05.03 | Does not exist | Review linked to PatientAppId; one review per visit; moderation flag optional | Review only after completed consult; doctor cannot write self-reviews | Not Started | QA
117 | 416 | QA | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.6 | TRU-06 | Review appeal — doctors can appeal a review; patients manage reviews and raise an appeal | TRU-06.04 | QA: only treating doctor of that visit can appeal | Regression | Trust | §13 + §2.8 | Review appeal / My reviews & appeal | Doctors can appeal a review / Manage reviews and raise an appeal | Doctor + Patient + Admin | QA | Yes | Yes | No | Yes | No | No | P2 | S | TRU-06.03 | — | Web, UI | TRU-06.03 | Does not exist | Appeal entity; admin resolves; patient my-reviews list | Appealed review hidden or marked pending per policy; admin decision audited | Not Started | QA
118 | 420 | QA | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.7 | TRU-07 | Ranking transparency — patients are shown why doctors are ranked as they are | TRU-07.04 | QA: changing weights changes order and explanation together | Regression | Trust | §13 + §2.2 | Ranking transparency / Ranking explanation | Patients are shown why doctors are ranked as they are / Transparent explanation of why doctors appear in a given order | Public + Patient app | QA | Yes | Yes | No | Yes | No | No | P1 | S | TRU-07.03 | — | Web, UI | TRU-07.03 | Does not exist | Documented ranking factors (verified, availability, fee, reviews, experience) + explain API/UI | Each search result has an explain link that matches the sort order | Not Started | QA
119 | 424 | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.1 | WEB-01 | Product home page — complete public website presenting the service | WEB-01.04 | QA: mobile viewport; deep link /book | Regression | Patient Website | §4 | Product home page | Complete public website presenting the service | Patient Website | QA | Yes | Yes | No | Yes | No | No | P1 | S | WEB-01.03 | — | Web, UI | WEB-01.03 | HomeoJobLanding ~50%; Velzon leftovers; CTAs incomplete for book/trust/apps | Book CTA, verified doctors, consult+SaaS pricing teaser, app download placeholders | Unauthenticated user can go Home → Book without calling the clinic | Not Started | QA
120 | 427 | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.2 | WEB-02 | Consultation & subscription pricing — transparent pricing display | WEB-02.03 | QA: fee matches checkout amount | Regression | Patient Website | §4 | Consultation & subscription pricing | Transparent pricing display | Patient Website | QA | Yes | No | No | No | No | No | P1 | S | WEB-02.02 | — | UI | WEB-02.02 | SaaS package marketing /pricing exists; no consult fee display per doctor | Keep SaaS pricing; add consult fee on doctor cards from ConsultFeeConfig | Patient sees consult fee before booking; doctor SaaS pricing still shown for doctors buying plans | Not Started | QA
121 | 431 | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.3 | WEB-03 | Doctor discovery — browse and search verified doctors | WEB-03.04 | QA: unverified excluded; filters combine; empty state | Regression | Patient Website | §4 + §2.2 | Doctor discovery | Browse and search verified doctors | Patient Website | QA | Yes | Yes | No | Yes | No | No | P0 | S | WEB-03.03 | — | Web, UI | WEB-03.03 | Does not exist as a patient product (marketing only) | /book search: name, condition, category; filters availability, fee, experience, language, location | Only verified doctors; ranking explanation available (TRU-07) | Not Started | QA
122 | 435 | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.4 | WEB-04 | Self-service booking — book an appointment online without calling the clinic | WEB-04.04 | QA: double-book same slot; hold expiry; OTP fail; consent required | Regression | Patient Website | §4 + §2.3 | Self-service booking | Book an appointment online without calling the clinic | Patient Website | QA | Yes | Yes | No | Yes | No | No | P0 | S | WEB-04.03 | — | Web, UI | WEB-04.03 | Staff-only appointments | Funnel /book/:id/slots → review+consent → create Patient+Appointment; OTP; rate-limit; respect schedule + unpaid hold policy PRE-03 | Slot no longer free after confirmed booking; consent written to ConsentRecord | Not Started | QA
123 | 437 | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.5 | WEB-05 | Online consultation payment on website — pay the fee at the time of booking | WEB-05.02 | QA: pay-at-clinic skip checkout; failed pay remains PENDING not PAID | Regression | Patient Website | §4 + §9 | Online consultation payment | Pay the consultation fee at the time of booking | Patient Website | QA | Yes | Yes | No | No | No | No | P0 | S | WEB-05.01 | — | UI | WEB-05.01 | Does not exist | Checkout uses PAY-03; success/fail pages; pay-at-clinic branch from PAY-05 | Closing the tab does not lose a captured payment (PAY-02) | Not Started | QA
124 | 441 | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.6 | WEB-06 | Contact & enquiry form — enquiries reach the admin team and are tracked | WEB-06.04 | QA: guest submit → admin sees row | Regression | Patient Website | §4 + §15 | Contact & enquiry form | Enquiries reach the admin team and are tracked | Patient Website + Admin | QA | Yes | Yes | No | Yes | No | No | P1 | S | WEB-06.03 | — | Web, UI | WEB-06.03 | EnquiryDetail API exists; public form partial; admin inbox screen missing | Confirmation + enquiry id; /admin/enquiries inbox; optional convert to SupportTicket | Every website enquiry is visible to admin with status | Not Started | QA
125 | 443 | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.7 | WEB-07 | Privacy policy — covering data protection, recording and pharmacy consent | WEB-07.02 | QA: booking consent shows policy version number | Regression | Legal | §4 + §17 | Privacy policy | Covering data protection, recording and pharmacy consent | Patient Website | QA | Yes | No | No | No | No | No | P0 | S | WEB-07.01 | — | UI | WEB-07.01 | Privacy page partial; not DPDP/tele/pharmacy complete | Publish PRE-03 legal copy: DPDP, recording, pharmacy, data-rights, family/caregiver | Versioned policy; booking consent references this version | Not Started | QA
126 | 445 | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.8 | WEB-08 | Terms of service — covering payments, refunds, telemedicine and medicine orders | WEB-08.02 | QA: terms checkbox required on confirm | Regression | Legal | §4 | Terms of service | Covering payments, refunds, telemedicine and medicine orders | Patient Website | QA | Yes | No | No | No | No | No | P0 | S | WEB-08.01 | — | UI | WEB-08.01 | Terms partial | Payments, refunds, telemedicine, HomeoMeds, codes-before-names | Checkout cannot complete without accepted terms version | Not Started | QA
127 | 449 | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.9 | WEB-09 | Doctor self-registration — doctors apply to join the platform online | WEB-09.04 | QA: register → admin queue row | Regression | Patient Website | §4 | Doctor self-registration | Doctors apply to join the platform online | Public | QA | Yes | Yes | No | Yes | No | No | P0 | S | WEB-09.03 | — | Web, UI | WEB-09.03 | RegisterDoctor ~90%; activates immediately; no document upload | Document upload; pending-verification message; TRU-01 status Pending | New doctor cannot take paid public consults until Approved | Not Started | QA
128 | 453 | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.10 | WEB-10 | Email activation — secure account activation by email link | WEB-10.04 | QA: used link, expired link, resend | Regression | Auth | §4 | Email activation | Secure account activation by email link | Public | QA | Yes | Yes | No | Yes | No | No | P1 | S | WEB-10.03 | — | Web, UI | WEB-10.03 | ActivateUser via /login?UserId= ~90%; align with verification; expiry/resend incomplete | Token expiry, resend, align with credentialing (activation ≠ verified practice) | Expired link fails; resend works; activated unverified still not in directory | Not Started | QA
129 | 458 | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.11 | WEB-11 | Waitlist offer — get offered a slot when one is freed by a cancellation (patient website + later app) | WEB-11.05 | QA: two waiters; first gets offer; expiry releases to second | Regression | Booking | §2.3 | Waitlist offer | Get offered a slot when one is freed by a cancellation | Patient Website + App | QA | Yes | Yes | No | Yes | No | No | P2 | S | WEB-11.04 | — | Web, UI | WEB-11.04 | Cancel hook stub in Phase 4; no waitlist records | BookingWaitlist; on cancel, offer FIFO; timeout | Cancelled slot offered to waitlisted patient before returning to open search | Not Started | QA
130 | 460 | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.12 | WEB-12 | Health articles — educational content to build trust and engagement | WEB-12.02 | QA: unpublished hidden | Regression | Patient Website | §2.2 | Health articles | Educational content to build trust and engagement | Patient Website + App | QA | Yes | No | No | No | No | No | P2 | S | WEB-12.01 | — | UI | WEB-12.01 | Blog/news APIs on classic exist for marketing | Reuse blog/news as health articles on public site and later patient app; admin already has news/blog | Published articles appear on public site; draft does not | Not Started | QA
131 | 464 | QA | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.1 | ERX-01 | Potency module — every remedy carries a defined potency from a managed list, no free text | ERX-01.04 | QA: free text potency rejected | Regression | eRx | §11 | Potency module | Every remedy carries a defined potency, selected from a managed list — no free text | Doctor Web + Admin | QA | Yes | Yes | No | Yes | No | No | P0 | S | ERX-01.03 | — | Web, UI | ERX-01.03 | Dose saved as empty free-text dose: '' | PotencyMaster CRUD; PotencyId on PrescriptionRemedyDetail; stop empty Dose | Cannot sign eRx with missing potency | Not Started | QA
132 | 468 | QA | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.2 | ERX-02 | Dosage details — frequency, duration and instructions recorded clearly | ERX-02.04 | QA: all three persist and print | Regression | eRx | §11 | Dosage details | Frequency, duration and instructions recorded clearly | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P0 | S | ERX-02.03 | — | Web, UI | ERX-02.03 | Unstructured/empty dose | Frequency, Duration, Instructions fields on each remedy line | Print/PDF shows frequency, duration, instructions | Not Started | QA
133 | 472 | QA | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.3 | ERX-03 | Visit notes kept separate from the prescription — private clinical notes never appear on the prescription given to the patient or pharmacy | ERX-03.04 | QA: print eRx vs export case PDF (doctor copy still has notes) | Regression | eRx | §11 + §5.3 | Visit notes kept separate from the prescription | The doctor’s private clinical notes never appear on the prescription given to the patient or pharmacy | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P0 | S | ERX-03.03 | — | Web, UI | ERX-03.03 | History notes mixed into Rx modal tabs | Visit Notes panel outside Rx; NoteType; IsErxExcluded; eRx print has remedies+labs only | Patient PDF and pharmacy payload contain zero private note text | Not Started | QA
134 | 476 | QA | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.4 | ERX-04 | Signed digital prescription — issued and locked once signed, so it cannot be altered afterwards | ERX-04.04 | QA: POST save after sign does not change snapshot | Regression | eRx | §11 + §2.5 + §5.3 | Signed digital prescription | Issued and locked once signed, so it cannot be altered afterwards / Official prescription issued by the doctor | Doctor Web | QA | Yes | Yes | No | Yes | No | No | P0 | S | ERX-04.03 | — | Web, UI | ERX-04.03 | SavePrescriptionDetail overwritable; no lock/sign | ErxSnapshot immutable on sign; subsequent edits create a new unsigned draft not a silent mutate | Signed snapshot hash stable; UI cannot edit locked lines | Not Started | QA
135 | 479 | QA | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.5 | ERX-05 | Prescription history — every prescription stored against the patient and visit | ERX-05.03 | QA: another doctor 403 | Regression | eRx | §11 | Prescription history | Every prescription stored against the patient and visit | Doctor + Patient | QA | No | Yes | No | No | No | No | P1 | S | ERX-05.02 | — | Web, UI | ERX-05.02 | Rx saved per appointment but no signed history product | List snapshots by PatientId; open past visit eRx | All signed eRx retrievable by patient and treating doctor | Not Started | QA
136 | 482 | QA | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.6 | ERX-06 | Patient view of prescription in app — patient sees the prescription immediately (codes until pharmacy accept) | ERX-06.03 | QA: doctor names vs patient codes differ until pharmacy OTP accept | Regression | eRx | §11 + §2.5 | Patient view in app | Patient sees the prescription immediately in the app | Patient App + Website | QA | No | Yes | No | No | No | No | P0 | S | ERX-06.02 | — | Web, UI | ERX-06.02 | No patient surface | Patient GET eRx by appointment; names redacted until Phase 14 accept; website optional view | Immediately after sign, patient API returns codes (or names if no HomeoMeds order required for in-clinic dispense policy — document) | Not Started | QA
137 | 485 | QA | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.7 | ERX-07 | Print & PDF — printable and downloadable prescription | ERX-07.03 | QA: notes leak test on patient PDF | Regression | eRx | §11 | Print & PDF | Printable and downloadable prescription | Doctor + Patient | QA | No | Yes | No | No | No | No | P1 | S | ERX-07.02 | — | Web, UI | ERX-07.02 | No eRx PDF | Patient copy without notes; doctor copy may include letterhead; SecureDocument store | PDF matches signed snapshot; notes absent on patient copy | Not Started | QA
138 | 487 | QA | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.8 | ERX-08 | Remedy code protection — patient sees remedy codes rather than names until a licensed pharmacy accepts the order | ERX-08.02 | Patient serializer tests (contract tests) | Regression | eRx | §11 | Remedy code protection | The patient sees remedy codes rather than remedy names until a licensed pharmacy accepts the order | Patient | QA | No | Yes | No | No | No | No | P0 | S | ERX-08.01 | — | Web | ERX-08.01 | Does not exist | Code map on snapshot items; patient serializer strips names; doctor always sees names | Patient JSON has no remedy name fields until PharmacyAccepted | Not Started | QA
139 | 493 | QA | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.10 | ERX-10 | Repeat prescription / refill — patient requests; doctor approves or rejects from the mobile app (inbox on web too) | ERX-10.04 | QA: cannot refill unsigned/locked-expired per policy | Regression | eRx | §11 + §3 + §2.7 | Repeat prescription / refill | Patient requests a refill; doctor approves or rejects from the mobile app | Patient + Doctor mobile + Doctor web | QA | Yes | Yes | No | Yes | No | No | P1 | S | ERX-10.03 | — | Web, UI | ERX-10.03 | Does not exist | RefillRequest against ErxSnapshot; doctor inbox; no case-taking on mobile | Reject/approve audited; approved refill creates a new order draft not an editable old snapshot | Not Started | QA
140 | 495 | QA | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.11 | ERX-11 | Lab orders alongside the prescription (keep existing labs on eRx snapshot) | ERX-11.02 | QA: labs visible on eRx; result values not required on patient copy | Regression | eRx | §11 | Lab orders | Tests ordered alongside the prescription | Doctor Web | QA | No | Yes | No | No | No | No | P1 | S | ERX-11.01 | — | Web | ERX-11.01 | Labs on Rx modal live | Include lab orders in signed snapshot; still not on private notes | Signed eRx PDF lists labs; results stay clinical-side | Not Started | QA
141 | 499 | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.1 | TEL-01 | Doctor availability — online or offline status and working hours | TEL-01.04 | QA: heartbeat expiry sets offline | Regression | Telemedicine | §10 + §3 | Doctor availability | Doctor sets online or offline status and working hours | Doctor Web + Doctor App | QA | Yes | Yes | No | Yes | No | No | P0 | S | TEL-01.03 | — | Web, UI | TEL-01.03 | E-CONSULT status + WhatsApp video stub only; no availability | TeleAvailability + heartbeat; working hours reuse daily schedule | Offline doctor cannot be offered instant consult | Not Started | QA
142 | 504 | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.2 | TEL-02 | Telemedicine waiting queue — who is waiting, how long, whether they have paid | TEL-02.05 | QA: wait time increases; paid badge matches PAY-08 | Regression | Telemedicine | §10 + §3 | Telemedicine waiting queue | Doctor sees who is waiting, for how long, and whether they have paid | Doctor Web + App | QA | Yes | Yes | No | Yes | No | No | P0 | S | TEL-02.04 | — | Web, UI | TEL-02.04 | E-CONSULT list only | Queue by doctor + Online + paid/confirmed; wait time; Join | Unpaid patients do not join if policy requires PAID | Not Started | QA
143 | 509 | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.3 | TEL-03 | Video consultation in browser — doctor consults directly from the web portal | TEL-03.05 | QA: replace WhatsApp alert; session ends write timestamp | Regression | Telemedicine | §10 | Video consultation in browser | Doctor consults directly from the web portal | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P0 | S | TEL-03.04 | — | Web, UI | TEL-03.04 | SweetAlert WhatsApp stub | /teleconsult/:sessionId in-browser video; replace stub; vendor from PRE-03 | Doctor and patient in same room linked to PatientAppId | Not Started | QA
144 | 511 | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.4 | TEL-04 | Video consultation on mobile — doctor and patient both consult from the app (apps in 16–17; same session tokens) | TEL-04.02 | Contract tests: token TTL, room id = session id | Regression | Telemedicine | §10 + §2.4 + §3 | Video consultation on mobile | Doctor and patient both consult from the app / Face-to-face consultation from home / Start the video or audio consultation from the phone | Patient App + Doctor App | QA | No | Yes | No | No | No | No | P0 | S | TEL-04.01 | — | Web | TEL-04.01 | No apps | Same TeleSession tokens; mobile join implemented in Phases 16–17 against this API | Web doctor + mobile patient in one session | Not Started | QA
145 | 513 | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.5 | TEL-05 | Device check — camera, microphone and connection tested before joining | TEL-05.02 | QA: deny camera permission → clear guidance | Regression | Telemedicine | §10 + §2.4 | Device check | Camera, microphone and connection tested before joining | Doctor Web + Patient | QA | Yes | No | No | No | No | No | P1 | S | TEL-05.01 | — | UI | TEL-05.01 | Does not exist | Pre-join device/network check UI; block join on hard fail with guidance | User sees camera/mic/network result before entering the room | Not Started | QA
146 | 517 | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.6 | TEL-06 | Waiting room — patient waits with live status until the doctor joins | TEL-06.04 | QA: doctor join transitions patient into the call | Regression | Telemedicine | §10 + §2.4 | Waiting room | Patient waits with live status / Wait with live status until the doctor joins | Patient | QA | Yes | Yes | No | Yes | No | No | P1 | S | TEL-06.03 | — | Web, UI | TEL-06.03 | Does not exist | Waiting room page: position, doctor online, paid, estimated wait | Status updates without refresh (poll/SignalR) | Not Started | QA
147 | 521 | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.7 | TEL-07 | Recording consent — consent captured before the consultation; no recording without it | TEL-07.04 | QA: decline → no record; audit row still written | Regression | Telemedicine | §10 + §2.4 + §17 | Recording consent | Consent captured before the consultation; no recording without it / Explicit consent requested before any recording | Patient + Doctor | QA | Yes | Yes | No | Yes | No | No | P0 | S | TEL-07.03 | — | Web, UI | TEL-07.03 | AudioCaseConsentLog only for audio case taking | ConsentRecord type TeleRecording; block record if declined; both sides see status | Recording pipeline cannot start if consent denied | Not Started | QA
148 | 524 | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.8 | TEL-08 | Rejoin after dropped call — either side can rejoin the same consultation | TEL-08.03 | QA: after End, rejoin 409 | Regression | Telemedicine | §10 + §2.4 | Rejoin after dropped call | Either side can rejoin the same consultation / Rejoin the same consultation if the connection drops | Doctor + Patient | QA | No | Yes | No | No | No | No | P0 | S | TEL-08.02 | — | Web, UI | TEL-08.02 | Does not exist | Session Active until End; rejoin tokens; dashboard Rejoin | Drop and rejoin same PatientAppId session; End prevents rejoin | Not Started | QA
149 | 527 | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.9 | TEL-09 | Join failure handling — clear fallback if the call cannot connect, with options to retry | TEL-09.03 | QA: simulated token fail | Regression | Telemedicine | §10 + §2.4 | Join failure handling / Fallback & join failure handling | Clear fallback if the call cannot connect / Clear guidance if the call fails, with options to retry | Doctor + Patient | QA | Yes | No | No | No | No | No | P1 | S | TEL-09.02 | — | Web, UI | TEL-09.02 | Does not exist | Error codes; retry; support ticket deep link later; do not silently fail | Every join failure has a user-visible next action | Not Started | QA
150 | 531 | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.10 | TEL-10 | Case-linked chat — chat attached to the consultation record, not a loose message thread | TEL-10.04 | QA: IDOR other session 403 | Regression | Telemedicine | §10 + §2.4 | Case-linked chat | Chat attached to the consultation record / Chat tied to the consultation, not a loose message thread | Doctor + Patient | QA | Yes | Yes | No | Yes | No | No | P1 | S | TEL-10.03 | — | Web, UI | TEL-10.03 | Does not exist | Messages keyed by TeleSession/PatientAppId; retained with the case | Chat not visible on a different appointment | Not Started | QA
151 | 535 | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.11 | TEL-11 | Consultation summary — issued to the patient at the end of the call | TEL-11.04 | QA: private notes not copied into summary by default | Regression | Telemedicine | §10 + §2.4 | Consultation summary | Issued to the patient at the end of the call / Written summary available immediately after the call | Patient + Doctor | QA | Yes | Yes | No | Yes | No | No | P1 | S | TEL-11.03 | — | Web, UI | TEL-11.03 | Does not exist | Doctor submits summary (not private notes); patient sees immediately; may share eRx id | Summary available without waiting for signed eRx if doctor issues it first | Not Started | QA
152 | 539 | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.12 | TEL-12 | Instant consultation — patient requests an immediate consultation with an available doctor | TEL-12.04 | QA: no online doctor → empty state; surcharge on checkout | Regression | Telemedicine | §10 + §2.3 | Instant consultation / Instant consult request / Queue & doctor offer | Patient can request an immediate consultation with an available doctor / See position in queue and accept an offered doctor | Patient + Doctor | QA | Yes | Yes | No | Yes | No | No | P1 | S | TEL-12.03 | — | Web, UI | TEL-12.03 | Does not exist | Instant request pool; offer doctor; patient accepts; optional surcharge from fee config | Offline doctors never offered; patient can decline an offered doctor | Not Started | QA
153 | 544 | QA | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.1 | COM-01 | SMS — appointment confirmation, registration confirmation, doctor-unavailable, OTP, reschedule and cancellation | COM-01.05 | QA: OTP SMS; reschedule old→new; cancel; doctor unavailable; opt-out honored | Regression | Notifications | §14 | SMS | Appointment confirmation, registration confirmation, doctor-unavailable notice, OTP, reschedule and cancellation alerts | Shared | QA | Yes | Yes | No | Yes | No | No | P0 | S | COM-01.04 | — | Web, UI | COM-01.04 | No SMS provider; WhatsApp exists separately | SmsProvider + templates + DLT; event hooks; DND/opt-out on Patient | Each listed event can send SMS; notify failure does not roll back the business transaction | Not Started | QA
154 | 548 | QA | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.2 | COM-02 | WhatsApp — templates, offers, health tips and bulk messaging with delivery reports and opt-out (complete remaining ~50%) | COM-02.04 | QA: opt-in required; template rejected state | Regression | Notifications | §14 | WhatsApp | Templates, offers, health tips and bulk messaging to patients, with delivery reports and opt-out | Doctor Web | QA | Yes | Yes | No | Yes | No | No | P1 | S | COM-02.03 | — | Web, UI | COM-02.03 | Meta Cloud send/templates/campaigns live; bulk/opt-in/analytics incomplete | Finish bulk queue UX, template approval states, delivery reports, opt-out | Bulk campaign shows delivered/failed; opted-out patients excluded | Not Started | QA
155 | 553 | QA | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.3 | COM-03 | Push notifications — booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests | COM-03.05 | QA: doctor and patient payloads isolated; token refresh | Regression | Notifications | §14 + §2.9 + §3 | Push notifications | Booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests / Patient waiting, new booking, reschedule, cancellation, refill request, payment received | Patient App + Doctor App | QA | Yes | Yes | No | Yes | No | No | P0 | S | COM-03.04 | — | Web, UI | COM-03.04 | Does not exist | DeviceToken + FCM/APNs; event fan-out; apps register tokens in Phases 16–17 | Each listed event has a template; unregister on logout | Not Started | QA
156 | 557 | QA | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.4 | COM-04 | Email — registration, activation, password reset, invoices and receipts | COM-04.04 | QA: reset still has no plaintext password; invoice attached | Regression | Notifications | §14 | Email | Registration, activation, password reset, invoices and receipts | Shared | QA | Yes | Yes | No | Yes | No | No | P1 | S | COM-04.03 | — | Web, UI | COM-04.03 | SMTP used for activation/forgot (plaintext issue fixed in Phase 0); no invoice email | Template emails for listed events; invoice PDF attach via SEC-09 | Each listed event has an email; bounce logged | Not Started | QA
157 | 561 | QA | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.5 | COM-05 | In-app notification centre — all alerts collected in one place for patients and doctors | COM-05.04 | QA: mark read; empty state; not Velzon demo route | Regression | Notifications | §14 + §2.8 | In-app notification centre / Notifications centre | All alerts collected in one place for patients and doctors / All alerts in one place | Patient App + Doctor Web/App | QA | Yes | Yes | No | Yes | No | No | P1 | S | COM-05.03 | — | Web, UI | COM-05.03 | Does not exist (Velzon notification demo is not product) | AppNotification inbox; mark read; do not use Velzon demo notifications | Same events as push appear in-app if push is denied | Not Started | QA
158 | 565 | QA | 13 | Phase 13 — Support & help desk (PDF §15) | 13.1 | SUP-01 | Patient support tickets — patients raise issues from the app and track them | SUP-01.04 | QA: IDOR; attachment via SEC-09 | Regression | Support | §15 + §2.9 | Patient support tickets / Help centre & support tickets | Patients raise issues from the app and track them to resolution | Patient App + Admin | QA | Yes | Yes | No | Yes | No | No | P1 | S | SUP-01.03 | — | Web, UI | SUP-01.03 | Does not exist; EnquiryDetail is not tickets; Velzon tickets demo ignore | SupportTicket reporter=Patient; status track; not Enquiry, not Velzon /apps-tickets-* | Patient sees status changes; cannot see other patients’ tickets | Not Started | QA
159 | 568 | QA | 13 | Phase 13 — Support & help desk (PDF §15) | 13.2 | SUP-02 | Doctor support tickets — doctors raise issues from the portal | SUP-02.03 | QA: doctor cannot see another doctor’s tickets | Regression | Support | §15 | Doctor support tickets | Doctors raise issues from the portal | Doctor Web + Admin | QA | Yes | Yes | No | No | No | No | P1 | S | SUP-02.02 | — | Web, UI | SUP-02.02 | Does not exist | Same ticket tables; reporter=Doctor | Doctor portal has Raise issue; tracks to resolution | Not Started | QA
160 | 572 | QA | 13 | Phase 13 — Support & help desk (PDF §15) | 13.3 | SUP-03 | Admin issue queue — all issues in one queue with priority, assignment and status | SUP-03.04 | QA: not using Velzon ticket pages | Regression | Support | §15 + §7.2 | Admin issue queue / Support ticket queue | All issues in one queue with priority, assignment and status / All patient and doctor issues in one queue with assignment and resolution | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P1 | S | SUP-03.03 | — | Web, UI | SUP-03.03 | Does not exist | /admin/support-tickets; SLA timestamps; assign | Patient and doctor tickets in one queue; assignable | Not Started | QA
161 | 575 | QA | 13 | Phase 13 — Support & help desk (PDF §15) | 13.4 | SUP-04 | Ticket conversation — full message thread with attachments | SUP-04.03 | QA: attachment unauthorised download 403 | Regression | Support | §15 | Ticket conversation | Full message thread with attachments | Admin + Doctor + Patient | QA | No | Yes | No | No | No | No | P1 | S | SUP-04.02 | — | Web, UI | SUP-04.02 | Does not exist | Threaded messages + SEC-09 attachments | Both sides see the same thread order | Not Started | QA
162 | 577 | QA | 13 | Phase 13 — Support & help desk (PDF §15) | 13.5 | SUP-05 | Enquiry management — website enquiries tracked (ties WEB-06) | SUP-05.02 | QA: convert to ticket keeps original enquiry id | Regression | Support | §15 + §4 | Enquiry management | Website enquiries reach the admin team and are tracked | Admin Portal | QA | Yes | No | No | No | No | No | P1 | S | SUP-05.01 | — | UI | SUP-05.01 | API exists; inbox missing | Complete WEB-06 admin inbox if not already; convert enquiry → ticket optional | No enquiry is only in email | Not Started | QA
163 | 581 | QA | 13 | Phase 13 — Support & help desk (PDF §15) | 13.6 | SUP-06 | Help centre — self-service help content for patients | SUP-06.04 | QA: unpublished hidden | Regression | Support | §15 + §2.9 | Help centre | Self-service help content for patients | Patient Website + App | QA | Yes | Yes | No | Yes | No | No | P2 | S | SUP-06.03 | — | Web, UI | SUP-06.03 | Does not exist | CMS articles or static help; searchable | Patient can open help without raising a ticket | Not Started | QA
164 | 585 | QA | 13 | Phase 13 — Support & help desk (PDF §15) | 13.7 | SUP-07 | Assisted booking — help for patients who need support booking | SUP-07.04 | QA: consent still captured; payment still Homeocentrum | Regression | Support | §15 + §2.9 | Assisted booking | Support for patients who need help booking / Help for patients who need support booking | Support + Reception + Patient | QA | Yes | Yes | No | Yes | No | No | P2 | S | SUP-07.03 | — | Web, UI | SUP-07.03 | Does not exist | Staff (admin/support/reception) can complete public booking on behalf of a patient with audit; patient app CTA to request assistance | Assisted booking appears in audit as staff-created; patient still owns the appointment | Not Started | QA
165 | 589 | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.1 | MED-01 | Pharmacy partner onboarding — licensed premises, licence records, activation checklist | MED-01.04 | QA: checklist incomplete blocks activate | Regression | HomeoMeds | §12 + §7.2 | Pharmacy partner onboarding / Pharmacy partner management | Licensed premises registered with licence records and an activation checklist / Onboard and activate licensed pharmacies | Pharmacy + Admin | QA | Yes | Yes | No | Yes | No | No | P0 | S | MED-01.03 | — | Web, UI | MED-01.03 | Does not exist | PharmacyPartner + licences; admin activation; pharmacy console login | Unactivated pharmacy cannot receive orders | Not Started | QA
166 | 592 | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.2 | MED-02 | Licence gating — expired or suspended licences blocked automatically from receiving orders | MED-02.03 | QA: expire a licence in test → order not offered | Regression | HomeoMeds | §12 | Licence gating | Pharmacies with expired or suspended licences are blocked automatically from receiving orders | Backend | QA | No | Yes | No | No | No | No | P0 | S | MED-02.02 | — | Web, UI | MED-02.02 | Does not exist | Scheduler; routing skip; banner on pharmacy console | Expired licence receives zero new orders the next minute | Not Started | QA
167 | 596 | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.3 | MED-03 | Fulfilment consent & pharmacy selection — patient chooses the seller and consents before the prescription is shared | MED-03.04 | QA: without consent, handoff API 403 | Regression | HomeoMeds | §12 + §2.7 | Fulfilment consent & pharmacy selection | The patient chooses the seller and consents before the prescription is shared | Patient | QA | Yes | Yes | No | Yes | No | No | P0 | S | MED-03.03 | — | Web, UI | MED-03.03 | Does not exist | ConsentRecord PharmacyShare; patient picks from routed sellers; share only after consent | No pharmacy sees names until patient consents and seller is selected (codes still protected until accept+OTP) | Not Started | QA
168 | 600 | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.4 | MED-04 | Prescription handoff — signed prescription becomes the order directly — no re-entry, no transcription errors | MED-04.04 | QA: line count mismatch fails sign-off | Regression | HomeoMeds | §12 + §2.7 | Prescription handoff / Order start | The signed prescription becomes the order directly — no re-entry, no transcription errors / Start an order directly from the prescription | Patient + Pharmacy | QA | Yes | Yes | No | Yes | No | No | P0 | S | MED-04.03 | — | Web, UI | MED-04.03 | Does not exist | MedicineOrder copied from ErxSnapshot items (codes); pharmacy never types remedies | Order lines == snapshot lines; pharmacy cannot add a different remedy | Not Started | QA
169 | 604 | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.5 | MED-05 | Rule-based seller routing — licence validity, service area, working hours and capacity | MED-05.04 | QA: capacity full excluded; hours closed excluded | Regression | HomeoMeds | §12 | Rule-based seller routing | Orders routed by licence validity, service area, working hours and capacity | Backend | QA | Yes | Yes | No | Yes | No | No | P0 | S | MED-05.03 | — | Web, UI | MED-05.03 | Does not exist | SellerRoutingRule engine | Out-of-area pharmacy never listed | Not Started | QA
170 | 607 | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.6 | MED-06 | Manual stock confirmation — pharmacy confirms availability — no live inventory integration required | MED-06.03 | QA: no inventory SKU table required | Regression | HomeoMeds | §12 | Manual stock confirmation | The pharmacy confirms availability — no live inventory integration required | Pharmacy console | QA | No | Yes | No | No | No | No | P0 | S | MED-06.02 | — | Web, UI | MED-06.02 | Does not exist | Accept/reject with stock flag; do not build inventory master | Reject for out-of-stock routes to next seller or exception queue | Not Started | QA
171 | 612 | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.7 | MED-07 | Pharmacy console — accept or reject, enter price quote, mark ready and dispatched | MED-07.05 | QA: accept without OTP fails; names still hidden to patient until accept succeeds | Regression | HomeoMeds | §12 | Pharmacy console | Accept or reject orders, enter the price quote, mark ready and dispatched | Pharmacy console | QA | Yes | Yes | No | Yes | No | No | P0 | S | MED-07.04 | — | Web, UI | MED-07.04 | Does not exist | /pharmacy/orders list+detail; OTP accept (SEC-07); quote; ready; dispatched | OTP required on accept; status visible to patient | Not Started | QA
172 | 616 | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.8 | MED-08 | Quote before payment — the patient always sees the price before paying | MED-08.04 | QA: price change after quote invalidates old quote | Regression | HomeoMeds | §12 + §2.7 | Quote before payment / Pharmacy selection & quote | The patient always sees the price before paying / Choose a licensed pharmacy and see the price before paying | Patient | QA | Yes | Yes | No | Yes | No | No | P0 | S | MED-08.03 | — | Web, UI | MED-08.03 | Does not exist | MedicineQuote; patient must confirm quote; then PAY-07 | Payment API rejects if quote not accepted by patient | Not Started | QA
173 | 619 | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.9 | MED-09 | Payment or cash on delivery — both options, with status tracking | MED-09.03 | QA: COD vs prepaid ledger split | Regression | HomeoMeds | §12 + §9 | Payment or cash on delivery | Both options supported, with status tracking | Patient | QA | No | Yes | No | No | No | No | P0 | S | MED-09.02 | — | Web, UI | MED-09.02 | Stream MEDICINE stub in Phase 6 | Online pay via PAY-02; COD_PENDING until pharmacy confirms collection | COD does not mark Stream MEDICINE as captured until collection confirmed | Not Started | QA
174 | 624 | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.10 | MED-10 | Order tracking — live status for the patient at every stage | MED-10.05 | QA: dispatched without ready is invalid transition | Regression | HomeoMeds | §12 + §2.7 | Order tracking | Live status for the patient at every stage / Live status from accepted to delivered | Patient | QA | Yes | Yes | No | Yes | No | No | P1 | S | MED-10.04 | — | Web, UI | MED-10.04 | Does not exist | Status timeline events; push updates COM-03 | Every status change visible; never silent skip | Not Started | QA
175 | 626 | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.11 | MED-11 | Medicine ledger shares — seller, platform and delivery recorded (FIN-03 live fill) | MED-11.02 | QA: consult GMV unchanged by a medicine order | Regression | HomeoMeds | §12 + §8 | Medicine ledger | Seller, platform and delivery shares recorded separately from consultation money | Account | QA | No | Yes | No | No | No | No | P0 | S | MED-11.01 | — | Web | MED-11.01 | Empty medicine ledger screen from Phase 7 | On pay/COD collect, write SplitSeller/Platform/Delivery from config | Account medicine ledger shows real rows after first order | Not Started | QA
176 | 630 | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.12 | MED-12 | Order exception queue — stuck, rejected or failed orders always surfaced — never silent | MED-12.04 | QA: silent discard impossible (metric + queue) | Regression | HomeoMeds | §12 | Order exception queue | Stuck, rejected or failed orders are always surfaced to the operations team — never silent | Admin + Account | QA | Yes | Yes | No | Yes | No | No | P0 | S | MED-12.03 | — | Web, UI | MED-12.03 | Does not exist | HomeoMeds exception queue; SLA; never drop | Rejected-by-all-sellers appears in queue within worker SLA | Not Started | QA
177 | 632 | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.13 | MED-13 | OTP-based control — key actions verified by OTP so Homeocentrum can monitor and trace every transaction | MED-13.02 | QA: Account OTP audit shows pharmacy accept | Regression | HomeoMeds | §12 + §17 | OTP-based control | Key actions verified by OTP so Homeocentrum can monitor and trace every transaction | Pharmacy + Account | QA | No | Yes | No | No | No | No | P0 | S | MED-13.01 | — | Web | MED-13.01 | SEC-07 infrastructure exists | OTP on pharmacy accept (and other high-risk); OtpAudit queryable | Accept without OTP fails; audit lists the action | Not Started | QA
178 | 635 | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.14 | MED-14 | Refill orders — repeat orders raised from an existing prescription | MED-14.03 | QA: original eRx unchanged | Regression | HomeoMeds | §12 + §2.7 + §11 | Refill orders / Order detail & refill | Repeat orders raised from an existing prescription / Full order history and one-tap refill request | Patient + Doctor | QA | No | Yes | No | No | No | No | P1 | S | MED-14.02 | — | Web, UI | MED-14.02 | ERX-10 refill request exists | Approved refill creates a new MedicineOrder from the same snapshot; one-tap patient | Refill does not mutate the original signed snapshot | Not Started | QA
179 | 637 | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.15 | MED-15 | Order review & consent (patient) — confirm and consent before the prescription is shared | MED-15.02 | QA: back button does not share | Regression | HomeoMeds | §2.7 | Order review & consent | Confirm and consent before the prescription is shared | Patient | QA | Yes | No | No | No | No | No | P0 | S | MED-15.01 | — | UI | MED-15.01 | Covered by MED-03; explicit review screen still required | Review screen listing codes (not names) + pharmacy + consent checkbox | Share does not occur until review confirmed | Not Started | QA
180 | 640 | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.16 | MED-16 | Medicines tab — all medicine orders in one place (API now; app UI in Phase 16) | MED-16.03 | QA: IDOR other patient 403 | Regression | HomeoMeds | §2.7 | Medicines tab | All medicine orders in one place | Patient | QA | No | Yes | No | No | No | No | P1 | S | MED-16.02 | — | Web, UI | MED-16.02 | Does not exist | GET my orders; website optional list; app tab Phase 16 | Patient sees all orders for their PatientId only | Not Started | QA
181 | 644 | QA | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.1 | CON-01 | Family members — add family members under one account | CON-01.04 | QA: adult consent rules for minors documented | Regression | Patient identity | §2.1 | Family members | Add family members under one account | Patient App (API now) | QA | Yes | Yes | No | Yes | No | No | P0 | S | CON-01.03 | — | Web, UI | CON-01.03 | Does not exist | FamilyMember under Patient account; bookings can be for a member | Member has own PatientId or MemberId linked; records isolated correctly | Not Started | QA
182 | 649 | QA | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.2 | CON-02 | Caregiver authorization — let a family member book and manage on their behalf | CON-02.05 | QA: revoked token cannot book | Regression | Patient identity | §2.1 | Caregiver authorization | Let a family member book and manage on their behalf | Patient App (API now) | QA | Yes | Yes | No | Yes | No | No | P0 | S | CON-02.04 | — | Web, UI | CON-02.04 | Does not exist | CaregiverAuth with scopes; OTP; withdrawable via consent centre | Caregiver cannot exceed granted scopes; withdrawal immediate | Not Started | QA
183 | 653 | QA | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.3 | CON-03 | Records timeline + consultation note + document upload APIs | CON-03.04 | QA: notes leak test on timeline JSON | Regression | Patient records | §2.5 | Records timeline / Consultation note / Document upload | Complete visit history in date order / Doctor’s notes for each visit / Upload reports, scans and previous prescriptions | Patient App (API now) | QA | Yes | Yes | No | Yes | No | No | P0 | S | CON-03.03 | — | Web, UI | CON-03.03 | Doctor history exists; no patient timeline; no patient upload | Patient timeline DTO (visits, summary, eRx codes, labs); consultation note = TEL-11 summary not private notes; uploads via SEC-09 | Private doctor notes never in patient timeline; uploads listed | Not Started | QA
184 | 657 | QA | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.4 | CON-04 | Follow-up plan & tasks — clear next steps after each consultation | CON-04.04 | QA: overdue flag | Regression | Continuity | §2.6 | Follow-up plan & tasks | Clear next steps after each consultation | Doctor Web + Patient | QA | Yes | Yes | No | Yes | No | No | P1 | S | CON-04.03 | — | Web, UI | CON-04.03 | Does not exist (follow-up option in notes does not save) | FollowUpTask created by doctor; patient sees tasks | Tasks persist against PatientAppId; due dates drive Phase 18 follow-up analysis | Not Started | QA
185 | 661 | QA | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.5 | CON-05 | Symptom diary — record symptoms between visits | CON-05.04 | QA: IDOR | Regression | Continuity | §2.6 | Symptom diary | Record symptoms between visits | Patient App (API now) | QA | Yes | Yes | No | Yes | No | No | P1 | S | CON-05.03 | — | Web, UI | CON-05.03 | Does not exist | SymptomDiary entries; doctor can read on board | Entries dated; treating doctor can read; other doctors 403 | Not Started | QA
186 | 665 | QA | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.6 | CON-06 | Progress tracking — see improvement over time across visits | CON-06.04 | QA: no dummy numbers | Regression | Continuity | §2.6 | Progress tracking | See improvement over time across visits | Patient + Doctor | QA | Yes | Yes | No | Yes | No | No | P2 | S | CON-06.03 | — | Web, UI | CON-06.03 | Does not exist | Progress series from diary + visit outcomes; not a fake chart | Empty state for new patients; series uses real diary/visit data | Not Started | QA
187 | 669 | QA | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.7 | CON-07 | Consent centre & data rights — view, manage and withdraw consents; request data | CON-07.04 | QA: withdraw marketing stops WhatsApp/SMS offers | Regression | Privacy | §17 + §2.8 | Consent centre & data rights | Patients can view, manage and withdraw consent / View, manage and withdraw consents; request data | Patient App (API now) | QA | Yes | Yes | No | Yes | No | No | P0 | S | CON-07.03 | — | Web, UI | CON-07.03 | ConsentRecord from Phase 0 | Patient list/withdraw; data export request (DPDP); deletion request workflow | Withdraw tele-recording prevents future recording; export request ticketed | Not Started | QA
188 | 671 | QA | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.8 | CON-08 | Patient payments & refunds read model | CON-08.02 | QA: commission/GST internal lines hidden | Regression | Patient money | §2.8 | Payments & refunds | Full payment history and refund status | Patient App (API now) | QA | No | Yes | No | No | No | No | P1 | S | CON-08.01 | — | Web | CON-08.01 | Ledger exists for Account | Patient-safe DTO of own consult+medicine payments and refunds — no other patients, no commission internals | Patient sees status matching PAY-08; no Account-only fields leaked | Not Started | QA
189 | 673 | QA | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.9 | CON-09 | Physical clinic appointment — book an in-person visit as well as online | CON-09.02 | QA: in-clinic does not require device check/video | Regression | Booking | §2.9 + §5.2 | Physical clinic appointment | Book an in-person visit as well as online | Patient | QA | No | Yes | No | No | No | No | P1 | S | CON-09.01 | — | Web | CON-09.01 | ConsultMode added in APT-02; public booking in WEB-04 | Ensure public/patient booking supports In-clinic as first-class, not tele-only | Patient can book in-clinic slot where doctor offers it | Not Started | QA
190 | 677 | QA | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.10 | CON-10 | Patient profile setup API — name, age, gender, contact and health basics | CON-10.04 | QA: cannot escalate to doctor role via profile PUT | Regression | Patient identity | §2.1 | Profile setup | Name, age, gender, contact and health basics | Patient App (API now) | QA | Yes | Yes | No | Yes | No | No | P0 | S | CON-10.03 | — | Web, UI | CON-10.03 | Clinic-created Patient exists; no self-serve profile product | Patient profile fields + health basics; used by OTP-verified patient token | Profile required before first paid booking (or soft-gate documented) | Not Started | QA
191 | 681 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.1 | PAT-01 | Patient app — language selection on first open | PAT-01.04 | QA both platforms: Language selection matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.1 | Language selection | Choose preferred language on first open | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-01.03 | — | Mobile | PAT-01.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Choose preferred language on first open | Not Started | QA
192 | 685 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.2 | PAT-02 | Patient app — welcome and introduction | PAT-02.04 | QA both platforms: Welcome & introduction matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.1 | Welcome & introduction | Guided introduction to the app | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-02.03 | — | Mobile | PAT-02.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Guided introduction to the app | Not Started | QA
193 | 689 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.3 | PAT-03 | Patient app — mobile number + OTP login (PatientAuth) | PAT-03.04 | QA both platforms: Mobile number + OTP login matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.1 | Mobile number + OTP login | Secure sign-in with no password to remember | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-03.03 | — | Mobile | PAT-03.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Secure sign-in with no password to remember | Not Started | QA
194 | 693 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.4 | PAT-04 | Patient app — profile setup | PAT-04.04 | QA both platforms: Profile setup matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.1 | Profile setup | Name, age, gender, contact and health basics | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-04.03 | — | Mobile | PAT-04.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Name, age, gender, contact and health basics | Not Started | QA
195 | 697 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.5 | PAT-05 | Patient app — privacy consent before data stored | PAT-05.04 | QA both platforms: Privacy consent matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.1 | Privacy consent | Clear consent before any personal data is stored | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-05.03 | — | Mobile | PAT-05.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Clear consent before any personal data is stored | Not Started | QA
196 | 701 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.6 | PAT-06 | Patient app — family members | PAT-06.04 | QA both platforms: Family members matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.1 | Family members | Add family members under one account | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-06.03 | — | Mobile | PAT-06.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Add family members under one account | Not Started | QA
197 | 705 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.7 | PAT-07 | Patient app — caregiver authorization | PAT-07.04 | QA both platforms: Caregiver authorization matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.1 | Caregiver authorization | Let a family member book and manage on their behalf | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-07.03 | — | Mobile | PAT-07.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Let a family member book and manage on their behalf | Not Started | QA
198 | 709 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.8 | PAT-08 | Patient app — home dashboard | PAT-08.04 | QA both platforms: Home dashboard matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.2 | Home dashboard | Personalised home with upcoming visits and quick actions | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-08.03 | — | Mobile | PAT-08.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Personalised home with upcoming visits and quick actions | Not Started | QA
199 | 713 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.9 | PAT-09 | Patient app — search and care categories | PAT-09.04 | QA both platforms: Search & care categories matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.2 | Search & care categories | Search by name, condition or category of care | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-09.03 | — | Mobile | PAT-09.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Search by name, condition or category of care | Not Started | QA
200 | 717 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.10 | PAT-10 | Patient app — search results | PAT-10.04 | QA both platforms: Search results matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.2 | Search results | Clear list of available doctors | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-10.03 | — | Mobile | PAT-10.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Clear list of available doctors | Not Started | QA
201 | 721 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.11 | PAT-11 | Patient app — discovery filters | PAT-11.04 | QA both platforms: Filters matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.2 | Filters | Narrow by availability, fee, experience, language and location | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-11.03 | — | Mobile | PAT-11.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Narrow by availability, fee, experience, language and location | Not Started | QA
202 | 725 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.12 | PAT-12 | Patient app — doctor profile | PAT-12.04 | QA both platforms: Doctor profile matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.2 | Doctor profile | Full profile with qualifications, experience and consultation fee | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-12.03 | — | Mobile | PAT-12.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Full profile with qualifications, experience and consultation fee | Not Started | QA
203 | 729 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.13 | PAT-13 | Patient app — verified badge on doctor | PAT-13.04 | QA both platforms: Credentials & verification matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.2 | Credentials & verification | Verified badge showing the doctor’s credentials are checked | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-13.03 | — | Mobile | PAT-13.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Verified badge showing the doctor’s credentials are checked | Not Started | QA
204 | 733 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.14 | PAT-14 | Patient app — ranking explanation | PAT-14.04 | QA both platforms: Ranking explanation matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.2 | Ranking explanation | Transparent explanation of why doctors appear in a given order | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-14.03 | — | Mobile | PAT-14.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Transparent explanation of why doctors appear in a given order | Not Started | QA
205 | 737 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.15 | PAT-15 | Patient app — health articles | PAT-15.04 | QA both platforms: Health articles matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.2 | Health articles | Educational content to build trust and engagement | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-15.03 | — | Mobile | PAT-15.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Educational content to build trust and engagement | Not Started | QA
206 | 741 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.16 | PAT-16 | Patient app — slot picker | PAT-16.04 | QA both platforms: Slot picker matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Slot picker | See real available time slots and choose one | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-16.03 | — | Mobile | PAT-16.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: See real available time slots and choose one | Not Started | QA
207 | 745 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.17 | PAT-17 | Patient app — booking review and consent | PAT-17.04 | QA both platforms: Booking review & consent matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Booking review & consent | Confirm details and consent before booking | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-17.03 | — | Mobile | PAT-17.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Confirm details and consent before booking | Not Started | QA
208 | 749 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.18 | PAT-18 | Patient app — checkout | PAT-18.04 | QA both platforms: Checkout matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Checkout | Pay the consultation fee inside the app | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-18.03 | — | Mobile | PAT-18.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Pay the consultation fee inside the app | Not Started | QA
209 | 753 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.19 | PAT-19 | Patient app — payment status | PAT-19.04 | QA both platforms: Payment status matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Payment status | Immediate confirmation of paid, pending or failed | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-19.03 | — | Mobile | PAT-19.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Immediate confirmation of paid, pending or failed | Not Started | QA
210 | 757 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.20 | PAT-20 | Patient app — appointment detail | PAT-20.04 | QA both platforms: Appointment detail matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Appointment detail | Full booking details in one place | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-20.03 | — | Mobile | PAT-20.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Full booking details in one place | Not Started | QA
211 | 761 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.21 | PAT-21 | Patient app — reschedule | PAT-21.04 | QA both platforms: Reschedule appointment matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Reschedule appointment | Move to another slot without calling the clinic | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-21.03 | — | Mobile | PAT-21.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Move to another slot without calling the clinic | Not Started | QA
212 | 765 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.22 | PAT-22 | Patient app — cancel | PAT-22.04 | QA both platforms: Cancel appointment matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Cancel appointment | Cancel with reason, refund handled per policy | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-22.03 | — | Mobile | PAT-22.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Cancel with reason, refund handled per policy | Not Started | QA
213 | 769 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.23 | PAT-23 | Patient app — waitlist offer | PAT-23.04 | QA both platforms: Waitlist offer matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Waitlist offer | Get offered a slot when one is freed by a cancellation | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-23.03 | — | Mobile | PAT-23.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Get offered a slot when one is freed by a cancellation | Not Started | QA
214 | 773 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.24 | PAT-24 | Patient app — instant consult request | PAT-24.04 | QA both platforms: Instant consult request matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Instant consult request | Request an immediate consultation with an available doctor | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-24.03 | — | Mobile | PAT-24.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Request an immediate consultation with an available doctor | Not Started | QA
215 | 777 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.25 | PAT-25 | Patient app — queue and doctor offer | PAT-25.04 | QA both platforms: Queue & doctor offer matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Queue & doctor offer | See position in queue and accept an offered doctor | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-25.03 | — | Mobile | PAT-25.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: See position in queue and accept an offered doctor | Not Started | QA
216 | 781 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.26 | PAT-26 | Patient app — device check | PAT-26.04 | QA both platforms: Device check matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.4 | Device check | Camera, microphone and network checked before the call | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-26.03 | — | Mobile | PAT-26.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Camera, microphone and network checked before the call | Not Started | QA
217 | 785 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.27 | PAT-27 | Patient app — waiting room | PAT-27.04 | QA both platforms: Waiting room matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.4 | Waiting room | Wait with live status until the doctor joins | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-27.03 | — | Mobile | PAT-27.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Wait with live status until the doctor joins | Not Started | QA
218 | 789 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.28 | PAT-28 | Patient app — live video | PAT-28.04 | QA both platforms: Live video consultation matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.4 | Live video consultation | Face-to-face consultation from home | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-28.03 | — | Mobile | PAT-28.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Face-to-face consultation from home | Not Started | QA
219 | 793 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.29 | PAT-29 | Patient app — recording consent | PAT-29.04 | QA both platforms: Recording consent matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.4 | Recording consent | Explicit consent requested before any recording | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-29.03 | — | Mobile | PAT-29.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Explicit consent requested before any recording | Not Started | QA
220 | 797 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.30 | PAT-30 | Patient app — join failure fallback | PAT-30.04 | QA both platforms: Fallback & join failure handling matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.4 | Fallback & join failure handling | Clear guidance if the call fails, with options to retry | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-30.03 | — | Mobile | PAT-30.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Clear guidance if the call fails, with options to retry | Not Started | QA
221 | 801 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.31 | PAT-31 | Patient app — case-linked chat | PAT-31.04 | QA both platforms: Case-linked chat matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.4 | Case-linked chat | Chat tied to the consultation, not a loose message thread | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-31.03 | — | Mobile | PAT-31.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Chat tied to the consultation, not a loose message thread | Not Started | QA
222 | 805 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.32 | PAT-32 | Patient app — consultation summary | PAT-32.04 | QA both platforms: Consultation summary matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.4 | Consultation summary | Written summary available immediately after the call | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-32.03 | — | Mobile | PAT-32.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Written summary available immediately after the call | Not Started | QA
223 | 809 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.33 | PAT-33 | Patient app — rejoin | PAT-33.04 | QA both platforms: Rejoin after dropped call matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.4 | Rejoin after dropped call | Rejoin the same consultation if the connection drops | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-33.03 | — | Mobile | PAT-33.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Rejoin the same consultation if the connection drops | Not Started | QA
224 | 813 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.34 | PAT-34 | Patient app — records timeline | PAT-34.04 | QA both platforms: Records timeline matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.5 | Records timeline | Complete visit history in date order | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-34.03 | — | Mobile | PAT-34.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Complete visit history in date order | Not Started | QA
225 | 817 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.35 | PAT-35 | Patient app — consultation note (summary, not private notes) | PAT-35.04 | QA both platforms: Consultation note matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.5 | Consultation note | Doctor’s notes for each visit | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-35.03 | — | Mobile | PAT-35.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Doctor’s notes for each visit | Not Started | QA
226 | 821 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.36 | PAT-36 | Patient app — signed eRx (codes until pharmacy accept) | PAT-36.04 | QA both platforms: Signed digital prescription matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.5 | Signed digital prescription | Official prescription issued by the doctor | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-36.03 | — | Mobile | PAT-36.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Official prescription issued by the doctor | Not Started | QA
227 | 825 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.37 | PAT-37 | Patient app — document upload | PAT-37.04 | QA both platforms: Document upload matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.5 | Document upload | Upload reports, scans and previous prescriptions | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-37.03 | — | Mobile | PAT-37.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Upload reports, scans and previous prescriptions | Not Started | QA
228 | 829 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.38 | PAT-38 | Patient app — follow-up plan and tasks | PAT-38.04 | QA both platforms: Follow-up plan & tasks matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.6 | Follow-up plan & tasks | Clear next steps after each consultation | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-38.03 | — | Mobile | PAT-38.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Clear next steps after each consultation | Not Started | QA
229 | 833 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.39 | PAT-39 | Patient app — symptom diary | PAT-39.04 | QA both platforms: Symptom diary matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.6 | Symptom diary | Record symptoms between visits | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-39.03 | — | Mobile | PAT-39.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Record symptoms between visits | Not Started | QA
230 | 837 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.40 | PAT-40 | Patient app — progress tracking | PAT-40.04 | QA both platforms: Progress tracking matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.6 | Progress tracking | See improvement over time across visits | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-40.03 | — | Mobile | PAT-40.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: See improvement over time across visits | Not Started | QA
231 | 841 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.41 | PAT-41 | Patient app — medicines tab | PAT-41.04 | QA both platforms: Medicines tab matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.7 | Medicines tab | All medicine orders in one place | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-41.03 | — | Mobile | PAT-41.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: All medicine orders in one place | Not Started | QA
232 | 845 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.42 | PAT-42 | Patient app — start HomeoMeds order from eRx | PAT-42.04 | QA both platforms: Order start matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.7 | Order start | Start an order directly from the prescription | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-42.03 | — | Mobile | PAT-42.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Start an order directly from the prescription | Not Started | QA
233 | 849 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.43 | PAT-43 | Patient app — pharmacy selection and quote | PAT-43.04 | QA both platforms: Pharmacy selection & quote matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.7 | Pharmacy selection & quote | Choose a licensed pharmacy and see the price before paying | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-43.03 | — | Mobile | PAT-43.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Choose a licensed pharmacy and see the price before paying | Not Started | QA
234 | 853 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.44 | PAT-44 | Patient app — order review and consent | PAT-44.04 | QA both platforms: Order review & consent matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.7 | Order review & consent | Confirm and consent before the prescription is shared | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-44.03 | — | Mobile | PAT-44.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Confirm and consent before the prescription is shared | Not Started | QA
235 | 857 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.45 | PAT-45 | Patient app — order tracking | PAT-45.04 | QA both platforms: Order tracking matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.7 | Order tracking | Live status from accepted to delivered | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-45.03 | — | Mobile | PAT-45.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Live status from accepted to delivered | Not Started | QA
236 | 861 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.46 | PAT-46 | Patient app — order detail and refill | PAT-46.04 | QA both platforms: Order detail & refill matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.7 | Order detail & refill | Full order history and one-tap refill request | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-46.03 | — | Mobile | PAT-46.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Full order history and one-tap refill request | Not Started | QA
237 | 865 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.47 | PAT-47 | Patient app — write a review | PAT-47.04 | QA both platforms: Write a review matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.8 | Write a review | Rate and review the consultation | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-47.03 | — | Mobile | PAT-47.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Rate and review the consultation | Not Started | QA
238 | 869 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.48 | PAT-48 | Patient app — my reviews and appeal | PAT-48.04 | QA both platforms: My reviews & appeal matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.8 | My reviews & appeal | Manage reviews and raise an appeal | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-48.03 | — | Mobile | PAT-48.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Manage reviews and raise an appeal | Not Started | QA
239 | 873 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.49 | PAT-49 | Patient app — payments and refunds | PAT-49.04 | QA both platforms: Payments & refunds matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.8 | Payments & refunds | Full payment history and refund status | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-49.03 | — | Mobile | PAT-49.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Full payment history and refund status | Not Started | QA
240 | 877 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.50 | PAT-50 | Patient app — profile and settings | PAT-50.04 | QA both platforms: Profile & settings matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.8 | Profile & settings | Manage personal details and preferences | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-50.03 | — | Mobile | PAT-50.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Manage personal details and preferences | Not Started | QA
241 | 881 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.51 | PAT-51 | Patient app — consent centre and data rights | PAT-51.04 | QA both platforms: Consent centre & data rights matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.8 | Consent centre & data rights | View, manage and withdraw consents; request data | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-51.03 | — | Mobile | PAT-51.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: View, manage and withdraw consents; request data | Not Started | QA
242 | 885 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.52 | PAT-52 | Patient app — notifications centre | PAT-52.04 | QA both platforms: Notifications centre matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.8 | Notifications centre | All alerts in one place | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-52.03 | — | Mobile | PAT-52.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: All alerts in one place | Not Started | QA
243 | 889 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.53 | PAT-53 | Patient app — help centre and tickets | PAT-53.04 | QA both platforms: Help centre & support tickets matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.9 | Help centre & support tickets | Raise an issue and track it to resolution | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-53.03 | — | Mobile | PAT-53.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Raise an issue and track it to resolution | Not Started | QA
244 | 893 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.54 | PAT-54 | Patient app — physical clinic booking | PAT-54.04 | QA both platforms: Physical clinic appointment matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.9 | Physical clinic appointment | Book an in-person visit as well as online | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-54.03 | — | Mobile | PAT-54.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Book an in-person visit as well as online | Not Started | QA
245 | 897 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.55 | PAT-55 | Patient app — assisted booking request | PAT-55.04 | QA both platforms: Assisted booking matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.9 | Assisted booking | Help for patients who need support booking | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-55.03 | — | Mobile | PAT-55.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Help for patients who need support booking | Not Started | QA
246 | 901 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.56 | PAT-56 | Patient app — low-data mode | PAT-56.04 | QA both platforms: Low-data mode matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.9 | Low-data mode | Works on slow or limited connections | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-56.03 | — | Mobile | PAT-56.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Works on slow or limited connections | Not Started | QA
247 | 905 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.57 | PAT-57 | Patient app — push notifications | PAT-57.04 | QA both platforms: Push notifications matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.9 | Push notifications | Booking confirmations, reminders, doctor ready, prescription issued, order updates | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-57.03 | — | Mobile | PAT-57.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Booking confirmations, reminders, doctor ready, prescription issued, order updates | Not Started | QA
248 | 907 | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.58 | PAT-58 | Patient app — iOS and Android store release, device matrix, and parity QA | PAT-58.02 | Parity QA spreadsheet: each PAT-01..57 on both OS | Regression | Patient Mobile | §2 + §18 | Patient mobile app iOS and Android | iOS and Android — onboarding, discovery, booking, payment, video consultation, records, prescriptions, follow-up, medicines, reviews, support, notifications | Patient Mobile App | QA | No | No | No | No | Yes | No | P0 | L | PAT-58.01 | — | Mobile | PAT-58.01 | No app | Store builds; crash-free join; feature parity checklist against every §2 row | Parity matrix signed: every §2 feature works on both OS | Not Started | QA
249 | 912 | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.1 | DMO-01 | Doctor app — login & identity (same login and same account as the web portal) | DMO-01.04 | QA: same DoctorId as web; reception accounts must not open doctor clinical actions | Regression | Doctor Mobile | §3 | Login & identity | Same login and same account as the web portal | Doctor Mobile App | QA | Yes | No | No | Yes | Yes | No | P0 | S | DMO-01.03 | — | Mobile | DMO-01.03 | No doctor app | Same Account login + DoctorId; bind device; no separate doctor identity | Web and app show the same queue for the same DoctorId | Not Started | QA
250 | 916 | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.2 | DMO-02 | Doctor app — first-run onboarding (guided setup, number confirmation and permissions) | DMO-02.04 | QA: number mismatch blocked | Regression | Doctor Mobile | §3 | First-run onboarding | Guided setup, number confirmation and permissions | Doctor Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | DMO-02.03 | — | Mobile | DMO-02.03 | No app | Confirm registered mobile; permission primer | Onboarding cannot be skipped past permission explanation for mic/camera/push | Not Started | QA
251 | 920 | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.3 | DMO-03 | Doctor app — notification permissions (push, microphone and camera handled properly) | DMO-03.04 | QA: deny each permission independently | Regression | Doctor Mobile | §3 | Notification permissions | Push, microphone and camera permissions handled properly | Doctor Mobile App | QA | Yes | No | No | Yes | Yes | No | P0 | S | DMO-03.03 | — | Mobile | DMO-03.03 | No app | OS permission flows; settings deep link if denied | Denied camera still allows queue viewing; join explains why it cannot start | Not Started | QA
252 | 924 | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.4 | DMO-04 | Doctor app — today’s queue & schedule (the full day at a glance) | DMO-04.04 | QA: parity with web counts | Regression | Doctor Mobile | §3 | Today’s queue & schedule | The full day at a glance | Doctor Mobile App | QA | Yes | No | No | Yes | Yes | No | P0 | S | DMO-04.03 | — | Mobile | DMO-04.03 | No app | Appointment list APIs; payment + tele flags; no Patient Board | Matches web dashboard buckets for today | Not Started | QA
253 | 928 | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.5 | DMO-05 | Doctor app — availability toggle (go online or offline, set working hours) | DMO-05.04 | QA: web and app status match within heartbeat | Regression | Doctor Mobile | §3 | Availability toggle | Go online or offline, set working hours | Doctor Mobile App | QA | Yes | No | No | Yes | Yes | No | P0 | S | DMO-05.03 | — | Mobile | DMO-05.03 | No app | Same TeleAvailability + schedule APIs as web | Toggle on app updates web and patient instant matching | Not Started | QA
254 | 932 | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.6 | DMO-06 | Doctor app — push notifications (waiting, booking, reschedule, cancellation, refill, payment received) | DMO-06.04 | QA: each event type deep link | Regression | Doctor Mobile | §3 | Push notifications | Patient waiting, new booking, reschedule, cancellation, refill request, payment received | Doctor Mobile App | QA | Yes | No | No | Yes | Yes | No | P0 | S | DMO-06.03 | — | Mobile | DMO-06.03 | No app | Consume COM-03 doctor templates | Each listed event delivers a push when permission granted | Not Started | QA
255 | 936 | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.7 | DMO-07 | Doctor app — patient context card (name, age, chief complaint and last visit) — NO case-taking | DMO-07.04 | QA: repertory endpoints never called from app | Regression | Doctor Mobile | §3 | Patient context card | Name, age, chief complaint and last visit before joining | Doctor Mobile App | QA | Yes | No | No | Yes | Yes | No | P0 | S | DMO-07.03 | — | Mobile | DMO-07.03 | No app; PDF: detailed case-taking stays on the web portal | Read-only card; explicitly no repertory/audio/Rx compose | No path to Patient Board clinical tools from the app | Not Started | QA
256 | 940 | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.8 | DMO-08 | Doctor app — join consultation (video or audio from the phone) | DMO-08.04 | QA: web patient + app doctor | Regression | Doctor Mobile | §3 | Join consultation | Start the video or audio consultation from the phone | Doctor Mobile App | QA | Yes | No | No | Yes | Yes | No | P0 | S | DMO-08.03 | — | Mobile | DMO-08.03 | No app | Same session tokens as TEL-03/04 | Join same room as web patient or mobile patient | Not Started | QA
257 | 944 | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.9 | DMO-09 | Doctor app — refill approval (approve or reject repeat prescription requests) | DMO-09.04 | QA: reject reason; cannot edit snapshot | Regression | Doctor Mobile | §3 + §11 | Refill approval | Approve or reject repeat prescription requests | Doctor Mobile App | QA | Yes | No | No | Yes | Yes | No | P0 | S | DMO-09.03 | — | Mobile | DMO-09.03 | No app | ERX-10 inbox; approve only — Patient Board remains web | Approve/reject from phone writes the same RefillRequest as web | Not Started | QA
258 | 948 | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.10 | DMO-10 | Doctor app — earnings summary (today, this week, this month, with payout status) | DMO-10.04 | QA: matches /account figures ± rounding | Regression | Doctor Mobile | §3 + §16 | Earnings summary | Today, this week and this month, with payout status | Doctor Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | DMO-10.03 | — | Mobile | DMO-10.03 | No app | Account ledger read model for this DoctorId — not a second money system | Figures match Account settlement for that doctor | Not Started | QA
259 | 952 | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.11 | DMO-11 | Doctor app — offline handling (weak connection or expired session) | DMO-11.04 | QA: airplane mode on join | Regression | Doctor Mobile | §3 | Offline handling | Clear behaviour on weak connection or expired session | Doctor Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | DMO-11.03 | — | Mobile | DMO-11.03 | No app | Queued actions policy (do not fake join); session expiry uses SEC-03 | Expired JWT cannot join video; user is told to re-login | Not Started | QA
260 | 954 | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.12 | DMO-12 | Doctor app — reliability monitoring (failures reported automatically) | DMO-12.02 | QA: simulated crash + join fail event | Regression | Doctor Mobile | §3 | Reliability monitoring | Failures are reported automatically, not left to a phone call | Doctor Mobile App | QA | No | No | No | No | Yes | No | P1 | S | DMO-12.01 | — | Mobile | DMO-12.01 | No app | Crash/error SDK; join failures also as TeleSessionEvent | A forced crash appears in the monitoring tool within SLA | Not Started | QA
261 | 956 | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.13 | DMO-13 | Doctor app — iOS and Android parity QA (queue, availability, notifications, context, video, refill, earnings) | DMO-13.02 | Parity QA DMO-01..12 both OS | Regression | Doctor Mobile | §3 + §18 | Doctor mobile app iOS and Android | iOS and Android — queue, availability, notifications, patient context, video consultation, refill approval, earnings | Doctor Mobile App | QA | No | No | No | No | Yes | No | P0 | L | DMO-13.01 | — | Mobile | DMO-13.01 | No app | Parity checklist for every §3 row on both OS | Parity matrix signed | Not Started | QA
262 | 960 | QA | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.1 | RPT-01 | Admin overview dashboard — platform-wide activity at a glance (replace Velzon ecommerce) | RPT-01.04 | QA: login as admin never shows fake store visits | Regression | Reports | §16 + §7.2 | Admin overview dashboard / Admin dashboard | Platform-wide activity at a glance / Live overview of the whole platform | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P0 | S | RPT-01.03 | — | Web, UI | RPT-01.03 | Velzon ecommerce dashboard 0% product; login lands /dashboard | True /admin/dashboard KPIs: doctors, credentialing, bookings, GMV, failed payments, tickets, HomeoMeds exceptions; redirect /dashboard away from StoreVisits | Admin home is product KPIs, not Velzon Revenue/StoreVisits | Not Started | QA
263 | 964 | QA | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.2 | RPT-02 | Doctor practice statistics — patient and consultation trends (extend existing charts) | RPT-02.04 | QA: empty new clinic | Regression | Reports | §16 + §5.1 | Doctor practice statistics | Patient and consultation trends | Doctor Web | QA | Yes | Yes | No | Yes | No | No | P1 | S | RPT-02.03 | — | Web, UI | RPT-02.03 | Patient stats charts live | Keep as foundation; ensure visit type/mode included after APT-02 | Trends include first vs follow-up when VisitType exists | Not Started | QA
264 | 968 | QA | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.3 | RPT-03 | Follow-up analysis — due/overdue patients and follow-up conversion | RPT-03.04 | QA: overdue vs due buckets | Regression | Reports | §16 | Follow-up analysis | Which patients are due or overdue for follow-up, and follow-up conversion | Doctor Web | QA | Yes | Yes | No | Yes | No | No | P1 | S | RPT-03.03 | — | Web, UI | RPT-03.03 | Does not exist; follow-up option in notes does not save | /doctor/follow-up-analysis from VisitType + CON-04 tasks | Due list and conversion first-visit → follow-up are real counts | Not Started | QA
265 | 972 | QA | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.4 | RPT-04 | Clinic performance analysis — appointments, slot utilisation, no-shows, cancellations, waiting time and revenue | RPT-04.04 | QA: cancelled excluded from completed; revenue uses ledger not client | Regression | Reports | §16 | Clinic performance analysis | Appointments, slot utilisation, no-shows, cancellations, waiting time and revenue | Doctor Web | QA | Yes | Yes | No | Yes | No | No | P1 | S | RPT-04.03 | — | Web, UI | RPT-04.03 | Does not exist | /doctor/clinic-performance including payment collected and tele duration if timed | Each KPI has a definition note on the screen (no silent formula) | Not Started | QA
266 | 975 | QA | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.5 | RPT-05 | Payment reconciliation report — bookings matched against payments | RPT-05.03 | QA: unmatched rows included | Regression | Reports | §16 + §7.2 | Payment reconciliation report / Consult booking & payment reconciliation | Bookings matched against payments / Match every booking against every payment | Admin + Account | QA | Yes | No | No | No | No | No | P1 | S | RPT-05.02 | — | Web, UI | RPT-05.02 | FIN-02 built the queue; this is the report/export | Exportable report from the same reconciliation query | CSV totals match on-screen KPIs | Not Started | QA
267 | 978 | QA | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.6 | RPT-06 | Settlement & payout reports — amounts due and paid to doctors and pharmacies | RPT-06.03 | QA: pharmacy lines appear only after HomeoMeds | Regression | Reports | §16 + §8 | Settlement & payout reports | Amounts due and paid to doctors and pharmacies | Account | QA | Yes | No | No | No | No | No | P1 | S | RPT-06.02 | — | Web, UI | RPT-06.02 | FIN-04/05 exist as ops screens | Formal report/export of runs and payouts | Paid vs due columns reconcile to ledger | Not Started | QA
268 | 980 | QA | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.7 | RPT-07 | GST & invoice reports (reporting surface of FIN-08) | RPT-07.02 | QA: number series gaps flagged | Regression | Reports | §16 + §8 | GST & invoice reports | Tax reporting | Account | QA | No | Yes | No | No | No | No | P1 | S | RPT-07.01 | — | Web | RPT-07.01 | FIN-08 built tax screen | Confirm report pack (GSTR-style export as agreed with CA) — configuration | Invoice list export matches FIN-08 | Not Started | QA
269 | 984 | QA | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.8 | RPT-08 | Doctor earnings summary — daily, weekly and monthly earnings with payout status (web + same API as DMO-10) | RPT-08.04 | QA: payout pending vs paid | Regression | Reports | §16 + §3 | Doctor earnings summary | Daily, weekly and monthly earnings with payout status | Doctor Web + App | QA | Yes | Yes | No | Yes | No | No | P1 | S | RPT-08.03 | — | Web, UI | RPT-08.03 | Does not exist | Web earnings page using same API as doctor app | Web and app match | Not Started | QA
270 | 988 | QA | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.9 | RPT-09 | Medicine order reports — order volumes, fulfilment and exceptions | RPT-09.04 | QA: cancelled orders not counted as delivered | Regression | Reports | §16 + §12 | Medicine order reports | Order volumes, fulfilment and exceptions | Admin + Account | QA | Yes | Yes | No | Yes | No | No | P1 | S | RPT-09.03 | — | Web, UI | RPT-09.03 | Does not exist | Volumes, SLA, exception counts from HomeoMeds | Exception count matches MED-12 queue | Not Started | QA
271 | 992 | QA | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.10 | RPT-10 | Platform users remaining 20% — import, export and activation control | RPT-10.04 | QA: export contains only permitted fields | Regression | Admin | §7.2 | Platform users | Manage all users with import, export and activation control | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P1 | S | RPT-10.03 | — | Web, UI | RPT-10.03 | List/Add/Edit live; Import/Export buttons dead; no verification column | Wire Import/Export; verification column; activate/lock; link credentialing | Import/Export work; unverified visible; lock prevents login | Not Started | QA
272 | 993 | QA | 19 | Phase 19 — Cross-surface QA, NFR, delivery summary gate (PDF §1 + §18) | 19.1 | QA-01 | One ecosystem proof — patient, appointment, prescription and payment created anywhere are visible everywhere | QA-01.01 | E2E: Reception creates patient+appt → Doctor board → sign eRx → Patient app sees codes → Pharmacy accept OTP → patient sees names+pay → Account ledger S2 and S5 | Regression | QA | §1 + §18 | One connected ecosystem | A patient, an appointment, a prescription and a payment created anywhere in the system are visible everywhere else | All | QA | Yes | Yes | No | No | Yes | No | P0 | L | — | — | — |  | Surfaces were built in phases | End-to-end scripts covering all six user types | Signed E2E pack: 6 roles, no dual ledgers, no dual appointments | Not Started | QA
273 | 994 | QA | 19 | Phase 19 — Cross-surface QA, NFR, delivery summary gate (PDF §1 + §18) | 19.1 | QA-01 | One ecosystem proof — patient, appointment, prescription and payment created anywhere are visible everywhere | QA-01.02 | E2E: Patient app books+pays tele → doctor app join → summary+eRx → refill on doctor app | Regression | QA | §1 + §18 | One connected ecosystem | A patient, an appointment, a prescription and a payment created anywhere in the system are visible everywhere else | All | QA | No | No | No | No | Yes | No | P0 | L | QA-01.01 | T-272 (QA-01.01) | — |  | Surfaces were built in phases | End-to-end scripts covering all six user types | Signed E2E pack: 6 roles, no dual ledgers, no dual appointments | Not Started | QA
274 | 995 | QA | 19 | Phase 19 — Cross-surface QA, NFR, delivery summary gate (PDF §1 + §18) | 19.1 | QA-01 | One ecosystem proof — patient, appointment, prescription and payment created anywhere are visible everywhere | QA-01.03 | Negative: Admin cannot payout; Account cannot edit repertory | Regression | QA | §1 + §18 | One connected ecosystem | A patient, an appointment, a prescription and a payment created anywhere in the system are visible everywhere else | All | QA | No | Yes | No | No | No | No | P0 | S | QA-01.02 | T-273 (QA-01.02) | — |  | Surfaces were built in phases | End-to-end scripts covering all six user types | Signed E2E pack: 6 roles, no dual ledgers, no dual appointments | Not Started | QA
275 | 996 | QA | 19 | Phase 19 — Cross-surface QA, NFR, delivery summary gate (PDF §1 + §18) | 19.2 | QA-02 | Delivery summary gate — every area in PDF §18 signed off | QA-02.01 | Traceability review: 01_PDF_Coverage every row has Main Task ID and final Status | Regression | QA | §18 | Summary of delivery | All features listed in this document are included in the delivery scope. | Programme | QA | No | No | No | No | No | No | P0 | M | — | — | — |  | This register is the scope | Walk the coverage sheet; zero PDF rows with Status≠Done unless formally deferred with client sign | Coverage sheet 100% mapped; deferred items have written client sign | Not Started | QA
276 | 997 | QA | 19 | Phase 19 — Cross-surface QA, NFR, delivery summary gate (PDF §1 + §18) | 19.2 | QA-02 | Delivery summary gate — every area in PDF §18 signed off | QA-02.02 | Do not ship Velzon demo tickets/KYC/ecommerce as product | Regression | QA | §18 | Summary of delivery | All features listed in this document are included in the delivery scope. | Programme | QA | Yes | No | No | No | No | No | P0 | S | QA-02.01 | T-275 (QA-02.01) | — |  | This register is the scope | Walk the coverage sheet; zero PDF rows with Status≠Done unless formally deferred with client sign | Coverage sheet 100% mapped; deferred items have written client sign | Not Started | QA
277 | 999 | QA | 19 | Phase 19 — Cross-surface QA, NFR, delivery summary gate (PDF §1 + §18) | 19.3 | NFR-01 | NFR — performance, low-data, reliability, secrets, dual-API freeze | NFR-01.02 | Performance: slot lock under concurrent public booking | Regression | NFR | §2.9 + §3 + §17 | Low-data mode / Reliability monitoring / Secure login | Works on slow connections; failures reported automatically; credentials protected | All | QA | No | Yes | No | No | No | No | P0 | M | NFR-01.01 | — | Web | NFR-01.01 | Known risks: plaintext passwords (fixed P0), secrets in appsettings, dual API drift | Rotate secrets; no new third API; patient low-data verified; doctor reliability SDK live | Load test on booking+webhook; secrets not in git; dual-API map documented | Not Started | QA
278 | 1000 | QA | 19 | Phase 19 — Cross-surface QA, NFR, delivery summary gate (PDF §1 + §18) | 19.3 | NFR-01 | NFR — performance, low-data, reliability, secrets, dual-API freeze | NFR-01.03 | Patient low-data mode QA on 2G profile | Regression | NFR | §2.9 + §3 + §17 | Low-data mode / Reliability monitoring / Secure login | Works on slow connections; failures reported automatically; credentials protected | All | QA | No | No | No | No | Yes | No | P0 | S | NFR-01.02 | T-277 (NFR-01.02) | Web |  | Known risks: plaintext passwords (fixed P0), secrets in appsettings, dual API drift | Rotate secrets; no new third API; patient low-data verified; doctor reliability SDK live | Load test on booking+webhook; secrets not in git; dual-API map documented | Not Started | QA

## 05_Web_Main_Tasks
Web MAIN TASKS — execute sub-tasks in Web Sequential sheet filtered by Main Task ID. Do not start a Main Task if Sister Tracks includes Web and those Web rows are not Done (API/DB first).
Seq | Phase | Phase Name | WBS | Main Task ID | Main Task | Work Type(s) | Module | PDF Section | PDF Feature | Surface | Sub-task count | First Track Seq | Last Track Seq | Sister Tracks | Priority (highest) | AS-IS | TO-BE | Status
1 | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.1 | PRE-01 | Decide settlement model — Homeocentrum holds all money (food-delivery / quick-commerce pattern) | Client Decision, Configuration | Finance | §9 + §8 | Every transaction passes through Homeocentrum | Account / Gateway | 3 | 1 | 3 | — | P0 | Only doctor SaaS subscription via client-side Razorpay; no consult/medicine ledger | Written decision: platform-held funds + periodic NEFT (v1) vs Razorpay Route (v2) | Not Started
2 | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.2 | PRE-02 | Decide reception cash policy — clinic retains vs remits to Homeocentrum | Client Decision, Configuration | Finance / Reception | §9 | Reception payment collection | Account / Reception | 3 | 4 | 6 | — | P0 | No reception collection; no S3 ledger | Policy for cash/UPI at clinic: retain at clinic (still ledgered) or remit | Not Started
3 | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.3 | PRE-03 | Vendor and legal gates — video SDK, SMS, WhatsApp, push, DPDP copy | Client Decision | Platform | §10 + §14 + §17 | Telemedicine + notifications + consent | Shared | 5 | 7 | 11 | — | P0 | WhatsApp Meta Cloud partial; no video SDK; no SMS provider; no FCM; privacy/terms incomplete for DPDP/tele/pharmacy | Named vendors + DPDP-ready legal copy before those phases start | Not Started
4 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.1 | FND-01 | One connected ecosystem — shared keys so a patient, appointment, prescription and payment created anywhere are visible everywhere | New, Existing Modification | Platform | §1 | One connected ecosystem serving six types of users | Shared | 3 | 12 | 14 | QA | P0 | Doctor/Admin/Reception web only; Patient, Account, Pharmacy roles do not exist; no shared payment or eRx keys | Canonical keys: UserId/DoctorId, PatientId, PatientAppId, CaseId, ErxId, LedgerTxnId, MedicineOrderId — used by every surface | Not Started
5 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.2 | FND-02 | Delivery footprint — 2 mobile apps · 5 web portals · payment · telemedicine · digital prescription · HomeoMeds (programme skeleton) | New | Platform | §1 | Delivery covers | Shared | 1 | 15 | 15 | UI, Mobile | P0 | 1 web SPA (Admin/Doctor/Reception + marketing). No patient app, doctor app, Account portal, Pharmacy console | Repo/route skeleton: Patient Website, Doctor Web, Reception, Admin, Account (+ Pharmacy console under HomeoMeds); Patient + Doctor mobile later | Not Started
6 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.3 | SEC-01 | Secure login — protected credentials for every user type | Data Migration, Existing Modification | Security | §17 | Secure login | All web + later mobile | 2 | 16 | 17 | UI, QA | P0 | POST /Account/Login on classic API; JWT in sessionStorage; doctor/user passwords compared plaintext; reception hashed on classic; fakeBackend() still mounted | Hashed passwords; Role claim on JWT; disable fake backend for production paths; Patient OTP login is Phase 8 (not password) | Not Started
7 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.4 | SEC-02 | Secure password reset — time-limited reset links (stop plaintext email + fake thunk) | New, Existing Modification | Security | §17 | Secure password reset | Admin / Doctor / Reception web | 2 | 18 | 19 | UI, QA | P0 | /forgot-password UI exists; thunk uses fake/Firebase; POST /users/ForgetPassword emails plaintext password | Tokenised reset (hash, TTL); email contains link only; ChangePassword for logged-in user | Not Started
8 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.5 | SEC-03 | Session control — proper sign-out across web and mobile | Existing Improvement, New | Security | §17 | Session control | All | 2 | 20 | 21 | UI, QA | P0 | Client clears sessionStorage; no server logout / token revoke; UserLoginStatus unused | POST Logout persists login status; optional token denylist; mobile will call the same API in Phase 16/17 | Not Started
9 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.6 | SEC-04 | Role-based access — each role sees only what it is permitted to see | Existing Improvement, New | Security | §17 | Role-based access | Admin / All web | 2 | 22 | 23 | UI, QA | P0 | RoleMaster + RoleDetail + MenuMaster exist; GetMenuByRole commented out on .NET 8; no per-route frontend ACL — any authenticated URL works | Re-enable GetMenuByRole; AuthProtected deny-by-default; [Authorize(Roles=)] on money/clinical APIs; Account cannot edit repertory; Admin cannot approve payouts | Not Started
10 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.7 | SEC-05 | Patient data protection — health records restricted to the treating doctor and the patient | Existing Improvement, Existing Modification | Security | §17 | Patient data protection | API | 2 | 24 | 25 | QA | P0 | Many repertory APIs have [Authorize] commented; directory browsing enabled for /attachments and /Blogs; no patient-scoped ACL on case data | Every case/Rx/note/lab query filtered by treating DoctorId (or PatientId for patient token); disable directory browsing | Not Started
11 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.8 | SEC-06 | Consent records infrastructure — every consent captured, stored and reviewable | New, Existing Improvement | Security / Trust | §17 | Consent records | Shared | 3 | 26 | 28 | QA | P0 | AudioCaseConsentLog exists for audio case taking only | ConsentRecord (PatientId, Type, Version, GrantedAt, WithdrawnAt, SourceSurface) covering privacy, booking, recording, pharmacy share, marketing | Not Started
12 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.9 | SEC-07 | OTP verification infrastructure — applied to sensitive actions including payouts and pharmacy acceptance | New | Security | §17 + §8 + §12 | OTP verification | Shared | 3 | 29 | 31 | QA | P0 | No generic OTP control plane; patient OTP login does not exist | OtpChallenge + OtpAuditLog; Account/Admin can query who/when/entity/success without seeing card data | Not Started
13 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.10 | SEC-08 | Complete audit trail — who did what and when across payments, prescriptions and approvals | New | Security | §17 + §9 | Complete audit trail | Shared | 2 | 32 | 33 | QA | P0 | No platform-wide audit; no AppointmentChangeLog; no payment webhook store | Append-only AuditEvent for money, eRx sign, credentialing, payout, pharmacy accept; payments get a dedicated trail in Phase 6 | Not Started
14 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.11 | SEC-09 | Secure documents — prescriptions, reports and uploads protected from unauthorised access | New | Security | §17 | Secure documents | Shared | 2 | 34 | 35 | QA | P1 | Attachments served with directory browsing; no signed URLs; no patient upload module | Authorised download; virus-scan hook; patient uploads in Phase 15 use this store | Not Started
15 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.1 | ADM-R01 | Keep and harden Admin Repertory sections (do not rebuild) | Existing Improvement, Existing | Repertory | §7.1 | Repertory sections | Admin Portal | 2 | 36 | 37 | QA | P2 | Admin Repertory section CRUD live (pages/Admin/Repertory) | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
16 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.2 | ADM-R02 | Keep and harden Admin Subsection & rubric tree (do not rebuild) | Existing Improvement, Existing | Repertory | §7.1 | Subsection & rubric tree | Admin Portal | 2 | 38 | 39 | QA | P2 | Hierarchical subsection/rubric tree + Excel import/export live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
17 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.3 | ADM-R03 | Keep and harden Admin Rubric–remedy mapping (do not rebuild) | Existing Improvement, Existing | Repertory | §7.1 | Rubric–remedy mapping | Admin Portal | 2 | 40 | 41 | QA | P2 | Rubric-remedy mapping by author/grade live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
18 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.4 | ADM-R04 | Keep and harden Admin Remedy-linked rubrics (do not rebuild) | Existing Improvement, Existing | Repertory | §7.1 | Remedy-linked rubrics | Admin Portal | 2 | 42 | 43 | QA | P2 | Remedial-rubrics viewer live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
19 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.5 | ADM-R05 | Keep and harden Admin Language master (do not rebuild) | Existing Improvement, Existing | Repertory | §7.1 | Language master | Admin Portal | 2 | 44 | 45 | QA | P2 | Language master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
20 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.6 | ADM-R06 | Keep and harden Admin Body part master (do not rebuild) | Existing Improvement, Existing | Repertory | §7.1 | Body part master | Admin Portal | 2 | 46 | 47 | QA | P2 | Body part master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
21 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.7 | ADM-R07 | Keep and harden Admin Intensity master (do not rebuild) | Existing Improvement, Existing | Repertory | §7.1 | Intensity master | Admin Portal | 2 | 48 | 49 | QA | P2 | Intensity master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
22 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.8 | ADM-R08 | Keep and harden Admin Remedy master (do not rebuild) | Existing Improvement, Existing | Repertory | §7.1 | Remedy master | Admin Portal | 2 | 50 | 51 | QA | P2 | Remedy master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
23 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.9 | ADM-R09 | Keep and harden Admin Remedy grade master (do not rebuild) | Existing Improvement, Existing | Repertory | §7.1 | Remedy grade master | Admin Portal | 2 | 52 | 53 | QA | P2 | Remedy grade master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
24 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.10 | ADM-M01 | Keep and harden Admin Author master (do not rebuild) | Existing Improvement, Existing | Materia Medica | §7.1 | Author master | Admin Portal | 2 | 54 | 55 | QA | P2 | Author master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
25 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.11 | ADM-M02 | Keep and harden Admin Materia medica master (do not rebuild) | Existing Improvement, Existing | Materia Medica | §7.1 | Materia medica master | Admin Portal | 2 | 56 | 57 | QA | P2 | MM master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
26 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.12 | ADM-M03 | Keep and harden Admin Materia medica heads (do not rebuild) | Existing Improvement, Existing | Materia Medica | §7.1 | Materia medica heads | Admin Portal | 2 | 58 | 59 | QA | P2 | MM heads live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
27 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.13 | ADM-M04 | Keep and harden Admin Materia medica remedies (do not rebuild) | Existing Improvement, Existing | Materia Medica | §7.1 | Materia medica remedies | Admin Portal | 2 | 60 | 61 | QA | P2 | Remedy-wise MM viewer live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
28 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.14 | ADM-D01 | Keep and harden Admin Diagnosis system (do not rebuild) | Existing Improvement, Existing | Diagnosis | §7.1 | Diagnosis system | Admin Portal | 2 | 62 | 63 | QA | P2 | Diagnosis system CRUD live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
29 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.15 | ADM-D02 | Keep and harden Admin Diagnosis therapeutics (do not rebuild) | Existing Improvement, Existing | Diagnosis | §7.1 | Diagnosis therapeutics | Admin Portal | 2 | 64 | 65 | QA | P2 | Therapeutics details live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
30 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.16 | ADM-D03 | Keep and harden Admin Diagnosis conditions (do not rebuild) | Existing Improvement, Existing | Diagnosis | §7.1 | Diagnosis conditions | Admin Portal | 2 | 66 | 67 | QA | P2 | Conditions + keyword→rubric live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
31 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.17 | ADM-A01 | Keep and harden Admin Drug system (do not rebuild) | Existing Improvement, Existing | Adverse Effect | §7.1 | Drug system | Admin Portal | 2 | 68 | 69 | QA | P2 | Drug system CRUD live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
32 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.18 | ADM-A02 | Keep and harden Admin Drug group (do not rebuild) | Existing Improvement, Existing | Adverse Effect | §7.1 | Drug group | Admin Portal | 2 | 70 | 71 | QA | P2 | Drug group CRUD live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
33 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.19 | ADM-A03 | Keep and harden Admin Allopathic drug & side effects (do not rebuild) | Existing Improvement, Existing | Adverse Effect | §7.1 | Allopathic drug & side effects | Admin Portal | 2 | 72 | 73 | QA | P2 | Allopathic drug + serious/other/adverse live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
34 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.20 | ADM-Q01 | Keep and harden Admin Question section, group & sub-group (do not rebuild) | Existing Improvement, Existing | Clinical Questions | §7.1 | Question section, group & sub-group | Admin Portal | 2 | 74 | 75 | QA | P2 | Existance / question group / subgroup CRUD live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
35 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.21 | ADM-Q02 | Keep and harden Admin Clinical question mapping (do not rebuild) | Existing Improvement, Existing | Clinical Questions | §7.1 | Clinical question mapping | Admin Portal | 2 | 76 | 77 | QA | P2 | Clinical questions mapped to body parts and rubrics live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
36 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.22 | ADM-3D1 | Keep and harden Admin 3D mesh key master (do not rebuild) | Existing Improvement, Existing | 3D Body | §7.1 | 3D mesh key master | Admin Portal | 2 | 78 | 79 | QA | P2 | Mesh key master on .NET 8 live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
37 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.23 | ADM-3D2 | Keep and harden Admin 3D section master (do not rebuild) | Existing Improvement, Existing | 3D Body | §7.1 | 3D section master | Admin Portal | 2 | 80 | 81 | QA | P2 | 3D section master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
38 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.24 | ADM-3D3 | Keep and harden Admin 3D hotspots (do not rebuild) | Existing Improvement, Existing | 3D Body | §7.1 | 3D hotspots | Admin Portal | 2 | 82 | 83 | QA | P2 | Hotspot master live; doctor viewer consumes them | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
39 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.25 | ADM-B01 | Business Management — Doctor qualifications (existing, used later by credentialing) | Existing Improvement, Existing | Business Management | §7.2 | Doctor qualifications | Admin Portal | 2 | 84 | 85 | QA | P2 | Qualifications CRUD on newer API live; used by RegisterDoctor | Keep; credentialing Phase 8 will reference QualificationId | Not Started
40 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.26 | ADM-B02 | Business Management — Lab & imaging test catalog (existing, used by eRx lab orders) | Existing Improvement, Existing | Business Management | §7.2 | Lab & imaging test catalog | Admin Portal | 2 | 86 | 87 | QA | P2 | Labs & imaging CRUD live; Patient Board orders from this catalogue | Keep; eRx Phase 10 continues to use the same catalogue | Not Started
41 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.27 | ADM-B03 | Business Management — Subscription packages (existing S1 SaaS; later tied to Account ledger) | Existing Improvement, Existing | Business Management | §7.2 | Subscription packages | Admin Portal | 2 | 88 | 89 | QA | P2 | Package CRUD live; Razorpay buy/renew partial (no webhook) | Do not overload PackageEntryDetail for consult/medicine money; Phase 6 ports payment verification | Not Started
42 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.28 | ADM-B04 | Business Management — Roles & menu permissions (existing DB, runtime ACL leftover) | Existing Improvement | Business Management | §7.2 | Roles & menu permissions | Admin Portal | 2 | 90 | 91 | UI, QA | P1 | Role CRUD screens live; runtime GetMenuByRole commented; no frontend route ACL | This is the product surface for SEC-04; complete wiring here | Not Started
43 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.1 | CLN-01 | Clinical workspace — single screen for the entire consultation | Existing | Patient Board | §5.3 | Clinical workspace | Doctor Web Portal | 1 | 92 | 92 | UI, QA | P1 | PatientBoard.js (~13.5k) is the workspace; ~90% — missing payment/tele/eRx header status | Keep one screen; add header chips for payment, tele session, signed eRx (chips light up as later phases land) | Not Started
44 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.2 | CLN-02 | Manual case taking — structured case taking (keep) | Existing Improvement, Existing | Patient Board | §5.3 | Manual case taking | Doctor Web Portal | 2 | 93 | 94 | QA | P2 | Classic case-taking tabs live | Regression only; do not rebuild | Not Started
45 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.3 | CLN-03 | Body parts & intensity selection (keep) | Existing Improvement, Existing | Patient Board | §5.3 | Body parts & intensity selection | Doctor Web Portal | 2 | 95 | 96 | QA | P2 | Body Parts tab + intensity chips live | Regression; intensity master from Phase 1 still drives chips | Not Started
46 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.4 | CLN-04 | Clinical questions — guided questions by section, group and sub-group (keep) | Existing Improvement, Existing | Patient Board | §5.3 | Clinical questions | Doctor Web Portal | 2 | 97 | 98 | QA | P2 | Questions tab loads Existance taxonomy live | Regression | Not Started
47 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.5 | CLN-05 | Diagnosis, therapeutics & pattern search (keep) | Existing Improvement, Existing | Patient Board | §5.3 | Diagnosis, therapeutics & pattern search | Doctor Web Portal | 2 | 99 | 100 | QA | P2 | Clinical Pattern tab live (13 keyword tabs + therapeutics) | Regression | Not Started
48 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.6 | CLN-06 | Repertory rubric search & selection (keep) | Existing Improvement, Existing | Patient Board | §5.3 | Repertory rubric search & selection | Doctor Web Portal | 2 | 101 | 102 | QA | P2 | Repertory tree + search live | Regression; small UX polish allowed but not a rewrite | Not Started
49 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.7 | CLN-07 | Manage selected rubrics — review, edit and remove (remaining ~10%) | Existing Improvement | Patient Board | §5.3 | Manage selected rubrics | Doctor Web Portal | 2 | 103 | 104 | UI, QA | P1 | Clipboard exists; confirm-delete / intensity-edit incomplete | Confirm delete; edit intensity on selected rubric; no accidental wipe | Not Started
50 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.8 | CLN-08 | Audio case taking — record and receive suggested rubrics (keep engine; do not rebuild) | Existing Improvement, Existing | Audio AI | §5.3 | Audio case taking | Doctor Web Portal | 2 | 105 | 106 | QA | P1 | Whisper + rubric engines + CaseTaking UI live on .NET 8 | Keep; follow existing AUDIO_CASE_TAKING_* docs; accuracy is the next task | Not Started
51 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.9 | CLN-09 | Improved rubric accuracy — enhanced accuracy rules for audio-based rubric suggestions | Existing Improvement | Audio AI | §5.3 | Improved rubric accuracy | Doctor Web Portal + Admin intelligence | 1 | 107 | 107 | UI, QA | P1 | Engine + admin metaphors/aliases exist; accuracy rules still in progress (~50%) | Complete accuracy rules per AUDIO_CASE_TAKING_AI_ENGINE docs; metaphor/alias QA | Not Started
52 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.10 | CLN-10 | Materia medica reference during consultation (remaining ~10%) | Existing Improvement | Patient Board | §5.3 | Materia medica reference | Doctor Web Portal | 2 | 108 | 109 | UI, QA | P2 | MM tab + repertorize differential accordion ~90% | Faster head navigation during case; do not rebuild MM masters | Not Started
53 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.11 | CLN-11 | Allopathic drug side-effect lookup (keep) | Existing Improvement, Existing | Patient Board | §5.3 | Allopathic drug side-effect lookup | Doctor Web Portal | 2 | 110 | 111 | QA | P2 | Adverse Effect tab live | Regression | Not Started
54 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.12 | CLN-12 | Repertorization & elimination (remaining ~10%) | Existing Improvement | Patient Board | §5.3 | Repertorization & elimination | Doctor Web Portal | 2 | 112 | 113 | UI, QA | P1 | Common/uncommon/elimination live ~90% | Stability polish; Center of Gravity is a NEW panel on the same rubrics (next task) | Not Started
55 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.13 | CLN-13 | Center of Gravity — new analysis identifying the central remedy of the case, with reasoning shown | New | Repertorization | §5.3 | Center of Gravity | Doctor Web Portal | 2 | 114 | 115 | UI, QA | P1 | Does not exist | POST /api/Repertorization/CenterOfGravity from selected rubric ids + intensities; UI panel with explainability | Not Started
56 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.14 | CLN-14 | Lab orders & lab entries (keep; later also sit on eRx) | Existing Improvement, Existing | Patient Board | §5.3 + §11 | Lab orders & lab entries | Doctor Web Portal | 2 | 116 | 117 | QA | P2 | Lab order + result entry on prescription modal live | Keep; when eRx splits notes from Rx, labs stay on the prescription/eRx side | Not Started
57 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.15 | CLN-15 | Appointment history notes (keep; split from eRx in Phase 10) | Existing Improvement, Existing | Patient Board | §5.3 | Appointment history notes | Doctor Web Portal | 2 | 118 | 119 | QA | P1 | AppointmentHistoryNote APIs live (classic); currently mixed into Rx modal tabs | Keep save/get; Phase 10 moves UX outside Rx modal and adds NoteType / IsErxExcluded | Not Started
58 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.16 | CLN-16 | Complaints & case details — wire Patient Board to existing SaveComplaints / SaveCaseDetails (~20% today) | Existing Improvement | Patient Board | §5.3 | Complaints & case details | Doctor Web Portal | 2 | 120 | 121 | UI, QA | P1 | Classic SaveComplaints / SaveCaseDetails APIs exist; Patient Board does not call them | Call the existing APIs from the board; Reception case-paper (Phase 5) uses a subset | Not Started
59 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.17 | CLN-17 | Patient back history — complete history of visits, notes, prescriptions and payments | Existing Improvement | Patient Board | §5.3 | Patient back history | Doctor Web Portal | 2 | 122 | 123 | UI, QA | P1 | History panel ~70%; no payment line (payments do not exist yet) | Timeline: visits, notes, eRx, labs; payment row added when Phase 6 lands (placeholder now) | Not Started
60 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.18 | CLN-18 | Export case data — download the full case in Excel or PDF | Existing Improvement | Patient Board | §5.3 | Export case data | Doctor Web Portal | 1 | 124 | 124 | UI, QA | P1 | Newer ExportCasesToExcel exists; no Patient Board export UI; no PDF | Toolbar Excel + PDF using existing Excel API + new PDF renderer; exclude private notes from patient-facing PDF (eRx print is Phase 10) | Not Started
61 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.19 | CLN-19 | Session restore — continue exactly where the doctor left off, across multiple patients (keep) | Existing Improvement, Existing | Patient Board | §5.3 | Session restore | Doctor Web Portal | 2 | 125 | 126 | QA | P2 | Up to 5 in-memory sessions + DoctorPatientBoardBackup live | Regression; header stack remains | Not Started
62 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.20 | CLN-20 | 3D anatomy viewer — interactive 3D body model linked to rubric search (remaining ~50%) | Existing Improvement | Anatomy | §5.3 | 3D anatomy viewer | Doctor Web Portal | 2 | 127 | 128 | UI, QA | P2 | three.js viewer + hotspot→search live; incomplete mesh coverage / UX | Complete GLB/hotspot coverage; mobile fallback later; admin 3D masters already in Phase 1 | Not Started
63 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.1 | DOC-01 | Doctor home dashboard — complete overview of the working day (remaining ~30%) | Existing Improvement | Doctor Dashboard | §5.1 | Doctor home dashboard | Doctor Web Portal | 2 | 129 | 130 | UI, QA | P1 | Widgets + BestSellingProducts ~70%; missing online toggle, tele queue, payment badges, follow-up due | Extend, do not replace; later phases light up tele/payment chips | Not Started
64 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.2 | DOC-02 | Patient counts & waiting list — live counts by status with quick actions (keep; extend paid/unpaid) | Existing Improvement, Existing | Doctor Dashboard | §5.1 | Patient counts & waiting list | Doctor Web Portal | 2 | 131 | 132 | QA | P1 | Status buckets WAITING, WALK-IN, NOT ARRIVED, E-CONSULT, REMAINING, COMPLETED live | Keep; add CANCELLED in Phase 4; paid/unpaid badge in Phase 6 | Not Started
65 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.3 | DOC-03 | Patient search, list & open case (remaining ~10%) | Existing Improvement | Doctor Dashboard | §5.1 | Patient search, list & open case | Doctor Web Portal | 2 | 133 | 134 | UI, QA | P1 | Search/list/open ~90%; missing last visit, unpaid, family filters | Add last-visit column; unpaid/family after those modules exist | Not Started
66 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.4 | DOC-04 | Add new patient — register a patient in seconds (keep) | Existing Improvement, Existing | Patients | §5.1 | Add new patient | Doctor Web Portal | 2 | 135 | 136 | QA | P1 | Create patient live | Regression; public self-registration is a different Patient identity in Phase 9 | Not Started
67 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.5 | DOC-05 | Import patients — bring existing patient records in bulk (keep) | Existing Improvement, Existing | Patients | §5.1 | Import patients | Doctor Web Portal | 2 | 137 | 138 | QA | P2 | Import live | Regression | Not Started
68 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.6 | DOC-06 | Export patients — download patient data in Excel, CSV or PDF (keep) | Existing Improvement | Patients | §5.1 | Export patients | Doctor Web Portal | 1 | 139 | 139 | UI, QA | P2 | Export live (confirm PDF vs Excel/CSV in QA) | If PDF is missing, add it as Existing Improvement; do not skip the PDF wording in the PDF | Not Started
69 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.7 | DOC-07 | Recent activity panel (keep) | Existing Improvement, Existing | Doctor Dashboard | §5.1 | Recent activity panel | Doctor Web Portal | 2 | 140 | 141 | QA | P2 | Recent activity live | Regression; later include payment/tele events when those exist | Not Started
70 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.8 | DOC-08 | Patient statistics charts (keep; foundation for clinic performance in Phase 18) | Existing Improvement, Existing | Doctor Dashboard | §5.1 | Patient statistics charts | Doctor Web Portal | 2 | 142 | 143 | QA | P2 | GetPatientStats / GetPatientStatsCharts + ApexCharts live | Keep; clinic performance report extends this in Phase 18 | Not Started
71 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.9 | DOC-09 | Manage reception staff — add, edit and remove reception users (backend done, UI absent) | Existing Improvement | Staff | §5.1 | Manage reception staff | Doctor Web Portal | 1 | 144 | 144 | UI, QA | P1 | .NET 8 api/ReceptionStaff CRUD exists; no SPA page | List/add/edit/disable at /doctor/reception-staff; doctor owns the staff record | Not Started
72 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.10 | DOC-10 | Doctor profile — clinic details, consultation fee, photo, qualifications, working hours, bank details | Existing Improvement | Doctor Profile | §5.1 | Doctor profile | Doctor Web Portal | 2 | 145 | 146 | UI, QA | P0 | /profile is Velzon first_name only (~20%); credentials sit on Doctor entity; no fee/KYC UI | Real doctor profile: clinic, photo, qualifications, consult fee (feeds Phase 6), hours (feeds schedule), bank KYC (feeds Account payees) | Not Started
73 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.1 | APT-01 | Appointment list & waiting patients — full day view with live status (keep; later payment/tele) | Existing Improvement, Existing | Appointments | §5.2 | Appointment list & waiting patients | Doctor Web Portal | 2 | 147 | 148 | QA | P1 | Day list + status live | Keep; reschedule/cancel/payment attach to this list | Not Started
74 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.2 | APT-02 | Create new appointment — persist visit type, consultation mode and fee | Existing Improvement | Appointments | §5.2 | Create new appointment | Doctor Web Portal | 2 | 149 | 150 | UI, QA | P0 | Create appointment ~90%; Formik modal has no VisitType / ConsultMode / fee | VisitType First/Follow-up; ConsultMode In-clinic / E-Consult; fee display from doctor profile / ConsultFeeConfig | Not Started
75 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.3 | APT-03 | Appointment status update — move patients through the visit stages (keep) | Existing Improvement, Existing | Appointments | §5.2 | Appointment status update | Doctor Web Portal | 2 | 151 | 152 | QA | P1 | Status transitions live | Keep; add CANCELLED in APT-06; do not reuse DeleteStatus as cancel | Not Started
76 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.4 | APT-04 | Appointment time update — adjust timings as the day runs (keep; distinct from formal reschedule) | Existing Improvement, Existing | Appointments | §5.2 | Appointment time update | Doctor Web Portal | 2 | 153 | 154 | QA | P1 | UpdateAppointmentTime live — changes a time only; no audit/notify | Keep same-day time tweak; formal reschedule (old→new, notify, conflict) is APT-05 | Not Started
77 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.5 | APT-05 | Reschedule appointment — move to a new slot with automatic patient notification (NEW — not a rename of UpdateAppointmentTime) | New, New Integration | Appointments | §5.2 + §2.3 + §6 | Reschedule appointment | Doctor Web + Reception + later Patient | 3 | 155 | 157 | UI, QA | P0 | Time can be edited; no formal Reschedule (audit, notify, old→new confirm) | POST RescheduleAppointment; AppointmentChangeLog; conflict 409 with alternatives; SMS/WhatsApp fan-out (notify failure must not roll back) | Not Started
78 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.6 | APT-06 | Cancel appointment — reason, free the slot, trigger refund where applicable (NEW CANCELLED status — do NOT reuse DeleteStatus) | New, New Integration | Appointments | §5.2 + §2.3 + §6 | Cancel appointment | Doctor Web + Reception + later Patient | 3 | 158 | 160 | UI, QA | P0 | No CANCELLED; DeleteStatus is soft-delete only | CANCELLED + reason fields; free slot; waitlist hook; if PAID evaluate refund policy (Phase 6/7) | Not Started
79 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.7 | APT-07 | Daily schedule setup — define working days, hours and break times (promote modal to first-class screen) | Existing Improvement | Scheduling | §5.2 | Daily schedule setup | Doctor Web Portal | 1 | 161 | 161 | UI, QA | P0 | DailyScheduleSetupModal + GetDailySchedule / SaveDailySchedule exist; not a first-class screen (draft marked 0%) | Promote to /doctor/schedule with week grid and copy-day; reuse existing APIs — do not rebuild | Not Started
80 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.8 | APT-08 | Appointment slot grid — visual slot-by-slot view of the day (keep; public booking reuses this) | Existing Improvement, Existing | Scheduling | §5.2 | Appointment slot grid | Doctor Web Portal | 2 | 162 | 163 | QA | P0 | Slot picker / grid live | Keep; Phase 9 public APIs reuse the same slot engine | Not Started
81 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.9 | APT-09 | Consultation payment status on every appointment (schema now; values live in Phase 6) | New | Appointments | §5.2 + §9 | Consultation payment status | Doctor Web Portal | 2 | 164 | 165 | UI, QA | P0 | No PaymentStatus on appointment | Add PaymentStatus UNPAID / PENDING / PAID / FAILED / PAY_AT_CLINIC / REFUNDED; UI badge; source of truth is webhook in Phase 6 not the client screen | Not Started
82 | 5 | Phase 5 — Reception portal (PDF §6) | 5.1 | REC-01 | Reception login — secure staff access (keep) | Existing Improvement, Existing | Reception | §6 | Reception login | Reception Portal | 2 | 166 | 167 | QA | P1 | Reception logs in via Account; JWT includes DoctorID; uses doctor dashboard layout | Keep login; Phase 0 hashing applies; later dedicated reception chrome | Not Started
83 | 5 | Phase 5 — Reception portal (PDF §6) | 5.2 | REC-02 | Reception profile — manage own profile details (0% today) | New | Reception | §6 | Reception profile | Reception Portal | 2 | 168 | 169 | UI, QA | P1 | No reception-specific profile; shared Velzon /profile | Name, mobile, attached doctor (read-only); cannot edit doctor bank/fee | Not Started
84 | 5 | Phase 5 — Reception portal (PDF §6) | 5.4 | REC-04 | Create patient — register a walk-in patient quickly (keep) | Existing Improvement, Existing | Reception | §6 | Create patient | Reception Portal | 2 | 170 | 171 | QA | P1 | Create patient live on shared dashboard | Keep on reception chrome | Not Started
85 | 5 | Phase 5 — Reception portal (PDF §6) | 5.5 | REC-05 | Patient search & list — find any patient instantly (keep) | Existing Improvement, Existing | Reception | §6 | Patient search & list | Reception Portal | 2 | 172 | 173 | QA | P1 | Search live | Keep; no opening full clinical board | Not Started
86 | 5 | Phase 5 — Reception portal (PDF §6) | 5.6 | REC-06 | Create & manage appointments — full appointment management (keep; plus reschedule/cancel from Phase 4) | New | Reception | §6 | Create & manage appointments | Reception Portal | 1 | 174 | 174 | UI, QA | P0 | Create/status/time live; reschedule/cancel missing until Phase 4 APIs | Enable RescheduleAppointment and CancelAppointment for JWT DoctorId; isReceptionUser must not block | Not Started
87 | 5 | Phase 5 — Reception portal (PDF §6) | 5.8 | REC-08 | Waiting queue management — manage the live queue and call the next patient | Existing Improvement | Reception | §6 | Waiting queue management | Reception Portal | 2 | 175 | 176 | UI, QA | P1 | Status buckets ~60%; no dedicated queue UX / call-next | Dedicated queue: walk-in vs tele; payment state; Call next; notify patient (later push) | Not Started
88 | 5 | Phase 5 — Reception portal (PDF §6) | 5.9 | REC-09 | Appointment status update (reception) — update as patients arrive and are seen (keep) | Existing Improvement, Existing | Reception | §6 | Appointment status update | Reception Portal | 2 | 177 | 178 | QA | P1 | Status update live | Keep on reception chrome | Not Started
89 | 5 | Phase 5 — Reception portal (PDF §6) | 5.10 | REC-10 | Appointment time update (reception) — adjust timings through the day (keep) | Existing Improvement, Existing | Reception | §6 | Appointment time update | Reception Portal | 2 | 179 | 180 | QA | P2 | Time update live | Keep; formal reschedule remains REC-06 | Not Started
90 | 5 | Phase 5 — Reception portal (PDF §6) | 5.12 | REC-12 | Log case paper / chief complaint — record the reason for visit before the consultation | New | Reception | §6 | Log case paper / chief complaint | Reception Portal | 2 | 181 | 182 | UI, QA | P1 | Missing; SaveComplaints exists but board is doctor-only | Restricted case-paper form (chief complaint only — no repertory/Rx); audit reception author | Not Started
91 | 5 | Phase 5 — Reception portal (PDF §6) | 5.13 | REC-13 | Collect consultation payment — cash, UPI, card or payment link and issue a receipt (API in Phase 6; UI shell now) | New | Reception | §6 + §9 | Collect consultation payment | Reception Portal | 1 | 183 | 183 | UI | P0 | Does not exist | UI modal ready; CollectAtReception API lands with payment spine in Phase 6 — do not fake a paid status here | Not Started
92 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.1 | PAY-01 | Consultation fee configuration — each doctor’s fee set and displayed to patients | New | Payments | §9 | Consultation fee configuration | Doctor profile + Public + Admin | 2 | 184 | 185 | UI, QA | P0 | No ConsultFeeConfig; doctor profile work in DOC-10 may have stored a fee field | ConsultFeeConfig (InClinic, EConsult, optional Instant surcharge, PayAtClinicEnabled, GST flags) | Not Started
93 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.2 | PAY-02 | Automatic payment verification — bank/webhook is source of truth, not the patient’s screen | New, New Integration | Payments | §9 | Automatic payment verification | Shared | 3 | 186 | 188 | QA | P0 | Razorpay checkout for S1 subscription only; no webhook; no signature verify on server | Port Razorpay to .NET 8; keys in config; POST /api/Payments/Webhook/Razorpay anonymous + signature verify; PaymentOrder table | Not Started
94 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.3 | PAY-03 | Online consultation payment — patient pays by card, UPI, netbanking or wallet | New, New Integration | Payments | §9 + §4 + §2.3 | Online consultation payment | Public web + later Patient app | 3 | 189 | 191 | UI, QA | P0 | Does not exist (only S1 SaaS) | CreateConsultOrder attached to PatientAppId; Razorpay Checkout; webhook sets PAID; do not overload PackageEntryDetail | Not Started
95 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.4 | PAY-04 | Reception payment collection — cash, UPI, card or payment link with printed receipt | New, New Integration | Payments | §9 + §6 | Reception payment collection | Reception Portal | 3 | 192 | 194 | UI, QA | P0 | Does not exist | CollectAtReception writes ledger S3; print receipt; payment-link uses same Razorpay order as online | Not Started
96 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.5 | PAY-05 | Pay-at-clinic option — book now, pay at the clinic where the doctor allows it | New | Payments | §9 | Pay-at-clinic option | Public + Doctor + Reception | 1 | 195 | 195 | UI, QA | P1 | Does not exist | PayAtClinicEnabled on fee config; appointment PaymentStatus=PAY_AT_CLINIC; tele queue may still require PAID (policy) | Not Started
97 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.6 | PAY-06 | Doctor subscription payment — buy and renew subscription packages (complete remaining ~30%) | Existing Improvement | Payments | §9 | Doctor subscription payment | Doctor Web Portal | 1 | 196 | 196 | UI, QA | P1 | Checkout works ~70%; no webhook, refund, invoice, GST, Account ledger | Same webhook spine; write S1 ledger; invoice; failed pay UX; PackageEntryDetail shape UNCHANGED | Not Started
98 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.7 | PAY-07 | Medicine payment — pay online or cash on delivery (API contract now; HomeoMeds Phase 14 implements orders) | New | Payments | §9 + §12 | Medicine payment | Shared | 2 | 197 | 198 | QA | P1 | Does not exist | PaymentOrder.Stream=MEDICINE; COD_PENDING until pharmacy confirms collection; do not mix with consult money | Not Started
99 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.8 | PAY-08 | Payment status everywhere — doctor, reception and patient all see the same payment status | New | Payments | §9 | Payment status everywhere | All | 1 | 199 | 199 | UI, QA | P0 | No shared status | Single PaymentStatus on appointment/order; all DTOs read it; never a second client-only flag | Not Started
100 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.9 | PAY-09 | Refunds — processed and tracked against the original payment | New, New Integration | Payments | §9 + §8 + §2.8 | Refunds | Account + Patient | 3 | 200 | 202 | UI, QA | P0 | Does not exist | Refund entity against original PaymentOrder; Razorpay refund API; cancel-appointment hook; patient sees status | Not Started
101 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.10 | PAY-10 | Payment receipts & invoices — issued for every transaction | New | Payments | §9 + §8 | Payment receipts & invoices | All | 2 | 203 | 204 | UI, QA | P1 | No invoice entity | Invoice numbering series from PRE-02; PDF receipt; GST fields; email in Phase 12 | Not Started
102 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.11 | PAY-11 | Complete payment audit trail — every transaction traceable end to end by Homeocentrum | New | Payments | §9 + §17 | Complete audit trail | Account | 2 | 205 | 206 | QA | P0 | No webhook store | PaymentEvent raw payloads + AuditEvent + OtpAudit for payouts; Account can reconstruct without Razorpay dashboard | Not Started
103 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.1 | FIN-01 | Unified transaction ledger — every rupee that moves through the platform, in one record | New | Account | §8 | Unified transaction ledger | Account Portal | 2 | 207 | 208 | UI, QA | P0 | Does not exist | Append-only LedgerEntry for S1–S7; filters; OTP audit link; Admin may view, Account owns movement | Not Started
104 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.2 | FIN-02 | Consultation payment reconciliation — online payments and reception collections matched and verified | New | Account | §8 + §7.2 + §16 | Consultation payment reconciliation | Account + Admin | 2 | 209 | 210 | UI, QA | P0 | Does not exist | Join booking ↔ payment ↔ appointment; KPI collected/pending/failed/refunded; CSV | Not Started
105 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.3 | FIN-03 | Medicine ledger — medicine money tracked separately from consultation money | New | Account | §8 + §12 | Medicine ledger | Account Portal | 2 | 211 | 212 | UI, QA | P1 | Does not exist | /account/medicine-ledger; Stream=MEDICINE; seller/platform/delivery split columns; filled in Phase 14 | Not Started
106 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.4 | FIN-04 | Settlement runs — scheduled settlement of amounts due to doctors and pharmacies | New | Account | §8 + §16 | Settlement runs | Account Portal | 2 | 213 | 214 | UI, QA | P0 | Does not exist | SettlementRun job T+N hold; net of commission/GST/refunds; pharmacies after Phase 14 | Not Started
107 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.5 | FIN-05 | Payout approval — payouts released only after OTP-verified approval | New, New Integration | Account | §8 + §17 | Payout approval | Account Portal | 3 | 215 | 217 | UI, QA | P0 | Does not exist | ApprovePayout requires SEC-07 OTP; Admin cannot approve; NEFT/file or gateway per PRE-01 | Not Started
108 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.6 | FIN-06 | Refund processing — Account issues and tracks refunds (uses PAY-09) | New | Account | §8 | Refund processing | Account Portal | 1 | 218 | 218 | UI, QA | P0 | Does not exist | /account/refunds UI on PAY-09 APIs; OTP if policy requires | Not Started
109 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.7 | FIN-07 | Payment exception handling — investigate and resolve every failed or disputed payment | New | Account | §8 + §7.2 | Payment exception handling | Account + Admin | 2 | 219 | 220 | UI, QA | P0 | Does not exist | Exception queue Failed/Partial/Webhook-mismatch/Refund-pending; retry/resolve with OTP on manual reconcile | Not Started
110 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.8 | FIN-08 | GST & invoice reports — invoice numbering and tax reporting | New | Account | §8 + §16 | GST & invoice reports | Account Portal | 2 | 221 | 222 | UI, QA | P1 | Does not exist | /account/tax export using Invoice table and PRE-02 GST treatment — configuration not hardcoded | Not Started
111 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.9 | FIN-09 | Payee records — bank and KYC details for doctors and pharmacies | New | Account | §8 | Payee records | Account Portal | 2 | 223 | 224 | UI, QA | P1 | Doctor bank fields added in DOC-10; no Account UI; no pharmacy | /account/payees; OTP on doctor KYC change (fraud); pharmacies after Phase 14 | Not Started
112 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.10 | FIN-10 | Clinic collection view — cash and UPI collected at reception, per clinic and per day | New | Account | §8 | Clinic collection view | Account Portal | 2 | 225 | 226 | UI, QA | P1 | Does not exist | /account/clinic-collections from CollectAtReception rows; respect PRE-02 retain vs remit | Not Started
113 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.11 | FIN-11 | Separation of duties — Account controls money; Admin controls platform and clinical data | New | Account | §8 | Separation of duties | Admin + Account | 1 | 227 | 227 | QA | P0 | Account role does not exist | Enforce in RBAC: Admin cannot ApprovePayout; Account cannot edit repertory/users’ clinical masters | Not Started
114 | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.1 | TRU-01 | Doctor credentialing — doctors upload qualification and registration documents for review | New | Trust | §13 + §7.2 | Doctor credentialing | Doctor Web + Admin | 2 | 228 | 229 | UI, QA | P0 | RegisterDoctor activates immediately; PassingUniversity/CertNo/QualificationId exist; no document store/queue | DoctorCredentialDocument + VerificationStatus Pending; do not auto-activate practice for public directory | Not Started
115 | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.2 | TRU-02 | Verification review — Admin approves, rejects or requests further information | New, New Integration | Trust | §13 + §7.2 | Verification review | Admin Portal | 3 | 230 | 232 | UI, QA | P0 | Does not exist | /admin/doctor-credentialing list + detail; email notify doctor | Not Started
116 | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.3 | TRU-03 | Verified badge — patients see which doctors have been verified | New | Trust | §13 + §2.2 | Verified badge / Credentials & verification | Public + Patient app | 1 | 233 | 233 | UI, QA | P0 | Does not exist | Badge on public doctor card and profile from VerificationStatus=Approved | Not Started
117 | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.4 | TRU-04 | Practice gate — only verified doctors appear to patients and take paid consultations | New | Trust | §13 | Practice gate | Public + Payments | 2 | 234 | 235 | QA | P0 | Any activated doctor could theoretically be listed; no public list yet | Public search and CreateConsultOrder require Approved; own-clinic staff booking may still work per PRE-03 | Not Started
118 | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.5 | TRU-05 | Patient reviews — patients rate and review consultations | New | Trust | §13 + §2.8 | Patient reviews / Write a review | Patient + Public | 2 | 236 | 237 | UI, QA | P1 | Does not exist | Review linked to PatientAppId; one review per visit; moderation flag optional | Not Started
119 | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.6 | TRU-06 | Review appeal — doctors can appeal a review; patients manage reviews and raise an appeal | New | Trust | §13 + §2.8 | Review appeal / My reviews & appeal | Doctor + Patient + Admin | 2 | 238 | 239 | UI, QA | P2 | Does not exist | Appeal entity; admin resolves; patient my-reviews list | Not Started
120 | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.7 | TRU-07 | Ranking transparency — patients are shown why doctors are ranked as they are | New | Trust | §13 + §2.2 | Ranking transparency / Ranking explanation | Public + Patient app | 2 | 240 | 241 | UI, QA | P1 | Does not exist | Documented ranking factors (verified, availability, fee, reviews, experience) + explain API/UI | Not Started
121 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.1 | WEB-01 | Product home page — complete public website presenting the service | Existing Improvement | Patient Website | §4 | Product home page | Patient Website | 2 | 242 | 243 | UI, QA | P1 | HomeoJobLanding ~50%; Velzon leftovers; CTAs incomplete for book/trust/apps | Book CTA, verified doctors, consult+SaaS pricing teaser, app download placeholders | Not Started
122 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.3 | WEB-03 | Doctor discovery — browse and search verified doctors | New | Patient Website | §4 + §2.2 | Doctor discovery | Patient Website | 2 | 244 | 245 | UI, QA | P0 | Does not exist as a patient product (marketing only) | /book search: name, condition, category; filters availability, fee, experience, language, location | Not Started
123 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.4 | WEB-04 | Self-service booking — book an appointment online without calling the clinic | New | Patient Website | §4 + §2.3 | Self-service booking | Patient Website | 2 | 246 | 247 | UI, QA | P0 | Staff-only appointments | Funnel /book/:id/slots → review+consent → create Patient+Appointment; OTP; rate-limit; respect schedule + unpaid hold policy PRE-03 | Not Started
124 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.6 | WEB-06 | Contact & enquiry form — enquiries reach the admin team and are tracked | Existing Improvement | Patient Website | §4 + §15 | Contact & enquiry form | Patient Website + Admin | 2 | 248 | 249 | UI, QA | P1 | EnquiryDetail API exists; public form partial; admin inbox screen missing | Confirmation + enquiry id; /admin/enquiries inbox; optional convert to SupportTicket | Not Started
125 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.9 | WEB-09 | Doctor self-registration — doctors apply to join the platform online | Existing Improvement | Patient Website | §4 | Doctor self-registration | Public | 2 | 250 | 251 | UI, QA | P0 | RegisterDoctor ~90%; activates immediately; no document upload | Document upload; pending-verification message; TRU-01 status Pending | Not Started
126 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.10 | WEB-10 | Email activation — secure account activation by email link | Existing Improvement | Auth | §4 | Email activation | Public | 2 | 252 | 253 | UI, QA | P1 | ActivateUser via /login?UserId= ~90%; align with verification; expiry/resend incomplete | Token expiry, resend, align with credentialing (activation ≠ verified practice) | Not Started
127 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.11 | WEB-11 | Waitlist offer — get offered a slot when one is freed by a cancellation (patient website + later app) | New, New Integration | Booking | §2.3 | Waitlist offer | Patient Website + App | 3 | 254 | 256 | UI, QA | P2 | Cancel hook stub in Phase 4; no waitlist records | BookingWaitlist; on cancel, offer FIFO; timeout | Not Started
128 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.1 | ERX-01 | Potency module — every remedy carries a defined potency from a managed list, no free text | New | eRx | §11 | Potency module | Doctor Web + Admin | 2 | 257 | 258 | UI, QA | P0 | Dose saved as empty free-text dose: '' | PotencyMaster CRUD; PotencyId on PrescriptionRemedyDetail; stop empty Dose | Not Started
129 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.2 | ERX-02 | Dosage details — frequency, duration and instructions recorded clearly | New | eRx | §11 | Dosage details | Doctor Web Portal | 2 | 259 | 260 | UI, QA | P0 | Unstructured/empty dose | Frequency, Duration, Instructions fields on each remedy line | Not Started
130 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.3 | ERX-03 | Visit notes kept separate from the prescription — private clinical notes never appear on the prescription given to the patient or pharmacy | New | eRx | §11 + §5.3 | Visit notes kept separate from the prescription | Doctor Web Portal | 2 | 261 | 262 | UI, QA | P0 | History notes mixed into Rx modal tabs | Visit Notes panel outside Rx; NoteType; IsErxExcluded; eRx print has remedies+labs only | Not Started
131 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.4 | ERX-04 | Signed digital prescription — issued and locked once signed, so it cannot be altered afterwards | New | eRx | §11 + §2.5 + §5.3 | Signed digital prescription | Doctor Web | 2 | 263 | 264 | UI, QA | P0 | SavePrescriptionDetail overwritable; no lock/sign | ErxSnapshot immutable on sign; subsequent edits create a new unsigned draft not a silent mutate | Not Started
132 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.5 | ERX-05 | Prescription history — every prescription stored against the patient and visit | New | eRx | §11 | Prescription history | Doctor + Patient | 1 | 265 | 265 | UI, QA | P1 | Rx saved per appointment but no signed history product | List snapshots by PatientId; open past visit eRx | Not Started
133 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.6 | ERX-06 | Patient view of prescription in app — patient sees the prescription immediately (codes until pharmacy accept) | New | eRx | §11 + §2.5 | Patient view in app | Patient App + Website | 1 | 266 | 266 | UI, QA | P0 | No patient surface | Patient GET eRx by appointment; names redacted until Phase 14 accept; website optional view | Not Started
134 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.7 | ERX-07 | Print & PDF — printable and downloadable prescription | New | eRx | §11 | Print & PDF | Doctor + Patient | 1 | 267 | 267 | UI, QA | P1 | No eRx PDF | Patient copy without notes; doctor copy may include letterhead; SecureDocument store | Not Started
135 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.8 | ERX-08 | Remedy code protection — patient sees remedy codes rather than names until a licensed pharmacy accepts the order | New | eRx | §11 | Remedy code protection | Patient | 1 | 268 | 268 | QA | P0 | Does not exist | Code map on snapshot items; patient serializer strips names; doctor always sees names | Not Started
136 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.9 | ERX-09 | Reveal on pharmacy acceptance — names and price revealed; payment QR or link generated (implemented with HomeoMeds; contract now) | New | eRx | §11 + §12 | Reveal on pharmacy acceptance | Patient + Pharmacy | 2 | 269 | 270 | — | P0 | Does not exist | Flag PharmacyAccepted on order; patient GET starts returning names; CreateMedicine payment link; full UI in Phase 14 | Not Started
137 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.10 | ERX-10 | Repeat prescription / refill — patient requests; doctor approves or rejects from the mobile app (inbox on web too) | New | eRx | §11 + §3 + §2.7 | Repeat prescription / refill | Patient + Doctor mobile + Doctor web | 2 | 271 | 272 | UI, QA | P1 | Does not exist | RefillRequest against ErxSnapshot; doctor inbox; no case-taking on mobile | Not Started
138 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.11 | ERX-11 | Lab orders alongside the prescription (keep existing labs on eRx snapshot) | Existing Improvement | eRx | §11 | Lab orders | Doctor Web | 1 | 273 | 273 | QA | P1 | Labs on Rx modal live | Include lab orders in signed snapshot; still not on private notes | Not Started
139 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.1 | TEL-01 | Doctor availability — online or offline status and working hours | New | Telemedicine | §10 + §3 | Doctor availability | Doctor Web + Doctor App | 2 | 274 | 275 | UI, QA | P0 | E-CONSULT status + WhatsApp video stub only; no availability | TeleAvailability + heartbeat; working hours reuse daily schedule | Not Started
140 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.2 | TEL-02 | Telemedicine waiting queue — who is waiting, how long, whether they have paid | New, New Integration | Telemedicine | §10 + §3 | Telemedicine waiting queue | Doctor Web + App | 3 | 276 | 278 | UI, QA | P0 | E-CONSULT list only | Queue by doctor + Online + paid/confirmed; wait time; Join | Not Started
141 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.3 | TEL-03 | Video consultation in browser — doctor consults directly from the web portal | New, New Integration | Telemedicine | §10 | Video consultation in browser | Doctor Web Portal | 3 | 279 | 281 | UI, QA | P0 | SweetAlert WhatsApp stub | /teleconsult/:sessionId in-browser video; replace stub; vendor from PRE-03 | Not Started
142 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.4 | TEL-04 | Video consultation on mobile — doctor and patient both consult from the app (apps in 16–17; same session tokens) | New | Telemedicine | §10 + §2.4 + §3 | Video consultation on mobile | Patient App + Doctor App | 1 | 282 | 282 | QA | P0 | No apps | Same TeleSession tokens; mobile join implemented in Phases 16–17 against this API | Not Started
143 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.6 | TEL-06 | Waiting room — patient waits with live status until the doctor joins | New | Telemedicine | §10 + §2.4 | Waiting room | Patient | 2 | 283 | 284 | UI, QA | P1 | Does not exist | Waiting room page: position, doctor online, paid, estimated wait | Not Started
144 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.7 | TEL-07 | Recording consent — consent captured before the consultation; no recording without it | New | Telemedicine | §10 + §2.4 + §17 | Recording consent | Patient + Doctor | 2 | 285 | 286 | UI, QA | P0 | AudioCaseConsentLog only for audio case taking | ConsentRecord type TeleRecording; block record if declined; both sides see status | Not Started
145 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.8 | TEL-08 | Rejoin after dropped call — either side can rejoin the same consultation | New | Telemedicine | §10 + §2.4 | Rejoin after dropped call | Doctor + Patient | 1 | 287 | 287 | UI, QA | P0 | Does not exist | Session Active until End; rejoin tokens; dashboard Rejoin | Not Started
146 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.9 | TEL-09 | Join failure handling — clear fallback if the call cannot connect, with options to retry | New | Telemedicine | §10 + §2.4 | Join failure handling / Fallback & join failure handling | Doctor + Patient | 1 | 288 | 288 | UI, QA | P1 | Does not exist | Error codes; retry; support ticket deep link later; do not silently fail | Not Started
147 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.10 | TEL-10 | Case-linked chat — chat attached to the consultation record, not a loose message thread | New | Telemedicine | §10 + §2.4 | Case-linked chat | Doctor + Patient | 2 | 289 | 290 | UI, QA | P1 | Does not exist | Messages keyed by TeleSession/PatientAppId; retained with the case | Not Started
148 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.11 | TEL-11 | Consultation summary — issued to the patient at the end of the call | New | Telemedicine | §10 + §2.4 | Consultation summary | Patient + Doctor | 2 | 291 | 292 | UI, QA | P1 | Does not exist | Doctor submits summary (not private notes); patient sees immediately; may share eRx id | Not Started
149 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.12 | TEL-12 | Instant consultation — patient requests an immediate consultation with an available doctor | New | Telemedicine | §10 + §2.3 | Instant consultation / Instant consult request / Queue & doctor offer | Patient + Doctor | 2 | 293 | 294 | UI, QA | P1 | Does not exist | Instant request pool; offer doctor; patient accepts; optional surcharge from fee config | Not Started
150 | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.1 | COM-01 | SMS — appointment confirmation, registration confirmation, doctor-unavailable, OTP, reschedule and cancellation | New, New Integration | Notifications | §14 | SMS | Shared | 3 | 295 | 297 | UI, QA | P0 | No SMS provider; WhatsApp exists separately | SmsProvider + templates + DLT; event hooks; DND/opt-out on Patient | Not Started
151 | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.2 | COM-02 | WhatsApp — templates, offers, health tips and bulk messaging with delivery reports and opt-out (complete remaining ~50%) | Existing Improvement | Notifications | §14 | WhatsApp | Doctor Web | 2 | 298 | 299 | UI, QA | P1 | Meta Cloud send/templates/campaigns live; bulk/opt-in/analytics incomplete | Finish bulk queue UX, template approval states, delivery reports, opt-out | Not Started
152 | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.3 | COM-03 | Push notifications — booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests | New, New Integration | Notifications | §14 + §2.9 + §3 | Push notifications | Patient App + Doctor App | 3 | 300 | 302 | UI, QA | P0 | Does not exist | DeviceToken + FCM/APNs; event fan-out; apps register tokens in Phases 16–17 | Not Started
153 | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.4 | COM-04 | Email — registration, activation, password reset, invoices and receipts | Existing Improvement | Notifications | §14 | Email | Shared | 2 | 303 | 304 | UI, QA | P1 | SMTP used for activation/forgot (plaintext issue fixed in Phase 0); no invoice email | Template emails for listed events; invoice PDF attach via SEC-09 | Not Started
154 | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.5 | COM-05 | In-app notification centre — all alerts collected in one place for patients and doctors | New | Notifications | §14 + §2.8 | In-app notification centre / Notifications centre | Patient App + Doctor Web/App | 2 | 305 | 306 | UI, QA | P1 | Does not exist (Velzon notification demo is not product) | AppNotification inbox; mark read; do not use Velzon demo notifications | Not Started
155 | 13 | Phase 13 — Support & help desk (PDF §15) | 13.1 | SUP-01 | Patient support tickets — patients raise issues from the app and track them | New | Support | §15 + §2.9 | Patient support tickets / Help centre & support tickets | Patient App + Admin | 2 | 307 | 308 | UI, QA | P1 | Does not exist; EnquiryDetail is not tickets; Velzon tickets demo ignore | SupportTicket reporter=Patient; status track; not Enquiry, not Velzon /apps-tickets-* | Not Started
156 | 13 | Phase 13 — Support & help desk (PDF §15) | 13.2 | SUP-02 | Doctor support tickets — doctors raise issues from the portal | New | Support | §15 | Doctor support tickets | Doctor Web + Admin | 1 | 309 | 309 | UI, QA | P1 | Does not exist | Same ticket tables; reporter=Doctor | Not Started
157 | 13 | Phase 13 — Support & help desk (PDF §15) | 13.3 | SUP-03 | Admin issue queue — all issues in one queue with priority, assignment and status | New | Support | §15 + §7.2 | Admin issue queue / Support ticket queue | Admin Portal | 2 | 310 | 311 | UI, QA | P1 | Does not exist | /admin/support-tickets; SLA timestamps; assign | Not Started
158 | 13 | Phase 13 — Support & help desk (PDF §15) | 13.4 | SUP-04 | Ticket conversation — full message thread with attachments | New | Support | §15 | Ticket conversation | Admin + Doctor + Patient | 1 | 312 | 312 | UI, QA | P1 | Does not exist | Threaded messages + SEC-09 attachments | Not Started
159 | 13 | Phase 13 — Support & help desk (PDF §15) | 13.6 | SUP-06 | Help centre — self-service help content for patients | New | Support | §15 + §2.9 | Help centre | Patient Website + App | 2 | 313 | 314 | UI, QA | P2 | Does not exist | CMS articles or static help; searchable | Not Started
160 | 13 | Phase 13 — Support & help desk (PDF §15) | 13.7 | SUP-07 | Assisted booking — help for patients who need support booking | New | Support | §15 + §2.9 | Assisted booking | Support + Reception + Patient | 2 | 315 | 316 | UI, QA | P2 | Does not exist | Staff (admin/support/reception) can complete public booking on behalf of a patient with audit; patient app CTA to request assistance | Not Started
161 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.1 | MED-01 | Pharmacy partner onboarding — licensed premises, licence records, activation checklist | New | HomeoMeds | §12 + §7.2 | Pharmacy partner onboarding / Pharmacy partner management | Pharmacy + Admin | 2 | 317 | 318 | UI, QA | P0 | Does not exist | PharmacyPartner + licences; admin activation; pharmacy console login | Not Started
162 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.2 | MED-02 | Licence gating — expired or suspended licences blocked automatically from receiving orders | New | HomeoMeds | §12 | Licence gating | Backend | 1 | 319 | 319 | UI, QA | P0 | Does not exist | Scheduler; routing skip; banner on pharmacy console | Not Started
163 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.3 | MED-03 | Fulfilment consent & pharmacy selection — patient chooses the seller and consents before the prescription is shared | New | HomeoMeds | §12 + §2.7 | Fulfilment consent & pharmacy selection | Patient | 2 | 320 | 321 | UI, QA | P0 | Does not exist | ConsentRecord PharmacyShare; patient picks from routed sellers; share only after consent | Not Started
164 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.4 | MED-04 | Prescription handoff — signed prescription becomes the order directly — no re-entry, no transcription errors | New | HomeoMeds | §12 + §2.7 | Prescription handoff / Order start | Patient + Pharmacy | 2 | 322 | 323 | UI, QA | P0 | Does not exist | MedicineOrder copied from ErxSnapshot items (codes); pharmacy never types remedies | Not Started
165 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.5 | MED-05 | Rule-based seller routing — licence validity, service area, working hours and capacity | New | HomeoMeds | §12 | Rule-based seller routing | Backend | 2 | 324 | 325 | UI, QA | P0 | Does not exist | SellerRoutingRule engine | Not Started
166 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.6 | MED-06 | Manual stock confirmation — pharmacy confirms availability — no live inventory integration required | New | HomeoMeds | §12 | Manual stock confirmation | Pharmacy console | 1 | 326 | 326 | UI, QA | P0 | Does not exist | Accept/reject with stock flag; do not build inventory master | Not Started
167 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.7 | MED-07 | Pharmacy console — accept or reject, enter price quote, mark ready and dispatched | New, New Integration | HomeoMeds | §12 | Pharmacy console | Pharmacy console | 3 | 327 | 329 | UI, QA | P0 | Does not exist | /pharmacy/orders list+detail; OTP accept (SEC-07); quote; ready; dispatched | Not Started
168 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.8 | MED-08 | Quote before payment — the patient always sees the price before paying | New | HomeoMeds | §12 + §2.7 | Quote before payment / Pharmacy selection & quote | Patient | 2 | 330 | 331 | UI, QA | P0 | Does not exist | MedicineQuote; patient must confirm quote; then PAY-07 | Not Started
169 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.9 | MED-09 | Payment or cash on delivery — both options, with status tracking | New | HomeoMeds | §12 + §9 | Payment or cash on delivery | Patient | 1 | 332 | 332 | UI, QA | P0 | Stream MEDICINE stub in Phase 6 | Online pay via PAY-02; COD_PENDING until pharmacy confirms collection | Not Started
170 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.10 | MED-10 | Order tracking — live status for the patient at every stage | New, New Integration | HomeoMeds | §12 + §2.7 | Order tracking | Patient | 3 | 333 | 335 | UI, QA | P1 | Does not exist | Status timeline events; push updates COM-03 | Not Started
171 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.11 | MED-11 | Medicine ledger shares — seller, platform and delivery recorded (FIN-03 live fill) | New | HomeoMeds | §12 + §8 | Medicine ledger | Account | 1 | 336 | 336 | QA | P0 | Empty medicine ledger screen from Phase 7 | On pay/COD collect, write SplitSeller/Platform/Delivery from config | Not Started
172 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.12 | MED-12 | Order exception queue — stuck, rejected or failed orders always surfaced — never silent | New | HomeoMeds | §12 | Order exception queue | Admin + Account | 2 | 337 | 338 | UI, QA | P0 | Does not exist | HomeoMeds exception queue; SLA; never drop | Not Started
173 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.13 | MED-13 | OTP-based control — key actions verified by OTP so Homeocentrum can monitor and trace every transaction | New | HomeoMeds | §12 + §17 | OTP-based control | Pharmacy + Account | 1 | 339 | 339 | QA | P0 | SEC-07 infrastructure exists | OTP on pharmacy accept (and other high-risk); OtpAudit queryable | Not Started
174 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.14 | MED-14 | Refill orders — repeat orders raised from an existing prescription | New | HomeoMeds | §12 + §2.7 + §11 | Refill orders / Order detail & refill | Patient + Doctor | 1 | 340 | 340 | UI, QA | P1 | ERX-10 refill request exists | Approved refill creates a new MedicineOrder from the same snapshot; one-tap patient | Not Started
175 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.16 | MED-16 | Medicines tab — all medicine orders in one place (API now; app UI in Phase 16) | New | HomeoMeds | §2.7 | Medicines tab | Patient | 1 | 341 | 341 | UI, QA | P1 | Does not exist | GET my orders; website optional list; app tab Phase 16 | Not Started
176 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.1 | CON-01 | Family members — add family members under one account | New | Patient identity | §2.1 | Family members | Patient App (API now) | 2 | 342 | 343 | UI, QA | P0 | Does not exist | FamilyMember under Patient account; bookings can be for a member | Not Started
177 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.2 | CON-02 | Caregiver authorization — let a family member book and manage on their behalf | New, New Integration | Patient identity | §2.1 | Caregiver authorization | Patient App (API now) | 3 | 344 | 346 | UI, QA | P0 | Does not exist | CaregiverAuth with scopes; OTP; withdrawable via consent centre | Not Started
178 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.3 | CON-03 | Records timeline + consultation note + document upload APIs | New | Patient records | §2.5 | Records timeline / Consultation note / Document upload | Patient App (API now) | 2 | 347 | 348 | UI, QA | P0 | Doctor history exists; no patient timeline; no patient upload | Patient timeline DTO (visits, summary, eRx codes, labs); consultation note = TEL-11 summary not private notes; uploads via SEC-09 | Not Started
179 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.4 | CON-04 | Follow-up plan & tasks — clear next steps after each consultation | New | Continuity | §2.6 | Follow-up plan & tasks | Doctor Web + Patient | 2 | 349 | 350 | UI, QA | P1 | Does not exist (follow-up option in notes does not save) | FollowUpTask created by doctor; patient sees tasks | Not Started
180 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.5 | CON-05 | Symptom diary — record symptoms between visits | New | Continuity | §2.6 | Symptom diary | Patient App (API now) | 2 | 351 | 352 | UI, QA | P1 | Does not exist | SymptomDiary entries; doctor can read on board | Not Started
181 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.6 | CON-06 | Progress tracking — see improvement over time across visits | New | Continuity | §2.6 | Progress tracking | Patient + Doctor | 2 | 353 | 354 | UI, QA | P2 | Does not exist | Progress series from diary + visit outcomes; not a fake chart | Not Started
182 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.7 | CON-07 | Consent centre & data rights — view, manage and withdraw consents; request data | New | Privacy | §17 + §2.8 | Consent centre & data rights | Patient App (API now) | 2 | 355 | 356 | UI, QA | P0 | ConsentRecord from Phase 0 | Patient list/withdraw; data export request (DPDP); deletion request workflow | Not Started
183 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.8 | CON-08 | Patient payments & refunds read model | New | Patient money | §2.8 | Payments & refunds | Patient App (API now) | 1 | 357 | 357 | QA | P1 | Ledger exists for Account | Patient-safe DTO of own consult+medicine payments and refunds — no other patients, no commission internals | Not Started
184 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.9 | CON-09 | Physical clinic appointment — book an in-person visit as well as online | Existing Improvement | Booking | §2.9 + §5.2 | Physical clinic appointment | Patient | 1 | 358 | 358 | QA | P1 | ConsultMode added in APT-02; public booking in WEB-04 | Ensure public/patient booking supports In-clinic as first-class, not tele-only | Not Started
185 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.10 | CON-10 | Patient profile setup API — name, age, gender, contact and health basics | New | Patient identity | §2.1 | Profile setup | Patient App (API now) | 2 | 359 | 360 | UI, QA | P0 | Clinic-created Patient exists; no self-serve profile product | Patient profile fields + health basics; used by OTP-verified patient token | Not Started
186 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.1 | RPT-01 | Admin overview dashboard — platform-wide activity at a glance (replace Velzon ecommerce) | Existing Improvement | Reports | §16 + §7.2 | Admin overview dashboard / Admin dashboard | Admin Portal | 2 | 361 | 362 | UI, QA | P0 | Velzon ecommerce dashboard 0% product; login lands /dashboard | True /admin/dashboard KPIs: doctors, credentialing, bookings, GMV, failed payments, tickets, HomeoMeds exceptions; redirect /dashboard away from StoreVisits | Not Started
187 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.2 | RPT-02 | Doctor practice statistics — patient and consultation trends (extend existing charts) | Existing Improvement | Reports | §16 + §5.1 | Doctor practice statistics | Doctor Web | 2 | 363 | 364 | UI, QA | P1 | Patient stats charts live | Keep as foundation; ensure visit type/mode included after APT-02 | Not Started
188 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.3 | RPT-03 | Follow-up analysis — due/overdue patients and follow-up conversion | New | Reports | §16 | Follow-up analysis | Doctor Web | 2 | 365 | 366 | UI, QA | P1 | Does not exist; follow-up option in notes does not save | /doctor/follow-up-analysis from VisitType + CON-04 tasks | Not Started
189 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.4 | RPT-04 | Clinic performance analysis — appointments, slot utilisation, no-shows, cancellations, waiting time and revenue | New | Reports | §16 | Clinic performance analysis | Doctor Web | 2 | 367 | 368 | UI, QA | P1 | Does not exist | /doctor/clinic-performance including payment collected and tele duration if timed | Not Started
190 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.5 | RPT-05 | Payment reconciliation report — bookings matched against payments | New | Reports | §16 + §7.2 | Payment reconciliation report / Consult booking & payment reconciliation | Admin + Account | 1 | 369 | 369 | UI, QA | P1 | FIN-02 built the queue; this is the report/export | Exportable report from the same reconciliation query | Not Started
191 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.6 | RPT-06 | Settlement & payout reports — amounts due and paid to doctors and pharmacies | New | Reports | §16 + §8 | Settlement & payout reports | Account | 1 | 370 | 370 | UI, QA | P1 | FIN-04/05 exist as ops screens | Formal report/export of runs and payouts | Not Started
192 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.7 | RPT-07 | GST & invoice reports (reporting surface of FIN-08) | New | Reports | §16 + §8 | GST & invoice reports | Account | 1 | 371 | 371 | QA | P1 | FIN-08 built tax screen | Confirm report pack (GSTR-style export as agreed with CA) — configuration | Not Started
193 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.8 | RPT-08 | Doctor earnings summary — daily, weekly and monthly earnings with payout status (web + same API as DMO-10) | New | Reports | §16 + §3 | Doctor earnings summary | Doctor Web + App | 2 | 372 | 373 | UI, QA | P1 | Does not exist | Web earnings page using same API as doctor app | Not Started
194 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.9 | RPT-09 | Medicine order reports — order volumes, fulfilment and exceptions | New | Reports | §16 + §12 | Medicine order reports | Admin + Account | 2 | 374 | 375 | UI, QA | P1 | Does not exist | Volumes, SLA, exception counts from HomeoMeds | Not Started
195 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.10 | RPT-10 | Platform users remaining 20% — import, export and activation control | Existing Improvement | Admin | §7.2 | Platform users | Admin Portal | 2 | 376 | 377 | UI, QA | P1 | List/Add/Edit live; Import/Export buttons dead; no verification column | Wire Import/Export; verification column; activate/lock; link credentialing | Not Started
196 | 19 | Phase 19 — Cross-surface QA, NFR, delivery summary gate (PDF §1 + §18) | 19.3 | NFR-01 | NFR — performance, low-data, reliability, secrets, dual-API freeze | Existing Modification | NFR | §2.9 + §3 + §17 | Low-data mode / Reliability monitoring / Secure login | All | 1 | 378 | 378 | QA | P0 | Known risks: plaintext passwords (fixed P0), secrets in appsettings, dual API drift | Rotate secrets; no new third API; patient low-data verified; doctor reliability SDK live | Not Started

## 06_UI_Main_Tasks
UI MAIN TASKS — execute sub-tasks in UI Sequential sheet filtered by Main Task ID. Do not start a Main Task if Sister Tracks includes Web and those Web rows are not Done (API/DB first).
Seq | Phase | Phase Name | WBS | Main Task ID | Main Task | Work Type(s) | Module | PDF Section | PDF Feature | Surface | Sub-task count | First Track Seq | Last Track Seq | Sister Tracks | Priority (highest) | AS-IS | TO-BE | Status
1 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.2 | FND-02 | Delivery footprint — 2 mobile apps · 5 web portals · payment · telemedicine · digital prescription · HomeoMeds (programme skeleton) | New, Existing Improvement | Platform | §1 | Delivery covers | Shared | 2 | 1 | 2 | Web, Mobile | P0 | 1 web SPA (Admin/Doctor/Reception + marketing). No patient app, doctor app, Account portal, Pharmacy console | Repo/route skeleton: Patient Website, Doctor Web, Reception, Admin, Account (+ Pharmacy console under HomeoMeds); Patient + Doctor mobile later | Not Started
2 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.3 | SEC-01 | Secure login — protected credentials for every user type | Existing Modification | Security | §17 | Secure login | All web + later mobile | 1 | 3 | 3 | Web, QA | P0 | POST /Account/Login on classic API; JWT in sessionStorage; doctor/user passwords compared plaintext; reception hashed on classic; fakeBackend() still mounted | Hashed passwords; Role claim on JWT; disable fake backend for production paths; Patient OTP login is Phase 8 (not password) | Not Started
3 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.4 | SEC-02 | Secure password reset — time-limited reset links (stop plaintext email + fake thunk) | Existing Improvement | Security | §17 | Secure password reset | Admin / Doctor / Reception web | 1 | 4 | 4 | Web, QA | P0 | /forgot-password UI exists; thunk uses fake/Firebase; POST /users/ForgetPassword emails plaintext password | Tokenised reset (hash, TTL); email contains link only; ChangePassword for logged-in user | Not Started
4 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.5 | SEC-03 | Session control — proper sign-out across web and mobile | Existing Improvement | Security | §17 | Session control | All | 1 | 5 | 5 | Web, QA | P0 | Client clears sessionStorage; no server logout / token revoke; UserLoginStatus unused | POST Logout persists login status; optional token denylist; mobile will call the same API in Phase 16/17 | Not Started
5 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.6 | SEC-04 | Role-based access — each role sees only what it is permitted to see | Existing Improvement | Security | §17 | Role-based access | Admin / All web | 1 | 6 | 6 | Web, QA | P0 | RoleMaster + RoleDetail + MenuMaster exist; GetMenuByRole commented out on .NET 8; no per-route frontend ACL — any authenticated URL works | Re-enable GetMenuByRole; AuthProtected deny-by-default; [Authorize(Roles=)] on money/clinical APIs; Account cannot edit repertory; Admin cannot approve payouts | Not Started
6 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.28 | ADM-B04 | Business Management — Roles & menu permissions (existing DB, runtime ACL leftover) | Existing Improvement | Business Management | §7.2 | Roles & menu permissions | Admin Portal | 1 | 7 | 7 | Web, QA | P1 | Role CRUD screens live; runtime GetMenuByRole commented; no frontend route ACL | This is the product surface for SEC-04; complete wiring here | Not Started
7 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.1 | CLN-01 | Clinical workspace — single screen for the entire consultation | Existing Improvement | Patient Board | §5.3 | Clinical workspace | Doctor Web Portal | 1 | 8 | 8 | Web, QA | P1 | PatientBoard.js (~13.5k) is the workspace; ~90% — missing payment/tele/eRx header status | Keep one screen; add header chips for payment, tele session, signed eRx (chips light up as later phases land) | Not Started
8 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.7 | CLN-07 | Manage selected rubrics — review, edit and remove (remaining ~10%) | Existing Improvement | Patient Board | §5.3 | Manage selected rubrics | Doctor Web Portal | 1 | 9 | 9 | Web, QA | P1 | Clipboard exists; confirm-delete / intensity-edit incomplete | Confirm delete; edit intensity on selected rubric; no accidental wipe | Not Started
9 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.9 | CLN-09 | Improved rubric accuracy — enhanced accuracy rules for audio-based rubric suggestions | Existing Improvement | Audio AI | §5.3 | Improved rubric accuracy | Doctor Web Portal + Admin intelligence | 1 | 10 | 10 | Web, QA | P1 | Engine + admin metaphors/aliases exist; accuracy rules still in progress (~50%) | Complete accuracy rules per AUDIO_CASE_TAKING_AI_ENGINE docs; metaphor/alias QA | Not Started
10 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.10 | CLN-10 | Materia medica reference during consultation (remaining ~10%) | Existing Improvement | Patient Board | §5.3 | Materia medica reference | Doctor Web Portal | 1 | 11 | 11 | Web, QA | P2 | MM tab + repertorize differential accordion ~90% | Faster head navigation during case; do not rebuild MM masters | Not Started
11 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.12 | CLN-12 | Repertorization & elimination (remaining ~10%) | Existing Improvement | Patient Board | §5.3 | Repertorization & elimination | Doctor Web Portal | 1 | 12 | 12 | Web, QA | P1 | Common/uncommon/elimination live ~90% | Stability polish; Center of Gravity is a NEW panel on the same rubrics (next task) | Not Started
12 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.13 | CLN-13 | Center of Gravity — new analysis identifying the central remedy of the case, with reasoning shown | New | Repertorization | §5.3 | Center of Gravity | Doctor Web Portal | 1 | 13 | 13 | Web, QA | P1 | Does not exist | POST /api/Repertorization/CenterOfGravity from selected rubric ids + intensities; UI panel with explainability | Not Started
13 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.16 | CLN-16 | Complaints & case details — wire Patient Board to existing SaveComplaints / SaveCaseDetails (~20% today) | Existing Improvement | Patient Board | §5.3 | Complaints & case details | Doctor Web Portal | 1 | 14 | 14 | Web, QA | P1 | Classic SaveComplaints / SaveCaseDetails APIs exist; Patient Board does not call them | Call the existing APIs from the board; Reception case-paper (Phase 5) uses a subset | Not Started
14 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.17 | CLN-17 | Patient back history — complete history of visits, notes, prescriptions and payments | Existing Improvement | Patient Board | §5.3 | Patient back history | Doctor Web Portal | 1 | 15 | 15 | Web, QA | P1 | History panel ~70%; no payment line (payments do not exist yet) | Timeline: visits, notes, eRx, labs; payment row added when Phase 6 lands (placeholder now) | Not Started
15 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.18 | CLN-18 | Export case data — download the full case in Excel or PDF | New | Patient Board | §5.3 | Export case data | Doctor Web Portal | 1 | 16 | 16 | Web, QA | P1 | Newer ExportCasesToExcel exists; no Patient Board export UI; no PDF | Toolbar Excel + PDF using existing Excel API + new PDF renderer; exclude private notes from patient-facing PDF (eRx print is Phase 10) | Not Started
16 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.20 | CLN-20 | 3D anatomy viewer — interactive 3D body model linked to rubric search (remaining ~50%) | Existing Improvement | Anatomy | §5.3 | 3D anatomy viewer | Doctor Web Portal | 1 | 17 | 17 | Web, QA | P2 | three.js viewer + hotspot→search live; incomplete mesh coverage / UX | Complete GLB/hotspot coverage; mobile fallback later; admin 3D masters already in Phase 1 | Not Started
17 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.1 | DOC-01 | Doctor home dashboard — complete overview of the working day (remaining ~30%) | Existing Improvement | Doctor Dashboard | §5.1 | Doctor home dashboard | Doctor Web Portal | 1 | 18 | 18 | Web, QA | P1 | Widgets + BestSellingProducts ~70%; missing online toggle, tele queue, payment badges, follow-up due | Extend, do not replace; later phases light up tele/payment chips | Not Started
18 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.3 | DOC-03 | Patient search, list & open case (remaining ~10%) | Existing Improvement | Doctor Dashboard | §5.1 | Patient search, list & open case | Doctor Web Portal | 1 | 19 | 19 | Web, QA | P1 | Search/list/open ~90%; missing last visit, unpaid, family filters | Add last-visit column; unpaid/family after those modules exist | Not Started
19 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.6 | DOC-06 | Export patients — download patient data in Excel, CSV or PDF (keep) | Existing Improvement | Patients | §5.1 | Export patients | Doctor Web Portal | 1 | 20 | 20 | Web, QA | P2 | Export live (confirm PDF vs Excel/CSV in QA) | If PDF is missing, add it as Existing Improvement; do not skip the PDF wording in the PDF | Not Started
20 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.9 | DOC-09 | Manage reception staff — add, edit and remove reception users (backend done, UI absent) | Existing Improvement | Staff | §5.1 | Manage reception staff | Doctor Web Portal | 1 | 21 | 21 | Web, QA | P1 | .NET 8 api/ReceptionStaff CRUD exists; no SPA page | List/add/edit/disable at /doctor/reception-staff; doctor owns the staff record | Not Started
21 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.10 | DOC-10 | Doctor profile — clinic details, consultation fee, photo, qualifications, working hours, bank details | Existing Improvement | Doctor Profile | §5.1 | Doctor profile | Doctor Web Portal | 1 | 22 | 22 | Web, QA | P0 | /profile is Velzon first_name only (~20%); credentials sit on Doctor entity; no fee/KYC UI | Real doctor profile: clinic, photo, qualifications, consult fee (feeds Phase 6), hours (feeds schedule), bank KYC (feeds Account payees) | Not Started
22 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.2 | APT-02 | Create new appointment — persist visit type, consultation mode and fee | Existing Improvement | Appointments | §5.2 | Create new appointment | Doctor Web Portal | 1 | 23 | 23 | Web, QA | P0 | Create appointment ~90%; Formik modal has no VisitType / ConsultMode / fee | VisitType First/Follow-up; ConsultMode In-clinic / E-Consult; fee display from doctor profile / ConsultFeeConfig | Not Started
23 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.5 | APT-05 | Reschedule appointment — move to a new slot with automatic patient notification (NEW — not a rename of UpdateAppointmentTime) | New | Appointments | §5.2 + §2.3 + §6 | Reschedule appointment | Doctor Web + Reception + later Patient | 1 | 24 | 24 | Web, QA | P0 | Time can be edited; no formal Reschedule (audit, notify, old→new confirm) | POST RescheduleAppointment; AppointmentChangeLog; conflict 409 with alternatives; SMS/WhatsApp fan-out (notify failure must not roll back) | Not Started
24 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.6 | APT-06 | Cancel appointment — reason, free the slot, trigger refund where applicable (NEW CANCELLED status — do NOT reuse DeleteStatus) | New | Appointments | §5.2 + §2.3 + §6 | Cancel appointment | Doctor Web + Reception + later Patient | 1 | 25 | 25 | Web, QA | P0 | No CANCELLED; DeleteStatus is soft-delete only | CANCELLED + reason fields; free slot; waitlist hook; if PAID evaluate refund policy (Phase 6/7) | Not Started
25 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.7 | APT-07 | Daily schedule setup — define working days, hours and break times (promote modal to first-class screen) | Existing Improvement | Scheduling | §5.2 | Daily schedule setup | Doctor Web Portal | 1 | 26 | 26 | Web, QA | P0 | DailyScheduleSetupModal + GetDailySchedule / SaveDailySchedule exist; not a first-class screen (draft marked 0%) | Promote to /doctor/schedule with week grid and copy-day; reuse existing APIs — do not rebuild | Not Started
26 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.9 | APT-09 | Consultation payment status on every appointment (schema now; values live in Phase 6) | New | Appointments | §5.2 + §9 | Consultation payment status | Doctor Web Portal | 1 | 27 | 27 | Web, QA | P0 | No PaymentStatus on appointment | Add PaymentStatus UNPAID / PENDING / PAID / FAILED / PAY_AT_CLINIC / REFUNDED; UI badge; source of truth is webhook in Phase 6 not the client screen | Not Started
27 | 5 | Phase 5 — Reception portal (PDF §6) | 5.2 | REC-02 | Reception profile — manage own profile details (0% today) | New | Reception | §6 | Reception profile | Reception Portal | 1 | 28 | 28 | Web, QA | P1 | No reception-specific profile; shared Velzon /profile | Name, mobile, attached doctor (read-only); cannot edit doctor bank/fee | Not Started
28 | 5 | Phase 5 — Reception portal (PDF §6) | 5.3 | REC-03 | Reception home dashboard — purpose-built front-desk dashboard (not only hidden doctor actions) | Existing Improvement | Reception | §6 | Reception home dashboard | Reception Portal | 2 | 29 | 30 | QA | P1 | Same /doctordashboard with some clinical actions disabled ~90% | Reception-first chrome: queue, collect pay, case paper, no repertory/Rx; optional /reception home route | Not Started
29 | 5 | Phase 5 — Reception portal (PDF §6) | 5.6 | REC-06 | Create & manage appointments — full appointment management (keep; plus reschedule/cancel from Phase 4) | New | Reception | §6 | Create & manage appointments | Reception Portal | 1 | 31 | 31 | Web, QA | P0 | Create/status/time live; reschedule/cancel missing until Phase 4 APIs | Enable RescheduleAppointment and CancelAppointment for JWT DoctorId; isReceptionUser must not block | Not Started
30 | 5 | Phase 5 — Reception portal (PDF §6) | 5.7 | REC-07 | New appointment — book on behalf of the patient (keep; same VisitType/ConsultMode/fee as APT-02) | Existing Improvement | Reception | §6 | New appointment | Reception Portal | 1 | 32 | 32 | QA | P1 | New appointment modal live; fields incomplete until APT-02 | Same modal fields as doctor so public booking later matches staff-created rows | Not Started
31 | 5 | Phase 5 — Reception portal (PDF §6) | 5.8 | REC-08 | Waiting queue management — manage the live queue and call the next patient | Existing Improvement | Reception | §6 | Waiting queue management | Reception Portal | 1 | 33 | 33 | Web, QA | P1 | Status buckets ~60%; no dedicated queue UX / call-next | Dedicated queue: walk-in vs tele; payment state; Call next; notify patient (later push) | Not Started
32 | 5 | Phase 5 — Reception portal (PDF §6) | 5.11 | REC-11 | View doctor schedule — see the doctor’s working schedule (read-only) | New | Reception | §6 | View doctor schedule | Reception Portal | 1 | 34 | 34 | QA | P1 | GetDailySchedule exists; no reception view | Read-only /reception/schedule using DoctorID from JWT | Not Started
33 | 5 | Phase 5 — Reception portal (PDF §6) | 5.12 | REC-12 | Log case paper / chief complaint — record the reason for visit before the consultation | New | Reception | §6 | Log case paper / chief complaint | Reception Portal | 1 | 35 | 35 | Web, QA | P1 | Missing; SaveComplaints exists but board is doctor-only | Restricted case-paper form (chief complaint only — no repertory/Rx); audit reception author | Not Started
34 | 5 | Phase 5 — Reception portal (PDF §6) | 5.13 | REC-13 | Collect consultation payment — cash, UPI, card or payment link and issue a receipt (API in Phase 6; UI shell now) | New | Reception | §6 + §9 | Collect consultation payment | Reception Portal | 1 | 36 | 36 | Web | P0 | Does not exist | UI modal ready; CollectAtReception API lands with payment spine in Phase 6 — do not fake a paid status here | Not Started
35 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.1 | PAY-01 | Consultation fee configuration — each doctor’s fee set and displayed to patients | New | Payments | §9 | Consultation fee configuration | Doctor profile + Public + Admin | 1 | 37 | 37 | Web, QA | P0 | No ConsultFeeConfig; doctor profile work in DOC-10 may have stored a fee field | ConsultFeeConfig (InClinic, EConsult, optional Instant surcharge, PayAtClinicEnabled, GST flags) | Not Started
36 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.3 | PAY-03 | Online consultation payment — patient pays by card, UPI, netbanking or wallet | New | Payments | §9 + §4 + §2.3 | Online consultation payment | Public web + later Patient app | 1 | 38 | 38 | Web, QA | P0 | Does not exist (only S1 SaaS) | CreateConsultOrder attached to PatientAppId; Razorpay Checkout; webhook sets PAID; do not overload PackageEntryDetail | Not Started
37 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.4 | PAY-04 | Reception payment collection — cash, UPI, card or payment link with printed receipt | New | Payments | §9 + §6 | Reception payment collection | Reception Portal | 1 | 39 | 39 | Web, QA | P0 | Does not exist | CollectAtReception writes ledger S3; print receipt; payment-link uses same Razorpay order as online | Not Started
38 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.5 | PAY-05 | Pay-at-clinic option — book now, pay at the clinic where the doctor allows it | New | Payments | §9 | Pay-at-clinic option | Public + Doctor + Reception | 1 | 40 | 40 | Web, QA | P1 | Does not exist | PayAtClinicEnabled on fee config; appointment PaymentStatus=PAY_AT_CLINIC; tele queue may still require PAID (policy) | Not Started
39 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.6 | PAY-06 | Doctor subscription payment — buy and renew subscription packages (complete remaining ~30%) | Existing Improvement | Payments | §9 | Doctor subscription payment | Doctor Web Portal | 1 | 41 | 41 | Web, QA | P1 | Checkout works ~70%; no webhook, refund, invoice, GST, Account ledger | Same webhook spine; write S1 ledger; invoice; failed pay UX; PackageEntryDetail shape UNCHANGED | Not Started
40 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.8 | PAY-08 | Payment status everywhere — doctor, reception and patient all see the same payment status | New | Payments | §9 | Payment status everywhere | All | 1 | 42 | 42 | Web, QA | P0 | No shared status | Single PaymentStatus on appointment/order; all DTOs read it; never a second client-only flag | Not Started
41 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.9 | PAY-09 | Refunds — processed and tracked against the original payment | New | Payments | §9 + §8 + §2.8 | Refunds | Account + Patient | 1 | 43 | 43 | Web, QA | P0 | Does not exist | Refund entity against original PaymentOrder; Razorpay refund API; cancel-appointment hook; patient sees status | Not Started
42 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.10 | PAY-10 | Payment receipts & invoices — issued for every transaction | New | Payments | §9 + §8 | Payment receipts & invoices | All | 1 | 44 | 44 | Web, QA | P1 | No invoice entity | Invoice numbering series from PRE-02; PDF receipt; GST fields; email in Phase 12 | Not Started
43 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.1 | FIN-01 | Unified transaction ledger — every rupee that moves through the platform, in one record | New | Account | §8 | Unified transaction ledger | Account Portal | 1 | 45 | 45 | Web, QA | P0 | Does not exist | Append-only LedgerEntry for S1–S7; filters; OTP audit link; Admin may view, Account owns movement | Not Started
44 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.2 | FIN-02 | Consultation payment reconciliation — online payments and reception collections matched and verified | New | Account | §8 + §7.2 + §16 | Consultation payment reconciliation | Account + Admin | 1 | 46 | 46 | Web, QA | P0 | Does not exist | Join booking ↔ payment ↔ appointment; KPI collected/pending/failed/refunded; CSV | Not Started
45 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.3 | FIN-03 | Medicine ledger — medicine money tracked separately from consultation money | New | Account | §8 + §12 | Medicine ledger | Account Portal | 1 | 47 | 47 | Web, QA | P1 | Does not exist | /account/medicine-ledger; Stream=MEDICINE; seller/platform/delivery split columns; filled in Phase 14 | Not Started
46 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.4 | FIN-04 | Settlement runs — scheduled settlement of amounts due to doctors and pharmacies | New | Account | §8 + §16 | Settlement runs | Account Portal | 1 | 48 | 48 | Web, QA | P0 | Does not exist | SettlementRun job T+N hold; net of commission/GST/refunds; pharmacies after Phase 14 | Not Started
47 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.5 | FIN-05 | Payout approval — payouts released only after OTP-verified approval | New | Account | §8 + §17 | Payout approval | Account Portal | 1 | 49 | 49 | Web, QA | P0 | Does not exist | ApprovePayout requires SEC-07 OTP; Admin cannot approve; NEFT/file or gateway per PRE-01 | Not Started
48 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.6 | FIN-06 | Refund processing — Account issues and tracks refunds (uses PAY-09) | New | Account | §8 | Refund processing | Account Portal | 1 | 50 | 50 | Web, QA | P0 | Does not exist | /account/refunds UI on PAY-09 APIs; OTP if policy requires | Not Started
49 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.7 | FIN-07 | Payment exception handling — investigate and resolve every failed or disputed payment | New | Account | §8 + §7.2 | Payment exception handling | Account + Admin | 1 | 51 | 51 | Web, QA | P0 | Does not exist | Exception queue Failed/Partial/Webhook-mismatch/Refund-pending; retry/resolve with OTP on manual reconcile | Not Started
50 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.8 | FIN-08 | GST & invoice reports — invoice numbering and tax reporting | New | Account | §8 + §16 | GST & invoice reports | Account Portal | 1 | 52 | 52 | Web, QA | P1 | Does not exist | /account/tax export using Invoice table and PRE-02 GST treatment — configuration not hardcoded | Not Started
51 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.9 | FIN-09 | Payee records — bank and KYC details for doctors and pharmacies | New | Account | §8 | Payee records | Account Portal | 1 | 53 | 53 | Web, QA | P1 | Doctor bank fields added in DOC-10; no Account UI; no pharmacy | /account/payees; OTP on doctor KYC change (fraud); pharmacies after Phase 14 | Not Started
52 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.10 | FIN-10 | Clinic collection view — cash and UPI collected at reception, per clinic and per day | New | Account | §8 | Clinic collection view | Account Portal | 1 | 54 | 54 | Web, QA | P1 | Does not exist | /account/clinic-collections from CollectAtReception rows; respect PRE-02 retain vs remit | Not Started
53 | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.1 | TRU-01 | Doctor credentialing — doctors upload qualification and registration documents for review | New | Trust | §13 + §7.2 | Doctor credentialing | Doctor Web + Admin | 1 | 55 | 55 | Web, QA | P0 | RegisterDoctor activates immediately; PassingUniversity/CertNo/QualificationId exist; no document store/queue | DoctorCredentialDocument + VerificationStatus Pending; do not auto-activate practice for public directory | Not Started
54 | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.2 | TRU-02 | Verification review — Admin approves, rejects or requests further information | New | Trust | §13 + §7.2 | Verification review | Admin Portal | 1 | 56 | 56 | Web, QA | P0 | Does not exist | /admin/doctor-credentialing list + detail; email notify doctor | Not Started
55 | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.3 | TRU-03 | Verified badge — patients see which doctors have been verified | New | Trust | §13 + §2.2 | Verified badge / Credentials & verification | Public + Patient app | 1 | 57 | 57 | Web, QA | P0 | Does not exist | Badge on public doctor card and profile from VerificationStatus=Approved | Not Started
56 | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.5 | TRU-05 | Patient reviews — patients rate and review consultations | New | Trust | §13 + §2.8 | Patient reviews / Write a review | Patient + Public | 1 | 58 | 58 | Web, QA | P1 | Does not exist | Review linked to PatientAppId; one review per visit; moderation flag optional | Not Started
57 | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.6 | TRU-06 | Review appeal — doctors can appeal a review; patients manage reviews and raise an appeal | New | Trust | §13 + §2.8 | Review appeal / My reviews & appeal | Doctor + Patient + Admin | 1 | 59 | 59 | Web, QA | P2 | Does not exist | Appeal entity; admin resolves; patient my-reviews list | Not Started
58 | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.7 | TRU-07 | Ranking transparency — patients are shown why doctors are ranked as they are | New | Trust | §13 + §2.2 | Ranking transparency / Ranking explanation | Public + Patient app | 1 | 60 | 60 | Web, QA | P1 | Does not exist | Documented ranking factors (verified, availability, fee, reviews, experience) + explain API/UI | Not Started
59 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.1 | WEB-01 | Product home page — complete public website presenting the service | Existing Improvement | Patient Website | §4 | Product home page | Patient Website | 1 | 61 | 61 | Web, QA | P1 | HomeoJobLanding ~50%; Velzon leftovers; CTAs incomplete for book/trust/apps | Book CTA, verified doctors, consult+SaaS pricing teaser, app download placeholders | Not Started
60 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.2 | WEB-02 | Consultation & subscription pricing — transparent pricing display | Existing Improvement | Patient Website | §4 | Consultation & subscription pricing | Patient Website | 2 | 62 | 63 | QA | P1 | SaaS package marketing /pricing exists; no consult fee display per doctor | Keep SaaS pricing; add consult fee on doctor cards from ConsultFeeConfig | Not Started
61 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.3 | WEB-03 | Doctor discovery — browse and search verified doctors | New | Patient Website | §4 + §2.2 | Doctor discovery | Patient Website | 1 | 64 | 64 | Web, QA | P0 | Does not exist as a patient product (marketing only) | /book search: name, condition, category; filters availability, fee, experience, language, location | Not Started
62 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.4 | WEB-04 | Self-service booking — book an appointment online without calling the clinic | New | Patient Website | §4 + §2.3 | Self-service booking | Patient Website | 1 | 65 | 65 | Web, QA | P0 | Staff-only appointments | Funnel /book/:id/slots → review+consent → create Patient+Appointment; OTP; rate-limit; respect schedule + unpaid hold policy PRE-03 | Not Started
63 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.5 | WEB-05 | Online consultation payment on website — pay the fee at the time of booking | New | Patient Website | §4 + §9 | Online consultation payment | Patient Website | 1 | 66 | 66 | QA | P0 | Does not exist | Checkout uses PAY-03; success/fail pages; pay-at-clinic branch from PAY-05 | Not Started
64 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.6 | WEB-06 | Contact & enquiry form — enquiries reach the admin team and are tracked | Existing Improvement | Patient Website | §4 + §15 | Contact & enquiry form | Patient Website + Admin | 1 | 67 | 67 | Web, QA | P1 | EnquiryDetail API exists; public form partial; admin inbox screen missing | Confirmation + enquiry id; /admin/enquiries inbox; optional convert to SupportTicket | Not Started
65 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.7 | WEB-07 | Privacy policy — covering data protection, recording and pharmacy consent | Existing Improvement | Legal | §4 + §17 | Privacy policy | Patient Website | 1 | 68 | 68 | QA | P0 | Privacy page partial; not DPDP/tele/pharmacy complete | Publish PRE-03 legal copy: DPDP, recording, pharmacy, data-rights, family/caregiver | Not Started
66 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.8 | WEB-08 | Terms of service — covering payments, refunds, telemedicine and medicine orders | Existing Improvement | Legal | §4 | Terms of service | Patient Website | 1 | 69 | 69 | QA | P0 | Terms partial | Payments, refunds, telemedicine, HomeoMeds, codes-before-names | Not Started
67 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.9 | WEB-09 | Doctor self-registration — doctors apply to join the platform online | Existing Improvement | Patient Website | §4 | Doctor self-registration | Public | 1 | 70 | 70 | Web, QA | P0 | RegisterDoctor ~90%; activates immediately; no document upload | Document upload; pending-verification message; TRU-01 status Pending | Not Started
68 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.10 | WEB-10 | Email activation — secure account activation by email link | Existing Improvement | Auth | §4 | Email activation | Public | 1 | 71 | 71 | Web, QA | P1 | ActivateUser via /login?UserId= ~90%; align with verification; expiry/resend incomplete | Token expiry, resend, align with credentialing (activation ≠ verified practice) | Not Started
69 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.11 | WEB-11 | Waitlist offer — get offered a slot when one is freed by a cancellation (patient website + later app) | New | Booking | §2.3 | Waitlist offer | Patient Website + App | 1 | 72 | 72 | Web, QA | P2 | Cancel hook stub in Phase 4; no waitlist records | BookingWaitlist; on cancel, offer FIFO; timeout | Not Started
70 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.12 | WEB-12 | Health articles — educational content to build trust and engagement | Existing Improvement | Patient Website | §2.2 | Health articles | Patient Website + App | 1 | 73 | 73 | QA | P2 | Blog/news APIs on classic exist for marketing | Reuse blog/news as health articles on public site and later patient app; admin already has news/blog | Not Started
71 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.1 | ERX-01 | Potency module — every remedy carries a defined potency from a managed list, no free text | New | eRx | §11 | Potency module | Doctor Web + Admin | 1 | 74 | 74 | Web, QA | P0 | Dose saved as empty free-text dose: '' | PotencyMaster CRUD; PotencyId on PrescriptionRemedyDetail; stop empty Dose | Not Started
72 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.2 | ERX-02 | Dosage details — frequency, duration and instructions recorded clearly | New | eRx | §11 | Dosage details | Doctor Web Portal | 1 | 75 | 75 | Web, QA | P0 | Unstructured/empty dose | Frequency, Duration, Instructions fields on each remedy line | Not Started
73 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.3 | ERX-03 | Visit notes kept separate from the prescription — private clinical notes never appear on the prescription given to the patient or pharmacy | New | eRx | §11 + §5.3 | Visit notes kept separate from the prescription | Doctor Web Portal | 1 | 76 | 76 | Web, QA | P0 | History notes mixed into Rx modal tabs | Visit Notes panel outside Rx; NoteType; IsErxExcluded; eRx print has remedies+labs only | Not Started
74 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.4 | ERX-04 | Signed digital prescription — issued and locked once signed, so it cannot be altered afterwards | New | eRx | §11 + §2.5 + §5.3 | Signed digital prescription | Doctor Web | 1 | 77 | 77 | Web, QA | P0 | SavePrescriptionDetail overwritable; no lock/sign | ErxSnapshot immutable on sign; subsequent edits create a new unsigned draft not a silent mutate | Not Started
75 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.5 | ERX-05 | Prescription history — every prescription stored against the patient and visit | New | eRx | §11 | Prescription history | Doctor + Patient | 1 | 78 | 78 | Web, QA | P1 | Rx saved per appointment but no signed history product | List snapshots by PatientId; open past visit eRx | Not Started
76 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.6 | ERX-06 | Patient view of prescription in app — patient sees the prescription immediately (codes until pharmacy accept) | New | eRx | §11 + §2.5 | Patient view in app | Patient App + Website | 1 | 79 | 79 | Web, QA | P0 | No patient surface | Patient GET eRx by appointment; names redacted until Phase 14 accept; website optional view | Not Started
77 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.7 | ERX-07 | Print & PDF — printable and downloadable prescription | New | eRx | §11 | Print & PDF | Doctor + Patient | 1 | 80 | 80 | Web, QA | P1 | No eRx PDF | Patient copy without notes; doctor copy may include letterhead; SecureDocument store | Not Started
78 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.10 | ERX-10 | Repeat prescription / refill — patient requests; doctor approves or rejects from the mobile app (inbox on web too) | New | eRx | §11 + §3 + §2.7 | Repeat prescription / refill | Patient + Doctor mobile + Doctor web | 1 | 81 | 81 | Web, QA | P1 | Does not exist | RefillRequest against ErxSnapshot; doctor inbox; no case-taking on mobile | Not Started
79 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.1 | TEL-01 | Doctor availability — online or offline status and working hours | New | Telemedicine | §10 + §3 | Doctor availability | Doctor Web + Doctor App | 1 | 82 | 82 | Web, QA | P0 | E-CONSULT status + WhatsApp video stub only; no availability | TeleAvailability + heartbeat; working hours reuse daily schedule | Not Started
80 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.2 | TEL-02 | Telemedicine waiting queue — who is waiting, how long, whether they have paid | New | Telemedicine | §10 + §3 | Telemedicine waiting queue | Doctor Web + App | 1 | 83 | 83 | Web, QA | P0 | E-CONSULT list only | Queue by doctor + Online + paid/confirmed; wait time; Join | Not Started
81 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.3 | TEL-03 | Video consultation in browser — doctor consults directly from the web portal | New | Telemedicine | §10 | Video consultation in browser | Doctor Web Portal | 1 | 84 | 84 | Web, QA | P0 | SweetAlert WhatsApp stub | /teleconsult/:sessionId in-browser video; replace stub; vendor from PRE-03 | Not Started
82 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.5 | TEL-05 | Device check — camera, microphone and connection tested before joining | New | Telemedicine | §10 + §2.4 | Device check | Doctor Web + Patient | 1 | 85 | 85 | QA | P1 | Does not exist | Pre-join device/network check UI; block join on hard fail with guidance | Not Started
83 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.6 | TEL-06 | Waiting room — patient waits with live status until the doctor joins | New | Telemedicine | §10 + §2.4 | Waiting room | Patient | 1 | 86 | 86 | Web, QA | P1 | Does not exist | Waiting room page: position, doctor online, paid, estimated wait | Not Started
84 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.7 | TEL-07 | Recording consent — consent captured before the consultation; no recording without it | New | Telemedicine | §10 + §2.4 + §17 | Recording consent | Patient + Doctor | 1 | 87 | 87 | Web, QA | P0 | AudioCaseConsentLog only for audio case taking | ConsentRecord type TeleRecording; block record if declined; both sides see status | Not Started
85 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.8 | TEL-08 | Rejoin after dropped call — either side can rejoin the same consultation | New | Telemedicine | §10 + §2.4 | Rejoin after dropped call | Doctor + Patient | 1 | 88 | 88 | Web, QA | P0 | Does not exist | Session Active until End; rejoin tokens; dashboard Rejoin | Not Started
86 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.9 | TEL-09 | Join failure handling — clear fallback if the call cannot connect, with options to retry | New | Telemedicine | §10 + §2.4 | Join failure handling / Fallback & join failure handling | Doctor + Patient | 1 | 89 | 89 | Web, QA | P1 | Does not exist | Error codes; retry; support ticket deep link later; do not silently fail | Not Started
87 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.10 | TEL-10 | Case-linked chat — chat attached to the consultation record, not a loose message thread | New | Telemedicine | §10 + §2.4 | Case-linked chat | Doctor + Patient | 1 | 90 | 90 | Web, QA | P1 | Does not exist | Messages keyed by TeleSession/PatientAppId; retained with the case | Not Started
88 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.11 | TEL-11 | Consultation summary — issued to the patient at the end of the call | New | Telemedicine | §10 + §2.4 | Consultation summary | Patient + Doctor | 1 | 91 | 91 | Web, QA | P1 | Does not exist | Doctor submits summary (not private notes); patient sees immediately; may share eRx id | Not Started
89 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.12 | TEL-12 | Instant consultation — patient requests an immediate consultation with an available doctor | New | Telemedicine | §10 + §2.3 | Instant consultation / Instant consult request / Queue & doctor offer | Patient + Doctor | 1 | 92 | 92 | Web, QA | P1 | Does not exist | Instant request pool; offer doctor; patient accepts; optional surcharge from fee config | Not Started
90 | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.1 | COM-01 | SMS — appointment confirmation, registration confirmation, doctor-unavailable, OTP, reschedule and cancellation | New | Notifications | §14 | SMS | Shared | 1 | 93 | 93 | Web, QA | P0 | No SMS provider; WhatsApp exists separately | SmsProvider + templates + DLT; event hooks; DND/opt-out on Patient | Not Started
91 | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.2 | COM-02 | WhatsApp — templates, offers, health tips and bulk messaging with delivery reports and opt-out (complete remaining ~50%) | Existing Improvement | Notifications | §14 | WhatsApp | Doctor Web | 1 | 94 | 94 | Web, QA | P1 | Meta Cloud send/templates/campaigns live; bulk/opt-in/analytics incomplete | Finish bulk queue UX, template approval states, delivery reports, opt-out | Not Started
92 | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.3 | COM-03 | Push notifications — booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests | New | Notifications | §14 + §2.9 + §3 | Push notifications | Patient App + Doctor App | 1 | 95 | 95 | Web, QA | P0 | Does not exist | DeviceToken + FCM/APNs; event fan-out; apps register tokens in Phases 16–17 | Not Started
93 | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.4 | COM-04 | Email — registration, activation, password reset, invoices and receipts | Existing Improvement | Notifications | §14 | Email | Shared | 1 | 96 | 96 | Web, QA | P1 | SMTP used for activation/forgot (plaintext issue fixed in Phase 0); no invoice email | Template emails for listed events; invoice PDF attach via SEC-09 | Not Started
94 | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.5 | COM-05 | In-app notification centre — all alerts collected in one place for patients and doctors | New | Notifications | §14 + §2.8 | In-app notification centre / Notifications centre | Patient App + Doctor Web/App | 1 | 97 | 97 | Web, QA | P1 | Does not exist (Velzon notification demo is not product) | AppNotification inbox; mark read; do not use Velzon demo notifications | Not Started
95 | 13 | Phase 13 — Support & help desk (PDF §15) | 13.1 | SUP-01 | Patient support tickets — patients raise issues from the app and track them | New | Support | §15 + §2.9 | Patient support tickets / Help centre & support tickets | Patient App + Admin | 1 | 98 | 98 | Web, QA | P1 | Does not exist; EnquiryDetail is not tickets; Velzon tickets demo ignore | SupportTicket reporter=Patient; status track; not Enquiry, not Velzon /apps-tickets-* | Not Started
96 | 13 | Phase 13 — Support & help desk (PDF §15) | 13.2 | SUP-02 | Doctor support tickets — doctors raise issues from the portal | New | Support | §15 | Doctor support tickets | Doctor Web + Admin | 1 | 99 | 99 | Web, QA | P1 | Does not exist | Same ticket tables; reporter=Doctor | Not Started
97 | 13 | Phase 13 — Support & help desk (PDF §15) | 13.3 | SUP-03 | Admin issue queue — all issues in one queue with priority, assignment and status | New | Support | §15 + §7.2 | Admin issue queue / Support ticket queue | Admin Portal | 1 | 100 | 100 | Web, QA | P1 | Does not exist | /admin/support-tickets; SLA timestamps; assign | Not Started
98 | 13 | Phase 13 — Support & help desk (PDF §15) | 13.4 | SUP-04 | Ticket conversation — full message thread with attachments | New | Support | §15 | Ticket conversation | Admin + Doctor + Patient | 1 | 101 | 101 | Web, QA | P1 | Does not exist | Threaded messages + SEC-09 attachments | Not Started
99 | 13 | Phase 13 — Support & help desk (PDF §15) | 13.5 | SUP-05 | Enquiry management — website enquiries tracked (ties WEB-06) | Existing Improvement | Support | §15 + §4 | Enquiry management | Admin Portal | 1 | 102 | 102 | QA | P1 | API exists; inbox missing | Complete WEB-06 admin inbox if not already; convert enquiry → ticket optional | Not Started
100 | 13 | Phase 13 — Support & help desk (PDF §15) | 13.6 | SUP-06 | Help centre — self-service help content for patients | New | Support | §15 + §2.9 | Help centre | Patient Website + App | 1 | 103 | 103 | Web, QA | P2 | Does not exist | CMS articles or static help; searchable | Not Started
101 | 13 | Phase 13 — Support & help desk (PDF §15) | 13.7 | SUP-07 | Assisted booking — help for patients who need support booking | New | Support | §15 + §2.9 | Assisted booking | Support + Reception + Patient | 1 | 104 | 104 | Web, QA | P2 | Does not exist | Staff (admin/support/reception) can complete public booking on behalf of a patient with audit; patient app CTA to request assistance | Not Started
102 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.1 | MED-01 | Pharmacy partner onboarding — licensed premises, licence records, activation checklist | New | HomeoMeds | §12 + §7.2 | Pharmacy partner onboarding / Pharmacy partner management | Pharmacy + Admin | 1 | 105 | 105 | Web, QA | P0 | Does not exist | PharmacyPartner + licences; admin activation; pharmacy console login | Not Started
103 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.2 | MED-02 | Licence gating — expired or suspended licences blocked automatically from receiving orders | New | HomeoMeds | §12 | Licence gating | Backend | 1 | 106 | 106 | Web, QA | P0 | Does not exist | Scheduler; routing skip; banner on pharmacy console | Not Started
104 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.3 | MED-03 | Fulfilment consent & pharmacy selection — patient chooses the seller and consents before the prescription is shared | New | HomeoMeds | §12 + §2.7 | Fulfilment consent & pharmacy selection | Patient | 1 | 107 | 107 | Web, QA | P0 | Does not exist | ConsentRecord PharmacyShare; patient picks from routed sellers; share only after consent | Not Started
105 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.4 | MED-04 | Prescription handoff — signed prescription becomes the order directly — no re-entry, no transcription errors | New | HomeoMeds | §12 + §2.7 | Prescription handoff / Order start | Patient + Pharmacy | 1 | 108 | 108 | Web, QA | P0 | Does not exist | MedicineOrder copied from ErxSnapshot items (codes); pharmacy never types remedies | Not Started
106 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.5 | MED-05 | Rule-based seller routing — licence validity, service area, working hours and capacity | New | HomeoMeds | §12 | Rule-based seller routing | Backend | 1 | 109 | 109 | Web, QA | P0 | Does not exist | SellerRoutingRule engine | Not Started
107 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.6 | MED-06 | Manual stock confirmation — pharmacy confirms availability — no live inventory integration required | New | HomeoMeds | §12 | Manual stock confirmation | Pharmacy console | 1 | 110 | 110 | Web, QA | P0 | Does not exist | Accept/reject with stock flag; do not build inventory master | Not Started
108 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.7 | MED-07 | Pharmacy console — accept or reject, enter price quote, mark ready and dispatched | New | HomeoMeds | §12 | Pharmacy console | Pharmacy console | 1 | 111 | 111 | Web, QA | P0 | Does not exist | /pharmacy/orders list+detail; OTP accept (SEC-07); quote; ready; dispatched | Not Started
109 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.8 | MED-08 | Quote before payment — the patient always sees the price before paying | New | HomeoMeds | §12 + §2.7 | Quote before payment / Pharmacy selection & quote | Patient | 1 | 112 | 112 | Web, QA | P0 | Does not exist | MedicineQuote; patient must confirm quote; then PAY-07 | Not Started
110 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.9 | MED-09 | Payment or cash on delivery — both options, with status tracking | New | HomeoMeds | §12 + §9 | Payment or cash on delivery | Patient | 1 | 113 | 113 | Web, QA | P0 | Stream MEDICINE stub in Phase 6 | Online pay via PAY-02; COD_PENDING until pharmacy confirms collection | Not Started
111 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.10 | MED-10 | Order tracking — live status for the patient at every stage | New | HomeoMeds | §12 + §2.7 | Order tracking | Patient | 1 | 114 | 114 | Web, QA | P1 | Does not exist | Status timeline events; push updates COM-03 | Not Started
112 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.12 | MED-12 | Order exception queue — stuck, rejected or failed orders always surfaced — never silent | New | HomeoMeds | §12 | Order exception queue | Admin + Account | 1 | 115 | 115 | Web, QA | P0 | Does not exist | HomeoMeds exception queue; SLA; never drop | Not Started
113 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.14 | MED-14 | Refill orders — repeat orders raised from an existing prescription | New | HomeoMeds | §12 + §2.7 + §11 | Refill orders / Order detail & refill | Patient + Doctor | 1 | 116 | 116 | Web, QA | P1 | ERX-10 refill request exists | Approved refill creates a new MedicineOrder from the same snapshot; one-tap patient | Not Started
114 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.15 | MED-15 | Order review & consent (patient) — confirm and consent before the prescription is shared | New | HomeoMeds | §2.7 | Order review & consent | Patient | 1 | 117 | 117 | QA | P0 | Covered by MED-03; explicit review screen still required | Review screen listing codes (not names) + pharmacy + consent checkbox | Not Started
115 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.16 | MED-16 | Medicines tab — all medicine orders in one place (API now; app UI in Phase 16) | New | HomeoMeds | §2.7 | Medicines tab | Patient | 1 | 118 | 118 | Web, QA | P1 | Does not exist | GET my orders; website optional list; app tab Phase 16 | Not Started
116 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.1 | CON-01 | Family members — add family members under one account | New | Patient identity | §2.1 | Family members | Patient App (API now) | 1 | 119 | 119 | Web, QA | P0 | Does not exist | FamilyMember under Patient account; bookings can be for a member | Not Started
117 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.2 | CON-02 | Caregiver authorization — let a family member book and manage on their behalf | New | Patient identity | §2.1 | Caregiver authorization | Patient App (API now) | 1 | 120 | 120 | Web, QA | P0 | Does not exist | CaregiverAuth with scopes; OTP; withdrawable via consent centre | Not Started
118 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.3 | CON-03 | Records timeline + consultation note + document upload APIs | New | Patient records | §2.5 | Records timeline / Consultation note / Document upload | Patient App (API now) | 1 | 121 | 121 | Web, QA | P0 | Doctor history exists; no patient timeline; no patient upload | Patient timeline DTO (visits, summary, eRx codes, labs); consultation note = TEL-11 summary not private notes; uploads via SEC-09 | Not Started
119 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.4 | CON-04 | Follow-up plan & tasks — clear next steps after each consultation | New | Continuity | §2.6 | Follow-up plan & tasks | Doctor Web + Patient | 1 | 122 | 122 | Web, QA | P1 | Does not exist (follow-up option in notes does not save) | FollowUpTask created by doctor; patient sees tasks | Not Started
120 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.5 | CON-05 | Symptom diary — record symptoms between visits | New | Continuity | §2.6 | Symptom diary | Patient App (API now) | 1 | 123 | 123 | Web, QA | P1 | Does not exist | SymptomDiary entries; doctor can read on board | Not Started
121 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.6 | CON-06 | Progress tracking — see improvement over time across visits | New | Continuity | §2.6 | Progress tracking | Patient + Doctor | 1 | 124 | 124 | Web, QA | P2 | Does not exist | Progress series from diary + visit outcomes; not a fake chart | Not Started
122 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.7 | CON-07 | Consent centre & data rights — view, manage and withdraw consents; request data | New | Privacy | §17 + §2.8 | Consent centre & data rights | Patient App (API now) | 1 | 125 | 125 | Web, QA | P0 | ConsentRecord from Phase 0 | Patient list/withdraw; data export request (DPDP); deletion request workflow | Not Started
123 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.10 | CON-10 | Patient profile setup API — name, age, gender, contact and health basics | New | Patient identity | §2.1 | Profile setup | Patient App (API now) | 1 | 126 | 126 | Web, QA | P0 | Clinic-created Patient exists; no self-serve profile product | Patient profile fields + health basics; used by OTP-verified patient token | Not Started
124 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.1 | RPT-01 | Admin overview dashboard — platform-wide activity at a glance (replace Velzon ecommerce) | Existing Improvement | Reports | §16 + §7.2 | Admin overview dashboard / Admin dashboard | Admin Portal | 1 | 127 | 127 | Web, QA | P0 | Velzon ecommerce dashboard 0% product; login lands /dashboard | True /admin/dashboard KPIs: doctors, credentialing, bookings, GMV, failed payments, tickets, HomeoMeds exceptions; redirect /dashboard away from StoreVisits | Not Started
125 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.2 | RPT-02 | Doctor practice statistics — patient and consultation trends (extend existing charts) | Existing Improvement | Reports | §16 + §5.1 | Doctor practice statistics | Doctor Web | 1 | 128 | 128 | Web, QA | P1 | Patient stats charts live | Keep as foundation; ensure visit type/mode included after APT-02 | Not Started
126 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.3 | RPT-03 | Follow-up analysis — due/overdue patients and follow-up conversion | New | Reports | §16 | Follow-up analysis | Doctor Web | 1 | 129 | 129 | Web, QA | P1 | Does not exist; follow-up option in notes does not save | /doctor/follow-up-analysis from VisitType + CON-04 tasks | Not Started
127 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.4 | RPT-04 | Clinic performance analysis — appointments, slot utilisation, no-shows, cancellations, waiting time and revenue | New | Reports | §16 | Clinic performance analysis | Doctor Web | 1 | 130 | 130 | Web, QA | P1 | Does not exist | /doctor/clinic-performance including payment collected and tele duration if timed | Not Started
128 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.5 | RPT-05 | Payment reconciliation report — bookings matched against payments | New | Reports | §16 + §7.2 | Payment reconciliation report / Consult booking & payment reconciliation | Admin + Account | 1 | 131 | 131 | Web, QA | P1 | FIN-02 built the queue; this is the report/export | Exportable report from the same reconciliation query | Not Started
129 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.6 | RPT-06 | Settlement & payout reports — amounts due and paid to doctors and pharmacies | New | Reports | §16 + §8 | Settlement & payout reports | Account | 1 | 132 | 132 | Web, QA | P1 | FIN-04/05 exist as ops screens | Formal report/export of runs and payouts | Not Started
130 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.8 | RPT-08 | Doctor earnings summary — daily, weekly and monthly earnings with payout status (web + same API as DMO-10) | New | Reports | §16 + §3 | Doctor earnings summary | Doctor Web + App | 1 | 133 | 133 | Web, QA | P1 | Does not exist | Web earnings page using same API as doctor app | Not Started
131 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.9 | RPT-09 | Medicine order reports — order volumes, fulfilment and exceptions | New | Reports | §16 + §12 | Medicine order reports | Admin + Account | 1 | 134 | 134 | Web, QA | P1 | Does not exist | Volumes, SLA, exception counts from HomeoMeds | Not Started
132 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.10 | RPT-10 | Platform users remaining 20% — import, export and activation control | Existing Improvement | Admin | §7.2 | Platform users | Admin Portal | 1 | 135 | 135 | Web, QA | P1 | List/Add/Edit live; Import/Export buttons dead; no verification column | Wire Import/Export; verification column; activate/lock; link credentialing | Not Started

## 07_Mobile_Main_Tasks
Mobile MAIN TASKS — execute sub-tasks in Mobile Sequential sheet filtered by Main Task ID. Do not start a Main Task if Sister Tracks includes Web and those Web rows are not Done (API/DB first).
Seq | Phase | Phase Name | WBS | Main Task ID | Main Task | Work Type(s) | Module | PDF Section | PDF Feature | Surface | Sub-task count | First Track Seq | Last Track Seq | Sister Tracks | Priority (highest) | AS-IS | TO-BE | Status
1 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.2 | FND-02 | Delivery footprint — 2 mobile apps · 5 web portals · payment · telemedicine · digital prescription · HomeoMeds (programme skeleton) | New | Platform | §1 | Delivery covers | Shared | 1 | 1 | 1 | Web, UI | P0 | 1 web SPA (Admin/Doctor/Reception + marketing). No patient app, doctor app, Account portal, Pharmacy console | Repo/route skeleton: Patient Website, Doctor Web, Reception, Admin, Account (+ Pharmacy console under HomeoMeds); Patient + Doctor mobile later | Not Started
2 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.1 | PAT-01 | Patient app — language selection on first open | New | Patient Mobile | §2.1 | Language selection | Patient Mobile App | 3 | 2 | 4 | QA | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
3 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.2 | PAT-02 | Patient app — welcome and introduction | New | Patient Mobile | §2.1 | Welcome & introduction | Patient Mobile App | 3 | 5 | 7 | QA | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
4 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.3 | PAT-03 | Patient app — mobile number + OTP login (PatientAuth) | New | Patient Mobile | §2.1 | Mobile number + OTP login | Patient Mobile App | 3 | 8 | 10 | QA | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
5 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.4 | PAT-04 | Patient app — profile setup | New | Patient Mobile | §2.1 | Profile setup | Patient Mobile App | 3 | 11 | 13 | QA | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
6 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.5 | PAT-05 | Patient app — privacy consent before data stored | New | Patient Mobile | §2.1 | Privacy consent | Patient Mobile App | 3 | 14 | 16 | QA | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
7 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.6 | PAT-06 | Patient app — family members | New | Patient Mobile | §2.1 | Family members | Patient Mobile App | 3 | 17 | 19 | QA | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
8 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.7 | PAT-07 | Patient app — caregiver authorization | New | Patient Mobile | §2.1 | Caregiver authorization | Patient Mobile App | 3 | 20 | 22 | QA | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
9 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.8 | PAT-08 | Patient app — home dashboard | New | Patient Mobile | §2.2 | Home dashboard | Patient Mobile App | 3 | 23 | 25 | QA | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
10 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.9 | PAT-09 | Patient app — search and care categories | New | Patient Mobile | §2.2 | Search & care categories | Patient Mobile App | 3 | 26 | 28 | QA | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
11 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.10 | PAT-10 | Patient app — search results | New | Patient Mobile | §2.2 | Search results | Patient Mobile App | 3 | 29 | 31 | QA | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
12 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.11 | PAT-11 | Patient app — discovery filters | New | Patient Mobile | §2.2 | Filters | Patient Mobile App | 3 | 32 | 34 | QA | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
13 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.12 | PAT-12 | Patient app — doctor profile | New | Patient Mobile | §2.2 | Doctor profile | Patient Mobile App | 3 | 35 | 37 | QA | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
14 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.13 | PAT-13 | Patient app — verified badge on doctor | New | Patient Mobile | §2.2 | Credentials & verification | Patient Mobile App | 3 | 38 | 40 | QA | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
15 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.14 | PAT-14 | Patient app — ranking explanation | New | Patient Mobile | §2.2 | Ranking explanation | Patient Mobile App | 3 | 41 | 43 | QA | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
16 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.15 | PAT-15 | Patient app — health articles | New | Patient Mobile | §2.2 | Health articles | Patient Mobile App | 3 | 44 | 46 | QA | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
17 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.16 | PAT-16 | Patient app — slot picker | New | Patient Mobile | §2.3 | Slot picker | Patient Mobile App | 3 | 47 | 49 | QA | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
18 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.17 | PAT-17 | Patient app — booking review and consent | New | Patient Mobile | §2.3 | Booking review & consent | Patient Mobile App | 3 | 50 | 52 | QA | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
19 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.18 | PAT-18 | Patient app — checkout | New | Patient Mobile | §2.3 | Checkout | Patient Mobile App | 3 | 53 | 55 | QA | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
20 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.19 | PAT-19 | Patient app — payment status | New | Patient Mobile | §2.3 | Payment status | Patient Mobile App | 3 | 56 | 58 | QA | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
21 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.20 | PAT-20 | Patient app — appointment detail | New | Patient Mobile | §2.3 | Appointment detail | Patient Mobile App | 3 | 59 | 61 | QA | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
22 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.21 | PAT-21 | Patient app — reschedule | New | Patient Mobile | §2.3 | Reschedule appointment | Patient Mobile App | 3 | 62 | 64 | QA | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
23 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.22 | PAT-22 | Patient app — cancel | New | Patient Mobile | §2.3 | Cancel appointment | Patient Mobile App | 3 | 65 | 67 | QA | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
24 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.23 | PAT-23 | Patient app — waitlist offer | New | Patient Mobile | §2.3 | Waitlist offer | Patient Mobile App | 3 | 68 | 70 | QA | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
25 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.24 | PAT-24 | Patient app — instant consult request | New | Patient Mobile | §2.3 | Instant consult request | Patient Mobile App | 3 | 71 | 73 | QA | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
26 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.25 | PAT-25 | Patient app — queue and doctor offer | New | Patient Mobile | §2.3 | Queue & doctor offer | Patient Mobile App | 3 | 74 | 76 | QA | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
27 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.26 | PAT-26 | Patient app — device check | New | Patient Mobile | §2.4 | Device check | Patient Mobile App | 3 | 77 | 79 | QA | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
28 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.27 | PAT-27 | Patient app — waiting room | New | Patient Mobile | §2.4 | Waiting room | Patient Mobile App | 3 | 80 | 82 | QA | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
29 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.28 | PAT-28 | Patient app — live video | New | Patient Mobile | §2.4 | Live video consultation | Patient Mobile App | 3 | 83 | 85 | QA | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
30 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.29 | PAT-29 | Patient app — recording consent | New | Patient Mobile | §2.4 | Recording consent | Patient Mobile App | 3 | 86 | 88 | QA | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
31 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.30 | PAT-30 | Patient app — join failure fallback | New | Patient Mobile | §2.4 | Fallback & join failure handling | Patient Mobile App | 3 | 89 | 91 | QA | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
32 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.31 | PAT-31 | Patient app — case-linked chat | New | Patient Mobile | §2.4 | Case-linked chat | Patient Mobile App | 3 | 92 | 94 | QA | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
33 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.32 | PAT-32 | Patient app — consultation summary | New | Patient Mobile | §2.4 | Consultation summary | Patient Mobile App | 3 | 95 | 97 | QA | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
34 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.33 | PAT-33 | Patient app — rejoin | New | Patient Mobile | §2.4 | Rejoin after dropped call | Patient Mobile App | 3 | 98 | 100 | QA | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
35 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.34 | PAT-34 | Patient app — records timeline | New | Patient Mobile | §2.5 | Records timeline | Patient Mobile App | 3 | 101 | 103 | QA | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
36 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.35 | PAT-35 | Patient app — consultation note (summary, not private notes) | New | Patient Mobile | §2.5 | Consultation note | Patient Mobile App | 3 | 104 | 106 | QA | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
37 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.36 | PAT-36 | Patient app — signed eRx (codes until pharmacy accept) | New | Patient Mobile | §2.5 | Signed digital prescription | Patient Mobile App | 3 | 107 | 109 | QA | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
38 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.37 | PAT-37 | Patient app — document upload | New | Patient Mobile | §2.5 | Document upload | Patient Mobile App | 3 | 110 | 112 | QA | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
39 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.38 | PAT-38 | Patient app — follow-up plan and tasks | New | Patient Mobile | §2.6 | Follow-up plan & tasks | Patient Mobile App | 3 | 113 | 115 | QA | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
40 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.39 | PAT-39 | Patient app — symptom diary | New | Patient Mobile | §2.6 | Symptom diary | Patient Mobile App | 3 | 116 | 118 | QA | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
41 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.40 | PAT-40 | Patient app — progress tracking | New | Patient Mobile | §2.6 | Progress tracking | Patient Mobile App | 3 | 119 | 121 | QA | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
42 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.41 | PAT-41 | Patient app — medicines tab | New | Patient Mobile | §2.7 | Medicines tab | Patient Mobile App | 3 | 122 | 124 | QA | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
43 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.42 | PAT-42 | Patient app — start HomeoMeds order from eRx | New | Patient Mobile | §2.7 | Order start | Patient Mobile App | 3 | 125 | 127 | QA | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
44 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.43 | PAT-43 | Patient app — pharmacy selection and quote | New | Patient Mobile | §2.7 | Pharmacy selection & quote | Patient Mobile App | 3 | 128 | 130 | QA | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
45 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.44 | PAT-44 | Patient app — order review and consent | New | Patient Mobile | §2.7 | Order review & consent | Patient Mobile App | 3 | 131 | 133 | QA | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
46 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.45 | PAT-45 | Patient app — order tracking | New | Patient Mobile | §2.7 | Order tracking | Patient Mobile App | 3 | 134 | 136 | QA | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
47 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.46 | PAT-46 | Patient app — order detail and refill | New | Patient Mobile | §2.7 | Order detail & refill | Patient Mobile App | 3 | 137 | 139 | QA | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
48 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.47 | PAT-47 | Patient app — write a review | New | Patient Mobile | §2.8 | Write a review | Patient Mobile App | 3 | 140 | 142 | QA | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
49 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.48 | PAT-48 | Patient app — my reviews and appeal | New | Patient Mobile | §2.8 | My reviews & appeal | Patient Mobile App | 3 | 143 | 145 | QA | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
50 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.49 | PAT-49 | Patient app — payments and refunds | New | Patient Mobile | §2.8 | Payments & refunds | Patient Mobile App | 3 | 146 | 148 | QA | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
51 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.50 | PAT-50 | Patient app — profile and settings | New | Patient Mobile | §2.8 | Profile & settings | Patient Mobile App | 3 | 149 | 151 | QA | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
52 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.51 | PAT-51 | Patient app — consent centre and data rights | New | Patient Mobile | §2.8 | Consent centre & data rights | Patient Mobile App | 3 | 152 | 154 | QA | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
53 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.52 | PAT-52 | Patient app — notifications centre | New | Patient Mobile | §2.8 | Notifications centre | Patient Mobile App | 3 | 155 | 157 | QA | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
54 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.53 | PAT-53 | Patient app — help centre and tickets | New | Patient Mobile | §2.9 | Help centre & support tickets | Patient Mobile App | 3 | 158 | 160 | QA | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
55 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.54 | PAT-54 | Patient app — physical clinic booking | New | Patient Mobile | §2.9 | Physical clinic appointment | Patient Mobile App | 3 | 161 | 163 | QA | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
56 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.55 | PAT-55 | Patient app — assisted booking request | New | Patient Mobile | §2.9 | Assisted booking | Patient Mobile App | 3 | 164 | 166 | QA | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
57 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.56 | PAT-56 | Patient app — low-data mode | New | Patient Mobile | §2.9 | Low-data mode | Patient Mobile App | 3 | 167 | 169 | QA | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
58 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.57 | PAT-57 | Patient app — push notifications | New | Patient Mobile | §2.9 | Push notifications | Patient Mobile App | 3 | 170 | 172 | QA | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
59 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.58 | PAT-58 | Patient app — iOS and Android store release, device matrix, and parity QA | New, New Integration | Patient Mobile | §2 + §18 | Patient mobile app iOS and Android | Patient Mobile App | 2 | 173 | 174 | QA | P0 | No app | Store builds; crash-free join; feature parity checklist against every §2 row | Not Started
60 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.1 | DMO-01 | Doctor app — login & identity (same login and same account as the web portal) | New | Doctor Mobile | §3 | Login & identity | Doctor Mobile App | 3 | 175 | 177 | QA | P0 | No doctor app | Same Account login + DoctorId; bind device; no separate doctor identity | Not Started
61 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.2 | DMO-02 | Doctor app — first-run onboarding (guided setup, number confirmation and permissions) | New | Doctor Mobile | §3 | First-run onboarding | Doctor Mobile App | 3 | 178 | 180 | QA | P1 | No app | Confirm registered mobile; permission primer | Not Started
62 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.3 | DMO-03 | Doctor app — notification permissions (push, microphone and camera handled properly) | New | Doctor Mobile | §3 | Notification permissions | Doctor Mobile App | 3 | 181 | 183 | QA | P0 | No app | OS permission flows; settings deep link if denied | Not Started
63 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.4 | DMO-04 | Doctor app — today’s queue & schedule (the full day at a glance) | New | Doctor Mobile | §3 | Today’s queue & schedule | Doctor Mobile App | 3 | 184 | 186 | QA | P0 | No app | Appointment list APIs; payment + tele flags; no Patient Board | Not Started
64 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.5 | DMO-05 | Doctor app — availability toggle (go online or offline, set working hours) | New | Doctor Mobile | §3 | Availability toggle | Doctor Mobile App | 3 | 187 | 189 | QA | P0 | No app | Same TeleAvailability + schedule APIs as web | Not Started
65 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.6 | DMO-06 | Doctor app — push notifications (waiting, booking, reschedule, cancellation, refill, payment received) | New | Doctor Mobile | §3 | Push notifications | Doctor Mobile App | 3 | 190 | 192 | QA | P0 | No app | Consume COM-03 doctor templates | Not Started
66 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.7 | DMO-07 | Doctor app — patient context card (name, age, chief complaint and last visit) — NO case-taking | New | Doctor Mobile | §3 | Patient context card | Doctor Mobile App | 3 | 193 | 195 | QA | P0 | No app; PDF: detailed case-taking stays on the web portal | Read-only card; explicitly no repertory/audio/Rx compose | Not Started
67 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.8 | DMO-08 | Doctor app — join consultation (video or audio from the phone) | New | Doctor Mobile | §3 | Join consultation | Doctor Mobile App | 3 | 196 | 198 | QA | P0 | No app | Same session tokens as TEL-03/04 | Not Started
68 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.9 | DMO-09 | Doctor app — refill approval (approve or reject repeat prescription requests) | New | Doctor Mobile | §3 + §11 | Refill approval | Doctor Mobile App | 3 | 199 | 201 | QA | P0 | No app | ERX-10 inbox; approve only — Patient Board remains web | Not Started
69 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.10 | DMO-10 | Doctor app — earnings summary (today, this week, this month, with payout status) | New | Doctor Mobile | §3 + §16 | Earnings summary | Doctor Mobile App | 3 | 202 | 204 | QA | P1 | No app | Account ledger read model for this DoctorId — not a second money system | Not Started
70 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.11 | DMO-11 | Doctor app — offline handling (weak connection or expired session) | New | Doctor Mobile | §3 | Offline handling | Doctor Mobile App | 3 | 205 | 207 | QA | P1 | No app | Queued actions policy (do not fake join); session expiry uses SEC-03 | Not Started
71 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.12 | DMO-12 | Doctor app — reliability monitoring (failures reported automatically) | New Integration | Doctor Mobile | §3 | Reliability monitoring | Doctor Mobile App | 1 | 208 | 208 | QA | P1 | No app | Crash/error SDK; join failures also as TeleSessionEvent | Not Started
72 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.13 | DMO-13 | Doctor app — iOS and Android parity QA (queue, availability, notifications, context, video, refill, earnings) | New | Doctor Mobile | §3 + §18 | Doctor mobile app iOS and Android | Doctor Mobile App | 1 | 209 | 209 | QA | P0 | No app | Parity checklist for every §3 row on both OS | Not Started

## 08_QA_Main_Tasks
QA MAIN TASKS — execute sub-tasks in QA Sequential sheet filtered by Main Task ID. Do not start a Main Task if Sister Tracks includes Web and those Web rows are not Done (API/DB first).
Seq | Phase | Phase Name | WBS | Main Task ID | Main Task | Work Type(s) | Module | PDF Section | PDF Feature | Surface | Sub-task count | First Track Seq | Last Track Seq | Sister Tracks | Priority (highest) | AS-IS | TO-BE | Status
1 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.1 | FND-01 | One connected ecosystem — shared keys so a patient, appointment, prescription and payment created anywhere are visible everywhere | Regression | Platform | §1 | One connected ecosystem serving six types of users | Shared | 1 | 1 | 1 | Web | P2 | Doctor/Admin/Reception web only; Patient, Account, Pharmacy roles do not exist; no shared payment or eRx keys | Canonical keys: UserId/DoctorId, PatientId, PatientAppId, CaseId, ErxId, LedgerTxnId, MedicineOrderId — used by every surface | Not Started
2 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.3 | SEC-01 | Secure login — protected credentials for every user type | Regression | Security | §17 | Secure login | All web + later mobile | 1 | 2 | 2 | Web, UI | P0 | POST /Account/Login on classic API; JWT in sessionStorage; doctor/user passwords compared plaintext; reception hashed on classic; fakeBackend() still mounted | Hashed passwords; Role claim on JWT; disable fake backend for production paths; Patient OTP login is Phase 8 (not password) | Not Started
3 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.4 | SEC-02 | Secure password reset — time-limited reset links (stop plaintext email + fake thunk) | Regression | Security | §17 | Secure password reset | Admin / Doctor / Reception web | 1 | 3 | 3 | Web, UI | P0 | /forgot-password UI exists; thunk uses fake/Firebase; POST /users/ForgetPassword emails plaintext password | Tokenised reset (hash, TTL); email contains link only; ChangePassword for logged-in user | Not Started
4 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.5 | SEC-03 | Session control — proper sign-out across web and mobile | Regression | Security | §17 | Session control | All | 1 | 4 | 4 | Web, UI | P0 | Client clears sessionStorage; no server logout / token revoke; UserLoginStatus unused | POST Logout persists login status; optional token denylist; mobile will call the same API in Phase 16/17 | Not Started
5 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.6 | SEC-04 | Role-based access — each role sees only what it is permitted to see | Regression | Security | §17 | Role-based access | Admin / All web | 1 | 5 | 5 | Web, UI | P0 | RoleMaster + RoleDetail + MenuMaster exist; GetMenuByRole commented out on .NET 8; no per-route frontend ACL — any authenticated URL works | Re-enable GetMenuByRole; AuthProtected deny-by-default; [Authorize(Roles=)] on money/clinical APIs; Account cannot edit repertory; Admin cannot approve payouts | Not Started
6 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.7 | SEC-05 | Patient data protection — health records restricted to the treating doctor and the patient | Regression | Security | §17 | Patient data protection | API | 1 | 6 | 6 | Web | P0 | Many repertory APIs have [Authorize] commented; directory browsing enabled for /attachments and /Blogs; no patient-scoped ACL on case data | Every case/Rx/note/lab query filtered by treating DoctorId (or PatientId for patient token); disable directory browsing | Not Started
7 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.8 | SEC-06 | Consent records infrastructure — every consent captured, stored and reviewable | Regression | Security / Trust | §17 | Consent records | Shared | 1 | 7 | 7 | Web | P0 | AudioCaseConsentLog exists for audio case taking only | ConsentRecord (PatientId, Type, Version, GrantedAt, WithdrawnAt, SourceSurface) covering privacy, booking, recording, pharmacy share, marketing | Not Started
8 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.9 | SEC-07 | OTP verification infrastructure — applied to sensitive actions including payouts and pharmacy acceptance | Regression | Security | §17 + §8 + §12 | OTP verification | Shared | 1 | 8 | 8 | Web | P0 | No generic OTP control plane; patient OTP login does not exist | OtpChallenge + OtpAuditLog; Account/Admin can query who/when/entity/success without seeing card data | Not Started
9 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.10 | SEC-08 | Complete audit trail — who did what and when across payments, prescriptions and approvals | Regression | Security | §17 + §9 | Complete audit trail | Shared | 1 | 9 | 9 | Web | P2 | No platform-wide audit; no AppointmentChangeLog; no payment webhook store | Append-only AuditEvent for money, eRx sign, credentialing, payout, pharmacy accept; payments get a dedicated trail in Phase 6 | Not Started
10 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.11 | SEC-09 | Secure documents — prescriptions, reports and uploads protected from unauthorised access | Regression | Security | §17 | Secure documents | Shared | 1 | 10 | 10 | Web | P1 | Attachments served with directory browsing; no signed URLs; no patient upload module | Authorised download; virus-scan hook; patient uploads in Phase 15 use this store | Not Started
11 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.1 | ADM-R01 | Keep and harden Admin Repertory sections (do not rebuild) | Existing | Repertory | §7.1 | Repertory sections | Admin Portal | 1 | 11 | 11 | Web | P2 | Admin Repertory section CRUD live (pages/Admin/Repertory) | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
12 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.2 | ADM-R02 | Keep and harden Admin Subsection & rubric tree (do not rebuild) | Existing | Repertory | §7.1 | Subsection & rubric tree | Admin Portal | 1 | 12 | 12 | Web | P2 | Hierarchical subsection/rubric tree + Excel import/export live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
13 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.3 | ADM-R03 | Keep and harden Admin Rubric–remedy mapping (do not rebuild) | Existing | Repertory | §7.1 | Rubric–remedy mapping | Admin Portal | 1 | 13 | 13 | Web | P2 | Rubric-remedy mapping by author/grade live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
14 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.4 | ADM-R04 | Keep and harden Admin Remedy-linked rubrics (do not rebuild) | Existing | Repertory | §7.1 | Remedy-linked rubrics | Admin Portal | 1 | 14 | 14 | Web | P2 | Remedial-rubrics viewer live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
15 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.5 | ADM-R05 | Keep and harden Admin Language master (do not rebuild) | Existing | Repertory | §7.1 | Language master | Admin Portal | 1 | 15 | 15 | Web | P2 | Language master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
16 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.6 | ADM-R06 | Keep and harden Admin Body part master (do not rebuild) | Existing | Repertory | §7.1 | Body part master | Admin Portal | 1 | 16 | 16 | Web | P2 | Body part master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
17 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.7 | ADM-R07 | Keep and harden Admin Intensity master (do not rebuild) | Existing | Repertory | §7.1 | Intensity master | Admin Portal | 1 | 17 | 17 | Web | P2 | Intensity master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
18 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.8 | ADM-R08 | Keep and harden Admin Remedy master (do not rebuild) | Existing | Repertory | §7.1 | Remedy master | Admin Portal | 1 | 18 | 18 | Web | P2 | Remedy master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
19 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.9 | ADM-R09 | Keep and harden Admin Remedy grade master (do not rebuild) | Existing | Repertory | §7.1 | Remedy grade master | Admin Portal | 1 | 19 | 19 | Web | P2 | Remedy grade master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
20 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.10 | ADM-M01 | Keep and harden Admin Author master (do not rebuild) | Existing | Materia Medica | §7.1 | Author master | Admin Portal | 1 | 20 | 20 | Web | P2 | Author master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
21 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.11 | ADM-M02 | Keep and harden Admin Materia medica master (do not rebuild) | Existing | Materia Medica | §7.1 | Materia medica master | Admin Portal | 1 | 21 | 21 | Web | P2 | MM master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
22 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.12 | ADM-M03 | Keep and harden Admin Materia medica heads (do not rebuild) | Existing | Materia Medica | §7.1 | Materia medica heads | Admin Portal | 1 | 22 | 22 | Web | P2 | MM heads live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
23 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.13 | ADM-M04 | Keep and harden Admin Materia medica remedies (do not rebuild) | Existing | Materia Medica | §7.1 | Materia medica remedies | Admin Portal | 1 | 23 | 23 | Web | P2 | Remedy-wise MM viewer live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
24 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.14 | ADM-D01 | Keep and harden Admin Diagnosis system (do not rebuild) | Existing | Diagnosis | §7.1 | Diagnosis system | Admin Portal | 1 | 24 | 24 | Web | P2 | Diagnosis system CRUD live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
25 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.15 | ADM-D02 | Keep and harden Admin Diagnosis therapeutics (do not rebuild) | Existing | Diagnosis | §7.1 | Diagnosis therapeutics | Admin Portal | 1 | 25 | 25 | Web | P2 | Therapeutics details live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
26 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.16 | ADM-D03 | Keep and harden Admin Diagnosis conditions (do not rebuild) | Existing | Diagnosis | §7.1 | Diagnosis conditions | Admin Portal | 1 | 26 | 26 | Web | P2 | Conditions + keyword→rubric live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
27 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.17 | ADM-A01 | Keep and harden Admin Drug system (do not rebuild) | Existing | Adverse Effect | §7.1 | Drug system | Admin Portal | 1 | 27 | 27 | Web | P2 | Drug system CRUD live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
28 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.18 | ADM-A02 | Keep and harden Admin Drug group (do not rebuild) | Existing | Adverse Effect | §7.1 | Drug group | Admin Portal | 1 | 28 | 28 | Web | P2 | Drug group CRUD live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
29 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.19 | ADM-A03 | Keep and harden Admin Allopathic drug & side effects (do not rebuild) | Existing | Adverse Effect | §7.1 | Allopathic drug & side effects | Admin Portal | 1 | 29 | 29 | Web | P2 | Allopathic drug + serious/other/adverse live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
30 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.20 | ADM-Q01 | Keep and harden Admin Question section, group & sub-group (do not rebuild) | Existing | Clinical Questions | §7.1 | Question section, group & sub-group | Admin Portal | 1 | 30 | 30 | Web | P2 | Existance / question group / subgroup CRUD live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
31 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.21 | ADM-Q02 | Keep and harden Admin Clinical question mapping (do not rebuild) | Existing | Clinical Questions | §7.1 | Clinical question mapping | Admin Portal | 1 | 31 | 31 | Web | P2 | Clinical questions mapped to body parts and rubrics live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
32 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.22 | ADM-3D1 | Keep and harden Admin 3D mesh key master (do not rebuild) | Existing | 3D Body | §7.1 | 3D mesh key master | Admin Portal | 1 | 32 | 32 | Web | P2 | Mesh key master on .NET 8 live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
33 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.23 | ADM-3D2 | Keep and harden Admin 3D section master (do not rebuild) | Existing | 3D Body | §7.1 | 3D section master | Admin Portal | 1 | 33 | 33 | Web | P2 | 3D section master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
34 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.24 | ADM-3D3 | Keep and harden Admin 3D hotspots (do not rebuild) | Existing | 3D Body | §7.1 | 3D hotspots | Admin Portal | 1 | 34 | 34 | Web | P2 | Hotspot master live; doctor viewer consumes them | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
35 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.25 | ADM-B01 | Business Management — Doctor qualifications (existing, used later by credentialing) | Existing | Business Management | §7.2 | Doctor qualifications | Admin Portal | 1 | 35 | 35 | Web | P2 | Qualifications CRUD on newer API live; used by RegisterDoctor | Keep; credentialing Phase 8 will reference QualificationId | Not Started
36 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.26 | ADM-B02 | Business Management — Lab & imaging test catalog (existing, used by eRx lab orders) | Existing | Business Management | §7.2 | Lab & imaging test catalog | Admin Portal | 1 | 36 | 36 | Web | P2 | Labs & imaging CRUD live; Patient Board orders from this catalogue | Keep; eRx Phase 10 continues to use the same catalogue | Not Started
37 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.27 | ADM-B03 | Business Management — Subscription packages (existing S1 SaaS; later tied to Account ledger) | Existing | Business Management | §7.2 | Subscription packages | Admin Portal | 1 | 37 | 37 | Web | P2 | Package CRUD live; Razorpay buy/renew partial (no webhook) | Do not overload PackageEntryDetail for consult/medicine money; Phase 6 ports payment verification | Not Started
38 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.28 | ADM-B04 | Business Management — Roles & menu permissions (existing DB, runtime ACL leftover) | Regression | Business Management | §7.2 | Roles & menu permissions | Admin Portal | 1 | 38 | 38 | Web, UI | P1 | Role CRUD screens live; runtime GetMenuByRole commented; no frontend route ACL | This is the product surface for SEC-04; complete wiring here | Not Started
39 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.1 | CLN-01 | Clinical workspace — single screen for the entire consultation | Regression | Patient Board | §5.3 | Clinical workspace | Doctor Web Portal | 1 | 39 | 39 | Web, UI | P1 | PatientBoard.js (~13.5k) is the workspace; ~90% — missing payment/tele/eRx header status | Keep one screen; add header chips for payment, tele session, signed eRx (chips light up as later phases land) | Not Started
40 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.2 | CLN-02 | Manual case taking — structured case taking (keep) | Existing | Patient Board | §5.3 | Manual case taking | Doctor Web Portal | 1 | 40 | 40 | Web | P2 | Classic case-taking tabs live | Regression only; do not rebuild | Not Started
41 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.3 | CLN-03 | Body parts & intensity selection (keep) | Existing | Patient Board | §5.3 | Body parts & intensity selection | Doctor Web Portal | 1 | 41 | 41 | Web | P2 | Body Parts tab + intensity chips live | Regression; intensity master from Phase 1 still drives chips | Not Started
42 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.4 | CLN-04 | Clinical questions — guided questions by section, group and sub-group (keep) | Existing | Patient Board | §5.3 | Clinical questions | Doctor Web Portal | 1 | 42 | 42 | Web | P2 | Questions tab loads Existance taxonomy live | Regression | Not Started
43 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.5 | CLN-05 | Diagnosis, therapeutics & pattern search (keep) | Existing | Patient Board | §5.3 | Diagnosis, therapeutics & pattern search | Doctor Web Portal | 1 | 43 | 43 | Web | P2 | Clinical Pattern tab live (13 keyword tabs + therapeutics) | Regression | Not Started
44 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.6 | CLN-06 | Repertory rubric search & selection (keep) | Existing | Patient Board | §5.3 | Repertory rubric search & selection | Doctor Web Portal | 1 | 44 | 44 | Web | P2 | Repertory tree + search live | Regression; small UX polish allowed but not a rewrite | Not Started
45 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.7 | CLN-07 | Manage selected rubrics — review, edit and remove (remaining ~10%) | Regression | Patient Board | §5.3 | Manage selected rubrics | Doctor Web Portal | 1 | 45 | 45 | Web, UI | P1 | Clipboard exists; confirm-delete / intensity-edit incomplete | Confirm delete; edit intensity on selected rubric; no accidental wipe | Not Started
46 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.8 | CLN-08 | Audio case taking — record and receive suggested rubrics (keep engine; do not rebuild) | Existing | Audio AI | §5.3 | Audio case taking | Doctor Web Portal | 1 | 46 | 46 | Web | P1 | Whisper + rubric engines + CaseTaking UI live on .NET 8 | Keep; follow existing AUDIO_CASE_TAKING_* docs; accuracy is the next task | Not Started
47 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.9 | CLN-09 | Improved rubric accuracy — enhanced accuracy rules for audio-based rubric suggestions | Regression | Audio AI | §5.3 | Improved rubric accuracy | Doctor Web Portal + Admin intelligence | 1 | 47 | 47 | Web, UI | P1 | Engine + admin metaphors/aliases exist; accuracy rules still in progress (~50%) | Complete accuracy rules per AUDIO_CASE_TAKING_AI_ENGINE docs; metaphor/alias QA | Not Started
48 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.10 | CLN-10 | Materia medica reference during consultation (remaining ~10%) | Regression | Patient Board | §5.3 | Materia medica reference | Doctor Web Portal | 1 | 48 | 48 | Web, UI | P2 | MM tab + repertorize differential accordion ~90% | Faster head navigation during case; do not rebuild MM masters | Not Started
49 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.11 | CLN-11 | Allopathic drug side-effect lookup (keep) | Existing | Patient Board | §5.3 | Allopathic drug side-effect lookup | Doctor Web Portal | 1 | 49 | 49 | Web | P2 | Adverse Effect tab live | Regression | Not Started
50 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.12 | CLN-12 | Repertorization & elimination (remaining ~10%) | Regression | Patient Board | §5.3 | Repertorization & elimination | Doctor Web Portal | 1 | 50 | 50 | Web, UI | P1 | Common/uncommon/elimination live ~90% | Stability polish; Center of Gravity is a NEW panel on the same rubrics (next task) | Not Started
51 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.13 | CLN-13 | Center of Gravity — new analysis identifying the central remedy of the case, with reasoning shown | Regression | Repertorization | §5.3 | Center of Gravity | Doctor Web Portal | 1 | 51 | 51 | Web, UI | P1 | Does not exist | POST /api/Repertorization/CenterOfGravity from selected rubric ids + intensities; UI panel with explainability | Not Started
52 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.14 | CLN-14 | Lab orders & lab entries (keep; later also sit on eRx) | Existing | Patient Board | §5.3 + §11 | Lab orders & lab entries | Doctor Web Portal | 1 | 52 | 52 | Web | P2 | Lab order + result entry on prescription modal live | Keep; when eRx splits notes from Rx, labs stay on the prescription/eRx side | Not Started
53 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.15 | CLN-15 | Appointment history notes (keep; split from eRx in Phase 10) | Existing | Patient Board | §5.3 | Appointment history notes | Doctor Web Portal | 1 | 53 | 53 | Web | P1 | AppointmentHistoryNote APIs live (classic); currently mixed into Rx modal tabs | Keep save/get; Phase 10 moves UX outside Rx modal and adds NoteType / IsErxExcluded | Not Started
54 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.16 | CLN-16 | Complaints & case details — wire Patient Board to existing SaveComplaints / SaveCaseDetails (~20% today) | Regression | Patient Board | §5.3 | Complaints & case details | Doctor Web Portal | 1 | 54 | 54 | Web, UI | P1 | Classic SaveComplaints / SaveCaseDetails APIs exist; Patient Board does not call them | Call the existing APIs from the board; Reception case-paper (Phase 5) uses a subset | Not Started
55 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.17 | CLN-17 | Patient back history — complete history of visits, notes, prescriptions and payments | Regression | Patient Board | §5.3 | Patient back history | Doctor Web Portal | 1 | 55 | 55 | Web, UI | P1 | History panel ~70%; no payment line (payments do not exist yet) | Timeline: visits, notes, eRx, labs; payment row added when Phase 6 lands (placeholder now) | Not Started
56 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.18 | CLN-18 | Export case data — download the full case in Excel or PDF | Regression | Patient Board | §5.3 | Export case data | Doctor Web Portal | 1 | 56 | 56 | Web, UI | P1 | Newer ExportCasesToExcel exists; no Patient Board export UI; no PDF | Toolbar Excel + PDF using existing Excel API + new PDF renderer; exclude private notes from patient-facing PDF (eRx print is Phase 10) | Not Started
57 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.19 | CLN-19 | Session restore — continue exactly where the doctor left off, across multiple patients (keep) | Existing | Patient Board | §5.3 | Session restore | Doctor Web Portal | 1 | 57 | 57 | Web | P2 | Up to 5 in-memory sessions + DoctorPatientBoardBackup live | Regression; header stack remains | Not Started
58 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.20 | CLN-20 | 3D anatomy viewer — interactive 3D body model linked to rubric search (remaining ~50%) | Regression | Anatomy | §5.3 | 3D anatomy viewer | Doctor Web Portal | 1 | 58 | 58 | Web, UI | P2 | three.js viewer + hotspot→search live; incomplete mesh coverage / UX | Complete GLB/hotspot coverage; mobile fallback later; admin 3D masters already in Phase 1 | Not Started
59 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.1 | DOC-01 | Doctor home dashboard — complete overview of the working day (remaining ~30%) | Regression | Doctor Dashboard | §5.1 | Doctor home dashboard | Doctor Web Portal | 1 | 59 | 59 | Web, UI | P1 | Widgets + BestSellingProducts ~70%; missing online toggle, tele queue, payment badges, follow-up due | Extend, do not replace; later phases light up tele/payment chips | Not Started
60 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.2 | DOC-02 | Patient counts & waiting list — live counts by status with quick actions (keep; extend paid/unpaid) | Existing | Doctor Dashboard | §5.1 | Patient counts & waiting list | Doctor Web Portal | 1 | 60 | 60 | Web | P1 | Status buckets WAITING, WALK-IN, NOT ARRIVED, E-CONSULT, REMAINING, COMPLETED live | Keep; add CANCELLED in Phase 4; paid/unpaid badge in Phase 6 | Not Started
61 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.3 | DOC-03 | Patient search, list & open case (remaining ~10%) | Regression | Doctor Dashboard | §5.1 | Patient search, list & open case | Doctor Web Portal | 1 | 61 | 61 | Web, UI | P1 | Search/list/open ~90%; missing last visit, unpaid, family filters | Add last-visit column; unpaid/family after those modules exist | Not Started
62 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.4 | DOC-04 | Add new patient — register a patient in seconds (keep) | Existing | Patients | §5.1 | Add new patient | Doctor Web Portal | 1 | 62 | 62 | Web | P1 | Create patient live | Regression; public self-registration is a different Patient identity in Phase 9 | Not Started
63 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.5 | DOC-05 | Import patients — bring existing patient records in bulk (keep) | Existing | Patients | §5.1 | Import patients | Doctor Web Portal | 1 | 63 | 63 | Web | P2 | Import live | Regression | Not Started
64 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.6 | DOC-06 | Export patients — download patient data in Excel, CSV or PDF (keep) | Regression | Patients | §5.1 | Export patients | Doctor Web Portal | 1 | 64 | 64 | Web, UI | P2 | Export live (confirm PDF vs Excel/CSV in QA) | If PDF is missing, add it as Existing Improvement; do not skip the PDF wording in the PDF | Not Started
65 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.7 | DOC-07 | Recent activity panel (keep) | Existing | Doctor Dashboard | §5.1 | Recent activity panel | Doctor Web Portal | 1 | 65 | 65 | Web | P2 | Recent activity live | Regression; later include payment/tele events when those exist | Not Started
66 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.8 | DOC-08 | Patient statistics charts (keep; foundation for clinic performance in Phase 18) | Existing | Doctor Dashboard | §5.1 | Patient statistics charts | Doctor Web Portal | 1 | 66 | 66 | Web | P2 | GetPatientStats / GetPatientStatsCharts + ApexCharts live | Keep; clinic performance report extends this in Phase 18 | Not Started
67 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.9 | DOC-09 | Manage reception staff — add, edit and remove reception users (backend done, UI absent) | Regression | Staff | §5.1 | Manage reception staff | Doctor Web Portal | 1 | 67 | 67 | Web, UI | P1 | .NET 8 api/ReceptionStaff CRUD exists; no SPA page | List/add/edit/disable at /doctor/reception-staff; doctor owns the staff record | Not Started
68 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.10 | DOC-10 | Doctor profile — clinic details, consultation fee, photo, qualifications, working hours, bank details | Regression | Doctor Profile | §5.1 | Doctor profile | Doctor Web Portal | 1 | 68 | 68 | Web, UI | P0 | /profile is Velzon first_name only (~20%); credentials sit on Doctor entity; no fee/KYC UI | Real doctor profile: clinic, photo, qualifications, consult fee (feeds Phase 6), hours (feeds schedule), bank KYC (feeds Account payees) | Not Started
69 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.1 | APT-01 | Appointment list & waiting patients — full day view with live status (keep; later payment/tele) | Existing | Appointments | §5.2 | Appointment list & waiting patients | Doctor Web Portal | 1 | 69 | 69 | Web | P1 | Day list + status live | Keep; reschedule/cancel/payment attach to this list | Not Started
70 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.2 | APT-02 | Create new appointment — persist visit type, consultation mode and fee | Regression | Appointments | §5.2 | Create new appointment | Doctor Web Portal | 1 | 70 | 70 | Web, UI | P0 | Create appointment ~90%; Formik modal has no VisitType / ConsultMode / fee | VisitType First/Follow-up; ConsultMode In-clinic / E-Consult; fee display from doctor profile / ConsultFeeConfig | Not Started
71 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.3 | APT-03 | Appointment status update — move patients through the visit stages (keep) | Existing | Appointments | §5.2 | Appointment status update | Doctor Web Portal | 1 | 71 | 71 | Web | P1 | Status transitions live | Keep; add CANCELLED in APT-06; do not reuse DeleteStatus as cancel | Not Started
72 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.4 | APT-04 | Appointment time update — adjust timings as the day runs (keep; distinct from formal reschedule) | Existing | Appointments | §5.2 | Appointment time update | Doctor Web Portal | 1 | 72 | 72 | Web | P1 | UpdateAppointmentTime live — changes a time only; no audit/notify | Keep same-day time tweak; formal reschedule (old→new, notify, conflict) is APT-05 | Not Started
73 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.5 | APT-05 | Reschedule appointment — move to a new slot with automatic patient notification (NEW — not a rename of UpdateAppointmentTime) | Regression | Appointments | §5.2 + §2.3 + §6 | Reschedule appointment | Doctor Web + Reception + later Patient | 1 | 73 | 73 | Web, UI | P0 | Time can be edited; no formal Reschedule (audit, notify, old→new confirm) | POST RescheduleAppointment; AppointmentChangeLog; conflict 409 with alternatives; SMS/WhatsApp fan-out (notify failure must not roll back) | Not Started
74 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.6 | APT-06 | Cancel appointment — reason, free the slot, trigger refund where applicable (NEW CANCELLED status — do NOT reuse DeleteStatus) | Regression | Appointments | §5.2 + §2.3 + §6 | Cancel appointment | Doctor Web + Reception + later Patient | 1 | 74 | 74 | Web, UI | P0 | No CANCELLED; DeleteStatus is soft-delete only | CANCELLED + reason fields; free slot; waitlist hook; if PAID evaluate refund policy (Phase 6/7) | Not Started
75 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.7 | APT-07 | Daily schedule setup — define working days, hours and break times (promote modal to first-class screen) | Regression | Scheduling | §5.2 | Daily schedule setup | Doctor Web Portal | 1 | 75 | 75 | Web, UI | P0 | DailyScheduleSetupModal + GetDailySchedule / SaveDailySchedule exist; not a first-class screen (draft marked 0%) | Promote to /doctor/schedule with week grid and copy-day; reuse existing APIs — do not rebuild | Not Started
76 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.8 | APT-08 | Appointment slot grid — visual slot-by-slot view of the day (keep; public booking reuses this) | Existing | Scheduling | §5.2 | Appointment slot grid | Doctor Web Portal | 1 | 76 | 76 | Web | P0 | Slot picker / grid live | Keep; Phase 9 public APIs reuse the same slot engine | Not Started
77 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.9 | APT-09 | Consultation payment status on every appointment (schema now; values live in Phase 6) | Regression | Appointments | §5.2 + §9 | Consultation payment status | Doctor Web Portal | 1 | 77 | 77 | Web, UI | P0 | No PaymentStatus on appointment | Add PaymentStatus UNPAID / PENDING / PAID / FAILED / PAY_AT_CLINIC / REFUNDED; UI badge; source of truth is webhook in Phase 6 not the client screen | Not Started
78 | 5 | Phase 5 — Reception portal (PDF §6) | 5.1 | REC-01 | Reception login — secure staff access (keep) | Existing | Reception | §6 | Reception login | Reception Portal | 1 | 78 | 78 | Web | P1 | Reception logs in via Account; JWT includes DoctorID; uses doctor dashboard layout | Keep login; Phase 0 hashing applies; later dedicated reception chrome | Not Started
79 | 5 | Phase 5 — Reception portal (PDF §6) | 5.2 | REC-02 | Reception profile — manage own profile details (0% today) | Regression | Reception | §6 | Reception profile | Reception Portal | 1 | 79 | 79 | Web, UI | P1 | No reception-specific profile; shared Velzon /profile | Name, mobile, attached doctor (read-only); cannot edit doctor bank/fee | Not Started
80 | 5 | Phase 5 — Reception portal (PDF §6) | 5.3 | REC-03 | Reception home dashboard — purpose-built front-desk dashboard (not only hidden doctor actions) | Regression | Reception | §6 | Reception home dashboard | Reception Portal | 1 | 80 | 80 | UI | P1 | Same /doctordashboard with some clinical actions disabled ~90% | Reception-first chrome: queue, collect pay, case paper, no repertory/Rx; optional /reception home route | Not Started
81 | 5 | Phase 5 — Reception portal (PDF §6) | 5.4 | REC-04 | Create patient — register a walk-in patient quickly (keep) | Existing | Reception | §6 | Create patient | Reception Portal | 1 | 81 | 81 | Web | P1 | Create patient live on shared dashboard | Keep on reception chrome | Not Started
82 | 5 | Phase 5 — Reception portal (PDF §6) | 5.5 | REC-05 | Patient search & list — find any patient instantly (keep) | Existing | Reception | §6 | Patient search & list | Reception Portal | 1 | 82 | 82 | Web | P1 | Search live | Keep; no opening full clinical board | Not Started
83 | 5 | Phase 5 — Reception portal (PDF §6) | 5.6 | REC-06 | Create & manage appointments — full appointment management (keep; plus reschedule/cancel from Phase 4) | Regression | Reception | §6 | Create & manage appointments | Reception Portal | 1 | 83 | 83 | Web, UI | P0 | Create/status/time live; reschedule/cancel missing until Phase 4 APIs | Enable RescheduleAppointment and CancelAppointment for JWT DoctorId; isReceptionUser must not block | Not Started
84 | 5 | Phase 5 — Reception portal (PDF §6) | 5.7 | REC-07 | New appointment — book on behalf of the patient (keep; same VisitType/ConsultMode/fee as APT-02) | Regression | Reception | §6 | New appointment | Reception Portal | 1 | 84 | 84 | UI | P1 | New appointment modal live; fields incomplete until APT-02 | Same modal fields as doctor so public booking later matches staff-created rows | Not Started
85 | 5 | Phase 5 — Reception portal (PDF §6) | 5.8 | REC-08 | Waiting queue management — manage the live queue and call the next patient | Regression | Reception | §6 | Waiting queue management | Reception Portal | 1 | 85 | 85 | Web, UI | P1 | Status buckets ~60%; no dedicated queue UX / call-next | Dedicated queue: walk-in vs tele; payment state; Call next; notify patient (later push) | Not Started
86 | 5 | Phase 5 — Reception portal (PDF §6) | 5.9 | REC-09 | Appointment status update (reception) — update as patients arrive and are seen (keep) | Existing | Reception | §6 | Appointment status update | Reception Portal | 1 | 86 | 86 | Web | P1 | Status update live | Keep on reception chrome | Not Started
87 | 5 | Phase 5 — Reception portal (PDF §6) | 5.10 | REC-10 | Appointment time update (reception) — adjust timings through the day (keep) | Existing | Reception | §6 | Appointment time update | Reception Portal | 1 | 87 | 87 | Web | P2 | Time update live | Keep; formal reschedule remains REC-06 | Not Started
88 | 5 | Phase 5 — Reception portal (PDF §6) | 5.11 | REC-11 | View doctor schedule — see the doctor’s working schedule (read-only) | Regression | Reception | §6 | View doctor schedule | Reception Portal | 1 | 88 | 88 | UI | P1 | GetDailySchedule exists; no reception view | Read-only /reception/schedule using DoctorID from JWT | Not Started
89 | 5 | Phase 5 — Reception portal (PDF §6) | 5.12 | REC-12 | Log case paper / chief complaint — record the reason for visit before the consultation | Regression | Reception | §6 | Log case paper / chief complaint | Reception Portal | 1 | 89 | 89 | Web, UI | P1 | Missing; SaveComplaints exists but board is doctor-only | Restricted case-paper form (chief complaint only — no repertory/Rx); audit reception author | Not Started
90 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.1 | PAY-01 | Consultation fee configuration — each doctor’s fee set and displayed to patients | Regression | Payments | §9 | Consultation fee configuration | Doctor profile + Public + Admin | 1 | 90 | 90 | Web, UI | P0 | No ConsultFeeConfig; doctor profile work in DOC-10 may have stored a fee field | ConsultFeeConfig (InClinic, EConsult, optional Instant surcharge, PayAtClinicEnabled, GST flags) | Not Started
91 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.2 | PAY-02 | Automatic payment verification — bank/webhook is source of truth, not the patient’s screen | Regression | Payments | §9 | Automatic payment verification | Shared | 1 | 91 | 91 | Web | P0 | Razorpay checkout for S1 subscription only; no webhook; no signature verify on server | Port Razorpay to .NET 8; keys in config; POST /api/Payments/Webhook/Razorpay anonymous + signature verify; PaymentOrder table | Not Started
92 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.3 | PAY-03 | Online consultation payment — patient pays by card, UPI, netbanking or wallet | Regression | Payments | §9 + §4 + §2.3 | Online consultation payment | Public web + later Patient app | 1 | 92 | 92 | Web, UI | P0 | Does not exist (only S1 SaaS) | CreateConsultOrder attached to PatientAppId; Razorpay Checkout; webhook sets PAID; do not overload PackageEntryDetail | Not Started
93 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.4 | PAY-04 | Reception payment collection — cash, UPI, card or payment link with printed receipt | Regression | Payments | §9 + §6 | Reception payment collection | Reception Portal | 1 | 93 | 93 | Web, UI | P0 | Does not exist | CollectAtReception writes ledger S3; print receipt; payment-link uses same Razorpay order as online | Not Started
94 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.5 | PAY-05 | Pay-at-clinic option — book now, pay at the clinic where the doctor allows it | Regression | Payments | §9 | Pay-at-clinic option | Public + Doctor + Reception | 1 | 94 | 94 | Web, UI | P1 | Does not exist | PayAtClinicEnabled on fee config; appointment PaymentStatus=PAY_AT_CLINIC; tele queue may still require PAID (policy) | Not Started
95 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.6 | PAY-06 | Doctor subscription payment — buy and renew subscription packages (complete remaining ~30%) | Regression | Payments | §9 | Doctor subscription payment | Doctor Web Portal | 1 | 95 | 95 | Web, UI | P1 | Checkout works ~70%; no webhook, refund, invoice, GST, Account ledger | Same webhook spine; write S1 ledger; invoice; failed pay UX; PackageEntryDetail shape UNCHANGED | Not Started
96 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.7 | PAY-07 | Medicine payment — pay online or cash on delivery (API contract now; HomeoMeds Phase 14 implements orders) | Regression | Payments | §9 + §12 | Medicine payment | Shared | 1 | 96 | 96 | Web | P2 | Does not exist | PaymentOrder.Stream=MEDICINE; COD_PENDING until pharmacy confirms collection; do not mix with consult money | Not Started
97 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.8 | PAY-08 | Payment status everywhere — doctor, reception and patient all see the same payment status | Regression | Payments | §9 | Payment status everywhere | All | 1 | 97 | 97 | Web, UI | P0 | No shared status | Single PaymentStatus on appointment/order; all DTOs read it; never a second client-only flag | Not Started
98 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.9 | PAY-09 | Refunds — processed and tracked against the original payment | Regression | Payments | §9 + §8 + §2.8 | Refunds | Account + Patient | 1 | 98 | 98 | Web, UI | P0 | Does not exist | Refund entity against original PaymentOrder; Razorpay refund API; cancel-appointment hook; patient sees status | Not Started
99 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.10 | PAY-10 | Payment receipts & invoices — issued for every transaction | Regression | Payments | §9 + §8 | Payment receipts & invoices | All | 1 | 99 | 99 | Web, UI | P1 | No invoice entity | Invoice numbering series from PRE-02; PDF receipt; GST fields; email in Phase 12 | Not Started
100 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.11 | PAY-11 | Complete payment audit trail — every transaction traceable end to end by Homeocentrum | Regression | Payments | §9 + §17 | Complete audit trail | Account | 1 | 100 | 100 | Web | P0 | No webhook store | PaymentEvent raw payloads + AuditEvent + OtpAudit for payouts; Account can reconstruct without Razorpay dashboard | Not Started
101 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.1 | FIN-01 | Unified transaction ledger — every rupee that moves through the platform, in one record | Regression | Account | §8 | Unified transaction ledger | Account Portal | 1 | 101 | 101 | Web, UI | P0 | Does not exist | Append-only LedgerEntry for S1–S7; filters; OTP audit link; Admin may view, Account owns movement | Not Started
102 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.2 | FIN-02 | Consultation payment reconciliation — online payments and reception collections matched and verified | Regression | Account | §8 + §7.2 + §16 | Consultation payment reconciliation | Account + Admin | 1 | 102 | 102 | Web, UI | P0 | Does not exist | Join booking ↔ payment ↔ appointment; KPI collected/pending/failed/refunded; CSV | Not Started
103 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.3 | FIN-03 | Medicine ledger — medicine money tracked separately from consultation money | Regression | Account | §8 + §12 | Medicine ledger | Account Portal | 1 | 103 | 103 | Web, UI | P1 | Does not exist | /account/medicine-ledger; Stream=MEDICINE; seller/platform/delivery split columns; filled in Phase 14 | Not Started
104 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.4 | FIN-04 | Settlement runs — scheduled settlement of amounts due to doctors and pharmacies | Regression | Account | §8 + §16 | Settlement runs | Account Portal | 1 | 104 | 104 | Web, UI | P0 | Does not exist | SettlementRun job T+N hold; net of commission/GST/refunds; pharmacies after Phase 14 | Not Started
105 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.5 | FIN-05 | Payout approval — payouts released only after OTP-verified approval | Regression | Account | §8 + §17 | Payout approval | Account Portal | 1 | 105 | 105 | Web, UI | P0 | Does not exist | ApprovePayout requires SEC-07 OTP; Admin cannot approve; NEFT/file or gateway per PRE-01 | Not Started
106 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.6 | FIN-06 | Refund processing — Account issues and tracks refunds (uses PAY-09) | Regression | Account | §8 | Refund processing | Account Portal | 1 | 106 | 106 | Web, UI | P0 | Does not exist | /account/refunds UI on PAY-09 APIs; OTP if policy requires | Not Started
107 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.7 | FIN-07 | Payment exception handling — investigate and resolve every failed or disputed payment | Regression | Account | §8 + §7.2 | Payment exception handling | Account + Admin | 1 | 107 | 107 | Web, UI | P0 | Does not exist | Exception queue Failed/Partial/Webhook-mismatch/Refund-pending; retry/resolve with OTP on manual reconcile | Not Started
108 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.8 | FIN-08 | GST & invoice reports — invoice numbering and tax reporting | Regression | Account | §8 + §16 | GST & invoice reports | Account Portal | 1 | 108 | 108 | Web, UI | P1 | Does not exist | /account/tax export using Invoice table and PRE-02 GST treatment — configuration not hardcoded | Not Started
109 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.9 | FIN-09 | Payee records — bank and KYC details for doctors and pharmacies | Regression | Account | §8 | Payee records | Account Portal | 1 | 109 | 109 | Web, UI | P1 | Doctor bank fields added in DOC-10; no Account UI; no pharmacy | /account/payees; OTP on doctor KYC change (fraud); pharmacies after Phase 14 | Not Started
110 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.10 | FIN-10 | Clinic collection view — cash and UPI collected at reception, per clinic and per day | Regression | Account | §8 | Clinic collection view | Account Portal | 1 | 110 | 110 | Web, UI | P1 | Does not exist | /account/clinic-collections from CollectAtReception rows; respect PRE-02 retain vs remit | Not Started
111 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.11 | FIN-11 | Separation of duties — Account controls money; Admin controls platform and clinical data | Regression | Account | §8 | Separation of duties | Admin + Account | 1 | 111 | 111 | Web | P0 | Account role does not exist | Enforce in RBAC: Admin cannot ApprovePayout; Account cannot edit repertory/users’ clinical masters | Not Started
112 | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.1 | TRU-01 | Doctor credentialing — doctors upload qualification and registration documents for review | Regression | Trust | §13 + §7.2 | Doctor credentialing | Doctor Web + Admin | 1 | 112 | 112 | Web, UI | P0 | RegisterDoctor activates immediately; PassingUniversity/CertNo/QualificationId exist; no document store/queue | DoctorCredentialDocument + VerificationStatus Pending; do not auto-activate practice for public directory | Not Started
113 | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.2 | TRU-02 | Verification review — Admin approves, rejects or requests further information | Regression | Trust | §13 + §7.2 | Verification review | Admin Portal | 1 | 113 | 113 | Web, UI | P0 | Does not exist | /admin/doctor-credentialing list + detail; email notify doctor | Not Started
114 | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.3 | TRU-03 | Verified badge — patients see which doctors have been verified | Regression | Trust | §13 + §2.2 | Verified badge / Credentials & verification | Public + Patient app | 1 | 114 | 114 | Web, UI | P0 | Does not exist | Badge on public doctor card and profile from VerificationStatus=Approved | Not Started
115 | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.4 | TRU-04 | Practice gate — only verified doctors appear to patients and take paid consultations | Regression | Trust | §13 | Practice gate | Public + Payments | 1 | 115 | 115 | Web | P0 | Any activated doctor could theoretically be listed; no public list yet | Public search and CreateConsultOrder require Approved; own-clinic staff booking may still work per PRE-03 | Not Started
116 | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.5 | TRU-05 | Patient reviews — patients rate and review consultations | Regression | Trust | §13 + §2.8 | Patient reviews / Write a review | Patient + Public | 1 | 116 | 116 | Web, UI | P1 | Does not exist | Review linked to PatientAppId; one review per visit; moderation flag optional | Not Started
117 | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.6 | TRU-06 | Review appeal — doctors can appeal a review; patients manage reviews and raise an appeal | Regression | Trust | §13 + §2.8 | Review appeal / My reviews & appeal | Doctor + Patient + Admin | 1 | 117 | 117 | Web, UI | P2 | Does not exist | Appeal entity; admin resolves; patient my-reviews list | Not Started
118 | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.7 | TRU-07 | Ranking transparency — patients are shown why doctors are ranked as they are | Regression | Trust | §13 + §2.2 | Ranking transparency / Ranking explanation | Public + Patient app | 1 | 118 | 118 | Web, UI | P1 | Does not exist | Documented ranking factors (verified, availability, fee, reviews, experience) + explain API/UI | Not Started
119 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.1 | WEB-01 | Product home page — complete public website presenting the service | Regression | Patient Website | §4 | Product home page | Patient Website | 1 | 119 | 119 | Web, UI | P1 | HomeoJobLanding ~50%; Velzon leftovers; CTAs incomplete for book/trust/apps | Book CTA, verified doctors, consult+SaaS pricing teaser, app download placeholders | Not Started
120 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.2 | WEB-02 | Consultation & subscription pricing — transparent pricing display | Regression | Patient Website | §4 | Consultation & subscription pricing | Patient Website | 1 | 120 | 120 | UI | P1 | SaaS package marketing /pricing exists; no consult fee display per doctor | Keep SaaS pricing; add consult fee on doctor cards from ConsultFeeConfig | Not Started
121 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.3 | WEB-03 | Doctor discovery — browse and search verified doctors | Regression | Patient Website | §4 + §2.2 | Doctor discovery | Patient Website | 1 | 121 | 121 | Web, UI | P0 | Does not exist as a patient product (marketing only) | /book search: name, condition, category; filters availability, fee, experience, language, location | Not Started
122 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.4 | WEB-04 | Self-service booking — book an appointment online without calling the clinic | Regression | Patient Website | §4 + §2.3 | Self-service booking | Patient Website | 1 | 122 | 122 | Web, UI | P0 | Staff-only appointments | Funnel /book/:id/slots → review+consent → create Patient+Appointment; OTP; rate-limit; respect schedule + unpaid hold policy PRE-03 | Not Started
123 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.5 | WEB-05 | Online consultation payment on website — pay the fee at the time of booking | Regression | Patient Website | §4 + §9 | Online consultation payment | Patient Website | 1 | 123 | 123 | UI | P0 | Does not exist | Checkout uses PAY-03; success/fail pages; pay-at-clinic branch from PAY-05 | Not Started
124 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.6 | WEB-06 | Contact & enquiry form — enquiries reach the admin team and are tracked | Regression | Patient Website | §4 + §15 | Contact & enquiry form | Patient Website + Admin | 1 | 124 | 124 | Web, UI | P1 | EnquiryDetail API exists; public form partial; admin inbox screen missing | Confirmation + enquiry id; /admin/enquiries inbox; optional convert to SupportTicket | Not Started
125 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.7 | WEB-07 | Privacy policy — covering data protection, recording and pharmacy consent | Regression | Legal | §4 + §17 | Privacy policy | Patient Website | 1 | 125 | 125 | UI | P0 | Privacy page partial; not DPDP/tele/pharmacy complete | Publish PRE-03 legal copy: DPDP, recording, pharmacy, data-rights, family/caregiver | Not Started
126 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.8 | WEB-08 | Terms of service — covering payments, refunds, telemedicine and medicine orders | Regression | Legal | §4 | Terms of service | Patient Website | 1 | 126 | 126 | UI | P0 | Terms partial | Payments, refunds, telemedicine, HomeoMeds, codes-before-names | Not Started
127 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.9 | WEB-09 | Doctor self-registration — doctors apply to join the platform online | Regression | Patient Website | §4 | Doctor self-registration | Public | 1 | 127 | 127 | Web, UI | P0 | RegisterDoctor ~90%; activates immediately; no document upload | Document upload; pending-verification message; TRU-01 status Pending | Not Started
128 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.10 | WEB-10 | Email activation — secure account activation by email link | Regression | Auth | §4 | Email activation | Public | 1 | 128 | 128 | Web, UI | P1 | ActivateUser via /login?UserId= ~90%; align with verification; expiry/resend incomplete | Token expiry, resend, align with credentialing (activation ≠ verified practice) | Not Started
129 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.11 | WEB-11 | Waitlist offer — get offered a slot when one is freed by a cancellation (patient website + later app) | Regression | Booking | §2.3 | Waitlist offer | Patient Website + App | 1 | 129 | 129 | Web, UI | P2 | Cancel hook stub in Phase 4; no waitlist records | BookingWaitlist; on cancel, offer FIFO; timeout | Not Started
130 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.12 | WEB-12 | Health articles — educational content to build trust and engagement | Regression | Patient Website | §2.2 | Health articles | Patient Website + App | 1 | 130 | 130 | UI | P2 | Blog/news APIs on classic exist for marketing | Reuse blog/news as health articles on public site and later patient app; admin already has news/blog | Not Started
131 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.1 | ERX-01 | Potency module — every remedy carries a defined potency from a managed list, no free text | Regression | eRx | §11 | Potency module | Doctor Web + Admin | 1 | 131 | 131 | Web, UI | P0 | Dose saved as empty free-text dose: '' | PotencyMaster CRUD; PotencyId on PrescriptionRemedyDetail; stop empty Dose | Not Started
132 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.2 | ERX-02 | Dosage details — frequency, duration and instructions recorded clearly | Regression | eRx | §11 | Dosage details | Doctor Web Portal | 1 | 132 | 132 | Web, UI | P0 | Unstructured/empty dose | Frequency, Duration, Instructions fields on each remedy line | Not Started
133 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.3 | ERX-03 | Visit notes kept separate from the prescription — private clinical notes never appear on the prescription given to the patient or pharmacy | Regression | eRx | §11 + §5.3 | Visit notes kept separate from the prescription | Doctor Web Portal | 1 | 133 | 133 | Web, UI | P0 | History notes mixed into Rx modal tabs | Visit Notes panel outside Rx; NoteType; IsErxExcluded; eRx print has remedies+labs only | Not Started
134 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.4 | ERX-04 | Signed digital prescription — issued and locked once signed, so it cannot be altered afterwards | Regression | eRx | §11 + §2.5 + §5.3 | Signed digital prescription | Doctor Web | 1 | 134 | 134 | Web, UI | P0 | SavePrescriptionDetail overwritable; no lock/sign | ErxSnapshot immutable on sign; subsequent edits create a new unsigned draft not a silent mutate | Not Started
135 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.5 | ERX-05 | Prescription history — every prescription stored against the patient and visit | Regression | eRx | §11 | Prescription history | Doctor + Patient | 1 | 135 | 135 | Web, UI | P1 | Rx saved per appointment but no signed history product | List snapshots by PatientId; open past visit eRx | Not Started
136 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.6 | ERX-06 | Patient view of prescription in app — patient sees the prescription immediately (codes until pharmacy accept) | Regression | eRx | §11 + §2.5 | Patient view in app | Patient App + Website | 1 | 136 | 136 | Web, UI | P0 | No patient surface | Patient GET eRx by appointment; names redacted until Phase 14 accept; website optional view | Not Started
137 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.7 | ERX-07 | Print & PDF — printable and downloadable prescription | Regression | eRx | §11 | Print & PDF | Doctor + Patient | 1 | 137 | 137 | Web, UI | P1 | No eRx PDF | Patient copy without notes; doctor copy may include letterhead; SecureDocument store | Not Started
138 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.8 | ERX-08 | Remedy code protection — patient sees remedy codes rather than names until a licensed pharmacy accepts the order | Regression | eRx | §11 | Remedy code protection | Patient | 1 | 138 | 138 | Web | P0 | Does not exist | Code map on snapshot items; patient serializer strips names; doctor always sees names | Not Started
139 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.10 | ERX-10 | Repeat prescription / refill — patient requests; doctor approves or rejects from the mobile app (inbox on web too) | Regression | eRx | §11 + §3 + §2.7 | Repeat prescription / refill | Patient + Doctor mobile + Doctor web | 1 | 139 | 139 | Web, UI | P1 | Does not exist | RefillRequest against ErxSnapshot; doctor inbox; no case-taking on mobile | Not Started
140 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.11 | ERX-11 | Lab orders alongside the prescription (keep existing labs on eRx snapshot) | Regression | eRx | §11 | Lab orders | Doctor Web | 1 | 140 | 140 | Web | P1 | Labs on Rx modal live | Include lab orders in signed snapshot; still not on private notes | Not Started
141 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.1 | TEL-01 | Doctor availability — online or offline status and working hours | Regression | Telemedicine | §10 + §3 | Doctor availability | Doctor Web + Doctor App | 1 | 141 | 141 | Web, UI | P0 | E-CONSULT status + WhatsApp video stub only; no availability | TeleAvailability + heartbeat; working hours reuse daily schedule | Not Started
142 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.2 | TEL-02 | Telemedicine waiting queue — who is waiting, how long, whether they have paid | Regression | Telemedicine | §10 + §3 | Telemedicine waiting queue | Doctor Web + App | 1 | 142 | 142 | Web, UI | P0 | E-CONSULT list only | Queue by doctor + Online + paid/confirmed; wait time; Join | Not Started
143 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.3 | TEL-03 | Video consultation in browser — doctor consults directly from the web portal | Regression | Telemedicine | §10 | Video consultation in browser | Doctor Web Portal | 1 | 143 | 143 | Web, UI | P0 | SweetAlert WhatsApp stub | /teleconsult/:sessionId in-browser video; replace stub; vendor from PRE-03 | Not Started
144 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.4 | TEL-04 | Video consultation on mobile — doctor and patient both consult from the app (apps in 16–17; same session tokens) | Regression | Telemedicine | §10 + §2.4 + §3 | Video consultation on mobile | Patient App + Doctor App | 1 | 144 | 144 | Web | P0 | No apps | Same TeleSession tokens; mobile join implemented in Phases 16–17 against this API | Not Started
145 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.5 | TEL-05 | Device check — camera, microphone and connection tested before joining | Regression | Telemedicine | §10 + §2.4 | Device check | Doctor Web + Patient | 1 | 145 | 145 | UI | P1 | Does not exist | Pre-join device/network check UI; block join on hard fail with guidance | Not Started
146 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.6 | TEL-06 | Waiting room — patient waits with live status until the doctor joins | Regression | Telemedicine | §10 + §2.4 | Waiting room | Patient | 1 | 146 | 146 | Web, UI | P1 | Does not exist | Waiting room page: position, doctor online, paid, estimated wait | Not Started
147 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.7 | TEL-07 | Recording consent — consent captured before the consultation; no recording without it | Regression | Telemedicine | §10 + §2.4 + §17 | Recording consent | Patient + Doctor | 1 | 147 | 147 | Web, UI | P0 | AudioCaseConsentLog only for audio case taking | ConsentRecord type TeleRecording; block record if declined; both sides see status | Not Started
148 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.8 | TEL-08 | Rejoin after dropped call — either side can rejoin the same consultation | Regression | Telemedicine | §10 + §2.4 | Rejoin after dropped call | Doctor + Patient | 1 | 148 | 148 | Web, UI | P0 | Does not exist | Session Active until End; rejoin tokens; dashboard Rejoin | Not Started
149 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.9 | TEL-09 | Join failure handling — clear fallback if the call cannot connect, with options to retry | Regression | Telemedicine | §10 + §2.4 | Join failure handling / Fallback & join failure handling | Doctor + Patient | 1 | 149 | 149 | Web, UI | P1 | Does not exist | Error codes; retry; support ticket deep link later; do not silently fail | Not Started
150 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.10 | TEL-10 | Case-linked chat — chat attached to the consultation record, not a loose message thread | Regression | Telemedicine | §10 + §2.4 | Case-linked chat | Doctor + Patient | 1 | 150 | 150 | Web, UI | P1 | Does not exist | Messages keyed by TeleSession/PatientAppId; retained with the case | Not Started
151 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.11 | TEL-11 | Consultation summary — issued to the patient at the end of the call | Regression | Telemedicine | §10 + §2.4 | Consultation summary | Patient + Doctor | 1 | 151 | 151 | Web, UI | P1 | Does not exist | Doctor submits summary (not private notes); patient sees immediately; may share eRx id | Not Started
152 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.12 | TEL-12 | Instant consultation — patient requests an immediate consultation with an available doctor | Regression | Telemedicine | §10 + §2.3 | Instant consultation / Instant consult request / Queue & doctor offer | Patient + Doctor | 1 | 152 | 152 | Web, UI | P1 | Does not exist | Instant request pool; offer doctor; patient accepts; optional surcharge from fee config | Not Started
153 | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.1 | COM-01 | SMS — appointment confirmation, registration confirmation, doctor-unavailable, OTP, reschedule and cancellation | Regression | Notifications | §14 | SMS | Shared | 1 | 153 | 153 | Web, UI | P0 | No SMS provider; WhatsApp exists separately | SmsProvider + templates + DLT; event hooks; DND/opt-out on Patient | Not Started
154 | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.2 | COM-02 | WhatsApp — templates, offers, health tips and bulk messaging with delivery reports and opt-out (complete remaining ~50%) | Regression | Notifications | §14 | WhatsApp | Doctor Web | 1 | 154 | 154 | Web, UI | P1 | Meta Cloud send/templates/campaigns live; bulk/opt-in/analytics incomplete | Finish bulk queue UX, template approval states, delivery reports, opt-out | Not Started
155 | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.3 | COM-03 | Push notifications — booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests | Regression | Notifications | §14 + §2.9 + §3 | Push notifications | Patient App + Doctor App | 1 | 155 | 155 | Web, UI | P0 | Does not exist | DeviceToken + FCM/APNs; event fan-out; apps register tokens in Phases 16–17 | Not Started
156 | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.4 | COM-04 | Email — registration, activation, password reset, invoices and receipts | Regression | Notifications | §14 | Email | Shared | 1 | 156 | 156 | Web, UI | P1 | SMTP used for activation/forgot (plaintext issue fixed in Phase 0); no invoice email | Template emails for listed events; invoice PDF attach via SEC-09 | Not Started
157 | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.5 | COM-05 | In-app notification centre — all alerts collected in one place for patients and doctors | Regression | Notifications | §14 + §2.8 | In-app notification centre / Notifications centre | Patient App + Doctor Web/App | 1 | 157 | 157 | Web, UI | P1 | Does not exist (Velzon notification demo is not product) | AppNotification inbox; mark read; do not use Velzon demo notifications | Not Started
158 | 13 | Phase 13 — Support & help desk (PDF §15) | 13.1 | SUP-01 | Patient support tickets — patients raise issues from the app and track them | Regression | Support | §15 + §2.9 | Patient support tickets / Help centre & support tickets | Patient App + Admin | 1 | 158 | 158 | Web, UI | P1 | Does not exist; EnquiryDetail is not tickets; Velzon tickets demo ignore | SupportTicket reporter=Patient; status track; not Enquiry, not Velzon /apps-tickets-* | Not Started
159 | 13 | Phase 13 — Support & help desk (PDF §15) | 13.2 | SUP-02 | Doctor support tickets — doctors raise issues from the portal | Regression | Support | §15 | Doctor support tickets | Doctor Web + Admin | 1 | 159 | 159 | Web, UI | P1 | Does not exist | Same ticket tables; reporter=Doctor | Not Started
160 | 13 | Phase 13 — Support & help desk (PDF §15) | 13.3 | SUP-03 | Admin issue queue — all issues in one queue with priority, assignment and status | Regression | Support | §15 + §7.2 | Admin issue queue / Support ticket queue | Admin Portal | 1 | 160 | 160 | Web, UI | P1 | Does not exist | /admin/support-tickets; SLA timestamps; assign | Not Started
161 | 13 | Phase 13 — Support & help desk (PDF §15) | 13.4 | SUP-04 | Ticket conversation — full message thread with attachments | Regression | Support | §15 | Ticket conversation | Admin + Doctor + Patient | 1 | 161 | 161 | Web, UI | P1 | Does not exist | Threaded messages + SEC-09 attachments | Not Started
162 | 13 | Phase 13 — Support & help desk (PDF §15) | 13.5 | SUP-05 | Enquiry management — website enquiries tracked (ties WEB-06) | Regression | Support | §15 + §4 | Enquiry management | Admin Portal | 1 | 162 | 162 | UI | P1 | API exists; inbox missing | Complete WEB-06 admin inbox if not already; convert enquiry → ticket optional | Not Started
163 | 13 | Phase 13 — Support & help desk (PDF §15) | 13.6 | SUP-06 | Help centre — self-service help content for patients | Regression | Support | §15 + §2.9 | Help centre | Patient Website + App | 1 | 163 | 163 | Web, UI | P2 | Does not exist | CMS articles or static help; searchable | Not Started
164 | 13 | Phase 13 — Support & help desk (PDF §15) | 13.7 | SUP-07 | Assisted booking — help for patients who need support booking | Regression | Support | §15 + §2.9 | Assisted booking | Support + Reception + Patient | 1 | 164 | 164 | Web, UI | P2 | Does not exist | Staff (admin/support/reception) can complete public booking on behalf of a patient with audit; patient app CTA to request assistance | Not Started
165 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.1 | MED-01 | Pharmacy partner onboarding — licensed premises, licence records, activation checklist | Regression | HomeoMeds | §12 + §7.2 | Pharmacy partner onboarding / Pharmacy partner management | Pharmacy + Admin | 1 | 165 | 165 | Web, UI | P0 | Does not exist | PharmacyPartner + licences; admin activation; pharmacy console login | Not Started
166 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.2 | MED-02 | Licence gating — expired or suspended licences blocked automatically from receiving orders | Regression | HomeoMeds | §12 | Licence gating | Backend | 1 | 166 | 166 | Web, UI | P0 | Does not exist | Scheduler; routing skip; banner on pharmacy console | Not Started
167 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.3 | MED-03 | Fulfilment consent & pharmacy selection — patient chooses the seller and consents before the prescription is shared | Regression | HomeoMeds | §12 + §2.7 | Fulfilment consent & pharmacy selection | Patient | 1 | 167 | 167 | Web, UI | P0 | Does not exist | ConsentRecord PharmacyShare; patient picks from routed sellers; share only after consent | Not Started
168 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.4 | MED-04 | Prescription handoff — signed prescription becomes the order directly — no re-entry, no transcription errors | Regression | HomeoMeds | §12 + §2.7 | Prescription handoff / Order start | Patient + Pharmacy | 1 | 168 | 168 | Web, UI | P0 | Does not exist | MedicineOrder copied from ErxSnapshot items (codes); pharmacy never types remedies | Not Started
169 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.5 | MED-05 | Rule-based seller routing — licence validity, service area, working hours and capacity | Regression | HomeoMeds | §12 | Rule-based seller routing | Backend | 1 | 169 | 169 | Web, UI | P0 | Does not exist | SellerRoutingRule engine | Not Started
170 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.6 | MED-06 | Manual stock confirmation — pharmacy confirms availability — no live inventory integration required | Regression | HomeoMeds | §12 | Manual stock confirmation | Pharmacy console | 1 | 170 | 170 | Web, UI | P0 | Does not exist | Accept/reject with stock flag; do not build inventory master | Not Started
171 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.7 | MED-07 | Pharmacy console — accept or reject, enter price quote, mark ready and dispatched | Regression | HomeoMeds | §12 | Pharmacy console | Pharmacy console | 1 | 171 | 171 | Web, UI | P0 | Does not exist | /pharmacy/orders list+detail; OTP accept (SEC-07); quote; ready; dispatched | Not Started
172 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.8 | MED-08 | Quote before payment — the patient always sees the price before paying | Regression | HomeoMeds | §12 + §2.7 | Quote before payment / Pharmacy selection & quote | Patient | 1 | 172 | 172 | Web, UI | P0 | Does not exist | MedicineQuote; patient must confirm quote; then PAY-07 | Not Started
173 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.9 | MED-09 | Payment or cash on delivery — both options, with status tracking | Regression | HomeoMeds | §12 + §9 | Payment or cash on delivery | Patient | 1 | 173 | 173 | Web, UI | P0 | Stream MEDICINE stub in Phase 6 | Online pay via PAY-02; COD_PENDING until pharmacy confirms collection | Not Started
174 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.10 | MED-10 | Order tracking — live status for the patient at every stage | Regression | HomeoMeds | §12 + §2.7 | Order tracking | Patient | 1 | 174 | 174 | Web, UI | P1 | Does not exist | Status timeline events; push updates COM-03 | Not Started
175 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.11 | MED-11 | Medicine ledger shares — seller, platform and delivery recorded (FIN-03 live fill) | Regression | HomeoMeds | §12 + §8 | Medicine ledger | Account | 1 | 175 | 175 | Web | P0 | Empty medicine ledger screen from Phase 7 | On pay/COD collect, write SplitSeller/Platform/Delivery from config | Not Started
176 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.12 | MED-12 | Order exception queue — stuck, rejected or failed orders always surfaced — never silent | Regression | HomeoMeds | §12 | Order exception queue | Admin + Account | 1 | 176 | 176 | Web, UI | P0 | Does not exist | HomeoMeds exception queue; SLA; never drop | Not Started
177 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.13 | MED-13 | OTP-based control — key actions verified by OTP so Homeocentrum can monitor and trace every transaction | Regression | HomeoMeds | §12 + §17 | OTP-based control | Pharmacy + Account | 1 | 177 | 177 | Web | P0 | SEC-07 infrastructure exists | OTP on pharmacy accept (and other high-risk); OtpAudit queryable | Not Started
178 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.14 | MED-14 | Refill orders — repeat orders raised from an existing prescription | Regression | HomeoMeds | §12 + §2.7 + §11 | Refill orders / Order detail & refill | Patient + Doctor | 1 | 178 | 178 | Web, UI | P1 | ERX-10 refill request exists | Approved refill creates a new MedicineOrder from the same snapshot; one-tap patient | Not Started
179 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.15 | MED-15 | Order review & consent (patient) — confirm and consent before the prescription is shared | Regression | HomeoMeds | §2.7 | Order review & consent | Patient | 1 | 179 | 179 | UI | P0 | Covered by MED-03; explicit review screen still required | Review screen listing codes (not names) + pharmacy + consent checkbox | Not Started
180 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.16 | MED-16 | Medicines tab — all medicine orders in one place (API now; app UI in Phase 16) | Regression | HomeoMeds | §2.7 | Medicines tab | Patient | 1 | 180 | 180 | Web, UI | P1 | Does not exist | GET my orders; website optional list; app tab Phase 16 | Not Started
181 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.1 | CON-01 | Family members — add family members under one account | Regression | Patient identity | §2.1 | Family members | Patient App (API now) | 1 | 181 | 181 | Web, UI | P0 | Does not exist | FamilyMember under Patient account; bookings can be for a member | Not Started
182 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.2 | CON-02 | Caregiver authorization — let a family member book and manage on their behalf | Regression | Patient identity | §2.1 | Caregiver authorization | Patient App (API now) | 1 | 182 | 182 | Web, UI | P0 | Does not exist | CaregiverAuth with scopes; OTP; withdrawable via consent centre | Not Started
183 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.3 | CON-03 | Records timeline + consultation note + document upload APIs | Regression | Patient records | §2.5 | Records timeline / Consultation note / Document upload | Patient App (API now) | 1 | 183 | 183 | Web, UI | P0 | Doctor history exists; no patient timeline; no patient upload | Patient timeline DTO (visits, summary, eRx codes, labs); consultation note = TEL-11 summary not private notes; uploads via SEC-09 | Not Started
184 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.4 | CON-04 | Follow-up plan & tasks — clear next steps after each consultation | Regression | Continuity | §2.6 | Follow-up plan & tasks | Doctor Web + Patient | 1 | 184 | 184 | Web, UI | P1 | Does not exist (follow-up option in notes does not save) | FollowUpTask created by doctor; patient sees tasks | Not Started
185 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.5 | CON-05 | Symptom diary — record symptoms between visits | Regression | Continuity | §2.6 | Symptom diary | Patient App (API now) | 1 | 185 | 185 | Web, UI | P1 | Does not exist | SymptomDiary entries; doctor can read on board | Not Started
186 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.6 | CON-06 | Progress tracking — see improvement over time across visits | Regression | Continuity | §2.6 | Progress tracking | Patient + Doctor | 1 | 186 | 186 | Web, UI | P2 | Does not exist | Progress series from diary + visit outcomes; not a fake chart | Not Started
187 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.7 | CON-07 | Consent centre & data rights — view, manage and withdraw consents; request data | Regression | Privacy | §17 + §2.8 | Consent centre & data rights | Patient App (API now) | 1 | 187 | 187 | Web, UI | P0 | ConsentRecord from Phase 0 | Patient list/withdraw; data export request (DPDP); deletion request workflow | Not Started
188 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.8 | CON-08 | Patient payments & refunds read model | Regression | Patient money | §2.8 | Payments & refunds | Patient App (API now) | 1 | 188 | 188 | Web | P1 | Ledger exists for Account | Patient-safe DTO of own consult+medicine payments and refunds — no other patients, no commission internals | Not Started
189 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.9 | CON-09 | Physical clinic appointment — book an in-person visit as well as online | Regression | Booking | §2.9 + §5.2 | Physical clinic appointment | Patient | 1 | 189 | 189 | Web | P1 | ConsultMode added in APT-02; public booking in WEB-04 | Ensure public/patient booking supports In-clinic as first-class, not tele-only | Not Started
190 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.10 | CON-10 | Patient profile setup API — name, age, gender, contact and health basics | Regression | Patient identity | §2.1 | Profile setup | Patient App (API now) | 1 | 190 | 190 | Web, UI | P0 | Clinic-created Patient exists; no self-serve profile product | Patient profile fields + health basics; used by OTP-verified patient token | Not Started
191 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.1 | PAT-01 | Patient app — language selection on first open | Regression | Patient Mobile | §2.1 | Language selection | Patient Mobile App | 1 | 191 | 191 | Mobile | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
192 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.2 | PAT-02 | Patient app — welcome and introduction | Regression | Patient Mobile | §2.1 | Welcome & introduction | Patient Mobile App | 1 | 192 | 192 | Mobile | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
193 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.3 | PAT-03 | Patient app — mobile number + OTP login (PatientAuth) | Regression | Patient Mobile | §2.1 | Mobile number + OTP login | Patient Mobile App | 1 | 193 | 193 | Mobile | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
194 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.4 | PAT-04 | Patient app — profile setup | Regression | Patient Mobile | §2.1 | Profile setup | Patient Mobile App | 1 | 194 | 194 | Mobile | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
195 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.5 | PAT-05 | Patient app — privacy consent before data stored | Regression | Patient Mobile | §2.1 | Privacy consent | Patient Mobile App | 1 | 195 | 195 | Mobile | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
196 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.6 | PAT-06 | Patient app — family members | Regression | Patient Mobile | §2.1 | Family members | Patient Mobile App | 1 | 196 | 196 | Mobile | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
197 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.7 | PAT-07 | Patient app — caregiver authorization | Regression | Patient Mobile | §2.1 | Caregiver authorization | Patient Mobile App | 1 | 197 | 197 | Mobile | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
198 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.8 | PAT-08 | Patient app — home dashboard | Regression | Patient Mobile | §2.2 | Home dashboard | Patient Mobile App | 1 | 198 | 198 | Mobile | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
199 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.9 | PAT-09 | Patient app — search and care categories | Regression | Patient Mobile | §2.2 | Search & care categories | Patient Mobile App | 1 | 199 | 199 | Mobile | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
200 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.10 | PAT-10 | Patient app — search results | Regression | Patient Mobile | §2.2 | Search results | Patient Mobile App | 1 | 200 | 200 | Mobile | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
201 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.11 | PAT-11 | Patient app — discovery filters | Regression | Patient Mobile | §2.2 | Filters | Patient Mobile App | 1 | 201 | 201 | Mobile | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
202 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.12 | PAT-12 | Patient app — doctor profile | Regression | Patient Mobile | §2.2 | Doctor profile | Patient Mobile App | 1 | 202 | 202 | Mobile | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
203 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.13 | PAT-13 | Patient app — verified badge on doctor | Regression | Patient Mobile | §2.2 | Credentials & verification | Patient Mobile App | 1 | 203 | 203 | Mobile | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
204 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.14 | PAT-14 | Patient app — ranking explanation | Regression | Patient Mobile | §2.2 | Ranking explanation | Patient Mobile App | 1 | 204 | 204 | Mobile | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
205 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.15 | PAT-15 | Patient app — health articles | Regression | Patient Mobile | §2.2 | Health articles | Patient Mobile App | 1 | 205 | 205 | Mobile | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
206 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.16 | PAT-16 | Patient app — slot picker | Regression | Patient Mobile | §2.3 | Slot picker | Patient Mobile App | 1 | 206 | 206 | Mobile | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
207 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.17 | PAT-17 | Patient app — booking review and consent | Regression | Patient Mobile | §2.3 | Booking review & consent | Patient Mobile App | 1 | 207 | 207 | Mobile | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
208 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.18 | PAT-18 | Patient app — checkout | Regression | Patient Mobile | §2.3 | Checkout | Patient Mobile App | 1 | 208 | 208 | Mobile | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
209 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.19 | PAT-19 | Patient app — payment status | Regression | Patient Mobile | §2.3 | Payment status | Patient Mobile App | 1 | 209 | 209 | Mobile | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
210 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.20 | PAT-20 | Patient app — appointment detail | Regression | Patient Mobile | §2.3 | Appointment detail | Patient Mobile App | 1 | 210 | 210 | Mobile | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
211 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.21 | PAT-21 | Patient app — reschedule | Regression | Patient Mobile | §2.3 | Reschedule appointment | Patient Mobile App | 1 | 211 | 211 | Mobile | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
212 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.22 | PAT-22 | Patient app — cancel | Regression | Patient Mobile | §2.3 | Cancel appointment | Patient Mobile App | 1 | 212 | 212 | Mobile | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
213 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.23 | PAT-23 | Patient app — waitlist offer | Regression | Patient Mobile | §2.3 | Waitlist offer | Patient Mobile App | 1 | 213 | 213 | Mobile | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
214 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.24 | PAT-24 | Patient app — instant consult request | Regression | Patient Mobile | §2.3 | Instant consult request | Patient Mobile App | 1 | 214 | 214 | Mobile | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
215 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.25 | PAT-25 | Patient app — queue and doctor offer | Regression | Patient Mobile | §2.3 | Queue & doctor offer | Patient Mobile App | 1 | 215 | 215 | Mobile | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
216 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.26 | PAT-26 | Patient app — device check | Regression | Patient Mobile | §2.4 | Device check | Patient Mobile App | 1 | 216 | 216 | Mobile | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
217 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.27 | PAT-27 | Patient app — waiting room | Regression | Patient Mobile | §2.4 | Waiting room | Patient Mobile App | 1 | 217 | 217 | Mobile | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
218 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.28 | PAT-28 | Patient app — live video | Regression | Patient Mobile | §2.4 | Live video consultation | Patient Mobile App | 1 | 218 | 218 | Mobile | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
219 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.29 | PAT-29 | Patient app — recording consent | Regression | Patient Mobile | §2.4 | Recording consent | Patient Mobile App | 1 | 219 | 219 | Mobile | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
220 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.30 | PAT-30 | Patient app — join failure fallback | Regression | Patient Mobile | §2.4 | Fallback & join failure handling | Patient Mobile App | 1 | 220 | 220 | Mobile | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
221 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.31 | PAT-31 | Patient app — case-linked chat | Regression | Patient Mobile | §2.4 | Case-linked chat | Patient Mobile App | 1 | 221 | 221 | Mobile | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
222 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.32 | PAT-32 | Patient app — consultation summary | Regression | Patient Mobile | §2.4 | Consultation summary | Patient Mobile App | 1 | 222 | 222 | Mobile | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
223 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.33 | PAT-33 | Patient app — rejoin | Regression | Patient Mobile | §2.4 | Rejoin after dropped call | Patient Mobile App | 1 | 223 | 223 | Mobile | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
224 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.34 | PAT-34 | Patient app — records timeline | Regression | Patient Mobile | §2.5 | Records timeline | Patient Mobile App | 1 | 224 | 224 | Mobile | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
225 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.35 | PAT-35 | Patient app — consultation note (summary, not private notes) | Regression | Patient Mobile | §2.5 | Consultation note | Patient Mobile App | 1 | 225 | 225 | Mobile | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
226 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.36 | PAT-36 | Patient app — signed eRx (codes until pharmacy accept) | Regression | Patient Mobile | §2.5 | Signed digital prescription | Patient Mobile App | 1 | 226 | 226 | Mobile | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
227 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.37 | PAT-37 | Patient app — document upload | Regression | Patient Mobile | §2.5 | Document upload | Patient Mobile App | 1 | 227 | 227 | Mobile | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
228 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.38 | PAT-38 | Patient app — follow-up plan and tasks | Regression | Patient Mobile | §2.6 | Follow-up plan & tasks | Patient Mobile App | 1 | 228 | 228 | Mobile | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
229 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.39 | PAT-39 | Patient app — symptom diary | Regression | Patient Mobile | §2.6 | Symptom diary | Patient Mobile App | 1 | 229 | 229 | Mobile | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
230 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.40 | PAT-40 | Patient app — progress tracking | Regression | Patient Mobile | §2.6 | Progress tracking | Patient Mobile App | 1 | 230 | 230 | Mobile | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
231 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.41 | PAT-41 | Patient app — medicines tab | Regression | Patient Mobile | §2.7 | Medicines tab | Patient Mobile App | 1 | 231 | 231 | Mobile | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
232 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.42 | PAT-42 | Patient app — start HomeoMeds order from eRx | Regression | Patient Mobile | §2.7 | Order start | Patient Mobile App | 1 | 232 | 232 | Mobile | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
233 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.43 | PAT-43 | Patient app — pharmacy selection and quote | Regression | Patient Mobile | §2.7 | Pharmacy selection & quote | Patient Mobile App | 1 | 233 | 233 | Mobile | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
234 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.44 | PAT-44 | Patient app — order review and consent | Regression | Patient Mobile | §2.7 | Order review & consent | Patient Mobile App | 1 | 234 | 234 | Mobile | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
235 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.45 | PAT-45 | Patient app — order tracking | Regression | Patient Mobile | §2.7 | Order tracking | Patient Mobile App | 1 | 235 | 235 | Mobile | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
236 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.46 | PAT-46 | Patient app — order detail and refill | Regression | Patient Mobile | §2.7 | Order detail & refill | Patient Mobile App | 1 | 236 | 236 | Mobile | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
237 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.47 | PAT-47 | Patient app — write a review | Regression | Patient Mobile | §2.8 | Write a review | Patient Mobile App | 1 | 237 | 237 | Mobile | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
238 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.48 | PAT-48 | Patient app — my reviews and appeal | Regression | Patient Mobile | §2.8 | My reviews & appeal | Patient Mobile App | 1 | 238 | 238 | Mobile | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
239 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.49 | PAT-49 | Patient app — payments and refunds | Regression | Patient Mobile | §2.8 | Payments & refunds | Patient Mobile App | 1 | 239 | 239 | Mobile | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
240 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.50 | PAT-50 | Patient app — profile and settings | Regression | Patient Mobile | §2.8 | Profile & settings | Patient Mobile App | 1 | 240 | 240 | Mobile | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
241 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.51 | PAT-51 | Patient app — consent centre and data rights | Regression | Patient Mobile | §2.8 | Consent centre & data rights | Patient Mobile App | 1 | 241 | 241 | Mobile | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
242 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.52 | PAT-52 | Patient app — notifications centre | Regression | Patient Mobile | §2.8 | Notifications centre | Patient Mobile App | 1 | 242 | 242 | Mobile | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
243 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.53 | PAT-53 | Patient app — help centre and tickets | Regression | Patient Mobile | §2.9 | Help centre & support tickets | Patient Mobile App | 1 | 243 | 243 | Mobile | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
244 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.54 | PAT-54 | Patient app — physical clinic booking | Regression | Patient Mobile | §2.9 | Physical clinic appointment | Patient Mobile App | 1 | 244 | 244 | Mobile | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
245 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.55 | PAT-55 | Patient app — assisted booking request | Regression | Patient Mobile | §2.9 | Assisted booking | Patient Mobile App | 1 | 245 | 245 | Mobile | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
246 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.56 | PAT-56 | Patient app — low-data mode | Regression | Patient Mobile | §2.9 | Low-data mode | Patient Mobile App | 1 | 246 | 246 | Mobile | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
247 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.57 | PAT-57 | Patient app — push notifications | Regression | Patient Mobile | §2.9 | Push notifications | Patient Mobile App | 1 | 247 | 247 | Mobile | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
248 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.58 | PAT-58 | Patient app — iOS and Android store release, device matrix, and parity QA | Regression | Patient Mobile | §2 + §18 | Patient mobile app iOS and Android | Patient Mobile App | 1 | 248 | 248 | Mobile | P0 | No app | Store builds; crash-free join; feature parity checklist against every §2 row | Not Started
249 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.1 | DMO-01 | Doctor app — login & identity (same login and same account as the web portal) | Regression | Doctor Mobile | §3 | Login & identity | Doctor Mobile App | 1 | 249 | 249 | Mobile | P0 | No doctor app | Same Account login + DoctorId; bind device; no separate doctor identity | Not Started
250 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.2 | DMO-02 | Doctor app — first-run onboarding (guided setup, number confirmation and permissions) | Regression | Doctor Mobile | §3 | First-run onboarding | Doctor Mobile App | 1 | 250 | 250 | Mobile | P1 | No app | Confirm registered mobile; permission primer | Not Started
251 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.3 | DMO-03 | Doctor app — notification permissions (push, microphone and camera handled properly) | Regression | Doctor Mobile | §3 | Notification permissions | Doctor Mobile App | 1 | 251 | 251 | Mobile | P0 | No app | OS permission flows; settings deep link if denied | Not Started
252 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.4 | DMO-04 | Doctor app — today’s queue & schedule (the full day at a glance) | Regression | Doctor Mobile | §3 | Today’s queue & schedule | Doctor Mobile App | 1 | 252 | 252 | Mobile | P0 | No app | Appointment list APIs; payment + tele flags; no Patient Board | Not Started
253 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.5 | DMO-05 | Doctor app — availability toggle (go online or offline, set working hours) | Regression | Doctor Mobile | §3 | Availability toggle | Doctor Mobile App | 1 | 253 | 253 | Mobile | P0 | No app | Same TeleAvailability + schedule APIs as web | Not Started
254 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.6 | DMO-06 | Doctor app — push notifications (waiting, booking, reschedule, cancellation, refill, payment received) | Regression | Doctor Mobile | §3 | Push notifications | Doctor Mobile App | 1 | 254 | 254 | Mobile | P0 | No app | Consume COM-03 doctor templates | Not Started
255 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.7 | DMO-07 | Doctor app — patient context card (name, age, chief complaint and last visit) — NO case-taking | Regression | Doctor Mobile | §3 | Patient context card | Doctor Mobile App | 1 | 255 | 255 | Mobile | P0 | No app; PDF: detailed case-taking stays on the web portal | Read-only card; explicitly no repertory/audio/Rx compose | Not Started
256 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.8 | DMO-08 | Doctor app — join consultation (video or audio from the phone) | Regression | Doctor Mobile | §3 | Join consultation | Doctor Mobile App | 1 | 256 | 256 | Mobile | P0 | No app | Same session tokens as TEL-03/04 | Not Started
257 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.9 | DMO-09 | Doctor app — refill approval (approve or reject repeat prescription requests) | Regression | Doctor Mobile | §3 + §11 | Refill approval | Doctor Mobile App | 1 | 257 | 257 | Mobile | P0 | No app | ERX-10 inbox; approve only — Patient Board remains web | Not Started
258 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.10 | DMO-10 | Doctor app — earnings summary (today, this week, this month, with payout status) | Regression | Doctor Mobile | §3 + §16 | Earnings summary | Doctor Mobile App | 1 | 258 | 258 | Mobile | P1 | No app | Account ledger read model for this DoctorId — not a second money system | Not Started
259 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.11 | DMO-11 | Doctor app — offline handling (weak connection or expired session) | Regression | Doctor Mobile | §3 | Offline handling | Doctor Mobile App | 1 | 259 | 259 | Mobile | P1 | No app | Queued actions policy (do not fake join); session expiry uses SEC-03 | Not Started
260 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.12 | DMO-12 | Doctor app — reliability monitoring (failures reported automatically) | Regression | Doctor Mobile | §3 | Reliability monitoring | Doctor Mobile App | 1 | 260 | 260 | Mobile | P1 | No app | Crash/error SDK; join failures also as TeleSessionEvent | Not Started
261 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.13 | DMO-13 | Doctor app — iOS and Android parity QA (queue, availability, notifications, context, video, refill, earnings) | Regression | Doctor Mobile | §3 + §18 | Doctor mobile app iOS and Android | Doctor Mobile App | 1 | 261 | 261 | Mobile | P0 | No app | Parity checklist for every §3 row on both OS | Not Started
262 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.1 | RPT-01 | Admin overview dashboard — platform-wide activity at a glance (replace Velzon ecommerce) | Regression | Reports | §16 + §7.2 | Admin overview dashboard / Admin dashboard | Admin Portal | 1 | 262 | 262 | Web, UI | P0 | Velzon ecommerce dashboard 0% product; login lands /dashboard | True /admin/dashboard KPIs: doctors, credentialing, bookings, GMV, failed payments, tickets, HomeoMeds exceptions; redirect /dashboard away from StoreVisits | Not Started
263 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.2 | RPT-02 | Doctor practice statistics — patient and consultation trends (extend existing charts) | Regression | Reports | §16 + §5.1 | Doctor practice statistics | Doctor Web | 1 | 263 | 263 | Web, UI | P1 | Patient stats charts live | Keep as foundation; ensure visit type/mode included after APT-02 | Not Started
264 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.3 | RPT-03 | Follow-up analysis — due/overdue patients and follow-up conversion | Regression | Reports | §16 | Follow-up analysis | Doctor Web | 1 | 264 | 264 | Web, UI | P1 | Does not exist; follow-up option in notes does not save | /doctor/follow-up-analysis from VisitType + CON-04 tasks | Not Started
265 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.4 | RPT-04 | Clinic performance analysis — appointments, slot utilisation, no-shows, cancellations, waiting time and revenue | Regression | Reports | §16 | Clinic performance analysis | Doctor Web | 1 | 265 | 265 | Web, UI | P1 | Does not exist | /doctor/clinic-performance including payment collected and tele duration if timed | Not Started
266 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.5 | RPT-05 | Payment reconciliation report — bookings matched against payments | Regression | Reports | §16 + §7.2 | Payment reconciliation report / Consult booking & payment reconciliation | Admin + Account | 1 | 266 | 266 | Web, UI | P1 | FIN-02 built the queue; this is the report/export | Exportable report from the same reconciliation query | Not Started
267 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.6 | RPT-06 | Settlement & payout reports — amounts due and paid to doctors and pharmacies | Regression | Reports | §16 + §8 | Settlement & payout reports | Account | 1 | 267 | 267 | Web, UI | P1 | FIN-04/05 exist as ops screens | Formal report/export of runs and payouts | Not Started
268 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.7 | RPT-07 | GST & invoice reports (reporting surface of FIN-08) | Regression | Reports | §16 + §8 | GST & invoice reports | Account | 1 | 268 | 268 | Web | P1 | FIN-08 built tax screen | Confirm report pack (GSTR-style export as agreed with CA) — configuration | Not Started
269 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.8 | RPT-08 | Doctor earnings summary — daily, weekly and monthly earnings with payout status (web + same API as DMO-10) | Regression | Reports | §16 + §3 | Doctor earnings summary | Doctor Web + App | 1 | 269 | 269 | Web, UI | P1 | Does not exist | Web earnings page using same API as doctor app | Not Started
270 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.9 | RPT-09 | Medicine order reports — order volumes, fulfilment and exceptions | Regression | Reports | §16 + §12 | Medicine order reports | Admin + Account | 1 | 270 | 270 | Web, UI | P1 | Does not exist | Volumes, SLA, exception counts from HomeoMeds | Not Started
271 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.10 | RPT-10 | Platform users remaining 20% — import, export and activation control | Regression | Admin | §7.2 | Platform users | Admin Portal | 1 | 271 | 271 | Web, UI | P1 | List/Add/Edit live; Import/Export buttons dead; no verification column | Wire Import/Export; verification column; activate/lock; link credentialing | Not Started
272 | 19 | Phase 19 — Cross-surface QA, NFR, delivery summary gate (PDF §1 + §18) | 19.1 | QA-01 | One ecosystem proof — patient, appointment, prescription and payment created anywhere are visible everywhere | Regression | QA | §1 + §18 | One connected ecosystem | All | 3 | 272 | 274 | — | P0 | Surfaces were built in phases | End-to-end scripts covering all six user types | Not Started
273 | 19 | Phase 19 — Cross-surface QA, NFR, delivery summary gate (PDF §1 + §18) | 19.2 | QA-02 | Delivery summary gate — every area in PDF §18 signed off | Regression | QA | §18 | Summary of delivery | Programme | 2 | 275 | 276 | — | P0 | This register is the scope | Walk the coverage sheet; zero PDF rows with Status≠Done unless formally deferred with client sign | Not Started
274 | 19 | Phase 19 — Cross-surface QA, NFR, delivery summary gate (PDF §1 + §18) | 19.3 | NFR-01 | NFR — performance, low-data, reliability, secrets, dual-API freeze | Regression | NFR | §2.9 + §3 + §17 | Low-data mode / Reliability monitoring / Secure login | All | 2 | 277 | 278 | Web | P0 | Known risks: plaintext passwords (fixed P0), secrets in appsettings, dual API drift | Rotate secrets; no new third API; patient low-data verified; doctor reliability SDK live | Not Started

## 09_Traceability
LINE-BY-LINE TRACE — every master Seq 1…N appears once. Filter Track to audit a team. Count of rows must equal the master sequential register.
Original Seq | Track Seq | Track | Phase | Main Task ID | Sub Task ID | Sub Task | Work Type | Layer | Surface | Sister Tracks
1 | 1 | Web | PRE | PRE-01 | PRE-01.01 | Workshop with finance: confirm Homeocentrum is single merchant of record for consult + medicine + subscription | Client Decision | Decision | Account / Gateway | Web
2 | 2 | Web | PRE | PRE-01 | PRE-01.02 | Choose v1 payout mechanic: Homeocentrum-held + NEFT/IMPS vs Razorpay Route / linked accounts | Client Decision | Decision | Account / Gateway | Web
3 | 3 | Web | PRE | PRE-01 | PRE-01.03 | Record decision in config (SettlementModel) — engineering must not hardcode a split model | Configuration | Configuration | Account / Gateway | Web
4 | 4 | Web | PRE | PRE-02 | PRE-02.01 | OQ: cash collected at reception retained by clinic or remitted to Homeocentrum? | Client Decision | Decision | Account / Reception | Web
5 | 5 | Web | PRE | PRE-02 | PRE-02.02 | Document GST treatment on consult fee, platform fee, and medicine (on which amount, which GSTIN) | Client Decision | Decision | Account / Reception | Web
6 | 6 | Web | PRE | PRE-02 | PRE-02.03 | Confirm commission %, settlement hold T+N days, invoice numbering series — configuration not code | Configuration | Configuration | Account / Reception | Web
7 | 7 | Web | PRE | PRE-03 | PRE-03.01 | Select in-browser + mobile video vendor (Agora / Twilio / Daily / WebRTC self-host) — required for §10 | Client Decision | Decision | Shared | Web
8 | 8 | Web | PRE | PRE-03 | PRE-03.02 | Select SMS provider (MSG91 / Twilio / etc.) and confirm DLT templates for appointment/OTP/cancel | Client Decision | Decision | Shared | Web
9 | 9 | Web | PRE | PRE-03 | PRE-03.03 | Legal: privacy (data protection, recording, pharmacy consent) and terms (payments, refunds, telemedicine, medicine orders) drafted for §4 + §17 | Client Decision | Legal | Shared | Web
10 | 10 | Web | PRE | PRE-03 | PRE-03.04 | OQ: unpaid-booking slot hold duration vs release immediately if patient does not pay | Client Decision | Decision | Shared | Web
11 | 11 | Web | PRE | PRE-03 | PRE-03.05 | OQ: live-doctor credentialing backfill — auto-Approve existing doctors? Unverified doctors visible only to own clinic? | Client Decision | Decision | Shared | Web
12 | 12 | Web | 0 | FND-01 | FND-01.01 | Publish shared-key design (DoctorId, PatientId, PatientAppId, CaseId, ErxId, LedgerTxnId, MedicineOrderId) and event list (created/rescheduled/cancelled/paid/signed/accepted) | New | Architecture | Shared | Web, QA
13 | 13 | Web | 0 | FND-01 | FND-01.02 | Add role enum values Patient, Account, PharmacyPartner alongside existing Admin/Doctor/Reception (keep unused Management/Supervisor/Inspector unused) | New | Database + Auth | Shared | Web, QA
14 | 14 | Web | 0 | FND-01 | FND-01.03 | All new domain modules on NigaHomeopathy-API (.NET 8); do not create a third API; classic API only where login/Rx-write/Razorpay already live until ported | Existing Modification | Architecture | Shared | Web, QA
15 | 1 | QA | 0 | FND-01 | FND-01.04 | QA: create appointment on Reception → visible on Doctor web; pay on Patient web → same PaymentStatus on Doctor and Account (after Phase 6) | Regression | QA | Shared | Web, QA
16 | 1 | UI | 0 | FND-02 | FND-02.01 | Web: add Account layout + home redirect; Pharmacy layout stub; do not build screens yet | New | Web SPA | Shared | Web, UI, Mobile
17 | 2 | UI | 0 | FND-02 | FND-02.02 | Extend roles.js and AuthProtected with per-route ACL skeleton (deny-by-default for new routes) | Existing Improvement | Web SPA | Shared | Web, UI, Mobile
18 | 1 | Mobile | 0 | FND-02 | FND-02.03 | Mobile: create Patient app and Doctor app repository/bootstrap (React Native or agreed stack) — empty shells only | New | Mobile | Shared | Web, UI, Mobile
19 | 15 | Web | 0 | FND-02 | FND-02.04 | Document the five portals: Patient Website, Doctor Web Portal, Reception Portal, Admin Portal, Account Department (Pharmacy console is HomeoMeds, not a 6th portal in the PDF count) | New | Architecture | Shared | Web, UI, Mobile
20 | 16 | Web | 0 | SEC-01 | SEC-01.01 | DB/Migration: hash existing UserMaster passwords (bcrypt/PBKDF2); never store new plaintext | Data Migration | Database | All web + later mobile | Web, UI, QA
21 | 17 | Web | 0 | SEC-01 | SEC-01.02 | API: Login verifies hash; embed Role + DoctorId claims; keep classic login URL until .NET 8 login is cut over | Existing Modification | API | All web + later mobile | Web, UI, QA
22 | 3 | UI | 0 | SEC-01 | SEC-01.03 | UI: remove fakeBackend() from App.js production path; login still Formik/Yup | Existing Modification | Web SPA | All web + later mobile | Web, UI, QA
23 | 2 | QA | 0 | SEC-01 | SEC-01.04 | QA: Admin, Doctor, Reception login; invalid password; deactivated user; SQL injection/brute-force rate limit | Regression | QA | All web + later mobile | Web, UI, QA
24 | 18 | Web | 0 | SEC-02 | SEC-02.01 | DB: PasswordResetToken (UserId, TokenHash, ExpiresAt, UsedAt) | New | Database | Admin / Doctor / Reception web | Web, UI, QA
25 | 19 | Web | 0 | SEC-02 | SEC-02.02 | API: ForgotPassword sends reset link; ResetPassword consumes token; stop emailing plaintext; ChangePassword for authenticated user | Existing Modification | API | Admin / Doctor / Reception web | Web, UI, QA
26 | 4 | UI | 0 | SEC-02 | SEC-02.03 | UI: replace slices/auth/forgetpwd fake/Firebase with real APIs; /reset-password/:token success/expiry states | Existing Improvement | Web SPA | Admin / Doctor / Reception web | Web, UI, QA
27 | 3 | QA | 0 | SEC-02 | SEC-02.04 | QA: expired token, reused token, unknown email (no user enumeration), logged-in change password | Regression | QA | Admin / Doctor / Reception web | Web, UI, QA
28 | 20 | Web | 0 | SEC-03 | SEC-03.01 | API: POST /Account/Logout; persist UserLoginStatus; optional denylist until token expiry | Existing Improvement | API | All | Web, UI, QA
29 | 5 | UI | 0 | SEC-03 | SEC-03.02 | Web: Logout.js calls API then clears authUser + patient-board session (keep existing board clear) | Existing Improvement | Web SPA | All | Web, UI, QA
30 | 21 | Web | 0 | SEC-03 | SEC-03.03 | Contract: mobile apps MUST use the same Logout endpoint (implemented in Phases 16–17) | New | API contract | All | Web, UI, QA
31 | 4 | QA | 0 | SEC-03 | SEC-03.04 | QA: logout on one tab; expired session message; 401 interceptor | Regression | QA | All | Web, UI, QA
32 | 22 | Web | 0 | SEC-04 | SEC-04.01 | Backend: restore GetMenuByRole; add role attributes on new money and PII APIs | Existing Improvement | API | Admin / All web | Web, UI, QA
33 | 6 | UI | 0 | SEC-04 | SEC-04.02 | Frontend: hide routes the role cannot view; keep Velzon demo routes out of production menus | Existing Improvement | Web SPA | Admin / All web | Web, UI, QA
34 | 23 | Web | 0 | SEC-04 | SEC-04.03 | Separation of duties seed: Account role controls money; Admin controls platform and clinical data — neither can perform the other’s role (PDF §8) | New | Configuration | Admin / All web | Web, UI, QA
35 | 5 | QA | 0 | SEC-04 | SEC-04.04 | QA: Reception cannot open repertory masters; Account cannot edit diagnosis; Doctor cannot see platform-wide ledger | Regression | QA | Admin / All web | Web, UI, QA
36 | 24 | Web | 0 | SEC-05 | SEC-05.01 | API: enforce DoctorId ownership on Patient, Appointment, Case, Rx, notes, labs, board backup | Existing Improvement | API | API | Web, QA
37 | 25 | Web | 0 | SEC-05 | SEC-05.02 | Disable directory browsing on /attachments and /Blogs; signed-URL or authorised download for documents | Existing Modification | API | API | Web, QA
38 | 6 | QA | 0 | SEC-05 | SEC-05.03 | QA: IDOR tests (swap PatientAppId / CaseId in requests) | Regression | QA | API | Web, QA
39 | 26 | Web | 0 | SEC-06 | SEC-06.01 | DB: ConsentRecord + ConsentType master (Privacy, Booking, TeleRecording, PharmacyShare, Marketing, Caregiver) | New | Database | Shared | Web, QA
40 | 27 | Web | 0 | SEC-06 | SEC-06.02 | API: Grant / Withdraw / List-mine / Admin-audit (no clinical content in the API response beyond type+time) | New | API | Shared | Web, QA
41 | 28 | Web | 0 | SEC-06 | SEC-06.03 | Reuse AudioCaseConsentLog pattern; do not fork a second consent model for telemedicine (Phase 11 will write TeleRecording into ConsentRecord) | Existing Improvement | API | Shared | Web, QA
42 | 7 | QA | 0 | SEC-06 | SEC-06.04 | QA: grant, withdraw, re-grant; audit log immutable | Regression | QA | Shared | Web, QA
43 | 29 | Web | 0 | SEC-07 | SEC-07.01 | DB: OtpChallenge, OtpAuditLog (Action, EntityType, EntityId, ToMasked, Success, At) | New | Database | Shared | Web, QA
44 | 30 | Web | 0 | SEC-07 | SEC-07.02 | API: RequestOtp / VerifyOtp (generic); rate-limit; lockout; SMS provider adapter stub until PRE-03 vendor is live | New | API | Shared | Web, QA
45 | 31 | Web | 0 | SEC-07 | SEC-07.03 | GET /api/Otp/Audit for Account and Admin (masked destination) | New | API | Shared | Web, QA
46 | 8 | QA | 0 | SEC-07 | SEC-07.04 | QA: replay OTP, expiry, max attempts, audit completeness | Regression | QA | Shared | Web, QA
47 | 32 | Web | 0 | SEC-08 | SEC-08.01 | DB: AuditEvent (ActorUserId, Role, Action, Entity, OldJson, NewJson, At, CorrelationId) | New | Database | Shared | Web, QA
48 | 33 | Web | 0 | SEC-08 | SEC-08.02 | API middleware: write audit on mutating money/Rx/approval endpoints (start with a helper used by later phases) | New | API | Shared | Web, QA
49 | 9 | QA | 0 | SEC-08 | SEC-08.03 | QA: sample sign-prescription / approve-payout (when those exist) produce audit rows | Regression | QA | Shared | Web, QA
50 | 34 | Web | 0 | SEC-09 | SEC-09.01 | DB: SecureDocument (OwnerType, OwnerId, BlobPath, Mime, Hash, CreatedBy) | New | Database | Shared | Web, QA
51 | 35 | Web | 0 | SEC-09 | SEC-09.02 | API: upload (multipart) + authorised GET; no public folder listing | New | API | Shared | Web, QA
52 | 10 | QA | 0 | SEC-09 | SEC-09.03 | QA: doctor of record can download; other doctor 403; anonymous 401 | Regression | QA | Shared | Web, QA
53 | 11 | QA | 1 | ADM-R01 | ADM-R01.01 | Regression: list / add / edit / (import-export if present) for Repertory sections | Existing | QA | Admin Portal | Web, QA
54 | 36 | Web | 1 | ADM-R01 | ADM-R01.02 | ACL: only Admin (and permitted roles) can mutate Repertory sections; Doctor is read-only consumer on Patient Board | Existing Improvement | Security | Admin Portal | Web, QA
55 | 37 | Web | 1 | ADM-R01 | ADM-R01.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Repertory sections; do not silently switch | Existing | API hygiene | Admin Portal | Web, QA
56 | 12 | QA | 1 | ADM-R02 | ADM-R02.01 | Regression: list / add / edit / (import-export if present) for Subsection & rubric tree | Existing | QA | Admin Portal | Web, QA
57 | 38 | Web | 1 | ADM-R02 | ADM-R02.02 | ACL: only Admin (and permitted roles) can mutate Subsection & rubric tree; Doctor is read-only consumer on Patient Board | Existing Improvement | Security | Admin Portal | Web, QA
58 | 39 | Web | 1 | ADM-R02 | ADM-R02.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Subsection & rubric tree; do not silently switch | Existing | API hygiene | Admin Portal | Web, QA
59 | 13 | QA | 1 | ADM-R03 | ADM-R03.01 | Regression: list / add / edit / (import-export if present) for Rubric–remedy mapping | Existing | QA | Admin Portal | Web, QA
60 | 40 | Web | 1 | ADM-R03 | ADM-R03.02 | ACL: only Admin (and permitted roles) can mutate Rubric–remedy mapping; Doctor is read-only consumer on Patient Board | Existing Improvement | Security | Admin Portal | Web, QA
61 | 41 | Web | 1 | ADM-R03 | ADM-R03.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Rubric–remedy mapping; do not silently switch | Existing | API hygiene | Admin Portal | Web, QA
62 | 14 | QA | 1 | ADM-R04 | ADM-R04.01 | Regression: list / add / edit / (import-export if present) for Remedy-linked rubrics | Existing | QA | Admin Portal | Web, QA
63 | 42 | Web | 1 | ADM-R04 | ADM-R04.02 | ACL: only Admin (and permitted roles) can mutate Remedy-linked rubrics; Doctor is read-only consumer on Patient Board | Existing Improvement | Security | Admin Portal | Web, QA
64 | 43 | Web | 1 | ADM-R04 | ADM-R04.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Remedy-linked rubrics; do not silently switch | Existing | API hygiene | Admin Portal | Web, QA
65 | 15 | QA | 1 | ADM-R05 | ADM-R05.01 | Regression: list / add / edit / (import-export if present) for Language master | Existing | QA | Admin Portal | Web, QA
66 | 44 | Web | 1 | ADM-R05 | ADM-R05.02 | ACL: only Admin (and permitted roles) can mutate Language master; Doctor is read-only consumer on Patient Board | Existing Improvement | Security | Admin Portal | Web, QA
67 | 45 | Web | 1 | ADM-R05 | ADM-R05.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Language master; do not silently switch | Existing | API hygiene | Admin Portal | Web, QA
68 | 16 | QA | 1 | ADM-R06 | ADM-R06.01 | Regression: list / add / edit / (import-export if present) for Body part master | Existing | QA | Admin Portal | Web, QA
69 | 46 | Web | 1 | ADM-R06 | ADM-R06.02 | ACL: only Admin (and permitted roles) can mutate Body part master; Doctor is read-only consumer on Patient Board | Existing Improvement | Security | Admin Portal | Web, QA
70 | 47 | Web | 1 | ADM-R06 | ADM-R06.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Body part master; do not silently switch | Existing | API hygiene | Admin Portal | Web, QA
71 | 17 | QA | 1 | ADM-R07 | ADM-R07.01 | Regression: list / add / edit / (import-export if present) for Intensity master | Existing | QA | Admin Portal | Web, QA
72 | 48 | Web | 1 | ADM-R07 | ADM-R07.02 | ACL: only Admin (and permitted roles) can mutate Intensity master; Doctor is read-only consumer on Patient Board | Existing Improvement | Security | Admin Portal | Web, QA
73 | 49 | Web | 1 | ADM-R07 | ADM-R07.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Intensity master; do not silently switch | Existing | API hygiene | Admin Portal | Web, QA
74 | 18 | QA | 1 | ADM-R08 | ADM-R08.01 | Regression: list / add / edit / (import-export if present) for Remedy master | Existing | QA | Admin Portal | Web, QA
75 | 50 | Web | 1 | ADM-R08 | ADM-R08.02 | ACL: only Admin (and permitted roles) can mutate Remedy master; Doctor is read-only consumer on Patient Board | Existing Improvement | Security | Admin Portal | Web, QA
76 | 51 | Web | 1 | ADM-R08 | ADM-R08.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Remedy master; do not silently switch | Existing | API hygiene | Admin Portal | Web, QA
77 | 19 | QA | 1 | ADM-R09 | ADM-R09.01 | Regression: list / add / edit / (import-export if present) for Remedy grade master | Existing | QA | Admin Portal | Web, QA
78 | 52 | Web | 1 | ADM-R09 | ADM-R09.02 | ACL: only Admin (and permitted roles) can mutate Remedy grade master; Doctor is read-only consumer on Patient Board | Existing Improvement | Security | Admin Portal | Web, QA
79 | 53 | Web | 1 | ADM-R09 | ADM-R09.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Remedy grade master; do not silently switch | Existing | API hygiene | Admin Portal | Web, QA
80 | 20 | QA | 1 | ADM-M01 | ADM-M01.01 | Regression: list / add / edit / (import-export if present) for Author master | Existing | QA | Admin Portal | Web, QA
81 | 54 | Web | 1 | ADM-M01 | ADM-M01.02 | ACL: only Admin (and permitted roles) can mutate Author master; Doctor is read-only consumer on Patient Board | Existing Improvement | Security | Admin Portal | Web, QA
82 | 55 | Web | 1 | ADM-M01 | ADM-M01.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Author master; do not silently switch | Existing | API hygiene | Admin Portal | Web, QA
83 | 21 | QA | 1 | ADM-M02 | ADM-M02.01 | Regression: list / add / edit / (import-export if present) for Materia medica master | Existing | QA | Admin Portal | Web, QA
84 | 56 | Web | 1 | ADM-M02 | ADM-M02.02 | ACL: only Admin (and permitted roles) can mutate Materia medica master; Doctor is read-only consumer on Patient Board | Existing Improvement | Security | Admin Portal | Web, QA
85 | 57 | Web | 1 | ADM-M02 | ADM-M02.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Materia medica master; do not silently switch | Existing | API hygiene | Admin Portal | Web, QA
86 | 22 | QA | 1 | ADM-M03 | ADM-M03.01 | Regression: list / add / edit / (import-export if present) for Materia medica heads | Existing | QA | Admin Portal | Web, QA
87 | 58 | Web | 1 | ADM-M03 | ADM-M03.02 | ACL: only Admin (and permitted roles) can mutate Materia medica heads; Doctor is read-only consumer on Patient Board | Existing Improvement | Security | Admin Portal | Web, QA
88 | 59 | Web | 1 | ADM-M03 | ADM-M03.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Materia medica heads; do not silently switch | Existing | API hygiene | Admin Portal | Web, QA
89 | 23 | QA | 1 | ADM-M04 | ADM-M04.01 | Regression: list / add / edit / (import-export if present) for Materia medica remedies | Existing | QA | Admin Portal | Web, QA
90 | 60 | Web | 1 | ADM-M04 | ADM-M04.02 | ACL: only Admin (and permitted roles) can mutate Materia medica remedies; Doctor is read-only consumer on Patient Board | Existing Improvement | Security | Admin Portal | Web, QA
91 | 61 | Web | 1 | ADM-M04 | ADM-M04.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Materia medica remedies; do not silently switch | Existing | API hygiene | Admin Portal | Web, QA
92 | 24 | QA | 1 | ADM-D01 | ADM-D01.01 | Regression: list / add / edit / (import-export if present) for Diagnosis system | Existing | QA | Admin Portal | Web, QA
93 | 62 | Web | 1 | ADM-D01 | ADM-D01.02 | ACL: only Admin (and permitted roles) can mutate Diagnosis system; Doctor is read-only consumer on Patient Board | Existing Improvement | Security | Admin Portal | Web, QA
94 | 63 | Web | 1 | ADM-D01 | ADM-D01.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Diagnosis system; do not silently switch | Existing | API hygiene | Admin Portal | Web, QA
95 | 25 | QA | 1 | ADM-D02 | ADM-D02.01 | Regression: list / add / edit / (import-export if present) for Diagnosis therapeutics | Existing | QA | Admin Portal | Web, QA
96 | 64 | Web | 1 | ADM-D02 | ADM-D02.02 | ACL: only Admin (and permitted roles) can mutate Diagnosis therapeutics; Doctor is read-only consumer on Patient Board | Existing Improvement | Security | Admin Portal | Web, QA
97 | 65 | Web | 1 | ADM-D02 | ADM-D02.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Diagnosis therapeutics; do not silently switch | Existing | API hygiene | Admin Portal | Web, QA
98 | 26 | QA | 1 | ADM-D03 | ADM-D03.01 | Regression: list / add / edit / (import-export if present) for Diagnosis conditions | Existing | QA | Admin Portal | Web, QA
99 | 66 | Web | 1 | ADM-D03 | ADM-D03.02 | ACL: only Admin (and permitted roles) can mutate Diagnosis conditions; Doctor is read-only consumer on Patient Board | Existing Improvement | Security | Admin Portal | Web, QA
100 | 67 | Web | 1 | ADM-D03 | ADM-D03.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Diagnosis conditions; do not silently switch | Existing | API hygiene | Admin Portal | Web, QA
101 | 27 | QA | 1 | ADM-A01 | ADM-A01.01 | Regression: list / add / edit / (import-export if present) for Drug system | Existing | QA | Admin Portal | Web, QA
102 | 68 | Web | 1 | ADM-A01 | ADM-A01.02 | ACL: only Admin (and permitted roles) can mutate Drug system; Doctor is read-only consumer on Patient Board | Existing Improvement | Security | Admin Portal | Web, QA
103 | 69 | Web | 1 | ADM-A01 | ADM-A01.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Drug system; do not silently switch | Existing | API hygiene | Admin Portal | Web, QA
104 | 28 | QA | 1 | ADM-A02 | ADM-A02.01 | Regression: list / add / edit / (import-export if present) for Drug group | Existing | QA | Admin Portal | Web, QA
105 | 70 | Web | 1 | ADM-A02 | ADM-A02.02 | ACL: only Admin (and permitted roles) can mutate Drug group; Doctor is read-only consumer on Patient Board | Existing Improvement | Security | Admin Portal | Web, QA
106 | 71 | Web | 1 | ADM-A02 | ADM-A02.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Drug group; do not silently switch | Existing | API hygiene | Admin Portal | Web, QA
107 | 29 | QA | 1 | ADM-A03 | ADM-A03.01 | Regression: list / add / edit / (import-export if present) for Allopathic drug & side effects | Existing | QA | Admin Portal | Web, QA
108 | 72 | Web | 1 | ADM-A03 | ADM-A03.02 | ACL: only Admin (and permitted roles) can mutate Allopathic drug & side effects; Doctor is read-only consumer on Patient Board | Existing Improvement | Security | Admin Portal | Web, QA
109 | 73 | Web | 1 | ADM-A03 | ADM-A03.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Allopathic drug & side effects; do not silently switch | Existing | API hygiene | Admin Portal | Web, QA
110 | 30 | QA | 1 | ADM-Q01 | ADM-Q01.01 | Regression: list / add / edit / (import-export if present) for Question section, group & sub-group | Existing | QA | Admin Portal | Web, QA
111 | 74 | Web | 1 | ADM-Q01 | ADM-Q01.02 | ACL: only Admin (and permitted roles) can mutate Question section, group & sub-group; Doctor is read-only consumer on Patient Board | Existing Improvement | Security | Admin Portal | Web, QA
112 | 75 | Web | 1 | ADM-Q01 | ADM-Q01.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Question section, group & sub-group; do not silently switch | Existing | API hygiene | Admin Portal | Web, QA
113 | 31 | QA | 1 | ADM-Q02 | ADM-Q02.01 | Regression: list / add / edit / (import-export if present) for Clinical question mapping | Existing | QA | Admin Portal | Web, QA
114 | 76 | Web | 1 | ADM-Q02 | ADM-Q02.02 | ACL: only Admin (and permitted roles) can mutate Clinical question mapping; Doctor is read-only consumer on Patient Board | Existing Improvement | Security | Admin Portal | Web, QA
115 | 77 | Web | 1 | ADM-Q02 | ADM-Q02.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Clinical question mapping; do not silently switch | Existing | API hygiene | Admin Portal | Web, QA
116 | 32 | QA | 1 | ADM-3D1 | ADM-3D1.01 | Regression: list / add / edit / (import-export if present) for 3D mesh key master | Existing | QA | Admin Portal | Web, QA
117 | 78 | Web | 1 | ADM-3D1 | ADM-3D1.02 | ACL: only Admin (and permitted roles) can mutate 3D mesh key master; Doctor is read-only consumer on Patient Board | Existing Improvement | Security | Admin Portal | Web, QA
118 | 79 | Web | 1 | ADM-3D1 | ADM-3D1.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for 3D mesh key master; do not silently switch | Existing | API hygiene | Admin Portal | Web, QA
119 | 33 | QA | 1 | ADM-3D2 | ADM-3D2.01 | Regression: list / add / edit / (import-export if present) for 3D section master | Existing | QA | Admin Portal | Web, QA
120 | 80 | Web | 1 | ADM-3D2 | ADM-3D2.02 | ACL: only Admin (and permitted roles) can mutate 3D section master; Doctor is read-only consumer on Patient Board | Existing Improvement | Security | Admin Portal | Web, QA
121 | 81 | Web | 1 | ADM-3D2 | ADM-3D2.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for 3D section master; do not silently switch | Existing | API hygiene | Admin Portal | Web, QA
122 | 34 | QA | 1 | ADM-3D3 | ADM-3D3.01 | Regression: list / add / edit / (import-export if present) for 3D hotspots | Existing | QA | Admin Portal | Web, QA
123 | 82 | Web | 1 | ADM-3D3 | ADM-3D3.02 | ACL: only Admin (and permitted roles) can mutate 3D hotspots; Doctor is read-only consumer on Patient Board | Existing Improvement | Security | Admin Portal | Web, QA
124 | 83 | Web | 1 | ADM-3D3 | ADM-3D3.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for 3D hotspots; do not silently switch | Existing | API hygiene | Admin Portal | Web, QA
125 | 35 | QA | 1 | ADM-B01 | ADM-B01.01 | Regression: qualifications list/add/edit | Existing | QA | Admin Portal | Web, QA
126 | 84 | Web | 1 | ADM-B01 | ADM-B01.02 | ACL on qualification APIs | Existing Improvement | Security | Admin Portal | Web, QA
127 | 85 | Web | 1 | ADM-B01 | ADM-B01.03 | Confirm UI uses newer API (not classic) for qualifications | Existing | API hygiene | Admin Portal | Web, QA
128 | 36 | QA | 1 | ADM-B02 | ADM-B02.01 | Regression: lab catalog CRUD and doctor order pick-list | Existing | QA | Admin Portal | Web, QA
129 | 86 | Web | 1 | ADM-B02 | ADM-B02.02 | ACL on catalog mutate | Existing Improvement | Security | Admin Portal | Web, QA
130 | 87 | Web | 1 | ADM-B02 | ADM-B02.03 | Confirm classic PatientLab APIs still read this catalogue | Existing | API hygiene | Admin Portal | Web, QA
131 | 37 | QA | 1 | ADM-B03 | ADM-B03.01 | Regression: package list/add/edit; doctor Widgets still reads packages | Existing | QA | Admin Portal | Web, QA
132 | 88 | Web | 1 | ADM-B03 | ADM-B03.02 | ACL on package mutate | Existing Improvement | Security | Admin Portal | Web, QA
133 | 89 | Web | 1 | ADM-B03 | ADM-B03.03 | Note in code: PackageEntryDetail is S1 only — never reuse for S2 consult or S5 medicine | Existing | API hygiene | Admin Portal | Web, QA
134 | 90 | Web | 1 | ADM-B04 | ADM-B04.01 | No schema change unless Account/Pharmacy/Patient roles need new MenuMaster rows — seed those menus | Existing Improvement | Database | Admin Portal | Web, UI, QA
135 | 91 | Web | 1 | ADM-B04 | ADM-B04.02 | Restore GetMenuByRole on .NET 8; seed menus for Account and (later) Pharmacy | Existing Improvement | API | Admin Portal | Web, UI, QA
136 | 7 | UI | 1 | ADM-B04 | ADM-B04.03 | Admin role pages remain; frontend consumes menu API instead of hard-coded LayoutMenuData for domain items | Existing Improvement | Web SPA | Admin Portal | Web, UI, QA
137 | 38 | QA | 1 | ADM-B04 | ADM-B04.04 | QA: edit role menu → user of that role no longer sees the item | Regression | QA | Admin Portal | Web, UI, QA
138 | 8 | UI | 2 | CLN-01 | CLN-01.01 | UI: Patient Board header shows appointment, visit type, consult mode placeholders (wired in Phases 4 and 6) | Existing Improvement | Web SPA | Doctor Web Portal | Web, UI, QA
139 | 92 | Web | 2 | CLN-01 | CLN-01.02 | Do not split the board into multiple apps; mobile doctor app will NOT get case-taking (PDF §3) | Existing | Architecture | Doctor Web Portal | Web, UI, QA
140 | 39 | QA | 2 | CLN-01 | CLN-01.03 | Regression: open case from dashboard still remounts via PatientBoardRoute | Regression | QA | Doctor Web Portal | Web, UI, QA
141 | 40 | QA | 2 | CLN-02 | CLN-02.01 | Regression: create case, add rubrics via manual path, repertorize | Existing | QA | Doctor Web Portal | Web, QA
142 | 93 | Web | 2 | CLN-02 | CLN-02.02 | ACL: only treating doctor (not Reception) can run full case taking | Existing Improvement | Security | Doctor Web Portal | Web, QA
143 | 94 | Web | 2 | CLN-02 | CLN-02.03 | Confirm clipboard/repertorization APIs still on the correct host | Existing | API hygiene | Doctor Web Portal | Web, QA
144 | 41 | QA | 2 | CLN-03 | CLN-03.01 | Regression: body part → rubrics; intensity chip | Existing | QA | Doctor Web Portal | Web, QA
145 | 95 | Web | 2 | CLN-03 | CLN-03.02 | ACL: doctor-only | Existing Improvement | Security | Doctor Web Portal | Web, QA
146 | 96 | Web | 2 | CLN-03 | CLN-03.03 | API host unchanged | Existing | API hygiene | Doctor Web Portal | Web, QA
147 | 42 | QA | 2 | CLN-04 | CLN-04.01 | Regression: full question drill-down | Existing | QA | Doctor Web Portal | Web, QA
148 | 97 | Web | 2 | CLN-04 | CLN-04.02 | ACL doctor-only | Existing Improvement | Security | Doctor Web Portal | Web, QA
149 | 98 | Web | 2 | CLN-04 | CLN-04.03 | API host unchanged | Existing | API hygiene | Doctor Web Portal | Web, QA
150 | 43 | QA | 2 | CLN-05 | CLN-05.01 | Regression: diagnosis search + therapeutics | Existing | QA | Doctor Web Portal | Web, QA
151 | 99 | Web | 2 | CLN-05 | CLN-05.02 | ACL doctor-only | Existing Improvement | Security | Doctor Web Portal | Web, QA
152 | 100 | Web | 2 | CLN-05 | CLN-05.03 | API host unchanged | Existing | API hygiene | Doctor Web Portal | Web, QA
153 | 44 | QA | 2 | CLN-06 | CLN-06.01 | Regression: tree + search + add to clipboard | Existing | QA | Doctor Web Portal | Web, QA
154 | 101 | Web | 2 | CLN-06 | CLN-06.02 | ACL doctor-only | Existing Improvement | Security | Doctor Web Portal | Web, QA
155 | 102 | Web | 2 | CLN-06 | CLN-06.03 | Confirm subsection search host (newer vs classic) documented | Existing | API hygiene | Doctor Web Portal | Web, QA
156 | 103 | Web | 2 | CLN-07 | CLN-07.01 | No new table — clipboard already persisted via board backup / repertorization payload | Existing Improvement | Database | Doctor Web Portal | Web, UI, QA
157 | 104 | Web | 2 | CLN-07 | CLN-07.02 | If intensity-on-clipboard is client-only, persist it on backup payload | Existing Improvement | API | Doctor Web Portal | Web, UI, QA
158 | 9 | UI | 2 | CLN-07 | CLN-07.03 | Clipboard UX: confirm delete; intensity edit; count badge | Existing Improvement | Web SPA | Doctor Web Portal | Web, UI, QA
159 | 45 | QA | 2 | CLN-07 | CLN-07.04 | QA: remove, undo-not-required, backup restore still has remaining rubrics | Regression | QA | Doctor Web Portal | Web, UI, QA
160 | 46 | QA | 2 | CLN-08 | CLN-08.01 | Regression: record, poll, approve/reject suggested rubrics | Existing | QA | Doctor Web Portal | Web, QA
161 | 105 | Web | 2 | CLN-08 | CLN-08.02 | Consent: audio consent continues to write AudioCaseConsentLog (later also ConsentRecord) | Existing Improvement | Security | Doctor Web Portal | Web, QA
162 | 106 | Web | 2 | CLN-08 | CLN-08.03 | Confirm audio queue/worker still healthy | Existing | API hygiene | Doctor Web Portal | Web, QA
163 | 107 | Web | 2 | CLN-09 | CLN-09.01 | Follow AUDIO_CASE_TAKING_* docs: accuracy rules, aliases, metaphors, benchmark | Existing Improvement | Backend | Doctor Web Portal + Admin intelligence | Web, UI, QA
164 | 10 | UI | 2 | CLN-09 | CLN-09.02 | Admin: metaphor/alias approve-reject remaining UX | Existing Improvement | Web SPA | Doctor Web Portal + Admin intelligence | Web, UI, QA
165 | 47 | QA | 2 | CLN-09 | CLN-09.03 | QA: golden transcripts → expected rubric IDs within tolerance | Regression | QA | Doctor Web Portal + Admin intelligence | Web, UI, QA
166 | 108 | Web | 2 | CLN-10 | CLN-10.01 | No schema change | Existing Improvement | Database | Doctor Web Portal | Web, UI, QA
167 | 109 | Web | 2 | CLN-10 | CLN-10.02 | Existing MM APIs — add a lightweight get-by-remedy if chatty | Existing Improvement | API | Doctor Web Portal | Web, UI, QA
168 | 11 | UI | 2 | CLN-10 | CLN-10.03 | MM tab: faster head navigation / keep place in case | Existing Improvement | Web SPA | Doctor Web Portal | Web, UI, QA
169 | 48 | QA | 2 | CLN-10 | CLN-10.04 | QA: open MM for a repertorized remedy | Regression | QA | Doctor Web Portal | Web, UI, QA
170 | 49 | QA | 2 | CLN-11 | CLN-11.01 | Regression: search drug → side effects | Existing | QA | Doctor Web Portal | Web, QA
171 | 110 | Web | 2 | CLN-11 | CLN-11.02 | ACL doctor-only | Existing Improvement | Security | Doctor Web Portal | Web, QA
172 | 111 | Web | 2 | CLN-11 | CLN-11.03 | API host unchanged | Existing | API hygiene | Doctor Web Portal | Web, QA
173 | 112 | Web | 2 | CLN-12 | CLN-12.01 | No schema change | Existing Improvement | Database | Doctor Web Portal | Web, UI, QA
174 | 113 | Web | 2 | CLN-12 | CLN-12.02 | Keep existing repertorization APIs; fix any known scoring edge cases | Existing Improvement | API | Doctor Web Portal | Web, UI, QA
175 | 12 | UI | 2 | CLN-12 | CLN-12.03 | Repertorize tab stability; then COG sits beside it | Existing Improvement | Web SPA | Doctor Web Portal | Web, UI, QA
176 | 50 | QA | 2 | CLN-12 | CLN-12.04 | QA: known case → expected top remedies | Regression | QA | Doctor Web Portal | Web, UI, QA
177 | 114 | Web | 2 | CLN-13 | CLN-13.01 | No mandatory new table (algorithm on selected rubrics); optional CogRun log for support | New | Database | Doctor Web Portal | Web, UI, QA
178 | 115 | Web | 2 | CLN-13 | CLN-13.02 | POST /api/Repertorization/CenterOfGravity — input rubric ids + intensities; output ranked remedies + reasons | New | API | Doctor Web Portal | Web, UI, QA
179 | 13 | UI | 2 | CLN-13 | CLN-13.03 | Patient Board → Repertorize tab → Center of Gravity sub-panel (toggle vs classic elimination) | New | Web SPA | Doctor Web Portal | Web, UI, QA
180 | 51 | QA | 2 | CLN-13 | CLN-13.04 | QA: same clipboard as classic repertorize; COG reasons cite contributing rubrics; empty clipboard → clear empty state | Regression | QA | Doctor Web Portal | Web, UI, QA
181 | 52 | QA | 2 | CLN-14 | CLN-14.01 | Regression: order lab from catalogue; enter result | Existing | QA | Doctor Web Portal | Web, QA
182 | 116 | Web | 2 | CLN-14 | CLN-14.02 | ACL doctor-only | Existing Improvement | Security | Doctor Web Portal | Web, QA
183 | 117 | Web | 2 | CLN-14 | CLN-14.03 | API: classic PatientLab still authoritative until ported | Existing | API hygiene | Doctor Web Portal | Web, QA
184 | 53 | QA | 2 | CLN-15 | CLN-15.01 | Regression: add/list notes on a visit | Existing | QA | Doctor Web Portal | Web, QA
185 | 118 | Web | 2 | CLN-15 | CLN-15.02 | ACL doctor-only | Existing Improvement | Security | Doctor Web Portal | Web, QA
186 | 119 | Web | 2 | CLN-15 | CLN-15.03 | Do not dual-write; classic notes stay until Phase 10 extends them | Existing | API hygiene | Doctor Web Portal | Web, QA
187 | 120 | Web | 2 | CLN-16 | CLN-16.01 | Use existing tables — no new schema unless fields are missing vs PDF | Existing Improvement | Database | Doctor Web Portal | Web, UI, QA
188 | 121 | Web | 2 | CLN-16 | CLN-16.02 | Keep classic SaveComplaints / SaveCaseDetails; add GET if missing | Existing Improvement | API | Doctor Web Portal | Web, UI, QA
189 | 14 | UI | 2 | CLN-16 | CLN-16.03 | Patient Board: complaints + case details form that actually POSTs | Existing Improvement | Web SPA | Doctor Web Portal | Web, UI, QA
190 | 54 | QA | 2 | CLN-16 | CLN-16.04 | QA: save, reload, second doctor cannot read | Regression | QA | Doctor Web Portal | Web, UI, QA
191 | 122 | Web | 2 | CLN-17 | CLN-17.01 | No new table — compose from Appointment + notes + Rx + (later) ConsultPayment | Existing Improvement | Database | Doctor Web Portal | Web, UI, QA
192 | 123 | Web | 2 | CLN-17 | CLN-17.02 | GET patient timeline DTO including payment status when column exists | Existing Improvement | API | Doctor Web Portal | Web, UI, QA
193 | 15 | UI | 2 | CLN-17 | CLN-17.03 | History panel: date-ordered visits; open past eRx; payment badge placeholder | Existing Improvement | Web SPA | Doctor Web Portal | Web, UI, QA
194 | 55 | QA | 2 | CLN-17 | CLN-17.04 | QA: multi-visit patient; empty new patient | Regression | QA | Doctor Web Portal | Web, UI, QA
195 | 124 | Web | 2 | CLN-18 | CLN-18.01 | Reuse ExportCasesToExcel; add PDF generation of the clinical case (doctor copy, includes notes) | Existing Improvement | API | Doctor Web Portal | Web, UI, QA
196 | 16 | UI | 2 | CLN-18 | CLN-18.02 | Patient Board toolbar: Export Excel / Export PDF | New | Web SPA | Doctor Web Portal | Web, UI, QA
197 | 56 | QA | 2 | CLN-18 | CLN-18.03 | QA: export matches on-screen rubrics + Rx; unauthorised doctor 403 | Regression | QA | Doctor Web Portal | Web, UI, QA
198 | 57 | QA | 2 | CLN-19 | CLN-19.01 | Regression: backup, restore, 5-session stack | Existing | QA | Doctor Web Portal | Web, QA
199 | 125 | Web | 2 | CLN-19 | CLN-19.02 | ACL: backup scoped to DoctorId | Existing Improvement | Security | Doctor Web Portal | Web, QA
200 | 126 | Web | 2 | CLN-19 | CLN-19.03 | API: PatientBoardBackup on .NET 8 unchanged | Existing | API hygiene | Doctor Web Portal | Web, QA
201 | 127 | Web | 2 | CLN-20 | CLN-20.01 | No new tables — Mesh/Section/Hotspot masters already exist | Existing Improvement | Database | Doctor Web Portal | Web, UI, QA
202 | 128 | Web | 2 | CLN-20 | CLN-20.02 | Fix hotspot mapping gaps on newer threeDBodyPart APIs | Existing Improvement | API | Doctor Web Portal | Web, UI, QA
203 | 17 | UI | 2 | CLN-20 | CLN-20.03 | Viewer UX: incomplete regions, loading, fallback message | Existing Improvement | Web SPA | Doctor Web Portal | Web, UI, QA
204 | 58 | QA | 2 | CLN-20 | CLN-20.04 | QA: click hotspot → subsection search results | Regression | QA | Doctor Web Portal | Web, UI, QA
205 | 129 | Web | 3 | DOC-01 | DOC-01.01 | No new dashboard table | Existing Improvement | Database | Doctor Web Portal | Web, UI, QA
206 | 130 | Web | 3 | DOC-01 | DOC-01.02 | Extend dashboard DTOs with paymentStatus / tele flags when columns exist (nullable until Phase 6/11) | Existing Improvement | API | Doctor Web Portal | Web, UI, QA
207 | 18 | UI | 3 | DOC-01 | DOC-01.03 | Dashboard chrome: keep counts; add slots for Online toggle, tele queue, unpaid badge | Existing Improvement | Web SPA | Doctor Web Portal | Web, UI, QA
208 | 59 | QA | 3 | DOC-01 | DOC-01.04 | QA: existing buckets still populate; reception still shares layout until Phase 5 reception chrome | Regression | QA | Doctor Web Portal | Web, UI, QA
209 | 60 | QA | 3 | DOC-02 | DOC-02.01 | Regression: each bucket count and click-through | Existing | QA | Doctor Web Portal | Web, QA
210 | 131 | Web | 3 | DOC-02 | DOC-02.02 | Reception sharing this view is OK until Phase 5 splits chrome | Existing Improvement | Security | Doctor Web Portal | Web, QA
211 | 132 | Web | 3 | DOC-02 | DOC-02.03 | API: existing dashboard count endpoints | Existing | API hygiene | Doctor Web Portal | Web, QA
212 | 133 | Web | 3 | DOC-03 | DOC-03.01 | Use existing Patient + Appointment — add DTO fields | Existing Improvement | Database | Doctor Web Portal | Web, UI, QA
213 | 134 | Web | 3 | DOC-03 | DOC-03.02 | Search DTO includes lastVisitAt | Existing Improvement | API | Doctor Web Portal | Web, UI, QA
214 | 19 | UI | 3 | DOC-03 | DOC-03.03 | List columns: last visit; later payment/family | Existing Improvement | Web SPA | Doctor Web Portal | Web, UI, QA
215 | 61 | QA | 3 | DOC-03 | DOC-03.04 | QA: search by name/mobile; open case | Regression | QA | Doctor Web Portal | Web, UI, QA
216 | 62 | QA | 3 | DOC-04 | DOC-04.01 | Regression: add patient validation and save | Existing | QA | Doctor Web Portal | Web, QA
217 | 135 | Web | 3 | DOC-04 | DOC-04.02 | ACL: doctor/reception of that clinic only | Existing Improvement | Security | Doctor Web Portal | Web, QA
218 | 136 | Web | 3 | DOC-04 | DOC-04.03 | API unchanged | Existing | API hygiene | Doctor Web Portal | Web, QA
219 | 63 | QA | 3 | DOC-05 | DOC-05.01 | Regression: template + import + error rows | Existing | QA | Doctor Web Portal | Web, QA
220 | 137 | Web | 3 | DOC-05 | DOC-05.02 | ACL doctor-only (or reception if already allowed) | Existing Improvement | Security | Doctor Web Portal | Web, QA
221 | 138 | Web | 3 | DOC-05 | DOC-05.03 | API unchanged | Existing | API hygiene | Doctor Web Portal | Web, QA
222 | 139 | Web | 3 | DOC-06 | DOC-06.01 | Audit current export formats; add PDF if only Excel/CSV exist today | Existing Improvement | API | Doctor Web Portal | Web, UI, QA
223 | 20 | UI | 3 | DOC-06 | DOC-06.02 | UI: Excel / CSV / PDF actions labelled as in the delivery document | Existing Improvement | Web SPA | Doctor Web Portal | Web, UI, QA
224 | 64 | QA | 3 | DOC-06 | DOC-06.03 | QA: another doctor cannot export this list | Regression | QA | Doctor Web Portal | Web, UI, QA
225 | 65 | QA | 3 | DOC-07 | DOC-07.01 | Regression: activity loads | Existing | QA | Doctor Web Portal | Web, QA
226 | 140 | Web | 3 | DOC-07 | DOC-07.02 | ACL scoped to doctor | Existing Improvement | Security | Doctor Web Portal | Web, QA
227 | 141 | Web | 3 | DOC-07 | DOC-07.03 | API unchanged | Existing | API hygiene | Doctor Web Portal | Web, QA
228 | 66 | QA | 3 | DOC-08 | DOC-08.01 | Regression: stats charts date range | Existing | QA | Doctor Web Portal | Web, QA
229 | 142 | Web | 3 | DOC-08 | DOC-08.02 | ACL doctor-only | Existing Improvement | Security | Doctor Web Portal | Web, QA
230 | 143 | Web | 3 | DOC-08 | DOC-08.03 | API unchanged | Existing | API hygiene | Doctor Web Portal | Web, QA
231 | 144 | Web | 3 | DOC-09 | DOC-09.01 | No new API — authorise that the doctor owns the staff record on existing CRUD | Existing Improvement | API | Doctor Web Portal | Web, UI, QA
232 | 21 | UI | 3 | DOC-09 | DOC-09.02 | Build /doctor/reception-staff list, add, edit, disable pages; menu entry in doctor chrome | Existing Improvement | Web SPA | Doctor Web Portal | Web, UI, QA
233 | 67 | QA | 3 | DOC-09 | DOC-09.03 | QA: reception user cannot manage other doctors’ staff; disable prevents login | Regression | QA | Doctor Web Portal | Web, UI, QA
234 | 145 | Web | 3 | DOC-10 | DOC-10.01 | Extend Doctor / add DoctorPayeeKyc fields (bank, PAN) used later by Account; ConsultFeeConfig may wait until Phase 6 — store fee on profile now if simpler | Existing Improvement | Database | Doctor Web Portal | Web, UI, QA
235 | 146 | Web | 3 | DOC-10 | DOC-10.02 | GET/PUT /api/Profile/Me (doctor DTO); POST photo multipart; do not allow role escalation | Existing Improvement | API | Doctor Web Portal | Web, UI, QA
236 | 22 | UI | 3 | DOC-10 | DOC-10.03 | Replace Velzon /profile for doctor role with clinic/fee/photo/qualifications/hours/bank tabs | Existing Improvement | Web SPA | Doctor Web Portal | Web, UI, QA
237 | 68 | QA | 3 | DOC-10 | DOC-10.04 | QA: reception cannot edit doctor bank details; photo displays on public profile later | Regression | QA | Doctor Web Portal | Web, UI, QA
238 | 69 | QA | 4 | APT-01 | APT-01.01 | Regression: day list, status colour, open patient | Existing | QA | Doctor Web Portal | Web, QA
239 | 147 | Web | 4 | APT-01 | APT-01.02 | ACL doctor/reception of that DoctorId | Existing Improvement | Security | Doctor Web Portal | Web, QA
240 | 148 | Web | 4 | APT-01 | APT-01.03 | API unchanged | Existing | API hygiene | Doctor Web Portal | Web, QA
241 | 149 | Web | 4 | APT-02 | APT-02.01 | DB: PatientAppointment.VisitType, ConsultMode; migrate existing rows VisitType=First (do not infer retrospectively) | Existing Improvement | Database | Doctor Web Portal | Web, UI, QA
242 | 150 | Web | 4 | APT-02 | APT-02.02 | API: create/update appointment accepts the new fields; PATCH VisitType | Existing Improvement | API | Doctor Web Portal | Web, UI, QA
243 | 23 | UI | 4 | APT-02 | APT-02.03 | Doctor/Reception new-appointment modal: visit type, consult mode, fee (placeholder until Phase 6 config) | Existing Improvement | Web SPA | Doctor Web Portal | Web, UI, QA
244 | 70 | QA | 4 | APT-02 | APT-02.04 | QA: staff-created appointments carry the same fields public booking will use in Phase 9 | Regression | QA | Doctor Web Portal | Web, UI, QA
245 | 71 | QA | 4 | APT-03 | APT-03.01 | Regression: each status transition | Existing | QA | Doctor Web Portal | Web, QA
246 | 151 | Web | 4 | APT-03 | APT-03.02 | ACL doctor/reception | Existing Improvement | Security | Doctor Web Portal | Web, QA
247 | 152 | Web | 4 | APT-03 | APT-03.03 | API unchanged | Existing | API hygiene | Doctor Web Portal | Web, QA
248 | 72 | QA | 4 | APT-04 | APT-04.01 | Regression: UpdateAppointmentTime on dashboard | Existing | QA | Doctor Web Portal | Web, QA
249 | 153 | Web | 4 | APT-04 | APT-04.02 | Document in UI that Reschedule is the patient-notified path | Existing Improvement | Security | Doctor Web Portal | Web, QA
250 | 154 | Web | 4 | APT-04 | APT-04.03 | API: keep UpdateAppointmentTime; Reschedule wraps it | Existing | API hygiene | Doctor Web Portal | Web, QA
251 | 155 | Web | 4 | APT-05 | APT-05.01 | DB: AppointmentChangeLog (PatientAppId, Action, OldValue, NewValue, ByUserId, ByRole, At) + indexes | New | Database | Doctor Web + Reception + later Patient | Web, UI, QA
252 | 156 | Web | 4 | APT-05 | APT-05.02 | API: POST /api/PatientAppointment/RescheduleAppointment — validate schedule, bookings, not in the past; 409 with alternatives; wrap UpdateAppointmentTime; GET ChangeLog/{id} | New | API | Doctor Web + Reception + later Patient | Web, UI, QA
253 | 24 | UI | 4 | APT-05 | APT-05.03 | UI: RescheduleModal shared by Doctor and Reception — old date/time + new slot picker; reason optional | New | Web SPA | Doctor Web + Reception + later Patient | Web, UI, QA
254 | 157 | Web | 4 | APT-05 | APT-05.04 | Notifications: SMS + WhatsApp + (later) push — old→new; must not block the transaction if notify fails | New Integration | Integration | Doctor Web + Reception + later Patient | Web, UI, QA
255 | 73 | QA | 4 | APT-05 | APT-05.05 | QA: slot taken → 409; patient already booked elsewhere; across a schedule change; reception authorised for own DoctorId only | Regression | QA | Doctor Web + Reception + later Patient | Web, UI, QA
256 | 158 | Web | 4 | APT-06 | APT-06.01 | DB: add CANCELLED to status set; CancelReasonCode, CancelReasonText, CancelledBy, CancelledAt; DeleteStatus remains administrative | New | Database | Doctor Web + Reception + later Patient | Web, UI, QA
257 | 159 | Web | 4 | APT-06 | APT-06.02 | API: POST /api/PatientAppointment/CancelAppointment — reason required (enum; text if Other); free slot; offer waitlist stub; if PAID enqueue refund policy | New | API | Doctor Web + Reception + later Patient | Web, UI, QA
258 | 25 | UI | 4 | APT-06 | APT-06.03 | UI: CancelAppointmentModal shared by Doctor and Reception; dashboard Cancelled filter | New | Web SPA | Doctor Web + Reception + later Patient | Web, UI, QA
259 | 160 | Web | 4 | APT-06 | APT-06.04 | Waitlist worker stub: on cancel, offer freed slot (full waitlist capture is Phase 9 GST waitlist) | New Integration | Integration | Doctor Web + Reception + later Patient | Web, UI, QA
260 | 74 | QA | 4 | APT-06 | APT-06.05 | QA: reason mandatory; all three roles (later Patient) cancel with correct authorisation; freed slot bookable | Regression | QA | Doctor Web + Reception + later Patient | Web, UI, QA
261 | 26 | UI | 4 | APT-07 | APT-07.01 | Promote DailyScheduleSetupModal to /doctor/schedule; week grid; copy-day; reuse Get/SaveDailySchedule | Existing Improvement | Web SPA | Doctor Web Portal | Web, UI, QA
262 | 161 | Web | 4 | APT-07 | APT-07.02 | No new API unless validation (breaks, overlapping hours) is missing — add server-side validation | Existing Improvement | API | Doctor Web Portal | Web, UI, QA
263 | 75 | QA | 4 | APT-07 | APT-07.03 | QA: save week; public slot generator (Phase 9) uses this data; reception read-only is Phase 5 | Regression | QA | Doctor Web Portal | Web, UI, QA
264 | 76 | QA | 4 | APT-08 | APT-08.01 | Regression: slot grid vs schedule | Existing | QA | Doctor Web Portal | Web, QA
265 | 162 | Web | 4 | APT-08 | APT-08.02 | ACL doctor/reception | Existing Improvement | Security | Doctor Web Portal | Web, QA
266 | 163 | Web | 4 | APT-08 | APT-08.03 | Document GetAppointmentSlots as the public-booking engine — do not fork a second slot calculator | Existing | API hygiene | Doctor Web Portal | Web, QA
267 | 164 | Web | 4 | APT-09 | APT-09.01 | DB: PatientAppointment.PaymentStatus, PaymentMethod, PayAtClinicAllowed; default UNPAID | New | Database | Doctor Web Portal | Web, UI, QA
268 | 165 | Web | 4 | APT-09 | APT-09.02 | API: include PaymentStatus on all appointment DTOs (doctor, reception, later public/patient) | New | API | Doctor Web Portal | Web, UI, QA
269 | 27 | UI | 4 | APT-09 | APT-09.03 | UI: Paid / Unpaid / Pay-at-clinic / Failed badges on doctor appointment list | New | Web SPA | Doctor Web Portal | Web, UI, QA
270 | 77 | QA | 4 | APT-09 | APT-09.04 | QA: same appointment shows the same badge on doctor and reception | Regression | QA | Doctor Web Portal | Web, UI, QA
271 | 78 | QA | 5 | REC-01 | REC-01.01 | Regression: reception login with DoctorID claim | Existing | QA | Reception Portal | Web, QA
272 | 166 | Web | 5 | REC-01 | REC-01.02 | Disabled staff cannot login (after DOC-09) | Existing Improvement | Security | Reception Portal | Web, QA
273 | 167 | Web | 5 | REC-01 | REC-01.03 | Same Login API as doctor | Existing | API hygiene | Reception Portal | Web, QA
274 | 168 | Web | 5 | REC-02 | REC-02.01 | Reuse Profile/Me with role=Reception DTO (no new table if UserMaster suffices) | New | Database | Reception Portal | Web, UI, QA
275 | 169 | Web | 5 | REC-02 | REC-02.02 | GET/PUT profile fields allowed for reception; ignore clinic fee/bank | New | API | Reception Portal | Web, UI, QA
276 | 28 | UI | 5 | REC-02 | REC-02.03 | /profile reception variant | New | Web SPA | Reception Portal | Web, UI, QA
277 | 79 | QA | 5 | REC-02 | REC-02.04 | QA: cannot edit doctor qualifications or fee | Regression | QA | Reception Portal | Web, UI, QA
278 | 29 | UI | 5 | REC-03 | REC-03.01 | Route /reception (or role-based chrome on existing dashboard) hiding clinical tabs | Existing Improvement | Web SPA | Reception Portal | UI, QA
279 | 30 | UI | 5 | REC-03 | REC-03.02 | Quick actions: new patient, new appointment, collect payment, case paper, schedule | Existing Improvement | Web SPA | Reception Portal | UI, QA
280 | 80 | QA | 5 | REC-03 | REC-03.03 | QA: deep-link to Patient Board full clinical URL is 403 for reception | Regression | QA | Reception Portal | UI, QA
281 | 81 | QA | 5 | REC-04 | REC-04.01 | Regression: reception create patient | Existing | QA | Reception Portal | Web, QA
282 | 170 | Web | 5 | REC-04 | REC-04.02 | ACL: own doctor only | Existing Improvement | Security | Reception Portal | Web, QA
283 | 171 | Web | 5 | REC-04 | REC-04.03 | Same create-patient API | Existing | API hygiene | Reception Portal | Web, QA
284 | 82 | QA | 5 | REC-05 | REC-05.01 | Regression: search by name/mobile | Existing | QA | Reception Portal | Web, QA
285 | 172 | Web | 5 | REC-05 | REC-05.02 | Opening a row goes to case paper or appointment, not full repertory | Existing Improvement | Security | Reception Portal | Web, QA
286 | 173 | Web | 5 | REC-05 | REC-05.03 | API unchanged | Existing | API hygiene | Reception Portal | Web, QA
287 | 174 | Web | 5 | REC-06 | REC-06.01 | Authorise Reception for Reschedule and Cancel for its own doctor's appointments only | New | API + SPA | Reception Portal | Web, UI, QA
288 | 31 | UI | 5 | REC-06 | REC-06.02 | Reception UI uses the same Reschedule/Cancel modals as doctor | New | Web SPA | Reception Portal | Web, UI, QA
289 | 83 | QA | 5 | REC-06 | REC-06.03 | QA: cannot cancel another clinic’s appointment | Regression | QA | Reception Portal | Web, UI, QA
290 | 32 | UI | 5 | REC-07 | REC-07.01 | Share the extended new-appointment modal with reception chrome | Existing Improvement | Web SPA | Reception Portal | UI, QA
291 | 84 | QA | 5 | REC-07 | REC-07.02 | QA: in-clinic vs E-Consult both creatable from reception | Regression | QA | Reception Portal | UI, QA
292 | 175 | Web | 5 | REC-08 | REC-08.01 | No new table required if status+order suffice; optional QueuePosition | Existing Improvement | Database | Reception Portal | Web, UI, QA
293 | 176 | Web | 5 | REC-08 | REC-08.02 | Optional CallNext API that sets status and timestamp | Existing Improvement | API | Reception Portal | Web, UI, QA
294 | 33 | UI | 5 | REC-08 | REC-08.03 | Queue panel: order, wait time, paid/unpaid, Call next | Existing Improvement | Web SPA | Reception Portal | Web, UI, QA
295 | 85 | QA | 5 | REC-08 | REC-08.04 | QA: two waiting patients; call next picks the right one | Regression | QA | Reception Portal | Web, UI, QA
296 | 86 | QA | 5 | REC-09 | REC-09.01 | Regression: reception status update | Existing | QA | Reception Portal | Web, QA
297 | 177 | Web | 5 | REC-09 | REC-09.02 | ACL own doctor | Existing Improvement | Security | Reception Portal | Web, QA
298 | 178 | Web | 5 | REC-09 | REC-09.03 | Same status API as doctor | Existing | API hygiene | Reception Portal | Web, QA
299 | 87 | QA | 5 | REC-10 | REC-10.01 | Regression: reception UpdateAppointmentTime | Existing | QA | Reception Portal | Web, QA
300 | 179 | Web | 5 | REC-10 | REC-10.02 | ACL own doctor | Existing Improvement | Security | Reception Portal | Web, QA
301 | 180 | Web | 5 | REC-10 | REC-10.03 | Same API | Existing | API hygiene | Reception Portal | Web, QA
302 | 34 | UI | 5 | REC-11 | REC-11.01 | Frontend only over existing GetDailySchedule — /reception/schedule read-only | New | Web SPA | Reception Portal | UI, QA
303 | 88 | QA | 5 | REC-11 | REC-11.02 | QA: edit buttons hidden; doctor can still edit on /doctor/schedule | Regression | QA | Reception Portal | UI, QA
304 | 181 | Web | 5 | REC-12 | REC-12.01 | Reuse complaints table; add CreatedByRole=Reception | New | Database | Reception Portal | Web, UI, QA
305 | 182 | Web | 5 | REC-12 | REC-12.02 | POST case-paper subset of SaveComplaints; GET on board | New | API | Reception Portal | Web, UI, QA
306 | 35 | UI | 5 | REC-12 | REC-12.03 | /reception/case-paper or limited board | New | Web SPA | Reception Portal | Web, UI, QA
307 | 89 | QA | 5 | REC-12 | REC-12.04 | QA: doctor sees CC; reception 403 on repertory APIs | Regression | QA | Reception Portal | Web, UI, QA
308 | 36 | UI | 5 | REC-13 | REC-13.01 | Specify receipt fields (amount, method, appointment, GST placeholder) for Phase 6 implementation | New | Design | Reception Portal | Web, UI
309 | 183 | Web | 5 | REC-13 | REC-13.02 | Do not write PaymentStatus=PAID from the client — Account/webhook is source of truth (Phase 6) | New | Architecture | Reception Portal | Web, UI
310 | 184 | Web | 6 | PAY-01 | PAY-01.01 | DB: ConsultFeeConfig (DoctorId, InClinicFee, TeleFee, InstantSurcharge, Currency, PayAtClinicEnabled, EffectiveFrom) | New | Database | Doctor profile + Public + Admin | Web, UI, QA
311 | 185 | Web | 6 | PAY-01 | PAY-01.02 | API: GET public fee; PUT doctor/admin; history of changes in audit | New | API | Doctor profile + Public + Admin | Web, UI, QA
312 | 37 | UI | 6 | PAY-01 | PAY-01.03 | Doctor profile fee tab + later public doctor card | New | Web SPA | Doctor profile + Public + Admin | Web, UI, QA
313 | 90 | QA | 6 | PAY-01 | PAY-01.04 | QA: changing fee does not alter already-created unpaid orders without a rule (document the rule) | Regression | QA | Doctor profile + Public + Admin | Web, UI, QA
314 | 186 | Web | 6 | PAY-02 | PAY-02.01 | DB: PaymentOrder, PaymentEvent (raw webhook), idempotency key on payment_id | New | Database | Shared | Web, QA
315 | 187 | Web | 6 | PAY-02 | PAY-02.02 | Port Order/GenerateOrderId pattern to .NET 8; move keys to configuration; do not commit secrets | New Integration | API | Shared | Web, QA
316 | 188 | Web | 6 | PAY-02 | PAY-02.03 | Webhook handler payment.captured / payment.failed; signature verify; never trust client-only success | New Integration | API | Shared | Web, QA
317 | 91 | QA | 6 | PAY-02 | PAY-02.04 | QA: duplicate webhook; delayed webhook; failed capture; app closed mid-checkout | Regression | QA | Shared | Web, QA
318 | 189 | Web | 6 | PAY-03 | PAY-03.01 | DB: ConsultPayment linked to PaymentOrder + PatientAppId — NOT PackageEntryDetail | New | Database | Public web + later Patient app | Web, UI, QA
319 | 190 | Web | 6 | PAY-03 | PAY-03.02 | API: CreateConsultOrder, Verify (optional), status by appointment; amount from ConsultFeeConfig | New | API | Public web + later Patient app | Web, UI, QA
320 | 38 | UI | 6 | PAY-03 | PAY-03.03 | Public /book/pay/:bookingId using Razorpay pattern from Widgets.js but consult order API | New | Web SPA | Public web + later Patient app | Web, UI, QA
321 | 191 | Web | 6 | PAY-03 | PAY-03.04 | Razorpay Checkout methods: card, UPI, netbanking, wallet as enabled on the account | New Integration | Integration | Public web + later Patient app | Web, UI, QA
322 | 92 | QA | 6 | PAY-03 | PAY-03.05 | QA: success, failure, pending, double-click create order idempotent | Regression | QA | Public web + later Patient app | Web, UI, QA
323 | 192 | Web | 6 | PAY-04 | PAY-04.01 | Reuse PaymentOrder + ConsultPayment with Method=CASH/UPI_OFFLINE/CARD_POS/PAY_LINK | New | Database | Reception Portal | Web, UI, QA
324 | 193 | Web | 6 | PAY-04 | PAY-04.02 | API: CollectAtReception; generate pay-link; print receipt payload | New | API | Reception Portal | Web, UI, QA
325 | 39 | UI | 6 | PAY-04 | PAY-04.03 | Reception collect modal: amount, method, GST placeholder, print receipt | New | Web SPA | Reception Portal | Web, UI, QA
326 | 194 | Web | 6 | PAY-04 | PAY-04.04 | Pay-link SMS/WhatsApp optional (Phase 12); must still ledger if notify fails | New Integration | Integration | Reception Portal | Web, UI, QA
327 | 93 | QA | 6 | PAY-04 | PAY-04.05 | QA: cash collection visible in clinic collection view after Phase 7; cannot mark PAID without this API | Regression | QA | Reception Portal | Web, UI, QA
328 | 195 | Web | 6 | PAY-05 | PAY-05.01 | Honor PayAtClinicEnabled on public create-booking and checkout | New | API | Public + Doctor + Reception | Web, UI, QA
329 | 40 | UI | 6 | PAY-05 | PAY-05.02 | UI: public booking shows Pay at clinic vs Pay now; doctor list badge | New | Web SPA | Public + Doctor + Reception | Web, UI, QA
330 | 94 | QA | 6 | PAY-05 | PAY-05.03 | QA: doctor flag off → pay-at-clinic hidden; reception can still collect | Regression | QA | Public + Doctor + Reception | Web, UI, QA
331 | 196 | Web | 6 | PAY-06 | PAY-06.01 | Reuse PAY-02 webhook for S1 orders; link PackageEntryDetail as S1 only | Existing Improvement | API | Doctor Web Portal | Web, UI, QA
332 | 41 | UI | 6 | PAY-06 | PAY-06.02 | Widgets.js: handle failed pay; show invoice when Phase 7 invoice exists | Existing Improvement | Web SPA | Doctor Web Portal | Web, UI, QA
333 | 95 | QA | 6 | PAY-06 | PAY-06.03 | QA: renew, fail, webhook delay, last-5-days warning still works | Regression | QA | Doctor Web Portal | Web, UI, QA
334 | 197 | Web | 6 | PAY-07 | PAY-07.01 | Extend PaymentOrder with Stream=CONSULT¦SUBSCRIPTION¦MEDICINE so Phase 14 can attach without schema rewrite | New | Database | Shared | Web, QA
335 | 198 | Web | 6 | PAY-07 | PAY-07.02 | API stub: CreateMedicineOrder payment + COD status enum — implemented fully in Phase 14 | New | API | Shared | Web, QA
336 | 96 | QA | 6 | PAY-07 | PAY-07.03 | QA: stream isolation query (consult vs medicine totals differ) | Regression | QA | Shared | Web, QA
337 | 199 | Web | 6 | PAY-08 | PAY-08.01 | Single source: PaymentOrder/ConsultPayment → Appointment.PaymentStatus updated only by webhook or CollectAtReception | New | API | All | Web, UI, QA
338 | 42 | UI | 6 | PAY-08 | PAY-08.02 | Surface badges: doctor, reception; public confirmation page; patient app in Phase 16 consumes same API | New | Web SPA | All | Web, UI, QA
339 | 97 | QA | 6 | PAY-08 | PAY-08.03 | QA: three roles, one appointment, same enum value | Regression | QA | All | Web, UI, QA
340 | 200 | Web | 6 | PAY-09 | PAY-09.01 | DB: Refund (PaymentOrderId, Amount, Reason, Status, GatewayRefundId, ByUserId, At) | New | Database | Account + Patient | Web, UI, QA
341 | 201 | Web | 6 | PAY-09 | PAY-09.02 | API: create refund (Account); webhook refund.processed; cancel-appointment policy engine (full/partial/none) | New | API | Account + Patient | Web, UI, QA
342 | 43 | UI | 6 | PAY-09 | PAY-09.03 | Account refund screen in Phase 7; patient payments list in Phase 16 | New | Web SPA | Account + Patient | Web, UI, QA
343 | 202 | Web | 6 | PAY-09 | PAY-09.04 | Razorpay refund API + webhook | New Integration | Integration | Account + Patient | Web, UI, QA
344 | 98 | QA | 6 | PAY-09 | PAY-09.05 | QA: double refund blocked; cash collection refund is ledger-only per PRE-02 policy | Regression | QA | Account + Patient | Web, UI, QA
345 | 203 | Web | 6 | PAY-10 | PAY-10.01 | DB: Invoice (Number, Series, Stream, PaymentOrderId, GstBreakup, PdfPath) | New | Database | All | Web, UI, QA
346 | 204 | Web | 6 | PAY-10 | PAY-10.02 | API: get invoice by payment; generate PDF via SecureDocument | New | API | All | Web, UI, QA
347 | 44 | UI | 6 | PAY-10 | PAY-10.03 | Print/download on reception, doctor (subscription), later patient app | New | Web SPA | All | Web, UI, QA
348 | 99 | QA | 6 | PAY-10 | PAY-10.04 | QA: unique invoice numbers; cancelled invoice not reused | Regression | QA | All | Web, UI, QA
349 | 205 | Web | 6 | PAY-11 | PAY-11.01 | Persist raw webhook JSON; correlation id on Appointment and Ledger | New | Database | Account | Web, QA
350 | 206 | Web | 6 | PAY-11 | PAY-11.02 | Account query API: trail by appointment / payment / doctor (Phase 7 UI) | New | API | Account | Web, QA
351 | 100 | QA | 6 | PAY-11 | PAY-11.03 | QA: missing webhook still shows PENDING not PAID | Regression | QA | Account | Web, QA
352 | 207 | Web | 7 | FIN-01 | FIN-01.01 | DB: LedgerEntry (Stream, Direction, Amount, Gst, Commission, EntityType, EntityId, PaymentOrderId, At) immutable | New | Database | Account Portal | Web, UI, QA
353 | 208 | Web | 7 | FIN-01 | FIN-01.02 | API: GET /account/ledger filters; export; write-only from payment/settlement services | New | API | Account Portal | Web, UI, QA
354 | 45 | UI | 7 | FIN-01 | FIN-01.03 | /account/ledger UI — Account layout sidebar Finance | New | Web SPA | Account Portal | Web, UI, QA
355 | 101 | QA | 7 | FIN-01 | FIN-01.04 | QA: consult pay writes S2; subscription writes S1; they never share one row | Regression | QA | Account Portal | Web, UI, QA
356 | 209 | Web | 7 | FIN-02 | FIN-02.01 | Reuse ConsultPayment + Appointment; reconciliation query | New | Database | Account + Admin | Web, UI, QA
357 | 210 | Web | 7 | FIN-02 | FIN-02.02 | GET Admin/Account reconciliation + aggregates | New | API | Account + Admin | Web, UI, QA
358 | 46 | UI | 7 | FIN-02 | FIN-02.03 | /account/consult-recon and /admin/consult-payments (same data, Account owns, Admin views) | New | Web SPA | Account + Admin | Web, UI, QA
359 | 102 | QA | 7 | FIN-02 | FIN-02.04 | QA: unmatched payment appears in exception queue not silent | Regression | QA | Account + Admin | Web, UI, QA
360 | 211 | Web | 7 | FIN-03 | FIN-03.01 | LedgerEntry stream MEDICINE with SplitSeller/SplitPlatform/SplitDelivery | New | Database | Account Portal | Web, UI, QA
361 | 212 | Web | 7 | FIN-03 | FIN-03.02 | GET /account/medicine-ledger | New | API | Account Portal | Web, UI, QA
362 | 47 | UI | 7 | FIN-03 | FIN-03.03 | /account/medicine-ledger UI (empty until HomeoMeds orders exist — still ship the screen) | New | Web SPA | Account Portal | Web, UI, QA
363 | 103 | QA | 7 | FIN-03 | FIN-03.04 | QA: S2 consult row never appears on this screen | Regression | QA | Account Portal | Web, UI, QA
364 | 213 | Web | 7 | FIN-04 | FIN-04.01 | DB: SettlementRun, SettlementLine | New | Database | Account Portal | Web, UI, QA
365 | 214 | Web | 7 | FIN-04 | FIN-04.02 | API: create run (dry-run + commit); list; detail | New | API | Account Portal | Web, UI, QA
366 | 48 | UI | 7 | FIN-04 | FIN-04.03 | /account/settlements | New | Web SPA | Account Portal | Web, UI, QA
367 | 104 | QA | 7 | FIN-04 | FIN-04.04 | QA: hold days exclude too-new captures; refunds net out | Regression | QA | Account Portal | Web, UI, QA
368 | 215 | Web | 7 | FIN-05 | FIN-05.01 | DB: Payout (PayeeType Doctor¦Pharmacy, Amount, Status, SettlementRunId) | New | Database | Account Portal | Web, UI, QA
369 | 216 | Web | 7 | FIN-05 | FIN-05.02 | API: ApprovePayout with OTP; reject | New | API | Account Portal | Web, UI, QA
370 | 49 | UI | 7 | FIN-05 | FIN-05.03 | /account/payouts | New | Web SPA | Account Portal | Web, UI, QA
371 | 217 | Web | 7 | FIN-05 | FIN-05.04 | Bank file / Razorpay payout adapter per PRE-01 | New Integration | Integration | Account Portal | Web, UI, QA
372 | 105 | QA | 7 | FIN-05 | FIN-05.05 | QA: Account role only; replay OTP; Admin 403 on approve | Regression | QA | Account Portal | Web, UI, QA
373 | 50 | UI | 7 | FIN-06 | FIN-06.01 | UI /account/refunds: original payment, amount, reason, status | New | Web SPA | Account Portal | Web, UI, QA
374 | 218 | Web | 7 | FIN-06 | FIN-06.02 | Ledger reverse entries on successful refund | New | API | Account Portal | Web, UI, QA
375 | 106 | QA | 7 | FIN-06 | FIN-06.03 | QA: partial refund; full refund; cash-policy path | Regression | QA | Account Portal | Web, UI, QA
376 | 219 | Web | 7 | FIN-07 | FIN-07.01 | DB: PaymentException state machine | New | Database | Account + Admin | Web, UI, QA
377 | 220 | Web | 7 | FIN-07 | FIN-07.02 | API: list/detail/retry/resolve; created by webhook mismatches | New | API | Account + Admin | Web, UI, QA
378 | 51 | UI | 7 | FIN-07 | FIN-07.03 | /account/exceptions and /admin/payment-exceptions (same queue) | New | Web SPA | Account + Admin | Web, UI, QA
379 | 107 | QA | 7 | FIN-07 | FIN-07.04 | QA: failed webhook creates exception; manual resolve requires Account role + OTP | Regression | QA | Account + Admin | Web, UI, QA
380 | 221 | Web | 7 | FIN-08 | FIN-08.01 | Reuse Invoice; tax config table (GstRate, treatment flags) | New | Database | Account Portal | Web, UI, QA
381 | 222 | Web | 7 | FIN-08 | FIN-08.02 | GET tax report + CSV | New | API | Account Portal | Web, UI, QA
382 | 52 | UI | 7 | FIN-08 | FIN-08.03 | /account/tax | New | Web SPA | Account Portal | Web, UI, QA
383 | 108 | QA | 7 | FIN-08 | FIN-08.04 | QA: rates come from config; changing rate does not rewrite old invoices | Regression | QA | Account Portal | Web, UI, QA
384 | 223 | Web | 7 | FIN-09 | FIN-09.01 | DB: Payee (DoctorId/PharmacyId, Bank, PAN, KYC status) | New | Database | Account Portal | Web, UI, QA
385 | 224 | Web | 7 | FIN-09 | FIN-09.02 | API: list/update; OTP on bank change | New | API | Account Portal | Web, UI, QA
386 | 53 | UI | 7 | FIN-09 | FIN-09.03 | /account/payees | New | Web SPA | Account Portal | Web, UI, QA
387 | 109 | QA | 7 | FIN-09 | FIN-09.04 | QA: missing KYC blocks FIN-05 | Regression | QA | Account Portal | Web, UI, QA
388 | 225 | Web | 7 | FIN-10 | FIN-10.01 | Query ConsultPayment Method in CASH/UPI_OFFLINE grouped by DoctorId/date | New | Database | Account Portal | Web, UI, QA
389 | 226 | Web | 7 | FIN-10 | FIN-10.02 | GET clinic-collections | New | API | Account Portal | Web, UI, QA
390 | 54 | UI | 7 | FIN-10 | FIN-10.03 | /account/clinic-collections | New | Web SPA | Account Portal | Web, UI, QA
391 | 110 | QA | 7 | FIN-10 | FIN-10.04 | QA: online Razorpay consults do not appear as clinic cash | Regression | QA | Account Portal | Web, UI, QA
392 | 227 | Web | 7 | FIN-11 | FIN-11.01 | Seed Account role menus: ledger, recon, medicine ledger, exceptions, settlements, payouts, refunds, tax, payees, clinic collections | New | Configuration | Admin + Account | Web, QA
393 | 111 | QA | 7 | FIN-11 | FIN-11.02 | Negative tests: Admin POST ApprovePayout → 403; Account POST repertory section → 403 | Regression | QA | Admin + Account | Web, QA
394 | 228 | Web | 8 | TRU-01 | TRU-01.01 | DB: DoctorVerification (Pending/Approved/Rejected/NeedsInfo), DoctorCredentialDocument | New | Database | Doctor Web + Admin | Web, UI, QA
395 | 229 | Web | 8 | TRU-01 | TRU-01.02 | API: upload documents; MyStatus; RegisterDoctor modified to VerificationStatus=Pending (not auto-practice) | New | API | Doctor Web + Admin | Web, UI, QA
396 | 55 | UI | 8 | TRU-01 | TRU-01.03 | Doctor profile credentials tab + document upload | New | Web SPA | Doctor Web + Admin | Web, UI, QA
397 | 112 | QA | 8 | TRU-01 | TRU-01.04 | QA: doctor without docs cannot appear in public directory (Phase 9) | Regression | QA | Doctor Web + Admin | Web, UI, QA
398 | 230 | Web | 8 | TRU-02 | TRU-02.01 | Reuse DoctorVerification | New | Database | Admin Portal | Web, UI, QA
399 | 231 | Web | 8 | TRU-02 | TRU-02.02 | API: Queue, {id}, Approve, Reject, RequestInfo | New | API | Admin Portal | Web, UI, QA
400 | 56 | UI | 8 | TRU-02 | TRU-02.03 | /admin/doctor-credentialing and /:doctorId; verification column on users list | New | Web SPA | Admin Portal | Web, UI, QA
401 | 232 | Web | 8 | TRU-02 | TRU-02.04 | Email notify (Phase 12 SMTP already used for activation) | New Integration | Integration | Admin Portal | Web, UI, QA
402 | 113 | QA | 8 | TRU-02 | TRU-02.05 | QA: reject reason required; request-info reopens Pending | Regression | QA | Admin Portal | Web, UI, QA
403 | 233 | Web | 8 | TRU-03 | TRU-03.01 | Public doctor DTO includes isVerified | New | API | Public + Patient app | Web, UI, QA
404 | 57 | UI | 8 | TRU-03 | TRU-03.02 | Badge component for website (Phase 9) and patient app (Phase 16) | New | Web SPA | Public + Patient app | Web, UI, QA
405 | 114 | QA | 8 | TRU-03 | TRU-03.03 | QA: pending doctor has no badge | Regression | QA | Public + Patient app | Web, UI, QA
406 | 234 | Web | 8 | TRU-04 | TRU-04.01 | Public doctor list filter VerificationStatus=Approved | New | API | Public + Payments | Web, QA
407 | 235 | Web | 8 | TRU-04 | TRU-04.02 | CreateConsultOrder rejects unverified doctor for patient-originated bookings | New | API | Public + Payments | Web, QA
408 | 115 | QA | 8 | TRU-04 | TRU-04.03 | QA: reception can still book own clinic patient for unverified doctor if PRE-03 allows | Regression | QA | Public + Payments | Web, QA
409 | 236 | Web | 8 | TRU-05 | TRU-05.01 | DB: Review (PatientAppId, Rating, Text, Status, At) | New | Database | Patient + Public | Web, UI, QA
410 | 237 | Web | 8 | TRU-05 | TRU-05.02 | API: create (patient), list by doctor (public approved), doctor list own | New | API | Patient + Public | Web, UI, QA
411 | 58 | UI | 8 | TRU-05 | TRU-05.03 | Public doctor profile reviews; patient app write flow Phase 16 | New | Web SPA | Patient + Public | Web, UI, QA
412 | 116 | QA | 8 | TRU-05 | TRU-05.04 | QA: duplicate review blocked; incomplete visit blocked | Regression | QA | Patient + Public | Web, UI, QA
413 | 238 | Web | 8 | TRU-06 | TRU-06.01 | DB: ReviewAppeal | New | Database | Doctor + Patient + Admin | Web, UI, QA
414 | 239 | Web | 8 | TRU-06 | TRU-06.02 | API: doctor appeal; patient list/mine; admin resolve | New | API | Doctor + Patient + Admin | Web, UI, QA
415 | 59 | UI | 8 | TRU-06 | TRU-06.03 | Doctor dashboard my-reviews; admin queue | New | Web SPA | Doctor + Patient + Admin | Web, UI, QA
416 | 117 | QA | 8 | TRU-06 | TRU-06.04 | QA: only treating doctor of that visit can appeal | Regression | QA | Doctor + Patient + Admin | Web, UI, QA
417 | 240 | Web | 8 | TRU-07 | TRU-07.01 | Ranking config (weights) — not a black box hardcoded sort | New | Database | Public + Patient app | Web, UI, QA
418 | 241 | Web | 8 | TRU-07 | TRU-07.02 | GET doctors + GET ranking-explain/{doctorId} | New | API | Public + Patient app | Web, UI, QA
419 | 60 | UI | 8 | TRU-07 | TRU-07.03 | Search results: Why this order? panel | New | Web SPA | Public + Patient app | Web, UI, QA
420 | 118 | QA | 8 | TRU-07 | TRU-07.04 | QA: changing weights changes order and explanation together | Regression | QA | Public + Patient app | Web, UI, QA
421 | 242 | Web | 9 | WEB-01 | WEB-01.01 | No schema | Existing Improvement | Database | Patient Website | Web, UI, QA
422 | 243 | Web | 9 | WEB-01 | WEB-01.02 | Reuse public doctor/fee APIs when live | Existing Improvement | API | Patient Website | Web, UI, QA
423 | 61 | UI | 9 | WEB-01 | WEB-01.03 | HomeLandingPage: book, verified doctors, pricing teaser, store badges; strip leftover job-board feel | Existing Improvement | Web SPA | Patient Website | Web, UI, QA
424 | 119 | QA | 9 | WEB-01 | WEB-01.04 | QA: mobile viewport; deep link /book | Regression | QA | Patient Website | Web, UI, QA
425 | 62 | UI | 9 | WEB-02 | WEB-02.01 | Public doctor card shows in-clinic and tele fee | Existing Improvement | Web SPA | Patient Website | UI, QA
426 | 63 | UI | 9 | WEB-02 | WEB-02.02 | /pricing remains SaaS packages for doctors; label it clearly vs patient consult fees | Existing Improvement | Web SPA | Patient Website | UI, QA
427 | 120 | QA | 9 | WEB-02 | WEB-02.03 | QA: fee matches checkout amount | Regression | QA | Patient Website | UI, QA
428 | 244 | Web | 9 | WEB-03 | WEB-03.01 | Public doctor search indexes (from Doctor + verification + fee + schedule) | New | Database | Patient Website | Web, UI, QA
429 | 245 | Web | 9 | WEB-03 | WEB-03.02 | GET /api/Public/Doctors + filters + profile | New | API | Patient Website | Web, UI, QA
430 | 64 | UI | 9 | WEB-03 | WEB-03.03 | /book list + filters + doctor profile page | New | Web SPA | Patient Website | Web, UI, QA
431 | 121 | QA | 9 | WEB-03 | WEB-03.04 | QA: unverified excluded; filters combine; empty state | Regression | QA | Patient Website | Web, UI, QA
432 | 246 | Web | 9 | WEB-04 | WEB-04.01 | Reuse Patient + Appointment; BookingToken; PatientAuth OTP | New | Database | Patient Website | Web, UI, QA
433 | 247 | Web | 9 | WEB-04 | WEB-04.02 | Public: Doctors/{id}/Slots, Create, {bookingToken}; POST PatientAuth RequestOtp/VerifyOtp | New | API | Patient Website | Web, UI, QA
434 | 65 | UI | 9 | WEB-04 | WEB-04.03 | /book/:doctorId/slots; /book/confirm; booking success | New | Web SPA | Patient Website | Web, UI, QA
435 | 122 | QA | 9 | WEB-04 | WEB-04.04 | QA: double-book same slot; hold expiry; OTP fail; consent required | Regression | QA | Patient Website | Web, UI, QA
436 | 66 | UI | 9 | WEB-05 | WEB-05.01 | /book/pay/:bookingId + success/failure pages | New | Web SPA | Patient Website | UI, QA
437 | 123 | QA | 9 | WEB-05 | WEB-05.02 | QA: pay-at-clinic skip checkout; failed pay remains PENDING not PAID | Regression | QA | Patient Website | UI, QA
438 | 248 | Web | 9 | WEB-06 | WEB-06.01 | Reuse EnquiryDetail; add Status/AssignedTo if missing | Existing Improvement | Database | Patient Website + Admin | Web, UI, QA
439 | 249 | Web | 9 | WEB-06 | WEB-06.02 | Existing enquiry POST; admin list API if missing | Existing Improvement | API | Patient Website + Admin | Web, UI, QA
440 | 67 | UI | 9 | WEB-06 | WEB-06.03 | /contact confirmation; /admin/enquiries inbox (not Velzon mailbox) | Existing Improvement | Web SPA | Patient Website + Admin | Web, UI, QA
441 | 124 | QA | 9 | WEB-06 | WEB-06.04 | QA: guest submit → admin sees row | Regression | QA | Patient Website + Admin | Web, UI, QA
442 | 68 | UI | 9 | WEB-07 | WEB-07.01 | Replace /privacy content with signed legal copy; store PolicyVersion | Existing Improvement | Web SPA | Patient Website | UI, QA
443 | 125 | QA | 9 | WEB-07 | WEB-07.02 | QA: booking consent shows policy version number | Regression | QA | Patient Website | UI, QA
444 | 69 | UI | 9 | WEB-08 | WEB-08.01 | Replace /terms with signed copy; version stamp on booking/payment | Existing Improvement | Web SPA | Patient Website | UI, QA
445 | 126 | QA | 9 | WEB-08 | WEB-08.02 | QA: terms checkbox required on confirm | Regression | QA | Patient Website | UI, QA
446 | 250 | Web | 9 | WEB-09 | WEB-09.01 | Documents via TRU-01 tables | Existing Improvement | Database | Public | Web, UI, QA
447 | 251 | Web | 9 | WEB-09 | WEB-09.02 | RegisterDoctor sets Pending; does not auto-activate practice for directory | Existing Improvement | API | Public | Web, UI, QA
448 | 70 | UI | 9 | WEB-09 | WEB-09.03 | /register multipart docs; pending message; status page | Existing Improvement | Web SPA | Public | Web, UI, QA
449 | 127 | QA | 9 | WEB-09 | WEB-09.04 | QA: register → admin queue row | Regression | QA | Public | Web, UI, QA
450 | 252 | Web | 9 | WEB-10 | WEB-10.01 | Activation token TTL if missing | Existing Improvement | Database | Public | Web, UI, QA
451 | 253 | Web | 9 | WEB-10 | WEB-10.02 | Resend activation; do not treat activation as TRU-04 gate | Existing Improvement | API | Public | Web, UI, QA
452 | 71 | UI | 9 | WEB-10 | WEB-10.03 | Login activation query param UX + expiry copy | Existing Improvement | Web SPA | Public | Web, UI, QA
453 | 128 | QA | 9 | WEB-10 | WEB-10.04 | QA: used link, expired link, resend | Regression | QA | Public | Web, UI, QA
454 | 254 | Web | 9 | WEB-11 | WEB-11.01 | DB: BookingWaitlist | New | Database | Patient Website + App | Web, UI, QA
455 | 255 | Web | 9 | WEB-11 | WEB-11.02 | API: join waitlist; worker on CancelAppointment | New | API | Patient Website + App | Web, UI, QA
456 | 72 | UI | 9 | WEB-11 | WEB-11.03 | Public waitlist CTA on full days | New | Web SPA | Patient Website + App | Web, UI, QA
457 | 256 | Web | 9 | WEB-11 | WEB-11.04 | Notify SMS/push when Phase 12 exists | New Integration | Integration | Patient Website + App | Web, UI, QA
458 | 129 | QA | 9 | WEB-11 | WEB-11.05 | QA: two waiters; first gets offer; expiry releases to second | Regression | QA | Patient Website + App | Web, UI, QA
459 | 73 | UI | 9 | WEB-12 | WEB-12.01 | Public articles list/detail from existing blog/news APIs | Existing Improvement | Web SPA | Patient Website + App | UI, QA
460 | 130 | QA | 9 | WEB-12 | WEB-12.02 | QA: unpublished hidden | Regression | QA | Patient Website + App | UI, QA
461 | 257 | Web | 10 | ERX-01 | ERX-01.01 | DB: PotencyMaster; PrescriptionRemedyDetail.PotencyId | New | Database | Doctor Web + Admin | Web, UI, QA
462 | 258 | Web | 10 | ERX-01 | ERX-01.02 | API: potency DDL; extend SavePrescriptionDetail | New | API | Doctor Web + Admin | Web, UI, QA
463 | 74 | UI | 10 | ERX-01 | ERX-01.03 | Rx modal potency picker (6C, 30C, 200C, 1M…) | New | Web SPA | Doctor Web + Admin | Web, UI, QA
464 | 131 | QA | 10 | ERX-01 | ERX-01.04 | QA: free text potency rejected | Regression | QA | Doctor Web + Admin | Web, UI, QA
465 | 259 | Web | 10 | ERX-02 | ERX-02.01 | DB: Frequency, Duration, Instructions on remedy line | New | Database | Doctor Web Portal | Web, UI, QA
466 | 260 | Web | 10 | ERX-02 | ERX-02.02 | Extend save/get Rx APIs | New | API | Doctor Web Portal | Web, UI, QA
467 | 75 | UI | 10 | ERX-02 | ERX-02.03 | Rx row UI for the three fields | New | Web SPA | Doctor Web Portal | Web, UI, QA
468 | 132 | QA | 10 | ERX-02 | ERX-02.04 | QA: all three persist and print | Regression | QA | Doctor Web Portal | Web, UI, QA
469 | 261 | Web | 10 | ERX-03 | ERX-03.01 | Extend AppointmentHistoryNote with NoteType, IsErxExcluded | New | Database | Doctor Web Portal | Web, UI, QA
470 | 262 | Web | 10 | ERX-03 | ERX-03.02 | GET /api/Erx/ByAppointment/{id} returns snapshot without notes | New | API | Doctor Web Portal | Web, UI, QA
471 | 76 | UI | 10 | ERX-03 | ERX-03.03 | Move History Notes out of Rx modal; note types Chief complaint / Follow-up / General | New | Web SPA | Doctor Web Portal | Web, UI, QA
472 | 133 | QA | 10 | ERX-03 | ERX-03.04 | QA: print eRx vs export case PDF (doctor copy still has notes) | Regression | QA | Doctor Web Portal | Web, UI, QA
473 | 263 | Web | 10 | ERX-04 | ERX-04.01 | DB: ErxSnapshot, ErxSnapshotItem (codes+names stored; patient API returns codes until pharmacy accept) | New | Database | Doctor Web | Web, UI, QA
474 | 264 | Web | 10 | ERX-04 | ERX-04.02 | API: SignErx; GetErx; reject mutate of signed snapshot | New | API | Doctor Web | Web, UI, QA
475 | 77 | UI | 10 | ERX-04 | ERX-04.03 | Sign button; locked badge on board header | New | Web SPA | Doctor Web | Web, UI, QA
476 | 134 | QA | 10 | ERX-04 | ERX-04.04 | QA: POST save after sign does not change snapshot | Regression | QA | Doctor Web | Web, UI, QA
477 | 265 | Web | 10 | ERX-05 | ERX-05.01 | GET history by patient; by appointment | New | API | Doctor + Patient | Web, UI, QA
478 | 78 | UI | 10 | ERX-05 | ERX-05.02 | Doctor history panel lists signed eRx; patient timeline in Phase 16 | New | Web SPA | Doctor + Patient | Web, UI, QA
479 | 135 | QA | 10 | ERX-05 | ERX-05.03 | QA: another doctor 403 | Regression | QA | Doctor + Patient | Web, UI, QA
480 | 266 | Web | 10 | ERX-06 | ERX-06.01 | Patient-authorised GET Erx; apply code protection ERX-08 | New | API | Patient App + Website | Web, UI, QA
481 | 79 | UI | 10 | ERX-06 | ERX-06.02 | Web confirmation/records page can show the same payload before the app exists | New | Web SPA | Patient App + Website | Web, UI, QA
482 | 136 | QA | 10 | ERX-06 | ERX-06.03 | QA: doctor names vs patient codes differ until pharmacy OTP accept | Regression | QA | Patient App + Website | Web, UI, QA
483 | 267 | Web | 10 | ERX-07 | ERX-07.01 | PDF renderer from ErxSnapshot; store via SEC-09 | New | API | Doctor + Patient | Web, UI, QA
484 | 80 | UI | 10 | ERX-07 | ERX-07.02 | Print/Download on doctor board and later patient app | New | Web SPA | Doctor + Patient | Web, UI, QA
485 | 137 | QA | 10 | ERX-07 | ERX-07.03 | QA: notes leak test on patient PDF | Regression | QA | Doctor + Patient | Web, UI, QA
486 | 268 | Web | 10 | ERX-08 | ERX-08.01 | Assign stable remedy codes on snapshot items | New | API | Patient | Web, QA
487 | 138 | QA | 10 | ERX-08 | ERX-08.02 | Patient serializer tests (contract tests) | Regression | QA | Patient | Web, QA
488 | 269 | Web | 10 | ERX-09 | ERX-09.01 | API contract: AcceptOrder(OTP) → reveal names; Quote → PayQR | New | API | Patient + Pharmacy | Web
489 | 270 | Web | 10 | ERX-09 | ERX-09.02 | Implement fully with MED-* in Phase 14 — do not reveal names from doctor sign alone | New | Architecture | Patient + Pharmacy | Web
490 | 271 | Web | 10 | ERX-10 | ERX-10.01 | DB: RefillRequest | New | Database | Patient + Doctor mobile + Doctor web | Web, UI, QA
491 | 272 | Web | 10 | ERX-10 | ERX-10.02 | API: patient request; doctor inbox; approve/reject | New | API | Patient + Doctor mobile + Doctor web | Web, UI, QA
492 | 81 | UI | 10 | ERX-10 | ERX-10.03 | Doctor web inbox; doctor app in Phase 17; patient app in Phase 16 | New | Web SPA | Patient + Doctor mobile + Doctor web | Web, UI, QA
493 | 139 | QA | 10 | ERX-10 | ERX-10.04 | QA: cannot refill unsigned/locked-expired per policy | Regression | QA | Patient + Doctor mobile + Doctor web | Web, UI, QA
494 | 273 | Web | 10 | ERX-11 | ERX-11.01 | Copy lab orders into ErxSnapshot on sign | Existing Improvement | API | Doctor Web | Web, QA
495 | 140 | QA | 10 | ERX-11 | ERX-11.02 | QA: labs visible on eRx; result values not required on patient copy | Regression | QA | Doctor Web | Web, QA
496 | 274 | Web | 11 | TEL-01 | TEL-01.01 | DB: TeleAvailability (Online/Offline, LastHeartbeat) | New | Database | Doctor Web + Doctor App | Web, UI, QA
497 | 275 | Web | 11 | TEL-01 | TEL-01.02 | API: SET/GET availability; public GET by doctorId | New | API | Doctor Web + Doctor App | Web, UI, QA
498 | 82 | UI | 11 | TEL-01 | TEL-01.03 | Dashboard toggle Online for teleconsult | New | Web SPA | Doctor Web + Doctor App | Web, UI, QA
499 | 141 | QA | 11 | TEL-01 | TEL-01.04 | QA: heartbeat expiry sets offline | Regression | QA | Doctor Web + Doctor App | Web, UI, QA
500 | 276 | Web | 11 | TEL-02 | TEL-02.01 | Queue query on E-CONSULT + PaymentStatus + join time | New | Database | Doctor Web + App | Web, UI, QA
501 | 277 | Web | 11 | TEL-02 | TEL-02.02 | GET Tele/Queue; POST start session | New | API | Doctor Web + App | Web, UI, QA
502 | 83 | UI | 11 | TEL-02 | TEL-02.03 | Dedicated Tele queue on dashboard (beyond E-CONSULT list) | New | Web SPA | Doctor Web + App | Web, UI, QA
503 | 278 | Web | 11 | TEL-02 | TEL-02.04 | SignalR/poll | New Integration | Integration | Doctor Web + App | Web, UI, QA
504 | 142 | QA | 11 | TEL-02 | TEL-02.05 | QA: wait time increases; paid badge matches PAY-08 | Regression | QA | Doctor Web + App | Web, UI, QA
505 | 279 | Web | 11 | TEL-03 | TEL-03.01 | DB: TeleSession (PatientAppId, RoomId, Status) | New | Database | Doctor Web Portal | Web, UI, QA
506 | 280 | Web | 11 | TEL-03 | TEL-03.02 | API: create/end session; vendor tokens | New | API | Doctor Web Portal | Web, UI, QA
507 | 84 | UI | 11 | TEL-03 | TEL-03.03 | Full-page video room mute/end | New | Web SPA | Doctor Web Portal | Web, UI, QA
508 | 281 | Web | 11 | TEL-03 | TEL-03.04 | Video SDK (Agora/Twilio/Daily) | New Integration | Integration | Doctor Web Portal | Web, UI, QA
509 | 143 | QA | 11 | TEL-03 | TEL-03.05 | QA: replace WhatsApp alert; session ends write timestamp | Regression | QA | Doctor Web Portal | Web, UI, QA
510 | 282 | Web | 11 | TEL-04 | TEL-04.01 | Token API must be client-agnostic (web and mobile) | New | API | Patient App + Doctor App | Web, QA
511 | 144 | QA | 11 | TEL-04 | TEL-04.02 | Contract tests: token TTL, room id = session id | Regression | QA | Patient App + Doctor App | Web, QA
512 | 85 | UI | 11 | TEL-05 | TEL-05.01 | Shared device-check component (web); mobile equivalent in Phase 16 | New | Web SPA | Doctor Web + Patient | UI, QA
513 | 145 | QA | 11 | TEL-05 | TEL-05.02 | QA: deny camera permission → clear guidance | Regression | QA | Doctor Web + Patient | UI, QA
514 | 283 | Web | 11 | TEL-06 | TEL-06.01 | Session status events | New | Database | Patient | Web, UI, QA
515 | 284 | Web | 11 | TEL-06 | TEL-06.02 | GET session status for patient token | New | API | Patient | Web, UI, QA
516 | 86 | UI | 11 | TEL-06 | TEL-06.03 | Waiting room UI on web (and app later) | New | Web SPA | Patient | Web, UI, QA
517 | 146 | QA | 11 | TEL-06 | TEL-06.04 | QA: doctor join transitions patient into the call | Regression | QA | Patient | Web, UI, QA
518 | 285 | Web | 11 | TEL-07 | TEL-07.01 | Write ConsentRecord TeleRecording; TeleConsentLog events | New | Database | Patient + Doctor | Web, UI, QA
519 | 286 | Web | 11 | TEL-07 | TEL-07.02 | API: capture consent; session.recordAllowed | New | API | Patient + Doctor | Web, UI, QA
520 | 87 | UI | 11 | TEL-07 | TEL-07.03 | Pre-join modal both sides | New | Web SPA | Patient + Doctor | Web, UI, QA
521 | 147 | QA | 11 | TEL-07 | TEL-07.04 | QA: decline → no record; audit row still written | Regression | QA | Patient + Doctor | Web, UI, QA
522 | 287 | Web | 11 | TEL-08 | TEL-08.01 | API: Rejoin issues token if Status=Active | New | API | Doctor + Patient | Web, UI, QA
523 | 88 | UI | 11 | TEL-08 | TEL-08.02 | UI Rejoin on doctor dashboard and patient waiting/call fail | New | Web SPA | Doctor + Patient | Web, UI, QA
524 | 148 | QA | 11 | TEL-08 | TEL-08.03 | QA: after End, rejoin 409 | Regression | QA | Doctor + Patient | Web, UI, QA
525 | 288 | Web | 11 | TEL-09 | TEL-09.01 | Standardise join error codes; log TeleSessionEvent | New | API | Doctor + Patient | Web, UI, QA
526 | 89 | UI | 11 | TEL-09 | TEL-09.02 | Fallback UI: retry, rejoin, contact support | New | Web SPA | Doctor + Patient | Web, UI, QA
527 | 149 | QA | 11 | TEL-09 | TEL-09.03 | QA: simulated token fail | Regression | QA | Doctor + Patient | Web, UI, QA
528 | 289 | Web | 11 | TEL-10 | TEL-10.01 | DB: TeleChatMessage (SessionId, PatientAppId, Body, At) | New | Database | Doctor + Patient | Web, UI, QA
529 | 290 | Web | 11 | TEL-10 | TEL-10.02 | API: post/list; doctor and patient only | New | API | Doctor + Patient | Web, UI, QA
530 | 90 | UI | 11 | TEL-10 | TEL-10.03 | In-room chat panel | New | Web SPA | Doctor + Patient | Web, UI, QA
531 | 150 | QA | 11 | TEL-10 | TEL-10.04 | QA: IDOR other session 403 | Regression | QA | Doctor + Patient | Web, UI, QA
532 | 291 | Web | 11 | TEL-11 | TEL-11.01 | DB: ConsultationSummary (PatientAppId, Text, At) | New | Database | Patient + Doctor | Web, UI, QA
533 | 292 | Web | 11 | TEL-11 | TEL-11.02 | API: doctor PUT; patient GET | New | API | Patient + Doctor | Web, UI, QA
534 | 91 | UI | 11 | TEL-11 | TEL-11.03 | Post-call summary form; patient view | New | Web SPA | Patient + Doctor | Web, UI, QA
535 | 151 | QA | 11 | TEL-11 | TEL-11.04 | QA: private notes not copied into summary by default | Regression | QA | Patient + Doctor | Web, UI, QA
536 | 293 | Web | 11 | TEL-12 | TEL-12.01 | DB: InstantConsultRequest, DoctorOffer | New | Database | Patient + Doctor | Web, UI, QA
537 | 294 | Web | 11 | TEL-12 | TEL-12.02 | API: request, match, offer, accept, queue position | New | API | Patient + Doctor | Web, UI, QA
538 | 92 | UI | 11 | TEL-12 | TEL-12.03 | Patient instant CTA; doctor offer banner | New | Web SPA | Patient + Doctor | Web, UI, QA
539 | 152 | QA | 11 | TEL-12 | TEL-12.04 | QA: no online doctor → empty state; surcharge on checkout | Regression | QA | Patient + Doctor | Web, UI, QA
540 | 295 | Web | 12 | COM-01 | COM-01.01 | DB: SmsTemplate, SmsMessageLog; Patient.SmsOptOut | New | Database | Shared | Web, UI, QA
541 | 296 | Web | 12 | COM-01 | COM-01.02 | API: Templates CRUD; Send; History; event worker | New | API | Shared | Web, UI, QA
542 | 93 | UI | 12 | COM-01 | COM-01.03 | Doctor /doctor/sms enable-per-event; admin templates | New | Web SPA | Shared | Web, UI, QA
543 | 297 | Web | 12 | COM-01 | COM-01.04 | MSG91/Twilio/etc. from PRE-03 | New Integration | Integration | Shared | Web, UI, QA
544 | 153 | QA | 12 | COM-01 | COM-01.05 | QA: OTP SMS; reschedule old→new; cancel; doctor unavailable; opt-out honored | Regression | QA | Shared | Web, UI, QA
545 | 298 | Web | 12 | COM-02 | COM-02.01 | Extend WhatsApp log if delivery receipts not stored | Existing Improvement | Database | Doctor Web | Web, UI, QA
546 | 299 | Web | 12 | COM-02 | COM-02.02 | Finish bulk worker + receipt webhook | Existing Improvement | API | Doctor Web | Web, UI, QA
547 | 94 | UI | 12 | COM-02 | COM-02.03 | WhatsAppModal: campaign status, failures, opt-out | Existing Improvement | Web SPA | Doctor Web | Web, UI, QA
548 | 154 | QA | 12 | COM-02 | COM-02.04 | QA: opt-in required; template rejected state | Regression | QA | Doctor Web | Web, UI, QA
549 | 300 | Web | 12 | COM-03 | COM-03.01 | DB: DeviceToken, AppNotification | New | Database | Patient App + Doctor App | Web, UI, QA
550 | 301 | Web | 12 | COM-03 | COM-03.02 | API: Devices/Register; Notifications/Send; list | New | API | Patient App + Doctor App | Web, UI, QA
551 | 95 | UI | 12 | COM-03 | COM-03.03 | Server event hooks (apps consume in 16–17) | New | Web SPA | Patient App + Doctor App | Web, UI, QA
552 | 302 | Web | 12 | COM-03 | COM-03.04 | FCM + APNs | New Integration | Integration | Patient App + Doctor App | Web, UI, QA
553 | 155 | QA | 12 | COM-03 | COM-03.05 | QA: doctor and patient payloads isolated; token refresh | Regression | QA | Patient App + Doctor App | Web, UI, QA
554 | 303 | Web | 12 | COM-04 | COM-04.01 | EmailMessageLog if missing | Existing Improvement | Database | Shared | Web, UI, QA
555 | 304 | Web | 12 | COM-04 | COM-04.02 | Send invoice/receipt email on PAID; keep activation/reset | Existing Improvement | API | Shared | Web, UI, QA
556 | 96 | UI | 12 | COM-04 | COM-04.03 | No new public page — transactional only | Existing Improvement | Web SPA | Shared | Web, UI, QA
557 | 156 | QA | 12 | COM-04 | COM-04.04 | QA: reset still has no plaintext password; invoice attached | Regression | QA | Shared | Web, UI, QA
558 | 305 | Web | 12 | COM-05 | COM-05.01 | Reuse AppNotification | New | Database | Patient App + Doctor Web/App | Web, UI, QA
559 | 306 | Web | 12 | COM-05 | COM-05.02 | GET/PATCH notifications | New | API | Patient App + Doctor Web/App | Web, UI, QA
560 | 97 | UI | 12 | COM-05 | COM-05.03 | Doctor web bell; patient/doctor app centres in 16–17 | New | Web SPA | Patient App + Doctor Web/App | Web, UI, QA
561 | 157 | QA | 12 | COM-05 | COM-05.04 | QA: mark read; empty state; not Velzon demo route | Regression | QA | Patient App + Doctor Web/App | Web, UI, QA
562 | 307 | Web | 13 | SUP-01 | SUP-01.01 | DB: SupportTicket, SupportTicketMessage, SupportTicketAttachment | New | Database | Patient App + Admin | Web, UI, QA
563 | 308 | Web | 13 | SUP-01 | SUP-01.02 | API: create/list/mine for patient | New | API | Patient App + Admin | Web, UI, QA
564 | 98 | UI | 13 | SUP-01 | SUP-01.03 | Patient app screens in Phase 16; web help optional | New | Web SPA | Patient App + Admin | Web, UI, QA
565 | 158 | QA | 13 | SUP-01 | SUP-01.04 | QA: IDOR; attachment via SEC-09 | Regression | QA | Patient App + Admin | Web, UI, QA
566 | 309 | Web | 13 | SUP-02 | SUP-02.01 | Reuse SupportTicket with ReporterRole=Doctor | New | API | Doctor Web + Admin | Web, UI, QA
567 | 99 | UI | 13 | SUP-02 | SUP-02.02 | /doctor/support list/create/detail | New | Web SPA | Doctor Web + Admin | Web, UI, QA
568 | 159 | QA | 13 | SUP-02 | SUP-02.03 | QA: doctor cannot see another doctor’s tickets | Regression | QA | Doctor Web + Admin | Web, UI, QA
569 | 310 | Web | 13 | SUP-03 | SUP-03.01 | Extend ticket with Priority, Assignee, SLA | New | Database | Admin Portal | Web, UI, QA
570 | 311 | Web | 13 | SUP-03 | SUP-03.02 | Admin list/filter/assign/status | New | API | Admin Portal | Web, UI, QA
571 | 100 | UI | 13 | SUP-03 | SUP-03.03 | /admin/support-tickets and /:id | New | Web SPA | Admin Portal | Web, UI, QA
572 | 160 | QA | 13 | SUP-03 | SUP-03.04 | QA: not using Velzon ticket pages | Regression | QA | Admin Portal | Web, UI, QA
573 | 312 | Web | 13 | SUP-04 | SUP-04.01 | API: messages CRUD + attachment | New | API | Admin + Doctor + Patient | Web, UI, QA
574 | 101 | UI | 13 | SUP-04 | SUP-04.02 | Detail UI thread | New | Web SPA | Admin + Doctor + Patient | Web, UI, QA
575 | 161 | QA | 13 | SUP-04 | SUP-04.03 | QA: attachment unauthorised download 403 | Regression | QA | Admin + Doctor + Patient | Web, UI, QA
576 | 102 | UI | 13 | SUP-05 | SUP-05.01 | Admin enquiry inbox SLA fields | Existing Improvement | Web SPA | Admin Portal | UI, QA
577 | 162 | QA | 13 | SUP-05 | SUP-05.02 | QA: convert to ticket keeps original enquiry id | Regression | QA | Admin Portal | UI, QA
578 | 313 | Web | 13 | SUP-06 | SUP-06.01 | HelpArticle table or reuse blog category=help | New | Database | Patient Website + App | Web, UI, QA
579 | 314 | Web | 13 | SUP-06 | SUP-06.02 | Public GET help articles | New | API | Patient Website + App | Web, UI, QA
580 | 103 | UI | 13 | SUP-06 | SUP-06.03 | Help centre list/detail | New | Web SPA | Patient Website + App | Web, UI, QA
581 | 163 | QA | 13 | SUP-06 | SUP-06.04 | QA: unpublished hidden | Regression | QA | Patient Website + App | Web, UI, QA
582 | 315 | Web | 13 | SUP-07 | SUP-07.01 | Flag BookingChannel=Assisted; AssistedRequest ticket type | New | Database | Support + Reception + Patient | Web, UI, QA
583 | 316 | Web | 13 | SUP-07 | SUP-07.02 | API: request assistance; staff completes WEB-04 create on behalf | New | API | Support + Reception + Patient | Web, UI, QA
584 | 104 | UI | 13 | SUP-07 | SUP-07.03 | Patient CTA; admin/reception assisted-book wizard | New | Web SPA | Support + Reception + Patient | Web, UI, QA
585 | 164 | QA | 13 | SUP-07 | SUP-07.04 | QA: consent still captured; payment still Homeocentrum | Regression | QA | Support + Reception + Patient | Web, UI, QA
586 | 317 | Web | 14 | MED-01 | MED-01.01 | DB: PharmacyPartner, PharmacyLicence, activation checklist fields | New | Database | Pharmacy + Admin | Web, UI, QA
587 | 318 | Web | 14 | MED-01 | MED-01.02 | API: onboard, admin activate, pharmacy login role | New | API | Pharmacy + Admin | Web, UI, QA
588 | 105 | UI | 14 | MED-01 | MED-01.03 | /pharmacy/onboard; /admin pharmacy partners | New | Web SPA | Pharmacy + Admin | Web, UI, QA
589 | 165 | QA | 14 | MED-01 | MED-01.04 | QA: checklist incomplete blocks activate | Regression | QA | Pharmacy + Admin | Web, UI, QA
590 | 319 | Web | 14 | MED-02 | MED-02.01 | Job: mark licence expired/suspended; exclude from routing | New | Backend | Backend | Web, UI, QA
591 | 106 | UI | 14 | MED-02 | MED-02.02 | Pharmacy console status banner | New | Web SPA | Backend | Web, UI, QA
592 | 166 | QA | 14 | MED-02 | MED-02.03 | QA: expire a licence in test → order not offered | Regression | QA | Backend | Web, UI, QA
593 | 320 | Web | 14 | MED-03 | MED-03.01 | Consent + selected PharmacyPartnerId on MedicineOrder | New | Database | Patient | Web, UI, QA
594 | 321 | Web | 14 | MED-03 | MED-03.02 | API: list sellers; select; grant consent | New | API | Patient | Web, UI, QA
595 | 107 | UI | 14 | MED-03 | MED-03.03 | Patient pharmacy pick UI (web optional + app Phase 16) | New | Web SPA | Patient | Web, UI, QA
596 | 167 | QA | 14 | MED-03 | MED-03.04 | QA: without consent, handoff API 403 | Regression | QA | Patient | Web, UI, QA
597 | 322 | Web | 14 | MED-04 | MED-04.01 | DB: MedicineOrder, MedicineOrderItem from ErxSnapshot | New | Database | Patient + Pharmacy | Web, UI, QA
598 | 323 | Web | 14 | MED-04 | MED-04.02 | API: POST order from ErxId | New | API | Patient + Pharmacy | Web, UI, QA
599 | 108 | UI | 14 | MED-04 | MED-04.03 | Order start from patient eRx screen | New | Web SPA | Patient + Pharmacy | Web, UI, QA
600 | 168 | QA | 14 | MED-04 | MED-04.04 | QA: line count mismatch fails sign-off | Regression | QA | Patient + Pharmacy | Web, UI, QA
601 | 324 | Web | 14 | MED-05 | MED-05.01 | DB: SellerRoutingRule (area, hours, capacity) | New | Database | Backend | Web, UI, QA
602 | 325 | Web | 14 | MED-05 | MED-05.02 | Routing service used by seller list API | New | API | Backend | Web, UI, QA
603 | 109 | UI | 14 | MED-05 | MED-05.03 | Admin/pharmacy hours and area config UI | New | Web SPA | Backend | Web, UI, QA
604 | 169 | QA | 14 | MED-05 | MED-05.04 | QA: capacity full excluded; hours closed excluded | Regression | QA | Backend | Web, UI, QA
605 | 326 | Web | 14 | MED-06 | MED-06.01 | Accept payload includes stock confirmation; reject reason OUT_OF_STOCK | New | API | Pharmacy console | Web, UI, QA
606 | 110 | UI | 14 | MED-06 | MED-06.02 | Pharmacy UI confirm availability | New | Web SPA | Pharmacy console | Web, UI, QA
607 | 170 | QA | 14 | MED-06 | MED-06.03 | QA: no inventory SKU table required | Regression | QA | Pharmacy console | Web, UI, QA
608 | 327 | Web | 14 | MED-07 | MED-07.01 | Order status machine: Offered/Accepted/Rejected/Quoted/Paid/Ready/Dispatched/Delivered | New | Database | Pharmacy console | Web, UI, QA
609 | 328 | Web | 14 | MED-07 | MED-07.02 | API: accept(OTP), reject, quote, ready, dispatch | New | API | Pharmacy console | Web, UI, QA
610 | 111 | UI | 14 | MED-07 | MED-07.03 | /pharmacy/orders and detail | New | Web SPA | Pharmacy console | Web, UI, QA
611 | 329 | Web | 14 | MED-07 | MED-07.04 | OTP on accept | New Integration | Integration | Pharmacy console | Web, UI, QA
612 | 171 | QA | 14 | MED-07 | MED-07.05 | QA: accept without OTP fails; names still hidden to patient until accept succeeds | Regression | QA | Pharmacy console | Web, UI, QA
613 | 330 | Web | 14 | MED-08 | MED-08.01 | DB: MedicineQuote | New | Database | Patient | Web, UI, QA
614 | 331 | Web | 14 | MED-08 | MED-08.02 | API: quote, patient accept quote, then create medicine payment | New | API | Patient | Web, UI, QA
615 | 112 | UI | 14 | MED-08 | MED-08.03 | Patient quote screen | New | Web SPA | Patient | Web, UI, QA
616 | 172 | QA | 14 | MED-08 | MED-08.04 | QA: price change after quote invalidates old quote | Regression | QA | Patient | Web, UI, QA
617 | 332 | Web | 14 | MED-09 | MED-09.01 | Wire PAY-07 CreateMedicineOrder; COD status enum | New | API | Patient | Web, UI, QA
618 | 113 | UI | 14 | MED-09 | MED-09.02 | Patient pay vs COD UI | New | Web SPA | Patient | Web, UI, QA
619 | 173 | QA | 14 | MED-09 | MED-09.03 | QA: COD vs prepaid ledger split | Regression | QA | Patient | Web, UI, QA
620 | 333 | Web | 14 | MED-10 | MED-10.01 | DB: MedicineOrderEvent | New | Database | Patient | Web, UI, QA
621 | 334 | Web | 14 | MED-10 | MED-10.02 | GET tracking by order id (patient) | New | API | Patient | Web, UI, QA
622 | 114 | UI | 14 | MED-10 | MED-10.03 | Tracking UI | New | Web SPA | Patient | Web, UI, QA
623 | 335 | Web | 14 | MED-10 | MED-10.04 | Push on status change | New Integration | Integration | Patient | Web, UI, QA
624 | 174 | QA | 14 | MED-10 | MED-10.05 | QA: dispatched without ready is invalid transition | Regression | QA | Patient | Web, UI, QA
625 | 336 | Web | 14 | MED-11 | MED-11.01 | On captured medicine payment write three-share ledger lines | New | API | Account | Web, QA
626 | 175 | QA | 14 | MED-11 | MED-11.02 | QA: consult GMV unchanged by a medicine order | Regression | QA | Account | Web, QA
627 | 337 | Web | 14 | MED-12 | MED-12.01 | Exception rows for medicine orders | New | Database | Admin + Account | Web, UI, QA
628 | 338 | Web | 14 | MED-12 | MED-12.02 | Admin/ops list/detail/retry re-route | New | API | Admin + Account | Web, UI, QA
629 | 115 | UI | 14 | MED-12 | MED-12.03 | /admin/homemeds-exceptions | New | Web SPA | Admin + Account | Web, UI, QA
630 | 176 | QA | 14 | MED-12 | MED-12.04 | QA: silent discard impossible (metric + queue) | Regression | QA | Admin + Account | Web, UI, QA
631 | 339 | Web | 14 | MED-13 | MED-13.01 | Bind OTP actions: PharmacyAccept, (optional) QuoteLock, Payout already FIN-05 | New | API | Pharmacy + Account | Web, QA
632 | 177 | QA | 14 | MED-13 | MED-13.02 | QA: Account OTP audit shows pharmacy accept | Regression | QA | Pharmacy + Account | Web, QA
633 | 340 | Web | 14 | MED-14 | MED-14.01 | On doctor approve, clone order from snapshot; patient one-tap | New | API | Patient + Doctor | Web, UI, QA
634 | 116 | UI | 14 | MED-14 | MED-14.02 | Patient order detail + refill CTA | New | Web SPA | Patient + Doctor | Web, UI, QA
635 | 178 | QA | 14 | MED-14 | MED-14.03 | QA: original eRx unchanged | Regression | QA | Patient + Doctor | Web, UI, QA
636 | 117 | UI | 14 | MED-15 | MED-15.01 | Patient review screen before handoff | New | Web SPA | Patient | UI, QA
637 | 179 | QA | 14 | MED-15 | MED-15.02 | QA: back button does not share | Regression | QA | Patient | UI, QA
638 | 341 | Web | 14 | MED-16 | MED-16.01 | GET /api/Patient/MedicineOrders | New | API | Patient | Web, UI, QA
639 | 118 | UI | 14 | MED-16 | MED-16.02 | Optional web list; mobile tab later | New | Web SPA | Patient | Web, UI, QA
640 | 180 | QA | 14 | MED-16 | MED-16.03 | QA: IDOR other patient 403 | Regression | QA | Patient | Web, UI, QA
641 | 342 | Web | 15 | CON-01 | CON-01.01 | DB: FamilyMember | New | Database | Patient App (API now) | Web, UI, QA
642 | 343 | Web | 15 | CON-01 | CON-01.02 | API: CRUD family; book-as-member | New | API | Patient App (API now) | Web, UI, QA
643 | 119 | UI | 15 | CON-01 | CON-01.03 | Consumed in Phase 16 | New | Web SPA | Patient App (API now) | Web, UI, QA
644 | 181 | QA | 15 | CON-01 | CON-01.04 | QA: adult consent rules for minors documented | Regression | QA | Patient App (API now) | Web, UI, QA
645 | 344 | Web | 15 | CON-02 | CON-02.01 | DB: CaregiverAuth | New | Database | Patient App (API now) | Web, UI, QA
646 | 345 | Web | 15 | CON-02 | CON-02.02 | API: grant/revoke/list; booking authorisation check | New | API | Patient App (API now) | Web, UI, QA
647 | 120 | UI | 15 | CON-02 | CON-02.03 | Consumed in Phase 16 | New | Web SPA | Patient App (API now) | Web, UI, QA
648 | 346 | Web | 15 | CON-02 | CON-02.04 | OTP on grant | New Integration | Integration | Patient App (API now) | Web, UI, QA
649 | 182 | QA | 15 | CON-02 | CON-02.05 | QA: revoked token cannot book | Regression | QA | Patient App (API now) | Web, UI, QA
650 | 347 | Web | 15 | CON-03 | CON-03.01 | Reuse appointments + summary + eRx + SecureDocument | New | Database | Patient App (API now) | Web, UI, QA
651 | 348 | Web | 15 | CON-03 | CON-03.02 | GET timeline; GET consultation note (summary); POST documents | New | API | Patient App (API now) | Web, UI, QA
652 | 121 | UI | 15 | CON-03 | CON-03.03 | Consumed in Phase 16 | New | Web SPA | Patient App (API now) | Web, UI, QA
653 | 183 | QA | 15 | CON-03 | CON-03.04 | QA: notes leak test on timeline JSON | Regression | QA | Patient App (API now) | Web, UI, QA
654 | 349 | Web | 15 | CON-04 | CON-04.01 | DB: FollowUpPlan, FollowUpTask | New | Database | Doctor Web + Patient | Web, UI, QA
655 | 350 | Web | 15 | CON-04 | CON-04.02 | API: doctor set; patient list/complete | New | API | Doctor Web + Patient | Web, UI, QA
656 | 122 | UI | 15 | CON-04 | CON-04.03 | Doctor board follow-up panel; app in Phase 16 | New | Web SPA | Doctor Web + Patient | Web, UI, QA
657 | 184 | QA | 15 | CON-04 | CON-04.04 | QA: overdue flag | Regression | QA | Doctor Web + Patient | Web, UI, QA
658 | 351 | Web | 15 | CON-05 | CON-05.01 | DB: SymptomDiary | New | Database | Patient App (API now) | Web, UI, QA
659 | 352 | Web | 15 | CON-05 | CON-05.02 | API: patient CRUD; doctor GET by patient | New | API | Patient App (API now) | Web, UI, QA
660 | 123 | UI | 15 | CON-05 | CON-05.03 | Doctor board read-only; app write Phase 16 | New | Web SPA | Patient App (API now) | Web, UI, QA
661 | 185 | QA | 15 | CON-05 | CON-05.04 | QA: IDOR | Regression | QA | Patient App (API now) | Web, UI, QA
662 | 353 | Web | 15 | CON-06 | CON-06.01 | Derived API from diary + appointments | New | Database | Patient + Doctor | Web, UI, QA
663 | 354 | Web | 15 | CON-06 | CON-06.02 | GET progress series | New | API | Patient + Doctor | Web, UI, QA
664 | 124 | UI | 15 | CON-06 | CON-06.03 | Consumed in Phase 16 | New | Web SPA | Patient + Doctor | Web, UI, QA
665 | 186 | QA | 15 | CON-06 | CON-06.04 | QA: no dummy numbers | Regression | QA | Patient + Doctor | Web, UI, QA
666 | 355 | Web | 15 | CON-07 | CON-07.01 | Reuse ConsentRecord; DataRequest table | New | Database | Patient App (API now) | Web, UI, QA
667 | 356 | Web | 15 | CON-07 | CON-07.02 | API: list/withdraw; request export/delete | New | API | Patient App (API now) | Web, UI, QA
668 | 125 | UI | 15 | CON-07 | CON-07.03 | Consumed in Phase 16 | New | Web SPA | Patient App (API now) | Web, UI, QA
669 | 187 | QA | 15 | CON-07 | CON-07.04 | QA: withdraw marketing stops WhatsApp/SMS offers | Regression | QA | Patient App (API now) | Web, UI, QA
670 | 357 | Web | 15 | CON-08 | CON-08.01 | GET /api/Patient/Payments | New | API | Patient App (API now) | Web, QA
671 | 188 | QA | 15 | CON-08 | CON-08.02 | QA: commission/GST internal lines hidden | Regression | QA | Patient App (API now) | Web, QA
672 | 358 | Web | 15 | CON-09 | CON-09.01 | Public/patient create booking accepts ConsultMode=In-clinic; uses in-clinic fee | Existing Improvement | API | Patient | Web, QA
673 | 189 | QA | 15 | CON-09 | CON-09.02 | QA: in-clinic does not require device check/video | Regression | QA | Patient | Web, QA
674 | 359 | Web | 15 | CON-10 | CON-10.01 | Extend Patient with health-basics JSON/columns | New | Database | Patient App (API now) | Web, UI, QA
675 | 360 | Web | 15 | CON-10 | CON-10.02 | GET/PUT /api/Patient/Profile | New | API | Patient App (API now) | Web, UI, QA
676 | 126 | UI | 15 | CON-10 | CON-10.03 | Consumed in Phase 16 | New | Web SPA | Patient App (API now) | Web, UI, QA
677 | 190 | QA | 15 | CON-10 | CON-10.04 | QA: cannot escalate to doctor role via profile PUT | Regression | QA | Patient App (API now) | Web, UI, QA
678 | 2 | Mobile | 16 | PAT-01 | PAT-01.01 | UI: Language selection screens (empty, loading, error, offline) | New | Mobile UI | Patient Mobile App | Mobile, QA
679 | 3 | Mobile | 16 | PAT-01 | PAT-01.02 | Wire to the Phase 8–15 API for: Language selection | New | Mobile client | Patient Mobile App | Mobile, QA
680 | 4 | Mobile | 16 | PAT-01 | PAT-01.03 | Low-data assets where applicable; accessibility labels | New | Mobile UX | Patient Mobile App | Mobile, QA
681 | 191 | QA | 16 | PAT-01 | PAT-01.04 | QA both platforms: Language selection matches website/API status; no local fake paid/signed state | Regression | QA | Patient Mobile App | Mobile, QA
682 | 5 | Mobile | 16 | PAT-02 | PAT-02.01 | UI: Welcome & introduction screens (empty, loading, error, offline) | New | Mobile UI | Patient Mobile App | Mobile, QA
683 | 6 | Mobile | 16 | PAT-02 | PAT-02.02 | Wire to the Phase 8–15 API for: Welcome & introduction | New | Mobile client | Patient Mobile App | Mobile, QA
684 | 7 | Mobile | 16 | PAT-02 | PAT-02.03 | Low-data assets where applicable; accessibility labels | New | Mobile UX | Patient Mobile App | Mobile, QA
685 | 192 | QA | 16 | PAT-02 | PAT-02.04 | QA both platforms: Welcome & introduction matches website/API status; no local fake paid/signed state | Regression | QA | Patient Mobile App | Mobile, QA
686 | 8 | Mobile | 16 | PAT-03 | PAT-03.01 | UI: Mobile number + OTP login screens (empty, loading, error, offline) | New | Mobile UI | Patient Mobile App | Mobile, QA
687 | 9 | Mobile | 16 | PAT-03 | PAT-03.02 | Wire to the Phase 8–15 API for: Mobile number + OTP login | New | Mobile client | Patient Mobile App | Mobile, QA
688 | 10 | Mobile | 16 | PAT-03 | PAT-03.03 | Low-data assets where applicable; accessibility labels | New | Mobile UX | Patient Mobile App | Mobile, QA
689 | 193 | QA | 16 | PAT-03 | PAT-03.04 | QA both platforms: Mobile number + OTP login matches website/API status; no local fake paid/signed state | Regression | QA | Patient Mobile App | Mobile, QA
690 | 11 | Mobile | 16 | PAT-04 | PAT-04.01 | UI: Profile setup screens (empty, loading, error, offline) | New | Mobile UI | Patient Mobile App | Mobile, QA
691 | 12 | Mobile | 16 | PAT-04 | PAT-04.02 | Wire to the Phase 8–15 API for: Profile setup | New | Mobile client | Patient Mobile App | Mobile, QA
692 | 13 | Mobile | 16 | PAT-04 | PAT-04.03 | Low-data assets where applicable; accessibility labels | New | Mobile UX | Patient Mobile App | Mobile, QA
693 | 194 | QA | 16 | PAT-04 | PAT-04.04 | QA both platforms: Profile setup matches website/API status; no local fake paid/signed state | Regression | QA | Patient Mobile App | Mobile, QA
694 | 14 | Mobile | 16 | PAT-05 | PAT-05.01 | UI: Privacy consent screens (empty, loading, error, offline) | New | Mobile UI | Patient Mobile App | Mobile, QA
695 | 15 | Mobile | 16 | PAT-05 | PAT-05.02 | Wire to the Phase 8–15 API for: Privacy consent | New | Mobile client | Patient Mobile App | Mobile, QA
696 | 16 | Mobile | 16 | PAT-05 | PAT-05.03 | Low-data assets where applicable; accessibility labels | New | Mobile UX | Patient Mobile App | Mobile, QA
697 | 195 | QA | 16 | PAT-05 | PAT-05.04 | QA both platforms: Privacy consent matches website/API status; no local fake paid/signed state | Regression | QA | Patient Mobile App | Mobile, QA
698 | 17 | Mobile | 16 | PAT-06 | PAT-06.01 | UI: Family members screens (empty, loading, error, offline) | New | Mobile UI | Patient Mobile App | Mobile, QA
699 | 18 | Mobile | 16 | PAT-06 | PAT-06.02 | Wire to the Phase 8–15 API for: Family members | New | Mobile client | Patient Mobile App | Mobile, QA
700 | 19 | Mobile | 16 | PAT-06 | PAT-06.03 | Low-data assets where applicable; accessibility labels | New | Mobile UX | Patient Mobile App | Mobile, QA
701 | 196 | QA | 16 | PAT-06 | PAT-06.04 | QA both platforms: Family members matches website/API status; no local fake paid/signed state | Regression | QA | Patient Mobile App | Mobile, QA
702 | 20 | Mobile | 16 | PAT-07 | PAT-07.01 | UI: Caregiver authorization screens (empty, loading, error, offline) | New | Mobile UI | Patient Mobile App | Mobile, QA
703 | 21 | Mobile | 16 | PAT-07 | PAT-07.02 | Wire to the Phase 8–15 API for: Caregiver authorization | New | Mobile client | Patient Mobile App | Mobile, QA
704 | 22 | Mobile | 16 | PAT-07 | PAT-07.03 | Low-data assets where applicable; accessibility labels | New | Mobile UX | Patient Mobile App | Mobile, QA
705 | 197 | QA | 16 | PAT-07 | PAT-07.04 | QA both platforms: Caregiver authorization matches website/API status; no local fake paid/signed state | Regression | QA | Patient Mobile App | Mobile, QA
706 | 23 | Mobile | 16 | PAT-08 | PAT-08.01 | UI: Home dashboard screens (empty, loading, error, offline) | New | Mobile UI | Patient Mobile App | Mobile, QA
707 | 24 | Mobile | 16 | PAT-08 | PAT-08.02 | Wire to the Phase 8–15 API for: Home dashboard | New | Mobile client | Patient Mobile App | Mobile, QA
708 | 25 | Mobile | 16 | PAT-08 | PAT-08.03 | Low-data assets where applicable; accessibility labels | New | Mobile UX | Patient Mobile App | Mobile, QA
709 | 198 | QA | 16 | PAT-08 | PAT-08.04 | QA both platforms: Home dashboard matches website/API status; no local fake paid/signed state | Regression | QA | Patient Mobile App | Mobile, QA
710 | 26 | Mobile | 16 | PAT-09 | PAT-09.01 | UI: Search & care categories screens (empty, loading, error, offline) | New | Mobile UI | Patient Mobile App | Mobile, QA
711 | 27 | Mobile | 16 | PAT-09 | PAT-09.02 | Wire to the Phase 8–15 API for: Search & care categories | New | Mobile client | Patient Mobile App | Mobile, QA
712 | 28 | Mobile | 16 | PAT-09 | PAT-09.03 | Low-data assets where applicable; accessibility labels | New | Mobile UX | Patient Mobile App | Mobile, QA
713 | 199 | QA | 16 | PAT-09 | PAT-09.04 | QA both platforms: Search & care categories matches website/API status; no local fake paid/signed state | Regression | QA | Patient Mobile App | Mobile, QA
714 | 29 | Mobile | 16 | PAT-10 | PAT-10.01 | UI: Search results screens (empty, loading, error, offline) | New | Mobile UI | Patient Mobile App | Mobile, QA
715 | 30 | Mobile | 16 | PAT-10 | PAT-10.02 | Wire to the Phase 8–15 API for: Search results | New | Mobile client | Patient Mobile App | Mobile, QA
716 | 31 | Mobile | 16 | PAT-10 | PAT-10.03 | Low-data assets where applicable; accessibility labels | New | Mobile UX | Patient Mobile App | Mobile, QA
717 | 200 | QA | 16 | PAT-10 | PAT-10.04 | QA both platforms: Search results matches website/API status; no local fake paid/signed state | Regression | QA | Patient Mobile App | Mobile, QA
718 | 32 | Mobile | 16 | PAT-11 | PAT-11.01 | UI: Filters screens (empty, loading, error, offline) | New | Mobile UI | Patient Mobile App | Mobile, QA
719 | 33 | Mobile | 16 | PAT-11 | PAT-11.02 | Wire to the Phase 8–15 API for: Filters | New | Mobile client | Patient Mobile App | Mobile, QA
720 | 34 | Mobile | 16 | PAT-11 | PAT-11.03 | Low-data assets where applicable; accessibility labels | New | Mobile UX | Patient Mobile App | Mobile, QA
721 | 201 | QA | 16 | PAT-11 | PAT-11.04 | QA both platforms: Filters matches website/API status; no local fake paid/signed state | Regression | QA | Patient Mobile App | Mobile, QA
722 | 35 | Mobile | 16 | PAT-12 | PAT-12.01 | UI: Doctor profile screens (empty, loading, error, offline) | New | Mobile UI | Patient Mobile App | Mobile, QA
723 | 36 | Mobile | 16 | PAT-12 | PAT-12.02 | Wire to the Phase 8–15 API for: Doctor profile | New | Mobile client | Patient Mobile App | Mobile, QA
724 | 37 | Mobile | 16 | PAT-12 | PAT-12.03 | Low-data assets where applicable; accessibility labels | New | Mobile UX | Patient Mobile App | Mobile, QA
725 | 202 | QA | 16 | PAT-12 | PAT-12.04 | QA both platforms: Doctor profile matches website/API status; no local fake paid/signed state | Regression | QA | Patient Mobile App | Mobile, QA
726 | 38 | Mobile | 16 | PAT-13 | PAT-13.01 | UI: Credentials & verification screens (empty, loading, error, offline) | New | Mobile UI | Patient Mobile App | Mobile, QA
727 | 39 | Mobile | 16 | PAT-13 | PAT-13.02 | Wire to the Phase 8–15 API for: Credentials & verification | New | Mobile client | Patient Mobile App | Mobile, QA
728 | 40 | Mobile | 16 | PAT-13 | PAT-13.03 | Low-data assets where applicable; accessibility labels | New | Mobile UX | Patient Mobile App | Mobile, QA
729 | 203 | QA | 16 | PAT-13 | PAT-13.04 | QA both platforms: Credentials & verification matches website/API status; no local fake paid/signed state | Regression | QA | Patient Mobile App | Mobile, QA
730 | 41 | Mobile | 16 | PAT-14 | PAT-14.01 | UI: Ranking explanation screens (empty, loading, error, offline) | New | Mobile UI | Patient Mobile App | Mobile, QA
731 | 42 | Mobile | 16 | PAT-14 | PAT-14.02 | Wire to the Phase 8–15 API for: Ranking explanation | New | Mobile client | Patient Mobile App | Mobile, QA
732 | 43 | Mobile | 16 | PAT-14 | PAT-14.03 | Low-data assets where applicable; accessibility labels | New | Mobile UX | Patient Mobile App | Mobile, QA
733 | 204 | QA | 16 | PAT-14 | PAT-14.04 | QA both platforms: Ranking explanation matches website/API status; no local fake paid/signed state | Regression | QA | Patient Mobile App | Mobile, QA
734 | 44 | Mobile | 16 | PAT-15 | PAT-15.01 | UI: Health articles screens (empty, loading, error, offline) | New | Mobile UI | Patient Mobile App | Mobile, QA
735 | 45 | Mobile | 16 | PAT-15 | PAT-15.02 | Wire to the Phase 8–15 API for: Health articles | New | Mobile client | Patient Mobile App | Mobile, QA
736 | 46 | Mobile | 16 | PAT-15 | PAT-15.03 | Low-data assets where applicable; accessibility labels | New | Mobile UX | Patient Mobile App | Mobile, QA
737 | 205 | QA | 16 | PAT-15 | PAT-15.04 | QA both platforms: Health articles matches website/API status; no local fake paid/signed state | Regression | QA | Patient Mobile App | Mobile, QA
738 | 47 | Mobile | 16 | PAT-16 | PAT-16.01 | UI: Slot picker screens (empty, loading, error, offline) | New | Mobile UI | Patient Mobile App | Mobile, QA
739 | 48 | Mobile | 16 | PAT-16 | PAT-16.02 | Wire to the Phase 8–15 API for: Slot picker | New | Mobile client | Patient Mobile App | Mobile, QA
740 | 49 | Mobile | 16 | PAT-16 | PAT-16.03 | Low-data assets where applicable; accessibility labels | New | Mobile UX | Patient Mobile App | Mobile, QA
741 | 206 | QA | 16 | PAT-16 | PAT-16.04 | QA both platforms: Slot picker matches website/API status; no local fake paid/signed state | Regression | QA | Patient Mobile App | Mobile, QA
742 | 50 | Mobile | 16 | PAT-17 | PAT-17.01 | UI: Booking review & consent screens (empty, loading, error, offline) | New | Mobile UI | Patient Mobile App | Mobile, QA
743 | 51 | Mobile | 16 | PAT-17 | PAT-17.02 | Wire to the Phase 8–15 API for: Booking review & consent | New | Mobile client | Patient Mobile App | Mobile, QA
744 | 52 | Mobile | 16 | PAT-17 | PAT-17.03 | Low-data assets where applicable; accessibility labels | New | Mobile UX | Patient Mobile App | Mobile, QA
745 | 207 | QA | 16 | PAT-17 | PAT-17.04 | QA both platforms: Booking review & consent matches website/API status; no local fake paid/signed state | Regression | QA | Patient Mobile App | Mobile, QA
746 | 53 | Mobile | 16 | PAT-18 | PAT-18.01 | UI: Checkout screens (empty, loading, error, offline) | New | Mobile UI | Patient Mobile App | Mobile, QA
747 | 54 | Mobile | 16 | PAT-18 | PAT-18.02 | Wire to the Phase 8–15 API for: Checkout | New | Mobile client | Patient Mobile App | Mobile, QA
748 | 55 | Mobile | 16 | PAT-18 | PAT-18.03 | Low-data assets where applicable; accessibility labels | New | Mobile UX | Patient Mobile App | Mobile, QA
749 | 208 | QA | 16 | PAT-18 | PAT-18.04 | QA both platforms: Checkout matches website/API status; no local fake paid/signed state | Regression | QA | Patient Mobile App | Mobile, QA
750 | 56 | Mobile | 16 | PAT-19 | PAT-19.01 | UI: Payment status screens (empty, loading, error, offline) | New | Mobile UI | Patient Mobile App | Mobile, QA
751 | 57 | Mobile | 16 | PAT-19 | PAT-19.02 | Wire to the Phase 8–15 API for: Payment status | New | Mobile client | Patient Mobile App | Mobile, QA
752 | 58 | Mobile | 16 | PAT-19 | PAT-19.03 | Low-data assets where applicable; accessibility labels | New | Mobile UX | Patient Mobile App | Mobile, QA
753 | 209 | QA | 16 | PAT-19 | PAT-19.04 | QA both platforms: Payment status matches website/API status; no local fake paid/signed state | Regression | QA | Patient Mobile App | Mobile, QA
754 | 59 | Mobile | 16 | PAT-20 | PAT-20.01 | UI: Appointment detail screens (empty, loading, error, offline) | New | Mobile UI | Patient Mobile App | Mobile, QA
755 | 60 | Mobile | 16 | PAT-20 | PAT-20.02 | Wire to the Phase 8–15 API for: Appointment detail | New | Mobile client | Patient Mobile App | Mobile, QA
756 | 61 | Mobile | 16 | PAT-20 | PAT-20.03 | Low-data assets where applicable; accessibility labels | New | Mobile UX | Patient Mobile App | Mobile, QA
757 | 210 | QA | 16 | PAT-20 | PAT-20.04 | QA both platforms: Appointment detail matches website/API status; no local fake paid/signed state | Regression | QA | Patient Mobile App | Mobile, QA
758 | 62 | Mobile | 16 | PAT-21 | PAT-21.01 | UI: Reschedule appointment screens (empty, loading, error, offline) | New | Mobile UI | Patient Mobile App | Mobile, QA
759 | 63 | Mobile | 16 | PAT-21 | PAT-21.02 | Wire to the Phase 8–15 API for: Reschedule appointment | New | Mobile client | Patient Mobile App | Mobile, QA
760 | 64 | Mobile | 16 | PAT-21 | PAT-21.03 | Low-data assets where applicable; accessibility labels | New | Mobile UX | Patient Mobile App | Mobile, QA
761 | 211 | QA | 16 | PAT-21 | PAT-21.04 | QA both platforms: Reschedule appointment matches website/API status; no local fake paid/signed state | Regression | QA | Patient Mobile App | Mobile, QA
762 | 65 | Mobile | 16 | PAT-22 | PAT-22.01 | UI: Cancel appointment screens (empty, loading, error, offline) | New | Mobile UI | Patient Mobile App | Mobile, QA
763 | 66 | Mobile | 16 | PAT-22 | PAT-22.02 | Wire to the Phase 8–15 API for: Cancel appointment | New | Mobile client | Patient Mobile App | Mobile, QA
764 | 67 | Mobile | 16 | PAT-22 | PAT-22.03 | Low-data assets where applicable; accessibility labels | New | Mobile UX | Patient Mobile App | Mobile, QA
765 | 212 | QA | 16 | PAT-22 | PAT-22.04 | QA both platforms: Cancel appointment matches website/API status; no local fake paid/signed state | Regression | QA | Patient Mobile App | Mobile, QA
766 | 68 | Mobile | 16 | PAT-23 | PAT-23.01 | UI: Waitlist offer screens (empty, loading, error, offline) | New | Mobile UI | Patient Mobile App | Mobile, QA
767 | 69 | Mobile | 16 | PAT-23 | PAT-23.02 | Wire to the Phase 8–15 API for: Waitlist offer | New | Mobile client | Patient Mobile App | Mobile, QA
768 | 70 | Mobile | 16 | PAT-23 | PAT-23.03 | Low-data assets where applicable; accessibility labels | New | Mobile UX | Patient Mobile App | Mobile, QA
769 | 213 | QA | 16 | PAT-23 | PAT-23.04 | QA both platforms: Waitlist offer matches website/API status; no local fake paid/signed state | Regression | QA | Patient Mobile App | Mobile, QA
770 | 71 | Mobile | 16 | PAT-24 | PAT-24.01 | UI: Instant consult request screens (empty, loading, error, offline) | New | Mobile UI | Patient Mobile App | Mobile, QA
771 | 72 | Mobile | 16 | PAT-24 | PAT-24.02 | Wire to the Phase 8–15 API for: Instant consult request | New | Mobile client | Patient Mobile App | Mobile, QA
772 | 73 | Mobile | 16 | PAT-24 | PAT-24.03 | Low-data assets where applicable; accessibility labels | New | Mobile UX | Patient Mobile App | Mobile, QA
773 | 214 | QA | 16 | PAT-24 | PAT-24.04 | QA both platforms: Instant consult request matches website/API status; no local fake paid/signed state | Regression | QA | Patient Mobile App | Mobile, QA
774 | 74 | Mobile | 16 | PAT-25 | PAT-25.01 | UI: Queue & doctor offer screens (empty, loading, error, offline) | New | Mobile UI | Patient Mobile App | Mobile, QA
775 | 75 | Mobile | 16 | PAT-25 | PAT-25.02 | Wire to the Phase 8–15 API for: Queue & doctor offer | New | Mobile client | Patient Mobile App | Mobile, QA
776 | 76 | Mobile | 16 | PAT-25 | PAT-25.03 | Low-data assets where applicable; accessibility labels | New | Mobile UX | Patient Mobile App | Mobile, QA
777 | 215 | QA | 16 | PAT-25 | PAT-25.04 | QA both platforms: Queue & doctor offer matches website/API status; no local fake paid/signed state | Regression | QA | Patient Mobile App | Mobile, QA
778 | 77 | Mobile | 16 | PAT-26 | PAT-26.01 | UI: Device check screens (empty, loading, error, offline) | New | Mobile UI | Patient Mobile App | Mobile, QA
779 | 78 | Mobile | 16 | PAT-26 | PAT-26.02 | Wire to the Phase 8–15 API for: Device check | New | Mobile client | Patient Mobile App | Mobile, QA
780 | 79 | Mobile | 16 | PAT-26 | PAT-26.03 | Low-data assets where applicable; accessibility labels | New | Mobile UX | Patient Mobile App | Mobile, QA
781 | 216 | QA | 16 | PAT-26 | PAT-26.04 | QA both platforms: Device check matches website/API status; no local fake paid/signed state | Regression | QA | Patient Mobile App | Mobile, QA
782 | 80 | Mobile | 16 | PAT-27 | PAT-27.01 | UI: Waiting room screens (empty, loading, error, offline) | New | Mobile UI | Patient Mobile App | Mobile, QA
783 | 81 | Mobile | 16 | PAT-27 | PAT-27.02 | Wire to the Phase 8–15 API for: Waiting room | New | Mobile client | Patient Mobile App | Mobile, QA
784 | 82 | Mobile | 16 | PAT-27 | PAT-27.03 | Low-data assets where applicable; accessibility labels | New | Mobile UX | Patient Mobile App | Mobile, QA
785 | 217 | QA | 16 | PAT-27 | PAT-27.04 | QA both platforms: Waiting room matches website/API status; no local fake paid/signed state | Regression | QA | Patient Mobile App | Mobile, QA
786 | 83 | Mobile | 16 | PAT-28 | PAT-28.01 | UI: Live video consultation screens (empty, loading, error, offline) | New | Mobile UI | Patient Mobile App | Mobile, QA
787 | 84 | Mobile | 16 | PAT-28 | PAT-28.02 | Wire to the Phase 8–15 API for: Live video consultation | New | Mobile client | Patient Mobile App | Mobile, QA
788 | 85 | Mobile | 16 | PAT-28 | PAT-28.03 | Low-data assets where applicable; accessibility labels | New | Mobile UX | Patient Mobile App | Mobile, QA
789 | 218 | QA | 16 | PAT-28 | PAT-28.04 | QA both platforms: Live video consultation matches website/API status; no local fake paid/signed state | Regression | QA | Patient Mobile App | Mobile, QA
790 | 86 | Mobile | 16 | PAT-29 | PAT-29.01 | UI: Recording consent screens (empty, loading, error, offline) | New | Mobile UI | Patient Mobile App | Mobile, QA
791 | 87 | Mobile | 16 | PAT-29 | PAT-29.02 | Wire to the Phase 8–15 API for: Recording consent | New | Mobile client | Patient Mobile App | Mobile, QA
792 | 88 | Mobile | 16 | PAT-29 | PAT-29.03 | Low-data assets where applicable; accessibility labels | New | Mobile UX | Patient Mobile App | Mobile, QA
793 | 219 | QA | 16 | PAT-29 | PAT-29.04 | QA both platforms: Recording consent matches website/API status; no local fake paid/signed state | Regression | QA | Patient Mobile App | Mobile, QA
794 | 89 | Mobile | 16 | PAT-30 | PAT-30.01 | UI: Fallback & join failure handling screens (empty, loading, error, offline) | New | Mobile UI | Patient Mobile App | Mobile, QA
795 | 90 | Mobile | 16 | PAT-30 | PAT-30.02 | Wire to the Phase 8–15 API for: Fallback & join failure handling | New | Mobile client | Patient Mobile App | Mobile, QA
796 | 91 | Mobile | 16 | PAT-30 | PAT-30.03 | Low-data assets where applicable; accessibility labels | New | Mobile UX | Patient Mobile App | Mobile, QA
797 | 220 | QA | 16 | PAT-30 | PAT-30.04 | QA both platforms: Fallback & join failure handling matches website/API status; no local fake paid/signed state | Regression | QA | Patient Mobile App | Mobile, QA
798 | 92 | Mobile | 16 | PAT-31 | PAT-31.01 | UI: Case-linked chat screens (empty, loading, error, offline) | New | Mobile UI | Patient Mobile App | Mobile, QA
799 | 93 | Mobile | 16 | PAT-31 | PAT-31.02 | Wire to the Phase 8–15 API for: Case-linked chat | New | Mobile client | Patient Mobile App | Mobile, QA
800 | 94 | Mobile | 16 | PAT-31 | PAT-31.03 | Low-data assets where applicable; accessibility labels | New | Mobile UX | Patient Mobile App | Mobile, QA
801 | 221 | QA | 16 | PAT-31 | PAT-31.04 | QA both platforms: Case-linked chat matches website/API status; no local fake paid/signed state | Regression | QA | Patient Mobile App | Mobile, QA
802 | 95 | Mobile | 16 | PAT-32 | PAT-32.01 | UI: Consultation summary screens (empty, loading, error, offline) | New | Mobile UI | Patient Mobile App | Mobile, QA
803 | 96 | Mobile | 16 | PAT-32 | PAT-32.02 | Wire to the Phase 8–15 API for: Consultation summary | New | Mobile client | Patient Mobile App | Mobile, QA
804 | 97 | Mobile | 16 | PAT-32 | PAT-32.03 | Low-data assets where applicable; accessibility labels | New | Mobile UX | Patient Mobile App | Mobile, QA
805 | 222 | QA | 16 | PAT-32 | PAT-32.04 | QA both platforms: Consultation summary matches website/API status; no local fake paid/signed state | Regression | QA | Patient Mobile App | Mobile, QA
806 | 98 | Mobile | 16 | PAT-33 | PAT-33.01 | UI: Rejoin after dropped call screens (empty, loading, error, offline) | New | Mobile UI | Patient Mobile App | Mobile, QA
807 | 99 | Mobile | 16 | PAT-33 | PAT-33.02 | Wire to the Phase 8–15 API for: Rejoin after dropped call | New | Mobile client | Patient Mobile App | Mobile, QA
808 | 100 | Mobile | 16 | PAT-33 | PAT-33.03 | Low-data assets where applicable; accessibility labels | New | Mobile UX | Patient Mobile App | Mobile, QA
809 | 223 | QA | 16 | PAT-33 | PAT-33.04 | QA both platforms: Rejoin after dropped call matches website/API status; no local fake paid/signed state | Regression | QA | Patient Mobile App | Mobile, QA
810 | 101 | Mobile | 16 | PAT-34 | PAT-34.01 | UI: Records timeline screens (empty, loading, error, offline) | New | Mobile UI | Patient Mobile App | Mobile, QA
811 | 102 | Mobile | 16 | PAT-34 | PAT-34.02 | Wire to the Phase 8–15 API for: Records timeline | New | Mobile client | Patient Mobile App | Mobile, QA
812 | 103 | Mobile | 16 | PAT-34 | PAT-34.03 | Low-data assets where applicable; accessibility labels | New | Mobile UX | Patient Mobile App | Mobile, QA
813 | 224 | QA | 16 | PAT-34 | PAT-34.04 | QA both platforms: Records timeline matches website/API status; no local fake paid/signed state | Regression | QA | Patient Mobile App | Mobile, QA
814 | 104 | Mobile | 16 | PAT-35 | PAT-35.01 | UI: Consultation note screens (empty, loading, error, offline) | New | Mobile UI | Patient Mobile App | Mobile, QA
815 | 105 | Mobile | 16 | PAT-35 | PAT-35.02 | Wire to the Phase 8–15 API for: Consultation note | New | Mobile client | Patient Mobile App | Mobile, QA
816 | 106 | Mobile | 16 | PAT-35 | PAT-35.03 | Low-data assets where applicable; accessibility labels | New | Mobile UX | Patient Mobile App | Mobile, QA
817 | 225 | QA | 16 | PAT-35 | PAT-35.04 | QA both platforms: Consultation note matches website/API status; no local fake paid/signed state | Regression | QA | Patient Mobile App | Mobile, QA
818 | 107 | Mobile | 16 | PAT-36 | PAT-36.01 | UI: Signed digital prescription screens (empty, loading, error, offline) | New | Mobile UI | Patient Mobile App | Mobile, QA
819 | 108 | Mobile | 16 | PAT-36 | PAT-36.02 | Wire to the Phase 8–15 API for: Signed digital prescription | New | Mobile client | Patient Mobile App | Mobile, QA
820 | 109 | Mobile | 16 | PAT-36 | PAT-36.03 | Low-data assets where applicable; accessibility labels | New | Mobile UX | Patient Mobile App | Mobile, QA
821 | 226 | QA | 16 | PAT-36 | PAT-36.04 | QA both platforms: Signed digital prescription matches website/API status; no local fake paid/signed state | Regression | QA | Patient Mobile App | Mobile, QA
822 | 110 | Mobile | 16 | PAT-37 | PAT-37.01 | UI: Document upload screens (empty, loading, error, offline) | New | Mobile UI | Patient Mobile App | Mobile, QA
823 | 111 | Mobile | 16 | PAT-37 | PAT-37.02 | Wire to the Phase 8–15 API for: Document upload | New | Mobile client | Patient Mobile App | Mobile, QA
824 | 112 | Mobile | 16 | PAT-37 | PAT-37.03 | Low-data assets where applicable; accessibility labels | New | Mobile UX | Patient Mobile App | Mobile, QA
825 | 227 | QA | 16 | PAT-37 | PAT-37.04 | QA both platforms: Document upload matches website/API status; no local fake paid/signed state | Regression | QA | Patient Mobile App | Mobile, QA
826 | 113 | Mobile | 16 | PAT-38 | PAT-38.01 | UI: Follow-up plan & tasks screens (empty, loading, error, offline) | New | Mobile UI | Patient Mobile App | Mobile, QA
827 | 114 | Mobile | 16 | PAT-38 | PAT-38.02 | Wire to the Phase 8–15 API for: Follow-up plan & tasks | New | Mobile client | Patient Mobile App | Mobile, QA
828 | 115 | Mobile | 16 | PAT-38 | PAT-38.03 | Low-data assets where applicable; accessibility labels | New | Mobile UX | Patient Mobile App | Mobile, QA
829 | 228 | QA | 16 | PAT-38 | PAT-38.04 | QA both platforms: Follow-up plan & tasks matches website/API status; no local fake paid/signed state | Regression | QA | Patient Mobile App | Mobile, QA
830 | 116 | Mobile | 16 | PAT-39 | PAT-39.01 | UI: Symptom diary screens (empty, loading, error, offline) | New | Mobile UI | Patient Mobile App | Mobile, QA
831 | 117 | Mobile | 16 | PAT-39 | PAT-39.02 | Wire to the Phase 8–15 API for: Symptom diary | New | Mobile client | Patient Mobile App | Mobile, QA
832 | 118 | Mobile | 16 | PAT-39 | PAT-39.03 | Low-data assets where applicable; accessibility labels | New | Mobile UX | Patient Mobile App | Mobile, QA
833 | 229 | QA | 16 | PAT-39 | PAT-39.04 | QA both platforms: Symptom diary matches website/API status; no local fake paid/signed state | Regression | QA | Patient Mobile App | Mobile, QA
834 | 119 | Mobile | 16 | PAT-40 | PAT-40.01 | UI: Progress tracking screens (empty, loading, error, offline) | New | Mobile UI | Patient Mobile App | Mobile, QA
835 | 120 | Mobile | 16 | PAT-40 | PAT-40.02 | Wire to the Phase 8–15 API for: Progress tracking | New | Mobile client | Patient Mobile App | Mobile, QA
836 | 121 | Mobile | 16 | PAT-40 | PAT-40.03 | Low-data assets where applicable; accessibility labels | New | Mobile UX | Patient Mobile App | Mobile, QA
837 | 230 | QA | 16 | PAT-40 | PAT-40.04 | QA both platforms: Progress tracking matches website/API status; no local fake paid/signed state | Regression | QA | Patient Mobile App | Mobile, QA
838 | 122 | Mobile | 16 | PAT-41 | PAT-41.01 | UI: Medicines tab screens (empty, loading, error, offline) | New | Mobile UI | Patient Mobile App | Mobile, QA
839 | 123 | Mobile | 16 | PAT-41 | PAT-41.02 | Wire to the Phase 8–15 API for: Medicines tab | New | Mobile client | Patient Mobile App | Mobile, QA
840 | 124 | Mobile | 16 | PAT-41 | PAT-41.03 | Low-data assets where applicable; accessibility labels | New | Mobile UX | Patient Mobile App | Mobile, QA
841 | 231 | QA | 16 | PAT-41 | PAT-41.04 | QA both platforms: Medicines tab matches website/API status; no local fake paid/signed state | Regression | QA | Patient Mobile App | Mobile, QA
842 | 125 | Mobile | 16 | PAT-42 | PAT-42.01 | UI: Order start screens (empty, loading, error, offline) | New | Mobile UI | Patient Mobile App | Mobile, QA
843 | 126 | Mobile | 16 | PAT-42 | PAT-42.02 | Wire to the Phase 8–15 API for: Order start | New | Mobile client | Patient Mobile App | Mobile, QA
844 | 127 | Mobile | 16 | PAT-42 | PAT-42.03 | Low-data assets where applicable; accessibility labels | New | Mobile UX | Patient Mobile App | Mobile, QA
845 | 232 | QA | 16 | PAT-42 | PAT-42.04 | QA both platforms: Order start matches website/API status; no local fake paid/signed state | Regression | QA | Patient Mobile App | Mobile, QA
846 | 128 | Mobile | 16 | PAT-43 | PAT-43.01 | UI: Pharmacy selection & quote screens (empty, loading, error, offline) | New | Mobile UI | Patient Mobile App | Mobile, QA
847 | 129 | Mobile | 16 | PAT-43 | PAT-43.02 | Wire to the Phase 8–15 API for: Pharmacy selection & quote | New | Mobile client | Patient Mobile App | Mobile, QA
848 | 130 | Mobile | 16 | PAT-43 | PAT-43.03 | Low-data assets where applicable; accessibility labels | New | Mobile UX | Patient Mobile App | Mobile, QA
849 | 233 | QA | 16 | PAT-43 | PAT-43.04 | QA both platforms: Pharmacy selection & quote matches website/API status; no local fake paid/signed state | Regression | QA | Patient Mobile App | Mobile, QA
850 | 131 | Mobile | 16 | PAT-44 | PAT-44.01 | UI: Order review & consent screens (empty, loading, error, offline) | New | Mobile UI | Patient Mobile App | Mobile, QA
851 | 132 | Mobile | 16 | PAT-44 | PAT-44.02 | Wire to the Phase 8–15 API for: Order review & consent | New | Mobile client | Patient Mobile App | Mobile, QA
852 | 133 | Mobile | 16 | PAT-44 | PAT-44.03 | Low-data assets where applicable; accessibility labels | New | Mobile UX | Patient Mobile App | Mobile, QA
853 | 234 | QA | 16 | PAT-44 | PAT-44.04 | QA both platforms: Order review & consent matches website/API status; no local fake paid/signed state | Regression | QA | Patient Mobile App | Mobile, QA
854 | 134 | Mobile | 16 | PAT-45 | PAT-45.01 | UI: Order tracking screens (empty, loading, error, offline) | New | Mobile UI | Patient Mobile App | Mobile, QA
855 | 135 | Mobile | 16 | PAT-45 | PAT-45.02 | Wire to the Phase 8–15 API for: Order tracking | New | Mobile client | Patient Mobile App | Mobile, QA
856 | 136 | Mobile | 16 | PAT-45 | PAT-45.03 | Low-data assets where applicable; accessibility labels | New | Mobile UX | Patient Mobile App | Mobile, QA
857 | 235 | QA | 16 | PAT-45 | PAT-45.04 | QA both platforms: Order tracking matches website/API status; no local fake paid/signed state | Regression | QA | Patient Mobile App | Mobile, QA
858 | 137 | Mobile | 16 | PAT-46 | PAT-46.01 | UI: Order detail & refill screens (empty, loading, error, offline) | New | Mobile UI | Patient Mobile App | Mobile, QA
859 | 138 | Mobile | 16 | PAT-46 | PAT-46.02 | Wire to the Phase 8–15 API for: Order detail & refill | New | Mobile client | Patient Mobile App | Mobile, QA
860 | 139 | Mobile | 16 | PAT-46 | PAT-46.03 | Low-data assets where applicable; accessibility labels | New | Mobile UX | Patient Mobile App | Mobile, QA
861 | 236 | QA | 16 | PAT-46 | PAT-46.04 | QA both platforms: Order detail & refill matches website/API status; no local fake paid/signed state | Regression | QA | Patient Mobile App | Mobile, QA
862 | 140 | Mobile | 16 | PAT-47 | PAT-47.01 | UI: Write a review screens (empty, loading, error, offline) | New | Mobile UI | Patient Mobile App | Mobile, QA
863 | 141 | Mobile | 16 | PAT-47 | PAT-47.02 | Wire to the Phase 8–15 API for: Write a review | New | Mobile client | Patient Mobile App | Mobile, QA
864 | 142 | Mobile | 16 | PAT-47 | PAT-47.03 | Low-data assets where applicable; accessibility labels | New | Mobile UX | Patient Mobile App | Mobile, QA
865 | 237 | QA | 16 | PAT-47 | PAT-47.04 | QA both platforms: Write a review matches website/API status; no local fake paid/signed state | Regression | QA | Patient Mobile App | Mobile, QA
866 | 143 | Mobile | 16 | PAT-48 | PAT-48.01 | UI: My reviews & appeal screens (empty, loading, error, offline) | New | Mobile UI | Patient Mobile App | Mobile, QA
867 | 144 | Mobile | 16 | PAT-48 | PAT-48.02 | Wire to the Phase 8–15 API for: My reviews & appeal | New | Mobile client | Patient Mobile App | Mobile, QA
868 | 145 | Mobile | 16 | PAT-48 | PAT-48.03 | Low-data assets where applicable; accessibility labels | New | Mobile UX | Patient Mobile App | Mobile, QA
869 | 238 | QA | 16 | PAT-48 | PAT-48.04 | QA both platforms: My reviews & appeal matches website/API status; no local fake paid/signed state | Regression | QA | Patient Mobile App | Mobile, QA
870 | 146 | Mobile | 16 | PAT-49 | PAT-49.01 | UI: Payments & refunds screens (empty, loading, error, offline) | New | Mobile UI | Patient Mobile App | Mobile, QA
871 | 147 | Mobile | 16 | PAT-49 | PAT-49.02 | Wire to the Phase 8–15 API for: Payments & refunds | New | Mobile client | Patient Mobile App | Mobile, QA
872 | 148 | Mobile | 16 | PAT-49 | PAT-49.03 | Low-data assets where applicable; accessibility labels | New | Mobile UX | Patient Mobile App | Mobile, QA
873 | 239 | QA | 16 | PAT-49 | PAT-49.04 | QA both platforms: Payments & refunds matches website/API status; no local fake paid/signed state | Regression | QA | Patient Mobile App | Mobile, QA
874 | 149 | Mobile | 16 | PAT-50 | PAT-50.01 | UI: Profile & settings screens (empty, loading, error, offline) | New | Mobile UI | Patient Mobile App | Mobile, QA
875 | 150 | Mobile | 16 | PAT-50 | PAT-50.02 | Wire to the Phase 8–15 API for: Profile & settings | New | Mobile client | Patient Mobile App | Mobile, QA
876 | 151 | Mobile | 16 | PAT-50 | PAT-50.03 | Low-data assets where applicable; accessibility labels | New | Mobile UX | Patient Mobile App | Mobile, QA
877 | 240 | QA | 16 | PAT-50 | PAT-50.04 | QA both platforms: Profile & settings matches website/API status; no local fake paid/signed state | Regression | QA | Patient Mobile App | Mobile, QA
878 | 152 | Mobile | 16 | PAT-51 | PAT-51.01 | UI: Consent centre & data rights screens (empty, loading, error, offline) | New | Mobile UI | Patient Mobile App | Mobile, QA
879 | 153 | Mobile | 16 | PAT-51 | PAT-51.02 | Wire to the Phase 8–15 API for: Consent centre & data rights | New | Mobile client | Patient Mobile App | Mobile, QA
880 | 154 | Mobile | 16 | PAT-51 | PAT-51.03 | Low-data assets where applicable; accessibility labels | New | Mobile UX | Patient Mobile App | Mobile, QA
881 | 241 | QA | 16 | PAT-51 | PAT-51.04 | QA both platforms: Consent centre & data rights matches website/API status; no local fake paid/signed state | Regression | QA | Patient Mobile App | Mobile, QA
882 | 155 | Mobile | 16 | PAT-52 | PAT-52.01 | UI: Notifications centre screens (empty, loading, error, offline) | New | Mobile UI | Patient Mobile App | Mobile, QA
883 | 156 | Mobile | 16 | PAT-52 | PAT-52.02 | Wire to the Phase 8–15 API for: Notifications centre | New | Mobile client | Patient Mobile App | Mobile, QA
884 | 157 | Mobile | 16 | PAT-52 | PAT-52.03 | Low-data assets where applicable; accessibility labels | New | Mobile UX | Patient Mobile App | Mobile, QA
885 | 242 | QA | 16 | PAT-52 | PAT-52.04 | QA both platforms: Notifications centre matches website/API status; no local fake paid/signed state | Regression | QA | Patient Mobile App | Mobile, QA
886 | 158 | Mobile | 16 | PAT-53 | PAT-53.01 | UI: Help centre & support tickets screens (empty, loading, error, offline) | New | Mobile UI | Patient Mobile App | Mobile, QA
887 | 159 | Mobile | 16 | PAT-53 | PAT-53.02 | Wire to the Phase 8–15 API for: Help centre & support tickets | New | Mobile client | Patient Mobile App | Mobile, QA
888 | 160 | Mobile | 16 | PAT-53 | PAT-53.03 | Low-data assets where applicable; accessibility labels | New | Mobile UX | Patient Mobile App | Mobile, QA
889 | 243 | QA | 16 | PAT-53 | PAT-53.04 | QA both platforms: Help centre & support tickets matches website/API status; no local fake paid/signed state | Regression | QA | Patient Mobile App | Mobile, QA
890 | 161 | Mobile | 16 | PAT-54 | PAT-54.01 | UI: Physical clinic appointment screens (empty, loading, error, offline) | New | Mobile UI | Patient Mobile App | Mobile, QA
891 | 162 | Mobile | 16 | PAT-54 | PAT-54.02 | Wire to the Phase 8–15 API for: Physical clinic appointment | New | Mobile client | Patient Mobile App | Mobile, QA
892 | 163 | Mobile | 16 | PAT-54 | PAT-54.03 | Low-data assets where applicable; accessibility labels | New | Mobile UX | Patient Mobile App | Mobile, QA
893 | 244 | QA | 16 | PAT-54 | PAT-54.04 | QA both platforms: Physical clinic appointment matches website/API status; no local fake paid/signed state | Regression | QA | Patient Mobile App | Mobile, QA
894 | 164 | Mobile | 16 | PAT-55 | PAT-55.01 | UI: Assisted booking screens (empty, loading, error, offline) | New | Mobile UI | Patient Mobile App | Mobile, QA
895 | 165 | Mobile | 16 | PAT-55 | PAT-55.02 | Wire to the Phase 8–15 API for: Assisted booking | New | Mobile client | Patient Mobile App | Mobile, QA
896 | 166 | Mobile | 16 | PAT-55 | PAT-55.03 | Low-data assets where applicable; accessibility labels | New | Mobile UX | Patient Mobile App | Mobile, QA
897 | 245 | QA | 16 | PAT-55 | PAT-55.04 | QA both platforms: Assisted booking matches website/API status; no local fake paid/signed state | Regression | QA | Patient Mobile App | Mobile, QA
898 | 167 | Mobile | 16 | PAT-56 | PAT-56.01 | UI: Low-data mode screens (empty, loading, error, offline) | New | Mobile UI | Patient Mobile App | Mobile, QA
899 | 168 | Mobile | 16 | PAT-56 | PAT-56.02 | Wire to the Phase 8–15 API for: Low-data mode | New | Mobile client | Patient Mobile App | Mobile, QA
900 | 169 | Mobile | 16 | PAT-56 | PAT-56.03 | Low-data assets where applicable; accessibility labels | New | Mobile UX | Patient Mobile App | Mobile, QA
901 | 246 | QA | 16 | PAT-56 | PAT-56.04 | QA both platforms: Low-data mode matches website/API status; no local fake paid/signed state | Regression | QA | Patient Mobile App | Mobile, QA
902 | 170 | Mobile | 16 | PAT-57 | PAT-57.01 | UI: Push notifications screens (empty, loading, error, offline) | New | Mobile UI | Patient Mobile App | Mobile, QA
903 | 171 | Mobile | 16 | PAT-57 | PAT-57.02 | Wire to the Phase 8–15 API for: Push notifications | New | Mobile client | Patient Mobile App | Mobile, QA
904 | 172 | Mobile | 16 | PAT-57 | PAT-57.03 | Low-data assets where applicable; accessibility labels | New | Mobile UX | Patient Mobile App | Mobile, QA
905 | 247 | QA | 16 | PAT-57 | PAT-57.04 | QA both platforms: Push notifications matches website/API status; no local fake paid/signed state | Regression | QA | Patient Mobile App | Mobile, QA
906 | 173 | Mobile | 16 | PAT-58 | PAT-58.01 | CI: iOS + Android release builds; env pointing to .NET 8 | New | Mobile | Patient Mobile App | Mobile, QA
907 | 248 | QA | 16 | PAT-58 | PAT-58.02 | Parity QA spreadsheet: each PAT-01..57 on both OS | Regression | QA | Patient Mobile App | Mobile, QA
908 | 174 | Mobile | 16 | PAT-58 | PAT-58.03 | Crashlytics/Sentry equivalent for patient app | New Integration | Mobile | Patient Mobile App | Mobile, QA
909 | 175 | Mobile | 17 | DMO-01 | DMO-01.01 | Login screen (password or OTP-to-registered mobile) | New | Mobile UI | Doctor Mobile App | Mobile, QA
910 | 176 | Mobile | 17 | DMO-01 | DMO-01.02 | Call same Login API; store JWT securely (Keychain/Keystore) | New | Mobile client | Doctor Mobile App | Mobile, QA
911 | 177 | Mobile | 17 | DMO-01 | DMO-01.03 | Expired session → re-login; no case-taking entry point | New | Mobile UX | Doctor Mobile App | Mobile, QA
912 | 249 | QA | 17 | DMO-01 | DMO-01.04 | QA: same DoctorId as web; reception accounts must not open doctor clinical actions | Regression | QA | Doctor Mobile App | Mobile, QA
913 | 178 | Mobile | 17 | DMO-02 | DMO-02.01 | Onboarding screens | New | Mobile UI | Doctor Mobile App | Mobile, QA
914 | 179 | Mobile | 17 | DMO-02 | DMO-02.02 | Confirm number against profile | New | Mobile client | Doctor Mobile App | Mobile, QA
915 | 180 | Mobile | 17 | DMO-02 | DMO-02.03 | Skip vs required steps documented | New | Mobile UX | Doctor Mobile App | Mobile, QA
916 | 250 | QA | 17 | DMO-02 | DMO-02.04 | QA: number mismatch blocked | Regression | QA | Doctor Mobile App | Mobile, QA
917 | 181 | Mobile | 17 | DMO-03 | DMO-03.01 | Permission primer + settings CTA | New | Mobile UI | Doctor Mobile App | Mobile, QA
918 | 182 | Mobile | 17 | DMO-03 | DMO-03.02 | Register FCM/APNs token (COM-03) | New | Mobile client | Doctor Mobile App | Mobile, QA
919 | 183 | Mobile | 17 | DMO-03 | DMO-03.03 | Denied-state UX | New | Mobile UX | Doctor Mobile App | Mobile, QA
920 | 251 | QA | 17 | DMO-03 | DMO-03.04 | QA: deny each permission independently | Regression | QA | Doctor Mobile App | Mobile, QA
921 | 184 | Mobile | 17 | DMO-04 | DMO-04.01 | TodayQueue screen | New | Mobile UI | Doctor Mobile App | Mobile, QA
922 | 185 | Mobile | 17 | DMO-04 | DMO-04.02 | Existing appointment list APIs | New | Mobile client | Doctor Mobile App | Mobile, QA
923 | 186 | Mobile | 17 | DMO-04 | DMO-04.03 | Pull-to-refresh; empty Sunday | New | Mobile UX | Doctor Mobile App | Mobile, QA
924 | 252 | QA | 17 | DMO-04 | DMO-04.04 | QA: parity with web counts | Regression | QA | Doctor Mobile App | Mobile, QA
925 | 187 | Mobile | 17 | DMO-05 | DMO-05.01 | Availability + hours screens | New | Mobile UI | Doctor Mobile App | Mobile, QA
926 | 188 | Mobile | 17 | DMO-05 | DMO-05.02 | TEL-01 + APT-07 APIs (hours read/edit policy: edit hours may stay web-only if product decides — PDF says set working hours so include) | New | Mobile client | Doctor Mobile App | Mobile, QA
927 | 189 | Mobile | 17 | DMO-05 | DMO-05.03 | Offline banner | New | Mobile UX | Doctor Mobile App | Mobile, QA
928 | 253 | QA | 17 | DMO-05 | DMO-05.04 | QA: web and app status match within heartbeat | Regression | QA | Doctor Mobile App | Mobile, QA
929 | 190 | Mobile | 17 | DMO-06 | DMO-06.01 | Notification handling + deep links into queue/refill/join | New | Mobile UI | Doctor Mobile App | Mobile, QA
930 | 191 | Mobile | 17 | DMO-06 | DMO-06.02 | Device register | New | Mobile client | Doctor Mobile App | Mobile, QA
931 | 192 | Mobile | 17 | DMO-06 | DMO-06.03 | Foreground in-app banner | New | Mobile UX | Doctor Mobile App | Mobile, QA
932 | 254 | QA | 17 | DMO-06 | DMO-06.04 | QA: each event type deep link | Regression | QA | Doctor Mobile App | Mobile, QA
933 | 193 | Mobile | 17 | DMO-07 | DMO-07.01 | PatientCard read-only | New | Mobile UI | Doctor Mobile App | Mobile, QA
934 | 194 | Mobile | 17 | DMO-07 | DMO-07.02 | Context API (name, age, CC, last visit, payment, tele) | New | Mobile client | Doctor Mobile App | Mobile, QA
935 | 195 | Mobile | 17 | DMO-07 | DMO-07.03 | Do not ship case-taking tabs | New | Mobile UX | Doctor Mobile App | Mobile, QA
936 | 255 | QA | 17 | DMO-07 | DMO-07.04 | QA: repertory endpoints never called from app | Regression | QA | Doctor Mobile App | Mobile, QA
937 | 196 | Mobile | 17 | DMO-08 | DMO-08.01 | VideoRoom | New | Mobile UI | Doctor Mobile App | Mobile, QA
938 | 197 | Mobile | 17 | DMO-08 | DMO-08.02 | Tele session tokens | New | Mobile client | Doctor Mobile App | Mobile, QA
939 | 198 | Mobile | 17 | DMO-08 | DMO-08.03 | Audio-only fallback | New | Mobile UX | Doctor Mobile App | Mobile, QA
940 | 256 | QA | 17 | DMO-08 | DMO-08.04 | QA: web patient + app doctor | Regression | QA | Doctor Mobile App | Mobile, QA
941 | 199 | Mobile | 17 | DMO-09 | DMO-09.01 | RefillInbox + RefillDetail | New | Mobile UI | Doctor Mobile App | Mobile, QA
942 | 200 | Mobile | 17 | DMO-09 | DMO-09.02 | Approve/Reject APIs | New | Mobile client | Doctor Mobile App | Mobile, QA
943 | 201 | Mobile | 17 | DMO-09 | DMO-09.03 | Show codes vs names per policy (doctor sees names) | New | Mobile UX | Doctor Mobile App | Mobile, QA
944 | 257 | QA | 17 | DMO-09 | DMO-09.04 | QA: reject reason; cannot edit snapshot | Regression | QA | Doctor Mobile App | Mobile, QA
945 | 202 | Mobile | 17 | DMO-10 | DMO-10.01 | Earnings screens | New | Mobile UI | Doctor Mobile App | Mobile, QA
946 | 203 | Mobile | 17 | DMO-10 | DMO-10.02 | GET Earnings/Summary | New | Mobile client | Doctor Mobile App | Mobile, QA
947 | 204 | Mobile | 17 | DMO-10 | DMO-10.03 | Empty first week | New | Mobile UX | Doctor Mobile App | Mobile, QA
948 | 258 | QA | 17 | DMO-10 | DMO-10.04 | QA: matches /account figures ± rounding | Regression | QA | Doctor Mobile App | Mobile, QA
949 | 205 | Mobile | 17 | DMO-11 | DMO-11.01 | Offline/error screens | New | Mobile UI | Doctor Mobile App | Mobile, QA
950 | 206 | Mobile | 17 | DMO-11 | DMO-11.02 | 401 interceptor → logout API | New | Mobile client | Doctor Mobile App | Mobile, QA
951 | 207 | Mobile | 17 | DMO-11 | DMO-11.03 | No silent retry of payments | New | Mobile UX | Doctor Mobile App | Mobile, QA
952 | 259 | QA | 17 | DMO-11 | DMO-11.04 | QA: airplane mode on join | Regression | QA | Doctor Mobile App | Mobile, QA
953 | 208 | Mobile | 17 | DMO-12 | DMO-12.01 | Integrate Crashlytics/Sentry; map to doctorId hashed | New Integration | Mobile | Doctor Mobile App | Mobile, QA
954 | 260 | QA | 17 | DMO-12 | DMO-12.02 | QA: simulated crash + join fail event | Regression | QA | Doctor Mobile App | Mobile, QA
955 | 209 | Mobile | 17 | DMO-13 | DMO-13.01 | Release builds both OS | New | Mobile | Doctor Mobile App | Mobile, QA
956 | 261 | QA | 17 | DMO-13 | DMO-13.02 | Parity QA DMO-01..12 both OS | Regression | QA | Doctor Mobile App | Mobile, QA
957 | 361 | Web | 18 | RPT-01 | RPT-01.01 | No ecommerce tables | Existing Improvement | Database | Admin Portal | Web, UI, QA
958 | 362 | Web | 18 | RPT-01 | RPT-01.02 | GET /api/AdminDashboard/Overview | Existing Improvement | API | Admin Portal | Web, UI, QA
959 | 127 | UI | 18 | RPT-01 | RPT-01.03 | Replace pages/Admin/Dashboard; getHomeDashboardPath → /admin/dashboard | Existing Improvement | Web SPA | Admin Portal | Web, UI, QA
960 | 262 | QA | 18 | RPT-01 | RPT-01.04 | QA: login as admin never shows fake store visits | Regression | QA | Admin Portal | Web, UI, QA
961 | 363 | Web | 18 | RPT-02 | RPT-02.01 | No new warehouse required for v1 | Existing Improvement | Database | Doctor Web | Web, UI, QA
962 | 364 | Web | 18 | RPT-02 | RPT-02.02 | Extend GetPatientStatsCharts with VisitType/ConsultMode | Existing Improvement | API | Doctor Web | Web, UI, QA
963 | 128 | UI | 18 | RPT-02 | RPT-02.03 | Dashboard charts consume new series | Existing Improvement | Web SPA | Doctor Web | Web, UI, QA
964 | 263 | QA | 18 | RPT-02 | RPT-02.04 | QA: empty new clinic | Regression | QA | Doctor Web | Web, UI, QA
965 | 365 | Web | 18 | RPT-03 | RPT-03.01 | Queries on VisitType + FollowUpTask | New | Database | Doctor Web | Web, UI, QA
966 | 366 | Web | 18 | RPT-03 | RPT-03.02 | GET FollowUpDue, FollowUpSummary | New | API | Doctor Web | Web, UI, QA
967 | 129 | UI | 18 | RPT-03 | RPT-03.03 | /doctor/follow-up-analysis | New | Web SPA | Doctor Web | Web, UI, QA
968 | 264 | QA | 18 | RPT-03 | RPT-03.04 | QA: overdue vs due buckets | Regression | QA | Doctor Web | Web, UI, QA
969 | 367 | Web | 18 | RPT-04 | RPT-04.01 | Aggregate APIs beyond GetPatientStatsCharts | New | Database | Doctor Web | Web, UI, QA
970 | 368 | Web | 18 | RPT-04 | RPT-04.02 | GET ClinicPerformance | New | API | Doctor Web | Web, UI, QA
971 | 130 | UI | 18 | RPT-04 | RPT-04.03 | /doctor/clinic-performance | New | Web SPA | Doctor Web | Web, UI, QA
972 | 265 | QA | 18 | RPT-04 | RPT-04.04 | QA: cancelled excluded from completed; revenue uses ledger not client | Regression | QA | Doctor Web | Web, UI, QA
973 | 369 | Web | 18 | RPT-05 | RPT-05.01 | CSV/PDF export of FIN-02 query | New | API | Admin + Account | Web, UI, QA
974 | 131 | UI | 18 | RPT-05 | RPT-05.02 | Report UI on admin/account recon screens | New | Web SPA | Admin + Account | Web, UI, QA
975 | 266 | QA | 18 | RPT-05 | RPT-05.03 | QA: unmatched rows included | Regression | QA | Admin + Account | Web, UI, QA
976 | 370 | Web | 18 | RPT-06 | RPT-06.01 | Export settlement runs + payout register | New | API | Account | Web, UI, QA
977 | 132 | UI | 18 | RPT-06 | RPT-06.02 | Report UI | New | Web SPA | Account | Web, UI, QA
978 | 267 | QA | 18 | RPT-06 | RPT-06.03 | QA: pharmacy lines appear only after HomeoMeds | Regression | QA | Account | Web, UI, QA
979 | 371 | Web | 18 | RPT-07 | RPT-07.01 | Confirm CA format; implement export if not already in FIN-08 | New | API | Account | Web, QA
980 | 268 | QA | 18 | RPT-07 | RPT-07.02 | QA: number series gaps flagged | Regression | QA | Account | Web, QA
981 | 372 | Web | 18 | RPT-08 | RPT-08.01 | Reuse earnings API | New | Database | Doctor Web + App | Web, UI, QA
982 | 373 | Web | 18 | RPT-08 | RPT-08.02 | GET Earnings/Summary already for app — add if missing date buckets | New | API | Doctor Web + App | Web, UI, QA
983 | 133 | UI | 18 | RPT-08 | RPT-08.03 | /doctor/earnings | New | Web SPA | Doctor Web + App | Web, UI, QA
984 | 269 | QA | 18 | RPT-08 | RPT-08.04 | QA: payout pending vs paid | Regression | QA | Doctor Web + App | Web, UI, QA
985 | 374 | Web | 18 | RPT-09 | RPT-09.01 | Aggregates on MedicineOrder | New | Database | Admin + Account | Web, UI, QA
986 | 375 | Web | 18 | RPT-09 | RPT-09.02 | GET medicine order report | New | API | Admin + Account | Web, UI, QA
987 | 134 | UI | 18 | RPT-09 | RPT-09.03 | Admin/account report page | New | Web SPA | Admin + Account | Web, UI, QA
988 | 270 | QA | 18 | RPT-09 | RPT-09.04 | QA: cancelled orders not counted as delivered | Regression | QA | Admin + Account | Web, UI, QA
989 | 376 | Web | 18 | RPT-10 | RPT-10.01 | VerificationStatus on user/doctor list DTO | Existing Improvement | Database | Admin Portal | Web, UI, QA
990 | 377 | Web | 18 | RPT-10 | RPT-10.02 | User import/export APIs if missing | Existing Improvement | API | Admin Portal | Web, UI, QA
991 | 135 | UI | 18 | RPT-10 | RPT-10.03 | ListUser.js wire dead buttons; verification column | Existing Improvement | Web SPA | Admin Portal | Web, UI, QA
992 | 271 | QA | 18 | RPT-10 | RPT-10.04 | QA: export contains only permitted fields | Regression | QA | Admin Portal | Web, UI, QA
993 | 272 | QA | 19 | QA-01 | QA-01.01 | E2E: Reception creates patient+appt → Doctor board → sign eRx → Patient app sees codes → Pharmacy accept OTP → patient sees names+pay → Account ledger S2 and S5 | Regression | QA | All | QA
994 | 273 | QA | 19 | QA-01 | QA-01.02 | E2E: Patient app books+pays tele → doctor app join → summary+eRx → refill on doctor app | Regression | QA | All | QA
995 | 274 | QA | 19 | QA-01 | QA-01.03 | Negative: Admin cannot payout; Account cannot edit repertory | Regression | QA | All | QA
996 | 275 | QA | 19 | QA-02 | QA-02.01 | Traceability review: 01_PDF_Coverage every row has Main Task ID and final Status | Regression | QA | Programme | QA
997 | 276 | QA | 19 | QA-02 | QA-02.02 | Do not ship Velzon demo tickets/KYC/ecommerce as product | Regression | QA | Programme | QA
998 | 378 | Web | 19 | NFR-01 | NFR-01.01 | Rotate API secrets; keys in config/KeyVault; directory browsing remains off | Existing Modification | Security | All | Web, QA
999 | 277 | QA | 19 | NFR-01 | NFR-01.02 | Performance: slot lock under concurrent public booking | Regression | QA | All | Web, QA
1000 | 278 | QA | 19 | NFR-01 | NFR-01.03 | Patient low-data mode QA on 2G profile | Regression | QA | All | Web, QA

## 10_Dashboard
PLANNING COUNTS — exclusive track assignment from the master register
Sub-tasks by track
Track | Sub tasks
Web | 378
UI | 135
Mobile | 209
QA | 278
Work Type × Track
Work Type | Web | UI | Mobile | QA | Total
Existing | 52 | 0 | 0 | 51 | 103
Existing Improvement | 105 | 40 | 0 | 0 | 145
Existing Modification | 5 | 1 | 0 | 0 | 6
New | 187 | 94 | 207 | 0 | 488
New Integration | 17 | 0 | 2 | 0 | 19
Configuration | 2 | 0 | 0 | 0 | 2
Data Migration | 1 | 0 | 0 | 0 | 1
Client Decision | 9 | 0 | 0 | 0 | 9
Regression | 0 | 0 | 0 | 227 | 227
Phase × Track (sub-tasks)
Phase | Web | UI | Mobile | QA | Total
PRE | 11 | 0 | 0 | 0 | 11
0 | 24 | 6 | 1 | 10 | 41
1 | 56 | 1 | 0 | 28 | 85
2 | 37 | 10 | 0 | 20 | 67
3 | 18 | 5 | 0 | 10 | 33
4 | 19 | 5 | 0 | 9 | 33
5 | 18 | 9 | 0 | 12 | 39
6 | 23 | 8 | 0 | 11 | 42
7 | 21 | 10 | 0 | 11 | 42
8 | 14 | 6 | 0 | 7 | 27
9 | 15 | 13 | 0 | 12 | 40
10 | 17 | 8 | 0 | 10 | 35
11 | 21 | 11 | 0 | 12 | 44
12 | 12 | 5 | 0 | 5 | 22
13 | 10 | 7 | 0 | 7 | 24
14 | 25 | 14 | 0 | 16 | 55
15 | 19 | 8 | 0 | 10 | 37
18 | 17 | 9 | 0 | 10 | 36
19 | 1 | 0 | 0 | 7 | 8
16 | 0 | 0 | 173 | 58 | 231
17 | 0 | 0 | 35 | 13 | 48