## 00_Cover
HOMEOCENTRUM — MODULE REGISTER WITH EMPLOYEE + LAYER STATUS (LIVE SYNC)
1000 sub-tasks · edit yellow cells on M00–M19 · Frontend/Backend/Database/API/Mobile/Integration each has Scope + Status + Assigned · Master and Dashboard follow automatically
How to work this file (employees + layer status + sync)
1. Put real names on 00_Employees (yellow Name column). Keep “Unassigned”. Dropdowns on module sheets use those names.
2. EDIT on the module sheet (M05_Appointments, M17_Patient_Mobile, …). Yellow cells: Assigned To (lead), each function’s Status, each function’s Assigned, Notes.
3. Frontend / Backend / Database / API / Mobile / Integration: Scope Yes = this sub-task includes that work. Status N/A = not in this sub-task (Scope No). Status Not Started / In Progress / Done = remaining vs complete.
4. Change Frontend Status (or any layer Status) on the module sheet. 01_MASTER, 03_Web, 04_UI, 05_Mobile, 06_QA, 02_By_Module_Phase and 08_Dashboard update immediately (Excel formulas — no copy-paste).
5. Overall Status is calculated: all in-scope layers Done → Done; any Blocked → Blocked; any started but not all Done → In Progress; else Not Started. Do not type over Overall Status.
6. Layers Remaining = how many in-scope functions are not Done yet. Filter that column to see what is left in the module.
7. Same Sub Task ID is one row of work. Assign a lead plus a person per in-scope function (Frontend Assigned, API Assigned, …) when more than one employee works the row.
8. Do not type over Status on 01_MASTER or track sheets — those cells are live mirrors. Use “Open Module Sheet” to jump to the yellow editable row.
9. Develop sequentially inside a module (Web API → UI → Mobile → QA). Do not skip rows. Dashboard integrity must stay 1000.
10. Work Type (Existing / Existing Improvement / New / …) is the type of work, not completion. Completion is the six function Status columns.
Legend — function columns
Yes | Scope — this sub-task includes this function (Frontend/Backend/Database/API/Mobile/Integration).
No | Scope — not part of this sub-task. Status must stay N/A.
Not Started | In scope and remaining — not begun.
In Progress | In scope and remaining — someone is working it.
Done | In scope and complete.
Blocked | Cannot finish until a dependency or decision is cleared.
N/A | Not in scope for this row.
Yellow cell | Editable on the MODULE sheet only (assignment + layer Status).
Modules — open the sheet named here to assign people and mark layer Status
Code | Dev Module | Edit sheet | Sub tasks | Web | UI | Mobile | QA
M00 | PRE — Client gates | M00_PRE_Client_Gates | 11 | 11 | 0 | 0 | 0
M01 | Foundation & Security | M01_Foundation_Security | 41 | 24 | 6 | 1 | 10
M02 | Admin clinical masters | M02_Admin_Clinical | 85 | 56 | 1 | 0 | 28
M03 | Doctor clinical workspace | M03_Clinical_Workspace | 67 | 37 | 10 | 0 | 20
M04 | Doctor daily operations | M04_Doctor_Daily_Ops | 33 | 18 | 5 | 0 | 10
M05 | Appointments & scheduling | M05_Appointments | 40 | 23 | 6 | 0 | 11
M06 | Reception portal | M06_Reception | 39 | 18 | 9 | 0 | 12
M07 | Payment system | M07_Payments | 42 | 23 | 8 | 0 | 11
M08 | Account & finance | M08_Account_Finance | 44 | 22 | 10 | 0 | 12
M09 | Trust & verification | M09_Trust | 27 | 14 | 6 | 0 | 7
M10 | Patient website | M10_Patient_Website | 35 | 12 | 12 | 0 | 11
M11 | Digital prescription (eRx) | M11_Digital_eRx | 35 | 17 | 8 | 0 | 10
M12 | Telemedicine | M12_Telemedicine | 44 | 21 | 11 | 0 | 12
M13 | Communications | M13_Communications | 22 | 12 | 5 | 0 | 5
M14 | Support & help desk | M14_Support | 24 | 10 | 7 | 0 | 7
M15 | HomeoMeds | M15_HomeoMeds | 55 | 25 | 14 | 0 | 16
M16 | Patient continuity APIs | M16_Patient_APIs | 33 | 17 | 8 | 0 | 8
M17 | Patient mobile app | M17_Patient_Mobile | 231 | 0 | 0 | 173 | 58
M18 | Doctor mobile app | M18_Doctor_Mobile | 48 | 0 | 0 | 35 | 13
M19 | Reports, NFR & delivery gate | M19_Reports_NFR_Gate | 44 | 18 | 9 | 0 | 17

## 00_Employees
EMPLOYEES — type real names in column B (yellow). Keep row 3 as Unassigned. Google Sheets: open 00_Sheets_Dropdown once and connect the dropdowns. After that, a new name in column B appears on every module sheet by itself.
Emp ID | Name (shows in Assigned dropdowns) | Function | Track | Active
UNASSIGNED | Unassigned | Any | Any | Yes
E01 | Gourav Nikam | Frontend | UI | Yes
E02 | Digvijay Jadhav | Frontend | UI | Yes
E03 | Gourav Nikam | Backend | Web | Yes
E04 |  | Backend | Web | Yes
E05 | Gourav Nikam | Database | Web | Yes
E06 | Gourav Nikam | API | Web | Yes
E07 |  | API | Web | Yes
E08 | Pranav Bandekar | Mobile | Mobile | Yes
E09 |  | Mobile | Mobile | Yes
E10 | Gourav Nikam | Integration | Web | Yes
E11 |  | QA | QA | Yes
E12 |  | QA | QA | Yes
E13 | Gourav Nikam | Tech Lead | Any | Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes

## 00_Sheets_Dropdown
GOOGLE SHEETS — make Assigned To grow when you type a name in 00_Employees column B
Excel cannot do this after you upload to Google Sheets. Do this once in Google Sheets. After that, new names in column B appear by themselves.
1. This file must be open in Google Sheets (File → Import → Replace, or upload to Drive and open with Sheets).
2. Menu: Extensions → Apps Script.
3. Delete any code in Code.gs. Copy ALL of the script in cell A20 below. Paste it. Click Save (disk icon).
4. Function dropdown: choose setupAssignedDropdowns. Click Run. Click Allow / Review permissions for your Google account.
5. Reload this spreadsheet. You should see a Homeocentrum menu. You can also use Homeocentrum → Connect Assigned dropdowns to Employees.
6. Go to 00_Employees. Type a real name in a yellow cell in column B. Open M05_Appointments. Click Assigned To (lead) — the new name is in the list. No second setup.
Do not type Assigned names on Master. Edit on the module sheet. Keep row 3 as Unassigned.
Copy everything in A20 (the script). Paste into Apps Script.
/** * Homeocentrum — Assigned To dropdowns follow 00_Employees column B. * One-time setup in Google Sheets: * Extensions → Apps Script → paste this file → Save → Run setupAssignedDropdowns → Allow. * After that, type a new name in 00_Employees column B and it appears on every module sheet. */ function onOpen() { SpreadsheetApp.getUi() .createMenu("Homeocentrum") .addItem("Connect Assigned dropdowns to Employees", "setupAssignedDropdowns") .addToUi(); } function setupAssignedDropdowns() { var ss = SpreadsheetApp.getActive(); var emp = ss.getSheetByName("00_Employees"); if (!emp) { SpreadsheetApp.getUi().alert("Sheet 00_Employees was not found."); return; } var nameRange = emp.getRange("B3:B100"); var rule = SpreadsheetApp.newDataValidation() .requireValueInRange(nameRange, true) .setAllowInvalid(true) .setHelpText("Pick a name from 00_Employees column B. New names appear automatically.") .build(); var sheetsDone = 0; ss.getSheets().forEach(function (sh) { if (!/^M\d{2}_/.test(sh.getName())) return; var lastCol = Math.max(sh.getLastColumn(), 42); var headers = sh.getRange(2, 1, 1, lastCol).getValues()[0]; var lastRow = Math.max(sh.getLastRow(), 3); var height = lastRow - 2; if (height < 1) return; headers.forEach(function (h, i) { var title = String(h ¦¦ ""); if (title === "Assigned To (lead)" ¦¦ / Assigned$/.test(title)) { sh.getRange(3, i + 1, height, 1).setDataValidation(rule); } }); sheetsDone++; }); SpreadsheetApp.getUi().alert( "Done. Assigned To on " + sheetsDone + " module sheets now follows 00_Employees column B.\n\n" + "Type a new name in column B — it appears in the dropdown. You do not need to run this again." ); }

## 01_MASTER
MASTER MIRROR — do not type Status here. It is live from M00–M19. Click Open Module Sheet to assign an employee or mark Frontend/API/… Done. Filter to find work.
Module Seq | Original Seq | Dev Module Code | Dev Module | Track | Phase | Phase Name | WBS | Main Task ID | Main Task | Sub Task ID | Sub Task | Work Type | Source Module / Area | PDF Section | PDF Feature (exact wording) | PDF Delivery Text | Application Surface | Layer | Assigned To (lead) | Frontend | Frontend Status | Frontend Assigned | Backend | Backend Status | Backend Assigned | Database | Database Status | Database Assigned | API | API Status | API Assigned | Mobile | Mobile Status | Mobile Assigned | Integration | Integration Status | Integration Assigned | Layers Remaining | Overall Status | Notes | Open Module Sheet
1 | 1 | M00 | PRE — Client gates | Web | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.1 | PRE-01 | Decide settlement model — Homeocentrum holds all money (food-delivery / quick-commerce pattern) | PRE-01.01 | Workshop with finance: confirm Homeocentrum is single merchant of record for consult + medicine + subscription | Client Decision | Finance | §9 + §8 | Every transaction passes through Homeocentrum | Built on the principle: every transaction passes through Homeocentrum, in the same way a food-delivery or quick-commerce platform holds all payments centrally. | Account / Gateway | Decision | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 0 | N/A |  | Edit on module sheet
2 | 2 | M00 | PRE — Client gates | Web | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.1 | PRE-01 | Decide settlement model — Homeocentrum holds all money (food-delivery / quick-commerce pattern) | PRE-01.02 | Choose v1 payout mechanic: Homeocentrum-held + NEFT/IMPS vs Razorpay Route / linked accounts | Client Decision | Finance | §9 + §8 | Every transaction passes through Homeocentrum | Built on the principle: every transaction passes through Homeocentrum, in the same way a food-delivery or quick-commerce platform holds all payments centrally. | Account / Gateway | Decision | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | 1 | Not Started |  | Edit on module sheet
3 | 3 | M00 | PRE — Client gates | Web | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.1 | PRE-01 | Decide settlement model — Homeocentrum holds all money (food-delivery / quick-commerce pattern) | PRE-01.03 | Record decision in config (SettlementModel) — engineering must not hardcode a split model | Configuration | Finance | §9 + §8 | Every transaction passes through Homeocentrum | Built on the principle: every transaction passes through Homeocentrum, in the same way a food-delivery or quick-commerce platform holds all payments centrally. | Account / Gateway | Configuration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
4 | 4 | M00 | PRE — Client gates | Web | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.2 | PRE-02 | Decide reception cash policy — clinic retains vs remits to Homeocentrum | PRE-02.01 | OQ: cash collected at reception retained by clinic or remitted to Homeocentrum? | Client Decision | Finance / Reception | §9 | Reception payment collection | Cash, UPI, card or payment link with printed receipt | Account / Reception | Decision | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 0 | N/A |  | Edit on module sheet
5 | 5 | M00 | PRE — Client gates | Web | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.2 | PRE-02 | Decide reception cash policy — clinic retains vs remits to Homeocentrum | PRE-02.02 | Document GST treatment on consult fee, platform fee, and medicine (on which amount, which GSTIN) | Client Decision | Finance / Reception | §9 | Reception payment collection | Cash, UPI, card or payment link with printed receipt | Account / Reception | Decision | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 0 | N/A |  | Edit on module sheet
6 | 6 | M00 | PRE — Client gates | Web | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.2 | PRE-02 | Decide reception cash policy — clinic retains vs remits to Homeocentrum | PRE-02.03 | Confirm commission %, settlement hold T+N days, invoice numbering series — configuration not code | Configuration | Finance / Reception | §9 | Reception payment collection | Cash, UPI, card or payment link with printed receipt | Account / Reception | Configuration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
7 | 7 | M00 | PRE — Client gates | Web | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.3 | PRE-03 | Vendor and legal gates — video SDK, SMS, WhatsApp, push, DPDP copy | PRE-03.01 | Select in-browser + mobile video vendor (Agora / Twilio / Daily / WebRTC self-host) — required for §10 | Client Decision | Platform | §10 + §14 + §17 | Telemedicine + notifications + consent | Video consultation; SMS/WhatsApp/Push/Email; consent records | Shared | Decision | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | 1 | Not Started |  | Edit on module sheet
8 | 8 | M00 | PRE — Client gates | Web | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.3 | PRE-03 | Vendor and legal gates — video SDK, SMS, WhatsApp, push, DPDP copy | PRE-03.02 | Select SMS provider (MSG91 / Twilio / etc.) and confirm DLT templates for appointment/OTP/cancel | Client Decision | Platform | §10 + §14 + §17 | Telemedicine + notifications + consent | Video consultation; SMS/WhatsApp/Push/Email; consent records | Shared | Decision | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | 1 | Not Started |  | Edit on module sheet
9 | 9 | M00 | PRE — Client gates | Web | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.3 | PRE-03 | Vendor and legal gates — video SDK, SMS, WhatsApp, push, DPDP copy | PRE-03.03 | Legal: privacy (data protection, recording, pharmacy consent) and terms (payments, refunds, telemedicine, medicine orders) drafted for §4 + §17 | Client Decision | Platform | §10 + §14 + §17 | Telemedicine + notifications + consent | Video consultation; SMS/WhatsApp/Push/Email; consent records | Shared | Legal | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 0 | N/A |  | Edit on module sheet
10 | 10 | M00 | PRE — Client gates | Web | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.3 | PRE-03 | Vendor and legal gates — video SDK, SMS, WhatsApp, push, DPDP copy | PRE-03.04 | OQ: unpaid-booking slot hold duration vs release immediately if patient does not pay | Client Decision | Platform | §10 + §14 + §17 | Telemedicine + notifications + consent | Video consultation; SMS/WhatsApp/Push/Email; consent records | Shared | Decision | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 0 | N/A |  | Edit on module sheet
11 | 11 | M00 | PRE — Client gates | Web | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.3 | PRE-03 | Vendor and legal gates — video SDK, SMS, WhatsApp, push, DPDP copy | PRE-03.05 | OQ: live-doctor credentialing backfill — auto-Approve existing doctors? Unverified doctors visible only to own clinic? | Client Decision | Platform | §10 + §14 + §17 | Telemedicine + notifications + consent | Video consultation; SMS/WhatsApp/Push/Email; consent records | Shared | Decision | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 0 | N/A |  | Edit on module sheet
12 | 12 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.1 | FND-01 | One connected ecosystem — shared keys so a patient, appointment, prescription and payment created anywhere are visible everywhere | FND-01.01 | Publish shared-key design (DoctorId, PatientId, PatientAppId, CaseId, ErxId, LedgerTxnId, MedicineOrderId) and event list (created/rescheduled/cancelled/paid/signed/accepted) | New | Platform | §1 | One connected ecosystem serving six types of users | A patient, an appointment, a prescription and a payment created anywhere in the system are visible everywhere else — there are no separate systems to reconcile. | Shared | Architecture | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
13 | 13 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.1 | FND-01 | One connected ecosystem — shared keys so a patient, appointment, prescription and payment created anywhere are visible everywhere | FND-01.02 | Add role enum values Patient, Account, PharmacyPartner alongside existing Admin/Doctor/Reception (keep unused Management/Supervisor/Inspector unused) | New | Platform | §1 | One connected ecosystem serving six types of users | A patient, an appointment, a prescription and a payment created anywhere in the system are visible everywhere else — there are no separate systems to reconcile. | Shared | Database + Auth | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
14 | 14 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.1 | FND-01 | One connected ecosystem — shared keys so a patient, appointment, prescription and payment created anywhere are visible everywhere | FND-01.03 | All new domain modules on NigaHomeopathy-API (.NET 8); do not create a third API; classic API only where login/Rx-write/Razorpay already live until ported | Existing Modification | Platform | §1 | One connected ecosystem serving six types of users | A patient, an appointment, a prescription and a payment created anywhere in the system are visible everywhere else — there are no separate systems to reconcile. | Shared | Architecture | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
15 | 15 | M01 | Foundation & Security | QA | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.1 | FND-01 | One connected ecosystem — shared keys so a patient, appointment, prescription and payment created anywhere are visible everywhere | FND-01.04 | QA: create appointment on Reception → visible on Doctor web; pay on Patient web → same PaymentStatus on Doctor and Account (after Phase 6) | Regression | Platform | §1 | One connected ecosystem serving six types of users | A patient, an appointment, a prescription and a payment created anywhere in the system are visible everywhere else — there are no separate systems to reconcile. | Shared | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
16 | 16 | M01 | Foundation & Security | UI | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.2 | FND-02 | Delivery footprint — 2 mobile apps · 5 web portals · payment · telemedicine · digital prescription · HomeoMeds (programme skeleton) | FND-02.01 | Web: add Account layout + home redirect; Pharmacy layout stub; do not build screens yet | New | Platform | §1 | Delivery covers | 2 mobile applications · 5 web portals · payment system · telemedicine · digital prescription · online medicine delivery. | Shared | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
17 | 17 | M01 | Foundation & Security | UI | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.2 | FND-02 | Delivery footprint — 2 mobile apps · 5 web portals · payment · telemedicine · digital prescription · HomeoMeds (programme skeleton) | FND-02.02 | Extend roles.js and AuthProtected with per-route ACL skeleton (deny-by-default for new routes) | Existing Improvement | Platform | §1 | Delivery covers | 2 mobile applications · 5 web portals · payment system · telemedicine · digital prescription · online medicine delivery. | Shared | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
18 | 18 | M01 | Foundation & Security | Mobile | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.2 | FND-02 | Delivery footprint — 2 mobile apps · 5 web portals · payment · telemedicine · digital prescription · HomeoMeds (programme skeleton) | FND-02.03 | Mobile: create Patient app and Doctor app repository/bootstrap (React Native or agreed stack) — empty shells only | New | Platform | §1 | Delivery covers | 2 mobile applications · 5 web portals · payment system · telemedicine · digital prescription · online medicine delivery. | Shared | Mobile | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 1 | Not Started |  | Edit on module sheet
19 | 19 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.2 | FND-02 | Delivery footprint — 2 mobile apps · 5 web portals · payment · telemedicine · digital prescription · HomeoMeds (programme skeleton) | FND-02.04 | Document the five portals: Patient Website, Doctor Web Portal, Reception Portal, Admin Portal, Account Department (Pharmacy console is HomeoMeds, not a 6th portal in the PDF count) | New | Platform | §1 | Delivery covers | 2 mobile applications · 5 web portals · payment system · telemedicine · digital prescription · online medicine delivery. | Shared | Architecture | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 0 | N/A |  | Edit on module sheet
20 | 20 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.3 | SEC-01 | Secure login — protected credentials for every user type | SEC-01.01 | DB/Migration: hash existing UserMaster passwords (bcrypt/PBKDF2); never store new plaintext | Data Migration | Security | §17 | Secure login | Protected credentials for every user type | All web + later mobile | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
21 | 21 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.3 | SEC-01 | Secure login — protected credentials for every user type | SEC-01.02 | API: Login verifies hash; embed Role + DoctorId claims; keep classic login URL until .NET 8 login is cut over | Existing Modification | Security | §17 | Secure login | Protected credentials for every user type | All web + later mobile | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
22 | 22 | M01 | Foundation & Security | UI | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.3 | SEC-01 | Secure login — protected credentials for every user type | SEC-01.03 | UI: remove fakeBackend() from App.js production path; login still Formik/Yup | Existing Modification | Security | §17 | Secure login | Protected credentials for every user type | All web + later mobile | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
23 | 23 | M01 | Foundation & Security | QA | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.3 | SEC-01 | Secure login — protected credentials for every user type | SEC-01.04 | QA: Admin, Doctor, Reception login; invalid password; deactivated user; SQL injection/brute-force rate limit | Regression | Security | §17 | Secure login | Protected credentials for every user type | All web + later mobile | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
24 | 24 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.4 | SEC-02 | Secure password reset — time-limited reset links (stop plaintext email + fake thunk) | SEC-02.01 | DB: PasswordResetToken (UserId, TokenHash, ExpiresAt, UsedAt) | New | Security | §17 | Secure password reset | Time-limited reset links | Admin / Doctor / Reception web | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
25 | 25 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.4 | SEC-02 | Secure password reset — time-limited reset links (stop plaintext email + fake thunk) | SEC-02.02 | API: ForgotPassword sends reset link; ResetPassword consumes token; stop emailing plaintext; ChangePassword for authenticated user | Existing Modification | Security | §17 | Secure password reset | Time-limited reset links | Admin / Doctor / Reception web | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
26 | 26 | M01 | Foundation & Security | UI | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.4 | SEC-02 | Secure password reset — time-limited reset links (stop plaintext email + fake thunk) | SEC-02.03 | UI: replace slices/auth/forgetpwd fake/Firebase with real APIs; /reset-password/:token success/expiry states | Existing Improvement | Security | §17 | Secure password reset | Time-limited reset links | Admin / Doctor / Reception web | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
27 | 27 | M01 | Foundation & Security | QA | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.4 | SEC-02 | Secure password reset — time-limited reset links (stop plaintext email + fake thunk) | SEC-02.04 | QA: expired token, reused token, unknown email (no user enumeration), logged-in change password | Regression | Security | §17 | Secure password reset | Time-limited reset links | Admin / Doctor / Reception web | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
28 | 28 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.5 | SEC-03 | Session control — proper sign-out across web and mobile | SEC-03.01 | API: POST /Account/Logout; persist UserLoginStatus; optional denylist until token expiry | Existing Improvement | Security | §17 | Session control | Proper sign-out across web and mobile | All | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
29 | 29 | M01 | Foundation & Security | UI | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.5 | SEC-03 | Session control — proper sign-out across web and mobile | SEC-03.02 | Web: Logout.js calls API then clears authUser + patient-board session (keep existing board clear) | Existing Improvement | Security | §17 | Session control | Proper sign-out across web and mobile | All | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
30 | 30 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.5 | SEC-03 | Session control — proper sign-out across web and mobile | SEC-03.03 | Contract: mobile apps MUST use the same Logout endpoint (implemented in Phases 16–17) | New | Security | §17 | Session control | Proper sign-out across web and mobile | All | API contract | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
31 | 31 | M01 | Foundation & Security | QA | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.5 | SEC-03 | Session control — proper sign-out across web and mobile | SEC-03.04 | QA: logout on one tab; expired session message; 401 interceptor | Regression | Security | §17 | Session control | Proper sign-out across web and mobile | All | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
32 | 32 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.6 | SEC-04 | Role-based access — each role sees only what it is permitted to see | SEC-04.01 | Backend: restore GetMenuByRole; add role attributes on new money and PII APIs | Existing Improvement | Security | §17 | Role-based access | Each role sees only what it is permitted to see | Admin / All web | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
33 | 33 | M01 | Foundation & Security | UI | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.6 | SEC-04 | Role-based access — each role sees only what it is permitted to see | SEC-04.02 | Frontend: hide routes the role cannot view; keep Velzon demo routes out of production menus | Existing Improvement | Security | §17 | Role-based access | Each role sees only what it is permitted to see | Admin / All web | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
34 | 34 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.6 | SEC-04 | Role-based access — each role sees only what it is permitted to see | SEC-04.03 | Separation of duties seed: Account role controls money; Admin controls platform and clinical data — neither can perform the other’s role (PDF §8) | New | Security | §17 | Role-based access | Each role sees only what it is permitted to see | Admin / All web | Configuration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
35 | 35 | M01 | Foundation & Security | QA | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.6 | SEC-04 | Role-based access — each role sees only what it is permitted to see | SEC-04.04 | QA: Reception cannot open repertory masters; Account cannot edit diagnosis; Doctor cannot see platform-wide ledger | Regression | Security | §17 | Role-based access | Each role sees only what it is permitted to see | Admin / All web | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
36 | 36 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.7 | SEC-05 | Patient data protection — health records restricted to the treating doctor and the patient | SEC-05.01 | API: enforce DoctorId ownership on Patient, Appointment, Case, Rx, notes, labs, board backup | Existing Improvement | Security | §17 | Patient data protection | Health records restricted to the treating doctor and the patient | API | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
37 | 37 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.7 | SEC-05 | Patient data protection — health records restricted to the treating doctor and the patient | SEC-05.02 | Disable directory browsing on /attachments and /Blogs; signed-URL or authorised download for documents | Existing Modification | Security | §17 | Patient data protection | Health records restricted to the treating doctor and the patient | API | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
38 | 38 | M01 | Foundation & Security | QA | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.7 | SEC-05 | Patient data protection — health records restricted to the treating doctor and the patient | SEC-05.03 | QA: IDOR tests (swap PatientAppId / CaseId in requests) | Regression | Security | §17 | Patient data protection | Health records restricted to the treating doctor and the patient | API | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
39 | 39 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.8 | SEC-06 | Consent records infrastructure — every consent captured, stored and reviewable | SEC-06.01 | DB: ConsentRecord + ConsentType master (Privacy, Booking, TeleRecording, PharmacyShare, Marketing, Caregiver) | New | Security / Trust | §17 | Consent records | Every consent captured, stored and reviewable | Shared | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
40 | 40 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.8 | SEC-06 | Consent records infrastructure — every consent captured, stored and reviewable | SEC-06.02 | API: Grant / Withdraw / List-mine / Admin-audit (no clinical content in the API response beyond type+time) | New | Security / Trust | §17 | Consent records | Every consent captured, stored and reviewable | Shared | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
41 | 41 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.8 | SEC-06 | Consent records infrastructure — every consent captured, stored and reviewable | SEC-06.03 | Reuse AudioCaseConsentLog pattern; do not fork a second consent model for telemedicine (Phase 11 will write TeleRecording into ConsentRecord) | Existing Improvement | Security / Trust | §17 | Consent records | Every consent captured, stored and reviewable | Shared | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
42 | 42 | M01 | Foundation & Security | QA | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.8 | SEC-06 | Consent records infrastructure — every consent captured, stored and reviewable | SEC-06.04 | QA: grant, withdraw, re-grant; audit log immutable | Regression | Security / Trust | §17 | Consent records | Every consent captured, stored and reviewable | Shared | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
43 | 43 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.9 | SEC-07 | OTP verification infrastructure — applied to sensitive actions including payouts and pharmacy acceptance | SEC-07.01 | DB: OtpChallenge, OtpAuditLog (Action, EntityType, EntityId, ToMasked, Success, At) | New | Security | §17 + §8 + §12 | OTP verification | Applied to sensitive actions including payouts and pharmacy acceptance | Shared | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
44 | 44 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.9 | SEC-07 | OTP verification infrastructure — applied to sensitive actions including payouts and pharmacy acceptance | SEC-07.02 | API: RequestOtp / VerifyOtp (generic); rate-limit; lockout; SMS provider adapter stub until PRE-03 vendor is live | New | Security | §17 + §8 + §12 | OTP verification | Applied to sensitive actions including payouts and pharmacy acceptance | Shared | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
45 | 45 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.9 | SEC-07 | OTP verification infrastructure — applied to sensitive actions including payouts and pharmacy acceptance | SEC-07.03 | GET /api/Otp/Audit for Account and Admin (masked destination) | New | Security | §17 + §8 + §12 | OTP verification | Applied to sensitive actions including payouts and pharmacy acceptance | Shared | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
46 | 46 | M01 | Foundation & Security | QA | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.9 | SEC-07 | OTP verification infrastructure — applied to sensitive actions including payouts and pharmacy acceptance | SEC-07.04 | QA: replay OTP, expiry, max attempts, audit completeness | Regression | Security | §17 + §8 + §12 | OTP verification | Applied to sensitive actions including payouts and pharmacy acceptance | Shared | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
47 | 47 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.10 | SEC-08 | Complete audit trail — who did what and when across payments, prescriptions and approvals | SEC-08.01 | DB: AuditEvent (ActorUserId, Role, Action, Entity, OldJson, NewJson, At, CorrelationId) | New | Security | §17 + §9 | Complete audit trail | Who did what, and when, across payments, prescriptions and approvals / Every transaction traceable end to end by Homeocentrum | Shared | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
48 | 48 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.10 | SEC-08 | Complete audit trail — who did what and when across payments, prescriptions and approvals | SEC-08.02 | API middleware: write audit on mutating money/Rx/approval endpoints (start with a helper used by later phases) | New | Security | §17 + §9 | Complete audit trail | Who did what, and when, across payments, prescriptions and approvals / Every transaction traceable end to end by Homeocentrum | Shared | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
49 | 49 | M01 | Foundation & Security | QA | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.10 | SEC-08 | Complete audit trail — who did what and when across payments, prescriptions and approvals | SEC-08.03 | QA: sample sign-prescription / approve-payout (when those exist) produce audit rows | Regression | Security | §17 + §9 | Complete audit trail | Who did what, and when, across payments, prescriptions and approvals / Every transaction traceable end to end by Homeocentrum | Shared | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
50 | 50 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.11 | SEC-09 | Secure documents — prescriptions, reports and uploads protected from unauthorised access | SEC-09.01 | DB: SecureDocument (OwnerType, OwnerId, BlobPath, Mime, Hash, CreatedBy) | New | Security | §17 | Secure documents | Prescriptions, reports and uploads protected from unauthorised access | Shared | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
51 | 51 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.11 | SEC-09 | Secure documents — prescriptions, reports and uploads protected from unauthorised access | SEC-09.02 | API: upload (multipart) + authorised GET; no public folder listing | New | Security | §17 | Secure documents | Prescriptions, reports and uploads protected from unauthorised access | Shared | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
52 | 52 | M01 | Foundation & Security | QA | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.11 | SEC-09 | Secure documents — prescriptions, reports and uploads protected from unauthorised access | SEC-09.03 | QA: doctor of record can download; other doctor 403; anonymous 401 | Regression | Security | §17 | Secure documents | Prescriptions, reports and uploads protected from unauthorised access | Shared | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
53 | 53 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.1 | ADM-R01 | Keep and harden Admin Repertory sections (do not rebuild) | ADM-R01.01 | Regression: list / add / edit / (import-export if present) for Repertory sections | Existing | Repertory | §7.1 | Repertory sections | Manage repertory sections | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
54 | 54 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.1 | ADM-R01 | Keep and harden Admin Repertory sections (do not rebuild) | ADM-R01.02 | ACL: only Admin (and permitted roles) can mutate Repertory sections; Doctor is read-only consumer on Patient Board | Existing Improvement | Repertory | §7.1 | Repertory sections | Manage repertory sections | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
55 | 55 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.1 | ADM-R01 | Keep and harden Admin Repertory sections (do not rebuild) | ADM-R01.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Repertory sections; do not silently switch | Existing | Repertory | §7.1 | Repertory sections | Manage repertory sections | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
56 | 56 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.2 | ADM-R02 | Keep and harden Admin Subsection & rubric tree (do not rebuild) | ADM-R02.01 | Regression: list / add / edit / (import-export if present) for Subsection & rubric tree | Existing | Repertory | §7.1 | Subsection & rubric tree | Manage the full rubric hierarchy | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
57 | 57 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.2 | ADM-R02 | Keep and harden Admin Subsection & rubric tree (do not rebuild) | ADM-R02.02 | ACL: only Admin (and permitted roles) can mutate Subsection & rubric tree; Doctor is read-only consumer on Patient Board | Existing Improvement | Repertory | §7.1 | Subsection & rubric tree | Manage the full rubric hierarchy | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
58 | 58 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.2 | ADM-R02 | Keep and harden Admin Subsection & rubric tree (do not rebuild) | ADM-R02.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Subsection & rubric tree; do not silently switch | Existing | Repertory | §7.1 | Subsection & rubric tree | Manage the full rubric hierarchy | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
59 | 59 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.3 | ADM-R03 | Keep and harden Admin Rubric–remedy mapping (do not rebuild) | ADM-R03.01 | Regression: list / add / edit / (import-export if present) for Rubric–remedy mapping | Existing | Repertory | §7.1 | Rubric–remedy mapping | Map remedies to rubrics with author and grade | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
60 | 60 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.3 | ADM-R03 | Keep and harden Admin Rubric–remedy mapping (do not rebuild) | ADM-R03.02 | ACL: only Admin (and permitted roles) can mutate Rubric–remedy mapping; Doctor is read-only consumer on Patient Board | Existing Improvement | Repertory | §7.1 | Rubric–remedy mapping | Map remedies to rubrics with author and grade | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
61 | 61 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.3 | ADM-R03 | Keep and harden Admin Rubric–remedy mapping (do not rebuild) | ADM-R03.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Rubric–remedy mapping; do not silently switch | Existing | Repertory | §7.1 | Rubric–remedy mapping | Map remedies to rubrics with author and grade | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
62 | 62 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.4 | ADM-R04 | Keep and harden Admin Remedy-linked rubrics (do not rebuild) | ADM-R04.01 | Regression: list / add / edit / (import-export if present) for Remedy-linked rubrics | Existing | Repertory | §7.1 | Remedy-linked rubrics | View all rubrics linked to a remedy | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
63 | 63 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.4 | ADM-R04 | Keep and harden Admin Remedy-linked rubrics (do not rebuild) | ADM-R04.02 | ACL: only Admin (and permitted roles) can mutate Remedy-linked rubrics; Doctor is read-only consumer on Patient Board | Existing Improvement | Repertory | §7.1 | Remedy-linked rubrics | View all rubrics linked to a remedy | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
64 | 64 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.4 | ADM-R04 | Keep and harden Admin Remedy-linked rubrics (do not rebuild) | ADM-R04.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Remedy-linked rubrics; do not silently switch | Existing | Repertory | §7.1 | Remedy-linked rubrics | View all rubrics linked to a remedy | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
65 | 65 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.5 | ADM-R05 | Keep and harden Admin Language master (do not rebuild) | ADM-R05.01 | Regression: list / add / edit / (import-export if present) for Language master | Existing | Repertory | §7.1 | Language master | Manage languages | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
66 | 66 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.5 | ADM-R05 | Keep and harden Admin Language master (do not rebuild) | ADM-R05.02 | ACL: only Admin (and permitted roles) can mutate Language master; Doctor is read-only consumer on Patient Board | Existing Improvement | Repertory | §7.1 | Language master | Manage languages | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
67 | 67 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.5 | ADM-R05 | Keep and harden Admin Language master (do not rebuild) | ADM-R05.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Language master; do not silently switch | Existing | Repertory | §7.1 | Language master | Manage languages | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
68 | 68 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.6 | ADM-R06 | Keep and harden Admin Body part master (do not rebuild) | ADM-R06.01 | Regression: list / add / edit / (import-export if present) for Body part master | Existing | Repertory | §7.1 | Body part master | Manage body parts | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
69 | 69 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.6 | ADM-R06 | Keep and harden Admin Body part master (do not rebuild) | ADM-R06.02 | ACL: only Admin (and permitted roles) can mutate Body part master; Doctor is read-only consumer on Patient Board | Existing Improvement | Repertory | §7.1 | Body part master | Manage body parts | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
70 | 70 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.6 | ADM-R06 | Keep and harden Admin Body part master (do not rebuild) | ADM-R06.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Body part master; do not silently switch | Existing | Repertory | §7.1 | Body part master | Manage body parts | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
71 | 71 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.7 | ADM-R07 | Keep and harden Admin Intensity master (do not rebuild) | ADM-R07.01 | Regression: list / add / edit / (import-export if present) for Intensity master | Existing | Repertory | §7.1 | Intensity master | Manage intensity levels | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
72 | 72 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.7 | ADM-R07 | Keep and harden Admin Intensity master (do not rebuild) | ADM-R07.02 | ACL: only Admin (and permitted roles) can mutate Intensity master; Doctor is read-only consumer on Patient Board | Existing Improvement | Repertory | §7.1 | Intensity master | Manage intensity levels | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
73 | 73 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.7 | ADM-R07 | Keep and harden Admin Intensity master (do not rebuild) | ADM-R07.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Intensity master; do not silently switch | Existing | Repertory | §7.1 | Intensity master | Manage intensity levels | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
74 | 74 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.8 | ADM-R08 | Keep and harden Admin Remedy master (do not rebuild) | ADM-R08.01 | Regression: list / add / edit / (import-export if present) for Remedy master | Existing | Repertory | §7.1 | Remedy master | Manage the remedy library | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
75 | 75 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.8 | ADM-R08 | Keep and harden Admin Remedy master (do not rebuild) | ADM-R08.02 | ACL: only Admin (and permitted roles) can mutate Remedy master; Doctor is read-only consumer on Patient Board | Existing Improvement | Repertory | §7.1 | Remedy master | Manage the remedy library | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
76 | 76 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.8 | ADM-R08 | Keep and harden Admin Remedy master (do not rebuild) | ADM-R08.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Remedy master; do not silently switch | Existing | Repertory | §7.1 | Remedy master | Manage the remedy library | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
77 | 77 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.9 | ADM-R09 | Keep and harden Admin Remedy grade master (do not rebuild) | ADM-R09.01 | Regression: list / add / edit / (import-export if present) for Remedy grade master | Existing | Repertory | §7.1 | Remedy grade master | Manage remedy grading | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
78 | 78 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.9 | ADM-R09 | Keep and harden Admin Remedy grade master (do not rebuild) | ADM-R09.02 | ACL: only Admin (and permitted roles) can mutate Remedy grade master; Doctor is read-only consumer on Patient Board | Existing Improvement | Repertory | §7.1 | Remedy grade master | Manage remedy grading | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
79 | 79 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.9 | ADM-R09 | Keep and harden Admin Remedy grade master (do not rebuild) | ADM-R09.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Remedy grade master; do not silently switch | Existing | Repertory | §7.1 | Remedy grade master | Manage remedy grading | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
80 | 80 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.10 | ADM-M01 | Keep and harden Admin Author master (do not rebuild) | ADM-M01.01 | Regression: list / add / edit / (import-export if present) for Author master | Existing | Materia Medica | §7.1 | Author master | Manage materia medica authors | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
81 | 81 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.10 | ADM-M01 | Keep and harden Admin Author master (do not rebuild) | ADM-M01.02 | ACL: only Admin (and permitted roles) can mutate Author master; Doctor is read-only consumer on Patient Board | Existing Improvement | Materia Medica | §7.1 | Author master | Manage materia medica authors | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
82 | 82 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.10 | ADM-M01 | Keep and harden Admin Author master (do not rebuild) | ADM-M01.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Author master; do not silently switch | Existing | Materia Medica | §7.1 | Author master | Manage materia medica authors | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
83 | 83 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.11 | ADM-M02 | Keep and harden Admin Materia medica master (do not rebuild) | ADM-M02.01 | Regression: list / add / edit / (import-export if present) for Materia medica master | Existing | Materia Medica | §7.1 | Materia medica master | Manage the materia medica library | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
84 | 84 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.11 | ADM-M02 | Keep and harden Admin Materia medica master (do not rebuild) | ADM-M02.02 | ACL: only Admin (and permitted roles) can mutate Materia medica master; Doctor is read-only consumer on Patient Board | Existing Improvement | Materia Medica | §7.1 | Materia medica master | Manage the materia medica library | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
85 | 85 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.11 | ADM-M02 | Keep and harden Admin Materia medica master (do not rebuild) | ADM-M02.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Materia medica master; do not silently switch | Existing | Materia Medica | §7.1 | Materia medica master | Manage the materia medica library | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
86 | 86 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.12 | ADM-M03 | Keep and harden Admin Materia medica heads (do not rebuild) | ADM-M03.01 | Regression: list / add / edit / (import-export if present) for Materia medica heads | Existing | Materia Medica | §7.1 | Materia medica heads | Manage chapter headings | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
87 | 87 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.12 | ADM-M03 | Keep and harden Admin Materia medica heads (do not rebuild) | ADM-M03.02 | ACL: only Admin (and permitted roles) can mutate Materia medica heads; Doctor is read-only consumer on Patient Board | Existing Improvement | Materia Medica | §7.1 | Materia medica heads | Manage chapter headings | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
88 | 88 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.12 | ADM-M03 | Keep and harden Admin Materia medica heads (do not rebuild) | ADM-M03.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Materia medica heads; do not silently switch | Existing | Materia Medica | §7.1 | Materia medica heads | Manage chapter headings | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
89 | 89 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.13 | ADM-M04 | Keep and harden Admin Materia medica remedies (do not rebuild) | ADM-M04.01 | Regression: list / add / edit / (import-export if present) for Materia medica remedies | Existing | Materia Medica | §7.1 | Materia medica remedies | View remedy-wise materia medica | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
90 | 90 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.13 | ADM-M04 | Keep and harden Admin Materia medica remedies (do not rebuild) | ADM-M04.02 | ACL: only Admin (and permitted roles) can mutate Materia medica remedies; Doctor is read-only consumer on Patient Board | Existing Improvement | Materia Medica | §7.1 | Materia medica remedies | View remedy-wise materia medica | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
91 | 91 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.13 | ADM-M04 | Keep and harden Admin Materia medica remedies (do not rebuild) | ADM-M04.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Materia medica remedies; do not silently switch | Existing | Materia Medica | §7.1 | Materia medica remedies | View remedy-wise materia medica | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
92 | 92 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.14 | ADM-D01 | Keep and harden Admin Diagnosis system (do not rebuild) | ADM-D01.01 | Regression: list / add / edit / (import-export if present) for Diagnosis system | Existing | Diagnosis | §7.1 | Diagnosis system | Manage diagnosis systems | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
93 | 93 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.14 | ADM-D01 | Keep and harden Admin Diagnosis system (do not rebuild) | ADM-D01.02 | ACL: only Admin (and permitted roles) can mutate Diagnosis system; Doctor is read-only consumer on Patient Board | Existing Improvement | Diagnosis | §7.1 | Diagnosis system | Manage diagnosis systems | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
94 | 94 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.14 | ADM-D01 | Keep and harden Admin Diagnosis system (do not rebuild) | ADM-D01.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Diagnosis system; do not silently switch | Existing | Diagnosis | §7.1 | Diagnosis system | Manage diagnosis systems | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
95 | 95 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.15 | ADM-D02 | Keep and harden Admin Diagnosis therapeutics (do not rebuild) | ADM-D02.01 | Regression: list / add / edit / (import-export if present) for Diagnosis therapeutics | Existing | Diagnosis | §7.1 | Diagnosis therapeutics | Manage therapeutics | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
96 | 96 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.15 | ADM-D02 | Keep and harden Admin Diagnosis therapeutics (do not rebuild) | ADM-D02.02 | ACL: only Admin (and permitted roles) can mutate Diagnosis therapeutics; Doctor is read-only consumer on Patient Board | Existing Improvement | Diagnosis | §7.1 | Diagnosis therapeutics | Manage therapeutics | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
97 | 97 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.15 | ADM-D02 | Keep and harden Admin Diagnosis therapeutics (do not rebuild) | ADM-D02.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Diagnosis therapeutics; do not silently switch | Existing | Diagnosis | §7.1 | Diagnosis therapeutics | Manage therapeutics | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
98 | 98 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.16 | ADM-D03 | Keep and harden Admin Diagnosis conditions (do not rebuild) | ADM-D03.01 | Regression: list / add / edit / (import-export if present) for Diagnosis conditions | Existing | Diagnosis | §7.1 | Diagnosis conditions | Manage conditions and linked rubrics | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
99 | 99 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.16 | ADM-D03 | Keep and harden Admin Diagnosis conditions (do not rebuild) | ADM-D03.02 | ACL: only Admin (and permitted roles) can mutate Diagnosis conditions; Doctor is read-only consumer on Patient Board | Existing Improvement | Diagnosis | §7.1 | Diagnosis conditions | Manage conditions and linked rubrics | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
100 | 100 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.16 | ADM-D03 | Keep and harden Admin Diagnosis conditions (do not rebuild) | ADM-D03.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Diagnosis conditions; do not silently switch | Existing | Diagnosis | §7.1 | Diagnosis conditions | Manage conditions and linked rubrics | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
101 | 101 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.17 | ADM-A01 | Keep and harden Admin Drug system (do not rebuild) | ADM-A01.01 | Regression: list / add / edit / (import-export if present) for Drug system | Existing | Adverse Effect | §7.1 | Drug system | Manage conventional drug systems | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
102 | 102 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.17 | ADM-A01 | Keep and harden Admin Drug system (do not rebuild) | ADM-A01.02 | ACL: only Admin (and permitted roles) can mutate Drug system; Doctor is read-only consumer on Patient Board | Existing Improvement | Adverse Effect | §7.1 | Drug system | Manage conventional drug systems | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
103 | 103 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.17 | ADM-A01 | Keep and harden Admin Drug system (do not rebuild) | ADM-A01.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Drug system; do not silently switch | Existing | Adverse Effect | §7.1 | Drug system | Manage conventional drug systems | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
104 | 104 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.18 | ADM-A02 | Keep and harden Admin Drug group (do not rebuild) | ADM-A02.01 | Regression: list / add / edit / (import-export if present) for Drug group | Existing | Adverse Effect | §7.1 | Drug group | Manage drug groups | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
105 | 105 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.18 | ADM-A02 | Keep and harden Admin Drug group (do not rebuild) | ADM-A02.02 | ACL: only Admin (and permitted roles) can mutate Drug group; Doctor is read-only consumer on Patient Board | Existing Improvement | Adverse Effect | §7.1 | Drug group | Manage drug groups | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
106 | 106 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.18 | ADM-A02 | Keep and harden Admin Drug group (do not rebuild) | ADM-A02.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Drug group; do not silently switch | Existing | Adverse Effect | §7.1 | Drug group | Manage drug groups | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
107 | 107 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.19 | ADM-A03 | Keep and harden Admin Allopathic drug & side effects (do not rebuild) | ADM-A03.01 | Regression: list / add / edit / (import-export if present) for Allopathic drug & side effects | Existing | Adverse Effect | §7.1 | Allopathic drug & side effects | Manage drugs with side effects and adverse reactions | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
108 | 108 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.19 | ADM-A03 | Keep and harden Admin Allopathic drug & side effects (do not rebuild) | ADM-A03.02 | ACL: only Admin (and permitted roles) can mutate Allopathic drug & side effects; Doctor is read-only consumer on Patient Board | Existing Improvement | Adverse Effect | §7.1 | Allopathic drug & side effects | Manage drugs with side effects and adverse reactions | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
109 | 109 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.19 | ADM-A03 | Keep and harden Admin Allopathic drug & side effects (do not rebuild) | ADM-A03.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Allopathic drug & side effects; do not silently switch | Existing | Adverse Effect | §7.1 | Allopathic drug & side effects | Manage drugs with side effects and adverse reactions | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
110 | 110 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.20 | ADM-Q01 | Keep and harden Admin Question section, group & sub-group (do not rebuild) | ADM-Q01.01 | Regression: list / add / edit / (import-export if present) for Question section, group & sub-group | Existing | Clinical Questions | §7.1 | Question section, group & sub-group | Manage the clinical questionnaire structure | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
111 | 111 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.20 | ADM-Q01 | Keep and harden Admin Question section, group & sub-group (do not rebuild) | ADM-Q01.02 | ACL: only Admin (and permitted roles) can mutate Question section, group & sub-group; Doctor is read-only consumer on Patient Board | Existing Improvement | Clinical Questions | §7.1 | Question section, group & sub-group | Manage the clinical questionnaire structure | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
112 | 112 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.20 | ADM-Q01 | Keep and harden Admin Question section, group & sub-group (do not rebuild) | ADM-Q01.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Question section, group & sub-group; do not silently switch | Existing | Clinical Questions | §7.1 | Question section, group & sub-group | Manage the clinical questionnaire structure | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
113 | 113 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.21 | ADM-Q02 | Keep and harden Admin Clinical question mapping (do not rebuild) | ADM-Q02.01 | Regression: list / add / edit / (import-export if present) for Clinical question mapping | Existing | Clinical Questions | §7.1 | Clinical question mapping | Map questions to body parts and rubrics | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
114 | 114 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.21 | ADM-Q02 | Keep and harden Admin Clinical question mapping (do not rebuild) | ADM-Q02.02 | ACL: only Admin (and permitted roles) can mutate Clinical question mapping; Doctor is read-only consumer on Patient Board | Existing Improvement | Clinical Questions | §7.1 | Clinical question mapping | Map questions to body parts and rubrics | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
115 | 115 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.21 | ADM-Q02 | Keep and harden Admin Clinical question mapping (do not rebuild) | ADM-Q02.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Clinical question mapping; do not silently switch | Existing | Clinical Questions | §7.1 | Clinical question mapping | Map questions to body parts and rubrics | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
116 | 116 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.22 | ADM-3D1 | Keep and harden Admin 3D mesh key master (do not rebuild) | ADM-3D1.01 | Regression: list / add / edit / (import-export if present) for 3D mesh key master | Existing | 3D Body | §7.1 | 3D mesh key master | Manage 3D model references | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
117 | 117 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.22 | ADM-3D1 | Keep and harden Admin 3D mesh key master (do not rebuild) | ADM-3D1.02 | ACL: only Admin (and permitted roles) can mutate 3D mesh key master; Doctor is read-only consumer on Patient Board | Existing Improvement | 3D Body | §7.1 | 3D mesh key master | Manage 3D model references | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
118 | 118 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.22 | ADM-3D1 | Keep and harden Admin 3D mesh key master (do not rebuild) | ADM-3D1.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for 3D mesh key master; do not silently switch | Existing | 3D Body | §7.1 | 3D mesh key master | Manage 3D model references | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
119 | 119 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.23 | ADM-3D2 | Keep and harden Admin 3D section master (do not rebuild) | ADM-3D2.01 | Regression: list / add / edit / (import-export if present) for 3D section master | Existing | 3D Body | §7.1 | 3D section master | Manage 3D body sections | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
120 | 120 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.23 | ADM-3D2 | Keep and harden Admin 3D section master (do not rebuild) | ADM-3D2.02 | ACL: only Admin (and permitted roles) can mutate 3D section master; Doctor is read-only consumer on Patient Board | Existing Improvement | 3D Body | §7.1 | 3D section master | Manage 3D body sections | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
121 | 121 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.23 | ADM-3D2 | Keep and harden Admin 3D section master (do not rebuild) | ADM-3D2.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for 3D section master; do not silently switch | Existing | 3D Body | §7.1 | 3D section master | Manage 3D body sections | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
122 | 122 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.24 | ADM-3D3 | Keep and harden Admin 3D hotspots (do not rebuild) | ADM-3D3.01 | Regression: list / add / edit / (import-export if present) for 3D hotspots | Existing | 3D Body | §7.1 | 3D hotspots | Manage clickable points on the 3D model | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
123 | 123 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.24 | ADM-3D3 | Keep and harden Admin 3D hotspots (do not rebuild) | ADM-3D3.02 | ACL: only Admin (and permitted roles) can mutate 3D hotspots; Doctor is read-only consumer on Patient Board | Existing Improvement | 3D Body | §7.1 | 3D hotspots | Manage clickable points on the 3D model | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
124 | 124 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.24 | ADM-3D3 | Keep and harden Admin 3D hotspots (do not rebuild) | ADM-3D3.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for 3D hotspots; do not silently switch | Existing | 3D Body | §7.1 | 3D hotspots | Manage clickable points on the 3D model | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
125 | 125 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.25 | ADM-B01 | Business Management — Doctor qualifications (existing, used later by credentialing) | ADM-B01.01 | Regression: qualifications list/add/edit | Existing | Business Management | §7.2 | Doctor qualifications | Manage the qualification list | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
126 | 126 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.25 | ADM-B01 | Business Management — Doctor qualifications (existing, used later by credentialing) | ADM-B01.02 | ACL on qualification APIs | Existing Improvement | Business Management | §7.2 | Doctor qualifications | Manage the qualification list | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
127 | 127 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.25 | ADM-B01 | Business Management — Doctor qualifications (existing, used later by credentialing) | ADM-B01.03 | Confirm UI uses newer API (not classic) for qualifications | Existing | Business Management | §7.2 | Doctor qualifications | Manage the qualification list | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
128 | 128 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.26 | ADM-B02 | Business Management — Lab & imaging test catalog (existing, used by eRx lab orders) | ADM-B02.01 | Regression: lab catalog CRUD and doctor order pick-list | Existing | Business Management | §7.2 | Lab & imaging test catalog | Manage the test catalogue | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
129 | 129 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.26 | ADM-B02 | Business Management — Lab & imaging test catalog (existing, used by eRx lab orders) | ADM-B02.02 | ACL on catalog mutate | Existing Improvement | Business Management | §7.2 | Lab & imaging test catalog | Manage the test catalogue | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
130 | 130 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.26 | ADM-B02 | Business Management — Lab & imaging test catalog (existing, used by eRx lab orders) | ADM-B02.03 | Confirm classic PatientLab APIs still read this catalogue | Existing | Business Management | §7.2 | Lab & imaging test catalog | Manage the test catalogue | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
131 | 131 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.27 | ADM-B03 | Business Management — Subscription packages (existing S1 SaaS; later tied to Account ledger) | ADM-B03.01 | Regression: package list/add/edit; doctor Widgets still reads packages | Existing | Business Management | §7.2 | Subscription packages | Manage doctor subscription plans | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
132 | 132 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.27 | ADM-B03 | Business Management — Subscription packages (existing S1 SaaS; later tied to Account ledger) | ADM-B03.02 | ACL on package mutate | Existing Improvement | Business Management | §7.2 | Subscription packages | Manage doctor subscription plans | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
133 | 133 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.27 | ADM-B03 | Business Management — Subscription packages (existing S1 SaaS; later tied to Account ledger) | ADM-B03.03 | Note in code: PackageEntryDetail is S1 only — never reuse for S2 consult or S5 medicine | Existing | Business Management | §7.2 | Subscription packages | Manage doctor subscription plans | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
134 | 134 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.28 | ADM-B04 | Business Management — Roles & menu permissions (existing DB, runtime ACL leftover) | ADM-B04.01 | No schema change unless Account/Pharmacy/Patient roles need new MenuMaster rows — seed those menus | Existing Improvement | Business Management | §7.2 | Roles & menu permissions | Control exactly what each role can access | Admin Portal | Database | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | Yes | In Progress | Gourav Nikam | No | N/A |  | No | N/A |  | No | N/A |  | 1 | In Progress |  | Edit on module sheet
135 | 135 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.28 | ADM-B04 | Business Management — Roles & menu permissions (existing DB, runtime ACL leftover) | ADM-B04.02 | Restore GetMenuByRole on .NET 8; seed menus for Account and (later) Pharmacy | Existing Improvement | Business Management | §7.2 | Roles & menu permissions | Control exactly what each role can access | Admin Portal | API | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | Yes | In Progress | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 1 | In Progress |  | Edit on module sheet
136 | 136 | M02 | Admin clinical masters | UI | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.28 | ADM-B04 | Business Management — Roles & menu permissions (existing DB, runtime ACL leftover) | ADM-B04.03 | Admin role pages remain; frontend consumes menu API instead of hard-coded LayoutMenuData for domain items | Existing Improvement | Business Management | §7.2 | Roles & menu permissions | Control exactly what each role can access | Admin Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
137 | 137 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.28 | ADM-B04 | Business Management — Roles & menu permissions (existing DB, runtime ACL leftover) | ADM-B04.04 | QA: edit role menu → user of that role no longer sees the item | Regression | Business Management | §7.2 | Roles & menu permissions | Control exactly what each role can access | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
138 | 138 | M03 | Doctor clinical workspace | UI | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.1 | CLN-01 | Clinical workspace — single screen for the entire consultation | CLN-01.01 | UI: Patient Board header shows appointment, visit type, consult mode placeholders (wired in Phases 4 and 6) | Existing Improvement | Patient Board | §5.3 | Clinical workspace | Single screen for the entire consultation | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
139 | 139 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.1 | CLN-01 | Clinical workspace — single screen for the entire consultation | CLN-01.02 | Do not split the board into multiple apps; mobile doctor app will NOT get case-taking (PDF §3) | Existing | Patient Board | §5.3 | Clinical workspace | Single screen for the entire consultation | Doctor Web Portal | Architecture | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 0 | N/A |  | Edit on module sheet
140 | 140 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.1 | CLN-01 | Clinical workspace — single screen for the entire consultation | CLN-01.03 | Regression: open case from dashboard still remounts via PatientBoardRoute | Regression | Patient Board | §5.3 | Clinical workspace | Single screen for the entire consultation | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
141 | 141 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.2 | CLN-02 | Manual case taking — structured case taking (keep) | CLN-02.01 | Regression: create case, add rubrics via manual path, repertorize | Existing | Patient Board | §5.3 | Manual case taking | Structured case taking | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
142 | 142 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.2 | CLN-02 | Manual case taking — structured case taking (keep) | CLN-02.02 | ACL: only treating doctor (not Reception) can run full case taking | Existing Improvement | Patient Board | §5.3 | Manual case taking | Structured case taking | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
143 | 143 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.2 | CLN-02 | Manual case taking — structured case taking (keep) | CLN-02.03 | Confirm clipboard/repertorization APIs still on the correct host | Existing | Patient Board | §5.3 | Manual case taking | Structured case taking | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
144 | 144 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.3 | CLN-03 | Body parts & intensity selection (keep) | CLN-03.01 | Regression: body part → rubrics; intensity chip | Existing | Patient Board | §5.3 | Body parts & intensity selection | Select affected areas and severity | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
145 | 145 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.3 | CLN-03 | Body parts & intensity selection (keep) | CLN-03.02 | ACL: doctor-only | Existing Improvement | Patient Board | §5.3 | Body parts & intensity selection | Select affected areas and severity | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
146 | 146 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.3 | CLN-03 | Body parts & intensity selection (keep) | CLN-03.03 | API host unchanged | Existing | Patient Board | §5.3 | Body parts & intensity selection | Select affected areas and severity | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
147 | 147 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.4 | CLN-04 | Clinical questions — guided questions by section, group and sub-group (keep) | CLN-04.01 | Regression: full question drill-down | Existing | Patient Board | §5.3 | Clinical questions | Guided questions by section, group and sub-group | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
148 | 148 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.4 | CLN-04 | Clinical questions — guided questions by section, group and sub-group (keep) | CLN-04.02 | ACL doctor-only | Existing Improvement | Patient Board | §5.3 | Clinical questions | Guided questions by section, group and sub-group | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
149 | 149 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.4 | CLN-04 | Clinical questions — guided questions by section, group and sub-group (keep) | CLN-04.03 | API host unchanged | Existing | Patient Board | §5.3 | Clinical questions | Guided questions by section, group and sub-group | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
150 | 150 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.5 | CLN-05 | Diagnosis, therapeutics & pattern search (keep) | CLN-05.01 | Regression: diagnosis search + therapeutics | Existing | Patient Board | §5.3 | Diagnosis, therapeutics & pattern search | Search diagnoses and linked therapeutics | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
151 | 151 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.5 | CLN-05 | Diagnosis, therapeutics & pattern search (keep) | CLN-05.02 | ACL doctor-only | Existing Improvement | Patient Board | §5.3 | Diagnosis, therapeutics & pattern search | Search diagnoses and linked therapeutics | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
152 | 152 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.5 | CLN-05 | Diagnosis, therapeutics & pattern search (keep) | CLN-05.03 | API host unchanged | Existing | Patient Board | §5.3 | Diagnosis, therapeutics & pattern search | Search diagnoses and linked therapeutics | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
153 | 153 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.6 | CLN-06 | Repertory rubric search & selection (keep) | CLN-06.01 | Regression: tree + search + add to clipboard | Existing | Patient Board | §5.3 | Repertory rubric search & selection | Search and select from the full repertory | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
154 | 154 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.6 | CLN-06 | Repertory rubric search & selection (keep) | CLN-06.02 | ACL doctor-only | Existing Improvement | Patient Board | §5.3 | Repertory rubric search & selection | Search and select from the full repertory | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
155 | 155 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.6 | CLN-06 | Repertory rubric search & selection (keep) | CLN-06.03 | Confirm subsection search host (newer vs classic) documented | Existing | Patient Board | §5.3 | Repertory rubric search & selection | Search and select from the full repertory | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
156 | 156 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.7 | CLN-07 | Manage selected rubrics — review, edit and remove (remaining ~10%) | CLN-07.01 | No new table — clipboard already persisted via board backup / repertorization payload | Existing Improvement | Patient Board | §5.3 | Manage selected rubrics | Review, edit and remove selected rubrics | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
157 | 157 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.7 | CLN-07 | Manage selected rubrics — review, edit and remove (remaining ~10%) | CLN-07.02 | If intensity-on-clipboard is client-only, persist it on backup payload | Existing Improvement | Patient Board | §5.3 | Manage selected rubrics | Review, edit and remove selected rubrics | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
158 | 158 | M03 | Doctor clinical workspace | UI | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.7 | CLN-07 | Manage selected rubrics — review, edit and remove (remaining ~10%) | CLN-07.03 | Clipboard UX: confirm delete; intensity edit; count badge | Existing Improvement | Patient Board | §5.3 | Manage selected rubrics | Review, edit and remove selected rubrics | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
159 | 159 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.7 | CLN-07 | Manage selected rubrics — review, edit and remove (remaining ~10%) | CLN-07.04 | QA: remove, undo-not-required, backup restore still has remaining rubrics | Regression | Patient Board | §5.3 | Manage selected rubrics | Review, edit and remove selected rubrics | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
160 | 160 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.8 | CLN-08 | Audio case taking — record and receive suggested rubrics (keep engine; do not rebuild) | CLN-08.01 | Regression: record, poll, approve/reject suggested rubrics | Existing | Audio AI | §5.3 | Audio case taking | Record the consultation and receive suggested rubrics automatically | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
161 | 161 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.8 | CLN-08 | Audio case taking — record and receive suggested rubrics (keep engine; do not rebuild) | CLN-08.02 | Consent: audio consent continues to write AudioCaseConsentLog (later also ConsentRecord) | Existing Improvement | Audio AI | §5.3 | Audio case taking | Record the consultation and receive suggested rubrics automatically | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
162 | 162 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.8 | CLN-08 | Audio case taking — record and receive suggested rubrics (keep engine; do not rebuild) | CLN-08.03 | Confirm audio queue/worker still healthy | Existing | Audio AI | §5.3 | Audio case taking | Record the consultation and receive suggested rubrics automatically | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
163 | 163 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.9 | CLN-09 | Improved rubric accuracy — enhanced accuracy rules for audio-based rubric suggestions | CLN-09.01 | Follow AUDIO_CASE_TAKING_* docs: accuracy rules, aliases, metaphors, benchmark | Existing Improvement | Audio AI | §5.3 | Improved rubric accuracy | Enhanced accuracy rules for audio-based rubric suggestions | Doctor Web Portal + Admin intelligence | Backend | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
164 | 164 | M03 | Doctor clinical workspace | UI | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.9 | CLN-09 | Improved rubric accuracy — enhanced accuracy rules for audio-based rubric suggestions | CLN-09.02 | Admin: metaphor/alias approve-reject remaining UX | Existing Improvement | Audio AI | §5.3 | Improved rubric accuracy | Enhanced accuracy rules for audio-based rubric suggestions | Doctor Web Portal + Admin intelligence | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
165 | 165 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.9 | CLN-09 | Improved rubric accuracy — enhanced accuracy rules for audio-based rubric suggestions | CLN-09.03 | QA: golden transcripts → expected rubric IDs within tolerance | Regression | Audio AI | §5.3 | Improved rubric accuracy | Enhanced accuracy rules for audio-based rubric suggestions | Doctor Web Portal + Admin intelligence | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
166 | 166 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.10 | CLN-10 | Materia medica reference during consultation (remaining ~10%) | CLN-10.01 | No schema change | Existing Improvement | Patient Board | §5.3 | Materia medica reference | Browse materia medica during the consultation | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
167 | 167 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.10 | CLN-10 | Materia medica reference during consultation (remaining ~10%) | CLN-10.02 | Existing MM APIs — add a lightweight get-by-remedy if chatty | Existing Improvement | Patient Board | §5.3 | Materia medica reference | Browse materia medica during the consultation | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
168 | 168 | M03 | Doctor clinical workspace | UI | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.10 | CLN-10 | Materia medica reference during consultation (remaining ~10%) | CLN-10.03 | MM tab: faster head navigation / keep place in case | Existing Improvement | Patient Board | §5.3 | Materia medica reference | Browse materia medica during the consultation | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
169 | 169 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.10 | CLN-10 | Materia medica reference during consultation (remaining ~10%) | CLN-10.04 | QA: open MM for a repertorized remedy | Regression | Patient Board | §5.3 | Materia medica reference | Browse materia medica during the consultation | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
170 | 170 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.11 | CLN-11 | Allopathic drug side-effect lookup (keep) | CLN-11.01 | Regression: search drug → side effects | Existing | Patient Board | §5.3 | Allopathic drug side-effect lookup | Check side effects of conventional medicines | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
171 | 171 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.11 | CLN-11 | Allopathic drug side-effect lookup (keep) | CLN-11.02 | ACL doctor-only | Existing Improvement | Patient Board | §5.3 | Allopathic drug side-effect lookup | Check side effects of conventional medicines | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
172 | 172 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.11 | CLN-11 | Allopathic drug side-effect lookup (keep) | CLN-11.03 | API host unchanged | Existing | Patient Board | §5.3 | Allopathic drug side-effect lookup | Check side effects of conventional medicines | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
173 | 173 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.12 | CLN-12 | Repertorization & elimination (remaining ~10%) | CLN-12.01 | No schema change | Existing Improvement | Patient Board | §5.3 | Repertorization & elimination | Full repertorization with elimination | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
174 | 174 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.12 | CLN-12 | Repertorization & elimination (remaining ~10%) | CLN-12.02 | Keep existing repertorization APIs; fix any known scoring edge cases | Existing Improvement | Patient Board | §5.3 | Repertorization & elimination | Full repertorization with elimination | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
175 | 175 | M03 | Doctor clinical workspace | UI | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.12 | CLN-12 | Repertorization & elimination (remaining ~10%) | CLN-12.03 | Repertorize tab stability; then COG sits beside it | Existing Improvement | Patient Board | §5.3 | Repertorization & elimination | Full repertorization with elimination | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
176 | 176 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.12 | CLN-12 | Repertorization & elimination (remaining ~10%) | CLN-12.04 | QA: known case → expected top remedies | Regression | Patient Board | §5.3 | Repertorization & elimination | Full repertorization with elimination | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
177 | 177 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.13 | CLN-13 | Center of Gravity — new analysis identifying the central remedy of the case, with reasoning shown | CLN-13.01 | No mandatory new table (algorithm on selected rubrics); optional CogRun log for support | New | Repertorization | §5.3 | Center of Gravity | New analysis identifying the central remedy of the case, with reasoning shown | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
178 | 178 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.13 | CLN-13 | Center of Gravity — new analysis identifying the central remedy of the case, with reasoning shown | CLN-13.02 | POST /api/Repertorization/CenterOfGravity — input rubric ids + intensities; output ranked remedies + reasons | New | Repertorization | §5.3 | Center of Gravity | New analysis identifying the central remedy of the case, with reasoning shown | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
179 | 179 | M03 | Doctor clinical workspace | UI | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.13 | CLN-13 | Center of Gravity — new analysis identifying the central remedy of the case, with reasoning shown | CLN-13.03 | Patient Board → Repertorize tab → Center of Gravity sub-panel (toggle vs classic elimination) | New | Repertorization | §5.3 | Center of Gravity | New analysis identifying the central remedy of the case, with reasoning shown | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
180 | 180 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.13 | CLN-13 | Center of Gravity — new analysis identifying the central remedy of the case, with reasoning shown | CLN-13.04 | QA: same clipboard as classic repertorize; COG reasons cite contributing rubrics; empty clipboard → clear empty state | Regression | Repertorization | §5.3 | Center of Gravity | New analysis identifying the central remedy of the case, with reasoning shown | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
181 | 181 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.14 | CLN-14 | Lab orders & lab entries (keep; later also sit on eRx) | CLN-14.01 | Regression: order lab from catalogue; enter result | Existing | Patient Board | §5.3 + §11 | Lab orders & lab entries | Order tests and record results / Tests ordered alongside the prescription | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
182 | 182 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.14 | CLN-14 | Lab orders & lab entries (keep; later also sit on eRx) | CLN-14.02 | ACL doctor-only | Existing Improvement | Patient Board | §5.3 + §11 | Lab orders & lab entries | Order tests and record results / Tests ordered alongside the prescription | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
183 | 183 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.14 | CLN-14 | Lab orders & lab entries (keep; later also sit on eRx) | CLN-14.03 | API: classic PatientLab still authoritative until ported | Existing | Patient Board | §5.3 + §11 | Lab orders & lab entries | Order tests and record results / Tests ordered alongside the prescription | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
184 | 184 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.15 | CLN-15 | Appointment history notes (keep; split from eRx in Phase 10) | CLN-15.01 | Regression: add/list notes on a visit | Existing | Patient Board | §5.3 | Appointment history notes | Notes recorded against each visit | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
185 | 185 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.15 | CLN-15 | Appointment history notes (keep; split from eRx in Phase 10) | CLN-15.02 | ACL doctor-only | Existing Improvement | Patient Board | §5.3 | Appointment history notes | Notes recorded against each visit | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
186 | 186 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.15 | CLN-15 | Appointment history notes (keep; split from eRx in Phase 10) | CLN-15.03 | Do not dual-write; classic notes stay until Phase 10 extends them | Existing | Patient Board | §5.3 | Appointment history notes | Notes recorded against each visit | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
187 | 187 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.16 | CLN-16 | Complaints & case details — wire Patient Board to existing SaveComplaints / SaveCaseDetails (~20% today) | CLN-16.01 | Use existing tables — no new schema unless fields are missing vs PDF | Existing Improvement | Patient Board | §5.3 | Complaints & case details | Capture and store complaints and case details | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
188 | 188 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.16 | CLN-16 | Complaints & case details — wire Patient Board to existing SaveComplaints / SaveCaseDetails (~20% today) | CLN-16.02 | Keep classic SaveComplaints / SaveCaseDetails; add GET if missing | Existing Improvement | Patient Board | §5.3 | Complaints & case details | Capture and store complaints and case details | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
189 | 189 | M03 | Doctor clinical workspace | UI | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.16 | CLN-16 | Complaints & case details — wire Patient Board to existing SaveComplaints / SaveCaseDetails (~20% today) | CLN-16.03 | Patient Board: complaints + case details form that actually POSTs | Existing Improvement | Patient Board | §5.3 | Complaints & case details | Capture and store complaints and case details | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
190 | 190 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.16 | CLN-16 | Complaints & case details — wire Patient Board to existing SaveComplaints / SaveCaseDetails (~20% today) | CLN-16.04 | QA: save, reload, second doctor cannot read | Regression | Patient Board | §5.3 | Complaints & case details | Capture and store complaints and case details | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
191 | 191 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.17 | CLN-17 | Patient back history — complete history of visits, notes, prescriptions and payments | CLN-17.01 | No new table — compose from Appointment + notes + Rx + (later) ConsultPayment | Existing Improvement | Patient Board | §5.3 | Patient back history | Complete history of visits, notes, prescriptions and payments | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
192 | 192 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.17 | CLN-17 | Patient back history — complete history of visits, notes, prescriptions and payments | CLN-17.02 | GET patient timeline DTO including payment status when column exists | Existing Improvement | Patient Board | §5.3 | Patient back history | Complete history of visits, notes, prescriptions and payments | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
193 | 193 | M03 | Doctor clinical workspace | UI | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.17 | CLN-17 | Patient back history — complete history of visits, notes, prescriptions and payments | CLN-17.03 | History panel: date-ordered visits; open past eRx; payment badge placeholder | Existing Improvement | Patient Board | §5.3 | Patient back history | Complete history of visits, notes, prescriptions and payments | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
194 | 194 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.17 | CLN-17 | Patient back history — complete history of visits, notes, prescriptions and payments | CLN-17.04 | QA: multi-visit patient; empty new patient | Regression | Patient Board | §5.3 | Patient back history | Complete history of visits, notes, prescriptions and payments | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
195 | 195 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.18 | CLN-18 | Export case data — download the full case in Excel or PDF | CLN-18.01 | Reuse ExportCasesToExcel; add PDF generation of the clinical case (doctor copy, includes notes) | Existing Improvement | Patient Board | §5.3 | Export case data | Download the full case in Excel or PDF | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
196 | 196 | M03 | Doctor clinical workspace | UI | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.18 | CLN-18 | Export case data — download the full case in Excel or PDF | CLN-18.02 | Patient Board toolbar: Export Excel / Export PDF | New | Patient Board | §5.3 | Export case data | Download the full case in Excel or PDF | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
197 | 197 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.18 | CLN-18 | Export case data — download the full case in Excel or PDF | CLN-18.03 | QA: export matches on-screen rubrics + Rx; unauthorised doctor 403 | Regression | Patient Board | §5.3 | Export case data | Download the full case in Excel or PDF | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
198 | 198 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.19 | CLN-19 | Session restore — continue exactly where the doctor left off, across multiple patients (keep) | CLN-19.01 | Regression: backup, restore, 5-session stack | Existing | Patient Board | §5.3 | Session restore | Continue exactly where the doctor left off, across multiple patients | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
199 | 199 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.19 | CLN-19 | Session restore — continue exactly where the doctor left off, across multiple patients (keep) | CLN-19.02 | ACL: backup scoped to DoctorId | Existing Improvement | Patient Board | §5.3 | Session restore | Continue exactly where the doctor left off, across multiple patients | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
200 | 200 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.19 | CLN-19 | Session restore — continue exactly where the doctor left off, across multiple patients (keep) | CLN-19.03 | API: PatientBoardBackup on .NET 8 unchanged | Existing | Patient Board | §5.3 | Session restore | Continue exactly where the doctor left off, across multiple patients | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
201 | 201 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.20 | CLN-20 | 3D anatomy viewer — interactive 3D body model linked to rubric search (remaining ~50%) | CLN-20.01 | No new tables — Mesh/Section/Hotspot masters already exist | Existing Improvement | Anatomy | §5.3 | 3D anatomy viewer | Interactive 3D body model linked to rubric search | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
202 | 202 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.20 | CLN-20 | 3D anatomy viewer — interactive 3D body model linked to rubric search (remaining ~50%) | CLN-20.02 | Fix hotspot mapping gaps on newer threeDBodyPart APIs | Existing Improvement | Anatomy | §5.3 | 3D anatomy viewer | Interactive 3D body model linked to rubric search | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
203 | 203 | M03 | Doctor clinical workspace | UI | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.20 | CLN-20 | 3D anatomy viewer — interactive 3D body model linked to rubric search (remaining ~50%) | CLN-20.03 | Viewer UX: incomplete regions, loading, fallback message | Existing Improvement | Anatomy | §5.3 | 3D anatomy viewer | Interactive 3D body model linked to rubric search | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
204 | 204 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.20 | CLN-20 | 3D anatomy viewer — interactive 3D body model linked to rubric search (remaining ~50%) | CLN-20.04 | QA: click hotspot → subsection search results | Regression | Anatomy | §5.3 | 3D anatomy viewer | Interactive 3D body model linked to rubric search | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
205 | 205 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.1 | DOC-01 | Doctor home dashboard — complete overview of the working day (remaining ~30%) | DOC-01.01 | No new dashboard table | Existing Improvement | Doctor Dashboard | §5.1 | Doctor home dashboard | Complete overview of the working day | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
206 | 206 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.1 | DOC-01 | Doctor home dashboard — complete overview of the working day (remaining ~30%) | DOC-01.02 | Extend dashboard DTOs with paymentStatus / tele flags when columns exist (nullable until Phase 6/11) | Existing Improvement | Doctor Dashboard | §5.1 | Doctor home dashboard | Complete overview of the working day | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
207 | 207 | M04 | Doctor daily operations | UI | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.1 | DOC-01 | Doctor home dashboard — complete overview of the working day (remaining ~30%) | DOC-01.03 | Dashboard chrome: keep counts; add slots for Online toggle, tele queue, unpaid badge | Existing Improvement | Doctor Dashboard | §5.1 | Doctor home dashboard | Complete overview of the working day | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
208 | 208 | M04 | Doctor daily operations | QA | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.1 | DOC-01 | Doctor home dashboard — complete overview of the working day (remaining ~30%) | DOC-01.04 | QA: existing buckets still populate; reception still shares layout until Phase 5 reception chrome | Regression | Doctor Dashboard | §5.1 | Doctor home dashboard | Complete overview of the working day | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
209 | 209 | M04 | Doctor daily operations | QA | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.2 | DOC-02 | Patient counts & waiting list — live counts by status with quick actions (keep; extend paid/unpaid) | DOC-02.01 | Regression: each bucket count and click-through | Existing | Doctor Dashboard | §5.1 | Patient counts & waiting list | Live counts by status with quick actions | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
210 | 210 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.2 | DOC-02 | Patient counts & waiting list — live counts by status with quick actions (keep; extend paid/unpaid) | DOC-02.02 | Reception sharing this view is OK until Phase 5 splits chrome | Existing Improvement | Doctor Dashboard | §5.1 | Patient counts & waiting list | Live counts by status with quick actions | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
211 | 211 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.2 | DOC-02 | Patient counts & waiting list — live counts by status with quick actions (keep; extend paid/unpaid) | DOC-02.03 | API: existing dashboard count endpoints | Existing | Doctor Dashboard | §5.1 | Patient counts & waiting list | Live counts by status with quick actions | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
212 | 212 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.3 | DOC-03 | Patient search, list & open case (remaining ~10%) | DOC-03.01 | Use existing Patient + Appointment — add DTO fields | Existing Improvement | Doctor Dashboard | §5.1 | Patient search, list & open case | Find any patient and open their case instantly | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
213 | 213 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.3 | DOC-03 | Patient search, list & open case (remaining ~10%) | DOC-03.02 | Search DTO includes lastVisitAt | Existing Improvement | Doctor Dashboard | §5.1 | Patient search, list & open case | Find any patient and open their case instantly | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
214 | 214 | M04 | Doctor daily operations | UI | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.3 | DOC-03 | Patient search, list & open case (remaining ~10%) | DOC-03.03 | List columns: last visit; later payment/family | Existing Improvement | Doctor Dashboard | §5.1 | Patient search, list & open case | Find any patient and open their case instantly | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
215 | 215 | M04 | Doctor daily operations | QA | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.3 | DOC-03 | Patient search, list & open case (remaining ~10%) | DOC-03.04 | QA: search by name/mobile; open case | Regression | Doctor Dashboard | §5.1 | Patient search, list & open case | Find any patient and open their case instantly | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
216 | 216 | M04 | Doctor daily operations | QA | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.4 | DOC-04 | Add new patient — register a patient in seconds (keep) | DOC-04.01 | Regression: add patient validation and save | Existing | Patients | §5.1 | Add new patient | Register a patient in seconds | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
217 | 217 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.4 | DOC-04 | Add new patient — register a patient in seconds (keep) | DOC-04.02 | ACL: doctor/reception of that clinic only | Existing Improvement | Patients | §5.1 | Add new patient | Register a patient in seconds | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
218 | 218 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.4 | DOC-04 | Add new patient — register a patient in seconds (keep) | DOC-04.03 | API unchanged | Existing | Patients | §5.1 | Add new patient | Register a patient in seconds | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
219 | 219 | M04 | Doctor daily operations | QA | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.5 | DOC-05 | Import patients — bring existing patient records in bulk (keep) | DOC-05.01 | Regression: template + import + error rows | Existing | Patients | §5.1 | Import patients | Bring existing patient records in bulk | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
220 | 220 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.5 | DOC-05 | Import patients — bring existing patient records in bulk (keep) | DOC-05.02 | ACL doctor-only (or reception if already allowed) | Existing Improvement | Patients | §5.1 | Import patients | Bring existing patient records in bulk | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
221 | 221 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.5 | DOC-05 | Import patients — bring existing patient records in bulk (keep) | DOC-05.03 | API unchanged | Existing | Patients | §5.1 | Import patients | Bring existing patient records in bulk | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
222 | 222 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.6 | DOC-06 | Export patients — download patient data in Excel, CSV or PDF (keep) | DOC-06.01 | Audit current export formats; add PDF if only Excel/CSV exist today | Existing Improvement | Patients | §5.1 | Export patients | Download patient data in Excel, CSV or PDF | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
223 | 223 | M04 | Doctor daily operations | UI | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.6 | DOC-06 | Export patients — download patient data in Excel, CSV or PDF (keep) | DOC-06.02 | UI: Excel / CSV / PDF actions labelled as in the delivery document | Existing Improvement | Patients | §5.1 | Export patients | Download patient data in Excel, CSV or PDF | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
224 | 224 | M04 | Doctor daily operations | QA | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.6 | DOC-06 | Export patients — download patient data in Excel, CSV or PDF (keep) | DOC-06.03 | QA: another doctor cannot export this list | Regression | Patients | §5.1 | Export patients | Download patient data in Excel, CSV or PDF | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
225 | 225 | M04 | Doctor daily operations | QA | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.7 | DOC-07 | Recent activity panel (keep) | DOC-07.01 | Regression: activity loads | Existing | Doctor Dashboard | §5.1 | Recent activity panel | Everything that happened recently, at a glance | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
226 | 226 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.7 | DOC-07 | Recent activity panel (keep) | DOC-07.02 | ACL scoped to doctor | Existing Improvement | Doctor Dashboard | §5.1 | Recent activity panel | Everything that happened recently, at a glance | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
227 | 227 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.7 | DOC-07 | Recent activity panel (keep) | DOC-07.03 | API unchanged | Existing | Doctor Dashboard | §5.1 | Recent activity panel | Everything that happened recently, at a glance | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
228 | 228 | M04 | Doctor daily operations | QA | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.8 | DOC-08 | Patient statistics charts (keep; foundation for clinic performance in Phase 18) | DOC-08.01 | Regression: stats charts date range | Existing | Doctor Dashboard | §5.1 | Patient statistics charts | Visual practice statistics | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
229 | 229 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.8 | DOC-08 | Patient statistics charts (keep; foundation for clinic performance in Phase 18) | DOC-08.02 | ACL doctor-only | Existing Improvement | Doctor Dashboard | §5.1 | Patient statistics charts | Visual practice statistics | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
230 | 230 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.8 | DOC-08 | Patient statistics charts (keep; foundation for clinic performance in Phase 18) | DOC-08.03 | API unchanged | Existing | Doctor Dashboard | §5.1 | Patient statistics charts | Visual practice statistics | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
231 | 231 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.9 | DOC-09 | Manage reception staff — add, edit and remove reception users (backend done, UI absent) | DOC-09.01 | No new API — authorise that the doctor owns the staff record on existing CRUD | Existing Improvement | Staff | §5.1 | Manage reception staff | Add, edit and remove reception users | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
232 | 232 | M04 | Doctor daily operations | UI | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.9 | DOC-09 | Manage reception staff — add, edit and remove reception users (backend done, UI absent) | DOC-09.02 | Build /doctor/reception-staff list, add, edit, disable pages; menu entry in doctor chrome | Existing Improvement | Staff | §5.1 | Manage reception staff | Add, edit and remove reception users | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
233 | 233 | M04 | Doctor daily operations | QA | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.9 | DOC-09 | Manage reception staff — add, edit and remove reception users (backend done, UI absent) | DOC-09.03 | QA: reception user cannot manage other doctors’ staff; disable prevents login | Regression | Staff | §5.1 | Manage reception staff | Add, edit and remove reception users | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
234 | 234 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.10 | DOC-10 | Doctor profile — clinic details, consultation fee, photo, qualifications, working hours, bank details | DOC-10.01 | Extend Doctor / add DoctorPayeeKyc fields (bank, PAN) used later by Account; ConsultFeeConfig may wait until Phase 6 — store fee on profile now if simpler | Existing Improvement | Doctor Profile | §5.1 | Doctor profile | Clinic details, consultation fee, photo, qualifications, working hours, bank details | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
235 | 235 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.10 | DOC-10 | Doctor profile — clinic details, consultation fee, photo, qualifications, working hours, bank details | DOC-10.02 | GET/PUT /api/Profile/Me (doctor DTO); POST photo multipart; do not allow role escalation | Existing Improvement | Doctor Profile | §5.1 | Doctor profile | Clinic details, consultation fee, photo, qualifications, working hours, bank details | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
236 | 236 | M04 | Doctor daily operations | UI | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.10 | DOC-10 | Doctor profile — clinic details, consultation fee, photo, qualifications, working hours, bank details | DOC-10.03 | Replace Velzon /profile for doctor role with clinic/fee/photo/qualifications/hours/bank tabs | Existing Improvement | Doctor Profile | §5.1 | Doctor profile | Clinic details, consultation fee, photo, qualifications, working hours, bank details | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
237 | 237 | M04 | Doctor daily operations | QA | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.10 | DOC-10 | Doctor profile — clinic details, consultation fee, photo, qualifications, working hours, bank details | DOC-10.04 | QA: reception cannot edit doctor bank details; photo displays on public profile later | Regression | Doctor Profile | §5.1 | Doctor profile | Clinic details, consultation fee, photo, qualifications, working hours, bank details | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
238 | 238 | M05 | Appointments & scheduling | QA | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.1 | APT-01 | Appointment list & waiting patients — full day view with live status (keep; later payment/tele) | APT-01.01 | Regression: day list, status colour, open patient | Existing | Appointments | §5.2 | Appointment list & waiting patients | Full day view with live status | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
239 | 239 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.1 | APT-01 | Appointment list & waiting patients — full day view with live status (keep; later payment/tele) | APT-01.02 | ACL doctor/reception of that DoctorId | Existing Improvement | Appointments | §5.2 | Appointment list & waiting patients | Full day view with live status | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
240 | 240 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.1 | APT-01 | Appointment list & waiting patients — full day view with live status (keep; later payment/tele) | APT-01.03 | API unchanged | Existing | Appointments | §5.2 | Appointment list & waiting patients | Full day view with live status | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
241 | 241 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.2 | APT-02 | Create new appointment — persist visit type, consultation mode and fee | APT-02.01 | DB: PatientAppointment.VisitType, ConsultMode; migrate existing rows VisitType=First (do not infer retrospectively) | Existing Improvement | Appointments | §5.2 | Create new appointment | Book with visit type, consultation mode and fee | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
242 | 242 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.2 | APT-02 | Create new appointment — persist visit type, consultation mode and fee | APT-02.02 | API: create/update appointment accepts the new fields; PATCH VisitType | Existing Improvement | Appointments | §5.2 | Create new appointment | Book with visit type, consultation mode and fee | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
243 | 243 | M05 | Appointments & scheduling | UI | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.2 | APT-02 | Create new appointment — persist visit type, consultation mode and fee | APT-02.03 | Doctor/Reception new-appointment modal: visit type, consult mode, fee (placeholder until Phase 6 config) | Existing Improvement | Appointments | §5.2 | Create new appointment | Book with visit type, consultation mode and fee | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
244 | 244 | M05 | Appointments & scheduling | QA | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.2 | APT-02 | Create new appointment — persist visit type, consultation mode and fee | APT-02.04 | QA: staff-created appointments carry the same fields public booking will use in Phase 9 | Regression | Appointments | §5.2 | Create new appointment | Book with visit type, consultation mode and fee | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
245 | 245 | M05 | Appointments & scheduling | QA | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.3 | APT-03 | Appointment status update — move patients through the visit stages (keep) | APT-03.01 | Regression: each status transition | Existing | Appointments | §5.2 | Appointment status update | Move patients through the visit stages | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
246 | 246 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.3 | APT-03 | Appointment status update — move patients through the visit stages (keep) | APT-03.02 | ACL doctor/reception | Existing Improvement | Appointments | §5.2 | Appointment status update | Move patients through the visit stages | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
247 | 247 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.3 | APT-03 | Appointment status update — move patients through the visit stages (keep) | APT-03.03 | API unchanged | Existing | Appointments | §5.2 | Appointment status update | Move patients through the visit stages | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
248 | 248 | M05 | Appointments & scheduling | QA | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.4 | APT-04 | Appointment time update — adjust timings as the day runs (keep; distinct from formal reschedule) | APT-04.01 | Regression: UpdateAppointmentTime on dashboard | Existing | Appointments | §5.2 | Appointment time update | Adjust timings as the day runs | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
249 | 249 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.4 | APT-04 | Appointment time update — adjust timings as the day runs (keep; distinct from formal reschedule) | APT-04.02 | Document in UI that Reschedule is the patient-notified path | Existing Improvement | Appointments | §5.2 | Appointment time update | Adjust timings as the day runs | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
250 | 250 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.4 | APT-04 | Appointment time update — adjust timings as the day runs (keep; distinct from formal reschedule) | APT-04.03 | API: keep UpdateAppointmentTime; Reschedule wraps it | Existing | Appointments | §5.2 | Appointment time update | Adjust timings as the day runs | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
251 | 251 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.5 | APT-05 | Reschedule appointment — move to a new slot with automatic patient notification (NEW — not a rename of UpdateAppointmentTime) | APT-05.01 | DB: AppointmentChangeLog (PatientAppId, Action, OldValue, NewValue, ByUserId, ByRole, At) + indexes | New | Appointments | §5.2 + §2.3 + §6 | Reschedule appointment | Move to a new slot with automatic patient notification / Move to another slot without calling the clinic | Doctor Web + Reception + later Patient | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
252 | 252 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.5 | APT-05 | Reschedule appointment — move to a new slot with automatic patient notification (NEW — not a rename of UpdateAppointmentTime) | APT-05.02 | API: POST /api/PatientAppointment/RescheduleAppointment — validate schedule, bookings, not in the past; 409 with alternatives; wrap UpdateAppointmentTime; GET ChangeLog/{id} | New | Appointments | §5.2 + §2.3 + §6 | Reschedule appointment | Move to a new slot with automatic patient notification / Move to another slot without calling the clinic | Doctor Web + Reception + later Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
253 | 253 | M05 | Appointments & scheduling | UI | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.5 | APT-05 | Reschedule appointment — move to a new slot with automatic patient notification (NEW — not a rename of UpdateAppointmentTime) | APT-05.03 | UI: RescheduleModal shared by Doctor and Reception — old date/time + new slot picker; reason optional | New | Appointments | §5.2 + §2.3 + §6 | Reschedule appointment | Move to a new slot with automatic patient notification / Move to another slot without calling the clinic | Doctor Web + Reception + later Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
254 | 254 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.5 | APT-05 | Reschedule appointment — move to a new slot with automatic patient notification (NEW — not a rename of UpdateAppointmentTime) | APT-05.04 | Notifications: SMS + WhatsApp + (later) push — old→new; must not block the transaction if notify fails | New Integration | Appointments | §5.2 + §2.3 + §6 | Reschedule appointment | Move to a new slot with automatic patient notification / Move to another slot without calling the clinic | Doctor Web + Reception + later Patient | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
255 | 255 | M05 | Appointments & scheduling | QA | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.5 | APT-05 | Reschedule appointment — move to a new slot with automatic patient notification (NEW — not a rename of UpdateAppointmentTime) | APT-05.05 | QA: slot taken → 409; patient already booked elsewhere; across a schedule change; reception authorised for own DoctorId only | Regression | Appointments | §5.2 + §2.3 + §6 | Reschedule appointment | Move to a new slot with automatic patient notification / Move to another slot without calling the clinic | Doctor Web + Reception + later Patient | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
256 | 256 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.6 | APT-06 | Cancel appointment — reason, free the slot, trigger refund where applicable (NEW CANCELLED status — do NOT reuse DeleteStatus) | APT-06.01 | DB: add CANCELLED to status set; CancelReasonCode, CancelReasonText, CancelledBy, CancelledAt; DeleteStatus remains administrative | New | Appointments | §5.2 + §2.3 + §6 | Cancel appointment | Cancel with reason, free the slot, trigger refund where applicable / Cancel with reason, refund handled per policy | Doctor Web + Reception + later Patient | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
257 | 257 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.6 | APT-06 | Cancel appointment — reason, free the slot, trigger refund where applicable (NEW CANCELLED status — do NOT reuse DeleteStatus) | APT-06.02 | API: POST /api/PatientAppointment/CancelAppointment — reason required (enum; text if Other); free slot; offer waitlist stub; if PAID enqueue refund policy | New | Appointments | §5.2 + §2.3 + §6 | Cancel appointment | Cancel with reason, free the slot, trigger refund where applicable / Cancel with reason, refund handled per policy | Doctor Web + Reception + later Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
258 | 258 | M05 | Appointments & scheduling | UI | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.6 | APT-06 | Cancel appointment — reason, free the slot, trigger refund where applicable (NEW CANCELLED status — do NOT reuse DeleteStatus) | APT-06.03 | UI: CancelAppointmentModal shared by Doctor and Reception; dashboard Cancelled filter | New | Appointments | §5.2 + §2.3 + §6 | Cancel appointment | Cancel with reason, free the slot, trigger refund where applicable / Cancel with reason, refund handled per policy | Doctor Web + Reception + later Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
259 | 259 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.6 | APT-06 | Cancel appointment — reason, free the slot, trigger refund where applicable (NEW CANCELLED status — do NOT reuse DeleteStatus) | APT-06.04 | Waitlist worker stub: on cancel, offer freed slot (full waitlist capture is Phase 9 GST waitlist) | New Integration | Appointments | §5.2 + §2.3 + §6 | Cancel appointment | Cancel with reason, free the slot, trigger refund where applicable / Cancel with reason, refund handled per policy | Doctor Web + Reception + later Patient | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
260 | 260 | M05 | Appointments & scheduling | QA | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.6 | APT-06 | Cancel appointment — reason, free the slot, trigger refund where applicable (NEW CANCELLED status — do NOT reuse DeleteStatus) | APT-06.05 | QA: reason mandatory; all three roles (later Patient) cancel with correct authorisation; freed slot bookable | Regression | Appointments | §5.2 + §2.3 + §6 | Cancel appointment | Cancel with reason, free the slot, trigger refund where applicable / Cancel with reason, refund handled per policy | Doctor Web + Reception + later Patient | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
261 | 261 | M05 | Appointments & scheduling | UI | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.7 | APT-07 | Daily schedule setup — define working days, hours and break times (promote modal to first-class screen) | APT-07.01 | Promote DailyScheduleSetupModal to /doctor/schedule; week grid; copy-day; reuse Get/SaveDailySchedule | Existing Improvement | Scheduling | §5.2 | Daily schedule setup | Define working days, hours and break times | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
262 | 262 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.7 | APT-07 | Daily schedule setup — define working days, hours and break times (promote modal to first-class screen) | APT-07.02 | No new API unless validation (breaks, overlapping hours) is missing — add server-side validation | Existing Improvement | Scheduling | §5.2 | Daily schedule setup | Define working days, hours and break times | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
263 | 263 | M05 | Appointments & scheduling | QA | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.7 | APT-07 | Daily schedule setup — define working days, hours and break times (promote modal to first-class screen) | APT-07.03 | QA: save week; public slot generator (Phase 9) uses this data; reception read-only is Phase 5 | Regression | Scheduling | §5.2 | Daily schedule setup | Define working days, hours and break times | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
264 | 264 | M05 | Appointments & scheduling | QA | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.8 | APT-08 | Appointment slot grid — visual slot-by-slot view of the day (keep; public booking reuses this) | APT-08.01 | Regression: slot grid vs schedule | Existing | Scheduling | §5.2 | Appointment slot grid | Visual slot-by-slot view of the day | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
265 | 265 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.8 | APT-08 | Appointment slot grid — visual slot-by-slot view of the day (keep; public booking reuses this) | APT-08.02 | ACL doctor/reception | Existing Improvement | Scheduling | §5.2 | Appointment slot grid | Visual slot-by-slot view of the day | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
266 | 266 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.8 | APT-08 | Appointment slot grid — visual slot-by-slot view of the day (keep; public booking reuses this) | APT-08.03 | Document GetAppointmentSlots as the public-booking engine — do not fork a second slot calculator | Existing | Scheduling | §5.2 | Appointment slot grid | Visual slot-by-slot view of the day | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
267 | 267 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.9 | APT-09 | Consultation payment status on every appointment (schema now; values live in Phase 6) | APT-09.01 | DB: PatientAppointment.PaymentStatus, PaymentMethod, PayAtClinicAllowed; default UNPAID | New | Appointments | §5.2 + §9 | Consultation payment status | See paid, unpaid or pay-at-clinic on every appointment / Doctor, reception and patient all see the same payment status | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
268 | 268 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.9 | APT-09 | Consultation payment status on every appointment (schema now; values live in Phase 6) | APT-09.02 | API: include PaymentStatus on all appointment DTOs (doctor, reception, later public/patient) | New | Appointments | §5.2 + §9 | Consultation payment status | See paid, unpaid or pay-at-clinic on every appointment / Doctor, reception and patient all see the same payment status | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
269 | 269 | M05 | Appointments & scheduling | UI | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.9 | APT-09 | Consultation payment status on every appointment (schema now; values live in Phase 6) | APT-09.03 | UI: Paid / Unpaid / Pay-at-clinic / Failed badges on doctor appointment list | New | Appointments | §5.2 + §9 | Consultation payment status | See paid, unpaid or pay-at-clinic on every appointment / Doctor, reception and patient all see the same payment status | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
270 | 270 | M05 | Appointments & scheduling | QA | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.9 | APT-09 | Consultation payment status on every appointment (schema now; values live in Phase 6) | APT-09.04 | QA: same appointment shows the same badge on doctor and reception | Regression | Appointments | §5.2 + §9 | Consultation payment status | See paid, unpaid or pay-at-clinic on every appointment / Doctor, reception and patient all see the same payment status | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
271 | 271 | M06 | Reception portal | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.1 | REC-01 | Reception login — secure staff access (keep) | REC-01.01 | Regression: reception login with DoctorID claim | Existing | Reception | §6 | Reception login | Secure staff access | Reception Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
272 | 272 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.1 | REC-01 | Reception login — secure staff access (keep) | REC-01.02 | Disabled staff cannot login (after DOC-09) | Existing Improvement | Reception | §6 | Reception login | Secure staff access | Reception Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
273 | 273 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.1 | REC-01 | Reception login — secure staff access (keep) | REC-01.03 | Same Login API as doctor | Existing | Reception | §6 | Reception login | Secure staff access | Reception Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
274 | 274 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.2 | REC-02 | Reception profile — manage own profile details (0% today) | REC-02.01 | Reuse Profile/Me with role=Reception DTO (no new table if UserMaster suffices) | New | Reception | §6 | Reception profile | Manage own profile details | Reception Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
275 | 275 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.2 | REC-02 | Reception profile — manage own profile details (0% today) | REC-02.02 | GET/PUT profile fields allowed for reception; ignore clinic fee/bank | New | Reception | §6 | Reception profile | Manage own profile details | Reception Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
276 | 276 | M06 | Reception portal | UI | 5 | Phase 5 — Reception portal (PDF §6) | 5.2 | REC-02 | Reception profile — manage own profile details (0% today) | REC-02.03 | /profile reception variant | New | Reception | §6 | Reception profile | Manage own profile details | Reception Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
277 | 277 | M06 | Reception portal | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.2 | REC-02 | Reception profile — manage own profile details (0% today) | REC-02.04 | QA: cannot edit doctor qualifications or fee | Regression | Reception | §6 | Reception profile | Manage own profile details | Reception Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
278 | 278 | M06 | Reception portal | UI | 5 | Phase 5 — Reception portal (PDF §6) | 5.3 | REC-03 | Reception home dashboard — purpose-built front-desk dashboard (not only hidden doctor actions) | REC-03.01 | Route /reception (or role-based chrome on existing dashboard) hiding clinical tabs | Existing Improvement | Reception | §6 | Reception home dashboard | Purpose-built front-desk dashboard | Reception Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
279 | 279 | M06 | Reception portal | UI | 5 | Phase 5 — Reception portal (PDF §6) | 5.3 | REC-03 | Reception home dashboard — purpose-built front-desk dashboard (not only hidden doctor actions) | REC-03.02 | Quick actions: new patient, new appointment, collect payment, case paper, schedule | Existing Improvement | Reception | §6 | Reception home dashboard | Purpose-built front-desk dashboard | Reception Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
280 | 280 | M06 | Reception portal | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.3 | REC-03 | Reception home dashboard — purpose-built front-desk dashboard (not only hidden doctor actions) | REC-03.03 | QA: deep-link to Patient Board full clinical URL is 403 for reception | Regression | Reception | §6 | Reception home dashboard | Purpose-built front-desk dashboard | Reception Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
281 | 281 | M06 | Reception portal | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.4 | REC-04 | Create patient — register a walk-in patient quickly (keep) | REC-04.01 | Regression: reception create patient | Existing | Reception | §6 | Create patient | Register a walk-in patient quickly | Reception Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
282 | 282 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.4 | REC-04 | Create patient — register a walk-in patient quickly (keep) | REC-04.02 | ACL: own doctor only | Existing Improvement | Reception | §6 | Create patient | Register a walk-in patient quickly | Reception Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
283 | 283 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.4 | REC-04 | Create patient — register a walk-in patient quickly (keep) | REC-04.03 | Same create-patient API | Existing | Reception | §6 | Create patient | Register a walk-in patient quickly | Reception Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
284 | 284 | M06 | Reception portal | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.5 | REC-05 | Patient search & list — find any patient instantly (keep) | REC-05.01 | Regression: search by name/mobile | Existing | Reception | §6 | Patient search & list | Find any patient instantly | Reception Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
285 | 285 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.5 | REC-05 | Patient search & list — find any patient instantly (keep) | REC-05.02 | Opening a row goes to case paper or appointment, not full repertory | Existing Improvement | Reception | §6 | Patient search & list | Find any patient instantly | Reception Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
286 | 286 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.5 | REC-05 | Patient search & list — find any patient instantly (keep) | REC-05.03 | API unchanged | Existing | Reception | §6 | Patient search & list | Find any patient instantly | Reception Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
287 | 287 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.6 | REC-06 | Create & manage appointments — full appointment management (keep; plus reschedule/cancel from Phase 4) | REC-06.01 | Authorise Reception for Reschedule and Cancel for its own doctor's appointments only | New | Reception | §6 | Create & manage appointments | Full appointment management | Reception Portal | API + SPA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
288 | 288 | M06 | Reception portal | UI | 5 | Phase 5 — Reception portal (PDF §6) | 5.6 | REC-06 | Create & manage appointments — full appointment management (keep; plus reschedule/cancel from Phase 4) | REC-06.02 | Reception UI uses the same Reschedule/Cancel modals as doctor | New | Reception | §6 | Create & manage appointments | Full appointment management | Reception Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
289 | 289 | M06 | Reception portal | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.6 | REC-06 | Create & manage appointments — full appointment management (keep; plus reschedule/cancel from Phase 4) | REC-06.03 | QA: cannot cancel another clinic’s appointment | Regression | Reception | §6 | Create & manage appointments | Full appointment management | Reception Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
290 | 290 | M06 | Reception portal | UI | 5 | Phase 5 — Reception portal (PDF §6) | 5.7 | REC-07 | New appointment — book on behalf of the patient (keep; same VisitType/ConsultMode/fee as APT-02) | REC-07.01 | Share the extended new-appointment modal with reception chrome | Existing Improvement | Reception | §6 | New appointment | Book on behalf of the patient | Reception Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
291 | 291 | M06 | Reception portal | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.7 | REC-07 | New appointment — book on behalf of the patient (keep; same VisitType/ConsultMode/fee as APT-02) | REC-07.02 | QA: in-clinic vs E-Consult both creatable from reception | Regression | Reception | §6 | New appointment | Book on behalf of the patient | Reception Portal | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
292 | 292 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.8 | REC-08 | Waiting queue management — manage the live queue and call the next patient | REC-08.01 | No new table required if status+order suffice; optional QueuePosition | Existing Improvement | Reception | §6 | Waiting queue management | Manage the live queue and call the next patient | Reception Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
293 | 293 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.8 | REC-08 | Waiting queue management — manage the live queue and call the next patient | REC-08.02 | Optional CallNext API that sets status and timestamp | Existing Improvement | Reception | §6 | Waiting queue management | Manage the live queue and call the next patient | Reception Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
294 | 294 | M06 | Reception portal | UI | 5 | Phase 5 — Reception portal (PDF §6) | 5.8 | REC-08 | Waiting queue management — manage the live queue and call the next patient | REC-08.03 | Queue panel: order, wait time, paid/unpaid, Call next | Existing Improvement | Reception | §6 | Waiting queue management | Manage the live queue and call the next patient | Reception Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
295 | 295 | M06 | Reception portal | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.8 | REC-08 | Waiting queue management — manage the live queue and call the next patient | REC-08.04 | QA: two waiting patients; call next picks the right one | Regression | Reception | §6 | Waiting queue management | Manage the live queue and call the next patient | Reception Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
296 | 296 | M06 | Reception portal | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.9 | REC-09 | Appointment status update (reception) — update as patients arrive and are seen (keep) | REC-09.01 | Regression: reception status update | Existing | Reception | §6 | Appointment status update | Update as patients arrive and are seen | Reception Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
297 | 297 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.9 | REC-09 | Appointment status update (reception) — update as patients arrive and are seen (keep) | REC-09.02 | ACL own doctor | Existing Improvement | Reception | §6 | Appointment status update | Update as patients arrive and are seen | Reception Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
298 | 298 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.9 | REC-09 | Appointment status update (reception) — update as patients arrive and are seen (keep) | REC-09.03 | Same status API as doctor | Existing | Reception | §6 | Appointment status update | Update as patients arrive and are seen | Reception Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
299 | 299 | M06 | Reception portal | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.10 | REC-10 | Appointment time update (reception) — adjust timings through the day (keep) | REC-10.01 | Regression: reception UpdateAppointmentTime | Existing | Reception | §6 | Appointment time update | Adjust timings through the day | Reception Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
300 | 300 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.10 | REC-10 | Appointment time update (reception) — adjust timings through the day (keep) | REC-10.02 | ACL own doctor | Existing Improvement | Reception | §6 | Appointment time update | Adjust timings through the day | Reception Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
301 | 301 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.10 | REC-10 | Appointment time update (reception) — adjust timings through the day (keep) | REC-10.03 | Same API | Existing | Reception | §6 | Appointment time update | Adjust timings through the day | Reception Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
302 | 302 | M06 | Reception portal | UI | 5 | Phase 5 — Reception portal (PDF §6) | 5.11 | REC-11 | View doctor schedule — see the doctor’s working schedule (read-only) | REC-11.01 | Frontend only over existing GetDailySchedule — /reception/schedule read-only | New | Reception | §6 | View doctor schedule | See the doctor’s working schedule | Reception Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
303 | 303 | M06 | Reception portal | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.11 | REC-11 | View doctor schedule — see the doctor’s working schedule (read-only) | REC-11.02 | QA: edit buttons hidden; doctor can still edit on /doctor/schedule | Regression | Reception | §6 | View doctor schedule | See the doctor’s working schedule | Reception Portal | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
304 | 304 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.12 | REC-12 | Log case paper / chief complaint — record the reason for visit before the consultation | REC-12.01 | Reuse complaints table; add CreatedByRole=Reception | New | Reception | §6 | Log case paper / chief complaint | Record the reason for visit before the consultation | Reception Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
305 | 305 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.12 | REC-12 | Log case paper / chief complaint — record the reason for visit before the consultation | REC-12.02 | POST case-paper subset of SaveComplaints; GET on board | New | Reception | §6 | Log case paper / chief complaint | Record the reason for visit before the consultation | Reception Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
306 | 306 | M06 | Reception portal | UI | 5 | Phase 5 — Reception portal (PDF §6) | 5.12 | REC-12 | Log case paper / chief complaint — record the reason for visit before the consultation | REC-12.03 | /reception/case-paper or limited board | New | Reception | §6 | Log case paper / chief complaint | Record the reason for visit before the consultation | Reception Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
307 | 307 | M06 | Reception portal | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.12 | REC-12 | Log case paper / chief complaint — record the reason for visit before the consultation | REC-12.04 | QA: doctor sees CC; reception 403 on repertory APIs | Regression | Reception | §6 | Log case paper / chief complaint | Record the reason for visit before the consultation | Reception Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
308 | 308 | M06 | Reception portal | UI | 5 | Phase 5 — Reception portal (PDF §6) | 5.13 | REC-13 | Collect consultation payment — cash, UPI, card or payment link and issue a receipt (API in Phase 6; UI shell now) | REC-13.01 | Specify receipt fields (amount, method, appointment, GST placeholder) for Phase 6 implementation | New | Reception | §6 + §9 | Collect consultation payment | Take cash, UPI, card or payment link and issue a receipt | Reception Portal | Design | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
309 | 309 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.13 | REC-13 | Collect consultation payment — cash, UPI, card or payment link and issue a receipt (API in Phase 6; UI shell now) | REC-13.02 | Do not write PaymentStatus=PAID from the client — Account/webhook is source of truth (Phase 6) | New | Reception | §6 + §9 | Collect consultation payment | Take cash, UPI, card or payment link and issue a receipt | Reception Portal | Architecture | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
310 | 310 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.1 | PAY-01 | Consultation fee configuration — each doctor’s fee set and displayed to patients | PAY-01.01 | DB: ConsultFeeConfig (DoctorId, InClinicFee, TeleFee, InstantSurcharge, Currency, PayAtClinicEnabled, EffectiveFrom) | New | Payments | §9 | Consultation fee configuration | Each doctor’s fee set and displayed to patients | Doctor profile + Public + Admin | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
311 | 311 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.1 | PAY-01 | Consultation fee configuration — each doctor’s fee set and displayed to patients | PAY-01.02 | API: GET public fee; PUT doctor/admin; history of changes in audit | New | Payments | §9 | Consultation fee configuration | Each doctor’s fee set and displayed to patients | Doctor profile + Public + Admin | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
312 | 312 | M07 | Payment system | UI | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.1 | PAY-01 | Consultation fee configuration — each doctor’s fee set and displayed to patients | PAY-01.03 | Doctor profile fee tab + later public doctor card | New | Payments | §9 | Consultation fee configuration | Each doctor’s fee set and displayed to patients | Doctor profile + Public + Admin | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
313 | 313 | M07 | Payment system | QA | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.1 | PAY-01 | Consultation fee configuration — each doctor’s fee set and displayed to patients | PAY-01.04 | QA: changing fee does not alter already-created unpaid orders without a rule (document the rule) | Regression | Payments | §9 | Consultation fee configuration | Each doctor’s fee set and displayed to patients | Doctor profile + Public + Admin | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
314 | 314 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.2 | PAY-02 | Automatic payment verification — bank/webhook is source of truth, not the patient’s screen | PAY-02.01 | DB: PaymentOrder, PaymentEvent (raw webhook), idempotency key on payment_id | New | Payments | §9 | Automatic payment verification | Payments confirmed by the bank, not by the patient’s screen — nothing is lost if the app or browser closes | Shared | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
315 | 315 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.2 | PAY-02 | Automatic payment verification — bank/webhook is source of truth, not the patient’s screen | PAY-02.02 | Port Order/GenerateOrderId pattern to .NET 8; move keys to configuration; do not commit secrets | New Integration | Payments | §9 | Automatic payment verification | Payments confirmed by the bank, not by the patient’s screen — nothing is lost if the app or browser closes | Shared | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
316 | 316 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.2 | PAY-02 | Automatic payment verification — bank/webhook is source of truth, not the patient’s screen | PAY-02.03 | Webhook handler payment.captured / payment.failed; signature verify; never trust client-only success | New Integration | Payments | §9 | Automatic payment verification | Payments confirmed by the bank, not by the patient’s screen — nothing is lost if the app or browser closes | Shared | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
317 | 317 | M07 | Payment system | QA | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.2 | PAY-02 | Automatic payment verification — bank/webhook is source of truth, not the patient’s screen | PAY-02.04 | QA: duplicate webhook; delayed webhook; failed capture; app closed mid-checkout | Regression | Payments | §9 | Automatic payment verification | Payments confirmed by the bank, not by the patient’s screen — nothing is lost if the app or browser closes | Shared | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | 2 | Not Started |  | Edit on module sheet
318 | 318 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.3 | PAY-03 | Online consultation payment — patient pays by card, UPI, netbanking or wallet | PAY-03.01 | DB: ConsultPayment linked to PaymentOrder + PatientAppId — NOT PackageEntryDetail | New | Payments | §9 + §4 + §2.3 | Online consultation payment | Patient pays by card, UPI, netbanking or wallet / Pay the consultation fee at the time of booking / Pay the consultation fee inside the app | Public web + later Patient app | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
319 | 319 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.3 | PAY-03 | Online consultation payment — patient pays by card, UPI, netbanking or wallet | PAY-03.02 | API: CreateConsultOrder, Verify (optional), status by appointment; amount from ConsultFeeConfig | New | Payments | §9 + §4 + §2.3 | Online consultation payment | Patient pays by card, UPI, netbanking or wallet / Pay the consultation fee at the time of booking / Pay the consultation fee inside the app | Public web + later Patient app | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
320 | 320 | M07 | Payment system | UI | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.3 | PAY-03 | Online consultation payment — patient pays by card, UPI, netbanking or wallet | PAY-03.03 | Public /book/pay/:bookingId using Razorpay pattern from Widgets.js but consult order API | New | Payments | §9 + §4 + §2.3 | Online consultation payment | Patient pays by card, UPI, netbanking or wallet / Pay the consultation fee at the time of booking / Pay the consultation fee inside the app | Public web + later Patient app | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
321 | 321 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.3 | PAY-03 | Online consultation payment — patient pays by card, UPI, netbanking or wallet | PAY-03.04 | Razorpay Checkout methods: card, UPI, netbanking, wallet as enabled on the account | New Integration | Payments | §9 + §4 + §2.3 | Online consultation payment | Patient pays by card, UPI, netbanking or wallet / Pay the consultation fee at the time of booking / Pay the consultation fee inside the app | Public web + later Patient app | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
322 | 322 | M07 | Payment system | QA | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.3 | PAY-03 | Online consultation payment — patient pays by card, UPI, netbanking or wallet | PAY-03.05 | QA: success, failure, pending, double-click create order idempotent | Regression | Payments | §9 + §4 + §2.3 | Online consultation payment | Patient pays by card, UPI, netbanking or wallet / Pay the consultation fee at the time of booking / Pay the consultation fee inside the app | Public web + later Patient app | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
323 | 323 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.4 | PAY-04 | Reception payment collection — cash, UPI, card or payment link with printed receipt | PAY-04.01 | Reuse PaymentOrder + ConsultPayment with Method=CASH/UPI_OFFLINE/CARD_POS/PAY_LINK | New | Payments | §9 + §6 | Reception payment collection | Cash, UPI, card or payment link with printed receipt | Reception Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
324 | 324 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.4 | PAY-04 | Reception payment collection — cash, UPI, card or payment link with printed receipt | PAY-04.02 | API: CollectAtReception; generate pay-link; print receipt payload | New | Payments | §9 + §6 | Reception payment collection | Cash, UPI, card or payment link with printed receipt | Reception Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
325 | 325 | M07 | Payment system | UI | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.4 | PAY-04 | Reception payment collection — cash, UPI, card or payment link with printed receipt | PAY-04.03 | Reception collect modal: amount, method, GST placeholder, print receipt | New | Payments | §9 + §6 | Reception payment collection | Cash, UPI, card or payment link with printed receipt | Reception Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
326 | 326 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.4 | PAY-04 | Reception payment collection — cash, UPI, card or payment link with printed receipt | PAY-04.04 | Pay-link SMS/WhatsApp optional (Phase 12); must still ledger if notify fails | New Integration | Payments | §9 + §6 | Reception payment collection | Cash, UPI, card or payment link with printed receipt | Reception Portal | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
327 | 327 | M07 | Payment system | QA | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.4 | PAY-04 | Reception payment collection — cash, UPI, card or payment link with printed receipt | PAY-04.05 | QA: cash collection visible in clinic collection view after Phase 7; cannot mark PAID without this API | Regression | Payments | §9 + §6 | Reception payment collection | Cash, UPI, card or payment link with printed receipt | Reception Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
328 | 328 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.5 | PAY-05 | Pay-at-clinic option — book now, pay at the clinic where the doctor allows it | PAY-05.01 | Honor PayAtClinicEnabled on public create-booking and checkout | New | Payments | §9 | Pay-at-clinic option | Book now, pay at the clinic where the doctor allows it | Public + Doctor + Reception | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
329 | 329 | M07 | Payment system | UI | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.5 | PAY-05 | Pay-at-clinic option — book now, pay at the clinic where the doctor allows it | PAY-05.02 | UI: public booking shows Pay at clinic vs Pay now; doctor list badge | New | Payments | §9 | Pay-at-clinic option | Book now, pay at the clinic where the doctor allows it | Public + Doctor + Reception | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
330 | 330 | M07 | Payment system | QA | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.5 | PAY-05 | Pay-at-clinic option — book now, pay at the clinic where the doctor allows it | PAY-05.03 | QA: doctor flag off → pay-at-clinic hidden; reception can still collect | Regression | Payments | §9 | Pay-at-clinic option | Book now, pay at the clinic where the doctor allows it | Public + Doctor + Reception | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
331 | 331 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.6 | PAY-06 | Doctor subscription payment — buy and renew subscription packages (complete remaining ~30%) | PAY-06.01 | Reuse PAY-02 webhook for S1 orders; link PackageEntryDetail as S1 only | Existing Improvement | Payments | §9 | Doctor subscription payment | Buy and renew subscription packages | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | 2 | Not Started |  | Edit on module sheet
332 | 332 | M07 | Payment system | UI | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.6 | PAY-06 | Doctor subscription payment — buy and renew subscription packages (complete remaining ~30%) | PAY-06.02 | Widgets.js: handle failed pay; show invoice when Phase 7 invoice exists | Existing Improvement | Payments | §9 | Doctor subscription payment | Buy and renew subscription packages | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
333 | 333 | M07 | Payment system | QA | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.6 | PAY-06 | Doctor subscription payment — buy and renew subscription packages (complete remaining ~30%) | PAY-06.03 | QA: renew, fail, webhook delay, last-5-days warning still works | Regression | Payments | §9 | Doctor subscription payment | Buy and renew subscription packages | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
334 | 334 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.7 | PAY-07 | Medicine payment — pay online or cash on delivery (API contract now; HomeoMeds Phase 14 implements orders) | PAY-07.01 | Extend PaymentOrder with Stream=CONSULT¦SUBSCRIPTION¦MEDICINE so Phase 14 can attach without schema rewrite | New | Payments | §9 + §12 | Medicine payment | Pay online or choose cash on delivery / Both options supported, with status tracking | Shared | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
335 | 335 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.7 | PAY-07 | Medicine payment — pay online or cash on delivery (API contract now; HomeoMeds Phase 14 implements orders) | PAY-07.02 | API stub: CreateMedicineOrder payment + COD status enum — implemented fully in Phase 14 | New | Payments | §9 + §12 | Medicine payment | Pay online or choose cash on delivery / Both options supported, with status tracking | Shared | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
336 | 336 | M07 | Payment system | QA | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.7 | PAY-07 | Medicine payment — pay online or cash on delivery (API contract now; HomeoMeds Phase 14 implements orders) | PAY-07.03 | QA: stream isolation query (consult vs medicine totals differ) | Regression | Payments | §9 + §12 | Medicine payment | Pay online or choose cash on delivery / Both options supported, with status tracking | Shared | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
337 | 337 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.8 | PAY-08 | Payment status everywhere — doctor, reception and patient all see the same payment status | PAY-08.01 | Single source: PaymentOrder/ConsultPayment → Appointment.PaymentStatus updated only by webhook or CollectAtReception | New | Payments | §9 | Payment status everywhere | Doctor, reception and patient all see the same payment status | All | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
338 | 338 | M07 | Payment system | UI | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.8 | PAY-08 | Payment status everywhere — doctor, reception and patient all see the same payment status | PAY-08.02 | Surface badges: doctor, reception; public confirmation page; patient app in Phase 16 consumes same API | New | Payments | §9 | Payment status everywhere | Doctor, reception and patient all see the same payment status | All | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
339 | 339 | M07 | Payment system | QA | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.8 | PAY-08 | Payment status everywhere — doctor, reception and patient all see the same payment status | PAY-08.03 | QA: three roles, one appointment, same enum value | Regression | Payments | §9 | Payment status everywhere | Doctor, reception and patient all see the same payment status | All | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
340 | 340 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.9 | PAY-09 | Refunds — processed and tracked against the original payment | PAY-09.01 | DB: Refund (PaymentOrderId, Amount, Reason, Status, GatewayRefundId, ByUserId, At) | New | Payments | §9 + §8 + §2.8 | Refunds | Processed and tracked against the original payment / Issue and track refunds | Account + Patient | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
341 | 341 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.9 | PAY-09 | Refunds — processed and tracked against the original payment | PAY-09.02 | API: create refund (Account); webhook refund.processed; cancel-appointment policy engine (full/partial/none) | New | Payments | §9 + §8 + §2.8 | Refunds | Processed and tracked against the original payment / Issue and track refunds | Account + Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
342 | 342 | M07 | Payment system | UI | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.9 | PAY-09 | Refunds — processed and tracked against the original payment | PAY-09.03 | Account refund screen in Phase 7; patient payments list in Phase 16 | New | Payments | §9 + §8 + §2.8 | Refunds | Processed and tracked against the original payment / Issue and track refunds | Account + Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
343 | 343 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.9 | PAY-09 | Refunds — processed and tracked against the original payment | PAY-09.04 | Razorpay refund API + webhook | New Integration | Payments | §9 + §8 + §2.8 | Refunds | Processed and tracked against the original payment / Issue and track refunds | Account + Patient | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
344 | 344 | M07 | Payment system | QA | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.9 | PAY-09 | Refunds — processed and tracked against the original payment | PAY-09.05 | QA: double refund blocked; cash collection refund is ledger-only per PRE-02 policy | Regression | Payments | §9 + §8 + §2.8 | Refunds | Processed and tracked against the original payment / Issue and track refunds | Account + Patient | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
345 | 345 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.10 | PAY-10 | Payment receipts & invoices — issued for every transaction | PAY-10.01 | DB: Invoice (Number, Series, Stream, PaymentOrderId, GstBreakup, PdfPath) | New | Payments | §9 + §8 | Payment receipts & invoices | Issued for every transaction / Invoice numbering and tax reporting | All | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
346 | 346 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.10 | PAY-10 | Payment receipts & invoices — issued for every transaction | PAY-10.02 | API: get invoice by payment; generate PDF via SecureDocument | New | Payments | §9 + §8 | Payment receipts & invoices | Issued for every transaction / Invoice numbering and tax reporting | All | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
347 | 347 | M07 | Payment system | UI | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.10 | PAY-10 | Payment receipts & invoices — issued for every transaction | PAY-10.03 | Print/download on reception, doctor (subscription), later patient app | New | Payments | §9 + §8 | Payment receipts & invoices | Issued for every transaction / Invoice numbering and tax reporting | All | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
348 | 348 | M07 | Payment system | QA | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.10 | PAY-10 | Payment receipts & invoices — issued for every transaction | PAY-10.04 | QA: unique invoice numbers; cancelled invoice not reused | Regression | Payments | §9 + §8 | Payment receipts & invoices | Issued for every transaction / Invoice numbering and tax reporting | All | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
349 | 349 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.11 | PAY-11 | Complete payment audit trail — every transaction traceable end to end by Homeocentrum | PAY-11.01 | Persist raw webhook JSON; correlation id on Appointment and Ledger | New | Payments | §9 + §17 | Complete audit trail | Every transaction traceable end to end by Homeocentrum | Account | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
350 | 350 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.11 | PAY-11 | Complete payment audit trail — every transaction traceable end to end by Homeocentrum | PAY-11.02 | Account query API: trail by appointment / payment / doctor (Phase 7 UI) | New | Payments | §9 + §17 | Complete audit trail | Every transaction traceable end to end by Homeocentrum | Account | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
351 | 351 | M07 | Payment system | QA | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.11 | PAY-11 | Complete payment audit trail — every transaction traceable end to end by Homeocentrum | PAY-11.03 | QA: missing webhook still shows PENDING not PAID | Regression | Payments | §9 + §17 | Complete audit trail | Every transaction traceable end to end by Homeocentrum | Account | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
352 | 352 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.1 | FIN-01 | Unified transaction ledger — every rupee that moves through the platform, in one record | FIN-01.01 | DB: LedgerEntry (Stream, Direction, Amount, Gst, Commission, EntityType, EntityId, PaymentOrderId, At) immutable | New | Account | §8 | Unified transaction ledger | Every rupee that moves through the platform, in one record | Account Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
353 | 353 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.1 | FIN-01 | Unified transaction ledger — every rupee that moves through the platform, in one record | FIN-01.02 | API: GET /account/ledger filters; export; write-only from payment/settlement services | New | Account | §8 | Unified transaction ledger | Every rupee that moves through the platform, in one record | Account Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
354 | 354 | M08 | Account & finance | UI | 7 | Phase 7 — Account & finance department (PDF §8) | 7.1 | FIN-01 | Unified transaction ledger — every rupee that moves through the platform, in one record | FIN-01.03 | /account/ledger UI — Account layout sidebar Finance | New | Account | §8 | Unified transaction ledger | Every rupee that moves through the platform, in one record | Account Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
355 | 355 | M08 | Account & finance | QA | 7 | Phase 7 — Account & finance department (PDF §8) | 7.1 | FIN-01 | Unified transaction ledger — every rupee that moves through the platform, in one record | FIN-01.04 | QA: consult pay writes S2; subscription writes S1; they never share one row | Regression | Account | §8 | Unified transaction ledger | Every rupee that moves through the platform, in one record | Account Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
356 | 356 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.2 | FIN-02 | Consultation payment reconciliation — online payments and reception collections matched and verified | FIN-02.01 | Reuse ConsultPayment + Appointment; reconciliation query | New | Account | §8 + §7.2 + §16 | Consultation payment reconciliation | Online payments and reception collections matched and verified / Match every booking against every payment | Account + Admin | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
357 | 357 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.2 | FIN-02 | Consultation payment reconciliation — online payments and reception collections matched and verified | FIN-02.02 | GET Admin/Account reconciliation + aggregates | New | Account | §8 + §7.2 + §16 | Consultation payment reconciliation | Online payments and reception collections matched and verified / Match every booking against every payment | Account + Admin | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
358 | 358 | M08 | Account & finance | UI | 7 | Phase 7 — Account & finance department (PDF §8) | 7.2 | FIN-02 | Consultation payment reconciliation — online payments and reception collections matched and verified | FIN-02.03 | /account/consult-recon and /admin/consult-payments (same data, Account owns, Admin views) | New | Account | §8 + §7.2 + §16 | Consultation payment reconciliation | Online payments and reception collections matched and verified / Match every booking against every payment | Account + Admin | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
359 | 359 | M08 | Account & finance | QA | 7 | Phase 7 — Account & finance department (PDF §8) | 7.2 | FIN-02 | Consultation payment reconciliation — online payments and reception collections matched and verified | FIN-02.04 | QA: unmatched payment appears in exception queue not silent | Regression | Account | §8 + §7.2 + §16 | Consultation payment reconciliation | Online payments and reception collections matched and verified / Match every booking against every payment | Account + Admin | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
360 | 360 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.3 | FIN-03 | Medicine ledger — medicine money tracked separately from consultation money | FIN-03.01 | LedgerEntry stream MEDICINE with SplitSeller/SplitPlatform/SplitDelivery | New | Account | §8 + §12 | Medicine ledger | Medicine money tracked separately from consultation money / Seller, platform and delivery shares recorded separately from consultation money | Account Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
361 | 361 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.3 | FIN-03 | Medicine ledger — medicine money tracked separately from consultation money | FIN-03.02 | GET /account/medicine-ledger | New | Account | §8 + §12 | Medicine ledger | Medicine money tracked separately from consultation money / Seller, platform and delivery shares recorded separately from consultation money | Account Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
362 | 362 | M08 | Account & finance | UI | 7 | Phase 7 — Account & finance department (PDF §8) | 7.3 | FIN-03 | Medicine ledger — medicine money tracked separately from consultation money | FIN-03.03 | /account/medicine-ledger UI (empty until HomeoMeds orders exist — still ship the screen) | New | Account | §8 + §12 | Medicine ledger | Medicine money tracked separately from consultation money / Seller, platform and delivery shares recorded separately from consultation money | Account Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
363 | 363 | M08 | Account & finance | QA | 7 | Phase 7 — Account & finance department (PDF §8) | 7.3 | FIN-03 | Medicine ledger — medicine money tracked separately from consultation money | FIN-03.04 | QA: S2 consult row never appears on this screen | Regression | Account | §8 + §12 | Medicine ledger | Medicine money tracked separately from consultation money / Seller, platform and delivery shares recorded separately from consultation money | Account Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
364 | 364 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.4 | FIN-04 | Settlement runs — scheduled settlement of amounts due to doctors and pharmacies | FIN-04.01 | DB: SettlementRun, SettlementLine | New | Account | §8 + §16 | Settlement runs | Scheduled settlement of amounts due to doctors and pharmacies | Account Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
365 | 365 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.4 | FIN-04 | Settlement runs — scheduled settlement of amounts due to doctors and pharmacies | FIN-04.02 | API: create run (dry-run + commit); list; detail | New | Account | §8 + §16 | Settlement runs | Scheduled settlement of amounts due to doctors and pharmacies | Account Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
366 | 366 | M08 | Account & finance | UI | 7 | Phase 7 — Account & finance department (PDF §8) | 7.4 | FIN-04 | Settlement runs — scheduled settlement of amounts due to doctors and pharmacies | FIN-04.03 | /account/settlements | New | Account | §8 + §16 | Settlement runs | Scheduled settlement of amounts due to doctors and pharmacies | Account Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
367 | 367 | M08 | Account & finance | QA | 7 | Phase 7 — Account & finance department (PDF §8) | 7.4 | FIN-04 | Settlement runs — scheduled settlement of amounts due to doctors and pharmacies | FIN-04.04 | QA: hold days exclude too-new captures; refunds net out | Regression | Account | §8 + §16 | Settlement runs | Scheduled settlement of amounts due to doctors and pharmacies | Account Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
368 | 368 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.5 | FIN-05 | Payout approval — payouts released only after OTP-verified approval | FIN-05.01 | DB: Payout (PayeeType Doctor¦Pharmacy, Amount, Status, SettlementRunId) | New | Account | §8 + §17 | Payout approval | Payouts released only after OTP-verified approval | Account Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
369 | 369 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.5 | FIN-05 | Payout approval — payouts released only after OTP-verified approval | FIN-05.02 | API: ApprovePayout with OTP; reject | New | Account | §8 + §17 | Payout approval | Payouts released only after OTP-verified approval | Account Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
370 | 370 | M08 | Account & finance | UI | 7 | Phase 7 — Account & finance department (PDF §8) | 7.5 | FIN-05 | Payout approval — payouts released only after OTP-verified approval | FIN-05.03 | /account/payouts | New | Account | §8 + §17 | Payout approval | Payouts released only after OTP-verified approval | Account Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
371 | 371 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.5 | FIN-05 | Payout approval — payouts released only after OTP-verified approval | FIN-05.04 | Bank file / Razorpay payout adapter per PRE-01 | New Integration | Account | §8 + §17 | Payout approval | Payouts released only after OTP-verified approval | Account Portal | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
372 | 372 | M08 | Account & finance | QA | 7 | Phase 7 — Account & finance department (PDF §8) | 7.5 | FIN-05 | Payout approval — payouts released only after OTP-verified approval | FIN-05.05 | QA: Account role only; replay OTP; Admin 403 on approve | Regression | Account | §8 + §17 | Payout approval | Payouts released only after OTP-verified approval | Account Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
373 | 373 | M08 | Account & finance | UI | 7 | Phase 7 — Account & finance department (PDF §8) | 7.6 | FIN-06 | Refund processing — Account issues and tracks refunds (uses PAY-09) | FIN-06.01 | UI /account/refunds: original payment, amount, reason, status | New | Account | §8 | Refund processing | Issue and track refunds | Account Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
374 | 374 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.6 | FIN-06 | Refund processing — Account issues and tracks refunds (uses PAY-09) | FIN-06.02 | Ledger reverse entries on successful refund | New | Account | §8 | Refund processing | Issue and track refunds | Account Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
375 | 375 | M08 | Account & finance | QA | 7 | Phase 7 — Account & finance department (PDF §8) | 7.6 | FIN-06 | Refund processing — Account issues and tracks refunds (uses PAY-09) | FIN-06.03 | QA: partial refund; full refund; cash-policy path | Regression | Account | §8 | Refund processing | Issue and track refunds | Account Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
376 | 376 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.7 | FIN-07 | Payment exception handling — investigate and resolve every failed or disputed payment | FIN-07.01 | DB: PaymentException state machine | New | Account | §8 + §7.2 | Payment exception handling | Investigate and resolve every failed or disputed payment / Every failed or mismatched payment surfaced for action | Account + Admin | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
377 | 377 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.7 | FIN-07 | Payment exception handling — investigate and resolve every failed or disputed payment | FIN-07.02 | API: list/detail/retry/resolve; created by webhook mismatches | New | Account | §8 + §7.2 | Payment exception handling | Investigate and resolve every failed or disputed payment / Every failed or mismatched payment surfaced for action | Account + Admin | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
378 | 378 | M08 | Account & finance | UI | 7 | Phase 7 — Account & finance department (PDF §8) | 7.7 | FIN-07 | Payment exception handling — investigate and resolve every failed or disputed payment | FIN-07.03 | /account/exceptions and /admin/payment-exceptions (same queue) | New | Account | §8 + §7.2 | Payment exception handling | Investigate and resolve every failed or disputed payment / Every failed or mismatched payment surfaced for action | Account + Admin | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
379 | 379 | M08 | Account & finance | QA | 7 | Phase 7 — Account & finance department (PDF §8) | 7.7 | FIN-07 | Payment exception handling — investigate and resolve every failed or disputed payment | FIN-07.04 | QA: failed webhook creates exception; manual resolve requires Account role + OTP | Regression | Account | §8 + §7.2 | Payment exception handling | Investigate and resolve every failed or disputed payment / Every failed or mismatched payment surfaced for action | Account + Admin | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
380 | 380 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.8 | FIN-08 | GST & invoice reports — invoice numbering and tax reporting | FIN-08.01 | Reuse Invoice; tax config table (GstRate, treatment flags) | New | Account | §8 + §16 | GST & invoice reports | Invoice numbering and tax reporting | Account Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
381 | 381 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.8 | FIN-08 | GST & invoice reports — invoice numbering and tax reporting | FIN-08.02 | GET tax report + CSV | New | Account | §8 + §16 | GST & invoice reports | Invoice numbering and tax reporting | Account Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
382 | 382 | M08 | Account & finance | UI | 7 | Phase 7 — Account & finance department (PDF §8) | 7.8 | FIN-08 | GST & invoice reports — invoice numbering and tax reporting | FIN-08.03 | /account/tax | New | Account | §8 + §16 | GST & invoice reports | Invoice numbering and tax reporting | Account Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
383 | 383 | M08 | Account & finance | QA | 7 | Phase 7 — Account & finance department (PDF §8) | 7.8 | FIN-08 | GST & invoice reports — invoice numbering and tax reporting | FIN-08.04 | QA: rates come from config; changing rate does not rewrite old invoices | Regression | Account | §8 + §16 | GST & invoice reports | Invoice numbering and tax reporting | Account Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
384 | 384 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.9 | FIN-09 | Payee records — bank and KYC details for doctors and pharmacies | FIN-09.01 | DB: Payee (DoctorId/PharmacyId, Bank, PAN, KYC status) | New | Account | §8 | Payee records | Bank and KYC details for doctors and pharmacies | Account Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
385 | 385 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.9 | FIN-09 | Payee records — bank and KYC details for doctors and pharmacies | FIN-09.02 | API: list/update; OTP on bank change | New | Account | §8 | Payee records | Bank and KYC details for doctors and pharmacies | Account Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
386 | 386 | M08 | Account & finance | UI | 7 | Phase 7 — Account & finance department (PDF §8) | 7.9 | FIN-09 | Payee records — bank and KYC details for doctors and pharmacies | FIN-09.03 | /account/payees | New | Account | §8 | Payee records | Bank and KYC details for doctors and pharmacies | Account Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
387 | 387 | M08 | Account & finance | QA | 7 | Phase 7 — Account & finance department (PDF §8) | 7.9 | FIN-09 | Payee records — bank and KYC details for doctors and pharmacies | FIN-09.04 | QA: missing KYC blocks FIN-05 | Regression | Account | §8 | Payee records | Bank and KYC details for doctors and pharmacies | Account Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
388 | 388 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.10 | FIN-10 | Clinic collection view — cash and UPI collected at reception, per clinic and per day | FIN-10.01 | Query ConsultPayment Method in CASH/UPI_OFFLINE grouped by DoctorId/date | New | Account | §8 | Clinic collection view | Cash and UPI collected at reception, per clinic and per day | Account Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
389 | 389 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.10 | FIN-10 | Clinic collection view — cash and UPI collected at reception, per clinic and per day | FIN-10.02 | GET clinic-collections | New | Account | §8 | Clinic collection view | Cash and UPI collected at reception, per clinic and per day | Account Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
390 | 390 | M08 | Account & finance | UI | 7 | Phase 7 — Account & finance department (PDF §8) | 7.10 | FIN-10 | Clinic collection view — cash and UPI collected at reception, per clinic and per day | FIN-10.03 | /account/clinic-collections | New | Account | §8 | Clinic collection view | Cash and UPI collected at reception, per clinic and per day | Account Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
391 | 391 | M08 | Account & finance | QA | 7 | Phase 7 — Account & finance department (PDF §8) | 7.10 | FIN-10 | Clinic collection view — cash and UPI collected at reception, per clinic and per day | FIN-10.04 | QA: online Razorpay consults do not appear as clinic cash | Regression | Account | §8 | Clinic collection view | Cash and UPI collected at reception, per clinic and per day | Account Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
392 | 392 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.11 | FIN-11 | Separation of duties — Account controls money; Admin controls platform and clinical data | FIN-11.01 | Seed Account role menus: ledger, recon, medicine ledger, exceptions, settlements, payouts, refunds, tax, payees, clinic collections | New | Account | §8 | Separation of duties | The Account department controls money. Admin controls the platform and clinical data. Neither can perform the other’s role, which protects both. | Admin + Account | Configuration | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
393 | 393 | M08 | Account & finance | QA | 7 | Phase 7 — Account & finance department (PDF §8) | 7.11 | FIN-11 | Separation of duties — Account controls money; Admin controls platform and clinical data | FIN-11.02 | Negative tests: Admin POST ApprovePayout → 403; Account POST repertory section → 403 | Regression | Account | §8 | Separation of duties | The Account department controls money. Admin controls the platform and clinical data. Neither can perform the other’s role, which protects both. | Admin + Account | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
394 | 394 | M09 | Trust & verification | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.1 | TRU-01 | Doctor credentialing — doctors upload qualification and registration documents for review | TRU-01.01 | DB: DoctorVerification (Pending/Approved/Rejected/NeedsInfo), DoctorCredentialDocument | New | Trust | §13 + §7.2 | Doctor credentialing | Doctors upload qualification and registration documents for review | Doctor Web + Admin | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
395 | 395 | M09 | Trust & verification | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.1 | TRU-01 | Doctor credentialing — doctors upload qualification and registration documents for review | TRU-01.02 | API: upload documents; MyStatus; RegisterDoctor modified to VerificationStatus=Pending (not auto-practice) | New | Trust | §13 + §7.2 | Doctor credentialing | Doctors upload qualification and registration documents for review | Doctor Web + Admin | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
396 | 396 | M09 | Trust & verification | UI | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.1 | TRU-01 | Doctor credentialing — doctors upload qualification and registration documents for review | TRU-01.03 | Doctor profile credentials tab + document upload | New | Trust | §13 + §7.2 | Doctor credentialing | Doctors upload qualification and registration documents for review | Doctor Web + Admin | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
397 | 397 | M09 | Trust & verification | QA | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.1 | TRU-01 | Doctor credentialing — doctors upload qualification and registration documents for review | TRU-01.04 | QA: doctor without docs cannot appear in public directory (Phase 9) | Regression | Trust | §13 + §7.2 | Doctor credentialing | Doctors upload qualification and registration documents for review | Doctor Web + Admin | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
398 | 398 | M09 | Trust & verification | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.2 | TRU-02 | Verification review — Admin approves, rejects or requests further information | TRU-02.01 | Reuse DoctorVerification | New | Trust | §13 + §7.2 | Verification review | Admin approves, rejects or requests more information before they can practise on the platform | Admin Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
399 | 399 | M09 | Trust & verification | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.2 | TRU-02 | Verification review — Admin approves, rejects or requests further information | TRU-02.02 | API: Queue, {id}, Approve, Reject, RequestInfo | New | Trust | §13 + §7.2 | Verification review | Admin approves, rejects or requests more information before they can practise on the platform | Admin Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
400 | 400 | M09 | Trust & verification | UI | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.2 | TRU-02 | Verification review — Admin approves, rejects or requests further information | TRU-02.03 | /admin/doctor-credentialing and /:doctorId; verification column on users list | New | Trust | §13 + §7.2 | Verification review | Admin approves, rejects or requests more information before they can practise on the platform | Admin Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
401 | 401 | M09 | Trust & verification | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.2 | TRU-02 | Verification review — Admin approves, rejects or requests further information | TRU-02.04 | Email notify (Phase 12 SMTP already used for activation) | New Integration | Trust | §13 + §7.2 | Verification review | Admin approves, rejects or requests more information before they can practise on the platform | Admin Portal | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
402 | 402 | M09 | Trust & verification | QA | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.2 | TRU-02 | Verification review — Admin approves, rejects or requests further information | TRU-02.05 | QA: reject reason required; request-info reopens Pending | Regression | Trust | §13 + §7.2 | Verification review | Admin approves, rejects or requests more information before they can practise on the platform | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
403 | 403 | M09 | Trust & verification | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.3 | TRU-03 | Verified badge — patients see which doctors have been verified | TRU-03.01 | Public doctor DTO includes isVerified | New | Trust | §13 + §2.2 | Verified badge / Credentials & verification | Patients see which doctors have been verified / Verified badge showing the doctor’s credentials are checked | Public + Patient app | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
404 | 404 | M09 | Trust & verification | UI | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.3 | TRU-03 | Verified badge — patients see which doctors have been verified | TRU-03.02 | Badge component for website (Phase 9) and patient app (Phase 16) | New | Trust | §13 + §2.2 | Verified badge / Credentials & verification | Patients see which doctors have been verified / Verified badge showing the doctor’s credentials are checked | Public + Patient app | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
405 | 405 | M09 | Trust & verification | QA | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.3 | TRU-03 | Verified badge — patients see which doctors have been verified | TRU-03.03 | QA: pending doctor has no badge | Regression | Trust | §13 + §2.2 | Verified badge / Credentials & verification | Patients see which doctors have been verified / Verified badge showing the doctor’s credentials are checked | Public + Patient app | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
406 | 406 | M09 | Trust & verification | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.4 | TRU-04 | Practice gate — only verified doctors appear to patients and take paid consultations | TRU-04.01 | Public doctor list filter VerificationStatus=Approved | New | Trust | §13 | Practice gate | Only verified doctors appear to patients and take paid consultations | Public + Payments | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
407 | 407 | M09 | Trust & verification | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.4 | TRU-04 | Practice gate — only verified doctors appear to patients and take paid consultations | TRU-04.02 | CreateConsultOrder rejects unverified doctor for patient-originated bookings | New | Trust | §13 | Practice gate | Only verified doctors appear to patients and take paid consultations | Public + Payments | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
408 | 408 | M09 | Trust & verification | QA | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.4 | TRU-04 | Practice gate — only verified doctors appear to patients and take paid consultations | TRU-04.03 | QA: reception can still book own clinic patient for unverified doctor if PRE-03 allows | Regression | Trust | §13 | Practice gate | Only verified doctors appear to patients and take paid consultations | Public + Payments | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
409 | 409 | M09 | Trust & verification | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.5 | TRU-05 | Patient reviews — patients rate and review consultations | TRU-05.01 | DB: Review (PatientAppId, Rating, Text, Status, At) | New | Trust | §13 + §2.8 | Patient reviews / Write a review | Patients rate and review consultations / Rate and review the consultation | Patient + Public | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
410 | 410 | M09 | Trust & verification | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.5 | TRU-05 | Patient reviews — patients rate and review consultations | TRU-05.02 | API: create (patient), list by doctor (public approved), doctor list own | New | Trust | §13 + §2.8 | Patient reviews / Write a review | Patients rate and review consultations / Rate and review the consultation | Patient + Public | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
411 | 411 | M09 | Trust & verification | UI | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.5 | TRU-05 | Patient reviews — patients rate and review consultations | TRU-05.03 | Public doctor profile reviews; patient app write flow Phase 16 | New | Trust | §13 + §2.8 | Patient reviews / Write a review | Patients rate and review consultations / Rate and review the consultation | Patient + Public | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
412 | 412 | M09 | Trust & verification | QA | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.5 | TRU-05 | Patient reviews — patients rate and review consultations | TRU-05.04 | QA: duplicate review blocked; incomplete visit blocked | Regression | Trust | §13 + §2.8 | Patient reviews / Write a review | Patients rate and review consultations / Rate and review the consultation | Patient + Public | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
413 | 413 | M09 | Trust & verification | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.6 | TRU-06 | Review appeal — doctors can appeal a review; patients manage reviews and raise an appeal | TRU-06.01 | DB: ReviewAppeal | New | Trust | §13 + §2.8 | Review appeal / My reviews & appeal | Doctors can appeal a review / Manage reviews and raise an appeal | Doctor + Patient + Admin | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
414 | 414 | M09 | Trust & verification | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.6 | TRU-06 | Review appeal — doctors can appeal a review; patients manage reviews and raise an appeal | TRU-06.02 | API: doctor appeal; patient list/mine; admin resolve | New | Trust | §13 + §2.8 | Review appeal / My reviews & appeal | Doctors can appeal a review / Manage reviews and raise an appeal | Doctor + Patient + Admin | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
415 | 415 | M09 | Trust & verification | UI | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.6 | TRU-06 | Review appeal — doctors can appeal a review; patients manage reviews and raise an appeal | TRU-06.03 | Doctor dashboard my-reviews; admin queue | New | Trust | §13 + §2.8 | Review appeal / My reviews & appeal | Doctors can appeal a review / Manage reviews and raise an appeal | Doctor + Patient + Admin | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
416 | 416 | M09 | Trust & verification | QA | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.6 | TRU-06 | Review appeal — doctors can appeal a review; patients manage reviews and raise an appeal | TRU-06.04 | QA: only treating doctor of that visit can appeal | Regression | Trust | §13 + §2.8 | Review appeal / My reviews & appeal | Doctors can appeal a review / Manage reviews and raise an appeal | Doctor + Patient + Admin | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
417 | 417 | M09 | Trust & verification | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.7 | TRU-07 | Ranking transparency — patients are shown why doctors are ranked as they are | TRU-07.01 | Ranking config (weights) — not a black box hardcoded sort | New | Trust | §13 + §2.2 | Ranking transparency / Ranking explanation | Patients are shown why doctors are ranked as they are / Transparent explanation of why doctors appear in a given order | Public + Patient app | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
418 | 418 | M09 | Trust & verification | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.7 | TRU-07 | Ranking transparency — patients are shown why doctors are ranked as they are | TRU-07.02 | GET doctors + GET ranking-explain/{doctorId} | New | Trust | §13 + §2.2 | Ranking transparency / Ranking explanation | Patients are shown why doctors are ranked as they are / Transparent explanation of why doctors appear in a given order | Public + Patient app | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
419 | 419 | M09 | Trust & verification | UI | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.7 | TRU-07 | Ranking transparency — patients are shown why doctors are ranked as they are | TRU-07.03 | Search results: Why this order? panel | New | Trust | §13 + §2.2 | Ranking transparency / Ranking explanation | Patients are shown why doctors are ranked as they are / Transparent explanation of why doctors appear in a given order | Public + Patient app | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
420 | 420 | M09 | Trust & verification | QA | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.7 | TRU-07 | Ranking transparency — patients are shown why doctors are ranked as they are | TRU-07.04 | QA: changing weights changes order and explanation together | Regression | Trust | §13 + §2.2 | Ranking transparency / Ranking explanation | Patients are shown why doctors are ranked as they are / Transparent explanation of why doctors appear in a given order | Public + Patient app | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
421 | 421 | M10 | Patient website | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.1 | WEB-01 | Product home page — complete public website presenting the service | WEB-01.01 | No schema | Existing Improvement | Patient Website | §4 | Product home page | Complete public website presenting the service | Patient Website | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
422 | 422 | M10 | Patient website | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.1 | WEB-01 | Product home page — complete public website presenting the service | WEB-01.02 | Reuse public doctor/fee APIs when live | Existing Improvement | Patient Website | §4 | Product home page | Complete public website presenting the service | Patient Website | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
423 | 423 | M10 | Patient website | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.1 | WEB-01 | Product home page — complete public website presenting the service | WEB-01.03 | HomeLandingPage: book, verified doctors, pricing teaser, store badges; strip leftover job-board feel | Existing Improvement | Patient Website | §4 | Product home page | Complete public website presenting the service | Patient Website | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
424 | 424 | M10 | Patient website | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.1 | WEB-01 | Product home page — complete public website presenting the service | WEB-01.04 | QA: mobile viewport; deep link /book | Regression | Patient Website | §4 | Product home page | Complete public website presenting the service | Patient Website | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
425 | 425 | M10 | Patient website | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.2 | WEB-02 | Consultation & subscription pricing — transparent pricing display | WEB-02.01 | Public doctor card shows in-clinic and tele fee | Existing Improvement | Patient Website | §4 | Consultation & subscription pricing | Transparent pricing display | Patient Website | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
426 | 426 | M10 | Patient website | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.2 | WEB-02 | Consultation & subscription pricing — transparent pricing display | WEB-02.02 | /pricing remains SaaS packages for doctors; label it clearly vs patient consult fees | Existing Improvement | Patient Website | §4 | Consultation & subscription pricing | Transparent pricing display | Patient Website | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
427 | 427 | M10 | Patient website | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.2 | WEB-02 | Consultation & subscription pricing — transparent pricing display | WEB-02.03 | QA: fee matches checkout amount | Regression | Patient Website | §4 | Consultation & subscription pricing | Transparent pricing display | Patient Website | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
428 | 428 | M10 | Patient website | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.3 | WEB-03 | Doctor discovery — browse and search verified doctors | WEB-03.01 | Public doctor search indexes (from Doctor + verification + fee + schedule) | New | Patient Website | §4 + §2.2 | Doctor discovery | Browse and search verified doctors | Patient Website | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
429 | 429 | M10 | Patient website | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.3 | WEB-03 | Doctor discovery — browse and search verified doctors | WEB-03.02 | GET /api/Public/Doctors + filters + profile | New | Patient Website | §4 + §2.2 | Doctor discovery | Browse and search verified doctors | Patient Website | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
430 | 430 | M10 | Patient website | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.3 | WEB-03 | Doctor discovery — browse and search verified doctors | WEB-03.03 | /book list + filters + doctor profile page | New | Patient Website | §4 + §2.2 | Doctor discovery | Browse and search verified doctors | Patient Website | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
431 | 431 | M10 | Patient website | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.3 | WEB-03 | Doctor discovery — browse and search verified doctors | WEB-03.04 | QA: unverified excluded; filters combine; empty state | Regression | Patient Website | §4 + §2.2 | Doctor discovery | Browse and search verified doctors | Patient Website | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
432 | 432 | M10 | Patient website | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.4 | WEB-04 | Self-service booking — book an appointment online without calling the clinic | WEB-04.01 | Reuse Patient + Appointment; BookingToken; PatientAuth OTP | New | Patient Website | §4 + §2.3 | Self-service booking | Book an appointment online without calling the clinic | Patient Website | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
433 | 433 | M10 | Patient website | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.4 | WEB-04 | Self-service booking — book an appointment online without calling the clinic | WEB-04.02 | Public: Doctors/{id}/Slots, Create, {bookingToken}; POST PatientAuth RequestOtp/VerifyOtp | New | Patient Website | §4 + §2.3 | Self-service booking | Book an appointment online without calling the clinic | Patient Website | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
434 | 434 | M10 | Patient website | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.4 | WEB-04 | Self-service booking — book an appointment online without calling the clinic | WEB-04.03 | /book/:doctorId/slots; /book/confirm; booking success | New | Patient Website | §4 + §2.3 | Self-service booking | Book an appointment online without calling the clinic | Patient Website | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
435 | 435 | M10 | Patient website | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.4 | WEB-04 | Self-service booking — book an appointment online without calling the clinic | WEB-04.04 | QA: double-book same slot; hold expiry; OTP fail; consent required | Regression | Patient Website | §4 + §2.3 | Self-service booking | Book an appointment online without calling the clinic | Patient Website | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
436 | 436 | M10 | Patient website | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.5 | WEB-05 | Online consultation payment on website — pay the fee at the time of booking | WEB-05.01 | /book/pay/:bookingId + success/failure pages | New | Patient Website | §4 + §9 | Online consultation payment | Pay the consultation fee at the time of booking | Patient Website | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
437 | 437 | M10 | Patient website | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.5 | WEB-05 | Online consultation payment on website — pay the fee at the time of booking | WEB-05.02 | QA: pay-at-clinic skip checkout; failed pay remains PENDING not PAID | Regression | Patient Website | §4 + §9 | Online consultation payment | Pay the consultation fee at the time of booking | Patient Website | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
438 | 438 | M10 | Patient website | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.6 | WEB-06 | Contact & enquiry form — enquiries reach the admin team and are tracked | WEB-06.01 | Reuse EnquiryDetail; add Status/AssignedTo if missing | Existing Improvement | Patient Website | §4 + §15 | Contact & enquiry form | Enquiries reach the admin team and are tracked | Patient Website + Admin | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
439 | 439 | M10 | Patient website | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.6 | WEB-06 | Contact & enquiry form — enquiries reach the admin team and are tracked | WEB-06.02 | Existing enquiry POST; admin list API if missing | Existing Improvement | Patient Website | §4 + §15 | Contact & enquiry form | Enquiries reach the admin team and are tracked | Patient Website + Admin | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
440 | 440 | M10 | Patient website | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.6 | WEB-06 | Contact & enquiry form — enquiries reach the admin team and are tracked | WEB-06.03 | /contact confirmation; /admin/enquiries inbox (not Velzon mailbox) | Existing Improvement | Patient Website | §4 + §15 | Contact & enquiry form | Enquiries reach the admin team and are tracked | Patient Website + Admin | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
441 | 441 | M10 | Patient website | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.6 | WEB-06 | Contact & enquiry form — enquiries reach the admin team and are tracked | WEB-06.04 | QA: guest submit → admin sees row | Regression | Patient Website | §4 + §15 | Contact & enquiry form | Enquiries reach the admin team and are tracked | Patient Website + Admin | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
442 | 442 | M10 | Patient website | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.7 | WEB-07 | Privacy policy — covering data protection, recording and pharmacy consent | WEB-07.01 | Replace /privacy content with signed legal copy; store PolicyVersion | Existing Improvement | Legal | §4 + §17 | Privacy policy | Covering data protection, recording and pharmacy consent | Patient Website | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
443 | 443 | M10 | Patient website | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.7 | WEB-07 | Privacy policy — covering data protection, recording and pharmacy consent | WEB-07.02 | QA: booking consent shows policy version number | Regression | Legal | §4 + §17 | Privacy policy | Covering data protection, recording and pharmacy consent | Patient Website | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
444 | 444 | M10 | Patient website | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.8 | WEB-08 | Terms of service — covering payments, refunds, telemedicine and medicine orders | WEB-08.01 | Replace /terms with signed copy; version stamp on booking/payment | Existing Improvement | Legal | §4 | Terms of service | Covering payments, refunds, telemedicine and medicine orders | Patient Website | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
445 | 445 | M10 | Patient website | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.8 | WEB-08 | Terms of service — covering payments, refunds, telemedicine and medicine orders | WEB-08.02 | QA: terms checkbox required on confirm | Regression | Legal | §4 | Terms of service | Covering payments, refunds, telemedicine and medicine orders | Patient Website | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
446 | 446 | M10 | Patient website | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.9 | WEB-09 | Doctor self-registration — doctors apply to join the platform online | WEB-09.01 | Documents via TRU-01 tables | Existing Improvement | Patient Website | §4 | Doctor self-registration | Doctors apply to join the platform online | Public | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
447 | 447 | M10 | Patient website | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.9 | WEB-09 | Doctor self-registration — doctors apply to join the platform online | WEB-09.02 | RegisterDoctor sets Pending; does not auto-activate practice for directory | Existing Improvement | Patient Website | §4 | Doctor self-registration | Doctors apply to join the platform online | Public | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
448 | 448 | M10 | Patient website | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.9 | WEB-09 | Doctor self-registration — doctors apply to join the platform online | WEB-09.03 | /register multipart docs; pending message; status page | Existing Improvement | Patient Website | §4 | Doctor self-registration | Doctors apply to join the platform online | Public | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
449 | 449 | M10 | Patient website | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.9 | WEB-09 | Doctor self-registration — doctors apply to join the platform online | WEB-09.04 | QA: register → admin queue row | Regression | Patient Website | §4 | Doctor self-registration | Doctors apply to join the platform online | Public | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
450 | 450 | M10 | Patient website | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.10 | WEB-10 | Email activation — secure account activation by email link | WEB-10.01 | Activation token TTL if missing | Existing Improvement | Auth | §4 | Email activation | Secure account activation by email link | Public | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
451 | 451 | M10 | Patient website | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.10 | WEB-10 | Email activation — secure account activation by email link | WEB-10.02 | Resend activation; do not treat activation as TRU-04 gate | Existing Improvement | Auth | §4 | Email activation | Secure account activation by email link | Public | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
452 | 452 | M10 | Patient website | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.10 | WEB-10 | Email activation — secure account activation by email link | WEB-10.03 | Login activation query param UX + expiry copy | Existing Improvement | Auth | §4 | Email activation | Secure account activation by email link | Public | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
453 | 453 | M10 | Patient website | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.10 | WEB-10 | Email activation — secure account activation by email link | WEB-10.04 | QA: used link, expired link, resend | Regression | Auth | §4 | Email activation | Secure account activation by email link | Public | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
454 | 454 | M05 | Appointments & scheduling | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.11 | WEB-11 | Waitlist offer — get offered a slot when one is freed by a cancellation (patient website + later app) | WEB-11.01 | DB: BookingWaitlist | New | Booking | §2.3 | Waitlist offer | Get offered a slot when one is freed by a cancellation | Patient Website + App | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
455 | 455 | M05 | Appointments & scheduling | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.11 | WEB-11 | Waitlist offer — get offered a slot when one is freed by a cancellation (patient website + later app) | WEB-11.02 | API: join waitlist; worker on CancelAppointment | New | Booking | §2.3 | Waitlist offer | Get offered a slot when one is freed by a cancellation | Patient Website + App | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
456 | 456 | M05 | Appointments & scheduling | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.11 | WEB-11 | Waitlist offer — get offered a slot when one is freed by a cancellation (patient website + later app) | WEB-11.03 | Public waitlist CTA on full days | New | Booking | §2.3 | Waitlist offer | Get offered a slot when one is freed by a cancellation | Patient Website + App | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
457 | 457 | M05 | Appointments & scheduling | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.11 | WEB-11 | Waitlist offer — get offered a slot when one is freed by a cancellation (patient website + later app) | WEB-11.04 | Notify SMS/push when Phase 12 exists | New Integration | Booking | §2.3 | Waitlist offer | Get offered a slot when one is freed by a cancellation | Patient Website + App | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
458 | 458 | M05 | Appointments & scheduling | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.11 | WEB-11 | Waitlist offer — get offered a slot when one is freed by a cancellation (patient website + later app) | WEB-11.05 | QA: two waiters; first gets offer; expiry releases to second | Regression | Booking | §2.3 | Waitlist offer | Get offered a slot when one is freed by a cancellation | Patient Website + App | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
459 | 459 | M10 | Patient website | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.12 | WEB-12 | Health articles — educational content to build trust and engagement | WEB-12.01 | Public articles list/detail from existing blog/news APIs | Existing Improvement | Patient Website | §2.2 | Health articles | Educational content to build trust and engagement | Patient Website + App | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
460 | 460 | M10 | Patient website | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.12 | WEB-12 | Health articles — educational content to build trust and engagement | WEB-12.02 | QA: unpublished hidden | Regression | Patient Website | §2.2 | Health articles | Educational content to build trust and engagement | Patient Website + App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
461 | 461 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.1 | ERX-01 | Potency module — every remedy carries a defined potency from a managed list, no free text | ERX-01.01 | DB: PotencyMaster; PrescriptionRemedyDetail.PotencyId | New | eRx | §11 | Potency module | Every remedy carries a defined potency, selected from a managed list — no free text | Doctor Web + Admin | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
462 | 462 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.1 | ERX-01 | Potency module — every remedy carries a defined potency from a managed list, no free text | ERX-01.02 | API: potency DDL; extend SavePrescriptionDetail | New | eRx | §11 | Potency module | Every remedy carries a defined potency, selected from a managed list — no free text | Doctor Web + Admin | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
463 | 463 | M11 | Digital prescription (eRx) | UI | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.1 | ERX-01 | Potency module — every remedy carries a defined potency from a managed list, no free text | ERX-01.03 | Rx modal potency picker (6C, 30C, 200C, 1M…) | New | eRx | §11 | Potency module | Every remedy carries a defined potency, selected from a managed list — no free text | Doctor Web + Admin | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
464 | 464 | M11 | Digital prescription (eRx) | QA | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.1 | ERX-01 | Potency module — every remedy carries a defined potency from a managed list, no free text | ERX-01.04 | QA: free text potency rejected | Regression | eRx | §11 | Potency module | Every remedy carries a defined potency, selected from a managed list — no free text | Doctor Web + Admin | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
465 | 465 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.2 | ERX-02 | Dosage details — frequency, duration and instructions recorded clearly | ERX-02.01 | DB: Frequency, Duration, Instructions on remedy line | New | eRx | §11 | Dosage details | Frequency, duration and instructions recorded clearly | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
466 | 466 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.2 | ERX-02 | Dosage details — frequency, duration and instructions recorded clearly | ERX-02.02 | Extend save/get Rx APIs | New | eRx | §11 | Dosage details | Frequency, duration and instructions recorded clearly | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
467 | 467 | M11 | Digital prescription (eRx) | UI | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.2 | ERX-02 | Dosage details — frequency, duration and instructions recorded clearly | ERX-02.03 | Rx row UI for the three fields | New | eRx | §11 | Dosage details | Frequency, duration and instructions recorded clearly | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
468 | 468 | M11 | Digital prescription (eRx) | QA | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.2 | ERX-02 | Dosage details — frequency, duration and instructions recorded clearly | ERX-02.04 | QA: all three persist and print | Regression | eRx | §11 | Dosage details | Frequency, duration and instructions recorded clearly | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
469 | 469 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.3 | ERX-03 | Visit notes kept separate from the prescription — private clinical notes never appear on the prescription given to the patient or pharmacy | ERX-03.01 | Extend AppointmentHistoryNote with NoteType, IsErxExcluded | New | eRx | §11 + §5.3 | Visit notes kept separate from the prescription | The doctor’s private clinical notes never appear on the prescription given to the patient or pharmacy | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
470 | 470 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.3 | ERX-03 | Visit notes kept separate from the prescription — private clinical notes never appear on the prescription given to the patient or pharmacy | ERX-03.02 | GET /api/Erx/ByAppointment/{id} returns snapshot without notes | New | eRx | §11 + §5.3 | Visit notes kept separate from the prescription | The doctor’s private clinical notes never appear on the prescription given to the patient or pharmacy | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
471 | 471 | M11 | Digital prescription (eRx) | UI | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.3 | ERX-03 | Visit notes kept separate from the prescription — private clinical notes never appear on the prescription given to the patient or pharmacy | ERX-03.03 | Move History Notes out of Rx modal; note types Chief complaint / Follow-up / General | New | eRx | §11 + §5.3 | Visit notes kept separate from the prescription | The doctor’s private clinical notes never appear on the prescription given to the patient or pharmacy | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
472 | 472 | M11 | Digital prescription (eRx) | QA | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.3 | ERX-03 | Visit notes kept separate from the prescription — private clinical notes never appear on the prescription given to the patient or pharmacy | ERX-03.04 | QA: print eRx vs export case PDF (doctor copy still has notes) | Regression | eRx | §11 + §5.3 | Visit notes kept separate from the prescription | The doctor’s private clinical notes never appear on the prescription given to the patient or pharmacy | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
473 | 473 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.4 | ERX-04 | Signed digital prescription — issued and locked once signed, so it cannot be altered afterwards | ERX-04.01 | DB: ErxSnapshot, ErxSnapshotItem (codes+names stored; patient API returns codes until pharmacy accept) | New | eRx | §11 + §2.5 + §5.3 | Signed digital prescription | Issued and locked once signed, so it cannot be altered afterwards / Official prescription issued by the doctor | Doctor Web | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
474 | 474 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.4 | ERX-04 | Signed digital prescription — issued and locked once signed, so it cannot be altered afterwards | ERX-04.02 | API: SignErx; GetErx; reject mutate of signed snapshot | New | eRx | §11 + §2.5 + §5.3 | Signed digital prescription | Issued and locked once signed, so it cannot be altered afterwards / Official prescription issued by the doctor | Doctor Web | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
475 | 475 | M11 | Digital prescription (eRx) | UI | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.4 | ERX-04 | Signed digital prescription — issued and locked once signed, so it cannot be altered afterwards | ERX-04.03 | Sign button; locked badge on board header | New | eRx | §11 + §2.5 + §5.3 | Signed digital prescription | Issued and locked once signed, so it cannot be altered afterwards / Official prescription issued by the doctor | Doctor Web | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
476 | 476 | M11 | Digital prescription (eRx) | QA | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.4 | ERX-04 | Signed digital prescription — issued and locked once signed, so it cannot be altered afterwards | ERX-04.04 | QA: POST save after sign does not change snapshot | Regression | eRx | §11 + §2.5 + §5.3 | Signed digital prescription | Issued and locked once signed, so it cannot be altered afterwards / Official prescription issued by the doctor | Doctor Web | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
477 | 477 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.5 | ERX-05 | Prescription history — every prescription stored against the patient and visit | ERX-05.01 | GET history by patient; by appointment | New | eRx | §11 | Prescription history | Every prescription stored against the patient and visit | Doctor + Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
478 | 478 | M11 | Digital prescription (eRx) | UI | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.5 | ERX-05 | Prescription history — every prescription stored against the patient and visit | ERX-05.02 | Doctor history panel lists signed eRx; patient timeline in Phase 16 | New | eRx | §11 | Prescription history | Every prescription stored against the patient and visit | Doctor + Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
479 | 479 | M11 | Digital prescription (eRx) | QA | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.5 | ERX-05 | Prescription history — every prescription stored against the patient and visit | ERX-05.03 | QA: another doctor 403 | Regression | eRx | §11 | Prescription history | Every prescription stored against the patient and visit | Doctor + Patient | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
480 | 480 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.6 | ERX-06 | Patient view of prescription in app — patient sees the prescription immediately (codes until pharmacy accept) | ERX-06.01 | Patient-authorised GET Erx; apply code protection ERX-08 | New | eRx | §11 + §2.5 | Patient view in app | Patient sees the prescription immediately in the app | Patient App + Website | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
481 | 481 | M11 | Digital prescription (eRx) | UI | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.6 | ERX-06 | Patient view of prescription in app — patient sees the prescription immediately (codes until pharmacy accept) | ERX-06.02 | Web confirmation/records page can show the same payload before the app exists | New | eRx | §11 + §2.5 | Patient view in app | Patient sees the prescription immediately in the app | Patient App + Website | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
482 | 482 | M11 | Digital prescription (eRx) | QA | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.6 | ERX-06 | Patient view of prescription in app — patient sees the prescription immediately (codes until pharmacy accept) | ERX-06.03 | QA: doctor names vs patient codes differ until pharmacy OTP accept | Regression | eRx | §11 + §2.5 | Patient view in app | Patient sees the prescription immediately in the app | Patient App + Website | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
483 | 483 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.7 | ERX-07 | Print & PDF — printable and downloadable prescription | ERX-07.01 | PDF renderer from ErxSnapshot; store via SEC-09 | New | eRx | §11 | Print & PDF | Printable and downloadable prescription | Doctor + Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
484 | 484 | M11 | Digital prescription (eRx) | UI | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.7 | ERX-07 | Print & PDF — printable and downloadable prescription | ERX-07.02 | Print/Download on doctor board and later patient app | New | eRx | §11 | Print & PDF | Printable and downloadable prescription | Doctor + Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
485 | 485 | M11 | Digital prescription (eRx) | QA | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.7 | ERX-07 | Print & PDF — printable and downloadable prescription | ERX-07.03 | QA: notes leak test on patient PDF | Regression | eRx | §11 | Print & PDF | Printable and downloadable prescription | Doctor + Patient | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
486 | 486 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.8 | ERX-08 | Remedy code protection — patient sees remedy codes rather than names until a licensed pharmacy accepts the order | ERX-08.01 | Assign stable remedy codes on snapshot items | New | eRx | §11 | Remedy code protection | The patient sees remedy codes rather than remedy names until a licensed pharmacy accepts the order | Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
487 | 487 | M11 | Digital prescription (eRx) | QA | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.8 | ERX-08 | Remedy code protection — patient sees remedy codes rather than names until a licensed pharmacy accepts the order | ERX-08.02 | Patient serializer tests (contract tests) | Regression | eRx | §11 | Remedy code protection | The patient sees remedy codes rather than remedy names until a licensed pharmacy accepts the order | Patient | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
488 | 488 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.9 | ERX-09 | Reveal on pharmacy acceptance — names and price revealed; payment QR or link generated (implemented with HomeoMeds; contract now) | ERX-09.01 | API contract: AcceptOrder(OTP) → reveal names; Quote → PayQR | New | eRx | §11 + §12 | Reveal on pharmacy acceptance | Once a pharmacy accepts and verifies by OTP, the remedy names and price are revealed and a payment QR or link is generated | Patient + Pharmacy | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
489 | 489 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.9 | ERX-09 | Reveal on pharmacy acceptance — names and price revealed; payment QR or link generated (implemented with HomeoMeds; contract now) | ERX-09.02 | Implement fully with MED-* in Phase 14 — do not reveal names from doctor sign alone | New | eRx | §11 + §12 | Reveal on pharmacy acceptance | Once a pharmacy accepts and verifies by OTP, the remedy names and price are revealed and a payment QR or link is generated | Patient + Pharmacy | Architecture | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
490 | 490 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.10 | ERX-10 | Repeat prescription / refill — patient requests; doctor approves or rejects from the mobile app (inbox on web too) | ERX-10.01 | DB: RefillRequest | New | eRx | §11 + §3 + §2.7 | Repeat prescription / refill | Patient requests a refill; doctor approves or rejects from the mobile app | Patient + Doctor mobile + Doctor web | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
491 | 491 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.10 | ERX-10 | Repeat prescription / refill — patient requests; doctor approves or rejects from the mobile app (inbox on web too) | ERX-10.02 | API: patient request; doctor inbox; approve/reject | New | eRx | §11 + §3 + §2.7 | Repeat prescription / refill | Patient requests a refill; doctor approves or rejects from the mobile app | Patient + Doctor mobile + Doctor web | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
492 | 492 | M11 | Digital prescription (eRx) | UI | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.10 | ERX-10 | Repeat prescription / refill — patient requests; doctor approves or rejects from the mobile app (inbox on web too) | ERX-10.03 | Doctor web inbox; doctor app in Phase 17; patient app in Phase 16 | New | eRx | §11 + §3 + §2.7 | Repeat prescription / refill | Patient requests a refill; doctor approves or rejects from the mobile app | Patient + Doctor mobile + Doctor web | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
493 | 493 | M11 | Digital prescription (eRx) | QA | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.10 | ERX-10 | Repeat prescription / refill — patient requests; doctor approves or rejects from the mobile app (inbox on web too) | ERX-10.04 | QA: cannot refill unsigned/locked-expired per policy | Regression | eRx | §11 + §3 + §2.7 | Repeat prescription / refill | Patient requests a refill; doctor approves or rejects from the mobile app | Patient + Doctor mobile + Doctor web | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
494 | 494 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.11 | ERX-11 | Lab orders alongside the prescription (keep existing labs on eRx snapshot) | ERX-11.01 | Copy lab orders into ErxSnapshot on sign | Existing Improvement | eRx | §11 | Lab orders | Tests ordered alongside the prescription | Doctor Web | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
495 | 495 | M11 | Digital prescription (eRx) | QA | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.11 | ERX-11 | Lab orders alongside the prescription (keep existing labs on eRx snapshot) | ERX-11.02 | QA: labs visible on eRx; result values not required on patient copy | Regression | eRx | §11 | Lab orders | Tests ordered alongside the prescription | Doctor Web | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
496 | 496 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.1 | TEL-01 | Doctor availability — online or offline status and working hours | TEL-01.01 | DB: TeleAvailability (Online/Offline, LastHeartbeat) | New | Telemedicine | §10 + §3 | Doctor availability | Doctor sets online or offline status and working hours | Doctor Web + Doctor App | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
497 | 497 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.1 | TEL-01 | Doctor availability — online or offline status and working hours | TEL-01.02 | API: SET/GET availability; public GET by doctorId | New | Telemedicine | §10 + §3 | Doctor availability | Doctor sets online or offline status and working hours | Doctor Web + Doctor App | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
498 | 498 | M12 | Telemedicine | UI | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.1 | TEL-01 | Doctor availability — online or offline status and working hours | TEL-01.03 | Dashboard toggle Online for teleconsult | New | Telemedicine | §10 + §3 | Doctor availability | Doctor sets online or offline status and working hours | Doctor Web + Doctor App | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
499 | 499 | M12 | Telemedicine | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.1 | TEL-01 | Doctor availability — online or offline status and working hours | TEL-01.04 | QA: heartbeat expiry sets offline | Regression | Telemedicine | §10 + §3 | Doctor availability | Doctor sets online or offline status and working hours | Doctor Web + Doctor App | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
500 | 500 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.2 | TEL-02 | Telemedicine waiting queue — who is waiting, how long, whether they have paid | TEL-02.01 | Queue query on E-CONSULT + PaymentStatus + join time | New | Telemedicine | §10 + §3 | Telemedicine waiting queue | Doctor sees who is waiting, for how long, and whether they have paid | Doctor Web + App | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
501 | 501 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.2 | TEL-02 | Telemedicine waiting queue — who is waiting, how long, whether they have paid | TEL-02.02 | GET Tele/Queue; POST start session | New | Telemedicine | §10 + §3 | Telemedicine waiting queue | Doctor sees who is waiting, for how long, and whether they have paid | Doctor Web + App | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
502 | 502 | M12 | Telemedicine | UI | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.2 | TEL-02 | Telemedicine waiting queue — who is waiting, how long, whether they have paid | TEL-02.03 | Dedicated Tele queue on dashboard (beyond E-CONSULT list) | New | Telemedicine | §10 + §3 | Telemedicine waiting queue | Doctor sees who is waiting, for how long, and whether they have paid | Doctor Web + App | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
503 | 503 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.2 | TEL-02 | Telemedicine waiting queue — who is waiting, how long, whether they have paid | TEL-02.04 | SignalR/poll | New Integration | Telemedicine | §10 + §3 | Telemedicine waiting queue | Doctor sees who is waiting, for how long, and whether they have paid | Doctor Web + App | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
504 | 504 | M12 | Telemedicine | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.2 | TEL-02 | Telemedicine waiting queue — who is waiting, how long, whether they have paid | TEL-02.05 | QA: wait time increases; paid badge matches PAY-08 | Regression | Telemedicine | §10 + §3 | Telemedicine waiting queue | Doctor sees who is waiting, for how long, and whether they have paid | Doctor Web + App | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
505 | 505 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.3 | TEL-03 | Video consultation in browser — doctor consults directly from the web portal | TEL-03.01 | DB: TeleSession (PatientAppId, RoomId, Status) | New | Telemedicine | §10 | Video consultation in browser | Doctor consults directly from the web portal | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
506 | 506 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.3 | TEL-03 | Video consultation in browser — doctor consults directly from the web portal | TEL-03.02 | API: create/end session; vendor tokens | New | Telemedicine | §10 | Video consultation in browser | Doctor consults directly from the web portal | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
507 | 507 | M12 | Telemedicine | UI | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.3 | TEL-03 | Video consultation in browser — doctor consults directly from the web portal | TEL-03.03 | Full-page video room mute/end | New | Telemedicine | §10 | Video consultation in browser | Doctor consults directly from the web portal | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
508 | 508 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.3 | TEL-03 | Video consultation in browser — doctor consults directly from the web portal | TEL-03.04 | Video SDK (Agora/Twilio/Daily) | New Integration | Telemedicine | §10 | Video consultation in browser | Doctor consults directly from the web portal | Doctor Web Portal | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
509 | 509 | M12 | Telemedicine | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.3 | TEL-03 | Video consultation in browser — doctor consults directly from the web portal | TEL-03.05 | QA: replace WhatsApp alert; session ends write timestamp | Regression | Telemedicine | §10 | Video consultation in browser | Doctor consults directly from the web portal | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
510 | 510 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.4 | TEL-04 | Video consultation on mobile — doctor and patient both consult from the app (apps in 16–17; same session tokens) | TEL-04.01 | Token API must be client-agnostic (web and mobile) | New | Telemedicine | §10 + §2.4 + §3 | Video consultation on mobile | Doctor and patient both consult from the app / Face-to-face consultation from home / Start the video or audio consultation from the phone | Patient App + Doctor App | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
511 | 511 | M12 | Telemedicine | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.4 | TEL-04 | Video consultation on mobile — doctor and patient both consult from the app (apps in 16–17; same session tokens) | TEL-04.02 | Contract tests: token TTL, room id = session id | Regression | Telemedicine | §10 + §2.4 + §3 | Video consultation on mobile | Doctor and patient both consult from the app / Face-to-face consultation from home / Start the video or audio consultation from the phone | Patient App + Doctor App | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
512 | 512 | M12 | Telemedicine | UI | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.5 | TEL-05 | Device check — camera, microphone and connection tested before joining | TEL-05.01 | Shared device-check component (web); mobile equivalent in Phase 16 | New | Telemedicine | §10 + §2.4 | Device check | Camera, microphone and connection tested before joining | Doctor Web + Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
513 | 513 | M12 | Telemedicine | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.5 | TEL-05 | Device check — camera, microphone and connection tested before joining | TEL-05.02 | QA: deny camera permission → clear guidance | Regression | Telemedicine | §10 + §2.4 | Device check | Camera, microphone and connection tested before joining | Doctor Web + Patient | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
514 | 514 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.6 | TEL-06 | Waiting room — patient waits with live status until the doctor joins | TEL-06.01 | Session status events | New | Telemedicine | §10 + §2.4 | Waiting room | Patient waits with live status / Wait with live status until the doctor joins | Patient | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
515 | 515 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.6 | TEL-06 | Waiting room — patient waits with live status until the doctor joins | TEL-06.02 | GET session status for patient token | New | Telemedicine | §10 + §2.4 | Waiting room | Patient waits with live status / Wait with live status until the doctor joins | Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
516 | 516 | M12 | Telemedicine | UI | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.6 | TEL-06 | Waiting room — patient waits with live status until the doctor joins | TEL-06.03 | Waiting room UI on web (and app later) | New | Telemedicine | §10 + §2.4 | Waiting room | Patient waits with live status / Wait with live status until the doctor joins | Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
517 | 517 | M12 | Telemedicine | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.6 | TEL-06 | Waiting room — patient waits with live status until the doctor joins | TEL-06.04 | QA: doctor join transitions patient into the call | Regression | Telemedicine | §10 + §2.4 | Waiting room | Patient waits with live status / Wait with live status until the doctor joins | Patient | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
518 | 518 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.7 | TEL-07 | Recording consent — consent captured before the consultation; no recording without it | TEL-07.01 | Write ConsentRecord TeleRecording; TeleConsentLog events | New | Telemedicine | §10 + §2.4 + §17 | Recording consent | Consent captured before the consultation; no recording without it / Explicit consent requested before any recording | Patient + Doctor | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
519 | 519 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.7 | TEL-07 | Recording consent — consent captured before the consultation; no recording without it | TEL-07.02 | API: capture consent; session.recordAllowed | New | Telemedicine | §10 + §2.4 + §17 | Recording consent | Consent captured before the consultation; no recording without it / Explicit consent requested before any recording | Patient + Doctor | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
520 | 520 | M12 | Telemedicine | UI | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.7 | TEL-07 | Recording consent — consent captured before the consultation; no recording without it | TEL-07.03 | Pre-join modal both sides | New | Telemedicine | §10 + §2.4 + §17 | Recording consent | Consent captured before the consultation; no recording without it / Explicit consent requested before any recording | Patient + Doctor | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
521 | 521 | M12 | Telemedicine | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.7 | TEL-07 | Recording consent — consent captured before the consultation; no recording without it | TEL-07.04 | QA: decline → no record; audit row still written | Regression | Telemedicine | §10 + §2.4 + §17 | Recording consent | Consent captured before the consultation; no recording without it / Explicit consent requested before any recording | Patient + Doctor | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
522 | 522 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.8 | TEL-08 | Rejoin after dropped call — either side can rejoin the same consultation | TEL-08.01 | API: Rejoin issues token if Status=Active | New | Telemedicine | §10 + §2.4 | Rejoin after dropped call | Either side can rejoin the same consultation / Rejoin the same consultation if the connection drops | Doctor + Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
523 | 523 | M12 | Telemedicine | UI | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.8 | TEL-08 | Rejoin after dropped call — either side can rejoin the same consultation | TEL-08.02 | UI Rejoin on doctor dashboard and patient waiting/call fail | New | Telemedicine | §10 + §2.4 | Rejoin after dropped call | Either side can rejoin the same consultation / Rejoin the same consultation if the connection drops | Doctor + Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
524 | 524 | M12 | Telemedicine | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.8 | TEL-08 | Rejoin after dropped call — either side can rejoin the same consultation | TEL-08.03 | QA: after End, rejoin 409 | Regression | Telemedicine | §10 + §2.4 | Rejoin after dropped call | Either side can rejoin the same consultation / Rejoin the same consultation if the connection drops | Doctor + Patient | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
525 | 525 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.9 | TEL-09 | Join failure handling — clear fallback if the call cannot connect, with options to retry | TEL-09.01 | Standardise join error codes; log TeleSessionEvent | New | Telemedicine | §10 + §2.4 | Join failure handling / Fallback & join failure handling | Clear fallback if the call cannot connect / Clear guidance if the call fails, with options to retry | Doctor + Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
526 | 526 | M12 | Telemedicine | UI | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.9 | TEL-09 | Join failure handling — clear fallback if the call cannot connect, with options to retry | TEL-09.02 | Fallback UI: retry, rejoin, contact support | New | Telemedicine | §10 + §2.4 | Join failure handling / Fallback & join failure handling | Clear fallback if the call cannot connect / Clear guidance if the call fails, with options to retry | Doctor + Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
527 | 527 | M12 | Telemedicine | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.9 | TEL-09 | Join failure handling — clear fallback if the call cannot connect, with options to retry | TEL-09.03 | QA: simulated token fail | Regression | Telemedicine | §10 + §2.4 | Join failure handling / Fallback & join failure handling | Clear fallback if the call cannot connect / Clear guidance if the call fails, with options to retry | Doctor + Patient | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
528 | 528 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.10 | TEL-10 | Case-linked chat — chat attached to the consultation record, not a loose message thread | TEL-10.01 | DB: TeleChatMessage (SessionId, PatientAppId, Body, At) | New | Telemedicine | §10 + §2.4 | Case-linked chat | Chat attached to the consultation record / Chat tied to the consultation, not a loose message thread | Doctor + Patient | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
529 | 529 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.10 | TEL-10 | Case-linked chat — chat attached to the consultation record, not a loose message thread | TEL-10.02 | API: post/list; doctor and patient only | New | Telemedicine | §10 + §2.4 | Case-linked chat | Chat attached to the consultation record / Chat tied to the consultation, not a loose message thread | Doctor + Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
530 | 530 | M12 | Telemedicine | UI | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.10 | TEL-10 | Case-linked chat — chat attached to the consultation record, not a loose message thread | TEL-10.03 | In-room chat panel | New | Telemedicine | §10 + §2.4 | Case-linked chat | Chat attached to the consultation record / Chat tied to the consultation, not a loose message thread | Doctor + Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
531 | 531 | M12 | Telemedicine | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.10 | TEL-10 | Case-linked chat — chat attached to the consultation record, not a loose message thread | TEL-10.04 | QA: IDOR other session 403 | Regression | Telemedicine | §10 + §2.4 | Case-linked chat | Chat attached to the consultation record / Chat tied to the consultation, not a loose message thread | Doctor + Patient | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
532 | 532 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.11 | TEL-11 | Consultation summary — issued to the patient at the end of the call | TEL-11.01 | DB: ConsultationSummary (PatientAppId, Text, At) | New | Telemedicine | §10 + §2.4 | Consultation summary | Issued to the patient at the end of the call / Written summary available immediately after the call | Patient + Doctor | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
533 | 533 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.11 | TEL-11 | Consultation summary — issued to the patient at the end of the call | TEL-11.02 | API: doctor PUT; patient GET | New | Telemedicine | §10 + §2.4 | Consultation summary | Issued to the patient at the end of the call / Written summary available immediately after the call | Patient + Doctor | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
534 | 534 | M12 | Telemedicine | UI | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.11 | TEL-11 | Consultation summary — issued to the patient at the end of the call | TEL-11.03 | Post-call summary form; patient view | New | Telemedicine | §10 + §2.4 | Consultation summary | Issued to the patient at the end of the call / Written summary available immediately after the call | Patient + Doctor | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
535 | 535 | M12 | Telemedicine | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.11 | TEL-11 | Consultation summary — issued to the patient at the end of the call | TEL-11.04 | QA: private notes not copied into summary by default | Regression | Telemedicine | §10 + §2.4 | Consultation summary | Issued to the patient at the end of the call / Written summary available immediately after the call | Patient + Doctor | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
536 | 536 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.12 | TEL-12 | Instant consultation — patient requests an immediate consultation with an available doctor | TEL-12.01 | DB: InstantConsultRequest, DoctorOffer | New | Telemedicine | §10 + §2.3 | Instant consultation / Instant consult request / Queue & doctor offer | Patient can request an immediate consultation with an available doctor / See position in queue and accept an offered doctor | Patient + Doctor | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
537 | 537 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.12 | TEL-12 | Instant consultation — patient requests an immediate consultation with an available doctor | TEL-12.02 | API: request, match, offer, accept, queue position | New | Telemedicine | §10 + §2.3 | Instant consultation / Instant consult request / Queue & doctor offer | Patient can request an immediate consultation with an available doctor / See position in queue and accept an offered doctor | Patient + Doctor | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
538 | 538 | M12 | Telemedicine | UI | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.12 | TEL-12 | Instant consultation — patient requests an immediate consultation with an available doctor | TEL-12.03 | Patient instant CTA; doctor offer banner | New | Telemedicine | §10 + §2.3 | Instant consultation / Instant consult request / Queue & doctor offer | Patient can request an immediate consultation with an available doctor / See position in queue and accept an offered doctor | Patient + Doctor | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
539 | 539 | M12 | Telemedicine | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.12 | TEL-12 | Instant consultation — patient requests an immediate consultation with an available doctor | TEL-12.04 | QA: no online doctor → empty state; surcharge on checkout | Regression | Telemedicine | §10 + §2.3 | Instant consultation / Instant consult request / Queue & doctor offer | Patient can request an immediate consultation with an available doctor / See position in queue and accept an offered doctor | Patient + Doctor | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
540 | 540 | M13 | Communications | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.1 | COM-01 | SMS — appointment confirmation, registration confirmation, doctor-unavailable, OTP, reschedule and cancellation | COM-01.01 | DB: SmsTemplate, SmsMessageLog; Patient.SmsOptOut | New | Notifications | §14 | SMS | Appointment confirmation, registration confirmation, doctor-unavailable notice, OTP, reschedule and cancellation alerts | Shared | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
541 | 541 | M13 | Communications | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.1 | COM-01 | SMS — appointment confirmation, registration confirmation, doctor-unavailable, OTP, reschedule and cancellation | COM-01.02 | API: Templates CRUD; Send; History; event worker | New | Notifications | §14 | SMS | Appointment confirmation, registration confirmation, doctor-unavailable notice, OTP, reschedule and cancellation alerts | Shared | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
542 | 542 | M13 | Communications | UI | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.1 | COM-01 | SMS — appointment confirmation, registration confirmation, doctor-unavailable, OTP, reschedule and cancellation | COM-01.03 | Doctor /doctor/sms enable-per-event; admin templates | New | Notifications | §14 | SMS | Appointment confirmation, registration confirmation, doctor-unavailable notice, OTP, reschedule and cancellation alerts | Shared | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
543 | 543 | M13 | Communications | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.1 | COM-01 | SMS — appointment confirmation, registration confirmation, doctor-unavailable, OTP, reschedule and cancellation | COM-01.04 | MSG91/Twilio/etc. from PRE-03 | New Integration | Notifications | §14 | SMS | Appointment confirmation, registration confirmation, doctor-unavailable notice, OTP, reschedule and cancellation alerts | Shared | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
544 | 544 | M13 | Communications | QA | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.1 | COM-01 | SMS — appointment confirmation, registration confirmation, doctor-unavailable, OTP, reschedule and cancellation | COM-01.05 | QA: OTP SMS; reschedule old→new; cancel; doctor unavailable; opt-out honored | Regression | Notifications | §14 | SMS | Appointment confirmation, registration confirmation, doctor-unavailable notice, OTP, reschedule and cancellation alerts | Shared | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
545 | 545 | M13 | Communications | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.2 | COM-02 | WhatsApp — templates, offers, health tips and bulk messaging with delivery reports and opt-out (complete remaining ~50%) | COM-02.01 | Extend WhatsApp log if delivery receipts not stored | Existing Improvement | Notifications | §14 | WhatsApp | Templates, offers, health tips and bulk messaging to patients, with delivery reports and opt-out | Doctor Web | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
546 | 546 | M13 | Communications | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.2 | COM-02 | WhatsApp — templates, offers, health tips and bulk messaging with delivery reports and opt-out (complete remaining ~50%) | COM-02.02 | Finish bulk worker + receipt webhook | Existing Improvement | Notifications | §14 | WhatsApp | Templates, offers, health tips and bulk messaging to patients, with delivery reports and opt-out | Doctor Web | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
547 | 547 | M13 | Communications | UI | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.2 | COM-02 | WhatsApp — templates, offers, health tips and bulk messaging with delivery reports and opt-out (complete remaining ~50%) | COM-02.03 | WhatsAppModal: campaign status, failures, opt-out | Existing Improvement | Notifications | §14 | WhatsApp | Templates, offers, health tips and bulk messaging to patients, with delivery reports and opt-out | Doctor Web | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
548 | 548 | M13 | Communications | QA | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.2 | COM-02 | WhatsApp — templates, offers, health tips and bulk messaging with delivery reports and opt-out (complete remaining ~50%) | COM-02.04 | QA: opt-in required; template rejected state | Regression | Notifications | §14 | WhatsApp | Templates, offers, health tips and bulk messaging to patients, with delivery reports and opt-out | Doctor Web | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
549 | 549 | M13 | Communications | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.3 | COM-03 | Push notifications — booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests | COM-03.01 | DB: DeviceToken, AppNotification | New | Notifications | §14 + §2.9 + §3 | Push notifications | Booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests / Patient waiting, new booking, reschedule, cancellation, refill request, payment received | Patient App + Doctor App | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
550 | 550 | M13 | Communications | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.3 | COM-03 | Push notifications — booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests | COM-03.02 | API: Devices/Register; Notifications/Send; list | New | Notifications | §14 + §2.9 + §3 | Push notifications | Booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests / Patient waiting, new booking, reschedule, cancellation, refill request, payment received | Patient App + Doctor App | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
551 | 551 | M13 | Communications | UI | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.3 | COM-03 | Push notifications — booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests | COM-03.03 | Server event hooks (apps consume in 16–17) | New | Notifications | §14 + §2.9 + §3 | Push notifications | Booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests / Patient waiting, new booking, reschedule, cancellation, refill request, payment received | Patient App + Doctor App | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
552 | 552 | M13 | Communications | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.3 | COM-03 | Push notifications — booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests | COM-03.04 | FCM + APNs | New Integration | Notifications | §14 + §2.9 + §3 | Push notifications | Booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests / Patient waiting, new booking, reschedule, cancellation, refill request, payment received | Patient App + Doctor App | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
553 | 553 | M13 | Communications | QA | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.3 | COM-03 | Push notifications — booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests | COM-03.05 | QA: doctor and patient payloads isolated; token refresh | Regression | Notifications | §14 + §2.9 + §3 | Push notifications | Booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests / Patient waiting, new booking, reschedule, cancellation, refill request, payment received | Patient App + Doctor App | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
554 | 554 | M13 | Communications | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.4 | COM-04 | Email — registration, activation, password reset, invoices and receipts | COM-04.01 | EmailMessageLog if missing | Existing Improvement | Notifications | §14 | Email | Registration, activation, password reset, invoices and receipts | Shared | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
555 | 555 | M13 | Communications | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.4 | COM-04 | Email — registration, activation, password reset, invoices and receipts | COM-04.02 | Send invoice/receipt email on PAID; keep activation/reset | Existing Improvement | Notifications | §14 | Email | Registration, activation, password reset, invoices and receipts | Shared | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
556 | 556 | M13 | Communications | UI | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.4 | COM-04 | Email — registration, activation, password reset, invoices and receipts | COM-04.03 | No new public page — transactional only | Existing Improvement | Notifications | §14 | Email | Registration, activation, password reset, invoices and receipts | Shared | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
557 | 557 | M13 | Communications | QA | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.4 | COM-04 | Email — registration, activation, password reset, invoices and receipts | COM-04.04 | QA: reset still has no plaintext password; invoice attached | Regression | Notifications | §14 | Email | Registration, activation, password reset, invoices and receipts | Shared | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
558 | 558 | M13 | Communications | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.5 | COM-05 | In-app notification centre — all alerts collected in one place for patients and doctors | COM-05.01 | Reuse AppNotification | New | Notifications | §14 + §2.8 | In-app notification centre / Notifications centre | All alerts collected in one place for patients and doctors / All alerts in one place | Patient App + Doctor Web/App | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
559 | 559 | M13 | Communications | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.5 | COM-05 | In-app notification centre — all alerts collected in one place for patients and doctors | COM-05.02 | GET/PATCH notifications | New | Notifications | §14 + §2.8 | In-app notification centre / Notifications centre | All alerts collected in one place for patients and doctors / All alerts in one place | Patient App + Doctor Web/App | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
560 | 560 | M13 | Communications | UI | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.5 | COM-05 | In-app notification centre — all alerts collected in one place for patients and doctors | COM-05.03 | Doctor web bell; patient/doctor app centres in 16–17 | New | Notifications | §14 + §2.8 | In-app notification centre / Notifications centre | All alerts collected in one place for patients and doctors / All alerts in one place | Patient App + Doctor Web/App | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
561 | 561 | M13 | Communications | QA | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.5 | COM-05 | In-app notification centre — all alerts collected in one place for patients and doctors | COM-05.04 | QA: mark read; empty state; not Velzon demo route | Regression | Notifications | §14 + §2.8 | In-app notification centre / Notifications centre | All alerts collected in one place for patients and doctors / All alerts in one place | Patient App + Doctor Web/App | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
562 | 562 | M14 | Support & help desk | Web | 13 | Phase 13 — Support & help desk (PDF §15) | 13.1 | SUP-01 | Patient support tickets — patients raise issues from the app and track them | SUP-01.01 | DB: SupportTicket, SupportTicketMessage, SupportTicketAttachment | New | Support | §15 + §2.9 | Patient support tickets / Help centre & support tickets | Patients raise issues from the app and track them to resolution | Patient App + Admin | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
563 | 563 | M14 | Support & help desk | Web | 13 | Phase 13 — Support & help desk (PDF §15) | 13.1 | SUP-01 | Patient support tickets — patients raise issues from the app and track them | SUP-01.02 | API: create/list/mine for patient | New | Support | §15 + §2.9 | Patient support tickets / Help centre & support tickets | Patients raise issues from the app and track them to resolution | Patient App + Admin | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
564 | 564 | M14 | Support & help desk | UI | 13 | Phase 13 — Support & help desk (PDF §15) | 13.1 | SUP-01 | Patient support tickets — patients raise issues from the app and track them | SUP-01.03 | Patient app screens in Phase 16; web help optional | New | Support | §15 + §2.9 | Patient support tickets / Help centre & support tickets | Patients raise issues from the app and track them to resolution | Patient App + Admin | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
565 | 565 | M14 | Support & help desk | QA | 13 | Phase 13 — Support & help desk (PDF §15) | 13.1 | SUP-01 | Patient support tickets — patients raise issues from the app and track them | SUP-01.04 | QA: IDOR; attachment via SEC-09 | Regression | Support | §15 + §2.9 | Patient support tickets / Help centre & support tickets | Patients raise issues from the app and track them to resolution | Patient App + Admin | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
566 | 566 | M14 | Support & help desk | Web | 13 | Phase 13 — Support & help desk (PDF §15) | 13.2 | SUP-02 | Doctor support tickets — doctors raise issues from the portal | SUP-02.01 | Reuse SupportTicket with ReporterRole=Doctor | New | Support | §15 | Doctor support tickets | Doctors raise issues from the portal | Doctor Web + Admin | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
567 | 567 | M14 | Support & help desk | UI | 13 | Phase 13 — Support & help desk (PDF §15) | 13.2 | SUP-02 | Doctor support tickets — doctors raise issues from the portal | SUP-02.02 | /doctor/support list/create/detail | New | Support | §15 | Doctor support tickets | Doctors raise issues from the portal | Doctor Web + Admin | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
568 | 568 | M14 | Support & help desk | QA | 13 | Phase 13 — Support & help desk (PDF §15) | 13.2 | SUP-02 | Doctor support tickets — doctors raise issues from the portal | SUP-02.03 | QA: doctor cannot see another doctor’s tickets | Regression | Support | §15 | Doctor support tickets | Doctors raise issues from the portal | Doctor Web + Admin | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
569 | 569 | M14 | Support & help desk | Web | 13 | Phase 13 — Support & help desk (PDF §15) | 13.3 | SUP-03 | Admin issue queue — all issues in one queue with priority, assignment and status | SUP-03.01 | Extend ticket with Priority, Assignee, SLA | New | Support | §15 + §7.2 | Admin issue queue / Support ticket queue | All issues in one queue with priority, assignment and status / All patient and doctor issues in one queue with assignment and resolution | Admin Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
570 | 570 | M14 | Support & help desk | Web | 13 | Phase 13 — Support & help desk (PDF §15) | 13.3 | SUP-03 | Admin issue queue — all issues in one queue with priority, assignment and status | SUP-03.02 | Admin list/filter/assign/status | New | Support | §15 + §7.2 | Admin issue queue / Support ticket queue | All issues in one queue with priority, assignment and status / All patient and doctor issues in one queue with assignment and resolution | Admin Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
571 | 571 | M14 | Support & help desk | UI | 13 | Phase 13 — Support & help desk (PDF §15) | 13.3 | SUP-03 | Admin issue queue — all issues in one queue with priority, assignment and status | SUP-03.03 | /admin/support-tickets and /:id | New | Support | §15 + §7.2 | Admin issue queue / Support ticket queue | All issues in one queue with priority, assignment and status / All patient and doctor issues in one queue with assignment and resolution | Admin Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
572 | 572 | M14 | Support & help desk | QA | 13 | Phase 13 — Support & help desk (PDF §15) | 13.3 | SUP-03 | Admin issue queue — all issues in one queue with priority, assignment and status | SUP-03.04 | QA: not using Velzon ticket pages | Regression | Support | §15 + §7.2 | Admin issue queue / Support ticket queue | All issues in one queue with priority, assignment and status / All patient and doctor issues in one queue with assignment and resolution | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
573 | 573 | M14 | Support & help desk | Web | 13 | Phase 13 — Support & help desk (PDF §15) | 13.4 | SUP-04 | Ticket conversation — full message thread with attachments | SUP-04.01 | API: messages CRUD + attachment | New | Support | §15 | Ticket conversation | Full message thread with attachments | Admin + Doctor + Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
574 | 574 | M14 | Support & help desk | UI | 13 | Phase 13 — Support & help desk (PDF §15) | 13.4 | SUP-04 | Ticket conversation — full message thread with attachments | SUP-04.02 | Detail UI thread | New | Support | §15 | Ticket conversation | Full message thread with attachments | Admin + Doctor + Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
575 | 575 | M14 | Support & help desk | QA | 13 | Phase 13 — Support & help desk (PDF §15) | 13.4 | SUP-04 | Ticket conversation — full message thread with attachments | SUP-04.03 | QA: attachment unauthorised download 403 | Regression | Support | §15 | Ticket conversation | Full message thread with attachments | Admin + Doctor + Patient | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
576 | 576 | M14 | Support & help desk | UI | 13 | Phase 13 — Support & help desk (PDF §15) | 13.5 | SUP-05 | Enquiry management — website enquiries tracked (ties WEB-06) | SUP-05.01 | Admin enquiry inbox SLA fields | Existing Improvement | Support | §15 + §4 | Enquiry management | Website enquiries reach the admin team and are tracked | Admin Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
577 | 577 | M14 | Support & help desk | QA | 13 | Phase 13 — Support & help desk (PDF §15) | 13.5 | SUP-05 | Enquiry management — website enquiries tracked (ties WEB-06) | SUP-05.02 | QA: convert to ticket keeps original enquiry id | Regression | Support | §15 + §4 | Enquiry management | Website enquiries reach the admin team and are tracked | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
578 | 578 | M14 | Support & help desk | Web | 13 | Phase 13 — Support & help desk (PDF §15) | 13.6 | SUP-06 | Help centre — self-service help content for patients | SUP-06.01 | HelpArticle table or reuse blog category=help | New | Support | §15 + §2.9 | Help centre | Self-service help content for patients | Patient Website + App | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
579 | 579 | M14 | Support & help desk | Web | 13 | Phase 13 — Support & help desk (PDF §15) | 13.6 | SUP-06 | Help centre — self-service help content for patients | SUP-06.02 | Public GET help articles | New | Support | §15 + §2.9 | Help centre | Self-service help content for patients | Patient Website + App | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
580 | 580 | M14 | Support & help desk | UI | 13 | Phase 13 — Support & help desk (PDF §15) | 13.6 | SUP-06 | Help centre — self-service help content for patients | SUP-06.03 | Help centre list/detail | New | Support | §15 + §2.9 | Help centre | Self-service help content for patients | Patient Website + App | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
581 | 581 | M14 | Support & help desk | QA | 13 | Phase 13 — Support & help desk (PDF §15) | 13.6 | SUP-06 | Help centre — self-service help content for patients | SUP-06.04 | QA: unpublished hidden | Regression | Support | §15 + §2.9 | Help centre | Self-service help content for patients | Patient Website + App | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
582 | 582 | M14 | Support & help desk | Web | 13 | Phase 13 — Support & help desk (PDF §15) | 13.7 | SUP-07 | Assisted booking — help for patients who need support booking | SUP-07.01 | Flag BookingChannel=Assisted; AssistedRequest ticket type | New | Support | §15 + §2.9 | Assisted booking | Support for patients who need help booking / Help for patients who need support booking | Support + Reception + Patient | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
583 | 583 | M14 | Support & help desk | Web | 13 | Phase 13 — Support & help desk (PDF §15) | 13.7 | SUP-07 | Assisted booking — help for patients who need support booking | SUP-07.02 | API: request assistance; staff completes WEB-04 create on behalf | New | Support | §15 + §2.9 | Assisted booking | Support for patients who need help booking / Help for patients who need support booking | Support + Reception + Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
584 | 584 | M14 | Support & help desk | UI | 13 | Phase 13 — Support & help desk (PDF §15) | 13.7 | SUP-07 | Assisted booking — help for patients who need support booking | SUP-07.03 | Patient CTA; admin/reception assisted-book wizard | New | Support | §15 + §2.9 | Assisted booking | Support for patients who need help booking / Help for patients who need support booking | Support + Reception + Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
585 | 585 | M14 | Support & help desk | QA | 13 | Phase 13 — Support & help desk (PDF §15) | 13.7 | SUP-07 | Assisted booking — help for patients who need support booking | SUP-07.04 | QA: consent still captured; payment still Homeocentrum | Regression | Support | §15 + §2.9 | Assisted booking | Support for patients who need help booking / Help for patients who need support booking | Support + Reception + Patient | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
586 | 586 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.1 | MED-01 | Pharmacy partner onboarding — licensed premises, licence records, activation checklist | MED-01.01 | DB: PharmacyPartner, PharmacyLicence, activation checklist fields | New | HomeoMeds | §12 + §7.2 | Pharmacy partner onboarding / Pharmacy partner management | Licensed premises registered with licence records and an activation checklist / Onboard and activate licensed pharmacies | Pharmacy + Admin | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
587 | 587 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.1 | MED-01 | Pharmacy partner onboarding — licensed premises, licence records, activation checklist | MED-01.02 | API: onboard, admin activate, pharmacy login role | New | HomeoMeds | §12 + §7.2 | Pharmacy partner onboarding / Pharmacy partner management | Licensed premises registered with licence records and an activation checklist / Onboard and activate licensed pharmacies | Pharmacy + Admin | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
588 | 588 | M15 | HomeoMeds | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.1 | MED-01 | Pharmacy partner onboarding — licensed premises, licence records, activation checklist | MED-01.03 | /pharmacy/onboard; /admin pharmacy partners | New | HomeoMeds | §12 + §7.2 | Pharmacy partner onboarding / Pharmacy partner management | Licensed premises registered with licence records and an activation checklist / Onboard and activate licensed pharmacies | Pharmacy + Admin | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
589 | 589 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.1 | MED-01 | Pharmacy partner onboarding — licensed premises, licence records, activation checklist | MED-01.04 | QA: checklist incomplete blocks activate | Regression | HomeoMeds | §12 + §7.2 | Pharmacy partner onboarding / Pharmacy partner management | Licensed premises registered with licence records and an activation checklist / Onboard and activate licensed pharmacies | Pharmacy + Admin | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
590 | 590 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.2 | MED-02 | Licence gating — expired or suspended licences blocked automatically from receiving orders | MED-02.01 | Job: mark licence expired/suspended; exclude from routing | New | HomeoMeds | §12 | Licence gating | Pharmacies with expired or suspended licences are blocked automatically from receiving orders | Backend | Backend | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
591 | 591 | M15 | HomeoMeds | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.2 | MED-02 | Licence gating — expired or suspended licences blocked automatically from receiving orders | MED-02.02 | Pharmacy console status banner | New | HomeoMeds | §12 | Licence gating | Pharmacies with expired or suspended licences are blocked automatically from receiving orders | Backend | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
592 | 592 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.2 | MED-02 | Licence gating — expired or suspended licences blocked automatically from receiving orders | MED-02.03 | QA: expire a licence in test → order not offered | Regression | HomeoMeds | §12 | Licence gating | Pharmacies with expired or suspended licences are blocked automatically from receiving orders | Backend | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
593 | 593 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.3 | MED-03 | Fulfilment consent & pharmacy selection — patient chooses the seller and consents before the prescription is shared | MED-03.01 | Consent + selected PharmacyPartnerId on MedicineOrder | New | HomeoMeds | §12 + §2.7 | Fulfilment consent & pharmacy selection | The patient chooses the seller and consents before the prescription is shared | Patient | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
594 | 594 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.3 | MED-03 | Fulfilment consent & pharmacy selection — patient chooses the seller and consents before the prescription is shared | MED-03.02 | API: list sellers; select; grant consent | New | HomeoMeds | §12 + §2.7 | Fulfilment consent & pharmacy selection | The patient chooses the seller and consents before the prescription is shared | Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
595 | 595 | M15 | HomeoMeds | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.3 | MED-03 | Fulfilment consent & pharmacy selection — patient chooses the seller and consents before the prescription is shared | MED-03.03 | Patient pharmacy pick UI (web optional + app Phase 16) | New | HomeoMeds | §12 + §2.7 | Fulfilment consent & pharmacy selection | The patient chooses the seller and consents before the prescription is shared | Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
596 | 596 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.3 | MED-03 | Fulfilment consent & pharmacy selection — patient chooses the seller and consents before the prescription is shared | MED-03.04 | QA: without consent, handoff API 403 | Regression | HomeoMeds | §12 + §2.7 | Fulfilment consent & pharmacy selection | The patient chooses the seller and consents before the prescription is shared | Patient | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
597 | 597 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.4 | MED-04 | Prescription handoff — signed prescription becomes the order directly — no re-entry, no transcription errors | MED-04.01 | DB: MedicineOrder, MedicineOrderItem from ErxSnapshot | New | HomeoMeds | §12 + §2.7 | Prescription handoff / Order start | The signed prescription becomes the order directly — no re-entry, no transcription errors / Start an order directly from the prescription | Patient + Pharmacy | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
598 | 598 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.4 | MED-04 | Prescription handoff — signed prescription becomes the order directly — no re-entry, no transcription errors | MED-04.02 | API: POST order from ErxId | New | HomeoMeds | §12 + §2.7 | Prescription handoff / Order start | The signed prescription becomes the order directly — no re-entry, no transcription errors / Start an order directly from the prescription | Patient + Pharmacy | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
599 | 599 | M15 | HomeoMeds | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.4 | MED-04 | Prescription handoff — signed prescription becomes the order directly — no re-entry, no transcription errors | MED-04.03 | Order start from patient eRx screen | New | HomeoMeds | §12 + §2.7 | Prescription handoff / Order start | The signed prescription becomes the order directly — no re-entry, no transcription errors / Start an order directly from the prescription | Patient + Pharmacy | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
600 | 600 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.4 | MED-04 | Prescription handoff — signed prescription becomes the order directly — no re-entry, no transcription errors | MED-04.04 | QA: line count mismatch fails sign-off | Regression | HomeoMeds | §12 + §2.7 | Prescription handoff / Order start | The signed prescription becomes the order directly — no re-entry, no transcription errors / Start an order directly from the prescription | Patient + Pharmacy | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
601 | 601 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.5 | MED-05 | Rule-based seller routing — licence validity, service area, working hours and capacity | MED-05.01 | DB: SellerRoutingRule (area, hours, capacity) | New | HomeoMeds | §12 | Rule-based seller routing | Orders routed by licence validity, service area, working hours and capacity | Backend | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
602 | 602 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.5 | MED-05 | Rule-based seller routing — licence validity, service area, working hours and capacity | MED-05.02 | Routing service used by seller list API | New | HomeoMeds | §12 | Rule-based seller routing | Orders routed by licence validity, service area, working hours and capacity | Backend | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
603 | 603 | M15 | HomeoMeds | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.5 | MED-05 | Rule-based seller routing — licence validity, service area, working hours and capacity | MED-05.03 | Admin/pharmacy hours and area config UI | New | HomeoMeds | §12 | Rule-based seller routing | Orders routed by licence validity, service area, working hours and capacity | Backend | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
604 | 604 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.5 | MED-05 | Rule-based seller routing — licence validity, service area, working hours and capacity | MED-05.04 | QA: capacity full excluded; hours closed excluded | Regression | HomeoMeds | §12 | Rule-based seller routing | Orders routed by licence validity, service area, working hours and capacity | Backend | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
605 | 605 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.6 | MED-06 | Manual stock confirmation — pharmacy confirms availability — no live inventory integration required | MED-06.01 | Accept payload includes stock confirmation; reject reason OUT_OF_STOCK | New | HomeoMeds | §12 | Manual stock confirmation | The pharmacy confirms availability — no live inventory integration required | Pharmacy console | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
606 | 606 | M15 | HomeoMeds | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.6 | MED-06 | Manual stock confirmation — pharmacy confirms availability — no live inventory integration required | MED-06.02 | Pharmacy UI confirm availability | New | HomeoMeds | §12 | Manual stock confirmation | The pharmacy confirms availability — no live inventory integration required | Pharmacy console | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
607 | 607 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.6 | MED-06 | Manual stock confirmation — pharmacy confirms availability — no live inventory integration required | MED-06.03 | QA: no inventory SKU table required | Regression | HomeoMeds | §12 | Manual stock confirmation | The pharmacy confirms availability — no live inventory integration required | Pharmacy console | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
608 | 608 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.7 | MED-07 | Pharmacy console — accept or reject, enter price quote, mark ready and dispatched | MED-07.01 | Order status machine: Offered/Accepted/Rejected/Quoted/Paid/Ready/Dispatched/Delivered | New | HomeoMeds | §12 | Pharmacy console | Accept or reject orders, enter the price quote, mark ready and dispatched | Pharmacy console | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
609 | 609 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.7 | MED-07 | Pharmacy console — accept or reject, enter price quote, mark ready and dispatched | MED-07.02 | API: accept(OTP), reject, quote, ready, dispatch | New | HomeoMeds | §12 | Pharmacy console | Accept or reject orders, enter the price quote, mark ready and dispatched | Pharmacy console | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
610 | 610 | M15 | HomeoMeds | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.7 | MED-07 | Pharmacy console — accept or reject, enter price quote, mark ready and dispatched | MED-07.03 | /pharmacy/orders and detail | New | HomeoMeds | §12 | Pharmacy console | Accept or reject orders, enter the price quote, mark ready and dispatched | Pharmacy console | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
611 | 611 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.7 | MED-07 | Pharmacy console — accept or reject, enter price quote, mark ready and dispatched | MED-07.04 | OTP on accept | New Integration | HomeoMeds | §12 | Pharmacy console | Accept or reject orders, enter the price quote, mark ready and dispatched | Pharmacy console | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
612 | 612 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.7 | MED-07 | Pharmacy console — accept or reject, enter price quote, mark ready and dispatched | MED-07.05 | QA: accept without OTP fails; names still hidden to patient until accept succeeds | Regression | HomeoMeds | §12 | Pharmacy console | Accept or reject orders, enter the price quote, mark ready and dispatched | Pharmacy console | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
613 | 613 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.8 | MED-08 | Quote before payment — the patient always sees the price before paying | MED-08.01 | DB: MedicineQuote | New | HomeoMeds | §12 + §2.7 | Quote before payment / Pharmacy selection & quote | The patient always sees the price before paying / Choose a licensed pharmacy and see the price before paying | Patient | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
614 | 614 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.8 | MED-08 | Quote before payment — the patient always sees the price before paying | MED-08.02 | API: quote, patient accept quote, then create medicine payment | New | HomeoMeds | §12 + §2.7 | Quote before payment / Pharmacy selection & quote | The patient always sees the price before paying / Choose a licensed pharmacy and see the price before paying | Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
615 | 615 | M15 | HomeoMeds | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.8 | MED-08 | Quote before payment — the patient always sees the price before paying | MED-08.03 | Patient quote screen | New | HomeoMeds | §12 + §2.7 | Quote before payment / Pharmacy selection & quote | The patient always sees the price before paying / Choose a licensed pharmacy and see the price before paying | Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
616 | 616 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.8 | MED-08 | Quote before payment — the patient always sees the price before paying | MED-08.04 | QA: price change after quote invalidates old quote | Regression | HomeoMeds | §12 + §2.7 | Quote before payment / Pharmacy selection & quote | The patient always sees the price before paying / Choose a licensed pharmacy and see the price before paying | Patient | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
617 | 617 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.9 | MED-09 | Payment or cash on delivery — both options, with status tracking | MED-09.01 | Wire PAY-07 CreateMedicineOrder; COD status enum | New | HomeoMeds | §12 + §9 | Payment or cash on delivery | Both options supported, with status tracking | Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
618 | 618 | M15 | HomeoMeds | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.9 | MED-09 | Payment or cash on delivery — both options, with status tracking | MED-09.02 | Patient pay vs COD UI | New | HomeoMeds | §12 + §9 | Payment or cash on delivery | Both options supported, with status tracking | Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
619 | 619 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.9 | MED-09 | Payment or cash on delivery — both options, with status tracking | MED-09.03 | QA: COD vs prepaid ledger split | Regression | HomeoMeds | §12 + §9 | Payment or cash on delivery | Both options supported, with status tracking | Patient | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
620 | 620 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.10 | MED-10 | Order tracking — live status for the patient at every stage | MED-10.01 | DB: MedicineOrderEvent | New | HomeoMeds | §12 + §2.7 | Order tracking | Live status for the patient at every stage / Live status from accepted to delivered | Patient | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
621 | 621 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.10 | MED-10 | Order tracking — live status for the patient at every stage | MED-10.02 | GET tracking by order id (patient) | New | HomeoMeds | §12 + §2.7 | Order tracking | Live status for the patient at every stage / Live status from accepted to delivered | Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
622 | 622 | M15 | HomeoMeds | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.10 | MED-10 | Order tracking — live status for the patient at every stage | MED-10.03 | Tracking UI | New | HomeoMeds | §12 + §2.7 | Order tracking | Live status for the patient at every stage / Live status from accepted to delivered | Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
623 | 623 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.10 | MED-10 | Order tracking — live status for the patient at every stage | MED-10.04 | Push on status change | New Integration | HomeoMeds | §12 + §2.7 | Order tracking | Live status for the patient at every stage / Live status from accepted to delivered | Patient | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
624 | 624 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.10 | MED-10 | Order tracking — live status for the patient at every stage | MED-10.05 | QA: dispatched without ready is invalid transition | Regression | HomeoMeds | §12 + §2.7 | Order tracking | Live status for the patient at every stage / Live status from accepted to delivered | Patient | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
625 | 625 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.11 | MED-11 | Medicine ledger shares — seller, platform and delivery recorded (FIN-03 live fill) | MED-11.01 | On captured medicine payment write three-share ledger lines | New | HomeoMeds | §12 + §8 | Medicine ledger | Seller, platform and delivery shares recorded separately from consultation money | Account | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
626 | 626 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.11 | MED-11 | Medicine ledger shares — seller, platform and delivery recorded (FIN-03 live fill) | MED-11.02 | QA: consult GMV unchanged by a medicine order | Regression | HomeoMeds | §12 + §8 | Medicine ledger | Seller, platform and delivery shares recorded separately from consultation money | Account | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
627 | 627 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.12 | MED-12 | Order exception queue — stuck, rejected or failed orders always surfaced — never silent | MED-12.01 | Exception rows for medicine orders | New | HomeoMeds | §12 | Order exception queue | Stuck, rejected or failed orders are always surfaced to the operations team — never silent | Admin + Account | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
628 | 628 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.12 | MED-12 | Order exception queue — stuck, rejected or failed orders always surfaced — never silent | MED-12.02 | Admin/ops list/detail/retry re-route | New | HomeoMeds | §12 | Order exception queue | Stuck, rejected or failed orders are always surfaced to the operations team — never silent | Admin + Account | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
629 | 629 | M15 | HomeoMeds | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.12 | MED-12 | Order exception queue — stuck, rejected or failed orders always surfaced — never silent | MED-12.03 | /admin/homemeds-exceptions | New | HomeoMeds | §12 | Order exception queue | Stuck, rejected or failed orders are always surfaced to the operations team — never silent | Admin + Account | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
630 | 630 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.12 | MED-12 | Order exception queue — stuck, rejected or failed orders always surfaced — never silent | MED-12.04 | QA: silent discard impossible (metric + queue) | Regression | HomeoMeds | §12 | Order exception queue | Stuck, rejected or failed orders are always surfaced to the operations team — never silent | Admin + Account | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
631 | 631 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.13 | MED-13 | OTP-based control — key actions verified by OTP so Homeocentrum can monitor and trace every transaction | MED-13.01 | Bind OTP actions: PharmacyAccept, (optional) QuoteLock, Payout already FIN-05 | New | HomeoMeds | §12 + §17 | OTP-based control | Key actions verified by OTP so Homeocentrum can monitor and trace every transaction | Pharmacy + Account | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
632 | 632 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.13 | MED-13 | OTP-based control — key actions verified by OTP so Homeocentrum can monitor and trace every transaction | MED-13.02 | QA: Account OTP audit shows pharmacy accept | Regression | HomeoMeds | §12 + §17 | OTP-based control | Key actions verified by OTP so Homeocentrum can monitor and trace every transaction | Pharmacy + Account | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
633 | 633 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.14 | MED-14 | Refill orders — repeat orders raised from an existing prescription | MED-14.01 | On doctor approve, clone order from snapshot; patient one-tap | New | HomeoMeds | §12 + §2.7 + §11 | Refill orders / Order detail & refill | Repeat orders raised from an existing prescription / Full order history and one-tap refill request | Patient + Doctor | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
634 | 634 | M15 | HomeoMeds | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.14 | MED-14 | Refill orders — repeat orders raised from an existing prescription | MED-14.02 | Patient order detail + refill CTA | New | HomeoMeds | §12 + §2.7 + §11 | Refill orders / Order detail & refill | Repeat orders raised from an existing prescription / Full order history and one-tap refill request | Patient + Doctor | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
635 | 635 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.14 | MED-14 | Refill orders — repeat orders raised from an existing prescription | MED-14.03 | QA: original eRx unchanged | Regression | HomeoMeds | §12 + §2.7 + §11 | Refill orders / Order detail & refill | Repeat orders raised from an existing prescription / Full order history and one-tap refill request | Patient + Doctor | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
636 | 636 | M15 | HomeoMeds | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.15 | MED-15 | Order review & consent (patient) — confirm and consent before the prescription is shared | MED-15.01 | Patient review screen before handoff | New | HomeoMeds | §2.7 | Order review & consent | Confirm and consent before the prescription is shared | Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
637 | 637 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.15 | MED-15 | Order review & consent (patient) — confirm and consent before the prescription is shared | MED-15.02 | QA: back button does not share | Regression | HomeoMeds | §2.7 | Order review & consent | Confirm and consent before the prescription is shared | Patient | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
638 | 638 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.16 | MED-16 | Medicines tab — all medicine orders in one place (API now; app UI in Phase 16) | MED-16.01 | GET /api/Patient/MedicineOrders | New | HomeoMeds | §2.7 | Medicines tab | All medicine orders in one place | Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
639 | 639 | M15 | HomeoMeds | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.16 | MED-16 | Medicines tab — all medicine orders in one place (API now; app UI in Phase 16) | MED-16.02 | Optional web list; mobile tab later | New | HomeoMeds | §2.7 | Medicines tab | All medicine orders in one place | Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
640 | 640 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.16 | MED-16 | Medicines tab — all medicine orders in one place (API now; app UI in Phase 16) | MED-16.03 | QA: IDOR other patient 403 | Regression | HomeoMeds | §2.7 | Medicines tab | All medicine orders in one place | Patient | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
641 | 641 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.1 | CON-01 | Family members — add family members under one account | CON-01.01 | DB: FamilyMember | New | Patient identity | §2.1 | Family members | Add family members under one account | Patient App (API now) | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
642 | 642 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.1 | CON-01 | Family members — add family members under one account | CON-01.02 | API: CRUD family; book-as-member | New | Patient identity | §2.1 | Family members | Add family members under one account | Patient App (API now) | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
643 | 643 | M16 | Patient continuity APIs | UI | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.1 | CON-01 | Family members — add family members under one account | CON-01.03 | Consumed in Phase 16 | New | Patient identity | §2.1 | Family members | Add family members under one account | Patient App (API now) | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
644 | 644 | M16 | Patient continuity APIs | QA | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.1 | CON-01 | Family members — add family members under one account | CON-01.04 | QA: adult consent rules for minors documented | Regression | Patient identity | §2.1 | Family members | Add family members under one account | Patient App (API now) | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
645 | 645 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.2 | CON-02 | Caregiver authorization — let a family member book and manage on their behalf | CON-02.01 | DB: CaregiverAuth | New | Patient identity | §2.1 | Caregiver authorization | Let a family member book and manage on their behalf | Patient App (API now) | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
646 | 646 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.2 | CON-02 | Caregiver authorization — let a family member book and manage on their behalf | CON-02.02 | API: grant/revoke/list; booking authorisation check | New | Patient identity | §2.1 | Caregiver authorization | Let a family member book and manage on their behalf | Patient App (API now) | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
647 | 647 | M16 | Patient continuity APIs | UI | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.2 | CON-02 | Caregiver authorization — let a family member book and manage on their behalf | CON-02.03 | Consumed in Phase 16 | New | Patient identity | §2.1 | Caregiver authorization | Let a family member book and manage on their behalf | Patient App (API now) | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
648 | 648 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.2 | CON-02 | Caregiver authorization — let a family member book and manage on their behalf | CON-02.04 | OTP on grant | New Integration | Patient identity | §2.1 | Caregiver authorization | Let a family member book and manage on their behalf | Patient App (API now) | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
649 | 649 | M16 | Patient continuity APIs | QA | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.2 | CON-02 | Caregiver authorization — let a family member book and manage on their behalf | CON-02.05 | QA: revoked token cannot book | Regression | Patient identity | §2.1 | Caregiver authorization | Let a family member book and manage on their behalf | Patient App (API now) | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
650 | 650 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.3 | CON-03 | Records timeline + consultation note + document upload APIs | CON-03.01 | Reuse appointments + summary + eRx + SecureDocument | New | Patient records | §2.5 | Records timeline / Consultation note / Document upload | Complete visit history in date order / Doctor’s notes for each visit / Upload reports, scans and previous prescriptions | Patient App (API now) | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
651 | 651 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.3 | CON-03 | Records timeline + consultation note + document upload APIs | CON-03.02 | GET timeline; GET consultation note (summary); POST documents | New | Patient records | §2.5 | Records timeline / Consultation note / Document upload | Complete visit history in date order / Doctor’s notes for each visit / Upload reports, scans and previous prescriptions | Patient App (API now) | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
652 | 652 | M16 | Patient continuity APIs | UI | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.3 | CON-03 | Records timeline + consultation note + document upload APIs | CON-03.03 | Consumed in Phase 16 | New | Patient records | §2.5 | Records timeline / Consultation note / Document upload | Complete visit history in date order / Doctor’s notes for each visit / Upload reports, scans and previous prescriptions | Patient App (API now) | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
653 | 653 | M16 | Patient continuity APIs | QA | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.3 | CON-03 | Records timeline + consultation note + document upload APIs | CON-03.04 | QA: notes leak test on timeline JSON | Regression | Patient records | §2.5 | Records timeline / Consultation note / Document upload | Complete visit history in date order / Doctor’s notes for each visit / Upload reports, scans and previous prescriptions | Patient App (API now) | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
654 | 654 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.4 | CON-04 | Follow-up plan & tasks — clear next steps after each consultation | CON-04.01 | DB: FollowUpPlan, FollowUpTask | New | Continuity | §2.6 | Follow-up plan & tasks | Clear next steps after each consultation | Doctor Web + Patient | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
655 | 655 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.4 | CON-04 | Follow-up plan & tasks — clear next steps after each consultation | CON-04.02 | API: doctor set; patient list/complete | New | Continuity | §2.6 | Follow-up plan & tasks | Clear next steps after each consultation | Doctor Web + Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
656 | 656 | M16 | Patient continuity APIs | UI | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.4 | CON-04 | Follow-up plan & tasks — clear next steps after each consultation | CON-04.03 | Doctor board follow-up panel; app in Phase 16 | New | Continuity | §2.6 | Follow-up plan & tasks | Clear next steps after each consultation | Doctor Web + Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
657 | 657 | M16 | Patient continuity APIs | QA | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.4 | CON-04 | Follow-up plan & tasks — clear next steps after each consultation | CON-04.04 | QA: overdue flag | Regression | Continuity | §2.6 | Follow-up plan & tasks | Clear next steps after each consultation | Doctor Web + Patient | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
658 | 658 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.5 | CON-05 | Symptom diary — record symptoms between visits | CON-05.01 | DB: SymptomDiary | New | Continuity | §2.6 | Symptom diary | Record symptoms between visits | Patient App (API now) | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
659 | 659 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.5 | CON-05 | Symptom diary — record symptoms between visits | CON-05.02 | API: patient CRUD; doctor GET by patient | New | Continuity | §2.6 | Symptom diary | Record symptoms between visits | Patient App (API now) | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
660 | 660 | M16 | Patient continuity APIs | UI | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.5 | CON-05 | Symptom diary — record symptoms between visits | CON-05.03 | Doctor board read-only; app write Phase 16 | New | Continuity | §2.6 | Symptom diary | Record symptoms between visits | Patient App (API now) | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
661 | 661 | M16 | Patient continuity APIs | QA | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.5 | CON-05 | Symptom diary — record symptoms between visits | CON-05.04 | QA: IDOR | Regression | Continuity | §2.6 | Symptom diary | Record symptoms between visits | Patient App (API now) | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
662 | 662 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.6 | CON-06 | Progress tracking — see improvement over time across visits | CON-06.01 | Derived API from diary + appointments | New | Continuity | §2.6 | Progress tracking | See improvement over time across visits | Patient + Doctor | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
663 | 663 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.6 | CON-06 | Progress tracking — see improvement over time across visits | CON-06.02 | GET progress series | New | Continuity | §2.6 | Progress tracking | See improvement over time across visits | Patient + Doctor | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
664 | 664 | M16 | Patient continuity APIs | UI | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.6 | CON-06 | Progress tracking — see improvement over time across visits | CON-06.03 | Consumed in Phase 16 | New | Continuity | §2.6 | Progress tracking | See improvement over time across visits | Patient + Doctor | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
665 | 665 | M16 | Patient continuity APIs | QA | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.6 | CON-06 | Progress tracking — see improvement over time across visits | CON-06.04 | QA: no dummy numbers | Regression | Continuity | §2.6 | Progress tracking | See improvement over time across visits | Patient + Doctor | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
666 | 666 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.7 | CON-07 | Consent centre & data rights — view, manage and withdraw consents; request data | CON-07.01 | Reuse ConsentRecord; DataRequest table | New | Privacy | §17 + §2.8 | Consent centre & data rights | Patients can view, manage and withdraw consent / View, manage and withdraw consents; request data | Patient App (API now) | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
667 | 667 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.7 | CON-07 | Consent centre & data rights — view, manage and withdraw consents; request data | CON-07.02 | API: list/withdraw; request export/delete | New | Privacy | §17 + §2.8 | Consent centre & data rights | Patients can view, manage and withdraw consent / View, manage and withdraw consents; request data | Patient App (API now) | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
668 | 668 | M16 | Patient continuity APIs | UI | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.7 | CON-07 | Consent centre & data rights — view, manage and withdraw consents; request data | CON-07.03 | Consumed in Phase 16 | New | Privacy | §17 + §2.8 | Consent centre & data rights | Patients can view, manage and withdraw consent / View, manage and withdraw consents; request data | Patient App (API now) | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
669 | 669 | M16 | Patient continuity APIs | QA | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.7 | CON-07 | Consent centre & data rights — view, manage and withdraw consents; request data | CON-07.04 | QA: withdraw marketing stops WhatsApp/SMS offers | Regression | Privacy | §17 + §2.8 | Consent centre & data rights | Patients can view, manage and withdraw consent / View, manage and withdraw consents; request data | Patient App (API now) | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
670 | 670 | M08 | Account & finance | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.8 | CON-08 | Patient payments & refunds read model | CON-08.01 | GET /api/Patient/Payments | New | Patient money | §2.8 | Payments & refunds | Full payment history and refund status | Patient App (API now) | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
671 | 671 | M08 | Account & finance | QA | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.8 | CON-08 | Patient payments & refunds read model | CON-08.02 | QA: commission/GST internal lines hidden | Regression | Patient money | §2.8 | Payments & refunds | Full payment history and refund status | Patient App (API now) | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
672 | 672 | M05 | Appointments & scheduling | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.9 | CON-09 | Physical clinic appointment — book an in-person visit as well as online | CON-09.01 | Public/patient create booking accepts ConsultMode=In-clinic; uses in-clinic fee | Existing Improvement | Booking | §2.9 + §5.2 | Physical clinic appointment | Book an in-person visit as well as online | Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
673 | 673 | M05 | Appointments & scheduling | QA | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.9 | CON-09 | Physical clinic appointment — book an in-person visit as well as online | CON-09.02 | QA: in-clinic does not require device check/video | Regression | Booking | §2.9 + §5.2 | Physical clinic appointment | Book an in-person visit as well as online | Patient | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
674 | 674 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.10 | CON-10 | Patient profile setup API — name, age, gender, contact and health basics | CON-10.01 | Extend Patient with health-basics JSON/columns | New | Patient identity | §2.1 | Profile setup | Name, age, gender, contact and health basics | Patient App (API now) | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
675 | 675 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.10 | CON-10 | Patient profile setup API — name, age, gender, contact and health basics | CON-10.02 | GET/PUT /api/Patient/Profile | New | Patient identity | §2.1 | Profile setup | Name, age, gender, contact and health basics | Patient App (API now) | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
676 | 676 | M16 | Patient continuity APIs | UI | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.10 | CON-10 | Patient profile setup API — name, age, gender, contact and health basics | CON-10.03 | Consumed in Phase 16 | New | Patient identity | §2.1 | Profile setup | Name, age, gender, contact and health basics | Patient App (API now) | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
677 | 677 | M16 | Patient continuity APIs | QA | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.10 | CON-10 | Patient profile setup API — name, age, gender, contact and health basics | CON-10.04 | QA: cannot escalate to doctor role via profile PUT | Regression | Patient identity | §2.1 | Profile setup | Name, age, gender, contact and health basics | Patient App (API now) | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
678 | 678 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.1 | PAT-01 | Patient app — language selection on first open | PAT-01.01 | UI: Language selection screens (empty, loading, error, offline) | New | Patient Mobile | §2.1 | Language selection | Choose preferred language on first open | Patient Mobile App | Mobile UI | Pranav Bandekar | Yes | Done | Pranav Bandekar | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Done | Pranav Bandekar | No | N/A |  | 0 | Done |  | Edit on module sheet
679 | 679 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.1 | PAT-01 | Patient app — language selection on first open | PAT-01.02 | Wire to the Phase 8–15 API for: Language selection | New | Patient Mobile | §2.1 | Language selection | Choose preferred language on first open | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
680 | 680 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.1 | PAT-01 | Patient app — language selection on first open | PAT-01.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.1 | Language selection | Choose preferred language on first open | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
681 | 681 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.1 | PAT-01 | Patient app — language selection on first open | PAT-01.04 | QA both platforms: Language selection matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.1 | Language selection | Choose preferred language on first open | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
682 | 682 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.2 | PAT-02 | Patient app — welcome and introduction | PAT-02.01 | UI: Welcome & introduction screens (empty, loading, error, offline) | New | Patient Mobile | §2.1 | Welcome & introduction | Guided introduction to the app | Patient Mobile App | Mobile UI | Pranav Bandekar | Yes | Done | Pranav Bandekar | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Done | Pranav Bandekar | No | N/A |  | 0 | Done |  | Edit on module sheet
683 | 683 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.2 | PAT-02 | Patient app — welcome and introduction | PAT-02.02 | Wire to the Phase 8–15 API for: Welcome & introduction | New | Patient Mobile | §2.1 | Welcome & introduction | Guided introduction to the app | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
684 | 684 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.2 | PAT-02 | Patient app — welcome and introduction | PAT-02.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.1 | Welcome & introduction | Guided introduction to the app | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
685 | 685 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.2 | PAT-02 | Patient app — welcome and introduction | PAT-02.04 | QA both platforms: Welcome & introduction matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.1 | Welcome & introduction | Guided introduction to the app | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
686 | 686 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.3 | PAT-03 | Patient app — mobile number + OTP login (PatientAuth) | PAT-03.01 | UI: Mobile number + OTP login screens (empty, loading, error, offline) | New | Patient Mobile | §2.1 | Mobile number + OTP login | Secure sign-in with no password to remember | Patient Mobile App | Mobile UI | Pranav Bandekar | Yes | Done | Pranav Bandekar | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Done | Pranav Bandekar | No | N/A |  | 0 | Done |  | Edit on module sheet
687 | 687 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.3 | PAT-03 | Patient app — mobile number + OTP login (PatientAuth) | PAT-03.02 | Wire to the Phase 8–15 API for: Mobile number + OTP login | New | Patient Mobile | §2.1 | Mobile number + OTP login | Secure sign-in with no password to remember | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
688 | 688 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.3 | PAT-03 | Patient app — mobile number + OTP login (PatientAuth) | PAT-03.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.1 | Mobile number + OTP login | Secure sign-in with no password to remember | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
689 | 689 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.3 | PAT-03 | Patient app — mobile number + OTP login (PatientAuth) | PAT-03.04 | QA both platforms: Mobile number + OTP login matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.1 | Mobile number + OTP login | Secure sign-in with no password to remember | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
690 | 690 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.4 | PAT-04 | Patient app — profile setup | PAT-04.01 | UI: Profile setup screens (empty, loading, error, offline) | New | Patient Mobile | §2.1 | Profile setup | Name, age, gender, contact and health basics | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
691 | 691 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.4 | PAT-04 | Patient app — profile setup | PAT-04.02 | Wire to the Phase 8–15 API for: Profile setup | New | Patient Mobile | §2.1 | Profile setup | Name, age, gender, contact and health basics | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
692 | 692 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.4 | PAT-04 | Patient app — profile setup | PAT-04.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.1 | Profile setup | Name, age, gender, contact and health basics | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
693 | 693 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.4 | PAT-04 | Patient app — profile setup | PAT-04.04 | QA both platforms: Profile setup matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.1 | Profile setup | Name, age, gender, contact and health basics | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
694 | 694 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.5 | PAT-05 | Patient app — privacy consent before data stored | PAT-05.01 | UI: Privacy consent screens (empty, loading, error, offline) | New | Patient Mobile | §2.1 | Privacy consent | Clear consent before any personal data is stored | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
695 | 695 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.5 | PAT-05 | Patient app — privacy consent before data stored | PAT-05.02 | Wire to the Phase 8–15 API for: Privacy consent | New | Patient Mobile | §2.1 | Privacy consent | Clear consent before any personal data is stored | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
696 | 696 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.5 | PAT-05 | Patient app — privacy consent before data stored | PAT-05.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.1 | Privacy consent | Clear consent before any personal data is stored | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
697 | 697 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.5 | PAT-05 | Patient app — privacy consent before data stored | PAT-05.04 | QA both platforms: Privacy consent matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.1 | Privacy consent | Clear consent before any personal data is stored | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
698 | 698 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.6 | PAT-06 | Patient app — family members | PAT-06.01 | UI: Family members screens (empty, loading, error, offline) | New | Patient Mobile | §2.1 | Family members | Add family members under one account | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
699 | 699 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.6 | PAT-06 | Patient app — family members | PAT-06.02 | Wire to the Phase 8–15 API for: Family members | New | Patient Mobile | §2.1 | Family members | Add family members under one account | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
700 | 700 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.6 | PAT-06 | Patient app — family members | PAT-06.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.1 | Family members | Add family members under one account | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
701 | 701 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.6 | PAT-06 | Patient app — family members | PAT-06.04 | QA both platforms: Family members matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.1 | Family members | Add family members under one account | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
702 | 702 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.7 | PAT-07 | Patient app — caregiver authorization | PAT-07.01 | UI: Caregiver authorization screens (empty, loading, error, offline) | New | Patient Mobile | §2.1 | Caregiver authorization | Let a family member book and manage on their behalf | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
703 | 703 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.7 | PAT-07 | Patient app — caregiver authorization | PAT-07.02 | Wire to the Phase 8–15 API for: Caregiver authorization | New | Patient Mobile | §2.1 | Caregiver authorization | Let a family member book and manage on their behalf | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
704 | 704 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.7 | PAT-07 | Patient app — caregiver authorization | PAT-07.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.1 | Caregiver authorization | Let a family member book and manage on their behalf | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
705 | 705 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.7 | PAT-07 | Patient app — caregiver authorization | PAT-07.04 | QA both platforms: Caregiver authorization matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.1 | Caregiver authorization | Let a family member book and manage on their behalf | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
706 | 706 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.8 | PAT-08 | Patient app — home dashboard | PAT-08.01 | UI: Home dashboard screens (empty, loading, error, offline) | New | Patient Mobile | §2.2 | Home dashboard | Personalised home with upcoming visits and quick actions | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
707 | 707 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.8 | PAT-08 | Patient app — home dashboard | PAT-08.02 | Wire to the Phase 8–15 API for: Home dashboard | New | Patient Mobile | §2.2 | Home dashboard | Personalised home with upcoming visits and quick actions | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
708 | 708 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.8 | PAT-08 | Patient app — home dashboard | PAT-08.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.2 | Home dashboard | Personalised home with upcoming visits and quick actions | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
709 | 709 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.8 | PAT-08 | Patient app — home dashboard | PAT-08.04 | QA both platforms: Home dashboard matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.2 | Home dashboard | Personalised home with upcoming visits and quick actions | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
710 | 710 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.9 | PAT-09 | Patient app — search and care categories | PAT-09.01 | UI: Search & care categories screens (empty, loading, error, offline) | New | Patient Mobile | §2.2 | Search & care categories | Search by name, condition or category of care | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
711 | 711 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.9 | PAT-09 | Patient app — search and care categories | PAT-09.02 | Wire to the Phase 8–15 API for: Search & care categories | New | Patient Mobile | §2.2 | Search & care categories | Search by name, condition or category of care | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
712 | 712 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.9 | PAT-09 | Patient app — search and care categories | PAT-09.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.2 | Search & care categories | Search by name, condition or category of care | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
713 | 713 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.9 | PAT-09 | Patient app — search and care categories | PAT-09.04 | QA both platforms: Search & care categories matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.2 | Search & care categories | Search by name, condition or category of care | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
714 | 714 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.10 | PAT-10 | Patient app — search results | PAT-10.01 | UI: Search results screens (empty, loading, error, offline) | New | Patient Mobile | §2.2 | Search results | Clear list of available doctors | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
715 | 715 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.10 | PAT-10 | Patient app — search results | PAT-10.02 | Wire to the Phase 8–15 API for: Search results | New | Patient Mobile | §2.2 | Search results | Clear list of available doctors | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
716 | 716 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.10 | PAT-10 | Patient app — search results | PAT-10.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.2 | Search results | Clear list of available doctors | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
717 | 717 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.10 | PAT-10 | Patient app — search results | PAT-10.04 | QA both platforms: Search results matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.2 | Search results | Clear list of available doctors | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
718 | 718 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.11 | PAT-11 | Patient app — discovery filters | PAT-11.01 | UI: Filters screens (empty, loading, error, offline) | New | Patient Mobile | §2.2 | Filters | Narrow by availability, fee, experience, language and location | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
719 | 719 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.11 | PAT-11 | Patient app — discovery filters | PAT-11.02 | Wire to the Phase 8–15 API for: Filters | New | Patient Mobile | §2.2 | Filters | Narrow by availability, fee, experience, language and location | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
720 | 720 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.11 | PAT-11 | Patient app — discovery filters | PAT-11.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.2 | Filters | Narrow by availability, fee, experience, language and location | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
721 | 721 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.11 | PAT-11 | Patient app — discovery filters | PAT-11.04 | QA both platforms: Filters matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.2 | Filters | Narrow by availability, fee, experience, language and location | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
722 | 722 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.12 | PAT-12 | Patient app — doctor profile | PAT-12.01 | UI: Doctor profile screens (empty, loading, error, offline) | New | Patient Mobile | §2.2 | Doctor profile | Full profile with qualifications, experience and consultation fee | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
723 | 723 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.12 | PAT-12 | Patient app — doctor profile | PAT-12.02 | Wire to the Phase 8–15 API for: Doctor profile | New | Patient Mobile | §2.2 | Doctor profile | Full profile with qualifications, experience and consultation fee | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
724 | 724 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.12 | PAT-12 | Patient app — doctor profile | PAT-12.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.2 | Doctor profile | Full profile with qualifications, experience and consultation fee | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
725 | 725 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.12 | PAT-12 | Patient app — doctor profile | PAT-12.04 | QA both platforms: Doctor profile matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.2 | Doctor profile | Full profile with qualifications, experience and consultation fee | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
726 | 726 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.13 | PAT-13 | Patient app — verified badge on doctor | PAT-13.01 | UI: Credentials & verification screens (empty, loading, error, offline) | New | Patient Mobile | §2.2 | Credentials & verification | Verified badge showing the doctor’s credentials are checked | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
727 | 727 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.13 | PAT-13 | Patient app — verified badge on doctor | PAT-13.02 | Wire to the Phase 8–15 API for: Credentials & verification | New | Patient Mobile | §2.2 | Credentials & verification | Verified badge showing the doctor’s credentials are checked | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
728 | 728 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.13 | PAT-13 | Patient app — verified badge on doctor | PAT-13.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.2 | Credentials & verification | Verified badge showing the doctor’s credentials are checked | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
729 | 729 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.13 | PAT-13 | Patient app — verified badge on doctor | PAT-13.04 | QA both platforms: Credentials & verification matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.2 | Credentials & verification | Verified badge showing the doctor’s credentials are checked | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
730 | 730 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.14 | PAT-14 | Patient app — ranking explanation | PAT-14.01 | UI: Ranking explanation screens (empty, loading, error, offline) | New | Patient Mobile | §2.2 | Ranking explanation | Transparent explanation of why doctors appear in a given order | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
731 | 731 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.14 | PAT-14 | Patient app — ranking explanation | PAT-14.02 | Wire to the Phase 8–15 API for: Ranking explanation | New | Patient Mobile | §2.2 | Ranking explanation | Transparent explanation of why doctors appear in a given order | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
732 | 732 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.14 | PAT-14 | Patient app — ranking explanation | PAT-14.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.2 | Ranking explanation | Transparent explanation of why doctors appear in a given order | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
733 | 733 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.14 | PAT-14 | Patient app — ranking explanation | PAT-14.04 | QA both platforms: Ranking explanation matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.2 | Ranking explanation | Transparent explanation of why doctors appear in a given order | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
734 | 734 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.15 | PAT-15 | Patient app — health articles | PAT-15.01 | UI: Health articles screens (empty, loading, error, offline) | New | Patient Mobile | §2.2 | Health articles | Educational content to build trust and engagement | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
735 | 735 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.15 | PAT-15 | Patient app — health articles | PAT-15.02 | Wire to the Phase 8–15 API for: Health articles | New | Patient Mobile | §2.2 | Health articles | Educational content to build trust and engagement | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
736 | 736 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.15 | PAT-15 | Patient app — health articles | PAT-15.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.2 | Health articles | Educational content to build trust and engagement | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
737 | 737 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.15 | PAT-15 | Patient app — health articles | PAT-15.04 | QA both platforms: Health articles matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.2 | Health articles | Educational content to build trust and engagement | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
738 | 738 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.16 | PAT-16 | Patient app — slot picker | PAT-16.01 | UI: Slot picker screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Slot picker | See real available time slots and choose one | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
739 | 739 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.16 | PAT-16 | Patient app — slot picker | PAT-16.02 | Wire to the Phase 8–15 API for: Slot picker | New | Patient Mobile | §2.3 | Slot picker | See real available time slots and choose one | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
740 | 740 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.16 | PAT-16 | Patient app — slot picker | PAT-16.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Slot picker | See real available time slots and choose one | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
741 | 741 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.16 | PAT-16 | Patient app — slot picker | PAT-16.04 | QA both platforms: Slot picker matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Slot picker | See real available time slots and choose one | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
742 | 742 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.17 | PAT-17 | Patient app — booking review and consent | PAT-17.01 | UI: Booking review & consent screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Booking review & consent | Confirm details and consent before booking | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
743 | 743 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.17 | PAT-17 | Patient app — booking review and consent | PAT-17.02 | Wire to the Phase 8–15 API for: Booking review & consent | New | Patient Mobile | §2.3 | Booking review & consent | Confirm details and consent before booking | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
744 | 744 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.17 | PAT-17 | Patient app — booking review and consent | PAT-17.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Booking review & consent | Confirm details and consent before booking | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
745 | 745 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.17 | PAT-17 | Patient app — booking review and consent | PAT-17.04 | QA both platforms: Booking review & consent matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Booking review & consent | Confirm details and consent before booking | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
746 | 746 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.18 | PAT-18 | Patient app — checkout | PAT-18.01 | UI: Checkout screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Checkout | Pay the consultation fee inside the app | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
747 | 747 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.18 | PAT-18 | Patient app — checkout | PAT-18.02 | Wire to the Phase 8–15 API for: Checkout | New | Patient Mobile | §2.3 | Checkout | Pay the consultation fee inside the app | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
748 | 748 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.18 | PAT-18 | Patient app — checkout | PAT-18.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Checkout | Pay the consultation fee inside the app | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
749 | 749 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.18 | PAT-18 | Patient app — checkout | PAT-18.04 | QA both platforms: Checkout matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Checkout | Pay the consultation fee inside the app | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
750 | 750 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.19 | PAT-19 | Patient app — payment status | PAT-19.01 | UI: Payment status screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Payment status | Immediate confirmation of paid, pending or failed | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
751 | 751 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.19 | PAT-19 | Patient app — payment status | PAT-19.02 | Wire to the Phase 8–15 API for: Payment status | New | Patient Mobile | §2.3 | Payment status | Immediate confirmation of paid, pending or failed | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
752 | 752 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.19 | PAT-19 | Patient app — payment status | PAT-19.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Payment status | Immediate confirmation of paid, pending or failed | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
753 | 753 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.19 | PAT-19 | Patient app — payment status | PAT-19.04 | QA both platforms: Payment status matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Payment status | Immediate confirmation of paid, pending or failed | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
754 | 754 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.20 | PAT-20 | Patient app — appointment detail | PAT-20.01 | UI: Appointment detail screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Appointment detail | Full booking details in one place | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
755 | 755 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.20 | PAT-20 | Patient app — appointment detail | PAT-20.02 | Wire to the Phase 8–15 API for: Appointment detail | New | Patient Mobile | §2.3 | Appointment detail | Full booking details in one place | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
756 | 756 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.20 | PAT-20 | Patient app — appointment detail | PAT-20.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Appointment detail | Full booking details in one place | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
757 | 757 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.20 | PAT-20 | Patient app — appointment detail | PAT-20.04 | QA both platforms: Appointment detail matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Appointment detail | Full booking details in one place | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
758 | 758 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.21 | PAT-21 | Patient app — reschedule | PAT-21.01 | UI: Reschedule appointment screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Reschedule appointment | Move to another slot without calling the clinic | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
759 | 759 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.21 | PAT-21 | Patient app — reschedule | PAT-21.02 | Wire to the Phase 8–15 API for: Reschedule appointment | New | Patient Mobile | §2.3 | Reschedule appointment | Move to another slot without calling the clinic | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
760 | 760 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.21 | PAT-21 | Patient app — reschedule | PAT-21.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Reschedule appointment | Move to another slot without calling the clinic | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
761 | 761 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.21 | PAT-21 | Patient app — reschedule | PAT-21.04 | QA both platforms: Reschedule appointment matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Reschedule appointment | Move to another slot without calling the clinic | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
762 | 762 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.22 | PAT-22 | Patient app — cancel | PAT-22.01 | UI: Cancel appointment screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Cancel appointment | Cancel with reason, refund handled per policy | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
763 | 763 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.22 | PAT-22 | Patient app — cancel | PAT-22.02 | Wire to the Phase 8–15 API for: Cancel appointment | New | Patient Mobile | §2.3 | Cancel appointment | Cancel with reason, refund handled per policy | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
764 | 764 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.22 | PAT-22 | Patient app — cancel | PAT-22.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Cancel appointment | Cancel with reason, refund handled per policy | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
765 | 765 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.22 | PAT-22 | Patient app — cancel | PAT-22.04 | QA both platforms: Cancel appointment matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Cancel appointment | Cancel with reason, refund handled per policy | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
766 | 766 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.23 | PAT-23 | Patient app — waitlist offer | PAT-23.01 | UI: Waitlist offer screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Waitlist offer | Get offered a slot when one is freed by a cancellation | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
767 | 767 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.23 | PAT-23 | Patient app — waitlist offer | PAT-23.02 | Wire to the Phase 8–15 API for: Waitlist offer | New | Patient Mobile | §2.3 | Waitlist offer | Get offered a slot when one is freed by a cancellation | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
768 | 768 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.23 | PAT-23 | Patient app — waitlist offer | PAT-23.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Waitlist offer | Get offered a slot when one is freed by a cancellation | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
769 | 769 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.23 | PAT-23 | Patient app — waitlist offer | PAT-23.04 | QA both platforms: Waitlist offer matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Waitlist offer | Get offered a slot when one is freed by a cancellation | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
770 | 770 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.24 | PAT-24 | Patient app — instant consult request | PAT-24.01 | UI: Instant consult request screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Instant consult request | Request an immediate consultation with an available doctor | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
771 | 771 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.24 | PAT-24 | Patient app — instant consult request | PAT-24.02 | Wire to the Phase 8–15 API for: Instant consult request | New | Patient Mobile | §2.3 | Instant consult request | Request an immediate consultation with an available doctor | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
772 | 772 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.24 | PAT-24 | Patient app — instant consult request | PAT-24.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Instant consult request | Request an immediate consultation with an available doctor | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
773 | 773 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.24 | PAT-24 | Patient app — instant consult request | PAT-24.04 | QA both platforms: Instant consult request matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Instant consult request | Request an immediate consultation with an available doctor | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
774 | 774 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.25 | PAT-25 | Patient app — queue and doctor offer | PAT-25.01 | UI: Queue & doctor offer screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Queue & doctor offer | See position in queue and accept an offered doctor | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
775 | 775 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.25 | PAT-25 | Patient app — queue and doctor offer | PAT-25.02 | Wire to the Phase 8–15 API for: Queue & doctor offer | New | Patient Mobile | §2.3 | Queue & doctor offer | See position in queue and accept an offered doctor | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
776 | 776 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.25 | PAT-25 | Patient app — queue and doctor offer | PAT-25.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Queue & doctor offer | See position in queue and accept an offered doctor | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
777 | 777 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.25 | PAT-25 | Patient app — queue and doctor offer | PAT-25.04 | QA both platforms: Queue & doctor offer matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Queue & doctor offer | See position in queue and accept an offered doctor | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
778 | 778 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.26 | PAT-26 | Patient app — device check | PAT-26.01 | UI: Device check screens (empty, loading, error, offline) | New | Patient Mobile | §2.4 | Device check | Camera, microphone and network checked before the call | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
779 | 779 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.26 | PAT-26 | Patient app — device check | PAT-26.02 | Wire to the Phase 8–15 API for: Device check | New | Patient Mobile | §2.4 | Device check | Camera, microphone and network checked before the call | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
780 | 780 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.26 | PAT-26 | Patient app — device check | PAT-26.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.4 | Device check | Camera, microphone and network checked before the call | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
781 | 781 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.26 | PAT-26 | Patient app — device check | PAT-26.04 | QA both platforms: Device check matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.4 | Device check | Camera, microphone and network checked before the call | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
782 | 782 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.27 | PAT-27 | Patient app — waiting room | PAT-27.01 | UI: Waiting room screens (empty, loading, error, offline) | New | Patient Mobile | §2.4 | Waiting room | Wait with live status until the doctor joins | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
783 | 783 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.27 | PAT-27 | Patient app — waiting room | PAT-27.02 | Wire to the Phase 8–15 API for: Waiting room | New | Patient Mobile | §2.4 | Waiting room | Wait with live status until the doctor joins | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
784 | 784 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.27 | PAT-27 | Patient app — waiting room | PAT-27.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.4 | Waiting room | Wait with live status until the doctor joins | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
785 | 785 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.27 | PAT-27 | Patient app — waiting room | PAT-27.04 | QA both platforms: Waiting room matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.4 | Waiting room | Wait with live status until the doctor joins | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
786 | 786 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.28 | PAT-28 | Patient app — live video | PAT-28.01 | UI: Live video consultation screens (empty, loading, error, offline) | New | Patient Mobile | §2.4 | Live video consultation | Face-to-face consultation from home | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
787 | 787 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.28 | PAT-28 | Patient app — live video | PAT-28.02 | Wire to the Phase 8–15 API for: Live video consultation | New | Patient Mobile | §2.4 | Live video consultation | Face-to-face consultation from home | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
788 | 788 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.28 | PAT-28 | Patient app — live video | PAT-28.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.4 | Live video consultation | Face-to-face consultation from home | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
789 | 789 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.28 | PAT-28 | Patient app — live video | PAT-28.04 | QA both platforms: Live video consultation matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.4 | Live video consultation | Face-to-face consultation from home | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
790 | 790 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.29 | PAT-29 | Patient app — recording consent | PAT-29.01 | UI: Recording consent screens (empty, loading, error, offline) | New | Patient Mobile | §2.4 | Recording consent | Explicit consent requested before any recording | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
791 | 791 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.29 | PAT-29 | Patient app — recording consent | PAT-29.02 | Wire to the Phase 8–15 API for: Recording consent | New | Patient Mobile | §2.4 | Recording consent | Explicit consent requested before any recording | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
792 | 792 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.29 | PAT-29 | Patient app — recording consent | PAT-29.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.4 | Recording consent | Explicit consent requested before any recording | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
793 | 793 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.29 | PAT-29 | Patient app — recording consent | PAT-29.04 | QA both platforms: Recording consent matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.4 | Recording consent | Explicit consent requested before any recording | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
794 | 794 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.30 | PAT-30 | Patient app — join failure fallback | PAT-30.01 | UI: Fallback & join failure handling screens (empty, loading, error, offline) | New | Patient Mobile | §2.4 | Fallback & join failure handling | Clear guidance if the call fails, with options to retry | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
795 | 795 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.30 | PAT-30 | Patient app — join failure fallback | PAT-30.02 | Wire to the Phase 8–15 API for: Fallback & join failure handling | New | Patient Mobile | §2.4 | Fallback & join failure handling | Clear guidance if the call fails, with options to retry | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
796 | 796 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.30 | PAT-30 | Patient app — join failure fallback | PAT-30.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.4 | Fallback & join failure handling | Clear guidance if the call fails, with options to retry | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
797 | 797 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.30 | PAT-30 | Patient app — join failure fallback | PAT-30.04 | QA both platforms: Fallback & join failure handling matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.4 | Fallback & join failure handling | Clear guidance if the call fails, with options to retry | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
798 | 798 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.31 | PAT-31 | Patient app — case-linked chat | PAT-31.01 | UI: Case-linked chat screens (empty, loading, error, offline) | New | Patient Mobile | §2.4 | Case-linked chat | Chat tied to the consultation, not a loose message thread | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
799 | 799 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.31 | PAT-31 | Patient app — case-linked chat | PAT-31.02 | Wire to the Phase 8–15 API for: Case-linked chat | New | Patient Mobile | §2.4 | Case-linked chat | Chat tied to the consultation, not a loose message thread | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
800 | 800 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.31 | PAT-31 | Patient app — case-linked chat | PAT-31.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.4 | Case-linked chat | Chat tied to the consultation, not a loose message thread | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
801 | 801 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.31 | PAT-31 | Patient app — case-linked chat | PAT-31.04 | QA both platforms: Case-linked chat matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.4 | Case-linked chat | Chat tied to the consultation, not a loose message thread | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
802 | 802 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.32 | PAT-32 | Patient app — consultation summary | PAT-32.01 | UI: Consultation summary screens (empty, loading, error, offline) | New | Patient Mobile | §2.4 | Consultation summary | Written summary available immediately after the call | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
803 | 803 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.32 | PAT-32 | Patient app — consultation summary | PAT-32.02 | Wire to the Phase 8–15 API for: Consultation summary | New | Patient Mobile | §2.4 | Consultation summary | Written summary available immediately after the call | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
804 | 804 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.32 | PAT-32 | Patient app — consultation summary | PAT-32.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.4 | Consultation summary | Written summary available immediately after the call | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
805 | 805 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.32 | PAT-32 | Patient app — consultation summary | PAT-32.04 | QA both platforms: Consultation summary matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.4 | Consultation summary | Written summary available immediately after the call | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
806 | 806 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.33 | PAT-33 | Patient app — rejoin | PAT-33.01 | UI: Rejoin after dropped call screens (empty, loading, error, offline) | New | Patient Mobile | §2.4 | Rejoin after dropped call | Rejoin the same consultation if the connection drops | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
807 | 807 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.33 | PAT-33 | Patient app — rejoin | PAT-33.02 | Wire to the Phase 8–15 API for: Rejoin after dropped call | New | Patient Mobile | §2.4 | Rejoin after dropped call | Rejoin the same consultation if the connection drops | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
808 | 808 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.33 | PAT-33 | Patient app — rejoin | PAT-33.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.4 | Rejoin after dropped call | Rejoin the same consultation if the connection drops | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
809 | 809 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.33 | PAT-33 | Patient app — rejoin | PAT-33.04 | QA both platforms: Rejoin after dropped call matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.4 | Rejoin after dropped call | Rejoin the same consultation if the connection drops | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
810 | 810 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.34 | PAT-34 | Patient app — records timeline | PAT-34.01 | UI: Records timeline screens (empty, loading, error, offline) | New | Patient Mobile | §2.5 | Records timeline | Complete visit history in date order | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
811 | 811 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.34 | PAT-34 | Patient app — records timeline | PAT-34.02 | Wire to the Phase 8–15 API for: Records timeline | New | Patient Mobile | §2.5 | Records timeline | Complete visit history in date order | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
812 | 812 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.34 | PAT-34 | Patient app — records timeline | PAT-34.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.5 | Records timeline | Complete visit history in date order | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
813 | 813 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.34 | PAT-34 | Patient app — records timeline | PAT-34.04 | QA both platforms: Records timeline matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.5 | Records timeline | Complete visit history in date order | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
814 | 814 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.35 | PAT-35 | Patient app — consultation note (summary, not private notes) | PAT-35.01 | UI: Consultation note screens (empty, loading, error, offline) | New | Patient Mobile | §2.5 | Consultation note | Doctor’s notes for each visit | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
815 | 815 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.35 | PAT-35 | Patient app — consultation note (summary, not private notes) | PAT-35.02 | Wire to the Phase 8–15 API for: Consultation note | New | Patient Mobile | §2.5 | Consultation note | Doctor’s notes for each visit | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
816 | 816 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.35 | PAT-35 | Patient app — consultation note (summary, not private notes) | PAT-35.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.5 | Consultation note | Doctor’s notes for each visit | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
817 | 817 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.35 | PAT-35 | Patient app — consultation note (summary, not private notes) | PAT-35.04 | QA both platforms: Consultation note matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.5 | Consultation note | Doctor’s notes for each visit | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
818 | 818 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.36 | PAT-36 | Patient app — signed eRx (codes until pharmacy accept) | PAT-36.01 | UI: Signed digital prescription screens (empty, loading, error, offline) | New | Patient Mobile | §2.5 | Signed digital prescription | Official prescription issued by the doctor | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
819 | 819 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.36 | PAT-36 | Patient app — signed eRx (codes until pharmacy accept) | PAT-36.02 | Wire to the Phase 8–15 API for: Signed digital prescription | New | Patient Mobile | §2.5 | Signed digital prescription | Official prescription issued by the doctor | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
820 | 820 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.36 | PAT-36 | Patient app — signed eRx (codes until pharmacy accept) | PAT-36.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.5 | Signed digital prescription | Official prescription issued by the doctor | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
821 | 821 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.36 | PAT-36 | Patient app — signed eRx (codes until pharmacy accept) | PAT-36.04 | QA both platforms: Signed digital prescription matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.5 | Signed digital prescription | Official prescription issued by the doctor | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
822 | 822 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.37 | PAT-37 | Patient app — document upload | PAT-37.01 | UI: Document upload screens (empty, loading, error, offline) | New | Patient Mobile | §2.5 | Document upload | Upload reports, scans and previous prescriptions | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
823 | 823 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.37 | PAT-37 | Patient app — document upload | PAT-37.02 | Wire to the Phase 8–15 API for: Document upload | New | Patient Mobile | §2.5 | Document upload | Upload reports, scans and previous prescriptions | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
824 | 824 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.37 | PAT-37 | Patient app — document upload | PAT-37.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.5 | Document upload | Upload reports, scans and previous prescriptions | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
825 | 825 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.37 | PAT-37 | Patient app — document upload | PAT-37.04 | QA both platforms: Document upload matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.5 | Document upload | Upload reports, scans and previous prescriptions | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
826 | 826 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.38 | PAT-38 | Patient app — follow-up plan and tasks | PAT-38.01 | UI: Follow-up plan & tasks screens (empty, loading, error, offline) | New | Patient Mobile | §2.6 | Follow-up plan & tasks | Clear next steps after each consultation | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
827 | 827 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.38 | PAT-38 | Patient app — follow-up plan and tasks | PAT-38.02 | Wire to the Phase 8–15 API for: Follow-up plan & tasks | New | Patient Mobile | §2.6 | Follow-up plan & tasks | Clear next steps after each consultation | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
828 | 828 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.38 | PAT-38 | Patient app — follow-up plan and tasks | PAT-38.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.6 | Follow-up plan & tasks | Clear next steps after each consultation | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
829 | 829 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.38 | PAT-38 | Patient app — follow-up plan and tasks | PAT-38.04 | QA both platforms: Follow-up plan & tasks matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.6 | Follow-up plan & tasks | Clear next steps after each consultation | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
830 | 830 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.39 | PAT-39 | Patient app — symptom diary | PAT-39.01 | UI: Symptom diary screens (empty, loading, error, offline) | New | Patient Mobile | §2.6 | Symptom diary | Record symptoms between visits | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
831 | 831 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.39 | PAT-39 | Patient app — symptom diary | PAT-39.02 | Wire to the Phase 8–15 API for: Symptom diary | New | Patient Mobile | §2.6 | Symptom diary | Record symptoms between visits | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
832 | 832 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.39 | PAT-39 | Patient app — symptom diary | PAT-39.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.6 | Symptom diary | Record symptoms between visits | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
833 | 833 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.39 | PAT-39 | Patient app — symptom diary | PAT-39.04 | QA both platforms: Symptom diary matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.6 | Symptom diary | Record symptoms between visits | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
834 | 834 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.40 | PAT-40 | Patient app — progress tracking | PAT-40.01 | UI: Progress tracking screens (empty, loading, error, offline) | New | Patient Mobile | §2.6 | Progress tracking | See improvement over time across visits | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
835 | 835 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.40 | PAT-40 | Patient app — progress tracking | PAT-40.02 | Wire to the Phase 8–15 API for: Progress tracking | New | Patient Mobile | §2.6 | Progress tracking | See improvement over time across visits | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
836 | 836 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.40 | PAT-40 | Patient app — progress tracking | PAT-40.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.6 | Progress tracking | See improvement over time across visits | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
837 | 837 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.40 | PAT-40 | Patient app — progress tracking | PAT-40.04 | QA both platforms: Progress tracking matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.6 | Progress tracking | See improvement over time across visits | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
838 | 838 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.41 | PAT-41 | Patient app — medicines tab | PAT-41.01 | UI: Medicines tab screens (empty, loading, error, offline) | New | Patient Mobile | §2.7 | Medicines tab | All medicine orders in one place | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
839 | 839 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.41 | PAT-41 | Patient app — medicines tab | PAT-41.02 | Wire to the Phase 8–15 API for: Medicines tab | New | Patient Mobile | §2.7 | Medicines tab | All medicine orders in one place | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
840 | 840 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.41 | PAT-41 | Patient app — medicines tab | PAT-41.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.7 | Medicines tab | All medicine orders in one place | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
841 | 841 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.41 | PAT-41 | Patient app — medicines tab | PAT-41.04 | QA both platforms: Medicines tab matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.7 | Medicines tab | All medicine orders in one place | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
842 | 842 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.42 | PAT-42 | Patient app — start HomeoMeds order from eRx | PAT-42.01 | UI: Order start screens (empty, loading, error, offline) | New | Patient Mobile | §2.7 | Order start | Start an order directly from the prescription | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
843 | 843 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.42 | PAT-42 | Patient app — start HomeoMeds order from eRx | PAT-42.02 | Wire to the Phase 8–15 API for: Order start | New | Patient Mobile | §2.7 | Order start | Start an order directly from the prescription | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
844 | 844 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.42 | PAT-42 | Patient app — start HomeoMeds order from eRx | PAT-42.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.7 | Order start | Start an order directly from the prescription | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
845 | 845 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.42 | PAT-42 | Patient app — start HomeoMeds order from eRx | PAT-42.04 | QA both platforms: Order start matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.7 | Order start | Start an order directly from the prescription | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
846 | 846 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.43 | PAT-43 | Patient app — pharmacy selection and quote | PAT-43.01 | UI: Pharmacy selection & quote screens (empty, loading, error, offline) | New | Patient Mobile | §2.7 | Pharmacy selection & quote | Choose a licensed pharmacy and see the price before paying | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
847 | 847 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.43 | PAT-43 | Patient app — pharmacy selection and quote | PAT-43.02 | Wire to the Phase 8–15 API for: Pharmacy selection & quote | New | Patient Mobile | §2.7 | Pharmacy selection & quote | Choose a licensed pharmacy and see the price before paying | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
848 | 848 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.43 | PAT-43 | Patient app — pharmacy selection and quote | PAT-43.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.7 | Pharmacy selection & quote | Choose a licensed pharmacy and see the price before paying | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
849 | 849 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.43 | PAT-43 | Patient app — pharmacy selection and quote | PAT-43.04 | QA both platforms: Pharmacy selection & quote matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.7 | Pharmacy selection & quote | Choose a licensed pharmacy and see the price before paying | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
850 | 850 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.44 | PAT-44 | Patient app — order review and consent | PAT-44.01 | UI: Order review & consent screens (empty, loading, error, offline) | New | Patient Mobile | §2.7 | Order review & consent | Confirm and consent before the prescription is shared | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
851 | 851 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.44 | PAT-44 | Patient app — order review and consent | PAT-44.02 | Wire to the Phase 8–15 API for: Order review & consent | New | Patient Mobile | §2.7 | Order review & consent | Confirm and consent before the prescription is shared | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
852 | 852 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.44 | PAT-44 | Patient app — order review and consent | PAT-44.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.7 | Order review & consent | Confirm and consent before the prescription is shared | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
853 | 853 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.44 | PAT-44 | Patient app — order review and consent | PAT-44.04 | QA both platforms: Order review & consent matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.7 | Order review & consent | Confirm and consent before the prescription is shared | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
854 | 854 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.45 | PAT-45 | Patient app — order tracking | PAT-45.01 | UI: Order tracking screens (empty, loading, error, offline) | New | Patient Mobile | §2.7 | Order tracking | Live status from accepted to delivered | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
855 | 855 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.45 | PAT-45 | Patient app — order tracking | PAT-45.02 | Wire to the Phase 8–15 API for: Order tracking | New | Patient Mobile | §2.7 | Order tracking | Live status from accepted to delivered | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
856 | 856 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.45 | PAT-45 | Patient app — order tracking | PAT-45.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.7 | Order tracking | Live status from accepted to delivered | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
857 | 857 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.45 | PAT-45 | Patient app — order tracking | PAT-45.04 | QA both platforms: Order tracking matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.7 | Order tracking | Live status from accepted to delivered | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
858 | 858 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.46 | PAT-46 | Patient app — order detail and refill | PAT-46.01 | UI: Order detail & refill screens (empty, loading, error, offline) | New | Patient Mobile | §2.7 | Order detail & refill | Full order history and one-tap refill request | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
859 | 859 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.46 | PAT-46 | Patient app — order detail and refill | PAT-46.02 | Wire to the Phase 8–15 API for: Order detail & refill | New | Patient Mobile | §2.7 | Order detail & refill | Full order history and one-tap refill request | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
860 | 860 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.46 | PAT-46 | Patient app — order detail and refill | PAT-46.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.7 | Order detail & refill | Full order history and one-tap refill request | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
861 | 861 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.46 | PAT-46 | Patient app — order detail and refill | PAT-46.04 | QA both platforms: Order detail & refill matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.7 | Order detail & refill | Full order history and one-tap refill request | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
862 | 862 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.47 | PAT-47 | Patient app — write a review | PAT-47.01 | UI: Write a review screens (empty, loading, error, offline) | New | Patient Mobile | §2.8 | Write a review | Rate and review the consultation | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
863 | 863 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.47 | PAT-47 | Patient app — write a review | PAT-47.02 | Wire to the Phase 8–15 API for: Write a review | New | Patient Mobile | §2.8 | Write a review | Rate and review the consultation | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
864 | 864 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.47 | PAT-47 | Patient app — write a review | PAT-47.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.8 | Write a review | Rate and review the consultation | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
865 | 865 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.47 | PAT-47 | Patient app — write a review | PAT-47.04 | QA both platforms: Write a review matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.8 | Write a review | Rate and review the consultation | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
866 | 866 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.48 | PAT-48 | Patient app — my reviews and appeal | PAT-48.01 | UI: My reviews & appeal screens (empty, loading, error, offline) | New | Patient Mobile | §2.8 | My reviews & appeal | Manage reviews and raise an appeal | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
867 | 867 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.48 | PAT-48 | Patient app — my reviews and appeal | PAT-48.02 | Wire to the Phase 8–15 API for: My reviews & appeal | New | Patient Mobile | §2.8 | My reviews & appeal | Manage reviews and raise an appeal | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
868 | 868 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.48 | PAT-48 | Patient app — my reviews and appeal | PAT-48.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.8 | My reviews & appeal | Manage reviews and raise an appeal | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
869 | 869 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.48 | PAT-48 | Patient app — my reviews and appeal | PAT-48.04 | QA both platforms: My reviews & appeal matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.8 | My reviews & appeal | Manage reviews and raise an appeal | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
870 | 870 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.49 | PAT-49 | Patient app — payments and refunds | PAT-49.01 | UI: Payments & refunds screens (empty, loading, error, offline) | New | Patient Mobile | §2.8 | Payments & refunds | Full payment history and refund status | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
871 | 871 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.49 | PAT-49 | Patient app — payments and refunds | PAT-49.02 | Wire to the Phase 8–15 API for: Payments & refunds | New | Patient Mobile | §2.8 | Payments & refunds | Full payment history and refund status | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
872 | 872 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.49 | PAT-49 | Patient app — payments and refunds | PAT-49.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.8 | Payments & refunds | Full payment history and refund status | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
873 | 873 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.49 | PAT-49 | Patient app — payments and refunds | PAT-49.04 | QA both platforms: Payments & refunds matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.8 | Payments & refunds | Full payment history and refund status | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
874 | 874 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.50 | PAT-50 | Patient app — profile and settings | PAT-50.01 | UI: Profile & settings screens (empty, loading, error, offline) | New | Patient Mobile | §2.8 | Profile & settings | Manage personal details and preferences | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
875 | 875 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.50 | PAT-50 | Patient app — profile and settings | PAT-50.02 | Wire to the Phase 8–15 API for: Profile & settings | New | Patient Mobile | §2.8 | Profile & settings | Manage personal details and preferences | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
876 | 876 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.50 | PAT-50 | Patient app — profile and settings | PAT-50.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.8 | Profile & settings | Manage personal details and preferences | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
877 | 877 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.50 | PAT-50 | Patient app — profile and settings | PAT-50.04 | QA both platforms: Profile & settings matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.8 | Profile & settings | Manage personal details and preferences | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
878 | 878 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.51 | PAT-51 | Patient app — consent centre and data rights | PAT-51.01 | UI: Consent centre & data rights screens (empty, loading, error, offline) | New | Patient Mobile | §2.8 | Consent centre & data rights | View, manage and withdraw consents; request data | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
879 | 879 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.51 | PAT-51 | Patient app — consent centre and data rights | PAT-51.02 | Wire to the Phase 8–15 API for: Consent centre & data rights | New | Patient Mobile | §2.8 | Consent centre & data rights | View, manage and withdraw consents; request data | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
880 | 880 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.51 | PAT-51 | Patient app — consent centre and data rights | PAT-51.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.8 | Consent centre & data rights | View, manage and withdraw consents; request data | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
881 | 881 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.51 | PAT-51 | Patient app — consent centre and data rights | PAT-51.04 | QA both platforms: Consent centre & data rights matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.8 | Consent centre & data rights | View, manage and withdraw consents; request data | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
882 | 882 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.52 | PAT-52 | Patient app — notifications centre | PAT-52.01 | UI: Notifications centre screens (empty, loading, error, offline) | New | Patient Mobile | §2.8 | Notifications centre | All alerts in one place | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
883 | 883 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.52 | PAT-52 | Patient app — notifications centre | PAT-52.02 | Wire to the Phase 8–15 API for: Notifications centre | New | Patient Mobile | §2.8 | Notifications centre | All alerts in one place | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
884 | 884 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.52 | PAT-52 | Patient app — notifications centre | PAT-52.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.8 | Notifications centre | All alerts in one place | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
885 | 885 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.52 | PAT-52 | Patient app — notifications centre | PAT-52.04 | QA both platforms: Notifications centre matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.8 | Notifications centre | All alerts in one place | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
886 | 886 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.53 | PAT-53 | Patient app — help centre and tickets | PAT-53.01 | UI: Help centre & support tickets screens (empty, loading, error, offline) | New | Patient Mobile | §2.9 | Help centre & support tickets | Raise an issue and track it to resolution | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
887 | 887 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.53 | PAT-53 | Patient app — help centre and tickets | PAT-53.02 | Wire to the Phase 8–15 API for: Help centre & support tickets | New | Patient Mobile | §2.9 | Help centre & support tickets | Raise an issue and track it to resolution | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
888 | 888 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.53 | PAT-53 | Patient app — help centre and tickets | PAT-53.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.9 | Help centre & support tickets | Raise an issue and track it to resolution | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
889 | 889 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.53 | PAT-53 | Patient app — help centre and tickets | PAT-53.04 | QA both platforms: Help centre & support tickets matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.9 | Help centre & support tickets | Raise an issue and track it to resolution | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
890 | 890 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.54 | PAT-54 | Patient app — physical clinic booking | PAT-54.01 | UI: Physical clinic appointment screens (empty, loading, error, offline) | New | Patient Mobile | §2.9 | Physical clinic appointment | Book an in-person visit as well as online | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
891 | 891 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.54 | PAT-54 | Patient app — physical clinic booking | PAT-54.02 | Wire to the Phase 8–15 API for: Physical clinic appointment | New | Patient Mobile | §2.9 | Physical clinic appointment | Book an in-person visit as well as online | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
892 | 892 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.54 | PAT-54 | Patient app — physical clinic booking | PAT-54.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.9 | Physical clinic appointment | Book an in-person visit as well as online | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
893 | 893 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.54 | PAT-54 | Patient app — physical clinic booking | PAT-54.04 | QA both platforms: Physical clinic appointment matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.9 | Physical clinic appointment | Book an in-person visit as well as online | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
894 | 894 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.55 | PAT-55 | Patient app — assisted booking request | PAT-55.01 | UI: Assisted booking screens (empty, loading, error, offline) | New | Patient Mobile | §2.9 | Assisted booking | Help for patients who need support booking | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
895 | 895 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.55 | PAT-55 | Patient app — assisted booking request | PAT-55.02 | Wire to the Phase 8–15 API for: Assisted booking | New | Patient Mobile | §2.9 | Assisted booking | Help for patients who need support booking | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
896 | 896 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.55 | PAT-55 | Patient app — assisted booking request | PAT-55.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.9 | Assisted booking | Help for patients who need support booking | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
897 | 897 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.55 | PAT-55 | Patient app — assisted booking request | PAT-55.04 | QA both platforms: Assisted booking matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.9 | Assisted booking | Help for patients who need support booking | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
898 | 898 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.56 | PAT-56 | Patient app — low-data mode | PAT-56.01 | UI: Low-data mode screens (empty, loading, error, offline) | New | Patient Mobile | §2.9 | Low-data mode | Works on slow or limited connections | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
899 | 899 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.56 | PAT-56 | Patient app — low-data mode | PAT-56.02 | Wire to the Phase 8–15 API for: Low-data mode | New | Patient Mobile | §2.9 | Low-data mode | Works on slow or limited connections | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
900 | 900 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.56 | PAT-56 | Patient app — low-data mode | PAT-56.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.9 | Low-data mode | Works on slow or limited connections | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
901 | 901 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.56 | PAT-56 | Patient app — low-data mode | PAT-56.04 | QA both platforms: Low-data mode matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.9 | Low-data mode | Works on slow or limited connections | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
902 | 902 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.57 | PAT-57 | Patient app — push notifications | PAT-57.01 | UI: Push notifications screens (empty, loading, error, offline) | New | Patient Mobile | §2.9 | Push notifications | Booking confirmations, reminders, doctor ready, prescription issued, order updates | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
903 | 903 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.57 | PAT-57 | Patient app — push notifications | PAT-57.02 | Wire to the Phase 8–15 API for: Push notifications | New | Patient Mobile | §2.9 | Push notifications | Booking confirmations, reminders, doctor ready, prescription issued, order updates | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
904 | 904 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.57 | PAT-57 | Patient app — push notifications | PAT-57.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.9 | Push notifications | Booking confirmations, reminders, doctor ready, prescription issued, order updates | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
905 | 905 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.57 | PAT-57 | Patient app — push notifications | PAT-57.04 | QA both platforms: Push notifications matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.9 | Push notifications | Booking confirmations, reminders, doctor ready, prescription issued, order updates | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
906 | 906 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.58 | PAT-58 | Patient app — iOS and Android store release, device matrix, and parity QA | PAT-58.01 | CI: iOS + Android release builds; env pointing to .NET 8 | New | Patient Mobile | §2 + §18 | Patient mobile app iOS and Android | iOS and Android — onboarding, discovery, booking, payment, video consultation, records, prescriptions, follow-up, medicines, reviews, support, notifications | Patient Mobile App | Mobile | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 1 | Not Started |  | Edit on module sheet
907 | 907 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.58 | PAT-58 | Patient app — iOS and Android store release, device matrix, and parity QA | PAT-58.02 | Parity QA spreadsheet: each PAT-01..57 on both OS | Regression | Patient Mobile | §2 + §18 | Patient mobile app iOS and Android | iOS and Android — onboarding, discovery, booking, payment, video consultation, records, prescriptions, follow-up, medicines, reviews, support, notifications | Patient Mobile App | QA | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 1 | Not Started |  | Edit on module sheet
908 | 908 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.58 | PAT-58 | Patient app — iOS and Android store release, device matrix, and parity QA | PAT-58.03 | Crashlytics/Sentry equivalent for patient app | New Integration | Patient Mobile | §2 + §18 | Patient mobile app iOS and Android | iOS and Android — onboarding, discovery, booking, payment, video consultation, records, prescriptions, follow-up, medicines, reviews, support, notifications | Patient Mobile App | Mobile | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | 2 | Not Started |  | Edit on module sheet
909 | 909 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.1 | DMO-01 | Doctor app — login & identity (same login and same account as the web portal) | DMO-01.01 | Login screen (password or OTP-to-registered mobile) | New | Doctor Mobile | §3 | Login & identity | Same login and same account as the web portal | Doctor Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
910 | 910 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.1 | DMO-01 | Doctor app — login & identity (same login and same account as the web portal) | DMO-01.02 | Call same Login API; store JWT securely (Keychain/Keystore) | New | Doctor Mobile | §3 | Login & identity | Same login and same account as the web portal | Doctor Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
911 | 911 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.1 | DMO-01 | Doctor app — login & identity (same login and same account as the web portal) | DMO-01.03 | Expired session → re-login; no case-taking entry point | New | Doctor Mobile | §3 | Login & identity | Same login and same account as the web portal | Doctor Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
912 | 912 | M18 | Doctor mobile app | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.1 | DMO-01 | Doctor app — login & identity (same login and same account as the web portal) | DMO-01.04 | QA: same DoctorId as web; reception accounts must not open doctor clinical actions | Regression | Doctor Mobile | §3 | Login & identity | Same login and same account as the web portal | Doctor Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
913 | 913 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.2 | DMO-02 | Doctor app — first-run onboarding (guided setup, number confirmation and permissions) | DMO-02.01 | Onboarding screens | New | Doctor Mobile | §3 | First-run onboarding | Guided setup, number confirmation and permissions | Doctor Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
914 | 914 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.2 | DMO-02 | Doctor app — first-run onboarding (guided setup, number confirmation and permissions) | DMO-02.02 | Confirm number against profile | New | Doctor Mobile | §3 | First-run onboarding | Guided setup, number confirmation and permissions | Doctor Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
915 | 915 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.2 | DMO-02 | Doctor app — first-run onboarding (guided setup, number confirmation and permissions) | DMO-02.03 | Skip vs required steps documented | New | Doctor Mobile | §3 | First-run onboarding | Guided setup, number confirmation and permissions | Doctor Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
916 | 916 | M18 | Doctor mobile app | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.2 | DMO-02 | Doctor app — first-run onboarding (guided setup, number confirmation and permissions) | DMO-02.04 | QA: number mismatch blocked | Regression | Doctor Mobile | §3 | First-run onboarding | Guided setup, number confirmation and permissions | Doctor Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
917 | 917 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.3 | DMO-03 | Doctor app — notification permissions (push, microphone and camera handled properly) | DMO-03.01 | Permission primer + settings CTA | New | Doctor Mobile | §3 | Notification permissions | Push, microphone and camera permissions handled properly | Doctor Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
918 | 918 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.3 | DMO-03 | Doctor app — notification permissions (push, microphone and camera handled properly) | DMO-03.02 | Register FCM/APNs token (COM-03) | New | Doctor Mobile | §3 | Notification permissions | Push, microphone and camera permissions handled properly | Doctor Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
919 | 919 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.3 | DMO-03 | Doctor app — notification permissions (push, microphone and camera handled properly) | DMO-03.03 | Denied-state UX | New | Doctor Mobile | §3 | Notification permissions | Push, microphone and camera permissions handled properly | Doctor Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
920 | 920 | M18 | Doctor mobile app | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.3 | DMO-03 | Doctor app — notification permissions (push, microphone and camera handled properly) | DMO-03.04 | QA: deny each permission independently | Regression | Doctor Mobile | §3 | Notification permissions | Push, microphone and camera permissions handled properly | Doctor Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
921 | 921 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.4 | DMO-04 | Doctor app — today’s queue & schedule (the full day at a glance) | DMO-04.01 | TodayQueue screen | New | Doctor Mobile | §3 | Today’s queue & schedule | The full day at a glance | Doctor Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
922 | 922 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.4 | DMO-04 | Doctor app — today’s queue & schedule (the full day at a glance) | DMO-04.02 | Existing appointment list APIs | New | Doctor Mobile | §3 | Today’s queue & schedule | The full day at a glance | Doctor Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
923 | 923 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.4 | DMO-04 | Doctor app — today’s queue & schedule (the full day at a glance) | DMO-04.03 | Pull-to-refresh; empty Sunday | New | Doctor Mobile | §3 | Today’s queue & schedule | The full day at a glance | Doctor Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
924 | 924 | M18 | Doctor mobile app | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.4 | DMO-04 | Doctor app — today’s queue & schedule (the full day at a glance) | DMO-04.04 | QA: parity with web counts | Regression | Doctor Mobile | §3 | Today’s queue & schedule | The full day at a glance | Doctor Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
925 | 925 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.5 | DMO-05 | Doctor app — availability toggle (go online or offline, set working hours) | DMO-05.01 | Availability + hours screens | New | Doctor Mobile | §3 | Availability toggle | Go online or offline, set working hours | Doctor Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
926 | 926 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.5 | DMO-05 | Doctor app — availability toggle (go online or offline, set working hours) | DMO-05.02 | TEL-01 + APT-07 APIs (hours read/edit policy: edit hours may stay web-only if product decides — PDF says set working hours so include) | New | Doctor Mobile | §3 | Availability toggle | Go online or offline, set working hours | Doctor Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
927 | 927 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.5 | DMO-05 | Doctor app — availability toggle (go online or offline, set working hours) | DMO-05.03 | Offline banner | New | Doctor Mobile | §3 | Availability toggle | Go online or offline, set working hours | Doctor Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
928 | 928 | M18 | Doctor mobile app | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.5 | DMO-05 | Doctor app — availability toggle (go online or offline, set working hours) | DMO-05.04 | QA: web and app status match within heartbeat | Regression | Doctor Mobile | §3 | Availability toggle | Go online or offline, set working hours | Doctor Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
929 | 929 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.6 | DMO-06 | Doctor app — push notifications (waiting, booking, reschedule, cancellation, refill, payment received) | DMO-06.01 | Notification handling + deep links into queue/refill/join | New | Doctor Mobile | §3 | Push notifications | Patient waiting, new booking, reschedule, cancellation, refill request, payment received | Doctor Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
930 | 930 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.6 | DMO-06 | Doctor app — push notifications (waiting, booking, reschedule, cancellation, refill, payment received) | DMO-06.02 | Device register | New | Doctor Mobile | §3 | Push notifications | Patient waiting, new booking, reschedule, cancellation, refill request, payment received | Doctor Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
931 | 931 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.6 | DMO-06 | Doctor app — push notifications (waiting, booking, reschedule, cancellation, refill, payment received) | DMO-06.03 | Foreground in-app banner | New | Doctor Mobile | §3 | Push notifications | Patient waiting, new booking, reschedule, cancellation, refill request, payment received | Doctor Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
932 | 932 | M18 | Doctor mobile app | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.6 | DMO-06 | Doctor app — push notifications (waiting, booking, reschedule, cancellation, refill, payment received) | DMO-06.04 | QA: each event type deep link | Regression | Doctor Mobile | §3 | Push notifications | Patient waiting, new booking, reschedule, cancellation, refill request, payment received | Doctor Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
933 | 933 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.7 | DMO-07 | Doctor app — patient context card (name, age, chief complaint and last visit) — NO case-taking | DMO-07.01 | PatientCard read-only | New | Doctor Mobile | §3 | Patient context card | Name, age, chief complaint and last visit before joining | Doctor Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
934 | 934 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.7 | DMO-07 | Doctor app — patient context card (name, age, chief complaint and last visit) — NO case-taking | DMO-07.02 | Context API (name, age, CC, last visit, payment, tele) | New | Doctor Mobile | §3 | Patient context card | Name, age, chief complaint and last visit before joining | Doctor Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
935 | 935 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.7 | DMO-07 | Doctor app — patient context card (name, age, chief complaint and last visit) — NO case-taking | DMO-07.03 | Do not ship case-taking tabs | New | Doctor Mobile | §3 | Patient context card | Name, age, chief complaint and last visit before joining | Doctor Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
936 | 936 | M18 | Doctor mobile app | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.7 | DMO-07 | Doctor app — patient context card (name, age, chief complaint and last visit) — NO case-taking | DMO-07.04 | QA: repertory endpoints never called from app | Regression | Doctor Mobile | §3 | Patient context card | Name, age, chief complaint and last visit before joining | Doctor Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
937 | 937 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.8 | DMO-08 | Doctor app — join consultation (video or audio from the phone) | DMO-08.01 | VideoRoom | New | Doctor Mobile | §3 | Join consultation | Start the video or audio consultation from the phone | Doctor Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
938 | 938 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.8 | DMO-08 | Doctor app — join consultation (video or audio from the phone) | DMO-08.02 | Tele session tokens | New | Doctor Mobile | §3 | Join consultation | Start the video or audio consultation from the phone | Doctor Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
939 | 939 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.8 | DMO-08 | Doctor app — join consultation (video or audio from the phone) | DMO-08.03 | Audio-only fallback | New | Doctor Mobile | §3 | Join consultation | Start the video or audio consultation from the phone | Doctor Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
940 | 940 | M18 | Doctor mobile app | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.8 | DMO-08 | Doctor app — join consultation (video or audio from the phone) | DMO-08.04 | QA: web patient + app doctor | Regression | Doctor Mobile | §3 | Join consultation | Start the video or audio consultation from the phone | Doctor Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
941 | 941 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.9 | DMO-09 | Doctor app — refill approval (approve or reject repeat prescription requests) | DMO-09.01 | RefillInbox + RefillDetail | New | Doctor Mobile | §3 + §11 | Refill approval | Approve or reject repeat prescription requests | Doctor Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
942 | 942 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.9 | DMO-09 | Doctor app — refill approval (approve or reject repeat prescription requests) | DMO-09.02 | Approve/Reject APIs | New | Doctor Mobile | §3 + §11 | Refill approval | Approve or reject repeat prescription requests | Doctor Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
943 | 943 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.9 | DMO-09 | Doctor app — refill approval (approve or reject repeat prescription requests) | DMO-09.03 | Show codes vs names per policy (doctor sees names) | New | Doctor Mobile | §3 + §11 | Refill approval | Approve or reject repeat prescription requests | Doctor Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
944 | 944 | M18 | Doctor mobile app | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.9 | DMO-09 | Doctor app — refill approval (approve or reject repeat prescription requests) | DMO-09.04 | QA: reject reason; cannot edit snapshot | Regression | Doctor Mobile | §3 + §11 | Refill approval | Approve or reject repeat prescription requests | Doctor Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
945 | 945 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.10 | DMO-10 | Doctor app — earnings summary (today, this week, this month, with payout status) | DMO-10.01 | Earnings screens | New | Doctor Mobile | §3 + §16 | Earnings summary | Today, this week and this month, with payout status | Doctor Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
946 | 946 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.10 | DMO-10 | Doctor app — earnings summary (today, this week, this month, with payout status) | DMO-10.02 | GET Earnings/Summary | New | Doctor Mobile | §3 + §16 | Earnings summary | Today, this week and this month, with payout status | Doctor Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
947 | 947 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.10 | DMO-10 | Doctor app — earnings summary (today, this week, this month, with payout status) | DMO-10.03 | Empty first week | New | Doctor Mobile | §3 + §16 | Earnings summary | Today, this week and this month, with payout status | Doctor Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
948 | 948 | M18 | Doctor mobile app | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.10 | DMO-10 | Doctor app — earnings summary (today, this week, this month, with payout status) | DMO-10.04 | QA: matches /account figures ± rounding | Regression | Doctor Mobile | §3 + §16 | Earnings summary | Today, this week and this month, with payout status | Doctor Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
949 | 949 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.11 | DMO-11 | Doctor app — offline handling (weak connection or expired session) | DMO-11.01 | Offline/error screens | New | Doctor Mobile | §3 | Offline handling | Clear behaviour on weak connection or expired session | Doctor Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
950 | 950 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.11 | DMO-11 | Doctor app — offline handling (weak connection or expired session) | DMO-11.02 | 401 interceptor → logout API | New | Doctor Mobile | §3 | Offline handling | Clear behaviour on weak connection or expired session | Doctor Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
951 | 951 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.11 | DMO-11 | Doctor app — offline handling (weak connection or expired session) | DMO-11.03 | No silent retry of payments | New | Doctor Mobile | §3 | Offline handling | Clear behaviour on weak connection or expired session | Doctor Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
952 | 952 | M18 | Doctor mobile app | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.11 | DMO-11 | Doctor app — offline handling (weak connection or expired session) | DMO-11.04 | QA: airplane mode on join | Regression | Doctor Mobile | §3 | Offline handling | Clear behaviour on weak connection or expired session | Doctor Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
953 | 953 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.12 | DMO-12 | Doctor app — reliability monitoring (failures reported automatically) | DMO-12.01 | Integrate Crashlytics/Sentry; map to doctorId hashed | New Integration | Doctor Mobile | §3 | Reliability monitoring | Failures are reported automatically, not left to a phone call | Doctor Mobile App | Mobile | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | 2 | Not Started |  | Edit on module sheet
954 | 954 | M18 | Doctor mobile app | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.12 | DMO-12 | Doctor app — reliability monitoring (failures reported automatically) | DMO-12.02 | QA: simulated crash + join fail event | Regression | Doctor Mobile | §3 | Reliability monitoring | Failures are reported automatically, not left to a phone call | Doctor Mobile App | QA | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 1 | Not Started |  | Edit on module sheet
955 | 955 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.13 | DMO-13 | Doctor app — iOS and Android parity QA (queue, availability, notifications, context, video, refill, earnings) | DMO-13.01 | Release builds both OS | New | Doctor Mobile | §3 + §18 | Doctor mobile app iOS and Android | iOS and Android — queue, availability, notifications, patient context, video consultation, refill approval, earnings | Doctor Mobile App | Mobile | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 1 | Not Started |  | Edit on module sheet
956 | 956 | M18 | Doctor mobile app | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.13 | DMO-13 | Doctor app — iOS and Android parity QA (queue, availability, notifications, context, video, refill, earnings) | DMO-13.02 | Parity QA DMO-01..12 both OS | Regression | Doctor Mobile | §3 + §18 | Doctor mobile app iOS and Android | iOS and Android — queue, availability, notifications, patient context, video consultation, refill approval, earnings | Doctor Mobile App | QA | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 1 | Not Started |  | Edit on module sheet
957 | 957 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.1 | RPT-01 | Admin overview dashboard — platform-wide activity at a glance (replace Velzon ecommerce) | RPT-01.01 | No ecommerce tables | Existing Improvement | Reports | §16 + §7.2 | Admin overview dashboard / Admin dashboard | Platform-wide activity at a glance / Live overview of the whole platform | Admin Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
958 | 958 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.1 | RPT-01 | Admin overview dashboard — platform-wide activity at a glance (replace Velzon ecommerce) | RPT-01.02 | GET /api/AdminDashboard/Overview | Existing Improvement | Reports | §16 + §7.2 | Admin overview dashboard / Admin dashboard | Platform-wide activity at a glance / Live overview of the whole platform | Admin Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
959 | 959 | M19 | Reports, NFR & delivery gate | UI | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.1 | RPT-01 | Admin overview dashboard — platform-wide activity at a glance (replace Velzon ecommerce) | RPT-01.03 | Replace pages/Admin/Dashboard; getHomeDashboardPath → /admin/dashboard | Existing Improvement | Reports | §16 + §7.2 | Admin overview dashboard / Admin dashboard | Platform-wide activity at a glance / Live overview of the whole platform | Admin Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
960 | 960 | M19 | Reports, NFR & delivery gate | QA | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.1 | RPT-01 | Admin overview dashboard — platform-wide activity at a glance (replace Velzon ecommerce) | RPT-01.04 | QA: login as admin never shows fake store visits | Regression | Reports | §16 + §7.2 | Admin overview dashboard / Admin dashboard | Platform-wide activity at a glance / Live overview of the whole platform | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
961 | 961 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.2 | RPT-02 | Doctor practice statistics — patient and consultation trends (extend existing charts) | RPT-02.01 | No new warehouse required for v1 | Existing Improvement | Reports | §16 + §5.1 | Doctor practice statistics | Patient and consultation trends | Doctor Web | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
962 | 962 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.2 | RPT-02 | Doctor practice statistics — patient and consultation trends (extend existing charts) | RPT-02.02 | Extend GetPatientStatsCharts with VisitType/ConsultMode | Existing Improvement | Reports | §16 + §5.1 | Doctor practice statistics | Patient and consultation trends | Doctor Web | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
963 | 963 | M19 | Reports, NFR & delivery gate | UI | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.2 | RPT-02 | Doctor practice statistics — patient and consultation trends (extend existing charts) | RPT-02.03 | Dashboard charts consume new series | Existing Improvement | Reports | §16 + §5.1 | Doctor practice statistics | Patient and consultation trends | Doctor Web | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
964 | 964 | M19 | Reports, NFR & delivery gate | QA | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.2 | RPT-02 | Doctor practice statistics — patient and consultation trends (extend existing charts) | RPT-02.04 | QA: empty new clinic | Regression | Reports | §16 + §5.1 | Doctor practice statistics | Patient and consultation trends | Doctor Web | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
965 | 965 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.3 | RPT-03 | Follow-up analysis — due/overdue patients and follow-up conversion | RPT-03.01 | Queries on VisitType + FollowUpTask | New | Reports | §16 | Follow-up analysis | Which patients are due or overdue for follow-up, and follow-up conversion | Doctor Web | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
966 | 966 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.3 | RPT-03 | Follow-up analysis — due/overdue patients and follow-up conversion | RPT-03.02 | GET FollowUpDue, FollowUpSummary | New | Reports | §16 | Follow-up analysis | Which patients are due or overdue for follow-up, and follow-up conversion | Doctor Web | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
967 | 967 | M19 | Reports, NFR & delivery gate | UI | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.3 | RPT-03 | Follow-up analysis — due/overdue patients and follow-up conversion | RPT-03.03 | /doctor/follow-up-analysis | New | Reports | §16 | Follow-up analysis | Which patients are due or overdue for follow-up, and follow-up conversion | Doctor Web | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
968 | 968 | M19 | Reports, NFR & delivery gate | QA | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.3 | RPT-03 | Follow-up analysis — due/overdue patients and follow-up conversion | RPT-03.04 | QA: overdue vs due buckets | Regression | Reports | §16 | Follow-up analysis | Which patients are due or overdue for follow-up, and follow-up conversion | Doctor Web | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
969 | 969 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.4 | RPT-04 | Clinic performance analysis — appointments, slot utilisation, no-shows, cancellations, waiting time and revenue | RPT-04.01 | Aggregate APIs beyond GetPatientStatsCharts | New | Reports | §16 | Clinic performance analysis | Appointments, slot utilisation, no-shows, cancellations, waiting time and revenue | Doctor Web | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
970 | 970 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.4 | RPT-04 | Clinic performance analysis — appointments, slot utilisation, no-shows, cancellations, waiting time and revenue | RPT-04.02 | GET ClinicPerformance | New | Reports | §16 | Clinic performance analysis | Appointments, slot utilisation, no-shows, cancellations, waiting time and revenue | Doctor Web | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
971 | 971 | M19 | Reports, NFR & delivery gate | UI | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.4 | RPT-04 | Clinic performance analysis — appointments, slot utilisation, no-shows, cancellations, waiting time and revenue | RPT-04.03 | /doctor/clinic-performance | New | Reports | §16 | Clinic performance analysis | Appointments, slot utilisation, no-shows, cancellations, waiting time and revenue | Doctor Web | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
972 | 972 | M19 | Reports, NFR & delivery gate | QA | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.4 | RPT-04 | Clinic performance analysis — appointments, slot utilisation, no-shows, cancellations, waiting time and revenue | RPT-04.04 | QA: cancelled excluded from completed; revenue uses ledger not client | Regression | Reports | §16 | Clinic performance analysis | Appointments, slot utilisation, no-shows, cancellations, waiting time and revenue | Doctor Web | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
973 | 973 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.5 | RPT-05 | Payment reconciliation report — bookings matched against payments | RPT-05.01 | CSV/PDF export of FIN-02 query | New | Reports | §16 + §7.2 | Payment reconciliation report / Consult booking & payment reconciliation | Bookings matched against payments / Match every booking against every payment | Admin + Account | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
974 | 974 | M19 | Reports, NFR & delivery gate | UI | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.5 | RPT-05 | Payment reconciliation report — bookings matched against payments | RPT-05.02 | Report UI on admin/account recon screens | New | Reports | §16 + §7.2 | Payment reconciliation report / Consult booking & payment reconciliation | Bookings matched against payments / Match every booking against every payment | Admin + Account | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
975 | 975 | M19 | Reports, NFR & delivery gate | QA | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.5 | RPT-05 | Payment reconciliation report — bookings matched against payments | RPT-05.03 | QA: unmatched rows included | Regression | Reports | §16 + §7.2 | Payment reconciliation report / Consult booking & payment reconciliation | Bookings matched against payments / Match every booking against every payment | Admin + Account | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
976 | 976 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.6 | RPT-06 | Settlement & payout reports — amounts due and paid to doctors and pharmacies | RPT-06.01 | Export settlement runs + payout register | New | Reports | §16 + §8 | Settlement & payout reports | Amounts due and paid to doctors and pharmacies | Account | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
977 | 977 | M19 | Reports, NFR & delivery gate | UI | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.6 | RPT-06 | Settlement & payout reports — amounts due and paid to doctors and pharmacies | RPT-06.02 | Report UI | New | Reports | §16 + §8 | Settlement & payout reports | Amounts due and paid to doctors and pharmacies | Account | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
978 | 978 | M19 | Reports, NFR & delivery gate | QA | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.6 | RPT-06 | Settlement & payout reports — amounts due and paid to doctors and pharmacies | RPT-06.03 | QA: pharmacy lines appear only after HomeoMeds | Regression | Reports | §16 + §8 | Settlement & payout reports | Amounts due and paid to doctors and pharmacies | Account | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
979 | 979 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.7 | RPT-07 | GST & invoice reports (reporting surface of FIN-08) | RPT-07.01 | Confirm CA format; implement export if not already in FIN-08 | New | Reports | §16 + §8 | GST & invoice reports | Tax reporting | Account | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
980 | 980 | M19 | Reports, NFR & delivery gate | QA | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.7 | RPT-07 | GST & invoice reports (reporting surface of FIN-08) | RPT-07.02 | QA: number series gaps flagged | Regression | Reports | §16 + §8 | GST & invoice reports | Tax reporting | Account | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
981 | 981 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.8 | RPT-08 | Doctor earnings summary — daily, weekly and monthly earnings with payout status (web + same API as DMO-10) | RPT-08.01 | Reuse earnings API | New | Reports | §16 + §3 | Doctor earnings summary | Daily, weekly and monthly earnings with payout status | Doctor Web + App | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
982 | 982 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.8 | RPT-08 | Doctor earnings summary — daily, weekly and monthly earnings with payout status (web + same API as DMO-10) | RPT-08.02 | GET Earnings/Summary already for app — add if missing date buckets | New | Reports | §16 + §3 | Doctor earnings summary | Daily, weekly and monthly earnings with payout status | Doctor Web + App | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
983 | 983 | M19 | Reports, NFR & delivery gate | UI | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.8 | RPT-08 | Doctor earnings summary — daily, weekly and monthly earnings with payout status (web + same API as DMO-10) | RPT-08.03 | /doctor/earnings | New | Reports | §16 + §3 | Doctor earnings summary | Daily, weekly and monthly earnings with payout status | Doctor Web + App | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
984 | 984 | M19 | Reports, NFR & delivery gate | QA | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.8 | RPT-08 | Doctor earnings summary — daily, weekly and monthly earnings with payout status (web + same API as DMO-10) | RPT-08.04 | QA: payout pending vs paid | Regression | Reports | §16 + §3 | Doctor earnings summary | Daily, weekly and monthly earnings with payout status | Doctor Web + App | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
985 | 985 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.9 | RPT-09 | Medicine order reports — order volumes, fulfilment and exceptions | RPT-09.01 | Aggregates on MedicineOrder | New | Reports | §16 + §12 | Medicine order reports | Order volumes, fulfilment and exceptions | Admin + Account | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
986 | 986 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.9 | RPT-09 | Medicine order reports — order volumes, fulfilment and exceptions | RPT-09.02 | GET medicine order report | New | Reports | §16 + §12 | Medicine order reports | Order volumes, fulfilment and exceptions | Admin + Account | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
987 | 987 | M19 | Reports, NFR & delivery gate | UI | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.9 | RPT-09 | Medicine order reports — order volumes, fulfilment and exceptions | RPT-09.03 | Admin/account report page | New | Reports | §16 + §12 | Medicine order reports | Order volumes, fulfilment and exceptions | Admin + Account | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
988 | 988 | M19 | Reports, NFR & delivery gate | QA | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.9 | RPT-09 | Medicine order reports — order volumes, fulfilment and exceptions | RPT-09.04 | QA: cancelled orders not counted as delivered | Regression | Reports | §16 + §12 | Medicine order reports | Order volumes, fulfilment and exceptions | Admin + Account | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
989 | 989 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.10 | RPT-10 | Platform users remaining 20% — import, export and activation control | RPT-10.01 | VerificationStatus on user/doctor list DTO | Existing Improvement | Admin | §7.2 | Platform users | Manage all users with import, export and activation control | Admin Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
990 | 990 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.10 | RPT-10 | Platform users remaining 20% — import, export and activation control | RPT-10.02 | User import/export APIs if missing | Existing Improvement | Admin | §7.2 | Platform users | Manage all users with import, export and activation control | Admin Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
991 | 991 | M19 | Reports, NFR & delivery gate | UI | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.10 | RPT-10 | Platform users remaining 20% — import, export and activation control | RPT-10.03 | ListUser.js wire dead buttons; verification column | Existing Improvement | Admin | §7.2 | Platform users | Manage all users with import, export and activation control | Admin Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
992 | 992 | M19 | Reports, NFR & delivery gate | QA | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.10 | RPT-10 | Platform users remaining 20% — import, export and activation control | RPT-10.04 | QA: export contains only permitted fields | Regression | Admin | §7.2 | Platform users | Manage all users with import, export and activation control | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
993 | 993 | M19 | Reports, NFR & delivery gate | QA | 19 | Phase 19 — Cross-surface QA, NFR, delivery summary gate (PDF §1 + §18) | 19.1 | QA-01 | One ecosystem proof — patient, appointment, prescription and payment created anywhere are visible everywhere | QA-01.01 | E2E: Reception creates patient+appt → Doctor board → sign eRx → Patient app sees codes → Pharmacy accept OTP → patient sees names+pay → Account ledger S2 and S5 | Regression | QA | §1 + §18 | One connected ecosystem | A patient, an appointment, a prescription and a payment created anywhere in the system are visible everywhere else | All | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
994 | 994 | M19 | Reports, NFR & delivery gate | QA | 19 | Phase 19 — Cross-surface QA, NFR, delivery summary gate (PDF §1 + §18) | 19.1 | QA-01 | One ecosystem proof — patient, appointment, prescription and payment created anywhere are visible everywhere | QA-01.02 | E2E: Patient app books+pays tele → doctor app join → summary+eRx → refill on doctor app | Regression | QA | §1 + §18 | One connected ecosystem | A patient, an appointment, a prescription and a payment created anywhere in the system are visible everywhere else | All | QA | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 1 | Not Started |  | Edit on module sheet
995 | 995 | M19 | Reports, NFR & delivery gate | QA | 19 | Phase 19 — Cross-surface QA, NFR, delivery summary gate (PDF §1 + §18) | 19.1 | QA-01 | One ecosystem proof — patient, appointment, prescription and payment created anywhere are visible everywhere | QA-01.03 | Negative: Admin cannot payout; Account cannot edit repertory | Regression | QA | §1 + §18 | One connected ecosystem | A patient, an appointment, a prescription and a payment created anywhere in the system are visible everywhere else | All | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
996 | 996 | M19 | Reports, NFR & delivery gate | QA | 19 | Phase 19 — Cross-surface QA, NFR, delivery summary gate (PDF §1 + §18) | 19.2 | QA-02 | Delivery summary gate — every area in PDF §18 signed off | QA-02.01 | Traceability review: 01_PDF_Coverage every row has Main Task ID and final Status | Regression | QA | §18 | Summary of delivery | All features listed in this document are included in the delivery scope. | Programme | QA | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 0 | N/A |  | Edit on module sheet
997 | 997 | M19 | Reports, NFR & delivery gate | QA | 19 | Phase 19 — Cross-surface QA, NFR, delivery summary gate (PDF §1 + §18) | 19.2 | QA-02 | Delivery summary gate — every area in PDF §18 signed off | QA-02.02 | Do not ship Velzon demo tickets/KYC/ecommerce as product | Regression | QA | §18 | Summary of delivery | All features listed in this document are included in the delivery scope. | Programme | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
998 | 998 | M19 | Reports, NFR & delivery gate | Web | 19 | Phase 19 — Cross-surface QA, NFR, delivery summary gate (PDF §1 + §18) | 19.3 | NFR-01 | NFR — performance, low-data, reliability, secrets, dual-API freeze | NFR-01.01 | Rotate API secrets; keys in config/KeyVault; directory browsing remains off | Existing Modification | NFR | §2.9 + §3 + §17 | Low-data mode / Reliability monitoring / Secure login | Works on slow connections; failures reported automatically; credentials protected | All | Security | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
999 | 999 | M19 | Reports, NFR & delivery gate | QA | 19 | Phase 19 — Cross-surface QA, NFR, delivery summary gate (PDF §1 + §18) | 19.3 | NFR-01 | NFR — performance, low-data, reliability, secrets, dual-API freeze | NFR-01.02 | Performance: slot lock under concurrent public booking | Regression | NFR | §2.9 + §3 + §17 | Low-data mode / Reliability monitoring / Secure login | Works on slow connections; failures reported automatically; credentials protected | All | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
1000 | 1000 | M19 | Reports, NFR & delivery gate | QA | 19 | Phase 19 — Cross-surface QA, NFR, delivery summary gate (PDF §1 + §18) | 19.3 | NFR-01 | NFR — performance, low-data, reliability, secrets, dual-API freeze | NFR-01.03 | Patient low-data mode QA on 2G profile | Regression | NFR | §2.9 + §3 + §17 | Low-data mode / Reliability monitoring / Secure login | Works on slow connections; failures reported automatically; credentials protected | All | QA | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 1 | Not Started |  | Edit on module sheet

## 02_By_Module_Phase
ALL 1000 ROWS by module then phase. Live from module sheets. Filter Dev Module Code. To change Status or Assigned, use Open Module Sheet (do not type over formulas).
Module Seq | Original Seq | Dev Module Code | Dev Module | Track | Phase | Phase Name | WBS | Main Task ID | Main Task | Sub Task ID | Sub Task | Work Type | Source Module / Area | PDF Section | PDF Feature (exact wording) | PDF Delivery Text | Application Surface | Layer | Assigned To (lead) | Frontend | Frontend Status | Frontend Assigned | Backend | Backend Status | Backend Assigned | Database | Database Status | Database Assigned | API | API Status | API Assigned | Mobile | Mobile Status | Mobile Assigned | Integration | Integration Status | Integration Assigned | Layers Remaining | Overall Status | Notes | Open Module Sheet
1 | 1 | M00 | PRE — Client gates | Web | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.1 | PRE-01 | Decide settlement model — Homeocentrum holds all money (food-delivery / quick-commerce pattern) | PRE-01.01 | Workshop with finance: confirm Homeocentrum is single merchant of record for consult + medicine + subscription | Client Decision | Finance | §9 + §8 | Every transaction passes through Homeocentrum | Built on the principle: every transaction passes through Homeocentrum, in the same way a food-delivery or quick-commerce platform holds all payments centrally. | Account / Gateway | Decision | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 0 | N/A |  | Edit on module sheet
2 | 2 | M00 | PRE — Client gates | Web | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.1 | PRE-01 | Decide settlement model — Homeocentrum holds all money (food-delivery / quick-commerce pattern) | PRE-01.02 | Choose v1 payout mechanic: Homeocentrum-held + NEFT/IMPS vs Razorpay Route / linked accounts | Client Decision | Finance | §9 + §8 | Every transaction passes through Homeocentrum | Built on the principle: every transaction passes through Homeocentrum, in the same way a food-delivery or quick-commerce platform holds all payments centrally. | Account / Gateway | Decision | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | 1 | Not Started |  | Edit on module sheet
3 | 3 | M00 | PRE — Client gates | Web | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.1 | PRE-01 | Decide settlement model — Homeocentrum holds all money (food-delivery / quick-commerce pattern) | PRE-01.03 | Record decision in config (SettlementModel) — engineering must not hardcode a split model | Configuration | Finance | §9 + §8 | Every transaction passes through Homeocentrum | Built on the principle: every transaction passes through Homeocentrum, in the same way a food-delivery or quick-commerce platform holds all payments centrally. | Account / Gateway | Configuration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
4 | 4 | M00 | PRE — Client gates | Web | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.2 | PRE-02 | Decide reception cash policy — clinic retains vs remits to Homeocentrum | PRE-02.01 | OQ: cash collected at reception retained by clinic or remitted to Homeocentrum? | Client Decision | Finance / Reception | §9 | Reception payment collection | Cash, UPI, card or payment link with printed receipt | Account / Reception | Decision | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 0 | N/A |  | Edit on module sheet
5 | 5 | M00 | PRE — Client gates | Web | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.2 | PRE-02 | Decide reception cash policy — clinic retains vs remits to Homeocentrum | PRE-02.02 | Document GST treatment on consult fee, platform fee, and medicine (on which amount, which GSTIN) | Client Decision | Finance / Reception | §9 | Reception payment collection | Cash, UPI, card or payment link with printed receipt | Account / Reception | Decision | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 0 | N/A |  | Edit on module sheet
6 | 6 | M00 | PRE — Client gates | Web | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.2 | PRE-02 | Decide reception cash policy — clinic retains vs remits to Homeocentrum | PRE-02.03 | Confirm commission %, settlement hold T+N days, invoice numbering series — configuration not code | Configuration | Finance / Reception | §9 | Reception payment collection | Cash, UPI, card or payment link with printed receipt | Account / Reception | Configuration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
7 | 7 | M00 | PRE — Client gates | Web | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.3 | PRE-03 | Vendor and legal gates — video SDK, SMS, WhatsApp, push, DPDP copy | PRE-03.01 | Select in-browser + mobile video vendor (Agora / Twilio / Daily / WebRTC self-host) — required for §10 | Client Decision | Platform | §10 + §14 + §17 | Telemedicine + notifications + consent | Video consultation; SMS/WhatsApp/Push/Email; consent records | Shared | Decision | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | 1 | Not Started |  | Edit on module sheet
8 | 8 | M00 | PRE — Client gates | Web | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.3 | PRE-03 | Vendor and legal gates — video SDK, SMS, WhatsApp, push, DPDP copy | PRE-03.02 | Select SMS provider (MSG91 / Twilio / etc.) and confirm DLT templates for appointment/OTP/cancel | Client Decision | Platform | §10 + §14 + §17 | Telemedicine + notifications + consent | Video consultation; SMS/WhatsApp/Push/Email; consent records | Shared | Decision | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | 1 | Not Started |  | Edit on module sheet
9 | 9 | M00 | PRE — Client gates | Web | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.3 | PRE-03 | Vendor and legal gates — video SDK, SMS, WhatsApp, push, DPDP copy | PRE-03.03 | Legal: privacy (data protection, recording, pharmacy consent) and terms (payments, refunds, telemedicine, medicine orders) drafted for §4 + §17 | Client Decision | Platform | §10 + §14 + §17 | Telemedicine + notifications + consent | Video consultation; SMS/WhatsApp/Push/Email; consent records | Shared | Legal | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 0 | N/A |  | Edit on module sheet
10 | 10 | M00 | PRE — Client gates | Web | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.3 | PRE-03 | Vendor and legal gates — video SDK, SMS, WhatsApp, push, DPDP copy | PRE-03.04 | OQ: unpaid-booking slot hold duration vs release immediately if patient does not pay | Client Decision | Platform | §10 + §14 + §17 | Telemedicine + notifications + consent | Video consultation; SMS/WhatsApp/Push/Email; consent records | Shared | Decision | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 0 | N/A |  | Edit on module sheet
11 | 11 | M00 | PRE — Client gates | Web | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.3 | PRE-03 | Vendor and legal gates — video SDK, SMS, WhatsApp, push, DPDP copy | PRE-03.05 | OQ: live-doctor credentialing backfill — auto-Approve existing doctors? Unverified doctors visible only to own clinic? | Client Decision | Platform | §10 + §14 + §17 | Telemedicine + notifications + consent | Video consultation; SMS/WhatsApp/Push/Email; consent records | Shared | Decision | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 0 | N/A |  | Edit on module sheet
12 | 12 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.1 | FND-01 | One connected ecosystem — shared keys so a patient, appointment, prescription and payment created anywhere are visible everywhere | FND-01.01 | Publish shared-key design (DoctorId, PatientId, PatientAppId, CaseId, ErxId, LedgerTxnId, MedicineOrderId) and event list (created/rescheduled/cancelled/paid/signed/accepted) | New | Platform | §1 | One connected ecosystem serving six types of users | A patient, an appointment, a prescription and a payment created anywhere in the system are visible everywhere else — there are no separate systems to reconcile. | Shared | Architecture | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
13 | 13 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.1 | FND-01 | One connected ecosystem — shared keys so a patient, appointment, prescription and payment created anywhere are visible everywhere | FND-01.02 | Add role enum values Patient, Account, PharmacyPartner alongside existing Admin/Doctor/Reception (keep unused Management/Supervisor/Inspector unused) | New | Platform | §1 | One connected ecosystem serving six types of users | A patient, an appointment, a prescription and a payment created anywhere in the system are visible everywhere else — there are no separate systems to reconcile. | Shared | Database + Auth | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
14 | 14 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.1 | FND-01 | One connected ecosystem — shared keys so a patient, appointment, prescription and payment created anywhere are visible everywhere | FND-01.03 | All new domain modules on NigaHomeopathy-API (.NET 8); do not create a third API; classic API only where login/Rx-write/Razorpay already live until ported | Existing Modification | Platform | §1 | One connected ecosystem serving six types of users | A patient, an appointment, a prescription and a payment created anywhere in the system are visible everywhere else — there are no separate systems to reconcile. | Shared | Architecture | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
15 | 15 | M01 | Foundation & Security | QA | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.1 | FND-01 | One connected ecosystem — shared keys so a patient, appointment, prescription and payment created anywhere are visible everywhere | FND-01.04 | QA: create appointment on Reception → visible on Doctor web; pay on Patient web → same PaymentStatus on Doctor and Account (after Phase 6) | Regression | Platform | §1 | One connected ecosystem serving six types of users | A patient, an appointment, a prescription and a payment created anywhere in the system are visible everywhere else — there are no separate systems to reconcile. | Shared | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
16 | 16 | M01 | Foundation & Security | UI | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.2 | FND-02 | Delivery footprint — 2 mobile apps · 5 web portals · payment · telemedicine · digital prescription · HomeoMeds (programme skeleton) | FND-02.01 | Web: add Account layout + home redirect; Pharmacy layout stub; do not build screens yet | New | Platform | §1 | Delivery covers | 2 mobile applications · 5 web portals · payment system · telemedicine · digital prescription · online medicine delivery. | Shared | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
17 | 17 | M01 | Foundation & Security | UI | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.2 | FND-02 | Delivery footprint — 2 mobile apps · 5 web portals · payment · telemedicine · digital prescription · HomeoMeds (programme skeleton) | FND-02.02 | Extend roles.js and AuthProtected with per-route ACL skeleton (deny-by-default for new routes) | Existing Improvement | Platform | §1 | Delivery covers | 2 mobile applications · 5 web portals · payment system · telemedicine · digital prescription · online medicine delivery. | Shared | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
18 | 18 | M01 | Foundation & Security | Mobile | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.2 | FND-02 | Delivery footprint — 2 mobile apps · 5 web portals · payment · telemedicine · digital prescription · HomeoMeds (programme skeleton) | FND-02.03 | Mobile: create Patient app and Doctor app repository/bootstrap (React Native or agreed stack) — empty shells only | New | Platform | §1 | Delivery covers | 2 mobile applications · 5 web portals · payment system · telemedicine · digital prescription · online medicine delivery. | Shared | Mobile | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 1 | Not Started |  | Edit on module sheet
19 | 19 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.2 | FND-02 | Delivery footprint — 2 mobile apps · 5 web portals · payment · telemedicine · digital prescription · HomeoMeds (programme skeleton) | FND-02.04 | Document the five portals: Patient Website, Doctor Web Portal, Reception Portal, Admin Portal, Account Department (Pharmacy console is HomeoMeds, not a 6th portal in the PDF count) | New | Platform | §1 | Delivery covers | 2 mobile applications · 5 web portals · payment system · telemedicine · digital prescription · online medicine delivery. | Shared | Architecture | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 0 | N/A |  | Edit on module sheet
20 | 20 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.3 | SEC-01 | Secure login — protected credentials for every user type | SEC-01.01 | DB/Migration: hash existing UserMaster passwords (bcrypt/PBKDF2); never store new plaintext | Data Migration | Security | §17 | Secure login | Protected credentials for every user type | All web + later mobile | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
21 | 21 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.3 | SEC-01 | Secure login — protected credentials for every user type | SEC-01.02 | API: Login verifies hash; embed Role + DoctorId claims; keep classic login URL until .NET 8 login is cut over | Existing Modification | Security | §17 | Secure login | Protected credentials for every user type | All web + later mobile | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
22 | 22 | M01 | Foundation & Security | UI | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.3 | SEC-01 | Secure login — protected credentials for every user type | SEC-01.03 | UI: remove fakeBackend() from App.js production path; login still Formik/Yup | Existing Modification | Security | §17 | Secure login | Protected credentials for every user type | All web + later mobile | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
23 | 23 | M01 | Foundation & Security | QA | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.3 | SEC-01 | Secure login — protected credentials for every user type | SEC-01.04 | QA: Admin, Doctor, Reception login; invalid password; deactivated user; SQL injection/brute-force rate limit | Regression | Security | §17 | Secure login | Protected credentials for every user type | All web + later mobile | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
24 | 24 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.4 | SEC-02 | Secure password reset — time-limited reset links (stop plaintext email + fake thunk) | SEC-02.01 | DB: PasswordResetToken (UserId, TokenHash, ExpiresAt, UsedAt) | New | Security | §17 | Secure password reset | Time-limited reset links | Admin / Doctor / Reception web | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
25 | 25 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.4 | SEC-02 | Secure password reset — time-limited reset links (stop plaintext email + fake thunk) | SEC-02.02 | API: ForgotPassword sends reset link; ResetPassword consumes token; stop emailing plaintext; ChangePassword for authenticated user | Existing Modification | Security | §17 | Secure password reset | Time-limited reset links | Admin / Doctor / Reception web | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
26 | 26 | M01 | Foundation & Security | UI | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.4 | SEC-02 | Secure password reset — time-limited reset links (stop plaintext email + fake thunk) | SEC-02.03 | UI: replace slices/auth/forgetpwd fake/Firebase with real APIs; /reset-password/:token success/expiry states | Existing Improvement | Security | §17 | Secure password reset | Time-limited reset links | Admin / Doctor / Reception web | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
27 | 27 | M01 | Foundation & Security | QA | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.4 | SEC-02 | Secure password reset — time-limited reset links (stop plaintext email + fake thunk) | SEC-02.04 | QA: expired token, reused token, unknown email (no user enumeration), logged-in change password | Regression | Security | §17 | Secure password reset | Time-limited reset links | Admin / Doctor / Reception web | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
28 | 28 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.5 | SEC-03 | Session control — proper sign-out across web and mobile | SEC-03.01 | API: POST /Account/Logout; persist UserLoginStatus; optional denylist until token expiry | Existing Improvement | Security | §17 | Session control | Proper sign-out across web and mobile | All | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
29 | 29 | M01 | Foundation & Security | UI | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.5 | SEC-03 | Session control — proper sign-out across web and mobile | SEC-03.02 | Web: Logout.js calls API then clears authUser + patient-board session (keep existing board clear) | Existing Improvement | Security | §17 | Session control | Proper sign-out across web and mobile | All | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
30 | 30 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.5 | SEC-03 | Session control — proper sign-out across web and mobile | SEC-03.03 | Contract: mobile apps MUST use the same Logout endpoint (implemented in Phases 16–17) | New | Security | §17 | Session control | Proper sign-out across web and mobile | All | API contract | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
31 | 31 | M01 | Foundation & Security | QA | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.5 | SEC-03 | Session control — proper sign-out across web and mobile | SEC-03.04 | QA: logout on one tab; expired session message; 401 interceptor | Regression | Security | §17 | Session control | Proper sign-out across web and mobile | All | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
32 | 32 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.6 | SEC-04 | Role-based access — each role sees only what it is permitted to see | SEC-04.01 | Backend: restore GetMenuByRole; add role attributes on new money and PII APIs | Existing Improvement | Security | §17 | Role-based access | Each role sees only what it is permitted to see | Admin / All web | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
33 | 33 | M01 | Foundation & Security | UI | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.6 | SEC-04 | Role-based access — each role sees only what it is permitted to see | SEC-04.02 | Frontend: hide routes the role cannot view; keep Velzon demo routes out of production menus | Existing Improvement | Security | §17 | Role-based access | Each role sees only what it is permitted to see | Admin / All web | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
34 | 34 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.6 | SEC-04 | Role-based access — each role sees only what it is permitted to see | SEC-04.03 | Separation of duties seed: Account role controls money; Admin controls platform and clinical data — neither can perform the other’s role (PDF §8) | New | Security | §17 | Role-based access | Each role sees only what it is permitted to see | Admin / All web | Configuration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
35 | 35 | M01 | Foundation & Security | QA | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.6 | SEC-04 | Role-based access — each role sees only what it is permitted to see | SEC-04.04 | QA: Reception cannot open repertory masters; Account cannot edit diagnosis; Doctor cannot see platform-wide ledger | Regression | Security | §17 | Role-based access | Each role sees only what it is permitted to see | Admin / All web | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
36 | 36 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.7 | SEC-05 | Patient data protection — health records restricted to the treating doctor and the patient | SEC-05.01 | API: enforce DoctorId ownership on Patient, Appointment, Case, Rx, notes, labs, board backup | Existing Improvement | Security | §17 | Patient data protection | Health records restricted to the treating doctor and the patient | API | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
37 | 37 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.7 | SEC-05 | Patient data protection — health records restricted to the treating doctor and the patient | SEC-05.02 | Disable directory browsing on /attachments and /Blogs; signed-URL or authorised download for documents | Existing Modification | Security | §17 | Patient data protection | Health records restricted to the treating doctor and the patient | API | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
38 | 38 | M01 | Foundation & Security | QA | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.7 | SEC-05 | Patient data protection — health records restricted to the treating doctor and the patient | SEC-05.03 | QA: IDOR tests (swap PatientAppId / CaseId in requests) | Regression | Security | §17 | Patient data protection | Health records restricted to the treating doctor and the patient | API | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
39 | 39 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.8 | SEC-06 | Consent records infrastructure — every consent captured, stored and reviewable | SEC-06.01 | DB: ConsentRecord + ConsentType master (Privacy, Booking, TeleRecording, PharmacyShare, Marketing, Caregiver) | New | Security / Trust | §17 | Consent records | Every consent captured, stored and reviewable | Shared | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
40 | 40 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.8 | SEC-06 | Consent records infrastructure — every consent captured, stored and reviewable | SEC-06.02 | API: Grant / Withdraw / List-mine / Admin-audit (no clinical content in the API response beyond type+time) | New | Security / Trust | §17 | Consent records | Every consent captured, stored and reviewable | Shared | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
41 | 41 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.8 | SEC-06 | Consent records infrastructure — every consent captured, stored and reviewable | SEC-06.03 | Reuse AudioCaseConsentLog pattern; do not fork a second consent model for telemedicine (Phase 11 will write TeleRecording into ConsentRecord) | Existing Improvement | Security / Trust | §17 | Consent records | Every consent captured, stored and reviewable | Shared | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
42 | 42 | M01 | Foundation & Security | QA | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.8 | SEC-06 | Consent records infrastructure — every consent captured, stored and reviewable | SEC-06.04 | QA: grant, withdraw, re-grant; audit log immutable | Regression | Security / Trust | §17 | Consent records | Every consent captured, stored and reviewable | Shared | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
43 | 43 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.9 | SEC-07 | OTP verification infrastructure — applied to sensitive actions including payouts and pharmacy acceptance | SEC-07.01 | DB: OtpChallenge, OtpAuditLog (Action, EntityType, EntityId, ToMasked, Success, At) | New | Security | §17 + §8 + §12 | OTP verification | Applied to sensitive actions including payouts and pharmacy acceptance | Shared | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
44 | 44 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.9 | SEC-07 | OTP verification infrastructure — applied to sensitive actions including payouts and pharmacy acceptance | SEC-07.02 | API: RequestOtp / VerifyOtp (generic); rate-limit; lockout; SMS provider adapter stub until PRE-03 vendor is live | New | Security | §17 + §8 + §12 | OTP verification | Applied to sensitive actions including payouts and pharmacy acceptance | Shared | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
45 | 45 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.9 | SEC-07 | OTP verification infrastructure — applied to sensitive actions including payouts and pharmacy acceptance | SEC-07.03 | GET /api/Otp/Audit for Account and Admin (masked destination) | New | Security | §17 + §8 + §12 | OTP verification | Applied to sensitive actions including payouts and pharmacy acceptance | Shared | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
46 | 46 | M01 | Foundation & Security | QA | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.9 | SEC-07 | OTP verification infrastructure — applied to sensitive actions including payouts and pharmacy acceptance | SEC-07.04 | QA: replay OTP, expiry, max attempts, audit completeness | Regression | Security | §17 + §8 + §12 | OTP verification | Applied to sensitive actions including payouts and pharmacy acceptance | Shared | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
47 | 47 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.10 | SEC-08 | Complete audit trail — who did what and when across payments, prescriptions and approvals | SEC-08.01 | DB: AuditEvent (ActorUserId, Role, Action, Entity, OldJson, NewJson, At, CorrelationId) | New | Security | §17 + §9 | Complete audit trail | Who did what, and when, across payments, prescriptions and approvals / Every transaction traceable end to end by Homeocentrum | Shared | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
48 | 48 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.10 | SEC-08 | Complete audit trail — who did what and when across payments, prescriptions and approvals | SEC-08.02 | API middleware: write audit on mutating money/Rx/approval endpoints (start with a helper used by later phases) | New | Security | §17 + §9 | Complete audit trail | Who did what, and when, across payments, prescriptions and approvals / Every transaction traceable end to end by Homeocentrum | Shared | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
49 | 49 | M01 | Foundation & Security | QA | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.10 | SEC-08 | Complete audit trail — who did what and when across payments, prescriptions and approvals | SEC-08.03 | QA: sample sign-prescription / approve-payout (when those exist) produce audit rows | Regression | Security | §17 + §9 | Complete audit trail | Who did what, and when, across payments, prescriptions and approvals / Every transaction traceable end to end by Homeocentrum | Shared | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
50 | 50 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.11 | SEC-09 | Secure documents — prescriptions, reports and uploads protected from unauthorised access | SEC-09.01 | DB: SecureDocument (OwnerType, OwnerId, BlobPath, Mime, Hash, CreatedBy) | New | Security | §17 | Secure documents | Prescriptions, reports and uploads protected from unauthorised access | Shared | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
51 | 51 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.11 | SEC-09 | Secure documents — prescriptions, reports and uploads protected from unauthorised access | SEC-09.02 | API: upload (multipart) + authorised GET; no public folder listing | New | Security | §17 | Secure documents | Prescriptions, reports and uploads protected from unauthorised access | Shared | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
52 | 52 | M01 | Foundation & Security | QA | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.11 | SEC-09 | Secure documents — prescriptions, reports and uploads protected from unauthorised access | SEC-09.03 | QA: doctor of record can download; other doctor 403; anonymous 401 | Regression | Security | §17 | Secure documents | Prescriptions, reports and uploads protected from unauthorised access | Shared | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
53 | 53 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.1 | ADM-R01 | Keep and harden Admin Repertory sections (do not rebuild) | ADM-R01.01 | Regression: list / add / edit / (import-export if present) for Repertory sections | Existing | Repertory | §7.1 | Repertory sections | Manage repertory sections | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
54 | 54 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.1 | ADM-R01 | Keep and harden Admin Repertory sections (do not rebuild) | ADM-R01.02 | ACL: only Admin (and permitted roles) can mutate Repertory sections; Doctor is read-only consumer on Patient Board | Existing Improvement | Repertory | §7.1 | Repertory sections | Manage repertory sections | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
55 | 55 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.1 | ADM-R01 | Keep and harden Admin Repertory sections (do not rebuild) | ADM-R01.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Repertory sections; do not silently switch | Existing | Repertory | §7.1 | Repertory sections | Manage repertory sections | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
56 | 56 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.2 | ADM-R02 | Keep and harden Admin Subsection & rubric tree (do not rebuild) | ADM-R02.01 | Regression: list / add / edit / (import-export if present) for Subsection & rubric tree | Existing | Repertory | §7.1 | Subsection & rubric tree | Manage the full rubric hierarchy | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
57 | 57 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.2 | ADM-R02 | Keep and harden Admin Subsection & rubric tree (do not rebuild) | ADM-R02.02 | ACL: only Admin (and permitted roles) can mutate Subsection & rubric tree; Doctor is read-only consumer on Patient Board | Existing Improvement | Repertory | §7.1 | Subsection & rubric tree | Manage the full rubric hierarchy | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
58 | 58 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.2 | ADM-R02 | Keep and harden Admin Subsection & rubric tree (do not rebuild) | ADM-R02.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Subsection & rubric tree; do not silently switch | Existing | Repertory | §7.1 | Subsection & rubric tree | Manage the full rubric hierarchy | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
59 | 59 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.3 | ADM-R03 | Keep and harden Admin Rubric–remedy mapping (do not rebuild) | ADM-R03.01 | Regression: list / add / edit / (import-export if present) for Rubric–remedy mapping | Existing | Repertory | §7.1 | Rubric–remedy mapping | Map remedies to rubrics with author and grade | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
60 | 60 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.3 | ADM-R03 | Keep and harden Admin Rubric–remedy mapping (do not rebuild) | ADM-R03.02 | ACL: only Admin (and permitted roles) can mutate Rubric–remedy mapping; Doctor is read-only consumer on Patient Board | Existing Improvement | Repertory | §7.1 | Rubric–remedy mapping | Map remedies to rubrics with author and grade | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
61 | 61 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.3 | ADM-R03 | Keep and harden Admin Rubric–remedy mapping (do not rebuild) | ADM-R03.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Rubric–remedy mapping; do not silently switch | Existing | Repertory | §7.1 | Rubric–remedy mapping | Map remedies to rubrics with author and grade | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
62 | 62 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.4 | ADM-R04 | Keep and harden Admin Remedy-linked rubrics (do not rebuild) | ADM-R04.01 | Regression: list / add / edit / (import-export if present) for Remedy-linked rubrics | Existing | Repertory | §7.1 | Remedy-linked rubrics | View all rubrics linked to a remedy | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
63 | 63 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.4 | ADM-R04 | Keep and harden Admin Remedy-linked rubrics (do not rebuild) | ADM-R04.02 | ACL: only Admin (and permitted roles) can mutate Remedy-linked rubrics; Doctor is read-only consumer on Patient Board | Existing Improvement | Repertory | §7.1 | Remedy-linked rubrics | View all rubrics linked to a remedy | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
64 | 64 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.4 | ADM-R04 | Keep and harden Admin Remedy-linked rubrics (do not rebuild) | ADM-R04.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Remedy-linked rubrics; do not silently switch | Existing | Repertory | §7.1 | Remedy-linked rubrics | View all rubrics linked to a remedy | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
65 | 65 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.5 | ADM-R05 | Keep and harden Admin Language master (do not rebuild) | ADM-R05.01 | Regression: list / add / edit / (import-export if present) for Language master | Existing | Repertory | §7.1 | Language master | Manage languages | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
66 | 66 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.5 | ADM-R05 | Keep and harden Admin Language master (do not rebuild) | ADM-R05.02 | ACL: only Admin (and permitted roles) can mutate Language master; Doctor is read-only consumer on Patient Board | Existing Improvement | Repertory | §7.1 | Language master | Manage languages | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
67 | 67 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.5 | ADM-R05 | Keep and harden Admin Language master (do not rebuild) | ADM-R05.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Language master; do not silently switch | Existing | Repertory | §7.1 | Language master | Manage languages | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
68 | 68 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.6 | ADM-R06 | Keep and harden Admin Body part master (do not rebuild) | ADM-R06.01 | Regression: list / add / edit / (import-export if present) for Body part master | Existing | Repertory | §7.1 | Body part master | Manage body parts | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
69 | 69 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.6 | ADM-R06 | Keep and harden Admin Body part master (do not rebuild) | ADM-R06.02 | ACL: only Admin (and permitted roles) can mutate Body part master; Doctor is read-only consumer on Patient Board | Existing Improvement | Repertory | §7.1 | Body part master | Manage body parts | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
70 | 70 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.6 | ADM-R06 | Keep and harden Admin Body part master (do not rebuild) | ADM-R06.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Body part master; do not silently switch | Existing | Repertory | §7.1 | Body part master | Manage body parts | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
71 | 71 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.7 | ADM-R07 | Keep and harden Admin Intensity master (do not rebuild) | ADM-R07.01 | Regression: list / add / edit / (import-export if present) for Intensity master | Existing | Repertory | §7.1 | Intensity master | Manage intensity levels | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
72 | 72 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.7 | ADM-R07 | Keep and harden Admin Intensity master (do not rebuild) | ADM-R07.02 | ACL: only Admin (and permitted roles) can mutate Intensity master; Doctor is read-only consumer on Patient Board | Existing Improvement | Repertory | §7.1 | Intensity master | Manage intensity levels | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
73 | 73 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.7 | ADM-R07 | Keep and harden Admin Intensity master (do not rebuild) | ADM-R07.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Intensity master; do not silently switch | Existing | Repertory | §7.1 | Intensity master | Manage intensity levels | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
74 | 74 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.8 | ADM-R08 | Keep and harden Admin Remedy master (do not rebuild) | ADM-R08.01 | Regression: list / add / edit / (import-export if present) for Remedy master | Existing | Repertory | §7.1 | Remedy master | Manage the remedy library | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
75 | 75 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.8 | ADM-R08 | Keep and harden Admin Remedy master (do not rebuild) | ADM-R08.02 | ACL: only Admin (and permitted roles) can mutate Remedy master; Doctor is read-only consumer on Patient Board | Existing Improvement | Repertory | §7.1 | Remedy master | Manage the remedy library | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
76 | 76 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.8 | ADM-R08 | Keep and harden Admin Remedy master (do not rebuild) | ADM-R08.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Remedy master; do not silently switch | Existing | Repertory | §7.1 | Remedy master | Manage the remedy library | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
77 | 77 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.9 | ADM-R09 | Keep and harden Admin Remedy grade master (do not rebuild) | ADM-R09.01 | Regression: list / add / edit / (import-export if present) for Remedy grade master | Existing | Repertory | §7.1 | Remedy grade master | Manage remedy grading | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
78 | 78 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.9 | ADM-R09 | Keep and harden Admin Remedy grade master (do not rebuild) | ADM-R09.02 | ACL: only Admin (and permitted roles) can mutate Remedy grade master; Doctor is read-only consumer on Patient Board | Existing Improvement | Repertory | §7.1 | Remedy grade master | Manage remedy grading | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
79 | 79 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.9 | ADM-R09 | Keep and harden Admin Remedy grade master (do not rebuild) | ADM-R09.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Remedy grade master; do not silently switch | Existing | Repertory | §7.1 | Remedy grade master | Manage remedy grading | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
80 | 80 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.10 | ADM-M01 | Keep and harden Admin Author master (do not rebuild) | ADM-M01.01 | Regression: list / add / edit / (import-export if present) for Author master | Existing | Materia Medica | §7.1 | Author master | Manage materia medica authors | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
81 | 81 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.10 | ADM-M01 | Keep and harden Admin Author master (do not rebuild) | ADM-M01.02 | ACL: only Admin (and permitted roles) can mutate Author master; Doctor is read-only consumer on Patient Board | Existing Improvement | Materia Medica | §7.1 | Author master | Manage materia medica authors | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
82 | 82 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.10 | ADM-M01 | Keep and harden Admin Author master (do not rebuild) | ADM-M01.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Author master; do not silently switch | Existing | Materia Medica | §7.1 | Author master | Manage materia medica authors | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
83 | 83 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.11 | ADM-M02 | Keep and harden Admin Materia medica master (do not rebuild) | ADM-M02.01 | Regression: list / add / edit / (import-export if present) for Materia medica master | Existing | Materia Medica | §7.1 | Materia medica master | Manage the materia medica library | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
84 | 84 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.11 | ADM-M02 | Keep and harden Admin Materia medica master (do not rebuild) | ADM-M02.02 | ACL: only Admin (and permitted roles) can mutate Materia medica master; Doctor is read-only consumer on Patient Board | Existing Improvement | Materia Medica | §7.1 | Materia medica master | Manage the materia medica library | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
85 | 85 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.11 | ADM-M02 | Keep and harden Admin Materia medica master (do not rebuild) | ADM-M02.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Materia medica master; do not silently switch | Existing | Materia Medica | §7.1 | Materia medica master | Manage the materia medica library | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
86 | 86 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.12 | ADM-M03 | Keep and harden Admin Materia medica heads (do not rebuild) | ADM-M03.01 | Regression: list / add / edit / (import-export if present) for Materia medica heads | Existing | Materia Medica | §7.1 | Materia medica heads | Manage chapter headings | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
87 | 87 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.12 | ADM-M03 | Keep and harden Admin Materia medica heads (do not rebuild) | ADM-M03.02 | ACL: only Admin (and permitted roles) can mutate Materia medica heads; Doctor is read-only consumer on Patient Board | Existing Improvement | Materia Medica | §7.1 | Materia medica heads | Manage chapter headings | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
88 | 88 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.12 | ADM-M03 | Keep and harden Admin Materia medica heads (do not rebuild) | ADM-M03.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Materia medica heads; do not silently switch | Existing | Materia Medica | §7.1 | Materia medica heads | Manage chapter headings | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
89 | 89 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.13 | ADM-M04 | Keep and harden Admin Materia medica remedies (do not rebuild) | ADM-M04.01 | Regression: list / add / edit / (import-export if present) for Materia medica remedies | Existing | Materia Medica | §7.1 | Materia medica remedies | View remedy-wise materia medica | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
90 | 90 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.13 | ADM-M04 | Keep and harden Admin Materia medica remedies (do not rebuild) | ADM-M04.02 | ACL: only Admin (and permitted roles) can mutate Materia medica remedies; Doctor is read-only consumer on Patient Board | Existing Improvement | Materia Medica | §7.1 | Materia medica remedies | View remedy-wise materia medica | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
91 | 91 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.13 | ADM-M04 | Keep and harden Admin Materia medica remedies (do not rebuild) | ADM-M04.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Materia medica remedies; do not silently switch | Existing | Materia Medica | §7.1 | Materia medica remedies | View remedy-wise materia medica | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
92 | 92 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.14 | ADM-D01 | Keep and harden Admin Diagnosis system (do not rebuild) | ADM-D01.01 | Regression: list / add / edit / (import-export if present) for Diagnosis system | Existing | Diagnosis | §7.1 | Diagnosis system | Manage diagnosis systems | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
93 | 93 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.14 | ADM-D01 | Keep and harden Admin Diagnosis system (do not rebuild) | ADM-D01.02 | ACL: only Admin (and permitted roles) can mutate Diagnosis system; Doctor is read-only consumer on Patient Board | Existing Improvement | Diagnosis | §7.1 | Diagnosis system | Manage diagnosis systems | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
94 | 94 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.14 | ADM-D01 | Keep and harden Admin Diagnosis system (do not rebuild) | ADM-D01.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Diagnosis system; do not silently switch | Existing | Diagnosis | §7.1 | Diagnosis system | Manage diagnosis systems | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
95 | 95 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.15 | ADM-D02 | Keep and harden Admin Diagnosis therapeutics (do not rebuild) | ADM-D02.01 | Regression: list / add / edit / (import-export if present) for Diagnosis therapeutics | Existing | Diagnosis | §7.1 | Diagnosis therapeutics | Manage therapeutics | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
96 | 96 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.15 | ADM-D02 | Keep and harden Admin Diagnosis therapeutics (do not rebuild) | ADM-D02.02 | ACL: only Admin (and permitted roles) can mutate Diagnosis therapeutics; Doctor is read-only consumer on Patient Board | Existing Improvement | Diagnosis | §7.1 | Diagnosis therapeutics | Manage therapeutics | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
97 | 97 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.15 | ADM-D02 | Keep and harden Admin Diagnosis therapeutics (do not rebuild) | ADM-D02.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Diagnosis therapeutics; do not silently switch | Existing | Diagnosis | §7.1 | Diagnosis therapeutics | Manage therapeutics | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
98 | 98 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.16 | ADM-D03 | Keep and harden Admin Diagnosis conditions (do not rebuild) | ADM-D03.01 | Regression: list / add / edit / (import-export if present) for Diagnosis conditions | Existing | Diagnosis | §7.1 | Diagnosis conditions | Manage conditions and linked rubrics | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
99 | 99 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.16 | ADM-D03 | Keep and harden Admin Diagnosis conditions (do not rebuild) | ADM-D03.02 | ACL: only Admin (and permitted roles) can mutate Diagnosis conditions; Doctor is read-only consumer on Patient Board | Existing Improvement | Diagnosis | §7.1 | Diagnosis conditions | Manage conditions and linked rubrics | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
100 | 100 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.16 | ADM-D03 | Keep and harden Admin Diagnosis conditions (do not rebuild) | ADM-D03.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Diagnosis conditions; do not silently switch | Existing | Diagnosis | §7.1 | Diagnosis conditions | Manage conditions and linked rubrics | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
101 | 101 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.17 | ADM-A01 | Keep and harden Admin Drug system (do not rebuild) | ADM-A01.01 | Regression: list / add / edit / (import-export if present) for Drug system | Existing | Adverse Effect | §7.1 | Drug system | Manage conventional drug systems | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
102 | 102 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.17 | ADM-A01 | Keep and harden Admin Drug system (do not rebuild) | ADM-A01.02 | ACL: only Admin (and permitted roles) can mutate Drug system; Doctor is read-only consumer on Patient Board | Existing Improvement | Adverse Effect | §7.1 | Drug system | Manage conventional drug systems | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
103 | 103 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.17 | ADM-A01 | Keep and harden Admin Drug system (do not rebuild) | ADM-A01.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Drug system; do not silently switch | Existing | Adverse Effect | §7.1 | Drug system | Manage conventional drug systems | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
104 | 104 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.18 | ADM-A02 | Keep and harden Admin Drug group (do not rebuild) | ADM-A02.01 | Regression: list / add / edit / (import-export if present) for Drug group | Existing | Adverse Effect | §7.1 | Drug group | Manage drug groups | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
105 | 105 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.18 | ADM-A02 | Keep and harden Admin Drug group (do not rebuild) | ADM-A02.02 | ACL: only Admin (and permitted roles) can mutate Drug group; Doctor is read-only consumer on Patient Board | Existing Improvement | Adverse Effect | §7.1 | Drug group | Manage drug groups | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
106 | 106 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.18 | ADM-A02 | Keep and harden Admin Drug group (do not rebuild) | ADM-A02.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Drug group; do not silently switch | Existing | Adverse Effect | §7.1 | Drug group | Manage drug groups | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
107 | 107 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.19 | ADM-A03 | Keep and harden Admin Allopathic drug & side effects (do not rebuild) | ADM-A03.01 | Regression: list / add / edit / (import-export if present) for Allopathic drug & side effects | Existing | Adverse Effect | §7.1 | Allopathic drug & side effects | Manage drugs with side effects and adverse reactions | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
108 | 108 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.19 | ADM-A03 | Keep and harden Admin Allopathic drug & side effects (do not rebuild) | ADM-A03.02 | ACL: only Admin (and permitted roles) can mutate Allopathic drug & side effects; Doctor is read-only consumer on Patient Board | Existing Improvement | Adverse Effect | §7.1 | Allopathic drug & side effects | Manage drugs with side effects and adverse reactions | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
109 | 109 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.19 | ADM-A03 | Keep and harden Admin Allopathic drug & side effects (do not rebuild) | ADM-A03.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Allopathic drug & side effects; do not silently switch | Existing | Adverse Effect | §7.1 | Allopathic drug & side effects | Manage drugs with side effects and adverse reactions | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
110 | 110 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.20 | ADM-Q01 | Keep and harden Admin Question section, group & sub-group (do not rebuild) | ADM-Q01.01 | Regression: list / add / edit / (import-export if present) for Question section, group & sub-group | Existing | Clinical Questions | §7.1 | Question section, group & sub-group | Manage the clinical questionnaire structure | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
111 | 111 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.20 | ADM-Q01 | Keep and harden Admin Question section, group & sub-group (do not rebuild) | ADM-Q01.02 | ACL: only Admin (and permitted roles) can mutate Question section, group & sub-group; Doctor is read-only consumer on Patient Board | Existing Improvement | Clinical Questions | §7.1 | Question section, group & sub-group | Manage the clinical questionnaire structure | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
112 | 112 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.20 | ADM-Q01 | Keep and harden Admin Question section, group & sub-group (do not rebuild) | ADM-Q01.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Question section, group & sub-group; do not silently switch | Existing | Clinical Questions | §7.1 | Question section, group & sub-group | Manage the clinical questionnaire structure | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
113 | 113 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.21 | ADM-Q02 | Keep and harden Admin Clinical question mapping (do not rebuild) | ADM-Q02.01 | Regression: list / add / edit / (import-export if present) for Clinical question mapping | Existing | Clinical Questions | §7.1 | Clinical question mapping | Map questions to body parts and rubrics | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
114 | 114 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.21 | ADM-Q02 | Keep and harden Admin Clinical question mapping (do not rebuild) | ADM-Q02.02 | ACL: only Admin (and permitted roles) can mutate Clinical question mapping; Doctor is read-only consumer on Patient Board | Existing Improvement | Clinical Questions | §7.1 | Clinical question mapping | Map questions to body parts and rubrics | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
115 | 115 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.21 | ADM-Q02 | Keep and harden Admin Clinical question mapping (do not rebuild) | ADM-Q02.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Clinical question mapping; do not silently switch | Existing | Clinical Questions | §7.1 | Clinical question mapping | Map questions to body parts and rubrics | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
116 | 116 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.22 | ADM-3D1 | Keep and harden Admin 3D mesh key master (do not rebuild) | ADM-3D1.01 | Regression: list / add / edit / (import-export if present) for 3D mesh key master | Existing | 3D Body | §7.1 | 3D mesh key master | Manage 3D model references | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
117 | 117 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.22 | ADM-3D1 | Keep and harden Admin 3D mesh key master (do not rebuild) | ADM-3D1.02 | ACL: only Admin (and permitted roles) can mutate 3D mesh key master; Doctor is read-only consumer on Patient Board | Existing Improvement | 3D Body | §7.1 | 3D mesh key master | Manage 3D model references | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
118 | 118 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.22 | ADM-3D1 | Keep and harden Admin 3D mesh key master (do not rebuild) | ADM-3D1.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for 3D mesh key master; do not silently switch | Existing | 3D Body | §7.1 | 3D mesh key master | Manage 3D model references | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
119 | 119 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.23 | ADM-3D2 | Keep and harden Admin 3D section master (do not rebuild) | ADM-3D2.01 | Regression: list / add / edit / (import-export if present) for 3D section master | Existing | 3D Body | §7.1 | 3D section master | Manage 3D body sections | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
120 | 120 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.23 | ADM-3D2 | Keep and harden Admin 3D section master (do not rebuild) | ADM-3D2.02 | ACL: only Admin (and permitted roles) can mutate 3D section master; Doctor is read-only consumer on Patient Board | Existing Improvement | 3D Body | §7.1 | 3D section master | Manage 3D body sections | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
121 | 121 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.23 | ADM-3D2 | Keep and harden Admin 3D section master (do not rebuild) | ADM-3D2.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for 3D section master; do not silently switch | Existing | 3D Body | §7.1 | 3D section master | Manage 3D body sections | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
122 | 122 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.24 | ADM-3D3 | Keep and harden Admin 3D hotspots (do not rebuild) | ADM-3D3.01 | Regression: list / add / edit / (import-export if present) for 3D hotspots | Existing | 3D Body | §7.1 | 3D hotspots | Manage clickable points on the 3D model | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
123 | 123 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.24 | ADM-3D3 | Keep and harden Admin 3D hotspots (do not rebuild) | ADM-3D3.02 | ACL: only Admin (and permitted roles) can mutate 3D hotspots; Doctor is read-only consumer on Patient Board | Existing Improvement | 3D Body | §7.1 | 3D hotspots | Manage clickable points on the 3D model | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
124 | 124 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.24 | ADM-3D3 | Keep and harden Admin 3D hotspots (do not rebuild) | ADM-3D3.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for 3D hotspots; do not silently switch | Existing | 3D Body | §7.1 | 3D hotspots | Manage clickable points on the 3D model | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
125 | 125 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.25 | ADM-B01 | Business Management — Doctor qualifications (existing, used later by credentialing) | ADM-B01.01 | Regression: qualifications list/add/edit | Existing | Business Management | §7.2 | Doctor qualifications | Manage the qualification list | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
126 | 126 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.25 | ADM-B01 | Business Management — Doctor qualifications (existing, used later by credentialing) | ADM-B01.02 | ACL on qualification APIs | Existing Improvement | Business Management | §7.2 | Doctor qualifications | Manage the qualification list | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
127 | 127 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.25 | ADM-B01 | Business Management — Doctor qualifications (existing, used later by credentialing) | ADM-B01.03 | Confirm UI uses newer API (not classic) for qualifications | Existing | Business Management | §7.2 | Doctor qualifications | Manage the qualification list | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
128 | 128 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.26 | ADM-B02 | Business Management — Lab & imaging test catalog (existing, used by eRx lab orders) | ADM-B02.01 | Regression: lab catalog CRUD and doctor order pick-list | Existing | Business Management | §7.2 | Lab & imaging test catalog | Manage the test catalogue | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
129 | 129 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.26 | ADM-B02 | Business Management — Lab & imaging test catalog (existing, used by eRx lab orders) | ADM-B02.02 | ACL on catalog mutate | Existing Improvement | Business Management | §7.2 | Lab & imaging test catalog | Manage the test catalogue | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
130 | 130 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.26 | ADM-B02 | Business Management — Lab & imaging test catalog (existing, used by eRx lab orders) | ADM-B02.03 | Confirm classic PatientLab APIs still read this catalogue | Existing | Business Management | §7.2 | Lab & imaging test catalog | Manage the test catalogue | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
131 | 131 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.27 | ADM-B03 | Business Management — Subscription packages (existing S1 SaaS; later tied to Account ledger) | ADM-B03.01 | Regression: package list/add/edit; doctor Widgets still reads packages | Existing | Business Management | §7.2 | Subscription packages | Manage doctor subscription plans | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
132 | 132 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.27 | ADM-B03 | Business Management — Subscription packages (existing S1 SaaS; later tied to Account ledger) | ADM-B03.02 | ACL on package mutate | Existing Improvement | Business Management | §7.2 | Subscription packages | Manage doctor subscription plans | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
133 | 133 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.27 | ADM-B03 | Business Management — Subscription packages (existing S1 SaaS; later tied to Account ledger) | ADM-B03.03 | Note in code: PackageEntryDetail is S1 only — never reuse for S2 consult or S5 medicine | Existing | Business Management | §7.2 | Subscription packages | Manage doctor subscription plans | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
134 | 134 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.28 | ADM-B04 | Business Management — Roles & menu permissions (existing DB, runtime ACL leftover) | ADM-B04.01 | No schema change unless Account/Pharmacy/Patient roles need new MenuMaster rows — seed those menus | Existing Improvement | Business Management | §7.2 | Roles & menu permissions | Control exactly what each role can access | Admin Portal | Database | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | Yes | In Progress | Gourav Nikam | No | N/A |  | No | N/A |  | No | N/A |  | 1 | In Progress |  | Edit on module sheet
135 | 135 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.28 | ADM-B04 | Business Management — Roles & menu permissions (existing DB, runtime ACL leftover) | ADM-B04.02 | Restore GetMenuByRole on .NET 8; seed menus for Account and (later) Pharmacy | Existing Improvement | Business Management | §7.2 | Roles & menu permissions | Control exactly what each role can access | Admin Portal | API | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | Yes | In Progress | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 1 | In Progress |  | Edit on module sheet
136 | 136 | M02 | Admin clinical masters | UI | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.28 | ADM-B04 | Business Management — Roles & menu permissions (existing DB, runtime ACL leftover) | ADM-B04.03 | Admin role pages remain; frontend consumes menu API instead of hard-coded LayoutMenuData for domain items | Existing Improvement | Business Management | §7.2 | Roles & menu permissions | Control exactly what each role can access | Admin Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
137 | 137 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.28 | ADM-B04 | Business Management — Roles & menu permissions (existing DB, runtime ACL leftover) | ADM-B04.04 | QA: edit role menu → user of that role no longer sees the item | Regression | Business Management | §7.2 | Roles & menu permissions | Control exactly what each role can access | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
138 | 138 | M03 | Doctor clinical workspace | UI | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.1 | CLN-01 | Clinical workspace — single screen for the entire consultation | CLN-01.01 | UI: Patient Board header shows appointment, visit type, consult mode placeholders (wired in Phases 4 and 6) | Existing Improvement | Patient Board | §5.3 | Clinical workspace | Single screen for the entire consultation | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
139 | 139 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.1 | CLN-01 | Clinical workspace — single screen for the entire consultation | CLN-01.02 | Do not split the board into multiple apps; mobile doctor app will NOT get case-taking (PDF §3) | Existing | Patient Board | §5.3 | Clinical workspace | Single screen for the entire consultation | Doctor Web Portal | Architecture | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 0 | N/A |  | Edit on module sheet
140 | 140 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.1 | CLN-01 | Clinical workspace — single screen for the entire consultation | CLN-01.03 | Regression: open case from dashboard still remounts via PatientBoardRoute | Regression | Patient Board | §5.3 | Clinical workspace | Single screen for the entire consultation | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
141 | 141 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.2 | CLN-02 | Manual case taking — structured case taking (keep) | CLN-02.01 | Regression: create case, add rubrics via manual path, repertorize | Existing | Patient Board | §5.3 | Manual case taking | Structured case taking | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
142 | 142 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.2 | CLN-02 | Manual case taking — structured case taking (keep) | CLN-02.02 | ACL: only treating doctor (not Reception) can run full case taking | Existing Improvement | Patient Board | §5.3 | Manual case taking | Structured case taking | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
143 | 143 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.2 | CLN-02 | Manual case taking — structured case taking (keep) | CLN-02.03 | Confirm clipboard/repertorization APIs still on the correct host | Existing | Patient Board | §5.3 | Manual case taking | Structured case taking | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
144 | 144 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.3 | CLN-03 | Body parts & intensity selection (keep) | CLN-03.01 | Regression: body part → rubrics; intensity chip | Existing | Patient Board | §5.3 | Body parts & intensity selection | Select affected areas and severity | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
145 | 145 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.3 | CLN-03 | Body parts & intensity selection (keep) | CLN-03.02 | ACL: doctor-only | Existing Improvement | Patient Board | §5.3 | Body parts & intensity selection | Select affected areas and severity | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
146 | 146 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.3 | CLN-03 | Body parts & intensity selection (keep) | CLN-03.03 | API host unchanged | Existing | Patient Board | §5.3 | Body parts & intensity selection | Select affected areas and severity | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
147 | 147 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.4 | CLN-04 | Clinical questions — guided questions by section, group and sub-group (keep) | CLN-04.01 | Regression: full question drill-down | Existing | Patient Board | §5.3 | Clinical questions | Guided questions by section, group and sub-group | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
148 | 148 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.4 | CLN-04 | Clinical questions — guided questions by section, group and sub-group (keep) | CLN-04.02 | ACL doctor-only | Existing Improvement | Patient Board | §5.3 | Clinical questions | Guided questions by section, group and sub-group | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
149 | 149 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.4 | CLN-04 | Clinical questions — guided questions by section, group and sub-group (keep) | CLN-04.03 | API host unchanged | Existing | Patient Board | §5.3 | Clinical questions | Guided questions by section, group and sub-group | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
150 | 150 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.5 | CLN-05 | Diagnosis, therapeutics & pattern search (keep) | CLN-05.01 | Regression: diagnosis search + therapeutics | Existing | Patient Board | §5.3 | Diagnosis, therapeutics & pattern search | Search diagnoses and linked therapeutics | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
151 | 151 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.5 | CLN-05 | Diagnosis, therapeutics & pattern search (keep) | CLN-05.02 | ACL doctor-only | Existing Improvement | Patient Board | §5.3 | Diagnosis, therapeutics & pattern search | Search diagnoses and linked therapeutics | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
152 | 152 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.5 | CLN-05 | Diagnosis, therapeutics & pattern search (keep) | CLN-05.03 | API host unchanged | Existing | Patient Board | §5.3 | Diagnosis, therapeutics & pattern search | Search diagnoses and linked therapeutics | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
153 | 153 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.6 | CLN-06 | Repertory rubric search & selection (keep) | CLN-06.01 | Regression: tree + search + add to clipboard | Existing | Patient Board | §5.3 | Repertory rubric search & selection | Search and select from the full repertory | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
154 | 154 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.6 | CLN-06 | Repertory rubric search & selection (keep) | CLN-06.02 | ACL doctor-only | Existing Improvement | Patient Board | §5.3 | Repertory rubric search & selection | Search and select from the full repertory | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
155 | 155 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.6 | CLN-06 | Repertory rubric search & selection (keep) | CLN-06.03 | Confirm subsection search host (newer vs classic) documented | Existing | Patient Board | §5.3 | Repertory rubric search & selection | Search and select from the full repertory | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
156 | 156 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.7 | CLN-07 | Manage selected rubrics — review, edit and remove (remaining ~10%) | CLN-07.01 | No new table — clipboard already persisted via board backup / repertorization payload | Existing Improvement | Patient Board | §5.3 | Manage selected rubrics | Review, edit and remove selected rubrics | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
157 | 157 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.7 | CLN-07 | Manage selected rubrics — review, edit and remove (remaining ~10%) | CLN-07.02 | If intensity-on-clipboard is client-only, persist it on backup payload | Existing Improvement | Patient Board | §5.3 | Manage selected rubrics | Review, edit and remove selected rubrics | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
158 | 158 | M03 | Doctor clinical workspace | UI | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.7 | CLN-07 | Manage selected rubrics — review, edit and remove (remaining ~10%) | CLN-07.03 | Clipboard UX: confirm delete; intensity edit; count badge | Existing Improvement | Patient Board | §5.3 | Manage selected rubrics | Review, edit and remove selected rubrics | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
159 | 159 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.7 | CLN-07 | Manage selected rubrics — review, edit and remove (remaining ~10%) | CLN-07.04 | QA: remove, undo-not-required, backup restore still has remaining rubrics | Regression | Patient Board | §5.3 | Manage selected rubrics | Review, edit and remove selected rubrics | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
160 | 160 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.8 | CLN-08 | Audio case taking — record and receive suggested rubrics (keep engine; do not rebuild) | CLN-08.01 | Regression: record, poll, approve/reject suggested rubrics | Existing | Audio AI | §5.3 | Audio case taking | Record the consultation and receive suggested rubrics automatically | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
161 | 161 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.8 | CLN-08 | Audio case taking — record and receive suggested rubrics (keep engine; do not rebuild) | CLN-08.02 | Consent: audio consent continues to write AudioCaseConsentLog (later also ConsentRecord) | Existing Improvement | Audio AI | §5.3 | Audio case taking | Record the consultation and receive suggested rubrics automatically | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
162 | 162 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.8 | CLN-08 | Audio case taking — record and receive suggested rubrics (keep engine; do not rebuild) | CLN-08.03 | Confirm audio queue/worker still healthy | Existing | Audio AI | §5.3 | Audio case taking | Record the consultation and receive suggested rubrics automatically | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
163 | 163 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.9 | CLN-09 | Improved rubric accuracy — enhanced accuracy rules for audio-based rubric suggestions | CLN-09.01 | Follow AUDIO_CASE_TAKING_* docs: accuracy rules, aliases, metaphors, benchmark | Existing Improvement | Audio AI | §5.3 | Improved rubric accuracy | Enhanced accuracy rules for audio-based rubric suggestions | Doctor Web Portal + Admin intelligence | Backend | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
164 | 164 | M03 | Doctor clinical workspace | UI | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.9 | CLN-09 | Improved rubric accuracy — enhanced accuracy rules for audio-based rubric suggestions | CLN-09.02 | Admin: metaphor/alias approve-reject remaining UX | Existing Improvement | Audio AI | §5.3 | Improved rubric accuracy | Enhanced accuracy rules for audio-based rubric suggestions | Doctor Web Portal + Admin intelligence | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
165 | 165 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.9 | CLN-09 | Improved rubric accuracy — enhanced accuracy rules for audio-based rubric suggestions | CLN-09.03 | QA: golden transcripts → expected rubric IDs within tolerance | Regression | Audio AI | §5.3 | Improved rubric accuracy | Enhanced accuracy rules for audio-based rubric suggestions | Doctor Web Portal + Admin intelligence | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
166 | 166 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.10 | CLN-10 | Materia medica reference during consultation (remaining ~10%) | CLN-10.01 | No schema change | Existing Improvement | Patient Board | §5.3 | Materia medica reference | Browse materia medica during the consultation | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
167 | 167 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.10 | CLN-10 | Materia medica reference during consultation (remaining ~10%) | CLN-10.02 | Existing MM APIs — add a lightweight get-by-remedy if chatty | Existing Improvement | Patient Board | §5.3 | Materia medica reference | Browse materia medica during the consultation | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
168 | 168 | M03 | Doctor clinical workspace | UI | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.10 | CLN-10 | Materia medica reference during consultation (remaining ~10%) | CLN-10.03 | MM tab: faster head navigation / keep place in case | Existing Improvement | Patient Board | §5.3 | Materia medica reference | Browse materia medica during the consultation | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
169 | 169 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.10 | CLN-10 | Materia medica reference during consultation (remaining ~10%) | CLN-10.04 | QA: open MM for a repertorized remedy | Regression | Patient Board | §5.3 | Materia medica reference | Browse materia medica during the consultation | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
170 | 170 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.11 | CLN-11 | Allopathic drug side-effect lookup (keep) | CLN-11.01 | Regression: search drug → side effects | Existing | Patient Board | §5.3 | Allopathic drug side-effect lookup | Check side effects of conventional medicines | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
171 | 171 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.11 | CLN-11 | Allopathic drug side-effect lookup (keep) | CLN-11.02 | ACL doctor-only | Existing Improvement | Patient Board | §5.3 | Allopathic drug side-effect lookup | Check side effects of conventional medicines | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
172 | 172 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.11 | CLN-11 | Allopathic drug side-effect lookup (keep) | CLN-11.03 | API host unchanged | Existing | Patient Board | §5.3 | Allopathic drug side-effect lookup | Check side effects of conventional medicines | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
173 | 173 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.12 | CLN-12 | Repertorization & elimination (remaining ~10%) | CLN-12.01 | No schema change | Existing Improvement | Patient Board | §5.3 | Repertorization & elimination | Full repertorization with elimination | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
174 | 174 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.12 | CLN-12 | Repertorization & elimination (remaining ~10%) | CLN-12.02 | Keep existing repertorization APIs; fix any known scoring edge cases | Existing Improvement | Patient Board | §5.3 | Repertorization & elimination | Full repertorization with elimination | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
175 | 175 | M03 | Doctor clinical workspace | UI | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.12 | CLN-12 | Repertorization & elimination (remaining ~10%) | CLN-12.03 | Repertorize tab stability; then COG sits beside it | Existing Improvement | Patient Board | §5.3 | Repertorization & elimination | Full repertorization with elimination | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
176 | 176 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.12 | CLN-12 | Repertorization & elimination (remaining ~10%) | CLN-12.04 | QA: known case → expected top remedies | Regression | Patient Board | §5.3 | Repertorization & elimination | Full repertorization with elimination | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
177 | 177 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.13 | CLN-13 | Center of Gravity — new analysis identifying the central remedy of the case, with reasoning shown | CLN-13.01 | No mandatory new table (algorithm on selected rubrics); optional CogRun log for support | New | Repertorization | §5.3 | Center of Gravity | New analysis identifying the central remedy of the case, with reasoning shown | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
178 | 178 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.13 | CLN-13 | Center of Gravity — new analysis identifying the central remedy of the case, with reasoning shown | CLN-13.02 | POST /api/Repertorization/CenterOfGravity — input rubric ids + intensities; output ranked remedies + reasons | New | Repertorization | §5.3 | Center of Gravity | New analysis identifying the central remedy of the case, with reasoning shown | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
179 | 179 | M03 | Doctor clinical workspace | UI | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.13 | CLN-13 | Center of Gravity — new analysis identifying the central remedy of the case, with reasoning shown | CLN-13.03 | Patient Board → Repertorize tab → Center of Gravity sub-panel (toggle vs classic elimination) | New | Repertorization | §5.3 | Center of Gravity | New analysis identifying the central remedy of the case, with reasoning shown | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
180 | 180 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.13 | CLN-13 | Center of Gravity — new analysis identifying the central remedy of the case, with reasoning shown | CLN-13.04 | QA: same clipboard as classic repertorize; COG reasons cite contributing rubrics; empty clipboard → clear empty state | Regression | Repertorization | §5.3 | Center of Gravity | New analysis identifying the central remedy of the case, with reasoning shown | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
181 | 181 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.14 | CLN-14 | Lab orders & lab entries (keep; later also sit on eRx) | CLN-14.01 | Regression: order lab from catalogue; enter result | Existing | Patient Board | §5.3 + §11 | Lab orders & lab entries | Order tests and record results / Tests ordered alongside the prescription | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
182 | 182 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.14 | CLN-14 | Lab orders & lab entries (keep; later also sit on eRx) | CLN-14.02 | ACL doctor-only | Existing Improvement | Patient Board | §5.3 + §11 | Lab orders & lab entries | Order tests and record results / Tests ordered alongside the prescription | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
183 | 183 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.14 | CLN-14 | Lab orders & lab entries (keep; later also sit on eRx) | CLN-14.03 | API: classic PatientLab still authoritative until ported | Existing | Patient Board | §5.3 + §11 | Lab orders & lab entries | Order tests and record results / Tests ordered alongside the prescription | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
184 | 184 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.15 | CLN-15 | Appointment history notes (keep; split from eRx in Phase 10) | CLN-15.01 | Regression: add/list notes on a visit | Existing | Patient Board | §5.3 | Appointment history notes | Notes recorded against each visit | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
185 | 185 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.15 | CLN-15 | Appointment history notes (keep; split from eRx in Phase 10) | CLN-15.02 | ACL doctor-only | Existing Improvement | Patient Board | §5.3 | Appointment history notes | Notes recorded against each visit | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
186 | 186 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.15 | CLN-15 | Appointment history notes (keep; split from eRx in Phase 10) | CLN-15.03 | Do not dual-write; classic notes stay until Phase 10 extends them | Existing | Patient Board | §5.3 | Appointment history notes | Notes recorded against each visit | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
187 | 187 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.16 | CLN-16 | Complaints & case details — wire Patient Board to existing SaveComplaints / SaveCaseDetails (~20% today) | CLN-16.01 | Use existing tables — no new schema unless fields are missing vs PDF | Existing Improvement | Patient Board | §5.3 | Complaints & case details | Capture and store complaints and case details | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
188 | 188 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.16 | CLN-16 | Complaints & case details — wire Patient Board to existing SaveComplaints / SaveCaseDetails (~20% today) | CLN-16.02 | Keep classic SaveComplaints / SaveCaseDetails; add GET if missing | Existing Improvement | Patient Board | §5.3 | Complaints & case details | Capture and store complaints and case details | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
189 | 189 | M03 | Doctor clinical workspace | UI | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.16 | CLN-16 | Complaints & case details — wire Patient Board to existing SaveComplaints / SaveCaseDetails (~20% today) | CLN-16.03 | Patient Board: complaints + case details form that actually POSTs | Existing Improvement | Patient Board | §5.3 | Complaints & case details | Capture and store complaints and case details | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
190 | 190 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.16 | CLN-16 | Complaints & case details — wire Patient Board to existing SaveComplaints / SaveCaseDetails (~20% today) | CLN-16.04 | QA: save, reload, second doctor cannot read | Regression | Patient Board | §5.3 | Complaints & case details | Capture and store complaints and case details | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
191 | 191 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.17 | CLN-17 | Patient back history — complete history of visits, notes, prescriptions and payments | CLN-17.01 | No new table — compose from Appointment + notes + Rx + (later) ConsultPayment | Existing Improvement | Patient Board | §5.3 | Patient back history | Complete history of visits, notes, prescriptions and payments | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
192 | 192 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.17 | CLN-17 | Patient back history — complete history of visits, notes, prescriptions and payments | CLN-17.02 | GET patient timeline DTO including payment status when column exists | Existing Improvement | Patient Board | §5.3 | Patient back history | Complete history of visits, notes, prescriptions and payments | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
193 | 193 | M03 | Doctor clinical workspace | UI | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.17 | CLN-17 | Patient back history — complete history of visits, notes, prescriptions and payments | CLN-17.03 | History panel: date-ordered visits; open past eRx; payment badge placeholder | Existing Improvement | Patient Board | §5.3 | Patient back history | Complete history of visits, notes, prescriptions and payments | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
194 | 194 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.17 | CLN-17 | Patient back history — complete history of visits, notes, prescriptions and payments | CLN-17.04 | QA: multi-visit patient; empty new patient | Regression | Patient Board | §5.3 | Patient back history | Complete history of visits, notes, prescriptions and payments | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
195 | 195 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.18 | CLN-18 | Export case data — download the full case in Excel or PDF | CLN-18.01 | Reuse ExportCasesToExcel; add PDF generation of the clinical case (doctor copy, includes notes) | Existing Improvement | Patient Board | §5.3 | Export case data | Download the full case in Excel or PDF | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
196 | 196 | M03 | Doctor clinical workspace | UI | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.18 | CLN-18 | Export case data — download the full case in Excel or PDF | CLN-18.02 | Patient Board toolbar: Export Excel / Export PDF | New | Patient Board | §5.3 | Export case data | Download the full case in Excel or PDF | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
197 | 197 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.18 | CLN-18 | Export case data — download the full case in Excel or PDF | CLN-18.03 | QA: export matches on-screen rubrics + Rx; unauthorised doctor 403 | Regression | Patient Board | §5.3 | Export case data | Download the full case in Excel or PDF | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
198 | 198 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.19 | CLN-19 | Session restore — continue exactly where the doctor left off, across multiple patients (keep) | CLN-19.01 | Regression: backup, restore, 5-session stack | Existing | Patient Board | §5.3 | Session restore | Continue exactly where the doctor left off, across multiple patients | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
199 | 199 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.19 | CLN-19 | Session restore — continue exactly where the doctor left off, across multiple patients (keep) | CLN-19.02 | ACL: backup scoped to DoctorId | Existing Improvement | Patient Board | §5.3 | Session restore | Continue exactly where the doctor left off, across multiple patients | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
200 | 200 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.19 | CLN-19 | Session restore — continue exactly where the doctor left off, across multiple patients (keep) | CLN-19.03 | API: PatientBoardBackup on .NET 8 unchanged | Existing | Patient Board | §5.3 | Session restore | Continue exactly where the doctor left off, across multiple patients | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
201 | 201 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.20 | CLN-20 | 3D anatomy viewer — interactive 3D body model linked to rubric search (remaining ~50%) | CLN-20.01 | No new tables — Mesh/Section/Hotspot masters already exist | Existing Improvement | Anatomy | §5.3 | 3D anatomy viewer | Interactive 3D body model linked to rubric search | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
202 | 202 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.20 | CLN-20 | 3D anatomy viewer — interactive 3D body model linked to rubric search (remaining ~50%) | CLN-20.02 | Fix hotspot mapping gaps on newer threeDBodyPart APIs | Existing Improvement | Anatomy | §5.3 | 3D anatomy viewer | Interactive 3D body model linked to rubric search | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
203 | 203 | M03 | Doctor clinical workspace | UI | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.20 | CLN-20 | 3D anatomy viewer — interactive 3D body model linked to rubric search (remaining ~50%) | CLN-20.03 | Viewer UX: incomplete regions, loading, fallback message | Existing Improvement | Anatomy | §5.3 | 3D anatomy viewer | Interactive 3D body model linked to rubric search | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
204 | 204 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.20 | CLN-20 | 3D anatomy viewer — interactive 3D body model linked to rubric search (remaining ~50%) | CLN-20.04 | QA: click hotspot → subsection search results | Regression | Anatomy | §5.3 | 3D anatomy viewer | Interactive 3D body model linked to rubric search | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
205 | 205 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.1 | DOC-01 | Doctor home dashboard — complete overview of the working day (remaining ~30%) | DOC-01.01 | No new dashboard table | Existing Improvement | Doctor Dashboard | §5.1 | Doctor home dashboard | Complete overview of the working day | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
206 | 206 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.1 | DOC-01 | Doctor home dashboard — complete overview of the working day (remaining ~30%) | DOC-01.02 | Extend dashboard DTOs with paymentStatus / tele flags when columns exist (nullable until Phase 6/11) | Existing Improvement | Doctor Dashboard | §5.1 | Doctor home dashboard | Complete overview of the working day | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
207 | 207 | M04 | Doctor daily operations | UI | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.1 | DOC-01 | Doctor home dashboard — complete overview of the working day (remaining ~30%) | DOC-01.03 | Dashboard chrome: keep counts; add slots for Online toggle, tele queue, unpaid badge | Existing Improvement | Doctor Dashboard | §5.1 | Doctor home dashboard | Complete overview of the working day | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
208 | 208 | M04 | Doctor daily operations | QA | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.1 | DOC-01 | Doctor home dashboard — complete overview of the working day (remaining ~30%) | DOC-01.04 | QA: existing buckets still populate; reception still shares layout until Phase 5 reception chrome | Regression | Doctor Dashboard | §5.1 | Doctor home dashboard | Complete overview of the working day | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
209 | 209 | M04 | Doctor daily operations | QA | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.2 | DOC-02 | Patient counts & waiting list — live counts by status with quick actions (keep; extend paid/unpaid) | DOC-02.01 | Regression: each bucket count and click-through | Existing | Doctor Dashboard | §5.1 | Patient counts & waiting list | Live counts by status with quick actions | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
210 | 210 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.2 | DOC-02 | Patient counts & waiting list — live counts by status with quick actions (keep; extend paid/unpaid) | DOC-02.02 | Reception sharing this view is OK until Phase 5 splits chrome | Existing Improvement | Doctor Dashboard | §5.1 | Patient counts & waiting list | Live counts by status with quick actions | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
211 | 211 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.2 | DOC-02 | Patient counts & waiting list — live counts by status with quick actions (keep; extend paid/unpaid) | DOC-02.03 | API: existing dashboard count endpoints | Existing | Doctor Dashboard | §5.1 | Patient counts & waiting list | Live counts by status with quick actions | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
212 | 212 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.3 | DOC-03 | Patient search, list & open case (remaining ~10%) | DOC-03.01 | Use existing Patient + Appointment — add DTO fields | Existing Improvement | Doctor Dashboard | §5.1 | Patient search, list & open case | Find any patient and open their case instantly | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
213 | 213 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.3 | DOC-03 | Patient search, list & open case (remaining ~10%) | DOC-03.02 | Search DTO includes lastVisitAt | Existing Improvement | Doctor Dashboard | §5.1 | Patient search, list & open case | Find any patient and open their case instantly | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
214 | 214 | M04 | Doctor daily operations | UI | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.3 | DOC-03 | Patient search, list & open case (remaining ~10%) | DOC-03.03 | List columns: last visit; later payment/family | Existing Improvement | Doctor Dashboard | §5.1 | Patient search, list & open case | Find any patient and open their case instantly | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
215 | 215 | M04 | Doctor daily operations | QA | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.3 | DOC-03 | Patient search, list & open case (remaining ~10%) | DOC-03.04 | QA: search by name/mobile; open case | Regression | Doctor Dashboard | §5.1 | Patient search, list & open case | Find any patient and open their case instantly | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
216 | 216 | M04 | Doctor daily operations | QA | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.4 | DOC-04 | Add new patient — register a patient in seconds (keep) | DOC-04.01 | Regression: add patient validation and save | Existing | Patients | §5.1 | Add new patient | Register a patient in seconds | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
217 | 217 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.4 | DOC-04 | Add new patient — register a patient in seconds (keep) | DOC-04.02 | ACL: doctor/reception of that clinic only | Existing Improvement | Patients | §5.1 | Add new patient | Register a patient in seconds | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
218 | 218 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.4 | DOC-04 | Add new patient — register a patient in seconds (keep) | DOC-04.03 | API unchanged | Existing | Patients | §5.1 | Add new patient | Register a patient in seconds | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
219 | 219 | M04 | Doctor daily operations | QA | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.5 | DOC-05 | Import patients — bring existing patient records in bulk (keep) | DOC-05.01 | Regression: template + import + error rows | Existing | Patients | §5.1 | Import patients | Bring existing patient records in bulk | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
220 | 220 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.5 | DOC-05 | Import patients — bring existing patient records in bulk (keep) | DOC-05.02 | ACL doctor-only (or reception if already allowed) | Existing Improvement | Patients | §5.1 | Import patients | Bring existing patient records in bulk | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
221 | 221 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.5 | DOC-05 | Import patients — bring existing patient records in bulk (keep) | DOC-05.03 | API unchanged | Existing | Patients | §5.1 | Import patients | Bring existing patient records in bulk | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
222 | 222 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.6 | DOC-06 | Export patients — download patient data in Excel, CSV or PDF (keep) | DOC-06.01 | Audit current export formats; add PDF if only Excel/CSV exist today | Existing Improvement | Patients | §5.1 | Export patients | Download patient data in Excel, CSV or PDF | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
223 | 223 | M04 | Doctor daily operations | UI | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.6 | DOC-06 | Export patients — download patient data in Excel, CSV or PDF (keep) | DOC-06.02 | UI: Excel / CSV / PDF actions labelled as in the delivery document | Existing Improvement | Patients | §5.1 | Export patients | Download patient data in Excel, CSV or PDF | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
224 | 224 | M04 | Doctor daily operations | QA | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.6 | DOC-06 | Export patients — download patient data in Excel, CSV or PDF (keep) | DOC-06.03 | QA: another doctor cannot export this list | Regression | Patients | §5.1 | Export patients | Download patient data in Excel, CSV or PDF | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
225 | 225 | M04 | Doctor daily operations | QA | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.7 | DOC-07 | Recent activity panel (keep) | DOC-07.01 | Regression: activity loads | Existing | Doctor Dashboard | §5.1 | Recent activity panel | Everything that happened recently, at a glance | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
226 | 226 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.7 | DOC-07 | Recent activity panel (keep) | DOC-07.02 | ACL scoped to doctor | Existing Improvement | Doctor Dashboard | §5.1 | Recent activity panel | Everything that happened recently, at a glance | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
227 | 227 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.7 | DOC-07 | Recent activity panel (keep) | DOC-07.03 | API unchanged | Existing | Doctor Dashboard | §5.1 | Recent activity panel | Everything that happened recently, at a glance | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
228 | 228 | M04 | Doctor daily operations | QA | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.8 | DOC-08 | Patient statistics charts (keep; foundation for clinic performance in Phase 18) | DOC-08.01 | Regression: stats charts date range | Existing | Doctor Dashboard | §5.1 | Patient statistics charts | Visual practice statistics | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
229 | 229 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.8 | DOC-08 | Patient statistics charts (keep; foundation for clinic performance in Phase 18) | DOC-08.02 | ACL doctor-only | Existing Improvement | Doctor Dashboard | §5.1 | Patient statistics charts | Visual practice statistics | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
230 | 230 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.8 | DOC-08 | Patient statistics charts (keep; foundation for clinic performance in Phase 18) | DOC-08.03 | API unchanged | Existing | Doctor Dashboard | §5.1 | Patient statistics charts | Visual practice statistics | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
231 | 231 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.9 | DOC-09 | Manage reception staff — add, edit and remove reception users (backend done, UI absent) | DOC-09.01 | No new API — authorise that the doctor owns the staff record on existing CRUD | Existing Improvement | Staff | §5.1 | Manage reception staff | Add, edit and remove reception users | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
232 | 232 | M04 | Doctor daily operations | UI | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.9 | DOC-09 | Manage reception staff — add, edit and remove reception users (backend done, UI absent) | DOC-09.02 | Build /doctor/reception-staff list, add, edit, disable pages; menu entry in doctor chrome | Existing Improvement | Staff | §5.1 | Manage reception staff | Add, edit and remove reception users | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
233 | 233 | M04 | Doctor daily operations | QA | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.9 | DOC-09 | Manage reception staff — add, edit and remove reception users (backend done, UI absent) | DOC-09.03 | QA: reception user cannot manage other doctors’ staff; disable prevents login | Regression | Staff | §5.1 | Manage reception staff | Add, edit and remove reception users | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
234 | 234 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.10 | DOC-10 | Doctor profile — clinic details, consultation fee, photo, qualifications, working hours, bank details | DOC-10.01 | Extend Doctor / add DoctorPayeeKyc fields (bank, PAN) used later by Account; ConsultFeeConfig may wait until Phase 6 — store fee on profile now if simpler | Existing Improvement | Doctor Profile | §5.1 | Doctor profile | Clinic details, consultation fee, photo, qualifications, working hours, bank details | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
235 | 235 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.10 | DOC-10 | Doctor profile — clinic details, consultation fee, photo, qualifications, working hours, bank details | DOC-10.02 | GET/PUT /api/Profile/Me (doctor DTO); POST photo multipart; do not allow role escalation | Existing Improvement | Doctor Profile | §5.1 | Doctor profile | Clinic details, consultation fee, photo, qualifications, working hours, bank details | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
236 | 236 | M04 | Doctor daily operations | UI | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.10 | DOC-10 | Doctor profile — clinic details, consultation fee, photo, qualifications, working hours, bank details | DOC-10.03 | Replace Velzon /profile for doctor role with clinic/fee/photo/qualifications/hours/bank tabs | Existing Improvement | Doctor Profile | §5.1 | Doctor profile | Clinic details, consultation fee, photo, qualifications, working hours, bank details | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
237 | 237 | M04 | Doctor daily operations | QA | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.10 | DOC-10 | Doctor profile — clinic details, consultation fee, photo, qualifications, working hours, bank details | DOC-10.04 | QA: reception cannot edit doctor bank details; photo displays on public profile later | Regression | Doctor Profile | §5.1 | Doctor profile | Clinic details, consultation fee, photo, qualifications, working hours, bank details | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
238 | 238 | M05 | Appointments & scheduling | QA | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.1 | APT-01 | Appointment list & waiting patients — full day view with live status (keep; later payment/tele) | APT-01.01 | Regression: day list, status colour, open patient | Existing | Appointments | §5.2 | Appointment list & waiting patients | Full day view with live status | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
239 | 239 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.1 | APT-01 | Appointment list & waiting patients — full day view with live status (keep; later payment/tele) | APT-01.02 | ACL doctor/reception of that DoctorId | Existing Improvement | Appointments | §5.2 | Appointment list & waiting patients | Full day view with live status | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
240 | 240 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.1 | APT-01 | Appointment list & waiting patients — full day view with live status (keep; later payment/tele) | APT-01.03 | API unchanged | Existing | Appointments | §5.2 | Appointment list & waiting patients | Full day view with live status | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
241 | 241 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.2 | APT-02 | Create new appointment — persist visit type, consultation mode and fee | APT-02.01 | DB: PatientAppointment.VisitType, ConsultMode; migrate existing rows VisitType=First (do not infer retrospectively) | Existing Improvement | Appointments | §5.2 | Create new appointment | Book with visit type, consultation mode and fee | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
242 | 242 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.2 | APT-02 | Create new appointment — persist visit type, consultation mode and fee | APT-02.02 | API: create/update appointment accepts the new fields; PATCH VisitType | Existing Improvement | Appointments | §5.2 | Create new appointment | Book with visit type, consultation mode and fee | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
243 | 243 | M05 | Appointments & scheduling | UI | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.2 | APT-02 | Create new appointment — persist visit type, consultation mode and fee | APT-02.03 | Doctor/Reception new-appointment modal: visit type, consult mode, fee (placeholder until Phase 6 config) | Existing Improvement | Appointments | §5.2 | Create new appointment | Book with visit type, consultation mode and fee | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
244 | 244 | M05 | Appointments & scheduling | QA | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.2 | APT-02 | Create new appointment — persist visit type, consultation mode and fee | APT-02.04 | QA: staff-created appointments carry the same fields public booking will use in Phase 9 | Regression | Appointments | §5.2 | Create new appointment | Book with visit type, consultation mode and fee | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
245 | 245 | M05 | Appointments & scheduling | QA | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.3 | APT-03 | Appointment status update — move patients through the visit stages (keep) | APT-03.01 | Regression: each status transition | Existing | Appointments | §5.2 | Appointment status update | Move patients through the visit stages | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
246 | 246 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.3 | APT-03 | Appointment status update — move patients through the visit stages (keep) | APT-03.02 | ACL doctor/reception | Existing Improvement | Appointments | §5.2 | Appointment status update | Move patients through the visit stages | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
247 | 247 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.3 | APT-03 | Appointment status update — move patients through the visit stages (keep) | APT-03.03 | API unchanged | Existing | Appointments | §5.2 | Appointment status update | Move patients through the visit stages | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
248 | 248 | M05 | Appointments & scheduling | QA | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.4 | APT-04 | Appointment time update — adjust timings as the day runs (keep; distinct from formal reschedule) | APT-04.01 | Regression: UpdateAppointmentTime on dashboard | Existing | Appointments | §5.2 | Appointment time update | Adjust timings as the day runs | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
249 | 249 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.4 | APT-04 | Appointment time update — adjust timings as the day runs (keep; distinct from formal reschedule) | APT-04.02 | Document in UI that Reschedule is the patient-notified path | Existing Improvement | Appointments | §5.2 | Appointment time update | Adjust timings as the day runs | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
250 | 250 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.4 | APT-04 | Appointment time update — adjust timings as the day runs (keep; distinct from formal reschedule) | APT-04.03 | API: keep UpdateAppointmentTime; Reschedule wraps it | Existing | Appointments | §5.2 | Appointment time update | Adjust timings as the day runs | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
251 | 251 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.5 | APT-05 | Reschedule appointment — move to a new slot with automatic patient notification (NEW — not a rename of UpdateAppointmentTime) | APT-05.01 | DB: AppointmentChangeLog (PatientAppId, Action, OldValue, NewValue, ByUserId, ByRole, At) + indexes | New | Appointments | §5.2 + §2.3 + §6 | Reschedule appointment | Move to a new slot with automatic patient notification / Move to another slot without calling the clinic | Doctor Web + Reception + later Patient | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
252 | 252 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.5 | APT-05 | Reschedule appointment — move to a new slot with automatic patient notification (NEW — not a rename of UpdateAppointmentTime) | APT-05.02 | API: POST /api/PatientAppointment/RescheduleAppointment — validate schedule, bookings, not in the past; 409 with alternatives; wrap UpdateAppointmentTime; GET ChangeLog/{id} | New | Appointments | §5.2 + §2.3 + §6 | Reschedule appointment | Move to a new slot with automatic patient notification / Move to another slot without calling the clinic | Doctor Web + Reception + later Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
253 | 253 | M05 | Appointments & scheduling | UI | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.5 | APT-05 | Reschedule appointment — move to a new slot with automatic patient notification (NEW — not a rename of UpdateAppointmentTime) | APT-05.03 | UI: RescheduleModal shared by Doctor and Reception — old date/time + new slot picker; reason optional | New | Appointments | §5.2 + §2.3 + §6 | Reschedule appointment | Move to a new slot with automatic patient notification / Move to another slot without calling the clinic | Doctor Web + Reception + later Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
254 | 254 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.5 | APT-05 | Reschedule appointment — move to a new slot with automatic patient notification (NEW — not a rename of UpdateAppointmentTime) | APT-05.04 | Notifications: SMS + WhatsApp + (later) push — old→new; must not block the transaction if notify fails | New Integration | Appointments | §5.2 + §2.3 + §6 | Reschedule appointment | Move to a new slot with automatic patient notification / Move to another slot without calling the clinic | Doctor Web + Reception + later Patient | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
255 | 255 | M05 | Appointments & scheduling | QA | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.5 | APT-05 | Reschedule appointment — move to a new slot with automatic patient notification (NEW — not a rename of UpdateAppointmentTime) | APT-05.05 | QA: slot taken → 409; patient already booked elsewhere; across a schedule change; reception authorised for own DoctorId only | Regression | Appointments | §5.2 + §2.3 + §6 | Reschedule appointment | Move to a new slot with automatic patient notification / Move to another slot without calling the clinic | Doctor Web + Reception + later Patient | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
256 | 256 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.6 | APT-06 | Cancel appointment — reason, free the slot, trigger refund where applicable (NEW CANCELLED status — do NOT reuse DeleteStatus) | APT-06.01 | DB: add CANCELLED to status set; CancelReasonCode, CancelReasonText, CancelledBy, CancelledAt; DeleteStatus remains administrative | New | Appointments | §5.2 + §2.3 + §6 | Cancel appointment | Cancel with reason, free the slot, trigger refund where applicable / Cancel with reason, refund handled per policy | Doctor Web + Reception + later Patient | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
257 | 257 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.6 | APT-06 | Cancel appointment — reason, free the slot, trigger refund where applicable (NEW CANCELLED status — do NOT reuse DeleteStatus) | APT-06.02 | API: POST /api/PatientAppointment/CancelAppointment — reason required (enum; text if Other); free slot; offer waitlist stub; if PAID enqueue refund policy | New | Appointments | §5.2 + §2.3 + §6 | Cancel appointment | Cancel with reason, free the slot, trigger refund where applicable / Cancel with reason, refund handled per policy | Doctor Web + Reception + later Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
258 | 258 | M05 | Appointments & scheduling | UI | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.6 | APT-06 | Cancel appointment — reason, free the slot, trigger refund where applicable (NEW CANCELLED status — do NOT reuse DeleteStatus) | APT-06.03 | UI: CancelAppointmentModal shared by Doctor and Reception; dashboard Cancelled filter | New | Appointments | §5.2 + §2.3 + §6 | Cancel appointment | Cancel with reason, free the slot, trigger refund where applicable / Cancel with reason, refund handled per policy | Doctor Web + Reception + later Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
259 | 259 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.6 | APT-06 | Cancel appointment — reason, free the slot, trigger refund where applicable (NEW CANCELLED status — do NOT reuse DeleteStatus) | APT-06.04 | Waitlist worker stub: on cancel, offer freed slot (full waitlist capture is Phase 9 GST waitlist) | New Integration | Appointments | §5.2 + §2.3 + §6 | Cancel appointment | Cancel with reason, free the slot, trigger refund where applicable / Cancel with reason, refund handled per policy | Doctor Web + Reception + later Patient | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
260 | 260 | M05 | Appointments & scheduling | QA | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.6 | APT-06 | Cancel appointment — reason, free the slot, trigger refund where applicable (NEW CANCELLED status — do NOT reuse DeleteStatus) | APT-06.05 | QA: reason mandatory; all three roles (later Patient) cancel with correct authorisation; freed slot bookable | Regression | Appointments | §5.2 + §2.3 + §6 | Cancel appointment | Cancel with reason, free the slot, trigger refund where applicable / Cancel with reason, refund handled per policy | Doctor Web + Reception + later Patient | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
261 | 261 | M05 | Appointments & scheduling | UI | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.7 | APT-07 | Daily schedule setup — define working days, hours and break times (promote modal to first-class screen) | APT-07.01 | Promote DailyScheduleSetupModal to /doctor/schedule; week grid; copy-day; reuse Get/SaveDailySchedule | Existing Improvement | Scheduling | §5.2 | Daily schedule setup | Define working days, hours and break times | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
262 | 262 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.7 | APT-07 | Daily schedule setup — define working days, hours and break times (promote modal to first-class screen) | APT-07.02 | No new API unless validation (breaks, overlapping hours) is missing — add server-side validation | Existing Improvement | Scheduling | §5.2 | Daily schedule setup | Define working days, hours and break times | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
263 | 263 | M05 | Appointments & scheduling | QA | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.7 | APT-07 | Daily schedule setup — define working days, hours and break times (promote modal to first-class screen) | APT-07.03 | QA: save week; public slot generator (Phase 9) uses this data; reception read-only is Phase 5 | Regression | Scheduling | §5.2 | Daily schedule setup | Define working days, hours and break times | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
264 | 264 | M05 | Appointments & scheduling | QA | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.8 | APT-08 | Appointment slot grid — visual slot-by-slot view of the day (keep; public booking reuses this) | APT-08.01 | Regression: slot grid vs schedule | Existing | Scheduling | §5.2 | Appointment slot grid | Visual slot-by-slot view of the day | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
265 | 265 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.8 | APT-08 | Appointment slot grid — visual slot-by-slot view of the day (keep; public booking reuses this) | APT-08.02 | ACL doctor/reception | Existing Improvement | Scheduling | §5.2 | Appointment slot grid | Visual slot-by-slot view of the day | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
266 | 266 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.8 | APT-08 | Appointment slot grid — visual slot-by-slot view of the day (keep; public booking reuses this) | APT-08.03 | Document GetAppointmentSlots as the public-booking engine — do not fork a second slot calculator | Existing | Scheduling | §5.2 | Appointment slot grid | Visual slot-by-slot view of the day | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
267 | 267 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.9 | APT-09 | Consultation payment status on every appointment (schema now; values live in Phase 6) | APT-09.01 | DB: PatientAppointment.PaymentStatus, PaymentMethod, PayAtClinicAllowed; default UNPAID | New | Appointments | §5.2 + §9 | Consultation payment status | See paid, unpaid or pay-at-clinic on every appointment / Doctor, reception and patient all see the same payment status | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
268 | 268 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.9 | APT-09 | Consultation payment status on every appointment (schema now; values live in Phase 6) | APT-09.02 | API: include PaymentStatus on all appointment DTOs (doctor, reception, later public/patient) | New | Appointments | §5.2 + §9 | Consultation payment status | See paid, unpaid or pay-at-clinic on every appointment / Doctor, reception and patient all see the same payment status | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
269 | 269 | M05 | Appointments & scheduling | UI | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.9 | APT-09 | Consultation payment status on every appointment (schema now; values live in Phase 6) | APT-09.03 | UI: Paid / Unpaid / Pay-at-clinic / Failed badges on doctor appointment list | New | Appointments | §5.2 + §9 | Consultation payment status | See paid, unpaid or pay-at-clinic on every appointment / Doctor, reception and patient all see the same payment status | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
270 | 270 | M05 | Appointments & scheduling | QA | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.9 | APT-09 | Consultation payment status on every appointment (schema now; values live in Phase 6) | APT-09.04 | QA: same appointment shows the same badge on doctor and reception | Regression | Appointments | §5.2 + §9 | Consultation payment status | See paid, unpaid or pay-at-clinic on every appointment / Doctor, reception and patient all see the same payment status | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
271 | 454 | M05 | Appointments & scheduling | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.11 | WEB-11 | Waitlist offer — get offered a slot when one is freed by a cancellation (patient website + later app) | WEB-11.01 | DB: BookingWaitlist | New | Booking | §2.3 | Waitlist offer | Get offered a slot when one is freed by a cancellation | Patient Website + App | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
272 | 455 | M05 | Appointments & scheduling | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.11 | WEB-11 | Waitlist offer — get offered a slot when one is freed by a cancellation (patient website + later app) | WEB-11.02 | API: join waitlist; worker on CancelAppointment | New | Booking | §2.3 | Waitlist offer | Get offered a slot when one is freed by a cancellation | Patient Website + App | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
273 | 456 | M05 | Appointments & scheduling | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.11 | WEB-11 | Waitlist offer — get offered a slot when one is freed by a cancellation (patient website + later app) | WEB-11.03 | Public waitlist CTA on full days | New | Booking | §2.3 | Waitlist offer | Get offered a slot when one is freed by a cancellation | Patient Website + App | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
274 | 457 | M05 | Appointments & scheduling | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.11 | WEB-11 | Waitlist offer — get offered a slot when one is freed by a cancellation (patient website + later app) | WEB-11.04 | Notify SMS/push when Phase 12 exists | New Integration | Booking | §2.3 | Waitlist offer | Get offered a slot when one is freed by a cancellation | Patient Website + App | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
275 | 458 | M05 | Appointments & scheduling | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.11 | WEB-11 | Waitlist offer — get offered a slot when one is freed by a cancellation (patient website + later app) | WEB-11.05 | QA: two waiters; first gets offer; expiry releases to second | Regression | Booking | §2.3 | Waitlist offer | Get offered a slot when one is freed by a cancellation | Patient Website + App | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
276 | 672 | M05 | Appointments & scheduling | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.9 | CON-09 | Physical clinic appointment — book an in-person visit as well as online | CON-09.01 | Public/patient create booking accepts ConsultMode=In-clinic; uses in-clinic fee | Existing Improvement | Booking | §2.9 + §5.2 | Physical clinic appointment | Book an in-person visit as well as online | Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
277 | 673 | M05 | Appointments & scheduling | QA | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.9 | CON-09 | Physical clinic appointment — book an in-person visit as well as online | CON-09.02 | QA: in-clinic does not require device check/video | Regression | Booking | §2.9 + §5.2 | Physical clinic appointment | Book an in-person visit as well as online | Patient | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
278 | 271 | M06 | Reception portal | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.1 | REC-01 | Reception login — secure staff access (keep) | REC-01.01 | Regression: reception login with DoctorID claim | Existing | Reception | §6 | Reception login | Secure staff access | Reception Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
279 | 272 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.1 | REC-01 | Reception login — secure staff access (keep) | REC-01.02 | Disabled staff cannot login (after DOC-09) | Existing Improvement | Reception | §6 | Reception login | Secure staff access | Reception Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
280 | 273 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.1 | REC-01 | Reception login — secure staff access (keep) | REC-01.03 | Same Login API as doctor | Existing | Reception | §6 | Reception login | Secure staff access | Reception Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
281 | 274 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.2 | REC-02 | Reception profile — manage own profile details (0% today) | REC-02.01 | Reuse Profile/Me with role=Reception DTO (no new table if UserMaster suffices) | New | Reception | §6 | Reception profile | Manage own profile details | Reception Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
282 | 275 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.2 | REC-02 | Reception profile — manage own profile details (0% today) | REC-02.02 | GET/PUT profile fields allowed for reception; ignore clinic fee/bank | New | Reception | §6 | Reception profile | Manage own profile details | Reception Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
283 | 276 | M06 | Reception portal | UI | 5 | Phase 5 — Reception portal (PDF §6) | 5.2 | REC-02 | Reception profile — manage own profile details (0% today) | REC-02.03 | /profile reception variant | New | Reception | §6 | Reception profile | Manage own profile details | Reception Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
284 | 277 | M06 | Reception portal | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.2 | REC-02 | Reception profile — manage own profile details (0% today) | REC-02.04 | QA: cannot edit doctor qualifications or fee | Regression | Reception | §6 | Reception profile | Manage own profile details | Reception Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
285 | 278 | M06 | Reception portal | UI | 5 | Phase 5 — Reception portal (PDF §6) | 5.3 | REC-03 | Reception home dashboard — purpose-built front-desk dashboard (not only hidden doctor actions) | REC-03.01 | Route /reception (or role-based chrome on existing dashboard) hiding clinical tabs | Existing Improvement | Reception | §6 | Reception home dashboard | Purpose-built front-desk dashboard | Reception Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
286 | 279 | M06 | Reception portal | UI | 5 | Phase 5 — Reception portal (PDF §6) | 5.3 | REC-03 | Reception home dashboard — purpose-built front-desk dashboard (not only hidden doctor actions) | REC-03.02 | Quick actions: new patient, new appointment, collect payment, case paper, schedule | Existing Improvement | Reception | §6 | Reception home dashboard | Purpose-built front-desk dashboard | Reception Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
287 | 280 | M06 | Reception portal | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.3 | REC-03 | Reception home dashboard — purpose-built front-desk dashboard (not only hidden doctor actions) | REC-03.03 | QA: deep-link to Patient Board full clinical URL is 403 for reception | Regression | Reception | §6 | Reception home dashboard | Purpose-built front-desk dashboard | Reception Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
288 | 281 | M06 | Reception portal | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.4 | REC-04 | Create patient — register a walk-in patient quickly (keep) | REC-04.01 | Regression: reception create patient | Existing | Reception | §6 | Create patient | Register a walk-in patient quickly | Reception Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
289 | 282 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.4 | REC-04 | Create patient — register a walk-in patient quickly (keep) | REC-04.02 | ACL: own doctor only | Existing Improvement | Reception | §6 | Create patient | Register a walk-in patient quickly | Reception Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
290 | 283 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.4 | REC-04 | Create patient — register a walk-in patient quickly (keep) | REC-04.03 | Same create-patient API | Existing | Reception | §6 | Create patient | Register a walk-in patient quickly | Reception Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
291 | 284 | M06 | Reception portal | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.5 | REC-05 | Patient search & list — find any patient instantly (keep) | REC-05.01 | Regression: search by name/mobile | Existing | Reception | §6 | Patient search & list | Find any patient instantly | Reception Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
292 | 285 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.5 | REC-05 | Patient search & list — find any patient instantly (keep) | REC-05.02 | Opening a row goes to case paper or appointment, not full repertory | Existing Improvement | Reception | §6 | Patient search & list | Find any patient instantly | Reception Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
293 | 286 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.5 | REC-05 | Patient search & list — find any patient instantly (keep) | REC-05.03 | API unchanged | Existing | Reception | §6 | Patient search & list | Find any patient instantly | Reception Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
294 | 287 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.6 | REC-06 | Create & manage appointments — full appointment management (keep; plus reschedule/cancel from Phase 4) | REC-06.01 | Authorise Reception for Reschedule and Cancel for its own doctor's appointments only | New | Reception | §6 | Create & manage appointments | Full appointment management | Reception Portal | API + SPA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
295 | 288 | M06 | Reception portal | UI | 5 | Phase 5 — Reception portal (PDF §6) | 5.6 | REC-06 | Create & manage appointments — full appointment management (keep; plus reschedule/cancel from Phase 4) | REC-06.02 | Reception UI uses the same Reschedule/Cancel modals as doctor | New | Reception | §6 | Create & manage appointments | Full appointment management | Reception Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
296 | 289 | M06 | Reception portal | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.6 | REC-06 | Create & manage appointments — full appointment management (keep; plus reschedule/cancel from Phase 4) | REC-06.03 | QA: cannot cancel another clinic’s appointment | Regression | Reception | §6 | Create & manage appointments | Full appointment management | Reception Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
297 | 290 | M06 | Reception portal | UI | 5 | Phase 5 — Reception portal (PDF §6) | 5.7 | REC-07 | New appointment — book on behalf of the patient (keep; same VisitType/ConsultMode/fee as APT-02) | REC-07.01 | Share the extended new-appointment modal with reception chrome | Existing Improvement | Reception | §6 | New appointment | Book on behalf of the patient | Reception Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
298 | 291 | M06 | Reception portal | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.7 | REC-07 | New appointment — book on behalf of the patient (keep; same VisitType/ConsultMode/fee as APT-02) | REC-07.02 | QA: in-clinic vs E-Consult both creatable from reception | Regression | Reception | §6 | New appointment | Book on behalf of the patient | Reception Portal | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
299 | 292 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.8 | REC-08 | Waiting queue management — manage the live queue and call the next patient | REC-08.01 | No new table required if status+order suffice; optional QueuePosition | Existing Improvement | Reception | §6 | Waiting queue management | Manage the live queue and call the next patient | Reception Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
300 | 293 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.8 | REC-08 | Waiting queue management — manage the live queue and call the next patient | REC-08.02 | Optional CallNext API that sets status and timestamp | Existing Improvement | Reception | §6 | Waiting queue management | Manage the live queue and call the next patient | Reception Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
301 | 294 | M06 | Reception portal | UI | 5 | Phase 5 — Reception portal (PDF §6) | 5.8 | REC-08 | Waiting queue management — manage the live queue and call the next patient | REC-08.03 | Queue panel: order, wait time, paid/unpaid, Call next | Existing Improvement | Reception | §6 | Waiting queue management | Manage the live queue and call the next patient | Reception Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
302 | 295 | M06 | Reception portal | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.8 | REC-08 | Waiting queue management — manage the live queue and call the next patient | REC-08.04 | QA: two waiting patients; call next picks the right one | Regression | Reception | §6 | Waiting queue management | Manage the live queue and call the next patient | Reception Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
303 | 296 | M06 | Reception portal | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.9 | REC-09 | Appointment status update (reception) — update as patients arrive and are seen (keep) | REC-09.01 | Regression: reception status update | Existing | Reception | §6 | Appointment status update | Update as patients arrive and are seen | Reception Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
304 | 297 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.9 | REC-09 | Appointment status update (reception) — update as patients arrive and are seen (keep) | REC-09.02 | ACL own doctor | Existing Improvement | Reception | §6 | Appointment status update | Update as patients arrive and are seen | Reception Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
305 | 298 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.9 | REC-09 | Appointment status update (reception) — update as patients arrive and are seen (keep) | REC-09.03 | Same status API as doctor | Existing | Reception | §6 | Appointment status update | Update as patients arrive and are seen | Reception Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
306 | 299 | M06 | Reception portal | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.10 | REC-10 | Appointment time update (reception) — adjust timings through the day (keep) | REC-10.01 | Regression: reception UpdateAppointmentTime | Existing | Reception | §6 | Appointment time update | Adjust timings through the day | Reception Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
307 | 300 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.10 | REC-10 | Appointment time update (reception) — adjust timings through the day (keep) | REC-10.02 | ACL own doctor | Existing Improvement | Reception | §6 | Appointment time update | Adjust timings through the day | Reception Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
308 | 301 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.10 | REC-10 | Appointment time update (reception) — adjust timings through the day (keep) | REC-10.03 | Same API | Existing | Reception | §6 | Appointment time update | Adjust timings through the day | Reception Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
309 | 302 | M06 | Reception portal | UI | 5 | Phase 5 — Reception portal (PDF §6) | 5.11 | REC-11 | View doctor schedule — see the doctor’s working schedule (read-only) | REC-11.01 | Frontend only over existing GetDailySchedule — /reception/schedule read-only | New | Reception | §6 | View doctor schedule | See the doctor’s working schedule | Reception Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
310 | 303 | M06 | Reception portal | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.11 | REC-11 | View doctor schedule — see the doctor’s working schedule (read-only) | REC-11.02 | QA: edit buttons hidden; doctor can still edit on /doctor/schedule | Regression | Reception | §6 | View doctor schedule | See the doctor’s working schedule | Reception Portal | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
311 | 304 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.12 | REC-12 | Log case paper / chief complaint — record the reason for visit before the consultation | REC-12.01 | Reuse complaints table; add CreatedByRole=Reception | New | Reception | §6 | Log case paper / chief complaint | Record the reason for visit before the consultation | Reception Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
312 | 305 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.12 | REC-12 | Log case paper / chief complaint — record the reason for visit before the consultation | REC-12.02 | POST case-paper subset of SaveComplaints; GET on board | New | Reception | §6 | Log case paper / chief complaint | Record the reason for visit before the consultation | Reception Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
313 | 306 | M06 | Reception portal | UI | 5 | Phase 5 — Reception portal (PDF §6) | 5.12 | REC-12 | Log case paper / chief complaint — record the reason for visit before the consultation | REC-12.03 | /reception/case-paper or limited board | New | Reception | §6 | Log case paper / chief complaint | Record the reason for visit before the consultation | Reception Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
314 | 307 | M06 | Reception portal | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.12 | REC-12 | Log case paper / chief complaint — record the reason for visit before the consultation | REC-12.04 | QA: doctor sees CC; reception 403 on repertory APIs | Regression | Reception | §6 | Log case paper / chief complaint | Record the reason for visit before the consultation | Reception Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
315 | 308 | M06 | Reception portal | UI | 5 | Phase 5 — Reception portal (PDF §6) | 5.13 | REC-13 | Collect consultation payment — cash, UPI, card or payment link and issue a receipt (API in Phase 6; UI shell now) | REC-13.01 | Specify receipt fields (amount, method, appointment, GST placeholder) for Phase 6 implementation | New | Reception | §6 + §9 | Collect consultation payment | Take cash, UPI, card or payment link and issue a receipt | Reception Portal | Design | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
316 | 309 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.13 | REC-13 | Collect consultation payment — cash, UPI, card or payment link and issue a receipt (API in Phase 6; UI shell now) | REC-13.02 | Do not write PaymentStatus=PAID from the client — Account/webhook is source of truth (Phase 6) | New | Reception | §6 + §9 | Collect consultation payment | Take cash, UPI, card or payment link and issue a receipt | Reception Portal | Architecture | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
317 | 310 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.1 | PAY-01 | Consultation fee configuration — each doctor’s fee set and displayed to patients | PAY-01.01 | DB: ConsultFeeConfig (DoctorId, InClinicFee, TeleFee, InstantSurcharge, Currency, PayAtClinicEnabled, EffectiveFrom) | New | Payments | §9 | Consultation fee configuration | Each doctor’s fee set and displayed to patients | Doctor profile + Public + Admin | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
318 | 311 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.1 | PAY-01 | Consultation fee configuration — each doctor’s fee set and displayed to patients | PAY-01.02 | API: GET public fee; PUT doctor/admin; history of changes in audit | New | Payments | §9 | Consultation fee configuration | Each doctor’s fee set and displayed to patients | Doctor profile + Public + Admin | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
319 | 312 | M07 | Payment system | UI | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.1 | PAY-01 | Consultation fee configuration — each doctor’s fee set and displayed to patients | PAY-01.03 | Doctor profile fee tab + later public doctor card | New | Payments | §9 | Consultation fee configuration | Each doctor’s fee set and displayed to patients | Doctor profile + Public + Admin | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
320 | 313 | M07 | Payment system | QA | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.1 | PAY-01 | Consultation fee configuration — each doctor’s fee set and displayed to patients | PAY-01.04 | QA: changing fee does not alter already-created unpaid orders without a rule (document the rule) | Regression | Payments | §9 | Consultation fee configuration | Each doctor’s fee set and displayed to patients | Doctor profile + Public + Admin | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
321 | 314 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.2 | PAY-02 | Automatic payment verification — bank/webhook is source of truth, not the patient’s screen | PAY-02.01 | DB: PaymentOrder, PaymentEvent (raw webhook), idempotency key on payment_id | New | Payments | §9 | Automatic payment verification | Payments confirmed by the bank, not by the patient’s screen — nothing is lost if the app or browser closes | Shared | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
322 | 315 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.2 | PAY-02 | Automatic payment verification — bank/webhook is source of truth, not the patient’s screen | PAY-02.02 | Port Order/GenerateOrderId pattern to .NET 8; move keys to configuration; do not commit secrets | New Integration | Payments | §9 | Automatic payment verification | Payments confirmed by the bank, not by the patient’s screen — nothing is lost if the app or browser closes | Shared | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
323 | 316 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.2 | PAY-02 | Automatic payment verification — bank/webhook is source of truth, not the patient’s screen | PAY-02.03 | Webhook handler payment.captured / payment.failed; signature verify; never trust client-only success | New Integration | Payments | §9 | Automatic payment verification | Payments confirmed by the bank, not by the patient’s screen — nothing is lost if the app or browser closes | Shared | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
324 | 317 | M07 | Payment system | QA | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.2 | PAY-02 | Automatic payment verification — bank/webhook is source of truth, not the patient’s screen | PAY-02.04 | QA: duplicate webhook; delayed webhook; failed capture; app closed mid-checkout | Regression | Payments | §9 | Automatic payment verification | Payments confirmed by the bank, not by the patient’s screen — nothing is lost if the app or browser closes | Shared | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | 2 | Not Started |  | Edit on module sheet
325 | 318 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.3 | PAY-03 | Online consultation payment — patient pays by card, UPI, netbanking or wallet | PAY-03.01 | DB: ConsultPayment linked to PaymentOrder + PatientAppId — NOT PackageEntryDetail | New | Payments | §9 + §4 + §2.3 | Online consultation payment | Patient pays by card, UPI, netbanking or wallet / Pay the consultation fee at the time of booking / Pay the consultation fee inside the app | Public web + later Patient app | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
326 | 319 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.3 | PAY-03 | Online consultation payment — patient pays by card, UPI, netbanking or wallet | PAY-03.02 | API: CreateConsultOrder, Verify (optional), status by appointment; amount from ConsultFeeConfig | New | Payments | §9 + §4 + §2.3 | Online consultation payment | Patient pays by card, UPI, netbanking or wallet / Pay the consultation fee at the time of booking / Pay the consultation fee inside the app | Public web + later Patient app | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
327 | 320 | M07 | Payment system | UI | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.3 | PAY-03 | Online consultation payment — patient pays by card, UPI, netbanking or wallet | PAY-03.03 | Public /book/pay/:bookingId using Razorpay pattern from Widgets.js but consult order API | New | Payments | §9 + §4 + §2.3 | Online consultation payment | Patient pays by card, UPI, netbanking or wallet / Pay the consultation fee at the time of booking / Pay the consultation fee inside the app | Public web + later Patient app | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
328 | 321 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.3 | PAY-03 | Online consultation payment — patient pays by card, UPI, netbanking or wallet | PAY-03.04 | Razorpay Checkout methods: card, UPI, netbanking, wallet as enabled on the account | New Integration | Payments | §9 + §4 + §2.3 | Online consultation payment | Patient pays by card, UPI, netbanking or wallet / Pay the consultation fee at the time of booking / Pay the consultation fee inside the app | Public web + later Patient app | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
329 | 322 | M07 | Payment system | QA | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.3 | PAY-03 | Online consultation payment — patient pays by card, UPI, netbanking or wallet | PAY-03.05 | QA: success, failure, pending, double-click create order idempotent | Regression | Payments | §9 + §4 + §2.3 | Online consultation payment | Patient pays by card, UPI, netbanking or wallet / Pay the consultation fee at the time of booking / Pay the consultation fee inside the app | Public web + later Patient app | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
330 | 323 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.4 | PAY-04 | Reception payment collection — cash, UPI, card or payment link with printed receipt | PAY-04.01 | Reuse PaymentOrder + ConsultPayment with Method=CASH/UPI_OFFLINE/CARD_POS/PAY_LINK | New | Payments | §9 + §6 | Reception payment collection | Cash, UPI, card or payment link with printed receipt | Reception Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
331 | 324 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.4 | PAY-04 | Reception payment collection — cash, UPI, card or payment link with printed receipt | PAY-04.02 | API: CollectAtReception; generate pay-link; print receipt payload | New | Payments | §9 + §6 | Reception payment collection | Cash, UPI, card or payment link with printed receipt | Reception Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
332 | 325 | M07 | Payment system | UI | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.4 | PAY-04 | Reception payment collection — cash, UPI, card or payment link with printed receipt | PAY-04.03 | Reception collect modal: amount, method, GST placeholder, print receipt | New | Payments | §9 + §6 | Reception payment collection | Cash, UPI, card or payment link with printed receipt | Reception Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
333 | 326 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.4 | PAY-04 | Reception payment collection — cash, UPI, card or payment link with printed receipt | PAY-04.04 | Pay-link SMS/WhatsApp optional (Phase 12); must still ledger if notify fails | New Integration | Payments | §9 + §6 | Reception payment collection | Cash, UPI, card or payment link with printed receipt | Reception Portal | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
334 | 327 | M07 | Payment system | QA | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.4 | PAY-04 | Reception payment collection — cash, UPI, card or payment link with printed receipt | PAY-04.05 | QA: cash collection visible in clinic collection view after Phase 7; cannot mark PAID without this API | Regression | Payments | §9 + §6 | Reception payment collection | Cash, UPI, card or payment link with printed receipt | Reception Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
335 | 328 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.5 | PAY-05 | Pay-at-clinic option — book now, pay at the clinic where the doctor allows it | PAY-05.01 | Honor PayAtClinicEnabled on public create-booking and checkout | New | Payments | §9 | Pay-at-clinic option | Book now, pay at the clinic where the doctor allows it | Public + Doctor + Reception | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
336 | 329 | M07 | Payment system | UI | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.5 | PAY-05 | Pay-at-clinic option — book now, pay at the clinic where the doctor allows it | PAY-05.02 | UI: public booking shows Pay at clinic vs Pay now; doctor list badge | New | Payments | §9 | Pay-at-clinic option | Book now, pay at the clinic where the doctor allows it | Public + Doctor + Reception | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
337 | 330 | M07 | Payment system | QA | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.5 | PAY-05 | Pay-at-clinic option — book now, pay at the clinic where the doctor allows it | PAY-05.03 | QA: doctor flag off → pay-at-clinic hidden; reception can still collect | Regression | Payments | §9 | Pay-at-clinic option | Book now, pay at the clinic where the doctor allows it | Public + Doctor + Reception | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
338 | 331 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.6 | PAY-06 | Doctor subscription payment — buy and renew subscription packages (complete remaining ~30%) | PAY-06.01 | Reuse PAY-02 webhook for S1 orders; link PackageEntryDetail as S1 only | Existing Improvement | Payments | §9 | Doctor subscription payment | Buy and renew subscription packages | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | 2 | Not Started |  | Edit on module sheet
339 | 332 | M07 | Payment system | UI | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.6 | PAY-06 | Doctor subscription payment — buy and renew subscription packages (complete remaining ~30%) | PAY-06.02 | Widgets.js: handle failed pay; show invoice when Phase 7 invoice exists | Existing Improvement | Payments | §9 | Doctor subscription payment | Buy and renew subscription packages | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
340 | 333 | M07 | Payment system | QA | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.6 | PAY-06 | Doctor subscription payment — buy and renew subscription packages (complete remaining ~30%) | PAY-06.03 | QA: renew, fail, webhook delay, last-5-days warning still works | Regression | Payments | §9 | Doctor subscription payment | Buy and renew subscription packages | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
341 | 334 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.7 | PAY-07 | Medicine payment — pay online or cash on delivery (API contract now; HomeoMeds Phase 14 implements orders) | PAY-07.01 | Extend PaymentOrder with Stream=CONSULT¦SUBSCRIPTION¦MEDICINE so Phase 14 can attach without schema rewrite | New | Payments | §9 + §12 | Medicine payment | Pay online or choose cash on delivery / Both options supported, with status tracking | Shared | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
342 | 335 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.7 | PAY-07 | Medicine payment — pay online or cash on delivery (API contract now; HomeoMeds Phase 14 implements orders) | PAY-07.02 | API stub: CreateMedicineOrder payment + COD status enum — implemented fully in Phase 14 | New | Payments | §9 + §12 | Medicine payment | Pay online or choose cash on delivery / Both options supported, with status tracking | Shared | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
343 | 336 | M07 | Payment system | QA | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.7 | PAY-07 | Medicine payment — pay online or cash on delivery (API contract now; HomeoMeds Phase 14 implements orders) | PAY-07.03 | QA: stream isolation query (consult vs medicine totals differ) | Regression | Payments | §9 + §12 | Medicine payment | Pay online or choose cash on delivery / Both options supported, with status tracking | Shared | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
344 | 337 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.8 | PAY-08 | Payment status everywhere — doctor, reception and patient all see the same payment status | PAY-08.01 | Single source: PaymentOrder/ConsultPayment → Appointment.PaymentStatus updated only by webhook or CollectAtReception | New | Payments | §9 | Payment status everywhere | Doctor, reception and patient all see the same payment status | All | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
345 | 338 | M07 | Payment system | UI | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.8 | PAY-08 | Payment status everywhere — doctor, reception and patient all see the same payment status | PAY-08.02 | Surface badges: doctor, reception; public confirmation page; patient app in Phase 16 consumes same API | New | Payments | §9 | Payment status everywhere | Doctor, reception and patient all see the same payment status | All | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
346 | 339 | M07 | Payment system | QA | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.8 | PAY-08 | Payment status everywhere — doctor, reception and patient all see the same payment status | PAY-08.03 | QA: three roles, one appointment, same enum value | Regression | Payments | §9 | Payment status everywhere | Doctor, reception and patient all see the same payment status | All | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
347 | 340 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.9 | PAY-09 | Refunds — processed and tracked against the original payment | PAY-09.01 | DB: Refund (PaymentOrderId, Amount, Reason, Status, GatewayRefundId, ByUserId, At) | New | Payments | §9 + §8 + §2.8 | Refunds | Processed and tracked against the original payment / Issue and track refunds | Account + Patient | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
348 | 341 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.9 | PAY-09 | Refunds — processed and tracked against the original payment | PAY-09.02 | API: create refund (Account); webhook refund.processed; cancel-appointment policy engine (full/partial/none) | New | Payments | §9 + §8 + §2.8 | Refunds | Processed and tracked against the original payment / Issue and track refunds | Account + Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
349 | 342 | M07 | Payment system | UI | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.9 | PAY-09 | Refunds — processed and tracked against the original payment | PAY-09.03 | Account refund screen in Phase 7; patient payments list in Phase 16 | New | Payments | §9 + §8 + §2.8 | Refunds | Processed and tracked against the original payment / Issue and track refunds | Account + Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
350 | 343 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.9 | PAY-09 | Refunds — processed and tracked against the original payment | PAY-09.04 | Razorpay refund API + webhook | New Integration | Payments | §9 + §8 + §2.8 | Refunds | Processed and tracked against the original payment / Issue and track refunds | Account + Patient | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
351 | 344 | M07 | Payment system | QA | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.9 | PAY-09 | Refunds — processed and tracked against the original payment | PAY-09.05 | QA: double refund blocked; cash collection refund is ledger-only per PRE-02 policy | Regression | Payments | §9 + §8 + §2.8 | Refunds | Processed and tracked against the original payment / Issue and track refunds | Account + Patient | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
352 | 345 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.10 | PAY-10 | Payment receipts & invoices — issued for every transaction | PAY-10.01 | DB: Invoice (Number, Series, Stream, PaymentOrderId, GstBreakup, PdfPath) | New | Payments | §9 + §8 | Payment receipts & invoices | Issued for every transaction / Invoice numbering and tax reporting | All | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
353 | 346 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.10 | PAY-10 | Payment receipts & invoices — issued for every transaction | PAY-10.02 | API: get invoice by payment; generate PDF via SecureDocument | New | Payments | §9 + §8 | Payment receipts & invoices | Issued for every transaction / Invoice numbering and tax reporting | All | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
354 | 347 | M07 | Payment system | UI | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.10 | PAY-10 | Payment receipts & invoices — issued for every transaction | PAY-10.03 | Print/download on reception, doctor (subscription), later patient app | New | Payments | §9 + §8 | Payment receipts & invoices | Issued for every transaction / Invoice numbering and tax reporting | All | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
355 | 348 | M07 | Payment system | QA | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.10 | PAY-10 | Payment receipts & invoices — issued for every transaction | PAY-10.04 | QA: unique invoice numbers; cancelled invoice not reused | Regression | Payments | §9 + §8 | Payment receipts & invoices | Issued for every transaction / Invoice numbering and tax reporting | All | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
356 | 349 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.11 | PAY-11 | Complete payment audit trail — every transaction traceable end to end by Homeocentrum | PAY-11.01 | Persist raw webhook JSON; correlation id on Appointment and Ledger | New | Payments | §9 + §17 | Complete audit trail | Every transaction traceable end to end by Homeocentrum | Account | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
357 | 350 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.11 | PAY-11 | Complete payment audit trail — every transaction traceable end to end by Homeocentrum | PAY-11.02 | Account query API: trail by appointment / payment / doctor (Phase 7 UI) | New | Payments | §9 + §17 | Complete audit trail | Every transaction traceable end to end by Homeocentrum | Account | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
358 | 351 | M07 | Payment system | QA | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.11 | PAY-11 | Complete payment audit trail — every transaction traceable end to end by Homeocentrum | PAY-11.03 | QA: missing webhook still shows PENDING not PAID | Regression | Payments | §9 + §17 | Complete audit trail | Every transaction traceable end to end by Homeocentrum | Account | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
359 | 352 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.1 | FIN-01 | Unified transaction ledger — every rupee that moves through the platform, in one record | FIN-01.01 | DB: LedgerEntry (Stream, Direction, Amount, Gst, Commission, EntityType, EntityId, PaymentOrderId, At) immutable | New | Account | §8 | Unified transaction ledger | Every rupee that moves through the platform, in one record | Account Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
360 | 353 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.1 | FIN-01 | Unified transaction ledger — every rupee that moves through the platform, in one record | FIN-01.02 | API: GET /account/ledger filters; export; write-only from payment/settlement services | New | Account | §8 | Unified transaction ledger | Every rupee that moves through the platform, in one record | Account Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
361 | 354 | M08 | Account & finance | UI | 7 | Phase 7 — Account & finance department (PDF §8) | 7.1 | FIN-01 | Unified transaction ledger — every rupee that moves through the platform, in one record | FIN-01.03 | /account/ledger UI — Account layout sidebar Finance | New | Account | §8 | Unified transaction ledger | Every rupee that moves through the platform, in one record | Account Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
362 | 355 | M08 | Account & finance | QA | 7 | Phase 7 — Account & finance department (PDF §8) | 7.1 | FIN-01 | Unified transaction ledger — every rupee that moves through the platform, in one record | FIN-01.04 | QA: consult pay writes S2; subscription writes S1; they never share one row | Regression | Account | §8 | Unified transaction ledger | Every rupee that moves through the platform, in one record | Account Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
363 | 356 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.2 | FIN-02 | Consultation payment reconciliation — online payments and reception collections matched and verified | FIN-02.01 | Reuse ConsultPayment + Appointment; reconciliation query | New | Account | §8 + §7.2 + §16 | Consultation payment reconciliation | Online payments and reception collections matched and verified / Match every booking against every payment | Account + Admin | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
364 | 357 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.2 | FIN-02 | Consultation payment reconciliation — online payments and reception collections matched and verified | FIN-02.02 | GET Admin/Account reconciliation + aggregates | New | Account | §8 + §7.2 + §16 | Consultation payment reconciliation | Online payments and reception collections matched and verified / Match every booking against every payment | Account + Admin | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
365 | 358 | M08 | Account & finance | UI | 7 | Phase 7 — Account & finance department (PDF §8) | 7.2 | FIN-02 | Consultation payment reconciliation — online payments and reception collections matched and verified | FIN-02.03 | /account/consult-recon and /admin/consult-payments (same data, Account owns, Admin views) | New | Account | §8 + §7.2 + §16 | Consultation payment reconciliation | Online payments and reception collections matched and verified / Match every booking against every payment | Account + Admin | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
366 | 359 | M08 | Account & finance | QA | 7 | Phase 7 — Account & finance department (PDF §8) | 7.2 | FIN-02 | Consultation payment reconciliation — online payments and reception collections matched and verified | FIN-02.04 | QA: unmatched payment appears in exception queue not silent | Regression | Account | §8 + §7.2 + §16 | Consultation payment reconciliation | Online payments and reception collections matched and verified / Match every booking against every payment | Account + Admin | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
367 | 360 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.3 | FIN-03 | Medicine ledger — medicine money tracked separately from consultation money | FIN-03.01 | LedgerEntry stream MEDICINE with SplitSeller/SplitPlatform/SplitDelivery | New | Account | §8 + §12 | Medicine ledger | Medicine money tracked separately from consultation money / Seller, platform and delivery shares recorded separately from consultation money | Account Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
368 | 361 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.3 | FIN-03 | Medicine ledger — medicine money tracked separately from consultation money | FIN-03.02 | GET /account/medicine-ledger | New | Account | §8 + §12 | Medicine ledger | Medicine money tracked separately from consultation money / Seller, platform and delivery shares recorded separately from consultation money | Account Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
369 | 362 | M08 | Account & finance | UI | 7 | Phase 7 — Account & finance department (PDF §8) | 7.3 | FIN-03 | Medicine ledger — medicine money tracked separately from consultation money | FIN-03.03 | /account/medicine-ledger UI (empty until HomeoMeds orders exist — still ship the screen) | New | Account | §8 + §12 | Medicine ledger | Medicine money tracked separately from consultation money / Seller, platform and delivery shares recorded separately from consultation money | Account Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
370 | 363 | M08 | Account & finance | QA | 7 | Phase 7 — Account & finance department (PDF §8) | 7.3 | FIN-03 | Medicine ledger — medicine money tracked separately from consultation money | FIN-03.04 | QA: S2 consult row never appears on this screen | Regression | Account | §8 + §12 | Medicine ledger | Medicine money tracked separately from consultation money / Seller, platform and delivery shares recorded separately from consultation money | Account Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
371 | 364 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.4 | FIN-04 | Settlement runs — scheduled settlement of amounts due to doctors and pharmacies | FIN-04.01 | DB: SettlementRun, SettlementLine | New | Account | §8 + §16 | Settlement runs | Scheduled settlement of amounts due to doctors and pharmacies | Account Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
372 | 365 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.4 | FIN-04 | Settlement runs — scheduled settlement of amounts due to doctors and pharmacies | FIN-04.02 | API: create run (dry-run + commit); list; detail | New | Account | §8 + §16 | Settlement runs | Scheduled settlement of amounts due to doctors and pharmacies | Account Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
373 | 366 | M08 | Account & finance | UI | 7 | Phase 7 — Account & finance department (PDF §8) | 7.4 | FIN-04 | Settlement runs — scheduled settlement of amounts due to doctors and pharmacies | FIN-04.03 | /account/settlements | New | Account | §8 + §16 | Settlement runs | Scheduled settlement of amounts due to doctors and pharmacies | Account Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
374 | 367 | M08 | Account & finance | QA | 7 | Phase 7 — Account & finance department (PDF §8) | 7.4 | FIN-04 | Settlement runs — scheduled settlement of amounts due to doctors and pharmacies | FIN-04.04 | QA: hold days exclude too-new captures; refunds net out | Regression | Account | §8 + §16 | Settlement runs | Scheduled settlement of amounts due to doctors and pharmacies | Account Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
375 | 368 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.5 | FIN-05 | Payout approval — payouts released only after OTP-verified approval | FIN-05.01 | DB: Payout (PayeeType Doctor¦Pharmacy, Amount, Status, SettlementRunId) | New | Account | §8 + §17 | Payout approval | Payouts released only after OTP-verified approval | Account Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
376 | 369 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.5 | FIN-05 | Payout approval — payouts released only after OTP-verified approval | FIN-05.02 | API: ApprovePayout with OTP; reject | New | Account | §8 + §17 | Payout approval | Payouts released only after OTP-verified approval | Account Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
377 | 370 | M08 | Account & finance | UI | 7 | Phase 7 — Account & finance department (PDF §8) | 7.5 | FIN-05 | Payout approval — payouts released only after OTP-verified approval | FIN-05.03 | /account/payouts | New | Account | §8 + §17 | Payout approval | Payouts released only after OTP-verified approval | Account Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
378 | 371 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.5 | FIN-05 | Payout approval — payouts released only after OTP-verified approval | FIN-05.04 | Bank file / Razorpay payout adapter per PRE-01 | New Integration | Account | §8 + §17 | Payout approval | Payouts released only after OTP-verified approval | Account Portal | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
379 | 372 | M08 | Account & finance | QA | 7 | Phase 7 — Account & finance department (PDF §8) | 7.5 | FIN-05 | Payout approval — payouts released only after OTP-verified approval | FIN-05.05 | QA: Account role only; replay OTP; Admin 403 on approve | Regression | Account | §8 + §17 | Payout approval | Payouts released only after OTP-verified approval | Account Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
380 | 373 | M08 | Account & finance | UI | 7 | Phase 7 — Account & finance department (PDF §8) | 7.6 | FIN-06 | Refund processing — Account issues and tracks refunds (uses PAY-09) | FIN-06.01 | UI /account/refunds: original payment, amount, reason, status | New | Account | §8 | Refund processing | Issue and track refunds | Account Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
381 | 374 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.6 | FIN-06 | Refund processing — Account issues and tracks refunds (uses PAY-09) | FIN-06.02 | Ledger reverse entries on successful refund | New | Account | §8 | Refund processing | Issue and track refunds | Account Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
382 | 375 | M08 | Account & finance | QA | 7 | Phase 7 — Account & finance department (PDF §8) | 7.6 | FIN-06 | Refund processing — Account issues and tracks refunds (uses PAY-09) | FIN-06.03 | QA: partial refund; full refund; cash-policy path | Regression | Account | §8 | Refund processing | Issue and track refunds | Account Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
383 | 376 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.7 | FIN-07 | Payment exception handling — investigate and resolve every failed or disputed payment | FIN-07.01 | DB: PaymentException state machine | New | Account | §8 + §7.2 | Payment exception handling | Investigate and resolve every failed or disputed payment / Every failed or mismatched payment surfaced for action | Account + Admin | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
384 | 377 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.7 | FIN-07 | Payment exception handling — investigate and resolve every failed or disputed payment | FIN-07.02 | API: list/detail/retry/resolve; created by webhook mismatches | New | Account | §8 + §7.2 | Payment exception handling | Investigate and resolve every failed or disputed payment / Every failed or mismatched payment surfaced for action | Account + Admin | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
385 | 378 | M08 | Account & finance | UI | 7 | Phase 7 — Account & finance department (PDF §8) | 7.7 | FIN-07 | Payment exception handling — investigate and resolve every failed or disputed payment | FIN-07.03 | /account/exceptions and /admin/payment-exceptions (same queue) | New | Account | §8 + §7.2 | Payment exception handling | Investigate and resolve every failed or disputed payment / Every failed or mismatched payment surfaced for action | Account + Admin | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
386 | 379 | M08 | Account & finance | QA | 7 | Phase 7 — Account & finance department (PDF §8) | 7.7 | FIN-07 | Payment exception handling — investigate and resolve every failed or disputed payment | FIN-07.04 | QA: failed webhook creates exception; manual resolve requires Account role + OTP | Regression | Account | §8 + §7.2 | Payment exception handling | Investigate and resolve every failed or disputed payment / Every failed or mismatched payment surfaced for action | Account + Admin | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
387 | 380 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.8 | FIN-08 | GST & invoice reports — invoice numbering and tax reporting | FIN-08.01 | Reuse Invoice; tax config table (GstRate, treatment flags) | New | Account | §8 + §16 | GST & invoice reports | Invoice numbering and tax reporting | Account Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
388 | 381 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.8 | FIN-08 | GST & invoice reports — invoice numbering and tax reporting | FIN-08.02 | GET tax report + CSV | New | Account | §8 + §16 | GST & invoice reports | Invoice numbering and tax reporting | Account Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
389 | 382 | M08 | Account & finance | UI | 7 | Phase 7 — Account & finance department (PDF §8) | 7.8 | FIN-08 | GST & invoice reports — invoice numbering and tax reporting | FIN-08.03 | /account/tax | New | Account | §8 + §16 | GST & invoice reports | Invoice numbering and tax reporting | Account Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
390 | 383 | M08 | Account & finance | QA | 7 | Phase 7 — Account & finance department (PDF §8) | 7.8 | FIN-08 | GST & invoice reports — invoice numbering and tax reporting | FIN-08.04 | QA: rates come from config; changing rate does not rewrite old invoices | Regression | Account | §8 + §16 | GST & invoice reports | Invoice numbering and tax reporting | Account Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
391 | 384 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.9 | FIN-09 | Payee records — bank and KYC details for doctors and pharmacies | FIN-09.01 | DB: Payee (DoctorId/PharmacyId, Bank, PAN, KYC status) | New | Account | §8 | Payee records | Bank and KYC details for doctors and pharmacies | Account Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
392 | 385 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.9 | FIN-09 | Payee records — bank and KYC details for doctors and pharmacies | FIN-09.02 | API: list/update; OTP on bank change | New | Account | §8 | Payee records | Bank and KYC details for doctors and pharmacies | Account Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
393 | 386 | M08 | Account & finance | UI | 7 | Phase 7 — Account & finance department (PDF §8) | 7.9 | FIN-09 | Payee records — bank and KYC details for doctors and pharmacies | FIN-09.03 | /account/payees | New | Account | §8 | Payee records | Bank and KYC details for doctors and pharmacies | Account Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
394 | 387 | M08 | Account & finance | QA | 7 | Phase 7 — Account & finance department (PDF §8) | 7.9 | FIN-09 | Payee records — bank and KYC details for doctors and pharmacies | FIN-09.04 | QA: missing KYC blocks FIN-05 | Regression | Account | §8 | Payee records | Bank and KYC details for doctors and pharmacies | Account Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
395 | 388 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.10 | FIN-10 | Clinic collection view — cash and UPI collected at reception, per clinic and per day | FIN-10.01 | Query ConsultPayment Method in CASH/UPI_OFFLINE grouped by DoctorId/date | New | Account | §8 | Clinic collection view | Cash and UPI collected at reception, per clinic and per day | Account Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
396 | 389 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.10 | FIN-10 | Clinic collection view — cash and UPI collected at reception, per clinic and per day | FIN-10.02 | GET clinic-collections | New | Account | §8 | Clinic collection view | Cash and UPI collected at reception, per clinic and per day | Account Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
397 | 390 | M08 | Account & finance | UI | 7 | Phase 7 — Account & finance department (PDF §8) | 7.10 | FIN-10 | Clinic collection view — cash and UPI collected at reception, per clinic and per day | FIN-10.03 | /account/clinic-collections | New | Account | §8 | Clinic collection view | Cash and UPI collected at reception, per clinic and per day | Account Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
398 | 391 | M08 | Account & finance | QA | 7 | Phase 7 — Account & finance department (PDF §8) | 7.10 | FIN-10 | Clinic collection view — cash and UPI collected at reception, per clinic and per day | FIN-10.04 | QA: online Razorpay consults do not appear as clinic cash | Regression | Account | §8 | Clinic collection view | Cash and UPI collected at reception, per clinic and per day | Account Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
399 | 392 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.11 | FIN-11 | Separation of duties — Account controls money; Admin controls platform and clinical data | FIN-11.01 | Seed Account role menus: ledger, recon, medicine ledger, exceptions, settlements, payouts, refunds, tax, payees, clinic collections | New | Account | §8 | Separation of duties | The Account department controls money. Admin controls the platform and clinical data. Neither can perform the other’s role, which protects both. | Admin + Account | Configuration | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
400 | 393 | M08 | Account & finance | QA | 7 | Phase 7 — Account & finance department (PDF §8) | 7.11 | FIN-11 | Separation of duties — Account controls money; Admin controls platform and clinical data | FIN-11.02 | Negative tests: Admin POST ApprovePayout → 403; Account POST repertory section → 403 | Regression | Account | §8 | Separation of duties | The Account department controls money. Admin controls the platform and clinical data. Neither can perform the other’s role, which protects both. | Admin + Account | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
401 | 670 | M08 | Account & finance | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.8 | CON-08 | Patient payments & refunds read model | CON-08.01 | GET /api/Patient/Payments | New | Patient money | §2.8 | Payments & refunds | Full payment history and refund status | Patient App (API now) | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
402 | 671 | M08 | Account & finance | QA | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.8 | CON-08 | Patient payments & refunds read model | CON-08.02 | QA: commission/GST internal lines hidden | Regression | Patient money | §2.8 | Payments & refunds | Full payment history and refund status | Patient App (API now) | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
403 | 394 | M09 | Trust & verification | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.1 | TRU-01 | Doctor credentialing — doctors upload qualification and registration documents for review | TRU-01.01 | DB: DoctorVerification (Pending/Approved/Rejected/NeedsInfo), DoctorCredentialDocument | New | Trust | §13 + §7.2 | Doctor credentialing | Doctors upload qualification and registration documents for review | Doctor Web + Admin | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
404 | 395 | M09 | Trust & verification | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.1 | TRU-01 | Doctor credentialing — doctors upload qualification and registration documents for review | TRU-01.02 | API: upload documents; MyStatus; RegisterDoctor modified to VerificationStatus=Pending (not auto-practice) | New | Trust | §13 + §7.2 | Doctor credentialing | Doctors upload qualification and registration documents for review | Doctor Web + Admin | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
405 | 396 | M09 | Trust & verification | UI | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.1 | TRU-01 | Doctor credentialing — doctors upload qualification and registration documents for review | TRU-01.03 | Doctor profile credentials tab + document upload | New | Trust | §13 + §7.2 | Doctor credentialing | Doctors upload qualification and registration documents for review | Doctor Web + Admin | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
406 | 397 | M09 | Trust & verification | QA | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.1 | TRU-01 | Doctor credentialing — doctors upload qualification and registration documents for review | TRU-01.04 | QA: doctor without docs cannot appear in public directory (Phase 9) | Regression | Trust | §13 + §7.2 | Doctor credentialing | Doctors upload qualification and registration documents for review | Doctor Web + Admin | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
407 | 398 | M09 | Trust & verification | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.2 | TRU-02 | Verification review — Admin approves, rejects or requests further information | TRU-02.01 | Reuse DoctorVerification | New | Trust | §13 + §7.2 | Verification review | Admin approves, rejects or requests more information before they can practise on the platform | Admin Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
408 | 399 | M09 | Trust & verification | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.2 | TRU-02 | Verification review — Admin approves, rejects or requests further information | TRU-02.02 | API: Queue, {id}, Approve, Reject, RequestInfo | New | Trust | §13 + §7.2 | Verification review | Admin approves, rejects or requests more information before they can practise on the platform | Admin Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
409 | 400 | M09 | Trust & verification | UI | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.2 | TRU-02 | Verification review — Admin approves, rejects or requests further information | TRU-02.03 | /admin/doctor-credentialing and /:doctorId; verification column on users list | New | Trust | §13 + §7.2 | Verification review | Admin approves, rejects or requests more information before they can practise on the platform | Admin Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
410 | 401 | M09 | Trust & verification | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.2 | TRU-02 | Verification review — Admin approves, rejects or requests further information | TRU-02.04 | Email notify (Phase 12 SMTP already used for activation) | New Integration | Trust | §13 + §7.2 | Verification review | Admin approves, rejects or requests more information before they can practise on the platform | Admin Portal | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
411 | 402 | M09 | Trust & verification | QA | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.2 | TRU-02 | Verification review — Admin approves, rejects or requests further information | TRU-02.05 | QA: reject reason required; request-info reopens Pending | Regression | Trust | §13 + §7.2 | Verification review | Admin approves, rejects or requests more information before they can practise on the platform | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
412 | 403 | M09 | Trust & verification | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.3 | TRU-03 | Verified badge — patients see which doctors have been verified | TRU-03.01 | Public doctor DTO includes isVerified | New | Trust | §13 + §2.2 | Verified badge / Credentials & verification | Patients see which doctors have been verified / Verified badge showing the doctor’s credentials are checked | Public + Patient app | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
413 | 404 | M09 | Trust & verification | UI | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.3 | TRU-03 | Verified badge — patients see which doctors have been verified | TRU-03.02 | Badge component for website (Phase 9) and patient app (Phase 16) | New | Trust | §13 + §2.2 | Verified badge / Credentials & verification | Patients see which doctors have been verified / Verified badge showing the doctor’s credentials are checked | Public + Patient app | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
414 | 405 | M09 | Trust & verification | QA | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.3 | TRU-03 | Verified badge — patients see which doctors have been verified | TRU-03.03 | QA: pending doctor has no badge | Regression | Trust | §13 + §2.2 | Verified badge / Credentials & verification | Patients see which doctors have been verified / Verified badge showing the doctor’s credentials are checked | Public + Patient app | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
415 | 406 | M09 | Trust & verification | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.4 | TRU-04 | Practice gate — only verified doctors appear to patients and take paid consultations | TRU-04.01 | Public doctor list filter VerificationStatus=Approved | New | Trust | §13 | Practice gate | Only verified doctors appear to patients and take paid consultations | Public + Payments | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
416 | 407 | M09 | Trust & verification | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.4 | TRU-04 | Practice gate — only verified doctors appear to patients and take paid consultations | TRU-04.02 | CreateConsultOrder rejects unverified doctor for patient-originated bookings | New | Trust | §13 | Practice gate | Only verified doctors appear to patients and take paid consultations | Public + Payments | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
417 | 408 | M09 | Trust & verification | QA | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.4 | TRU-04 | Practice gate — only verified doctors appear to patients and take paid consultations | TRU-04.03 | QA: reception can still book own clinic patient for unverified doctor if PRE-03 allows | Regression | Trust | §13 | Practice gate | Only verified doctors appear to patients and take paid consultations | Public + Payments | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
418 | 409 | M09 | Trust & verification | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.5 | TRU-05 | Patient reviews — patients rate and review consultations | TRU-05.01 | DB: Review (PatientAppId, Rating, Text, Status, At) | New | Trust | §13 + §2.8 | Patient reviews / Write a review | Patients rate and review consultations / Rate and review the consultation | Patient + Public | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
419 | 410 | M09 | Trust & verification | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.5 | TRU-05 | Patient reviews — patients rate and review consultations | TRU-05.02 | API: create (patient), list by doctor (public approved), doctor list own | New | Trust | §13 + §2.8 | Patient reviews / Write a review | Patients rate and review consultations / Rate and review the consultation | Patient + Public | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
420 | 411 | M09 | Trust & verification | UI | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.5 | TRU-05 | Patient reviews — patients rate and review consultations | TRU-05.03 | Public doctor profile reviews; patient app write flow Phase 16 | New | Trust | §13 + §2.8 | Patient reviews / Write a review | Patients rate and review consultations / Rate and review the consultation | Patient + Public | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
421 | 412 | M09 | Trust & verification | QA | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.5 | TRU-05 | Patient reviews — patients rate and review consultations | TRU-05.04 | QA: duplicate review blocked; incomplete visit blocked | Regression | Trust | §13 + §2.8 | Patient reviews / Write a review | Patients rate and review consultations / Rate and review the consultation | Patient + Public | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
422 | 413 | M09 | Trust & verification | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.6 | TRU-06 | Review appeal — doctors can appeal a review; patients manage reviews and raise an appeal | TRU-06.01 | DB: ReviewAppeal | New | Trust | §13 + §2.8 | Review appeal / My reviews & appeal | Doctors can appeal a review / Manage reviews and raise an appeal | Doctor + Patient + Admin | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
423 | 414 | M09 | Trust & verification | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.6 | TRU-06 | Review appeal — doctors can appeal a review; patients manage reviews and raise an appeal | TRU-06.02 | API: doctor appeal; patient list/mine; admin resolve | New | Trust | §13 + §2.8 | Review appeal / My reviews & appeal | Doctors can appeal a review / Manage reviews and raise an appeal | Doctor + Patient + Admin | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
424 | 415 | M09 | Trust & verification | UI | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.6 | TRU-06 | Review appeal — doctors can appeal a review; patients manage reviews and raise an appeal | TRU-06.03 | Doctor dashboard my-reviews; admin queue | New | Trust | §13 + §2.8 | Review appeal / My reviews & appeal | Doctors can appeal a review / Manage reviews and raise an appeal | Doctor + Patient + Admin | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
425 | 416 | M09 | Trust & verification | QA | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.6 | TRU-06 | Review appeal — doctors can appeal a review; patients manage reviews and raise an appeal | TRU-06.04 | QA: only treating doctor of that visit can appeal | Regression | Trust | §13 + §2.8 | Review appeal / My reviews & appeal | Doctors can appeal a review / Manage reviews and raise an appeal | Doctor + Patient + Admin | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
426 | 417 | M09 | Trust & verification | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.7 | TRU-07 | Ranking transparency — patients are shown why doctors are ranked as they are | TRU-07.01 | Ranking config (weights) — not a black box hardcoded sort | New | Trust | §13 + §2.2 | Ranking transparency / Ranking explanation | Patients are shown why doctors are ranked as they are / Transparent explanation of why doctors appear in a given order | Public + Patient app | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
427 | 418 | M09 | Trust & verification | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.7 | TRU-07 | Ranking transparency — patients are shown why doctors are ranked as they are | TRU-07.02 | GET doctors + GET ranking-explain/{doctorId} | New | Trust | §13 + §2.2 | Ranking transparency / Ranking explanation | Patients are shown why doctors are ranked as they are / Transparent explanation of why doctors appear in a given order | Public + Patient app | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
428 | 419 | M09 | Trust & verification | UI | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.7 | TRU-07 | Ranking transparency — patients are shown why doctors are ranked as they are | TRU-07.03 | Search results: Why this order? panel | New | Trust | §13 + §2.2 | Ranking transparency / Ranking explanation | Patients are shown why doctors are ranked as they are / Transparent explanation of why doctors appear in a given order | Public + Patient app | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
429 | 420 | M09 | Trust & verification | QA | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.7 | TRU-07 | Ranking transparency — patients are shown why doctors are ranked as they are | TRU-07.04 | QA: changing weights changes order and explanation together | Regression | Trust | §13 + §2.2 | Ranking transparency / Ranking explanation | Patients are shown why doctors are ranked as they are / Transparent explanation of why doctors appear in a given order | Public + Patient app | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
430 | 421 | M10 | Patient website | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.1 | WEB-01 | Product home page — complete public website presenting the service | WEB-01.01 | No schema | Existing Improvement | Patient Website | §4 | Product home page | Complete public website presenting the service | Patient Website | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
431 | 422 | M10 | Patient website | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.1 | WEB-01 | Product home page — complete public website presenting the service | WEB-01.02 | Reuse public doctor/fee APIs when live | Existing Improvement | Patient Website | §4 | Product home page | Complete public website presenting the service | Patient Website | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
432 | 423 | M10 | Patient website | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.1 | WEB-01 | Product home page — complete public website presenting the service | WEB-01.03 | HomeLandingPage: book, verified doctors, pricing teaser, store badges; strip leftover job-board feel | Existing Improvement | Patient Website | §4 | Product home page | Complete public website presenting the service | Patient Website | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
433 | 424 | M10 | Patient website | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.1 | WEB-01 | Product home page — complete public website presenting the service | WEB-01.04 | QA: mobile viewport; deep link /book | Regression | Patient Website | §4 | Product home page | Complete public website presenting the service | Patient Website | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
434 | 425 | M10 | Patient website | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.2 | WEB-02 | Consultation & subscription pricing — transparent pricing display | WEB-02.01 | Public doctor card shows in-clinic and tele fee | Existing Improvement | Patient Website | §4 | Consultation & subscription pricing | Transparent pricing display | Patient Website | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
435 | 426 | M10 | Patient website | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.2 | WEB-02 | Consultation & subscription pricing — transparent pricing display | WEB-02.02 | /pricing remains SaaS packages for doctors; label it clearly vs patient consult fees | Existing Improvement | Patient Website | §4 | Consultation & subscription pricing | Transparent pricing display | Patient Website | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
436 | 427 | M10 | Patient website | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.2 | WEB-02 | Consultation & subscription pricing — transparent pricing display | WEB-02.03 | QA: fee matches checkout amount | Regression | Patient Website | §4 | Consultation & subscription pricing | Transparent pricing display | Patient Website | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
437 | 428 | M10 | Patient website | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.3 | WEB-03 | Doctor discovery — browse and search verified doctors | WEB-03.01 | Public doctor search indexes (from Doctor + verification + fee + schedule) | New | Patient Website | §4 + §2.2 | Doctor discovery | Browse and search verified doctors | Patient Website | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
438 | 429 | M10 | Patient website | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.3 | WEB-03 | Doctor discovery — browse and search verified doctors | WEB-03.02 | GET /api/Public/Doctors + filters + profile | New | Patient Website | §4 + §2.2 | Doctor discovery | Browse and search verified doctors | Patient Website | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
439 | 430 | M10 | Patient website | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.3 | WEB-03 | Doctor discovery — browse and search verified doctors | WEB-03.03 | /book list + filters + doctor profile page | New | Patient Website | §4 + §2.2 | Doctor discovery | Browse and search verified doctors | Patient Website | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
440 | 431 | M10 | Patient website | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.3 | WEB-03 | Doctor discovery — browse and search verified doctors | WEB-03.04 | QA: unverified excluded; filters combine; empty state | Regression | Patient Website | §4 + §2.2 | Doctor discovery | Browse and search verified doctors | Patient Website | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
441 | 432 | M10 | Patient website | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.4 | WEB-04 | Self-service booking — book an appointment online without calling the clinic | WEB-04.01 | Reuse Patient + Appointment; BookingToken; PatientAuth OTP | New | Patient Website | §4 + §2.3 | Self-service booking | Book an appointment online without calling the clinic | Patient Website | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
442 | 433 | M10 | Patient website | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.4 | WEB-04 | Self-service booking — book an appointment online without calling the clinic | WEB-04.02 | Public: Doctors/{id}/Slots, Create, {bookingToken}; POST PatientAuth RequestOtp/VerifyOtp | New | Patient Website | §4 + §2.3 | Self-service booking | Book an appointment online without calling the clinic | Patient Website | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
443 | 434 | M10 | Patient website | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.4 | WEB-04 | Self-service booking — book an appointment online without calling the clinic | WEB-04.03 | /book/:doctorId/slots; /book/confirm; booking success | New | Patient Website | §4 + §2.3 | Self-service booking | Book an appointment online without calling the clinic | Patient Website | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
444 | 435 | M10 | Patient website | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.4 | WEB-04 | Self-service booking — book an appointment online without calling the clinic | WEB-04.04 | QA: double-book same slot; hold expiry; OTP fail; consent required | Regression | Patient Website | §4 + §2.3 | Self-service booking | Book an appointment online without calling the clinic | Patient Website | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
445 | 436 | M10 | Patient website | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.5 | WEB-05 | Online consultation payment on website — pay the fee at the time of booking | WEB-05.01 | /book/pay/:bookingId + success/failure pages | New | Patient Website | §4 + §9 | Online consultation payment | Pay the consultation fee at the time of booking | Patient Website | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
446 | 437 | M10 | Patient website | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.5 | WEB-05 | Online consultation payment on website — pay the fee at the time of booking | WEB-05.02 | QA: pay-at-clinic skip checkout; failed pay remains PENDING not PAID | Regression | Patient Website | §4 + §9 | Online consultation payment | Pay the consultation fee at the time of booking | Patient Website | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
447 | 438 | M10 | Patient website | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.6 | WEB-06 | Contact & enquiry form — enquiries reach the admin team and are tracked | WEB-06.01 | Reuse EnquiryDetail; add Status/AssignedTo if missing | Existing Improvement | Patient Website | §4 + §15 | Contact & enquiry form | Enquiries reach the admin team and are tracked | Patient Website + Admin | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
448 | 439 | M10 | Patient website | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.6 | WEB-06 | Contact & enquiry form — enquiries reach the admin team and are tracked | WEB-06.02 | Existing enquiry POST; admin list API if missing | Existing Improvement | Patient Website | §4 + §15 | Contact & enquiry form | Enquiries reach the admin team and are tracked | Patient Website + Admin | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
449 | 440 | M10 | Patient website | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.6 | WEB-06 | Contact & enquiry form — enquiries reach the admin team and are tracked | WEB-06.03 | /contact confirmation; /admin/enquiries inbox (not Velzon mailbox) | Existing Improvement | Patient Website | §4 + §15 | Contact & enquiry form | Enquiries reach the admin team and are tracked | Patient Website + Admin | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
450 | 441 | M10 | Patient website | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.6 | WEB-06 | Contact & enquiry form — enquiries reach the admin team and are tracked | WEB-06.04 | QA: guest submit → admin sees row | Regression | Patient Website | §4 + §15 | Contact & enquiry form | Enquiries reach the admin team and are tracked | Patient Website + Admin | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
451 | 442 | M10 | Patient website | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.7 | WEB-07 | Privacy policy — covering data protection, recording and pharmacy consent | WEB-07.01 | Replace /privacy content with signed legal copy; store PolicyVersion | Existing Improvement | Legal | §4 + §17 | Privacy policy | Covering data protection, recording and pharmacy consent | Patient Website | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
452 | 443 | M10 | Patient website | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.7 | WEB-07 | Privacy policy — covering data protection, recording and pharmacy consent | WEB-07.02 | QA: booking consent shows policy version number | Regression | Legal | §4 + §17 | Privacy policy | Covering data protection, recording and pharmacy consent | Patient Website | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
453 | 444 | M10 | Patient website | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.8 | WEB-08 | Terms of service — covering payments, refunds, telemedicine and medicine orders | WEB-08.01 | Replace /terms with signed copy; version stamp on booking/payment | Existing Improvement | Legal | §4 | Terms of service | Covering payments, refunds, telemedicine and medicine orders | Patient Website | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
454 | 445 | M10 | Patient website | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.8 | WEB-08 | Terms of service — covering payments, refunds, telemedicine and medicine orders | WEB-08.02 | QA: terms checkbox required on confirm | Regression | Legal | §4 | Terms of service | Covering payments, refunds, telemedicine and medicine orders | Patient Website | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
455 | 446 | M10 | Patient website | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.9 | WEB-09 | Doctor self-registration — doctors apply to join the platform online | WEB-09.01 | Documents via TRU-01 tables | Existing Improvement | Patient Website | §4 | Doctor self-registration | Doctors apply to join the platform online | Public | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
456 | 447 | M10 | Patient website | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.9 | WEB-09 | Doctor self-registration — doctors apply to join the platform online | WEB-09.02 | RegisterDoctor sets Pending; does not auto-activate practice for directory | Existing Improvement | Patient Website | §4 | Doctor self-registration | Doctors apply to join the platform online | Public | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
457 | 448 | M10 | Patient website | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.9 | WEB-09 | Doctor self-registration — doctors apply to join the platform online | WEB-09.03 | /register multipart docs; pending message; status page | Existing Improvement | Patient Website | §4 | Doctor self-registration | Doctors apply to join the platform online | Public | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
458 | 449 | M10 | Patient website | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.9 | WEB-09 | Doctor self-registration — doctors apply to join the platform online | WEB-09.04 | QA: register → admin queue row | Regression | Patient Website | §4 | Doctor self-registration | Doctors apply to join the platform online | Public | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
459 | 450 | M10 | Patient website | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.10 | WEB-10 | Email activation — secure account activation by email link | WEB-10.01 | Activation token TTL if missing | Existing Improvement | Auth | §4 | Email activation | Secure account activation by email link | Public | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
460 | 451 | M10 | Patient website | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.10 | WEB-10 | Email activation — secure account activation by email link | WEB-10.02 | Resend activation; do not treat activation as TRU-04 gate | Existing Improvement | Auth | §4 | Email activation | Secure account activation by email link | Public | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
461 | 452 | M10 | Patient website | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.10 | WEB-10 | Email activation — secure account activation by email link | WEB-10.03 | Login activation query param UX + expiry copy | Existing Improvement | Auth | §4 | Email activation | Secure account activation by email link | Public | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
462 | 453 | M10 | Patient website | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.10 | WEB-10 | Email activation — secure account activation by email link | WEB-10.04 | QA: used link, expired link, resend | Regression | Auth | §4 | Email activation | Secure account activation by email link | Public | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
463 | 459 | M10 | Patient website | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.12 | WEB-12 | Health articles — educational content to build trust and engagement | WEB-12.01 | Public articles list/detail from existing blog/news APIs | Existing Improvement | Patient Website | §2.2 | Health articles | Educational content to build trust and engagement | Patient Website + App | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
464 | 460 | M10 | Patient website | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.12 | WEB-12 | Health articles — educational content to build trust and engagement | WEB-12.02 | QA: unpublished hidden | Regression | Patient Website | §2.2 | Health articles | Educational content to build trust and engagement | Patient Website + App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
465 | 461 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.1 | ERX-01 | Potency module — every remedy carries a defined potency from a managed list, no free text | ERX-01.01 | DB: PotencyMaster; PrescriptionRemedyDetail.PotencyId | New | eRx | §11 | Potency module | Every remedy carries a defined potency, selected from a managed list — no free text | Doctor Web + Admin | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
466 | 462 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.1 | ERX-01 | Potency module — every remedy carries a defined potency from a managed list, no free text | ERX-01.02 | API: potency DDL; extend SavePrescriptionDetail | New | eRx | §11 | Potency module | Every remedy carries a defined potency, selected from a managed list — no free text | Doctor Web + Admin | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
467 | 463 | M11 | Digital prescription (eRx) | UI | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.1 | ERX-01 | Potency module — every remedy carries a defined potency from a managed list, no free text | ERX-01.03 | Rx modal potency picker (6C, 30C, 200C, 1M…) | New | eRx | §11 | Potency module | Every remedy carries a defined potency, selected from a managed list — no free text | Doctor Web + Admin | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
468 | 464 | M11 | Digital prescription (eRx) | QA | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.1 | ERX-01 | Potency module — every remedy carries a defined potency from a managed list, no free text | ERX-01.04 | QA: free text potency rejected | Regression | eRx | §11 | Potency module | Every remedy carries a defined potency, selected from a managed list — no free text | Doctor Web + Admin | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
469 | 465 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.2 | ERX-02 | Dosage details — frequency, duration and instructions recorded clearly | ERX-02.01 | DB: Frequency, Duration, Instructions on remedy line | New | eRx | §11 | Dosage details | Frequency, duration and instructions recorded clearly | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
470 | 466 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.2 | ERX-02 | Dosage details — frequency, duration and instructions recorded clearly | ERX-02.02 | Extend save/get Rx APIs | New | eRx | §11 | Dosage details | Frequency, duration and instructions recorded clearly | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
471 | 467 | M11 | Digital prescription (eRx) | UI | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.2 | ERX-02 | Dosage details — frequency, duration and instructions recorded clearly | ERX-02.03 | Rx row UI for the three fields | New | eRx | §11 | Dosage details | Frequency, duration and instructions recorded clearly | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
472 | 468 | M11 | Digital prescription (eRx) | QA | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.2 | ERX-02 | Dosage details — frequency, duration and instructions recorded clearly | ERX-02.04 | QA: all three persist and print | Regression | eRx | §11 | Dosage details | Frequency, duration and instructions recorded clearly | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
473 | 469 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.3 | ERX-03 | Visit notes kept separate from the prescription — private clinical notes never appear on the prescription given to the patient or pharmacy | ERX-03.01 | Extend AppointmentHistoryNote with NoteType, IsErxExcluded | New | eRx | §11 + §5.3 | Visit notes kept separate from the prescription | The doctor’s private clinical notes never appear on the prescription given to the patient or pharmacy | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
474 | 470 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.3 | ERX-03 | Visit notes kept separate from the prescription — private clinical notes never appear on the prescription given to the patient or pharmacy | ERX-03.02 | GET /api/Erx/ByAppointment/{id} returns snapshot without notes | New | eRx | §11 + §5.3 | Visit notes kept separate from the prescription | The doctor’s private clinical notes never appear on the prescription given to the patient or pharmacy | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
475 | 471 | M11 | Digital prescription (eRx) | UI | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.3 | ERX-03 | Visit notes kept separate from the prescription — private clinical notes never appear on the prescription given to the patient or pharmacy | ERX-03.03 | Move History Notes out of Rx modal; note types Chief complaint / Follow-up / General | New | eRx | §11 + §5.3 | Visit notes kept separate from the prescription | The doctor’s private clinical notes never appear on the prescription given to the patient or pharmacy | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
476 | 472 | M11 | Digital prescription (eRx) | QA | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.3 | ERX-03 | Visit notes kept separate from the prescription — private clinical notes never appear on the prescription given to the patient or pharmacy | ERX-03.04 | QA: print eRx vs export case PDF (doctor copy still has notes) | Regression | eRx | §11 + §5.3 | Visit notes kept separate from the prescription | The doctor’s private clinical notes never appear on the prescription given to the patient or pharmacy | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
477 | 473 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.4 | ERX-04 | Signed digital prescription — issued and locked once signed, so it cannot be altered afterwards | ERX-04.01 | DB: ErxSnapshot, ErxSnapshotItem (codes+names stored; patient API returns codes until pharmacy accept) | New | eRx | §11 + §2.5 + §5.3 | Signed digital prescription | Issued and locked once signed, so it cannot be altered afterwards / Official prescription issued by the doctor | Doctor Web | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
478 | 474 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.4 | ERX-04 | Signed digital prescription — issued and locked once signed, so it cannot be altered afterwards | ERX-04.02 | API: SignErx; GetErx; reject mutate of signed snapshot | New | eRx | §11 + §2.5 + §5.3 | Signed digital prescription | Issued and locked once signed, so it cannot be altered afterwards / Official prescription issued by the doctor | Doctor Web | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
479 | 475 | M11 | Digital prescription (eRx) | UI | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.4 | ERX-04 | Signed digital prescription — issued and locked once signed, so it cannot be altered afterwards | ERX-04.03 | Sign button; locked badge on board header | New | eRx | §11 + §2.5 + §5.3 | Signed digital prescription | Issued and locked once signed, so it cannot be altered afterwards / Official prescription issued by the doctor | Doctor Web | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
480 | 476 | M11 | Digital prescription (eRx) | QA | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.4 | ERX-04 | Signed digital prescription — issued and locked once signed, so it cannot be altered afterwards | ERX-04.04 | QA: POST save after sign does not change snapshot | Regression | eRx | §11 + §2.5 + §5.3 | Signed digital prescription | Issued and locked once signed, so it cannot be altered afterwards / Official prescription issued by the doctor | Doctor Web | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
481 | 477 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.5 | ERX-05 | Prescription history — every prescription stored against the patient and visit | ERX-05.01 | GET history by patient; by appointment | New | eRx | §11 | Prescription history | Every prescription stored against the patient and visit | Doctor + Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
482 | 478 | M11 | Digital prescription (eRx) | UI | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.5 | ERX-05 | Prescription history — every prescription stored against the patient and visit | ERX-05.02 | Doctor history panel lists signed eRx; patient timeline in Phase 16 | New | eRx | §11 | Prescription history | Every prescription stored against the patient and visit | Doctor + Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
483 | 479 | M11 | Digital prescription (eRx) | QA | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.5 | ERX-05 | Prescription history — every prescription stored against the patient and visit | ERX-05.03 | QA: another doctor 403 | Regression | eRx | §11 | Prescription history | Every prescription stored against the patient and visit | Doctor + Patient | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
484 | 480 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.6 | ERX-06 | Patient view of prescription in app — patient sees the prescription immediately (codes until pharmacy accept) | ERX-06.01 | Patient-authorised GET Erx; apply code protection ERX-08 | New | eRx | §11 + §2.5 | Patient view in app | Patient sees the prescription immediately in the app | Patient App + Website | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
485 | 481 | M11 | Digital prescription (eRx) | UI | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.6 | ERX-06 | Patient view of prescription in app — patient sees the prescription immediately (codes until pharmacy accept) | ERX-06.02 | Web confirmation/records page can show the same payload before the app exists | New | eRx | §11 + §2.5 | Patient view in app | Patient sees the prescription immediately in the app | Patient App + Website | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
486 | 482 | M11 | Digital prescription (eRx) | QA | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.6 | ERX-06 | Patient view of prescription in app — patient sees the prescription immediately (codes until pharmacy accept) | ERX-06.03 | QA: doctor names vs patient codes differ until pharmacy OTP accept | Regression | eRx | §11 + §2.5 | Patient view in app | Patient sees the prescription immediately in the app | Patient App + Website | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
487 | 483 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.7 | ERX-07 | Print & PDF — printable and downloadable prescription | ERX-07.01 | PDF renderer from ErxSnapshot; store via SEC-09 | New | eRx | §11 | Print & PDF | Printable and downloadable prescription | Doctor + Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
488 | 484 | M11 | Digital prescription (eRx) | UI | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.7 | ERX-07 | Print & PDF — printable and downloadable prescription | ERX-07.02 | Print/Download on doctor board and later patient app | New | eRx | §11 | Print & PDF | Printable and downloadable prescription | Doctor + Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
489 | 485 | M11 | Digital prescription (eRx) | QA | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.7 | ERX-07 | Print & PDF — printable and downloadable prescription | ERX-07.03 | QA: notes leak test on patient PDF | Regression | eRx | §11 | Print & PDF | Printable and downloadable prescription | Doctor + Patient | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
490 | 486 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.8 | ERX-08 | Remedy code protection — patient sees remedy codes rather than names until a licensed pharmacy accepts the order | ERX-08.01 | Assign stable remedy codes on snapshot items | New | eRx | §11 | Remedy code protection | The patient sees remedy codes rather than remedy names until a licensed pharmacy accepts the order | Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
491 | 487 | M11 | Digital prescription (eRx) | QA | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.8 | ERX-08 | Remedy code protection — patient sees remedy codes rather than names until a licensed pharmacy accepts the order | ERX-08.02 | Patient serializer tests (contract tests) | Regression | eRx | §11 | Remedy code protection | The patient sees remedy codes rather than remedy names until a licensed pharmacy accepts the order | Patient | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
492 | 488 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.9 | ERX-09 | Reveal on pharmacy acceptance — names and price revealed; payment QR or link generated (implemented with HomeoMeds; contract now) | ERX-09.01 | API contract: AcceptOrder(OTP) → reveal names; Quote → PayQR | New | eRx | §11 + §12 | Reveal on pharmacy acceptance | Once a pharmacy accepts and verifies by OTP, the remedy names and price are revealed and a payment QR or link is generated | Patient + Pharmacy | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
493 | 489 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.9 | ERX-09 | Reveal on pharmacy acceptance — names and price revealed; payment QR or link generated (implemented with HomeoMeds; contract now) | ERX-09.02 | Implement fully with MED-* in Phase 14 — do not reveal names from doctor sign alone | New | eRx | §11 + §12 | Reveal on pharmacy acceptance | Once a pharmacy accepts and verifies by OTP, the remedy names and price are revealed and a payment QR or link is generated | Patient + Pharmacy | Architecture | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
494 | 490 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.10 | ERX-10 | Repeat prescription / refill — patient requests; doctor approves or rejects from the mobile app (inbox on web too) | ERX-10.01 | DB: RefillRequest | New | eRx | §11 + §3 + §2.7 | Repeat prescription / refill | Patient requests a refill; doctor approves or rejects from the mobile app | Patient + Doctor mobile + Doctor web | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
495 | 491 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.10 | ERX-10 | Repeat prescription / refill — patient requests; doctor approves or rejects from the mobile app (inbox on web too) | ERX-10.02 | API: patient request; doctor inbox; approve/reject | New | eRx | §11 + §3 + §2.7 | Repeat prescription / refill | Patient requests a refill; doctor approves or rejects from the mobile app | Patient + Doctor mobile + Doctor web | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
496 | 492 | M11 | Digital prescription (eRx) | UI | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.10 | ERX-10 | Repeat prescription / refill — patient requests; doctor approves or rejects from the mobile app (inbox on web too) | ERX-10.03 | Doctor web inbox; doctor app in Phase 17; patient app in Phase 16 | New | eRx | §11 + §3 + §2.7 | Repeat prescription / refill | Patient requests a refill; doctor approves or rejects from the mobile app | Patient + Doctor mobile + Doctor web | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
497 | 493 | M11 | Digital prescription (eRx) | QA | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.10 | ERX-10 | Repeat prescription / refill — patient requests; doctor approves or rejects from the mobile app (inbox on web too) | ERX-10.04 | QA: cannot refill unsigned/locked-expired per policy | Regression | eRx | §11 + §3 + §2.7 | Repeat prescription / refill | Patient requests a refill; doctor approves or rejects from the mobile app | Patient + Doctor mobile + Doctor web | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
498 | 494 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.11 | ERX-11 | Lab orders alongside the prescription (keep existing labs on eRx snapshot) | ERX-11.01 | Copy lab orders into ErxSnapshot on sign | Existing Improvement | eRx | §11 | Lab orders | Tests ordered alongside the prescription | Doctor Web | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
499 | 495 | M11 | Digital prescription (eRx) | QA | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.11 | ERX-11 | Lab orders alongside the prescription (keep existing labs on eRx snapshot) | ERX-11.02 | QA: labs visible on eRx; result values not required on patient copy | Regression | eRx | §11 | Lab orders | Tests ordered alongside the prescription | Doctor Web | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
500 | 496 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.1 | TEL-01 | Doctor availability — online or offline status and working hours | TEL-01.01 | DB: TeleAvailability (Online/Offline, LastHeartbeat) | New | Telemedicine | §10 + §3 | Doctor availability | Doctor sets online or offline status and working hours | Doctor Web + Doctor App | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
501 | 497 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.1 | TEL-01 | Doctor availability — online or offline status and working hours | TEL-01.02 | API: SET/GET availability; public GET by doctorId | New | Telemedicine | §10 + §3 | Doctor availability | Doctor sets online or offline status and working hours | Doctor Web + Doctor App | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
502 | 498 | M12 | Telemedicine | UI | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.1 | TEL-01 | Doctor availability — online or offline status and working hours | TEL-01.03 | Dashboard toggle Online for teleconsult | New | Telemedicine | §10 + §3 | Doctor availability | Doctor sets online or offline status and working hours | Doctor Web + Doctor App | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
503 | 499 | M12 | Telemedicine | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.1 | TEL-01 | Doctor availability — online or offline status and working hours | TEL-01.04 | QA: heartbeat expiry sets offline | Regression | Telemedicine | §10 + §3 | Doctor availability | Doctor sets online or offline status and working hours | Doctor Web + Doctor App | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
504 | 500 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.2 | TEL-02 | Telemedicine waiting queue — who is waiting, how long, whether they have paid | TEL-02.01 | Queue query on E-CONSULT + PaymentStatus + join time | New | Telemedicine | §10 + §3 | Telemedicine waiting queue | Doctor sees who is waiting, for how long, and whether they have paid | Doctor Web + App | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
505 | 501 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.2 | TEL-02 | Telemedicine waiting queue — who is waiting, how long, whether they have paid | TEL-02.02 | GET Tele/Queue; POST start session | New | Telemedicine | §10 + §3 | Telemedicine waiting queue | Doctor sees who is waiting, for how long, and whether they have paid | Doctor Web + App | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
506 | 502 | M12 | Telemedicine | UI | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.2 | TEL-02 | Telemedicine waiting queue — who is waiting, how long, whether they have paid | TEL-02.03 | Dedicated Tele queue on dashboard (beyond E-CONSULT list) | New | Telemedicine | §10 + §3 | Telemedicine waiting queue | Doctor sees who is waiting, for how long, and whether they have paid | Doctor Web + App | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
507 | 503 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.2 | TEL-02 | Telemedicine waiting queue — who is waiting, how long, whether they have paid | TEL-02.04 | SignalR/poll | New Integration | Telemedicine | §10 + §3 | Telemedicine waiting queue | Doctor sees who is waiting, for how long, and whether they have paid | Doctor Web + App | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
508 | 504 | M12 | Telemedicine | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.2 | TEL-02 | Telemedicine waiting queue — who is waiting, how long, whether they have paid | TEL-02.05 | QA: wait time increases; paid badge matches PAY-08 | Regression | Telemedicine | §10 + §3 | Telemedicine waiting queue | Doctor sees who is waiting, for how long, and whether they have paid | Doctor Web + App | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
509 | 505 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.3 | TEL-03 | Video consultation in browser — doctor consults directly from the web portal | TEL-03.01 | DB: TeleSession (PatientAppId, RoomId, Status) | New | Telemedicine | §10 | Video consultation in browser | Doctor consults directly from the web portal | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
510 | 506 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.3 | TEL-03 | Video consultation in browser — doctor consults directly from the web portal | TEL-03.02 | API: create/end session; vendor tokens | New | Telemedicine | §10 | Video consultation in browser | Doctor consults directly from the web portal | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
511 | 507 | M12 | Telemedicine | UI | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.3 | TEL-03 | Video consultation in browser — doctor consults directly from the web portal | TEL-03.03 | Full-page video room mute/end | New | Telemedicine | §10 | Video consultation in browser | Doctor consults directly from the web portal | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
512 | 508 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.3 | TEL-03 | Video consultation in browser — doctor consults directly from the web portal | TEL-03.04 | Video SDK (Agora/Twilio/Daily) | New Integration | Telemedicine | §10 | Video consultation in browser | Doctor consults directly from the web portal | Doctor Web Portal | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
513 | 509 | M12 | Telemedicine | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.3 | TEL-03 | Video consultation in browser — doctor consults directly from the web portal | TEL-03.05 | QA: replace WhatsApp alert; session ends write timestamp | Regression | Telemedicine | §10 | Video consultation in browser | Doctor consults directly from the web portal | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
514 | 510 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.4 | TEL-04 | Video consultation on mobile — doctor and patient both consult from the app (apps in 16–17; same session tokens) | TEL-04.01 | Token API must be client-agnostic (web and mobile) | New | Telemedicine | §10 + §2.4 + §3 | Video consultation on mobile | Doctor and patient both consult from the app / Face-to-face consultation from home / Start the video or audio consultation from the phone | Patient App + Doctor App | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
515 | 511 | M12 | Telemedicine | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.4 | TEL-04 | Video consultation on mobile — doctor and patient both consult from the app (apps in 16–17; same session tokens) | TEL-04.02 | Contract tests: token TTL, room id = session id | Regression | Telemedicine | §10 + §2.4 + §3 | Video consultation on mobile | Doctor and patient both consult from the app / Face-to-face consultation from home / Start the video or audio consultation from the phone | Patient App + Doctor App | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
516 | 512 | M12 | Telemedicine | UI | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.5 | TEL-05 | Device check — camera, microphone and connection tested before joining | TEL-05.01 | Shared device-check component (web); mobile equivalent in Phase 16 | New | Telemedicine | §10 + §2.4 | Device check | Camera, microphone and connection tested before joining | Doctor Web + Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
517 | 513 | M12 | Telemedicine | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.5 | TEL-05 | Device check — camera, microphone and connection tested before joining | TEL-05.02 | QA: deny camera permission → clear guidance | Regression | Telemedicine | §10 + §2.4 | Device check | Camera, microphone and connection tested before joining | Doctor Web + Patient | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
518 | 514 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.6 | TEL-06 | Waiting room — patient waits with live status until the doctor joins | TEL-06.01 | Session status events | New | Telemedicine | §10 + §2.4 | Waiting room | Patient waits with live status / Wait with live status until the doctor joins | Patient | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
519 | 515 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.6 | TEL-06 | Waiting room — patient waits with live status until the doctor joins | TEL-06.02 | GET session status for patient token | New | Telemedicine | §10 + §2.4 | Waiting room | Patient waits with live status / Wait with live status until the doctor joins | Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
520 | 516 | M12 | Telemedicine | UI | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.6 | TEL-06 | Waiting room — patient waits with live status until the doctor joins | TEL-06.03 | Waiting room UI on web (and app later) | New | Telemedicine | §10 + §2.4 | Waiting room | Patient waits with live status / Wait with live status until the doctor joins | Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
521 | 517 | M12 | Telemedicine | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.6 | TEL-06 | Waiting room — patient waits with live status until the doctor joins | TEL-06.04 | QA: doctor join transitions patient into the call | Regression | Telemedicine | §10 + §2.4 | Waiting room | Patient waits with live status / Wait with live status until the doctor joins | Patient | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
522 | 518 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.7 | TEL-07 | Recording consent — consent captured before the consultation; no recording without it | TEL-07.01 | Write ConsentRecord TeleRecording; TeleConsentLog events | New | Telemedicine | §10 + §2.4 + §17 | Recording consent | Consent captured before the consultation; no recording without it / Explicit consent requested before any recording | Patient + Doctor | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
523 | 519 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.7 | TEL-07 | Recording consent — consent captured before the consultation; no recording without it | TEL-07.02 | API: capture consent; session.recordAllowed | New | Telemedicine | §10 + §2.4 + §17 | Recording consent | Consent captured before the consultation; no recording without it / Explicit consent requested before any recording | Patient + Doctor | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
524 | 520 | M12 | Telemedicine | UI | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.7 | TEL-07 | Recording consent — consent captured before the consultation; no recording without it | TEL-07.03 | Pre-join modal both sides | New | Telemedicine | §10 + §2.4 + §17 | Recording consent | Consent captured before the consultation; no recording without it / Explicit consent requested before any recording | Patient + Doctor | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
525 | 521 | M12 | Telemedicine | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.7 | TEL-07 | Recording consent — consent captured before the consultation; no recording without it | TEL-07.04 | QA: decline → no record; audit row still written | Regression | Telemedicine | §10 + §2.4 + §17 | Recording consent | Consent captured before the consultation; no recording without it / Explicit consent requested before any recording | Patient + Doctor | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
526 | 522 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.8 | TEL-08 | Rejoin after dropped call — either side can rejoin the same consultation | TEL-08.01 | API: Rejoin issues token if Status=Active | New | Telemedicine | §10 + §2.4 | Rejoin after dropped call | Either side can rejoin the same consultation / Rejoin the same consultation if the connection drops | Doctor + Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
527 | 523 | M12 | Telemedicine | UI | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.8 | TEL-08 | Rejoin after dropped call — either side can rejoin the same consultation | TEL-08.02 | UI Rejoin on doctor dashboard and patient waiting/call fail | New | Telemedicine | §10 + §2.4 | Rejoin after dropped call | Either side can rejoin the same consultation / Rejoin the same consultation if the connection drops | Doctor + Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
528 | 524 | M12 | Telemedicine | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.8 | TEL-08 | Rejoin after dropped call — either side can rejoin the same consultation | TEL-08.03 | QA: after End, rejoin 409 | Regression | Telemedicine | §10 + §2.4 | Rejoin after dropped call | Either side can rejoin the same consultation / Rejoin the same consultation if the connection drops | Doctor + Patient | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
529 | 525 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.9 | TEL-09 | Join failure handling — clear fallback if the call cannot connect, with options to retry | TEL-09.01 | Standardise join error codes; log TeleSessionEvent | New | Telemedicine | §10 + §2.4 | Join failure handling / Fallback & join failure handling | Clear fallback if the call cannot connect / Clear guidance if the call fails, with options to retry | Doctor + Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
530 | 526 | M12 | Telemedicine | UI | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.9 | TEL-09 | Join failure handling — clear fallback if the call cannot connect, with options to retry | TEL-09.02 | Fallback UI: retry, rejoin, contact support | New | Telemedicine | §10 + §2.4 | Join failure handling / Fallback & join failure handling | Clear fallback if the call cannot connect / Clear guidance if the call fails, with options to retry | Doctor + Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
531 | 527 | M12 | Telemedicine | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.9 | TEL-09 | Join failure handling — clear fallback if the call cannot connect, with options to retry | TEL-09.03 | QA: simulated token fail | Regression | Telemedicine | §10 + §2.4 | Join failure handling / Fallback & join failure handling | Clear fallback if the call cannot connect / Clear guidance if the call fails, with options to retry | Doctor + Patient | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
532 | 528 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.10 | TEL-10 | Case-linked chat — chat attached to the consultation record, not a loose message thread | TEL-10.01 | DB: TeleChatMessage (SessionId, PatientAppId, Body, At) | New | Telemedicine | §10 + §2.4 | Case-linked chat | Chat attached to the consultation record / Chat tied to the consultation, not a loose message thread | Doctor + Patient | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
533 | 529 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.10 | TEL-10 | Case-linked chat — chat attached to the consultation record, not a loose message thread | TEL-10.02 | API: post/list; doctor and patient only | New | Telemedicine | §10 + §2.4 | Case-linked chat | Chat attached to the consultation record / Chat tied to the consultation, not a loose message thread | Doctor + Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
534 | 530 | M12 | Telemedicine | UI | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.10 | TEL-10 | Case-linked chat — chat attached to the consultation record, not a loose message thread | TEL-10.03 | In-room chat panel | New | Telemedicine | §10 + §2.4 | Case-linked chat | Chat attached to the consultation record / Chat tied to the consultation, not a loose message thread | Doctor + Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
535 | 531 | M12 | Telemedicine | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.10 | TEL-10 | Case-linked chat — chat attached to the consultation record, not a loose message thread | TEL-10.04 | QA: IDOR other session 403 | Regression | Telemedicine | §10 + §2.4 | Case-linked chat | Chat attached to the consultation record / Chat tied to the consultation, not a loose message thread | Doctor + Patient | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
536 | 532 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.11 | TEL-11 | Consultation summary — issued to the patient at the end of the call | TEL-11.01 | DB: ConsultationSummary (PatientAppId, Text, At) | New | Telemedicine | §10 + §2.4 | Consultation summary | Issued to the patient at the end of the call / Written summary available immediately after the call | Patient + Doctor | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
537 | 533 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.11 | TEL-11 | Consultation summary — issued to the patient at the end of the call | TEL-11.02 | API: doctor PUT; patient GET | New | Telemedicine | §10 + §2.4 | Consultation summary | Issued to the patient at the end of the call / Written summary available immediately after the call | Patient + Doctor | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
538 | 534 | M12 | Telemedicine | UI | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.11 | TEL-11 | Consultation summary — issued to the patient at the end of the call | TEL-11.03 | Post-call summary form; patient view | New | Telemedicine | §10 + §2.4 | Consultation summary | Issued to the patient at the end of the call / Written summary available immediately after the call | Patient + Doctor | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
539 | 535 | M12 | Telemedicine | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.11 | TEL-11 | Consultation summary — issued to the patient at the end of the call | TEL-11.04 | QA: private notes not copied into summary by default | Regression | Telemedicine | §10 + §2.4 | Consultation summary | Issued to the patient at the end of the call / Written summary available immediately after the call | Patient + Doctor | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
540 | 536 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.12 | TEL-12 | Instant consultation — patient requests an immediate consultation with an available doctor | TEL-12.01 | DB: InstantConsultRequest, DoctorOffer | New | Telemedicine | §10 + §2.3 | Instant consultation / Instant consult request / Queue & doctor offer | Patient can request an immediate consultation with an available doctor / See position in queue and accept an offered doctor | Patient + Doctor | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
541 | 537 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.12 | TEL-12 | Instant consultation — patient requests an immediate consultation with an available doctor | TEL-12.02 | API: request, match, offer, accept, queue position | New | Telemedicine | §10 + §2.3 | Instant consultation / Instant consult request / Queue & doctor offer | Patient can request an immediate consultation with an available doctor / See position in queue and accept an offered doctor | Patient + Doctor | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
542 | 538 | M12 | Telemedicine | UI | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.12 | TEL-12 | Instant consultation — patient requests an immediate consultation with an available doctor | TEL-12.03 | Patient instant CTA; doctor offer banner | New | Telemedicine | §10 + §2.3 | Instant consultation / Instant consult request / Queue & doctor offer | Patient can request an immediate consultation with an available doctor / See position in queue and accept an offered doctor | Patient + Doctor | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
543 | 539 | M12 | Telemedicine | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.12 | TEL-12 | Instant consultation — patient requests an immediate consultation with an available doctor | TEL-12.04 | QA: no online doctor → empty state; surcharge on checkout | Regression | Telemedicine | §10 + §2.3 | Instant consultation / Instant consult request / Queue & doctor offer | Patient can request an immediate consultation with an available doctor / See position in queue and accept an offered doctor | Patient + Doctor | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
544 | 540 | M13 | Communications | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.1 | COM-01 | SMS — appointment confirmation, registration confirmation, doctor-unavailable, OTP, reschedule and cancellation | COM-01.01 | DB: SmsTemplate, SmsMessageLog; Patient.SmsOptOut | New | Notifications | §14 | SMS | Appointment confirmation, registration confirmation, doctor-unavailable notice, OTP, reschedule and cancellation alerts | Shared | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
545 | 541 | M13 | Communications | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.1 | COM-01 | SMS — appointment confirmation, registration confirmation, doctor-unavailable, OTP, reschedule and cancellation | COM-01.02 | API: Templates CRUD; Send; History; event worker | New | Notifications | §14 | SMS | Appointment confirmation, registration confirmation, doctor-unavailable notice, OTP, reschedule and cancellation alerts | Shared | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
546 | 542 | M13 | Communications | UI | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.1 | COM-01 | SMS — appointment confirmation, registration confirmation, doctor-unavailable, OTP, reschedule and cancellation | COM-01.03 | Doctor /doctor/sms enable-per-event; admin templates | New | Notifications | §14 | SMS | Appointment confirmation, registration confirmation, doctor-unavailable notice, OTP, reschedule and cancellation alerts | Shared | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
547 | 543 | M13 | Communications | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.1 | COM-01 | SMS — appointment confirmation, registration confirmation, doctor-unavailable, OTP, reschedule and cancellation | COM-01.04 | MSG91/Twilio/etc. from PRE-03 | New Integration | Notifications | §14 | SMS | Appointment confirmation, registration confirmation, doctor-unavailable notice, OTP, reschedule and cancellation alerts | Shared | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
548 | 544 | M13 | Communications | QA | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.1 | COM-01 | SMS — appointment confirmation, registration confirmation, doctor-unavailable, OTP, reschedule and cancellation | COM-01.05 | QA: OTP SMS; reschedule old→new; cancel; doctor unavailable; opt-out honored | Regression | Notifications | §14 | SMS | Appointment confirmation, registration confirmation, doctor-unavailable notice, OTP, reschedule and cancellation alerts | Shared | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
549 | 545 | M13 | Communications | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.2 | COM-02 | WhatsApp — templates, offers, health tips and bulk messaging with delivery reports and opt-out (complete remaining ~50%) | COM-02.01 | Extend WhatsApp log if delivery receipts not stored | Existing Improvement | Notifications | §14 | WhatsApp | Templates, offers, health tips and bulk messaging to patients, with delivery reports and opt-out | Doctor Web | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
550 | 546 | M13 | Communications | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.2 | COM-02 | WhatsApp — templates, offers, health tips and bulk messaging with delivery reports and opt-out (complete remaining ~50%) | COM-02.02 | Finish bulk worker + receipt webhook | Existing Improvement | Notifications | §14 | WhatsApp | Templates, offers, health tips and bulk messaging to patients, with delivery reports and opt-out | Doctor Web | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
551 | 547 | M13 | Communications | UI | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.2 | COM-02 | WhatsApp — templates, offers, health tips and bulk messaging with delivery reports and opt-out (complete remaining ~50%) | COM-02.03 | WhatsAppModal: campaign status, failures, opt-out | Existing Improvement | Notifications | §14 | WhatsApp | Templates, offers, health tips and bulk messaging to patients, with delivery reports and opt-out | Doctor Web | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
552 | 548 | M13 | Communications | QA | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.2 | COM-02 | WhatsApp — templates, offers, health tips and bulk messaging with delivery reports and opt-out (complete remaining ~50%) | COM-02.04 | QA: opt-in required; template rejected state | Regression | Notifications | §14 | WhatsApp | Templates, offers, health tips and bulk messaging to patients, with delivery reports and opt-out | Doctor Web | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
553 | 549 | M13 | Communications | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.3 | COM-03 | Push notifications — booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests | COM-03.01 | DB: DeviceToken, AppNotification | New | Notifications | §14 + §2.9 + §3 | Push notifications | Booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests / Patient waiting, new booking, reschedule, cancellation, refill request, payment received | Patient App + Doctor App | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
554 | 550 | M13 | Communications | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.3 | COM-03 | Push notifications — booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests | COM-03.02 | API: Devices/Register; Notifications/Send; list | New | Notifications | §14 + §2.9 + §3 | Push notifications | Booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests / Patient waiting, new booking, reschedule, cancellation, refill request, payment received | Patient App + Doctor App | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
555 | 551 | M13 | Communications | UI | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.3 | COM-03 | Push notifications — booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests | COM-03.03 | Server event hooks (apps consume in 16–17) | New | Notifications | §14 + §2.9 + §3 | Push notifications | Booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests / Patient waiting, new booking, reschedule, cancellation, refill request, payment received | Patient App + Doctor App | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
556 | 552 | M13 | Communications | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.3 | COM-03 | Push notifications — booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests | COM-03.04 | FCM + APNs | New Integration | Notifications | §14 + §2.9 + §3 | Push notifications | Booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests / Patient waiting, new booking, reschedule, cancellation, refill request, payment received | Patient App + Doctor App | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
557 | 553 | M13 | Communications | QA | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.3 | COM-03 | Push notifications — booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests | COM-03.05 | QA: doctor and patient payloads isolated; token refresh | Regression | Notifications | §14 + §2.9 + §3 | Push notifications | Booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests / Patient waiting, new booking, reschedule, cancellation, refill request, payment received | Patient App + Doctor App | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
558 | 554 | M13 | Communications | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.4 | COM-04 | Email — registration, activation, password reset, invoices and receipts | COM-04.01 | EmailMessageLog if missing | Existing Improvement | Notifications | §14 | Email | Registration, activation, password reset, invoices and receipts | Shared | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
559 | 555 | M13 | Communications | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.4 | COM-04 | Email — registration, activation, password reset, invoices and receipts | COM-04.02 | Send invoice/receipt email on PAID; keep activation/reset | Existing Improvement | Notifications | §14 | Email | Registration, activation, password reset, invoices and receipts | Shared | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
560 | 556 | M13 | Communications | UI | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.4 | COM-04 | Email — registration, activation, password reset, invoices and receipts | COM-04.03 | No new public page — transactional only | Existing Improvement | Notifications | §14 | Email | Registration, activation, password reset, invoices and receipts | Shared | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
561 | 557 | M13 | Communications | QA | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.4 | COM-04 | Email — registration, activation, password reset, invoices and receipts | COM-04.04 | QA: reset still has no plaintext password; invoice attached | Regression | Notifications | §14 | Email | Registration, activation, password reset, invoices and receipts | Shared | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
562 | 558 | M13 | Communications | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.5 | COM-05 | In-app notification centre — all alerts collected in one place for patients and doctors | COM-05.01 | Reuse AppNotification | New | Notifications | §14 + §2.8 | In-app notification centre / Notifications centre | All alerts collected in one place for patients and doctors / All alerts in one place | Patient App + Doctor Web/App | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
563 | 559 | M13 | Communications | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.5 | COM-05 | In-app notification centre — all alerts collected in one place for patients and doctors | COM-05.02 | GET/PATCH notifications | New | Notifications | §14 + §2.8 | In-app notification centre / Notifications centre | All alerts collected in one place for patients and doctors / All alerts in one place | Patient App + Doctor Web/App | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
564 | 560 | M13 | Communications | UI | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.5 | COM-05 | In-app notification centre — all alerts collected in one place for patients and doctors | COM-05.03 | Doctor web bell; patient/doctor app centres in 16–17 | New | Notifications | §14 + §2.8 | In-app notification centre / Notifications centre | All alerts collected in one place for patients and doctors / All alerts in one place | Patient App + Doctor Web/App | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
565 | 561 | M13 | Communications | QA | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.5 | COM-05 | In-app notification centre — all alerts collected in one place for patients and doctors | COM-05.04 | QA: mark read; empty state; not Velzon demo route | Regression | Notifications | §14 + §2.8 | In-app notification centre / Notifications centre | All alerts collected in one place for patients and doctors / All alerts in one place | Patient App + Doctor Web/App | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
566 | 562 | M14 | Support & help desk | Web | 13 | Phase 13 — Support & help desk (PDF §15) | 13.1 | SUP-01 | Patient support tickets — patients raise issues from the app and track them | SUP-01.01 | DB: SupportTicket, SupportTicketMessage, SupportTicketAttachment | New | Support | §15 + §2.9 | Patient support tickets / Help centre & support tickets | Patients raise issues from the app and track them to resolution | Patient App + Admin | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
567 | 563 | M14 | Support & help desk | Web | 13 | Phase 13 — Support & help desk (PDF §15) | 13.1 | SUP-01 | Patient support tickets — patients raise issues from the app and track them | SUP-01.02 | API: create/list/mine for patient | New | Support | §15 + §2.9 | Patient support tickets / Help centre & support tickets | Patients raise issues from the app and track them to resolution | Patient App + Admin | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
568 | 564 | M14 | Support & help desk | UI | 13 | Phase 13 — Support & help desk (PDF §15) | 13.1 | SUP-01 | Patient support tickets — patients raise issues from the app and track them | SUP-01.03 | Patient app screens in Phase 16; web help optional | New | Support | §15 + §2.9 | Patient support tickets / Help centre & support tickets | Patients raise issues from the app and track them to resolution | Patient App + Admin | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
569 | 565 | M14 | Support & help desk | QA | 13 | Phase 13 — Support & help desk (PDF §15) | 13.1 | SUP-01 | Patient support tickets — patients raise issues from the app and track them | SUP-01.04 | QA: IDOR; attachment via SEC-09 | Regression | Support | §15 + §2.9 | Patient support tickets / Help centre & support tickets | Patients raise issues from the app and track them to resolution | Patient App + Admin | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
570 | 566 | M14 | Support & help desk | Web | 13 | Phase 13 — Support & help desk (PDF §15) | 13.2 | SUP-02 | Doctor support tickets — doctors raise issues from the portal | SUP-02.01 | Reuse SupportTicket with ReporterRole=Doctor | New | Support | §15 | Doctor support tickets | Doctors raise issues from the portal | Doctor Web + Admin | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
571 | 567 | M14 | Support & help desk | UI | 13 | Phase 13 — Support & help desk (PDF §15) | 13.2 | SUP-02 | Doctor support tickets — doctors raise issues from the portal | SUP-02.02 | /doctor/support list/create/detail | New | Support | §15 | Doctor support tickets | Doctors raise issues from the portal | Doctor Web + Admin | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
572 | 568 | M14 | Support & help desk | QA | 13 | Phase 13 — Support & help desk (PDF §15) | 13.2 | SUP-02 | Doctor support tickets — doctors raise issues from the portal | SUP-02.03 | QA: doctor cannot see another doctor’s tickets | Regression | Support | §15 | Doctor support tickets | Doctors raise issues from the portal | Doctor Web + Admin | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
573 | 569 | M14 | Support & help desk | Web | 13 | Phase 13 — Support & help desk (PDF §15) | 13.3 | SUP-03 | Admin issue queue — all issues in one queue with priority, assignment and status | SUP-03.01 | Extend ticket with Priority, Assignee, SLA | New | Support | §15 + §7.2 | Admin issue queue / Support ticket queue | All issues in one queue with priority, assignment and status / All patient and doctor issues in one queue with assignment and resolution | Admin Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
574 | 570 | M14 | Support & help desk | Web | 13 | Phase 13 — Support & help desk (PDF §15) | 13.3 | SUP-03 | Admin issue queue — all issues in one queue with priority, assignment and status | SUP-03.02 | Admin list/filter/assign/status | New | Support | §15 + §7.2 | Admin issue queue / Support ticket queue | All issues in one queue with priority, assignment and status / All patient and doctor issues in one queue with assignment and resolution | Admin Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
575 | 571 | M14 | Support & help desk | UI | 13 | Phase 13 — Support & help desk (PDF §15) | 13.3 | SUP-03 | Admin issue queue — all issues in one queue with priority, assignment and status | SUP-03.03 | /admin/support-tickets and /:id | New | Support | §15 + §7.2 | Admin issue queue / Support ticket queue | All issues in one queue with priority, assignment and status / All patient and doctor issues in one queue with assignment and resolution | Admin Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
576 | 572 | M14 | Support & help desk | QA | 13 | Phase 13 — Support & help desk (PDF §15) | 13.3 | SUP-03 | Admin issue queue — all issues in one queue with priority, assignment and status | SUP-03.04 | QA: not using Velzon ticket pages | Regression | Support | §15 + §7.2 | Admin issue queue / Support ticket queue | All issues in one queue with priority, assignment and status / All patient and doctor issues in one queue with assignment and resolution | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
577 | 573 | M14 | Support & help desk | Web | 13 | Phase 13 — Support & help desk (PDF §15) | 13.4 | SUP-04 | Ticket conversation — full message thread with attachments | SUP-04.01 | API: messages CRUD + attachment | New | Support | §15 | Ticket conversation | Full message thread with attachments | Admin + Doctor + Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
578 | 574 | M14 | Support & help desk | UI | 13 | Phase 13 — Support & help desk (PDF §15) | 13.4 | SUP-04 | Ticket conversation — full message thread with attachments | SUP-04.02 | Detail UI thread | New | Support | §15 | Ticket conversation | Full message thread with attachments | Admin + Doctor + Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
579 | 575 | M14 | Support & help desk | QA | 13 | Phase 13 — Support & help desk (PDF §15) | 13.4 | SUP-04 | Ticket conversation — full message thread with attachments | SUP-04.03 | QA: attachment unauthorised download 403 | Regression | Support | §15 | Ticket conversation | Full message thread with attachments | Admin + Doctor + Patient | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
580 | 576 | M14 | Support & help desk | UI | 13 | Phase 13 — Support & help desk (PDF §15) | 13.5 | SUP-05 | Enquiry management — website enquiries tracked (ties WEB-06) | SUP-05.01 | Admin enquiry inbox SLA fields | Existing Improvement | Support | §15 + §4 | Enquiry management | Website enquiries reach the admin team and are tracked | Admin Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
581 | 577 | M14 | Support & help desk | QA | 13 | Phase 13 — Support & help desk (PDF §15) | 13.5 | SUP-05 | Enquiry management — website enquiries tracked (ties WEB-06) | SUP-05.02 | QA: convert to ticket keeps original enquiry id | Regression | Support | §15 + §4 | Enquiry management | Website enquiries reach the admin team and are tracked | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
582 | 578 | M14 | Support & help desk | Web | 13 | Phase 13 — Support & help desk (PDF §15) | 13.6 | SUP-06 | Help centre — self-service help content for patients | SUP-06.01 | HelpArticle table or reuse blog category=help | New | Support | §15 + §2.9 | Help centre | Self-service help content for patients | Patient Website + App | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
583 | 579 | M14 | Support & help desk | Web | 13 | Phase 13 — Support & help desk (PDF §15) | 13.6 | SUP-06 | Help centre — self-service help content for patients | SUP-06.02 | Public GET help articles | New | Support | §15 + §2.9 | Help centre | Self-service help content for patients | Patient Website + App | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
584 | 580 | M14 | Support & help desk | UI | 13 | Phase 13 — Support & help desk (PDF §15) | 13.6 | SUP-06 | Help centre — self-service help content for patients | SUP-06.03 | Help centre list/detail | New | Support | §15 + §2.9 | Help centre | Self-service help content for patients | Patient Website + App | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
585 | 581 | M14 | Support & help desk | QA | 13 | Phase 13 — Support & help desk (PDF §15) | 13.6 | SUP-06 | Help centre — self-service help content for patients | SUP-06.04 | QA: unpublished hidden | Regression | Support | §15 + §2.9 | Help centre | Self-service help content for patients | Patient Website + App | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
586 | 582 | M14 | Support & help desk | Web | 13 | Phase 13 — Support & help desk (PDF §15) | 13.7 | SUP-07 | Assisted booking — help for patients who need support booking | SUP-07.01 | Flag BookingChannel=Assisted; AssistedRequest ticket type | New | Support | §15 + §2.9 | Assisted booking | Support for patients who need help booking / Help for patients who need support booking | Support + Reception + Patient | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
587 | 583 | M14 | Support & help desk | Web | 13 | Phase 13 — Support & help desk (PDF §15) | 13.7 | SUP-07 | Assisted booking — help for patients who need support booking | SUP-07.02 | API: request assistance; staff completes WEB-04 create on behalf | New | Support | §15 + §2.9 | Assisted booking | Support for patients who need help booking / Help for patients who need support booking | Support + Reception + Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
588 | 584 | M14 | Support & help desk | UI | 13 | Phase 13 — Support & help desk (PDF §15) | 13.7 | SUP-07 | Assisted booking — help for patients who need support booking | SUP-07.03 | Patient CTA; admin/reception assisted-book wizard | New | Support | §15 + §2.9 | Assisted booking | Support for patients who need help booking / Help for patients who need support booking | Support + Reception + Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
589 | 585 | M14 | Support & help desk | QA | 13 | Phase 13 — Support & help desk (PDF §15) | 13.7 | SUP-07 | Assisted booking — help for patients who need support booking | SUP-07.04 | QA: consent still captured; payment still Homeocentrum | Regression | Support | §15 + §2.9 | Assisted booking | Support for patients who need help booking / Help for patients who need support booking | Support + Reception + Patient | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
590 | 586 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.1 | MED-01 | Pharmacy partner onboarding — licensed premises, licence records, activation checklist | MED-01.01 | DB: PharmacyPartner, PharmacyLicence, activation checklist fields | New | HomeoMeds | §12 + §7.2 | Pharmacy partner onboarding / Pharmacy partner management | Licensed premises registered with licence records and an activation checklist / Onboard and activate licensed pharmacies | Pharmacy + Admin | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
591 | 587 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.1 | MED-01 | Pharmacy partner onboarding — licensed premises, licence records, activation checklist | MED-01.02 | API: onboard, admin activate, pharmacy login role | New | HomeoMeds | §12 + §7.2 | Pharmacy partner onboarding / Pharmacy partner management | Licensed premises registered with licence records and an activation checklist / Onboard and activate licensed pharmacies | Pharmacy + Admin | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
592 | 588 | M15 | HomeoMeds | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.1 | MED-01 | Pharmacy partner onboarding — licensed premises, licence records, activation checklist | MED-01.03 | /pharmacy/onboard; /admin pharmacy partners | New | HomeoMeds | §12 + §7.2 | Pharmacy partner onboarding / Pharmacy partner management | Licensed premises registered with licence records and an activation checklist / Onboard and activate licensed pharmacies | Pharmacy + Admin | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
593 | 589 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.1 | MED-01 | Pharmacy partner onboarding — licensed premises, licence records, activation checklist | MED-01.04 | QA: checklist incomplete blocks activate | Regression | HomeoMeds | §12 + §7.2 | Pharmacy partner onboarding / Pharmacy partner management | Licensed premises registered with licence records and an activation checklist / Onboard and activate licensed pharmacies | Pharmacy + Admin | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
594 | 590 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.2 | MED-02 | Licence gating — expired or suspended licences blocked automatically from receiving orders | MED-02.01 | Job: mark licence expired/suspended; exclude from routing | New | HomeoMeds | §12 | Licence gating | Pharmacies with expired or suspended licences are blocked automatically from receiving orders | Backend | Backend | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
595 | 591 | M15 | HomeoMeds | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.2 | MED-02 | Licence gating — expired or suspended licences blocked automatically from receiving orders | MED-02.02 | Pharmacy console status banner | New | HomeoMeds | §12 | Licence gating | Pharmacies with expired or suspended licences are blocked automatically from receiving orders | Backend | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
596 | 592 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.2 | MED-02 | Licence gating — expired or suspended licences blocked automatically from receiving orders | MED-02.03 | QA: expire a licence in test → order not offered | Regression | HomeoMeds | §12 | Licence gating | Pharmacies with expired or suspended licences are blocked automatically from receiving orders | Backend | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
597 | 593 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.3 | MED-03 | Fulfilment consent & pharmacy selection — patient chooses the seller and consents before the prescription is shared | MED-03.01 | Consent + selected PharmacyPartnerId on MedicineOrder | New | HomeoMeds | §12 + §2.7 | Fulfilment consent & pharmacy selection | The patient chooses the seller and consents before the prescription is shared | Patient | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
598 | 594 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.3 | MED-03 | Fulfilment consent & pharmacy selection — patient chooses the seller and consents before the prescription is shared | MED-03.02 | API: list sellers; select; grant consent | New | HomeoMeds | §12 + §2.7 | Fulfilment consent & pharmacy selection | The patient chooses the seller and consents before the prescription is shared | Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
599 | 595 | M15 | HomeoMeds | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.3 | MED-03 | Fulfilment consent & pharmacy selection — patient chooses the seller and consents before the prescription is shared | MED-03.03 | Patient pharmacy pick UI (web optional + app Phase 16) | New | HomeoMeds | §12 + §2.7 | Fulfilment consent & pharmacy selection | The patient chooses the seller and consents before the prescription is shared | Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
600 | 596 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.3 | MED-03 | Fulfilment consent & pharmacy selection — patient chooses the seller and consents before the prescription is shared | MED-03.04 | QA: without consent, handoff API 403 | Regression | HomeoMeds | §12 + §2.7 | Fulfilment consent & pharmacy selection | The patient chooses the seller and consents before the prescription is shared | Patient | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
601 | 597 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.4 | MED-04 | Prescription handoff — signed prescription becomes the order directly — no re-entry, no transcription errors | MED-04.01 | DB: MedicineOrder, MedicineOrderItem from ErxSnapshot | New | HomeoMeds | §12 + §2.7 | Prescription handoff / Order start | The signed prescription becomes the order directly — no re-entry, no transcription errors / Start an order directly from the prescription | Patient + Pharmacy | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
602 | 598 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.4 | MED-04 | Prescription handoff — signed prescription becomes the order directly — no re-entry, no transcription errors | MED-04.02 | API: POST order from ErxId | New | HomeoMeds | §12 + §2.7 | Prescription handoff / Order start | The signed prescription becomes the order directly — no re-entry, no transcription errors / Start an order directly from the prescription | Patient + Pharmacy | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
603 | 599 | M15 | HomeoMeds | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.4 | MED-04 | Prescription handoff — signed prescription becomes the order directly — no re-entry, no transcription errors | MED-04.03 | Order start from patient eRx screen | New | HomeoMeds | §12 + §2.7 | Prescription handoff / Order start | The signed prescription becomes the order directly — no re-entry, no transcription errors / Start an order directly from the prescription | Patient + Pharmacy | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
604 | 600 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.4 | MED-04 | Prescription handoff — signed prescription becomes the order directly — no re-entry, no transcription errors | MED-04.04 | QA: line count mismatch fails sign-off | Regression | HomeoMeds | §12 + §2.7 | Prescription handoff / Order start | The signed prescription becomes the order directly — no re-entry, no transcription errors / Start an order directly from the prescription | Patient + Pharmacy | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
605 | 601 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.5 | MED-05 | Rule-based seller routing — licence validity, service area, working hours and capacity | MED-05.01 | DB: SellerRoutingRule (area, hours, capacity) | New | HomeoMeds | §12 | Rule-based seller routing | Orders routed by licence validity, service area, working hours and capacity | Backend | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
606 | 602 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.5 | MED-05 | Rule-based seller routing — licence validity, service area, working hours and capacity | MED-05.02 | Routing service used by seller list API | New | HomeoMeds | §12 | Rule-based seller routing | Orders routed by licence validity, service area, working hours and capacity | Backend | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
607 | 603 | M15 | HomeoMeds | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.5 | MED-05 | Rule-based seller routing — licence validity, service area, working hours and capacity | MED-05.03 | Admin/pharmacy hours and area config UI | New | HomeoMeds | §12 | Rule-based seller routing | Orders routed by licence validity, service area, working hours and capacity | Backend | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
608 | 604 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.5 | MED-05 | Rule-based seller routing — licence validity, service area, working hours and capacity | MED-05.04 | QA: capacity full excluded; hours closed excluded | Regression | HomeoMeds | §12 | Rule-based seller routing | Orders routed by licence validity, service area, working hours and capacity | Backend | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
609 | 605 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.6 | MED-06 | Manual stock confirmation — pharmacy confirms availability — no live inventory integration required | MED-06.01 | Accept payload includes stock confirmation; reject reason OUT_OF_STOCK | New | HomeoMeds | §12 | Manual stock confirmation | The pharmacy confirms availability — no live inventory integration required | Pharmacy console | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
610 | 606 | M15 | HomeoMeds | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.6 | MED-06 | Manual stock confirmation — pharmacy confirms availability — no live inventory integration required | MED-06.02 | Pharmacy UI confirm availability | New | HomeoMeds | §12 | Manual stock confirmation | The pharmacy confirms availability — no live inventory integration required | Pharmacy console | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
611 | 607 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.6 | MED-06 | Manual stock confirmation — pharmacy confirms availability — no live inventory integration required | MED-06.03 | QA: no inventory SKU table required | Regression | HomeoMeds | §12 | Manual stock confirmation | The pharmacy confirms availability — no live inventory integration required | Pharmacy console | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
612 | 608 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.7 | MED-07 | Pharmacy console — accept or reject, enter price quote, mark ready and dispatched | MED-07.01 | Order status machine: Offered/Accepted/Rejected/Quoted/Paid/Ready/Dispatched/Delivered | New | HomeoMeds | §12 | Pharmacy console | Accept or reject orders, enter the price quote, mark ready and dispatched | Pharmacy console | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
613 | 609 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.7 | MED-07 | Pharmacy console — accept or reject, enter price quote, mark ready and dispatched | MED-07.02 | API: accept(OTP), reject, quote, ready, dispatch | New | HomeoMeds | §12 | Pharmacy console | Accept or reject orders, enter the price quote, mark ready and dispatched | Pharmacy console | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
614 | 610 | M15 | HomeoMeds | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.7 | MED-07 | Pharmacy console — accept or reject, enter price quote, mark ready and dispatched | MED-07.03 | /pharmacy/orders and detail | New | HomeoMeds | §12 | Pharmacy console | Accept or reject orders, enter the price quote, mark ready and dispatched | Pharmacy console | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
615 | 611 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.7 | MED-07 | Pharmacy console — accept or reject, enter price quote, mark ready and dispatched | MED-07.04 | OTP on accept | New Integration | HomeoMeds | §12 | Pharmacy console | Accept or reject orders, enter the price quote, mark ready and dispatched | Pharmacy console | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
616 | 612 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.7 | MED-07 | Pharmacy console — accept or reject, enter price quote, mark ready and dispatched | MED-07.05 | QA: accept without OTP fails; names still hidden to patient until accept succeeds | Regression | HomeoMeds | §12 | Pharmacy console | Accept or reject orders, enter the price quote, mark ready and dispatched | Pharmacy console | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
617 | 613 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.8 | MED-08 | Quote before payment — the patient always sees the price before paying | MED-08.01 | DB: MedicineQuote | New | HomeoMeds | §12 + §2.7 | Quote before payment / Pharmacy selection & quote | The patient always sees the price before paying / Choose a licensed pharmacy and see the price before paying | Patient | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
618 | 614 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.8 | MED-08 | Quote before payment — the patient always sees the price before paying | MED-08.02 | API: quote, patient accept quote, then create medicine payment | New | HomeoMeds | §12 + §2.7 | Quote before payment / Pharmacy selection & quote | The patient always sees the price before paying / Choose a licensed pharmacy and see the price before paying | Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
619 | 615 | M15 | HomeoMeds | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.8 | MED-08 | Quote before payment — the patient always sees the price before paying | MED-08.03 | Patient quote screen | New | HomeoMeds | §12 + §2.7 | Quote before payment / Pharmacy selection & quote | The patient always sees the price before paying / Choose a licensed pharmacy and see the price before paying | Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
620 | 616 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.8 | MED-08 | Quote before payment — the patient always sees the price before paying | MED-08.04 | QA: price change after quote invalidates old quote | Regression | HomeoMeds | §12 + §2.7 | Quote before payment / Pharmacy selection & quote | The patient always sees the price before paying / Choose a licensed pharmacy and see the price before paying | Patient | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
621 | 617 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.9 | MED-09 | Payment or cash on delivery — both options, with status tracking | MED-09.01 | Wire PAY-07 CreateMedicineOrder; COD status enum | New | HomeoMeds | §12 + §9 | Payment or cash on delivery | Both options supported, with status tracking | Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
622 | 618 | M15 | HomeoMeds | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.9 | MED-09 | Payment or cash on delivery — both options, with status tracking | MED-09.02 | Patient pay vs COD UI | New | HomeoMeds | §12 + §9 | Payment or cash on delivery | Both options supported, with status tracking | Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
623 | 619 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.9 | MED-09 | Payment or cash on delivery — both options, with status tracking | MED-09.03 | QA: COD vs prepaid ledger split | Regression | HomeoMeds | §12 + §9 | Payment or cash on delivery | Both options supported, with status tracking | Patient | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
624 | 620 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.10 | MED-10 | Order tracking — live status for the patient at every stage | MED-10.01 | DB: MedicineOrderEvent | New | HomeoMeds | §12 + §2.7 | Order tracking | Live status for the patient at every stage / Live status from accepted to delivered | Patient | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
625 | 621 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.10 | MED-10 | Order tracking — live status for the patient at every stage | MED-10.02 | GET tracking by order id (patient) | New | HomeoMeds | §12 + §2.7 | Order tracking | Live status for the patient at every stage / Live status from accepted to delivered | Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
626 | 622 | M15 | HomeoMeds | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.10 | MED-10 | Order tracking — live status for the patient at every stage | MED-10.03 | Tracking UI | New | HomeoMeds | §12 + §2.7 | Order tracking | Live status for the patient at every stage / Live status from accepted to delivered | Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
627 | 623 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.10 | MED-10 | Order tracking — live status for the patient at every stage | MED-10.04 | Push on status change | New Integration | HomeoMeds | §12 + §2.7 | Order tracking | Live status for the patient at every stage / Live status from accepted to delivered | Patient | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
628 | 624 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.10 | MED-10 | Order tracking — live status for the patient at every stage | MED-10.05 | QA: dispatched without ready is invalid transition | Regression | HomeoMeds | §12 + §2.7 | Order tracking | Live status for the patient at every stage / Live status from accepted to delivered | Patient | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
629 | 625 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.11 | MED-11 | Medicine ledger shares — seller, platform and delivery recorded (FIN-03 live fill) | MED-11.01 | On captured medicine payment write three-share ledger lines | New | HomeoMeds | §12 + §8 | Medicine ledger | Seller, platform and delivery shares recorded separately from consultation money | Account | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
630 | 626 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.11 | MED-11 | Medicine ledger shares — seller, platform and delivery recorded (FIN-03 live fill) | MED-11.02 | QA: consult GMV unchanged by a medicine order | Regression | HomeoMeds | §12 + §8 | Medicine ledger | Seller, platform and delivery shares recorded separately from consultation money | Account | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
631 | 627 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.12 | MED-12 | Order exception queue — stuck, rejected or failed orders always surfaced — never silent | MED-12.01 | Exception rows for medicine orders | New | HomeoMeds | §12 | Order exception queue | Stuck, rejected or failed orders are always surfaced to the operations team — never silent | Admin + Account | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
632 | 628 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.12 | MED-12 | Order exception queue — stuck, rejected or failed orders always surfaced — never silent | MED-12.02 | Admin/ops list/detail/retry re-route | New | HomeoMeds | §12 | Order exception queue | Stuck, rejected or failed orders are always surfaced to the operations team — never silent | Admin + Account | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
633 | 629 | M15 | HomeoMeds | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.12 | MED-12 | Order exception queue — stuck, rejected or failed orders always surfaced — never silent | MED-12.03 | /admin/homemeds-exceptions | New | HomeoMeds | §12 | Order exception queue | Stuck, rejected or failed orders are always surfaced to the operations team — never silent | Admin + Account | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
634 | 630 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.12 | MED-12 | Order exception queue — stuck, rejected or failed orders always surfaced — never silent | MED-12.04 | QA: silent discard impossible (metric + queue) | Regression | HomeoMeds | §12 | Order exception queue | Stuck, rejected or failed orders are always surfaced to the operations team — never silent | Admin + Account | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
635 | 631 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.13 | MED-13 | OTP-based control — key actions verified by OTP so Homeocentrum can monitor and trace every transaction | MED-13.01 | Bind OTP actions: PharmacyAccept, (optional) QuoteLock, Payout already FIN-05 | New | HomeoMeds | §12 + §17 | OTP-based control | Key actions verified by OTP so Homeocentrum can monitor and trace every transaction | Pharmacy + Account | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
636 | 632 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.13 | MED-13 | OTP-based control — key actions verified by OTP so Homeocentrum can monitor and trace every transaction | MED-13.02 | QA: Account OTP audit shows pharmacy accept | Regression | HomeoMeds | §12 + §17 | OTP-based control | Key actions verified by OTP so Homeocentrum can monitor and trace every transaction | Pharmacy + Account | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
637 | 633 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.14 | MED-14 | Refill orders — repeat orders raised from an existing prescription | MED-14.01 | On doctor approve, clone order from snapshot; patient one-tap | New | HomeoMeds | §12 + §2.7 + §11 | Refill orders / Order detail & refill | Repeat orders raised from an existing prescription / Full order history and one-tap refill request | Patient + Doctor | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
638 | 634 | M15 | HomeoMeds | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.14 | MED-14 | Refill orders — repeat orders raised from an existing prescription | MED-14.02 | Patient order detail + refill CTA | New | HomeoMeds | §12 + §2.7 + §11 | Refill orders / Order detail & refill | Repeat orders raised from an existing prescription / Full order history and one-tap refill request | Patient + Doctor | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
639 | 635 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.14 | MED-14 | Refill orders — repeat orders raised from an existing prescription | MED-14.03 | QA: original eRx unchanged | Regression | HomeoMeds | §12 + §2.7 + §11 | Refill orders / Order detail & refill | Repeat orders raised from an existing prescription / Full order history and one-tap refill request | Patient + Doctor | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
640 | 636 | M15 | HomeoMeds | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.15 | MED-15 | Order review & consent (patient) — confirm and consent before the prescription is shared | MED-15.01 | Patient review screen before handoff | New | HomeoMeds | §2.7 | Order review & consent | Confirm and consent before the prescription is shared | Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
641 | 637 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.15 | MED-15 | Order review & consent (patient) — confirm and consent before the prescription is shared | MED-15.02 | QA: back button does not share | Regression | HomeoMeds | §2.7 | Order review & consent | Confirm and consent before the prescription is shared | Patient | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
642 | 638 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.16 | MED-16 | Medicines tab — all medicine orders in one place (API now; app UI in Phase 16) | MED-16.01 | GET /api/Patient/MedicineOrders | New | HomeoMeds | §2.7 | Medicines tab | All medicine orders in one place | Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
643 | 639 | M15 | HomeoMeds | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.16 | MED-16 | Medicines tab — all medicine orders in one place (API now; app UI in Phase 16) | MED-16.02 | Optional web list; mobile tab later | New | HomeoMeds | §2.7 | Medicines tab | All medicine orders in one place | Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
644 | 640 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.16 | MED-16 | Medicines tab — all medicine orders in one place (API now; app UI in Phase 16) | MED-16.03 | QA: IDOR other patient 403 | Regression | HomeoMeds | §2.7 | Medicines tab | All medicine orders in one place | Patient | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
645 | 641 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.1 | CON-01 | Family members — add family members under one account | CON-01.01 | DB: FamilyMember | New | Patient identity | §2.1 | Family members | Add family members under one account | Patient App (API now) | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
646 | 642 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.1 | CON-01 | Family members — add family members under one account | CON-01.02 | API: CRUD family; book-as-member | New | Patient identity | §2.1 | Family members | Add family members under one account | Patient App (API now) | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
647 | 643 | M16 | Patient continuity APIs | UI | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.1 | CON-01 | Family members — add family members under one account | CON-01.03 | Consumed in Phase 16 | New | Patient identity | §2.1 | Family members | Add family members under one account | Patient App (API now) | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
648 | 644 | M16 | Patient continuity APIs | QA | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.1 | CON-01 | Family members — add family members under one account | CON-01.04 | QA: adult consent rules for minors documented | Regression | Patient identity | §2.1 | Family members | Add family members under one account | Patient App (API now) | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
649 | 645 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.2 | CON-02 | Caregiver authorization — let a family member book and manage on their behalf | CON-02.01 | DB: CaregiverAuth | New | Patient identity | §2.1 | Caregiver authorization | Let a family member book and manage on their behalf | Patient App (API now) | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
650 | 646 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.2 | CON-02 | Caregiver authorization — let a family member book and manage on their behalf | CON-02.02 | API: grant/revoke/list; booking authorisation check | New | Patient identity | §2.1 | Caregiver authorization | Let a family member book and manage on their behalf | Patient App (API now) | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
651 | 647 | M16 | Patient continuity APIs | UI | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.2 | CON-02 | Caregiver authorization — let a family member book and manage on their behalf | CON-02.03 | Consumed in Phase 16 | New | Patient identity | §2.1 | Caregiver authorization | Let a family member book and manage on their behalf | Patient App (API now) | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
652 | 648 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.2 | CON-02 | Caregiver authorization — let a family member book and manage on their behalf | CON-02.04 | OTP on grant | New Integration | Patient identity | §2.1 | Caregiver authorization | Let a family member book and manage on their behalf | Patient App (API now) | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
653 | 649 | M16 | Patient continuity APIs | QA | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.2 | CON-02 | Caregiver authorization — let a family member book and manage on their behalf | CON-02.05 | QA: revoked token cannot book | Regression | Patient identity | §2.1 | Caregiver authorization | Let a family member book and manage on their behalf | Patient App (API now) | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
654 | 650 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.3 | CON-03 | Records timeline + consultation note + document upload APIs | CON-03.01 | Reuse appointments + summary + eRx + SecureDocument | New | Patient records | §2.5 | Records timeline / Consultation note / Document upload | Complete visit history in date order / Doctor’s notes for each visit / Upload reports, scans and previous prescriptions | Patient App (API now) | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
655 | 651 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.3 | CON-03 | Records timeline + consultation note + document upload APIs | CON-03.02 | GET timeline; GET consultation note (summary); POST documents | New | Patient records | §2.5 | Records timeline / Consultation note / Document upload | Complete visit history in date order / Doctor’s notes for each visit / Upload reports, scans and previous prescriptions | Patient App (API now) | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
656 | 652 | M16 | Patient continuity APIs | UI | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.3 | CON-03 | Records timeline + consultation note + document upload APIs | CON-03.03 | Consumed in Phase 16 | New | Patient records | §2.5 | Records timeline / Consultation note / Document upload | Complete visit history in date order / Doctor’s notes for each visit / Upload reports, scans and previous prescriptions | Patient App (API now) | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
657 | 653 | M16 | Patient continuity APIs | QA | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.3 | CON-03 | Records timeline + consultation note + document upload APIs | CON-03.04 | QA: notes leak test on timeline JSON | Regression | Patient records | §2.5 | Records timeline / Consultation note / Document upload | Complete visit history in date order / Doctor’s notes for each visit / Upload reports, scans and previous prescriptions | Patient App (API now) | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
658 | 654 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.4 | CON-04 | Follow-up plan & tasks — clear next steps after each consultation | CON-04.01 | DB: FollowUpPlan, FollowUpTask | New | Continuity | §2.6 | Follow-up plan & tasks | Clear next steps after each consultation | Doctor Web + Patient | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
659 | 655 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.4 | CON-04 | Follow-up plan & tasks — clear next steps after each consultation | CON-04.02 | API: doctor set; patient list/complete | New | Continuity | §2.6 | Follow-up plan & tasks | Clear next steps after each consultation | Doctor Web + Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
660 | 656 | M16 | Patient continuity APIs | UI | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.4 | CON-04 | Follow-up plan & tasks — clear next steps after each consultation | CON-04.03 | Doctor board follow-up panel; app in Phase 16 | New | Continuity | §2.6 | Follow-up plan & tasks | Clear next steps after each consultation | Doctor Web + Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
661 | 657 | M16 | Patient continuity APIs | QA | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.4 | CON-04 | Follow-up plan & tasks — clear next steps after each consultation | CON-04.04 | QA: overdue flag | Regression | Continuity | §2.6 | Follow-up plan & tasks | Clear next steps after each consultation | Doctor Web + Patient | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
662 | 658 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.5 | CON-05 | Symptom diary — record symptoms between visits | CON-05.01 | DB: SymptomDiary | New | Continuity | §2.6 | Symptom diary | Record symptoms between visits | Patient App (API now) | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
663 | 659 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.5 | CON-05 | Symptom diary — record symptoms between visits | CON-05.02 | API: patient CRUD; doctor GET by patient | New | Continuity | §2.6 | Symptom diary | Record symptoms between visits | Patient App (API now) | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
664 | 660 | M16 | Patient continuity APIs | UI | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.5 | CON-05 | Symptom diary — record symptoms between visits | CON-05.03 | Doctor board read-only; app write Phase 16 | New | Continuity | §2.6 | Symptom diary | Record symptoms between visits | Patient App (API now) | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
665 | 661 | M16 | Patient continuity APIs | QA | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.5 | CON-05 | Symptom diary — record symptoms between visits | CON-05.04 | QA: IDOR | Regression | Continuity | §2.6 | Symptom diary | Record symptoms between visits | Patient App (API now) | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
666 | 662 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.6 | CON-06 | Progress tracking — see improvement over time across visits | CON-06.01 | Derived API from diary + appointments | New | Continuity | §2.6 | Progress tracking | See improvement over time across visits | Patient + Doctor | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
667 | 663 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.6 | CON-06 | Progress tracking — see improvement over time across visits | CON-06.02 | GET progress series | New | Continuity | §2.6 | Progress tracking | See improvement over time across visits | Patient + Doctor | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
668 | 664 | M16 | Patient continuity APIs | UI | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.6 | CON-06 | Progress tracking — see improvement over time across visits | CON-06.03 | Consumed in Phase 16 | New | Continuity | §2.6 | Progress tracking | See improvement over time across visits | Patient + Doctor | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
669 | 665 | M16 | Patient continuity APIs | QA | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.6 | CON-06 | Progress tracking — see improvement over time across visits | CON-06.04 | QA: no dummy numbers | Regression | Continuity | §2.6 | Progress tracking | See improvement over time across visits | Patient + Doctor | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
670 | 666 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.7 | CON-07 | Consent centre & data rights — view, manage and withdraw consents; request data | CON-07.01 | Reuse ConsentRecord; DataRequest table | New | Privacy | §17 + §2.8 | Consent centre & data rights | Patients can view, manage and withdraw consent / View, manage and withdraw consents; request data | Patient App (API now) | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
671 | 667 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.7 | CON-07 | Consent centre & data rights — view, manage and withdraw consents; request data | CON-07.02 | API: list/withdraw; request export/delete | New | Privacy | §17 + §2.8 | Consent centre & data rights | Patients can view, manage and withdraw consent / View, manage and withdraw consents; request data | Patient App (API now) | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
672 | 668 | M16 | Patient continuity APIs | UI | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.7 | CON-07 | Consent centre & data rights — view, manage and withdraw consents; request data | CON-07.03 | Consumed in Phase 16 | New | Privacy | §17 + §2.8 | Consent centre & data rights | Patients can view, manage and withdraw consent / View, manage and withdraw consents; request data | Patient App (API now) | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
673 | 669 | M16 | Patient continuity APIs | QA | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.7 | CON-07 | Consent centre & data rights — view, manage and withdraw consents; request data | CON-07.04 | QA: withdraw marketing stops WhatsApp/SMS offers | Regression | Privacy | §17 + §2.8 | Consent centre & data rights | Patients can view, manage and withdraw consent / View, manage and withdraw consents; request data | Patient App (API now) | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
674 | 674 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.10 | CON-10 | Patient profile setup API — name, age, gender, contact and health basics | CON-10.01 | Extend Patient with health-basics JSON/columns | New | Patient identity | §2.1 | Profile setup | Name, age, gender, contact and health basics | Patient App (API now) | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
675 | 675 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.10 | CON-10 | Patient profile setup API — name, age, gender, contact and health basics | CON-10.02 | GET/PUT /api/Patient/Profile | New | Patient identity | §2.1 | Profile setup | Name, age, gender, contact and health basics | Patient App (API now) | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
676 | 676 | M16 | Patient continuity APIs | UI | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.10 | CON-10 | Patient profile setup API — name, age, gender, contact and health basics | CON-10.03 | Consumed in Phase 16 | New | Patient identity | §2.1 | Profile setup | Name, age, gender, contact and health basics | Patient App (API now) | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
677 | 677 | M16 | Patient continuity APIs | QA | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.10 | CON-10 | Patient profile setup API — name, age, gender, contact and health basics | CON-10.04 | QA: cannot escalate to doctor role via profile PUT | Regression | Patient identity | §2.1 | Profile setup | Name, age, gender, contact and health basics | Patient App (API now) | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
678 | 678 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.1 | PAT-01 | Patient app — language selection on first open | PAT-01.01 | UI: Language selection screens (empty, loading, error, offline) | New | Patient Mobile | §2.1 | Language selection | Choose preferred language on first open | Patient Mobile App | Mobile UI | Pranav Bandekar | Yes | Done | Pranav Bandekar | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Done | Pranav Bandekar | No | N/A |  | 0 | Done |  | Edit on module sheet
679 | 679 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.1 | PAT-01 | Patient app — language selection on first open | PAT-01.02 | Wire to the Phase 8–15 API for: Language selection | New | Patient Mobile | §2.1 | Language selection | Choose preferred language on first open | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
680 | 680 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.1 | PAT-01 | Patient app — language selection on first open | PAT-01.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.1 | Language selection | Choose preferred language on first open | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
681 | 681 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.1 | PAT-01 | Patient app — language selection on first open | PAT-01.04 | QA both platforms: Language selection matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.1 | Language selection | Choose preferred language on first open | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
682 | 682 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.2 | PAT-02 | Patient app — welcome and introduction | PAT-02.01 | UI: Welcome & introduction screens (empty, loading, error, offline) | New | Patient Mobile | §2.1 | Welcome & introduction | Guided introduction to the app | Patient Mobile App | Mobile UI | Pranav Bandekar | Yes | Done | Pranav Bandekar | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Done | Pranav Bandekar | No | N/A |  | 0 | Done |  | Edit on module sheet
683 | 683 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.2 | PAT-02 | Patient app — welcome and introduction | PAT-02.02 | Wire to the Phase 8–15 API for: Welcome & introduction | New | Patient Mobile | §2.1 | Welcome & introduction | Guided introduction to the app | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
684 | 684 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.2 | PAT-02 | Patient app — welcome and introduction | PAT-02.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.1 | Welcome & introduction | Guided introduction to the app | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
685 | 685 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.2 | PAT-02 | Patient app — welcome and introduction | PAT-02.04 | QA both platforms: Welcome & introduction matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.1 | Welcome & introduction | Guided introduction to the app | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
686 | 686 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.3 | PAT-03 | Patient app — mobile number + OTP login (PatientAuth) | PAT-03.01 | UI: Mobile number + OTP login screens (empty, loading, error, offline) | New | Patient Mobile | §2.1 | Mobile number + OTP login | Secure sign-in with no password to remember | Patient Mobile App | Mobile UI | Pranav Bandekar | Yes | Done | Pranav Bandekar | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Done | Pranav Bandekar | No | N/A |  | 0 | Done |  | Edit on module sheet
687 | 687 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.3 | PAT-03 | Patient app — mobile number + OTP login (PatientAuth) | PAT-03.02 | Wire to the Phase 8–15 API for: Mobile number + OTP login | New | Patient Mobile | §2.1 | Mobile number + OTP login | Secure sign-in with no password to remember | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
688 | 688 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.3 | PAT-03 | Patient app — mobile number + OTP login (PatientAuth) | PAT-03.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.1 | Mobile number + OTP login | Secure sign-in with no password to remember | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
689 | 689 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.3 | PAT-03 | Patient app — mobile number + OTP login (PatientAuth) | PAT-03.04 | QA both platforms: Mobile number + OTP login matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.1 | Mobile number + OTP login | Secure sign-in with no password to remember | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
690 | 690 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.4 | PAT-04 | Patient app — profile setup | PAT-04.01 | UI: Profile setup screens (empty, loading, error, offline) | New | Patient Mobile | §2.1 | Profile setup | Name, age, gender, contact and health basics | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
691 | 691 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.4 | PAT-04 | Patient app — profile setup | PAT-04.02 | Wire to the Phase 8–15 API for: Profile setup | New | Patient Mobile | §2.1 | Profile setup | Name, age, gender, contact and health basics | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
692 | 692 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.4 | PAT-04 | Patient app — profile setup | PAT-04.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.1 | Profile setup | Name, age, gender, contact and health basics | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
693 | 693 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.4 | PAT-04 | Patient app — profile setup | PAT-04.04 | QA both platforms: Profile setup matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.1 | Profile setup | Name, age, gender, contact and health basics | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
694 | 694 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.5 | PAT-05 | Patient app — privacy consent before data stored | PAT-05.01 | UI: Privacy consent screens (empty, loading, error, offline) | New | Patient Mobile | §2.1 | Privacy consent | Clear consent before any personal data is stored | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
695 | 695 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.5 | PAT-05 | Patient app — privacy consent before data stored | PAT-05.02 | Wire to the Phase 8–15 API for: Privacy consent | New | Patient Mobile | §2.1 | Privacy consent | Clear consent before any personal data is stored | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
696 | 696 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.5 | PAT-05 | Patient app — privacy consent before data stored | PAT-05.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.1 | Privacy consent | Clear consent before any personal data is stored | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
697 | 697 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.5 | PAT-05 | Patient app — privacy consent before data stored | PAT-05.04 | QA both platforms: Privacy consent matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.1 | Privacy consent | Clear consent before any personal data is stored | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
698 | 698 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.6 | PAT-06 | Patient app — family members | PAT-06.01 | UI: Family members screens (empty, loading, error, offline) | New | Patient Mobile | §2.1 | Family members | Add family members under one account | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
699 | 699 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.6 | PAT-06 | Patient app — family members | PAT-06.02 | Wire to the Phase 8–15 API for: Family members | New | Patient Mobile | §2.1 | Family members | Add family members under one account | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
700 | 700 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.6 | PAT-06 | Patient app — family members | PAT-06.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.1 | Family members | Add family members under one account | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
701 | 701 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.6 | PAT-06 | Patient app — family members | PAT-06.04 | QA both platforms: Family members matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.1 | Family members | Add family members under one account | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
702 | 702 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.7 | PAT-07 | Patient app — caregiver authorization | PAT-07.01 | UI: Caregiver authorization screens (empty, loading, error, offline) | New | Patient Mobile | §2.1 | Caregiver authorization | Let a family member book and manage on their behalf | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
703 | 703 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.7 | PAT-07 | Patient app — caregiver authorization | PAT-07.02 | Wire to the Phase 8–15 API for: Caregiver authorization | New | Patient Mobile | §2.1 | Caregiver authorization | Let a family member book and manage on their behalf | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
704 | 704 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.7 | PAT-07 | Patient app — caregiver authorization | PAT-07.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.1 | Caregiver authorization | Let a family member book and manage on their behalf | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
705 | 705 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.7 | PAT-07 | Patient app — caregiver authorization | PAT-07.04 | QA both platforms: Caregiver authorization matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.1 | Caregiver authorization | Let a family member book and manage on their behalf | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
706 | 706 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.8 | PAT-08 | Patient app — home dashboard | PAT-08.01 | UI: Home dashboard screens (empty, loading, error, offline) | New | Patient Mobile | §2.2 | Home dashboard | Personalised home with upcoming visits and quick actions | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
707 | 707 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.8 | PAT-08 | Patient app — home dashboard | PAT-08.02 | Wire to the Phase 8–15 API for: Home dashboard | New | Patient Mobile | §2.2 | Home dashboard | Personalised home with upcoming visits and quick actions | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
708 | 708 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.8 | PAT-08 | Patient app — home dashboard | PAT-08.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.2 | Home dashboard | Personalised home with upcoming visits and quick actions | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
709 | 709 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.8 | PAT-08 | Patient app — home dashboard | PAT-08.04 | QA both platforms: Home dashboard matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.2 | Home dashboard | Personalised home with upcoming visits and quick actions | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
710 | 710 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.9 | PAT-09 | Patient app — search and care categories | PAT-09.01 | UI: Search & care categories screens (empty, loading, error, offline) | New | Patient Mobile | §2.2 | Search & care categories | Search by name, condition or category of care | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
711 | 711 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.9 | PAT-09 | Patient app — search and care categories | PAT-09.02 | Wire to the Phase 8–15 API for: Search & care categories | New | Patient Mobile | §2.2 | Search & care categories | Search by name, condition or category of care | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
712 | 712 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.9 | PAT-09 | Patient app — search and care categories | PAT-09.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.2 | Search & care categories | Search by name, condition or category of care | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
713 | 713 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.9 | PAT-09 | Patient app — search and care categories | PAT-09.04 | QA both platforms: Search & care categories matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.2 | Search & care categories | Search by name, condition or category of care | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
714 | 714 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.10 | PAT-10 | Patient app — search results | PAT-10.01 | UI: Search results screens (empty, loading, error, offline) | New | Patient Mobile | §2.2 | Search results | Clear list of available doctors | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
715 | 715 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.10 | PAT-10 | Patient app — search results | PAT-10.02 | Wire to the Phase 8–15 API for: Search results | New | Patient Mobile | §2.2 | Search results | Clear list of available doctors | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
716 | 716 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.10 | PAT-10 | Patient app — search results | PAT-10.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.2 | Search results | Clear list of available doctors | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
717 | 717 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.10 | PAT-10 | Patient app — search results | PAT-10.04 | QA both platforms: Search results matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.2 | Search results | Clear list of available doctors | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
718 | 718 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.11 | PAT-11 | Patient app — discovery filters | PAT-11.01 | UI: Filters screens (empty, loading, error, offline) | New | Patient Mobile | §2.2 | Filters | Narrow by availability, fee, experience, language and location | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
719 | 719 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.11 | PAT-11 | Patient app — discovery filters | PAT-11.02 | Wire to the Phase 8–15 API for: Filters | New | Patient Mobile | §2.2 | Filters | Narrow by availability, fee, experience, language and location | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
720 | 720 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.11 | PAT-11 | Patient app — discovery filters | PAT-11.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.2 | Filters | Narrow by availability, fee, experience, language and location | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
721 | 721 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.11 | PAT-11 | Patient app — discovery filters | PAT-11.04 | QA both platforms: Filters matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.2 | Filters | Narrow by availability, fee, experience, language and location | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
722 | 722 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.12 | PAT-12 | Patient app — doctor profile | PAT-12.01 | UI: Doctor profile screens (empty, loading, error, offline) | New | Patient Mobile | §2.2 | Doctor profile | Full profile with qualifications, experience and consultation fee | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
723 | 723 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.12 | PAT-12 | Patient app — doctor profile | PAT-12.02 | Wire to the Phase 8–15 API for: Doctor profile | New | Patient Mobile | §2.2 | Doctor profile | Full profile with qualifications, experience and consultation fee | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
724 | 724 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.12 | PAT-12 | Patient app — doctor profile | PAT-12.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.2 | Doctor profile | Full profile with qualifications, experience and consultation fee | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
725 | 725 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.12 | PAT-12 | Patient app — doctor profile | PAT-12.04 | QA both platforms: Doctor profile matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.2 | Doctor profile | Full profile with qualifications, experience and consultation fee | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
726 | 726 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.13 | PAT-13 | Patient app — verified badge on doctor | PAT-13.01 | UI: Credentials & verification screens (empty, loading, error, offline) | New | Patient Mobile | §2.2 | Credentials & verification | Verified badge showing the doctor’s credentials are checked | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
727 | 727 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.13 | PAT-13 | Patient app — verified badge on doctor | PAT-13.02 | Wire to the Phase 8–15 API for: Credentials & verification | New | Patient Mobile | §2.2 | Credentials & verification | Verified badge showing the doctor’s credentials are checked | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
728 | 728 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.13 | PAT-13 | Patient app — verified badge on doctor | PAT-13.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.2 | Credentials & verification | Verified badge showing the doctor’s credentials are checked | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
729 | 729 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.13 | PAT-13 | Patient app — verified badge on doctor | PAT-13.04 | QA both platforms: Credentials & verification matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.2 | Credentials & verification | Verified badge showing the doctor’s credentials are checked | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
730 | 730 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.14 | PAT-14 | Patient app — ranking explanation | PAT-14.01 | UI: Ranking explanation screens (empty, loading, error, offline) | New | Patient Mobile | §2.2 | Ranking explanation | Transparent explanation of why doctors appear in a given order | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
731 | 731 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.14 | PAT-14 | Patient app — ranking explanation | PAT-14.02 | Wire to the Phase 8–15 API for: Ranking explanation | New | Patient Mobile | §2.2 | Ranking explanation | Transparent explanation of why doctors appear in a given order | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
732 | 732 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.14 | PAT-14 | Patient app — ranking explanation | PAT-14.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.2 | Ranking explanation | Transparent explanation of why doctors appear in a given order | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
733 | 733 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.14 | PAT-14 | Patient app — ranking explanation | PAT-14.04 | QA both platforms: Ranking explanation matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.2 | Ranking explanation | Transparent explanation of why doctors appear in a given order | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
734 | 734 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.15 | PAT-15 | Patient app — health articles | PAT-15.01 | UI: Health articles screens (empty, loading, error, offline) | New | Patient Mobile | §2.2 | Health articles | Educational content to build trust and engagement | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
735 | 735 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.15 | PAT-15 | Patient app — health articles | PAT-15.02 | Wire to the Phase 8–15 API for: Health articles | New | Patient Mobile | §2.2 | Health articles | Educational content to build trust and engagement | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
736 | 736 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.15 | PAT-15 | Patient app — health articles | PAT-15.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.2 | Health articles | Educational content to build trust and engagement | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
737 | 737 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.15 | PAT-15 | Patient app — health articles | PAT-15.04 | QA both platforms: Health articles matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.2 | Health articles | Educational content to build trust and engagement | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
738 | 738 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.16 | PAT-16 | Patient app — slot picker | PAT-16.01 | UI: Slot picker screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Slot picker | See real available time slots and choose one | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
739 | 739 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.16 | PAT-16 | Patient app — slot picker | PAT-16.02 | Wire to the Phase 8–15 API for: Slot picker | New | Patient Mobile | §2.3 | Slot picker | See real available time slots and choose one | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
740 | 740 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.16 | PAT-16 | Patient app — slot picker | PAT-16.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Slot picker | See real available time slots and choose one | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
741 | 741 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.16 | PAT-16 | Patient app — slot picker | PAT-16.04 | QA both platforms: Slot picker matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Slot picker | See real available time slots and choose one | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
742 | 742 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.17 | PAT-17 | Patient app — booking review and consent | PAT-17.01 | UI: Booking review & consent screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Booking review & consent | Confirm details and consent before booking | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
743 | 743 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.17 | PAT-17 | Patient app — booking review and consent | PAT-17.02 | Wire to the Phase 8–15 API for: Booking review & consent | New | Patient Mobile | §2.3 | Booking review & consent | Confirm details and consent before booking | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
744 | 744 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.17 | PAT-17 | Patient app — booking review and consent | PAT-17.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Booking review & consent | Confirm details and consent before booking | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
745 | 745 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.17 | PAT-17 | Patient app — booking review and consent | PAT-17.04 | QA both platforms: Booking review & consent matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Booking review & consent | Confirm details and consent before booking | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
746 | 746 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.18 | PAT-18 | Patient app — checkout | PAT-18.01 | UI: Checkout screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Checkout | Pay the consultation fee inside the app | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
747 | 747 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.18 | PAT-18 | Patient app — checkout | PAT-18.02 | Wire to the Phase 8–15 API for: Checkout | New | Patient Mobile | §2.3 | Checkout | Pay the consultation fee inside the app | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
748 | 748 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.18 | PAT-18 | Patient app — checkout | PAT-18.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Checkout | Pay the consultation fee inside the app | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
749 | 749 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.18 | PAT-18 | Patient app — checkout | PAT-18.04 | QA both platforms: Checkout matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Checkout | Pay the consultation fee inside the app | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
750 | 750 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.19 | PAT-19 | Patient app — payment status | PAT-19.01 | UI: Payment status screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Payment status | Immediate confirmation of paid, pending or failed | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
751 | 751 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.19 | PAT-19 | Patient app — payment status | PAT-19.02 | Wire to the Phase 8–15 API for: Payment status | New | Patient Mobile | §2.3 | Payment status | Immediate confirmation of paid, pending or failed | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
752 | 752 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.19 | PAT-19 | Patient app — payment status | PAT-19.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Payment status | Immediate confirmation of paid, pending or failed | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
753 | 753 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.19 | PAT-19 | Patient app — payment status | PAT-19.04 | QA both platforms: Payment status matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Payment status | Immediate confirmation of paid, pending or failed | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
754 | 754 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.20 | PAT-20 | Patient app — appointment detail | PAT-20.01 | UI: Appointment detail screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Appointment detail | Full booking details in one place | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
755 | 755 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.20 | PAT-20 | Patient app — appointment detail | PAT-20.02 | Wire to the Phase 8–15 API for: Appointment detail | New | Patient Mobile | §2.3 | Appointment detail | Full booking details in one place | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
756 | 756 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.20 | PAT-20 | Patient app — appointment detail | PAT-20.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Appointment detail | Full booking details in one place | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
757 | 757 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.20 | PAT-20 | Patient app — appointment detail | PAT-20.04 | QA both platforms: Appointment detail matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Appointment detail | Full booking details in one place | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
758 | 758 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.21 | PAT-21 | Patient app — reschedule | PAT-21.01 | UI: Reschedule appointment screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Reschedule appointment | Move to another slot without calling the clinic | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
759 | 759 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.21 | PAT-21 | Patient app — reschedule | PAT-21.02 | Wire to the Phase 8–15 API for: Reschedule appointment | New | Patient Mobile | §2.3 | Reschedule appointment | Move to another slot without calling the clinic | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
760 | 760 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.21 | PAT-21 | Patient app — reschedule | PAT-21.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Reschedule appointment | Move to another slot without calling the clinic | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
761 | 761 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.21 | PAT-21 | Patient app — reschedule | PAT-21.04 | QA both platforms: Reschedule appointment matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Reschedule appointment | Move to another slot without calling the clinic | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
762 | 762 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.22 | PAT-22 | Patient app — cancel | PAT-22.01 | UI: Cancel appointment screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Cancel appointment | Cancel with reason, refund handled per policy | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
763 | 763 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.22 | PAT-22 | Patient app — cancel | PAT-22.02 | Wire to the Phase 8–15 API for: Cancel appointment | New | Patient Mobile | §2.3 | Cancel appointment | Cancel with reason, refund handled per policy | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
764 | 764 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.22 | PAT-22 | Patient app — cancel | PAT-22.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Cancel appointment | Cancel with reason, refund handled per policy | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
765 | 765 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.22 | PAT-22 | Patient app — cancel | PAT-22.04 | QA both platforms: Cancel appointment matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Cancel appointment | Cancel with reason, refund handled per policy | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
766 | 766 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.23 | PAT-23 | Patient app — waitlist offer | PAT-23.01 | UI: Waitlist offer screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Waitlist offer | Get offered a slot when one is freed by a cancellation | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
767 | 767 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.23 | PAT-23 | Patient app — waitlist offer | PAT-23.02 | Wire to the Phase 8–15 API for: Waitlist offer | New | Patient Mobile | §2.3 | Waitlist offer | Get offered a slot when one is freed by a cancellation | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
768 | 768 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.23 | PAT-23 | Patient app — waitlist offer | PAT-23.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Waitlist offer | Get offered a slot when one is freed by a cancellation | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
769 | 769 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.23 | PAT-23 | Patient app — waitlist offer | PAT-23.04 | QA both platforms: Waitlist offer matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Waitlist offer | Get offered a slot when one is freed by a cancellation | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
770 | 770 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.24 | PAT-24 | Patient app — instant consult request | PAT-24.01 | UI: Instant consult request screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Instant consult request | Request an immediate consultation with an available doctor | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
771 | 771 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.24 | PAT-24 | Patient app — instant consult request | PAT-24.02 | Wire to the Phase 8–15 API for: Instant consult request | New | Patient Mobile | §2.3 | Instant consult request | Request an immediate consultation with an available doctor | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
772 | 772 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.24 | PAT-24 | Patient app — instant consult request | PAT-24.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Instant consult request | Request an immediate consultation with an available doctor | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
773 | 773 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.24 | PAT-24 | Patient app — instant consult request | PAT-24.04 | QA both platforms: Instant consult request matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Instant consult request | Request an immediate consultation with an available doctor | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
774 | 774 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.25 | PAT-25 | Patient app — queue and doctor offer | PAT-25.01 | UI: Queue & doctor offer screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Queue & doctor offer | See position in queue and accept an offered doctor | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
775 | 775 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.25 | PAT-25 | Patient app — queue and doctor offer | PAT-25.02 | Wire to the Phase 8–15 API for: Queue & doctor offer | New | Patient Mobile | §2.3 | Queue & doctor offer | See position in queue and accept an offered doctor | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
776 | 776 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.25 | PAT-25 | Patient app — queue and doctor offer | PAT-25.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Queue & doctor offer | See position in queue and accept an offered doctor | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
777 | 777 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.25 | PAT-25 | Patient app — queue and doctor offer | PAT-25.04 | QA both platforms: Queue & doctor offer matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Queue & doctor offer | See position in queue and accept an offered doctor | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
778 | 778 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.26 | PAT-26 | Patient app — device check | PAT-26.01 | UI: Device check screens (empty, loading, error, offline) | New | Patient Mobile | §2.4 | Device check | Camera, microphone and network checked before the call | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
779 | 779 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.26 | PAT-26 | Patient app — device check | PAT-26.02 | Wire to the Phase 8–15 API for: Device check | New | Patient Mobile | §2.4 | Device check | Camera, microphone and network checked before the call | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
780 | 780 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.26 | PAT-26 | Patient app — device check | PAT-26.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.4 | Device check | Camera, microphone and network checked before the call | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
781 | 781 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.26 | PAT-26 | Patient app — device check | PAT-26.04 | QA both platforms: Device check matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.4 | Device check | Camera, microphone and network checked before the call | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
782 | 782 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.27 | PAT-27 | Patient app — waiting room | PAT-27.01 | UI: Waiting room screens (empty, loading, error, offline) | New | Patient Mobile | §2.4 | Waiting room | Wait with live status until the doctor joins | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
783 | 783 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.27 | PAT-27 | Patient app — waiting room | PAT-27.02 | Wire to the Phase 8–15 API for: Waiting room | New | Patient Mobile | §2.4 | Waiting room | Wait with live status until the doctor joins | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
784 | 784 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.27 | PAT-27 | Patient app — waiting room | PAT-27.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.4 | Waiting room | Wait with live status until the doctor joins | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
785 | 785 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.27 | PAT-27 | Patient app — waiting room | PAT-27.04 | QA both platforms: Waiting room matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.4 | Waiting room | Wait with live status until the doctor joins | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
786 | 786 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.28 | PAT-28 | Patient app — live video | PAT-28.01 | UI: Live video consultation screens (empty, loading, error, offline) | New | Patient Mobile | §2.4 | Live video consultation | Face-to-face consultation from home | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
787 | 787 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.28 | PAT-28 | Patient app — live video | PAT-28.02 | Wire to the Phase 8–15 API for: Live video consultation | New | Patient Mobile | §2.4 | Live video consultation | Face-to-face consultation from home | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
788 | 788 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.28 | PAT-28 | Patient app — live video | PAT-28.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.4 | Live video consultation | Face-to-face consultation from home | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
789 | 789 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.28 | PAT-28 | Patient app — live video | PAT-28.04 | QA both platforms: Live video consultation matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.4 | Live video consultation | Face-to-face consultation from home | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
790 | 790 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.29 | PAT-29 | Patient app — recording consent | PAT-29.01 | UI: Recording consent screens (empty, loading, error, offline) | New | Patient Mobile | §2.4 | Recording consent | Explicit consent requested before any recording | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
791 | 791 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.29 | PAT-29 | Patient app — recording consent | PAT-29.02 | Wire to the Phase 8–15 API for: Recording consent | New | Patient Mobile | §2.4 | Recording consent | Explicit consent requested before any recording | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
792 | 792 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.29 | PAT-29 | Patient app — recording consent | PAT-29.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.4 | Recording consent | Explicit consent requested before any recording | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
793 | 793 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.29 | PAT-29 | Patient app — recording consent | PAT-29.04 | QA both platforms: Recording consent matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.4 | Recording consent | Explicit consent requested before any recording | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
794 | 794 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.30 | PAT-30 | Patient app — join failure fallback | PAT-30.01 | UI: Fallback & join failure handling screens (empty, loading, error, offline) | New | Patient Mobile | §2.4 | Fallback & join failure handling | Clear guidance if the call fails, with options to retry | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
795 | 795 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.30 | PAT-30 | Patient app — join failure fallback | PAT-30.02 | Wire to the Phase 8–15 API for: Fallback & join failure handling | New | Patient Mobile | §2.4 | Fallback & join failure handling | Clear guidance if the call fails, with options to retry | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
796 | 796 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.30 | PAT-30 | Patient app — join failure fallback | PAT-30.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.4 | Fallback & join failure handling | Clear guidance if the call fails, with options to retry | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
797 | 797 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.30 | PAT-30 | Patient app — join failure fallback | PAT-30.04 | QA both platforms: Fallback & join failure handling matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.4 | Fallback & join failure handling | Clear guidance if the call fails, with options to retry | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
798 | 798 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.31 | PAT-31 | Patient app — case-linked chat | PAT-31.01 | UI: Case-linked chat screens (empty, loading, error, offline) | New | Patient Mobile | §2.4 | Case-linked chat | Chat tied to the consultation, not a loose message thread | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
799 | 799 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.31 | PAT-31 | Patient app — case-linked chat | PAT-31.02 | Wire to the Phase 8–15 API for: Case-linked chat | New | Patient Mobile | §2.4 | Case-linked chat | Chat tied to the consultation, not a loose message thread | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
800 | 800 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.31 | PAT-31 | Patient app — case-linked chat | PAT-31.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.4 | Case-linked chat | Chat tied to the consultation, not a loose message thread | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
801 | 801 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.31 | PAT-31 | Patient app — case-linked chat | PAT-31.04 | QA both platforms: Case-linked chat matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.4 | Case-linked chat | Chat tied to the consultation, not a loose message thread | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
802 | 802 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.32 | PAT-32 | Patient app — consultation summary | PAT-32.01 | UI: Consultation summary screens (empty, loading, error, offline) | New | Patient Mobile | §2.4 | Consultation summary | Written summary available immediately after the call | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
803 | 803 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.32 | PAT-32 | Patient app — consultation summary | PAT-32.02 | Wire to the Phase 8–15 API for: Consultation summary | New | Patient Mobile | §2.4 | Consultation summary | Written summary available immediately after the call | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
804 | 804 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.32 | PAT-32 | Patient app — consultation summary | PAT-32.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.4 | Consultation summary | Written summary available immediately after the call | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
805 | 805 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.32 | PAT-32 | Patient app — consultation summary | PAT-32.04 | QA both platforms: Consultation summary matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.4 | Consultation summary | Written summary available immediately after the call | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
806 | 806 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.33 | PAT-33 | Patient app — rejoin | PAT-33.01 | UI: Rejoin after dropped call screens (empty, loading, error, offline) | New | Patient Mobile | §2.4 | Rejoin after dropped call | Rejoin the same consultation if the connection drops | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
807 | 807 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.33 | PAT-33 | Patient app — rejoin | PAT-33.02 | Wire to the Phase 8–15 API for: Rejoin after dropped call | New | Patient Mobile | §2.4 | Rejoin after dropped call | Rejoin the same consultation if the connection drops | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
808 | 808 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.33 | PAT-33 | Patient app — rejoin | PAT-33.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.4 | Rejoin after dropped call | Rejoin the same consultation if the connection drops | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
809 | 809 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.33 | PAT-33 | Patient app — rejoin | PAT-33.04 | QA both platforms: Rejoin after dropped call matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.4 | Rejoin after dropped call | Rejoin the same consultation if the connection drops | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
810 | 810 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.34 | PAT-34 | Patient app — records timeline | PAT-34.01 | UI: Records timeline screens (empty, loading, error, offline) | New | Patient Mobile | §2.5 | Records timeline | Complete visit history in date order | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
811 | 811 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.34 | PAT-34 | Patient app — records timeline | PAT-34.02 | Wire to the Phase 8–15 API for: Records timeline | New | Patient Mobile | §2.5 | Records timeline | Complete visit history in date order | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
812 | 812 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.34 | PAT-34 | Patient app — records timeline | PAT-34.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.5 | Records timeline | Complete visit history in date order | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
813 | 813 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.34 | PAT-34 | Patient app — records timeline | PAT-34.04 | QA both platforms: Records timeline matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.5 | Records timeline | Complete visit history in date order | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
814 | 814 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.35 | PAT-35 | Patient app — consultation note (summary, not private notes) | PAT-35.01 | UI: Consultation note screens (empty, loading, error, offline) | New | Patient Mobile | §2.5 | Consultation note | Doctor’s notes for each visit | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
815 | 815 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.35 | PAT-35 | Patient app — consultation note (summary, not private notes) | PAT-35.02 | Wire to the Phase 8–15 API for: Consultation note | New | Patient Mobile | §2.5 | Consultation note | Doctor’s notes for each visit | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
816 | 816 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.35 | PAT-35 | Patient app — consultation note (summary, not private notes) | PAT-35.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.5 | Consultation note | Doctor’s notes for each visit | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
817 | 817 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.35 | PAT-35 | Patient app — consultation note (summary, not private notes) | PAT-35.04 | QA both platforms: Consultation note matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.5 | Consultation note | Doctor’s notes for each visit | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
818 | 818 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.36 | PAT-36 | Patient app — signed eRx (codes until pharmacy accept) | PAT-36.01 | UI: Signed digital prescription screens (empty, loading, error, offline) | New | Patient Mobile | §2.5 | Signed digital prescription | Official prescription issued by the doctor | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
819 | 819 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.36 | PAT-36 | Patient app — signed eRx (codes until pharmacy accept) | PAT-36.02 | Wire to the Phase 8–15 API for: Signed digital prescription | New | Patient Mobile | §2.5 | Signed digital prescription | Official prescription issued by the doctor | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
820 | 820 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.36 | PAT-36 | Patient app — signed eRx (codes until pharmacy accept) | PAT-36.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.5 | Signed digital prescription | Official prescription issued by the doctor | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
821 | 821 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.36 | PAT-36 | Patient app — signed eRx (codes until pharmacy accept) | PAT-36.04 | QA both platforms: Signed digital prescription matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.5 | Signed digital prescription | Official prescription issued by the doctor | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
822 | 822 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.37 | PAT-37 | Patient app — document upload | PAT-37.01 | UI: Document upload screens (empty, loading, error, offline) | New | Patient Mobile | §2.5 | Document upload | Upload reports, scans and previous prescriptions | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
823 | 823 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.37 | PAT-37 | Patient app — document upload | PAT-37.02 | Wire to the Phase 8–15 API for: Document upload | New | Patient Mobile | §2.5 | Document upload | Upload reports, scans and previous prescriptions | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
824 | 824 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.37 | PAT-37 | Patient app — document upload | PAT-37.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.5 | Document upload | Upload reports, scans and previous prescriptions | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
825 | 825 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.37 | PAT-37 | Patient app — document upload | PAT-37.04 | QA both platforms: Document upload matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.5 | Document upload | Upload reports, scans and previous prescriptions | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
826 | 826 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.38 | PAT-38 | Patient app — follow-up plan and tasks | PAT-38.01 | UI: Follow-up plan & tasks screens (empty, loading, error, offline) | New | Patient Mobile | §2.6 | Follow-up plan & tasks | Clear next steps after each consultation | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
827 | 827 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.38 | PAT-38 | Patient app — follow-up plan and tasks | PAT-38.02 | Wire to the Phase 8–15 API for: Follow-up plan & tasks | New | Patient Mobile | §2.6 | Follow-up plan & tasks | Clear next steps after each consultation | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
828 | 828 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.38 | PAT-38 | Patient app — follow-up plan and tasks | PAT-38.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.6 | Follow-up plan & tasks | Clear next steps after each consultation | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
829 | 829 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.38 | PAT-38 | Patient app — follow-up plan and tasks | PAT-38.04 | QA both platforms: Follow-up plan & tasks matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.6 | Follow-up plan & tasks | Clear next steps after each consultation | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
830 | 830 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.39 | PAT-39 | Patient app — symptom diary | PAT-39.01 | UI: Symptom diary screens (empty, loading, error, offline) | New | Patient Mobile | §2.6 | Symptom diary | Record symptoms between visits | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
831 | 831 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.39 | PAT-39 | Patient app — symptom diary | PAT-39.02 | Wire to the Phase 8–15 API for: Symptom diary | New | Patient Mobile | §2.6 | Symptom diary | Record symptoms between visits | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
832 | 832 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.39 | PAT-39 | Patient app — symptom diary | PAT-39.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.6 | Symptom diary | Record symptoms between visits | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
833 | 833 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.39 | PAT-39 | Patient app — symptom diary | PAT-39.04 | QA both platforms: Symptom diary matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.6 | Symptom diary | Record symptoms between visits | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
834 | 834 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.40 | PAT-40 | Patient app — progress tracking | PAT-40.01 | UI: Progress tracking screens (empty, loading, error, offline) | New | Patient Mobile | §2.6 | Progress tracking | See improvement over time across visits | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
835 | 835 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.40 | PAT-40 | Patient app — progress tracking | PAT-40.02 | Wire to the Phase 8–15 API for: Progress tracking | New | Patient Mobile | §2.6 | Progress tracking | See improvement over time across visits | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
836 | 836 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.40 | PAT-40 | Patient app — progress tracking | PAT-40.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.6 | Progress tracking | See improvement over time across visits | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
837 | 837 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.40 | PAT-40 | Patient app — progress tracking | PAT-40.04 | QA both platforms: Progress tracking matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.6 | Progress tracking | See improvement over time across visits | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
838 | 838 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.41 | PAT-41 | Patient app — medicines tab | PAT-41.01 | UI: Medicines tab screens (empty, loading, error, offline) | New | Patient Mobile | §2.7 | Medicines tab | All medicine orders in one place | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
839 | 839 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.41 | PAT-41 | Patient app — medicines tab | PAT-41.02 | Wire to the Phase 8–15 API for: Medicines tab | New | Patient Mobile | §2.7 | Medicines tab | All medicine orders in one place | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
840 | 840 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.41 | PAT-41 | Patient app — medicines tab | PAT-41.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.7 | Medicines tab | All medicine orders in one place | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
841 | 841 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.41 | PAT-41 | Patient app — medicines tab | PAT-41.04 | QA both platforms: Medicines tab matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.7 | Medicines tab | All medicine orders in one place | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
842 | 842 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.42 | PAT-42 | Patient app — start HomeoMeds order from eRx | PAT-42.01 | UI: Order start screens (empty, loading, error, offline) | New | Patient Mobile | §2.7 | Order start | Start an order directly from the prescription | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
843 | 843 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.42 | PAT-42 | Patient app — start HomeoMeds order from eRx | PAT-42.02 | Wire to the Phase 8–15 API for: Order start | New | Patient Mobile | §2.7 | Order start | Start an order directly from the prescription | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
844 | 844 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.42 | PAT-42 | Patient app — start HomeoMeds order from eRx | PAT-42.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.7 | Order start | Start an order directly from the prescription | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
845 | 845 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.42 | PAT-42 | Patient app — start HomeoMeds order from eRx | PAT-42.04 | QA both platforms: Order start matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.7 | Order start | Start an order directly from the prescription | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
846 | 846 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.43 | PAT-43 | Patient app — pharmacy selection and quote | PAT-43.01 | UI: Pharmacy selection & quote screens (empty, loading, error, offline) | New | Patient Mobile | §2.7 | Pharmacy selection & quote | Choose a licensed pharmacy and see the price before paying | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
847 | 847 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.43 | PAT-43 | Patient app — pharmacy selection and quote | PAT-43.02 | Wire to the Phase 8–15 API for: Pharmacy selection & quote | New | Patient Mobile | §2.7 | Pharmacy selection & quote | Choose a licensed pharmacy and see the price before paying | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
848 | 848 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.43 | PAT-43 | Patient app — pharmacy selection and quote | PAT-43.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.7 | Pharmacy selection & quote | Choose a licensed pharmacy and see the price before paying | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
849 | 849 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.43 | PAT-43 | Patient app — pharmacy selection and quote | PAT-43.04 | QA both platforms: Pharmacy selection & quote matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.7 | Pharmacy selection & quote | Choose a licensed pharmacy and see the price before paying | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
850 | 850 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.44 | PAT-44 | Patient app — order review and consent | PAT-44.01 | UI: Order review & consent screens (empty, loading, error, offline) | New | Patient Mobile | §2.7 | Order review & consent | Confirm and consent before the prescription is shared | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
851 | 851 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.44 | PAT-44 | Patient app — order review and consent | PAT-44.02 | Wire to the Phase 8–15 API for: Order review & consent | New | Patient Mobile | §2.7 | Order review & consent | Confirm and consent before the prescription is shared | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
852 | 852 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.44 | PAT-44 | Patient app — order review and consent | PAT-44.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.7 | Order review & consent | Confirm and consent before the prescription is shared | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
853 | 853 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.44 | PAT-44 | Patient app — order review and consent | PAT-44.04 | QA both platforms: Order review & consent matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.7 | Order review & consent | Confirm and consent before the prescription is shared | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
854 | 854 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.45 | PAT-45 | Patient app — order tracking | PAT-45.01 | UI: Order tracking screens (empty, loading, error, offline) | New | Patient Mobile | §2.7 | Order tracking | Live status from accepted to delivered | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
855 | 855 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.45 | PAT-45 | Patient app — order tracking | PAT-45.02 | Wire to the Phase 8–15 API for: Order tracking | New | Patient Mobile | §2.7 | Order tracking | Live status from accepted to delivered | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
856 | 856 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.45 | PAT-45 | Patient app — order tracking | PAT-45.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.7 | Order tracking | Live status from accepted to delivered | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
857 | 857 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.45 | PAT-45 | Patient app — order tracking | PAT-45.04 | QA both platforms: Order tracking matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.7 | Order tracking | Live status from accepted to delivered | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
858 | 858 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.46 | PAT-46 | Patient app — order detail and refill | PAT-46.01 | UI: Order detail & refill screens (empty, loading, error, offline) | New | Patient Mobile | §2.7 | Order detail & refill | Full order history and one-tap refill request | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
859 | 859 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.46 | PAT-46 | Patient app — order detail and refill | PAT-46.02 | Wire to the Phase 8–15 API for: Order detail & refill | New | Patient Mobile | §2.7 | Order detail & refill | Full order history and one-tap refill request | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
860 | 860 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.46 | PAT-46 | Patient app — order detail and refill | PAT-46.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.7 | Order detail & refill | Full order history and one-tap refill request | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
861 | 861 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.46 | PAT-46 | Patient app — order detail and refill | PAT-46.04 | QA both platforms: Order detail & refill matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.7 | Order detail & refill | Full order history and one-tap refill request | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
862 | 862 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.47 | PAT-47 | Patient app — write a review | PAT-47.01 | UI: Write a review screens (empty, loading, error, offline) | New | Patient Mobile | §2.8 | Write a review | Rate and review the consultation | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
863 | 863 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.47 | PAT-47 | Patient app — write a review | PAT-47.02 | Wire to the Phase 8–15 API for: Write a review | New | Patient Mobile | §2.8 | Write a review | Rate and review the consultation | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
864 | 864 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.47 | PAT-47 | Patient app — write a review | PAT-47.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.8 | Write a review | Rate and review the consultation | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
865 | 865 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.47 | PAT-47 | Patient app — write a review | PAT-47.04 | QA both platforms: Write a review matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.8 | Write a review | Rate and review the consultation | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
866 | 866 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.48 | PAT-48 | Patient app — my reviews and appeal | PAT-48.01 | UI: My reviews & appeal screens (empty, loading, error, offline) | New | Patient Mobile | §2.8 | My reviews & appeal | Manage reviews and raise an appeal | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
867 | 867 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.48 | PAT-48 | Patient app — my reviews and appeal | PAT-48.02 | Wire to the Phase 8–15 API for: My reviews & appeal | New | Patient Mobile | §2.8 | My reviews & appeal | Manage reviews and raise an appeal | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
868 | 868 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.48 | PAT-48 | Patient app — my reviews and appeal | PAT-48.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.8 | My reviews & appeal | Manage reviews and raise an appeal | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
869 | 869 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.48 | PAT-48 | Patient app — my reviews and appeal | PAT-48.04 | QA both platforms: My reviews & appeal matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.8 | My reviews & appeal | Manage reviews and raise an appeal | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
870 | 870 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.49 | PAT-49 | Patient app — payments and refunds | PAT-49.01 | UI: Payments & refunds screens (empty, loading, error, offline) | New | Patient Mobile | §2.8 | Payments & refunds | Full payment history and refund status | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
871 | 871 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.49 | PAT-49 | Patient app — payments and refunds | PAT-49.02 | Wire to the Phase 8–15 API for: Payments & refunds | New | Patient Mobile | §2.8 | Payments & refunds | Full payment history and refund status | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
872 | 872 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.49 | PAT-49 | Patient app — payments and refunds | PAT-49.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.8 | Payments & refunds | Full payment history and refund status | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
873 | 873 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.49 | PAT-49 | Patient app — payments and refunds | PAT-49.04 | QA both platforms: Payments & refunds matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.8 | Payments & refunds | Full payment history and refund status | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
874 | 874 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.50 | PAT-50 | Patient app — profile and settings | PAT-50.01 | UI: Profile & settings screens (empty, loading, error, offline) | New | Patient Mobile | §2.8 | Profile & settings | Manage personal details and preferences | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
875 | 875 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.50 | PAT-50 | Patient app — profile and settings | PAT-50.02 | Wire to the Phase 8–15 API for: Profile & settings | New | Patient Mobile | §2.8 | Profile & settings | Manage personal details and preferences | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
876 | 876 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.50 | PAT-50 | Patient app — profile and settings | PAT-50.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.8 | Profile & settings | Manage personal details and preferences | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
877 | 877 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.50 | PAT-50 | Patient app — profile and settings | PAT-50.04 | QA both platforms: Profile & settings matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.8 | Profile & settings | Manage personal details and preferences | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
878 | 878 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.51 | PAT-51 | Patient app — consent centre and data rights | PAT-51.01 | UI: Consent centre & data rights screens (empty, loading, error, offline) | New | Patient Mobile | §2.8 | Consent centre & data rights | View, manage and withdraw consents; request data | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
879 | 879 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.51 | PAT-51 | Patient app — consent centre and data rights | PAT-51.02 | Wire to the Phase 8–15 API for: Consent centre & data rights | New | Patient Mobile | §2.8 | Consent centre & data rights | View, manage and withdraw consents; request data | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
880 | 880 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.51 | PAT-51 | Patient app — consent centre and data rights | PAT-51.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.8 | Consent centre & data rights | View, manage and withdraw consents; request data | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
881 | 881 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.51 | PAT-51 | Patient app — consent centre and data rights | PAT-51.04 | QA both platforms: Consent centre & data rights matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.8 | Consent centre & data rights | View, manage and withdraw consents; request data | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
882 | 882 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.52 | PAT-52 | Patient app — notifications centre | PAT-52.01 | UI: Notifications centre screens (empty, loading, error, offline) | New | Patient Mobile | §2.8 | Notifications centre | All alerts in one place | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
883 | 883 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.52 | PAT-52 | Patient app — notifications centre | PAT-52.02 | Wire to the Phase 8–15 API for: Notifications centre | New | Patient Mobile | §2.8 | Notifications centre | All alerts in one place | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
884 | 884 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.52 | PAT-52 | Patient app — notifications centre | PAT-52.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.8 | Notifications centre | All alerts in one place | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
885 | 885 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.52 | PAT-52 | Patient app — notifications centre | PAT-52.04 | QA both platforms: Notifications centre matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.8 | Notifications centre | All alerts in one place | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
886 | 886 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.53 | PAT-53 | Patient app — help centre and tickets | PAT-53.01 | UI: Help centre & support tickets screens (empty, loading, error, offline) | New | Patient Mobile | §2.9 | Help centre & support tickets | Raise an issue and track it to resolution | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
887 | 887 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.53 | PAT-53 | Patient app — help centre and tickets | PAT-53.02 | Wire to the Phase 8–15 API for: Help centre & support tickets | New | Patient Mobile | §2.9 | Help centre & support tickets | Raise an issue and track it to resolution | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
888 | 888 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.53 | PAT-53 | Patient app — help centre and tickets | PAT-53.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.9 | Help centre & support tickets | Raise an issue and track it to resolution | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
889 | 889 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.53 | PAT-53 | Patient app — help centre and tickets | PAT-53.04 | QA both platforms: Help centre & support tickets matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.9 | Help centre & support tickets | Raise an issue and track it to resolution | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
890 | 890 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.54 | PAT-54 | Patient app — physical clinic booking | PAT-54.01 | UI: Physical clinic appointment screens (empty, loading, error, offline) | New | Patient Mobile | §2.9 | Physical clinic appointment | Book an in-person visit as well as online | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
891 | 891 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.54 | PAT-54 | Patient app — physical clinic booking | PAT-54.02 | Wire to the Phase 8–15 API for: Physical clinic appointment | New | Patient Mobile | §2.9 | Physical clinic appointment | Book an in-person visit as well as online | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
892 | 892 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.54 | PAT-54 | Patient app — physical clinic booking | PAT-54.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.9 | Physical clinic appointment | Book an in-person visit as well as online | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
893 | 893 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.54 | PAT-54 | Patient app — physical clinic booking | PAT-54.04 | QA both platforms: Physical clinic appointment matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.9 | Physical clinic appointment | Book an in-person visit as well as online | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
894 | 894 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.55 | PAT-55 | Patient app — assisted booking request | PAT-55.01 | UI: Assisted booking screens (empty, loading, error, offline) | New | Patient Mobile | §2.9 | Assisted booking | Help for patients who need support booking | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
895 | 895 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.55 | PAT-55 | Patient app — assisted booking request | PAT-55.02 | Wire to the Phase 8–15 API for: Assisted booking | New | Patient Mobile | §2.9 | Assisted booking | Help for patients who need support booking | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
896 | 896 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.55 | PAT-55 | Patient app — assisted booking request | PAT-55.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.9 | Assisted booking | Help for patients who need support booking | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
897 | 897 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.55 | PAT-55 | Patient app — assisted booking request | PAT-55.04 | QA both platforms: Assisted booking matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.9 | Assisted booking | Help for patients who need support booking | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
898 | 898 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.56 | PAT-56 | Patient app — low-data mode | PAT-56.01 | UI: Low-data mode screens (empty, loading, error, offline) | New | Patient Mobile | §2.9 | Low-data mode | Works on slow or limited connections | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
899 | 899 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.56 | PAT-56 | Patient app — low-data mode | PAT-56.02 | Wire to the Phase 8–15 API for: Low-data mode | New | Patient Mobile | §2.9 | Low-data mode | Works on slow or limited connections | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
900 | 900 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.56 | PAT-56 | Patient app — low-data mode | PAT-56.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.9 | Low-data mode | Works on slow or limited connections | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
901 | 901 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.56 | PAT-56 | Patient app — low-data mode | PAT-56.04 | QA both platforms: Low-data mode matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.9 | Low-data mode | Works on slow or limited connections | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
902 | 902 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.57 | PAT-57 | Patient app — push notifications | PAT-57.01 | UI: Push notifications screens (empty, loading, error, offline) | New | Patient Mobile | §2.9 | Push notifications | Booking confirmations, reminders, doctor ready, prescription issued, order updates | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
903 | 903 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.57 | PAT-57 | Patient app — push notifications | PAT-57.02 | Wire to the Phase 8–15 API for: Push notifications | New | Patient Mobile | §2.9 | Push notifications | Booking confirmations, reminders, doctor ready, prescription issued, order updates | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
904 | 904 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.57 | PAT-57 | Patient app — push notifications | PAT-57.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.9 | Push notifications | Booking confirmations, reminders, doctor ready, prescription issued, order updates | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
905 | 905 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.57 | PAT-57 | Patient app — push notifications | PAT-57.04 | QA both platforms: Push notifications matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.9 | Push notifications | Booking confirmations, reminders, doctor ready, prescription issued, order updates | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
906 | 906 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.58 | PAT-58 | Patient app — iOS and Android store release, device matrix, and parity QA | PAT-58.01 | CI: iOS + Android release builds; env pointing to .NET 8 | New | Patient Mobile | §2 + §18 | Patient mobile app iOS and Android | iOS and Android — onboarding, discovery, booking, payment, video consultation, records, prescriptions, follow-up, medicines, reviews, support, notifications | Patient Mobile App | Mobile | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 1 | Not Started |  | Edit on module sheet
907 | 907 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.58 | PAT-58 | Patient app — iOS and Android store release, device matrix, and parity QA | PAT-58.02 | Parity QA spreadsheet: each PAT-01..57 on both OS | Regression | Patient Mobile | §2 + §18 | Patient mobile app iOS and Android | iOS and Android — onboarding, discovery, booking, payment, video consultation, records, prescriptions, follow-up, medicines, reviews, support, notifications | Patient Mobile App | QA | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 1 | Not Started |  | Edit on module sheet
908 | 908 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.58 | PAT-58 | Patient app — iOS and Android store release, device matrix, and parity QA | PAT-58.03 | Crashlytics/Sentry equivalent for patient app | New Integration | Patient Mobile | §2 + §18 | Patient mobile app iOS and Android | iOS and Android — onboarding, discovery, booking, payment, video consultation, records, prescriptions, follow-up, medicines, reviews, support, notifications | Patient Mobile App | Mobile | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | 2 | Not Started |  | Edit on module sheet
909 | 909 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.1 | DMO-01 | Doctor app — login & identity (same login and same account as the web portal) | DMO-01.01 | Login screen (password or OTP-to-registered mobile) | New | Doctor Mobile | §3 | Login & identity | Same login and same account as the web portal | Doctor Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
910 | 910 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.1 | DMO-01 | Doctor app — login & identity (same login and same account as the web portal) | DMO-01.02 | Call same Login API; store JWT securely (Keychain/Keystore) | New | Doctor Mobile | §3 | Login & identity | Same login and same account as the web portal | Doctor Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
911 | 911 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.1 | DMO-01 | Doctor app — login & identity (same login and same account as the web portal) | DMO-01.03 | Expired session → re-login; no case-taking entry point | New | Doctor Mobile | §3 | Login & identity | Same login and same account as the web portal | Doctor Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
912 | 912 | M18 | Doctor mobile app | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.1 | DMO-01 | Doctor app — login & identity (same login and same account as the web portal) | DMO-01.04 | QA: same DoctorId as web; reception accounts must not open doctor clinical actions | Regression | Doctor Mobile | §3 | Login & identity | Same login and same account as the web portal | Doctor Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
913 | 913 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.2 | DMO-02 | Doctor app — first-run onboarding (guided setup, number confirmation and permissions) | DMO-02.01 | Onboarding screens | New | Doctor Mobile | §3 | First-run onboarding | Guided setup, number confirmation and permissions | Doctor Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
914 | 914 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.2 | DMO-02 | Doctor app — first-run onboarding (guided setup, number confirmation and permissions) | DMO-02.02 | Confirm number against profile | New | Doctor Mobile | §3 | First-run onboarding | Guided setup, number confirmation and permissions | Doctor Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
915 | 915 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.2 | DMO-02 | Doctor app — first-run onboarding (guided setup, number confirmation and permissions) | DMO-02.03 | Skip vs required steps documented | New | Doctor Mobile | §3 | First-run onboarding | Guided setup, number confirmation and permissions | Doctor Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
916 | 916 | M18 | Doctor mobile app | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.2 | DMO-02 | Doctor app — first-run onboarding (guided setup, number confirmation and permissions) | DMO-02.04 | QA: number mismatch blocked | Regression | Doctor Mobile | §3 | First-run onboarding | Guided setup, number confirmation and permissions | Doctor Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
917 | 917 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.3 | DMO-03 | Doctor app — notification permissions (push, microphone and camera handled properly) | DMO-03.01 | Permission primer + settings CTA | New | Doctor Mobile | §3 | Notification permissions | Push, microphone and camera permissions handled properly | Doctor Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
918 | 918 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.3 | DMO-03 | Doctor app — notification permissions (push, microphone and camera handled properly) | DMO-03.02 | Register FCM/APNs token (COM-03) | New | Doctor Mobile | §3 | Notification permissions | Push, microphone and camera permissions handled properly | Doctor Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
919 | 919 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.3 | DMO-03 | Doctor app — notification permissions (push, microphone and camera handled properly) | DMO-03.03 | Denied-state UX | New | Doctor Mobile | §3 | Notification permissions | Push, microphone and camera permissions handled properly | Doctor Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
920 | 920 | M18 | Doctor mobile app | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.3 | DMO-03 | Doctor app — notification permissions (push, microphone and camera handled properly) | DMO-03.04 | QA: deny each permission independently | Regression | Doctor Mobile | §3 | Notification permissions | Push, microphone and camera permissions handled properly | Doctor Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
921 | 921 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.4 | DMO-04 | Doctor app — today’s queue & schedule (the full day at a glance) | DMO-04.01 | TodayQueue screen | New | Doctor Mobile | §3 | Today’s queue & schedule | The full day at a glance | Doctor Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
922 | 922 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.4 | DMO-04 | Doctor app — today’s queue & schedule (the full day at a glance) | DMO-04.02 | Existing appointment list APIs | New | Doctor Mobile | §3 | Today’s queue & schedule | The full day at a glance | Doctor Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
923 | 923 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.4 | DMO-04 | Doctor app — today’s queue & schedule (the full day at a glance) | DMO-04.03 | Pull-to-refresh; empty Sunday | New | Doctor Mobile | §3 | Today’s queue & schedule | The full day at a glance | Doctor Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
924 | 924 | M18 | Doctor mobile app | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.4 | DMO-04 | Doctor app — today’s queue & schedule (the full day at a glance) | DMO-04.04 | QA: parity with web counts | Regression | Doctor Mobile | §3 | Today’s queue & schedule | The full day at a glance | Doctor Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
925 | 925 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.5 | DMO-05 | Doctor app — availability toggle (go online or offline, set working hours) | DMO-05.01 | Availability + hours screens | New | Doctor Mobile | §3 | Availability toggle | Go online or offline, set working hours | Doctor Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
926 | 926 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.5 | DMO-05 | Doctor app — availability toggle (go online or offline, set working hours) | DMO-05.02 | TEL-01 + APT-07 APIs (hours read/edit policy: edit hours may stay web-only if product decides — PDF says set working hours so include) | New | Doctor Mobile | §3 | Availability toggle | Go online or offline, set working hours | Doctor Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
927 | 927 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.5 | DMO-05 | Doctor app — availability toggle (go online or offline, set working hours) | DMO-05.03 | Offline banner | New | Doctor Mobile | §3 | Availability toggle | Go online or offline, set working hours | Doctor Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
928 | 928 | M18 | Doctor mobile app | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.5 | DMO-05 | Doctor app — availability toggle (go online or offline, set working hours) | DMO-05.04 | QA: web and app status match within heartbeat | Regression | Doctor Mobile | §3 | Availability toggle | Go online or offline, set working hours | Doctor Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
929 | 929 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.6 | DMO-06 | Doctor app — push notifications (waiting, booking, reschedule, cancellation, refill, payment received) | DMO-06.01 | Notification handling + deep links into queue/refill/join | New | Doctor Mobile | §3 | Push notifications | Patient waiting, new booking, reschedule, cancellation, refill request, payment received | Doctor Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
930 | 930 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.6 | DMO-06 | Doctor app — push notifications (waiting, booking, reschedule, cancellation, refill, payment received) | DMO-06.02 | Device register | New | Doctor Mobile | §3 | Push notifications | Patient waiting, new booking, reschedule, cancellation, refill request, payment received | Doctor Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
931 | 931 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.6 | DMO-06 | Doctor app — push notifications (waiting, booking, reschedule, cancellation, refill, payment received) | DMO-06.03 | Foreground in-app banner | New | Doctor Mobile | §3 | Push notifications | Patient waiting, new booking, reschedule, cancellation, refill request, payment received | Doctor Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
932 | 932 | M18 | Doctor mobile app | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.6 | DMO-06 | Doctor app — push notifications (waiting, booking, reschedule, cancellation, refill, payment received) | DMO-06.04 | QA: each event type deep link | Regression | Doctor Mobile | §3 | Push notifications | Patient waiting, new booking, reschedule, cancellation, refill request, payment received | Doctor Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
933 | 933 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.7 | DMO-07 | Doctor app — patient context card (name, age, chief complaint and last visit) — NO case-taking | DMO-07.01 | PatientCard read-only | New | Doctor Mobile | §3 | Patient context card | Name, age, chief complaint and last visit before joining | Doctor Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
934 | 934 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.7 | DMO-07 | Doctor app — patient context card (name, age, chief complaint and last visit) — NO case-taking | DMO-07.02 | Context API (name, age, CC, last visit, payment, tele) | New | Doctor Mobile | §3 | Patient context card | Name, age, chief complaint and last visit before joining | Doctor Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
935 | 935 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.7 | DMO-07 | Doctor app — patient context card (name, age, chief complaint and last visit) — NO case-taking | DMO-07.03 | Do not ship case-taking tabs | New | Doctor Mobile | §3 | Patient context card | Name, age, chief complaint and last visit before joining | Doctor Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
936 | 936 | M18 | Doctor mobile app | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.7 | DMO-07 | Doctor app — patient context card (name, age, chief complaint and last visit) — NO case-taking | DMO-07.04 | QA: repertory endpoints never called from app | Regression | Doctor Mobile | §3 | Patient context card | Name, age, chief complaint and last visit before joining | Doctor Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
937 | 937 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.8 | DMO-08 | Doctor app — join consultation (video or audio from the phone) | DMO-08.01 | VideoRoom | New | Doctor Mobile | §3 | Join consultation | Start the video or audio consultation from the phone | Doctor Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
938 | 938 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.8 | DMO-08 | Doctor app — join consultation (video or audio from the phone) | DMO-08.02 | Tele session tokens | New | Doctor Mobile | §3 | Join consultation | Start the video or audio consultation from the phone | Doctor Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
939 | 939 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.8 | DMO-08 | Doctor app — join consultation (video or audio from the phone) | DMO-08.03 | Audio-only fallback | New | Doctor Mobile | §3 | Join consultation | Start the video or audio consultation from the phone | Doctor Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
940 | 940 | M18 | Doctor mobile app | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.8 | DMO-08 | Doctor app — join consultation (video or audio from the phone) | DMO-08.04 | QA: web patient + app doctor | Regression | Doctor Mobile | §3 | Join consultation | Start the video or audio consultation from the phone | Doctor Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
941 | 941 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.9 | DMO-09 | Doctor app — refill approval (approve or reject repeat prescription requests) | DMO-09.01 | RefillInbox + RefillDetail | New | Doctor Mobile | §3 + §11 | Refill approval | Approve or reject repeat prescription requests | Doctor Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
942 | 942 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.9 | DMO-09 | Doctor app — refill approval (approve or reject repeat prescription requests) | DMO-09.02 | Approve/Reject APIs | New | Doctor Mobile | §3 + §11 | Refill approval | Approve or reject repeat prescription requests | Doctor Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
943 | 943 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.9 | DMO-09 | Doctor app — refill approval (approve or reject repeat prescription requests) | DMO-09.03 | Show codes vs names per policy (doctor sees names) | New | Doctor Mobile | §3 + §11 | Refill approval | Approve or reject repeat prescription requests | Doctor Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
944 | 944 | M18 | Doctor mobile app | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.9 | DMO-09 | Doctor app — refill approval (approve or reject repeat prescription requests) | DMO-09.04 | QA: reject reason; cannot edit snapshot | Regression | Doctor Mobile | §3 + §11 | Refill approval | Approve or reject repeat prescription requests | Doctor Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
945 | 945 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.10 | DMO-10 | Doctor app — earnings summary (today, this week, this month, with payout status) | DMO-10.01 | Earnings screens | New | Doctor Mobile | §3 + §16 | Earnings summary | Today, this week and this month, with payout status | Doctor Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
946 | 946 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.10 | DMO-10 | Doctor app — earnings summary (today, this week, this month, with payout status) | DMO-10.02 | GET Earnings/Summary | New | Doctor Mobile | §3 + §16 | Earnings summary | Today, this week and this month, with payout status | Doctor Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
947 | 947 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.10 | DMO-10 | Doctor app — earnings summary (today, this week, this month, with payout status) | DMO-10.03 | Empty first week | New | Doctor Mobile | §3 + §16 | Earnings summary | Today, this week and this month, with payout status | Doctor Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
948 | 948 | M18 | Doctor mobile app | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.10 | DMO-10 | Doctor app — earnings summary (today, this week, this month, with payout status) | DMO-10.04 | QA: matches /account figures ± rounding | Regression | Doctor Mobile | §3 + §16 | Earnings summary | Today, this week and this month, with payout status | Doctor Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
949 | 949 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.11 | DMO-11 | Doctor app — offline handling (weak connection or expired session) | DMO-11.01 | Offline/error screens | New | Doctor Mobile | §3 | Offline handling | Clear behaviour on weak connection or expired session | Doctor Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
950 | 950 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.11 | DMO-11 | Doctor app — offline handling (weak connection or expired session) | DMO-11.02 | 401 interceptor → logout API | New | Doctor Mobile | §3 | Offline handling | Clear behaviour on weak connection or expired session | Doctor Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
951 | 951 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.11 | DMO-11 | Doctor app — offline handling (weak connection or expired session) | DMO-11.03 | No silent retry of payments | New | Doctor Mobile | §3 | Offline handling | Clear behaviour on weak connection or expired session | Doctor Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
952 | 952 | M18 | Doctor mobile app | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.11 | DMO-11 | Doctor app — offline handling (weak connection or expired session) | DMO-11.04 | QA: airplane mode on join | Regression | Doctor Mobile | §3 | Offline handling | Clear behaviour on weak connection or expired session | Doctor Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
953 | 953 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.12 | DMO-12 | Doctor app — reliability monitoring (failures reported automatically) | DMO-12.01 | Integrate Crashlytics/Sentry; map to doctorId hashed | New Integration | Doctor Mobile | §3 | Reliability monitoring | Failures are reported automatically, not left to a phone call | Doctor Mobile App | Mobile | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | 2 | Not Started |  | Edit on module sheet
954 | 954 | M18 | Doctor mobile app | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.12 | DMO-12 | Doctor app — reliability monitoring (failures reported automatically) | DMO-12.02 | QA: simulated crash + join fail event | Regression | Doctor Mobile | §3 | Reliability monitoring | Failures are reported automatically, not left to a phone call | Doctor Mobile App | QA | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 1 | Not Started |  | Edit on module sheet
955 | 955 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.13 | DMO-13 | Doctor app — iOS and Android parity QA (queue, availability, notifications, context, video, refill, earnings) | DMO-13.01 | Release builds both OS | New | Doctor Mobile | §3 + §18 | Doctor mobile app iOS and Android | iOS and Android — queue, availability, notifications, patient context, video consultation, refill approval, earnings | Doctor Mobile App | Mobile | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 1 | Not Started |  | Edit on module sheet
956 | 956 | M18 | Doctor mobile app | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.13 | DMO-13 | Doctor app — iOS and Android parity QA (queue, availability, notifications, context, video, refill, earnings) | DMO-13.02 | Parity QA DMO-01..12 both OS | Regression | Doctor Mobile | §3 + §18 | Doctor mobile app iOS and Android | iOS and Android — queue, availability, notifications, patient context, video consultation, refill approval, earnings | Doctor Mobile App | QA | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 1 | Not Started |  | Edit on module sheet
957 | 957 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.1 | RPT-01 | Admin overview dashboard — platform-wide activity at a glance (replace Velzon ecommerce) | RPT-01.01 | No ecommerce tables | Existing Improvement | Reports | §16 + §7.2 | Admin overview dashboard / Admin dashboard | Platform-wide activity at a glance / Live overview of the whole platform | Admin Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
958 | 958 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.1 | RPT-01 | Admin overview dashboard — platform-wide activity at a glance (replace Velzon ecommerce) | RPT-01.02 | GET /api/AdminDashboard/Overview | Existing Improvement | Reports | §16 + §7.2 | Admin overview dashboard / Admin dashboard | Platform-wide activity at a glance / Live overview of the whole platform | Admin Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
959 | 959 | M19 | Reports, NFR & delivery gate | UI | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.1 | RPT-01 | Admin overview dashboard — platform-wide activity at a glance (replace Velzon ecommerce) | RPT-01.03 | Replace pages/Admin/Dashboard; getHomeDashboardPath → /admin/dashboard | Existing Improvement | Reports | §16 + §7.2 | Admin overview dashboard / Admin dashboard | Platform-wide activity at a glance / Live overview of the whole platform | Admin Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
960 | 960 | M19 | Reports, NFR & delivery gate | QA | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.1 | RPT-01 | Admin overview dashboard — platform-wide activity at a glance (replace Velzon ecommerce) | RPT-01.04 | QA: login as admin never shows fake store visits | Regression | Reports | §16 + §7.2 | Admin overview dashboard / Admin dashboard | Platform-wide activity at a glance / Live overview of the whole platform | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
961 | 961 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.2 | RPT-02 | Doctor practice statistics — patient and consultation trends (extend existing charts) | RPT-02.01 | No new warehouse required for v1 | Existing Improvement | Reports | §16 + §5.1 | Doctor practice statistics | Patient and consultation trends | Doctor Web | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
962 | 962 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.2 | RPT-02 | Doctor practice statistics — patient and consultation trends (extend existing charts) | RPT-02.02 | Extend GetPatientStatsCharts with VisitType/ConsultMode | Existing Improvement | Reports | §16 + §5.1 | Doctor practice statistics | Patient and consultation trends | Doctor Web | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
963 | 963 | M19 | Reports, NFR & delivery gate | UI | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.2 | RPT-02 | Doctor practice statistics — patient and consultation trends (extend existing charts) | RPT-02.03 | Dashboard charts consume new series | Existing Improvement | Reports | §16 + §5.1 | Doctor practice statistics | Patient and consultation trends | Doctor Web | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
964 | 964 | M19 | Reports, NFR & delivery gate | QA | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.2 | RPT-02 | Doctor practice statistics — patient and consultation trends (extend existing charts) | RPT-02.04 | QA: empty new clinic | Regression | Reports | §16 + §5.1 | Doctor practice statistics | Patient and consultation trends | Doctor Web | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
965 | 965 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.3 | RPT-03 | Follow-up analysis — due/overdue patients and follow-up conversion | RPT-03.01 | Queries on VisitType + FollowUpTask | New | Reports | §16 | Follow-up analysis | Which patients are due or overdue for follow-up, and follow-up conversion | Doctor Web | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
966 | 966 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.3 | RPT-03 | Follow-up analysis — due/overdue patients and follow-up conversion | RPT-03.02 | GET FollowUpDue, FollowUpSummary | New | Reports | §16 | Follow-up analysis | Which patients are due or overdue for follow-up, and follow-up conversion | Doctor Web | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
967 | 967 | M19 | Reports, NFR & delivery gate | UI | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.3 | RPT-03 | Follow-up analysis — due/overdue patients and follow-up conversion | RPT-03.03 | /doctor/follow-up-analysis | New | Reports | §16 | Follow-up analysis | Which patients are due or overdue for follow-up, and follow-up conversion | Doctor Web | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
968 | 968 | M19 | Reports, NFR & delivery gate | QA | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.3 | RPT-03 | Follow-up analysis — due/overdue patients and follow-up conversion | RPT-03.04 | QA: overdue vs due buckets | Regression | Reports | §16 | Follow-up analysis | Which patients are due or overdue for follow-up, and follow-up conversion | Doctor Web | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
969 | 969 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.4 | RPT-04 | Clinic performance analysis — appointments, slot utilisation, no-shows, cancellations, waiting time and revenue | RPT-04.01 | Aggregate APIs beyond GetPatientStatsCharts | New | Reports | §16 | Clinic performance analysis | Appointments, slot utilisation, no-shows, cancellations, waiting time and revenue | Doctor Web | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
970 | 970 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.4 | RPT-04 | Clinic performance analysis — appointments, slot utilisation, no-shows, cancellations, waiting time and revenue | RPT-04.02 | GET ClinicPerformance | New | Reports | §16 | Clinic performance analysis | Appointments, slot utilisation, no-shows, cancellations, waiting time and revenue | Doctor Web | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
971 | 971 | M19 | Reports, NFR & delivery gate | UI | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.4 | RPT-04 | Clinic performance analysis — appointments, slot utilisation, no-shows, cancellations, waiting time and revenue | RPT-04.03 | /doctor/clinic-performance | New | Reports | §16 | Clinic performance analysis | Appointments, slot utilisation, no-shows, cancellations, waiting time and revenue | Doctor Web | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
972 | 972 | M19 | Reports, NFR & delivery gate | QA | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.4 | RPT-04 | Clinic performance analysis — appointments, slot utilisation, no-shows, cancellations, waiting time and revenue | RPT-04.04 | QA: cancelled excluded from completed; revenue uses ledger not client | Regression | Reports | §16 | Clinic performance analysis | Appointments, slot utilisation, no-shows, cancellations, waiting time and revenue | Doctor Web | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
973 | 973 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.5 | RPT-05 | Payment reconciliation report — bookings matched against payments | RPT-05.01 | CSV/PDF export of FIN-02 query | New | Reports | §16 + §7.2 | Payment reconciliation report / Consult booking & payment reconciliation | Bookings matched against payments / Match every booking against every payment | Admin + Account | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
974 | 974 | M19 | Reports, NFR & delivery gate | UI | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.5 | RPT-05 | Payment reconciliation report — bookings matched against payments | RPT-05.02 | Report UI on admin/account recon screens | New | Reports | §16 + §7.2 | Payment reconciliation report / Consult booking & payment reconciliation | Bookings matched against payments / Match every booking against every payment | Admin + Account | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
975 | 975 | M19 | Reports, NFR & delivery gate | QA | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.5 | RPT-05 | Payment reconciliation report — bookings matched against payments | RPT-05.03 | QA: unmatched rows included | Regression | Reports | §16 + §7.2 | Payment reconciliation report / Consult booking & payment reconciliation | Bookings matched against payments / Match every booking against every payment | Admin + Account | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
976 | 976 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.6 | RPT-06 | Settlement & payout reports — amounts due and paid to doctors and pharmacies | RPT-06.01 | Export settlement runs + payout register | New | Reports | §16 + §8 | Settlement & payout reports | Amounts due and paid to doctors and pharmacies | Account | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
977 | 977 | M19 | Reports, NFR & delivery gate | UI | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.6 | RPT-06 | Settlement & payout reports — amounts due and paid to doctors and pharmacies | RPT-06.02 | Report UI | New | Reports | §16 + §8 | Settlement & payout reports | Amounts due and paid to doctors and pharmacies | Account | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
978 | 978 | M19 | Reports, NFR & delivery gate | QA | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.6 | RPT-06 | Settlement & payout reports — amounts due and paid to doctors and pharmacies | RPT-06.03 | QA: pharmacy lines appear only after HomeoMeds | Regression | Reports | §16 + §8 | Settlement & payout reports | Amounts due and paid to doctors and pharmacies | Account | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
979 | 979 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.7 | RPT-07 | GST & invoice reports (reporting surface of FIN-08) | RPT-07.01 | Confirm CA format; implement export if not already in FIN-08 | New | Reports | §16 + §8 | GST & invoice reports | Tax reporting | Account | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
980 | 980 | M19 | Reports, NFR & delivery gate | QA | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.7 | RPT-07 | GST & invoice reports (reporting surface of FIN-08) | RPT-07.02 | QA: number series gaps flagged | Regression | Reports | §16 + §8 | GST & invoice reports | Tax reporting | Account | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
981 | 981 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.8 | RPT-08 | Doctor earnings summary — daily, weekly and monthly earnings with payout status (web + same API as DMO-10) | RPT-08.01 | Reuse earnings API | New | Reports | §16 + §3 | Doctor earnings summary | Daily, weekly and monthly earnings with payout status | Doctor Web + App | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
982 | 982 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.8 | RPT-08 | Doctor earnings summary — daily, weekly and monthly earnings with payout status (web + same API as DMO-10) | RPT-08.02 | GET Earnings/Summary already for app — add if missing date buckets | New | Reports | §16 + §3 | Doctor earnings summary | Daily, weekly and monthly earnings with payout status | Doctor Web + App | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
983 | 983 | M19 | Reports, NFR & delivery gate | UI | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.8 | RPT-08 | Doctor earnings summary — daily, weekly and monthly earnings with payout status (web + same API as DMO-10) | RPT-08.03 | /doctor/earnings | New | Reports | §16 + §3 | Doctor earnings summary | Daily, weekly and monthly earnings with payout status | Doctor Web + App | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
984 | 984 | M19 | Reports, NFR & delivery gate | QA | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.8 | RPT-08 | Doctor earnings summary — daily, weekly and monthly earnings with payout status (web + same API as DMO-10) | RPT-08.04 | QA: payout pending vs paid | Regression | Reports | §16 + §3 | Doctor earnings summary | Daily, weekly and monthly earnings with payout status | Doctor Web + App | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
985 | 985 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.9 | RPT-09 | Medicine order reports — order volumes, fulfilment and exceptions | RPT-09.01 | Aggregates on MedicineOrder | New | Reports | §16 + §12 | Medicine order reports | Order volumes, fulfilment and exceptions | Admin + Account | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
986 | 986 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.9 | RPT-09 | Medicine order reports — order volumes, fulfilment and exceptions | RPT-09.02 | GET medicine order report | New | Reports | §16 + §12 | Medicine order reports | Order volumes, fulfilment and exceptions | Admin + Account | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
987 | 987 | M19 | Reports, NFR & delivery gate | UI | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.9 | RPT-09 | Medicine order reports — order volumes, fulfilment and exceptions | RPT-09.03 | Admin/account report page | New | Reports | §16 + §12 | Medicine order reports | Order volumes, fulfilment and exceptions | Admin + Account | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
988 | 988 | M19 | Reports, NFR & delivery gate | QA | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.9 | RPT-09 | Medicine order reports — order volumes, fulfilment and exceptions | RPT-09.04 | QA: cancelled orders not counted as delivered | Regression | Reports | §16 + §12 | Medicine order reports | Order volumes, fulfilment and exceptions | Admin + Account | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
989 | 989 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.10 | RPT-10 | Platform users remaining 20% — import, export and activation control | RPT-10.01 | VerificationStatus on user/doctor list DTO | Existing Improvement | Admin | §7.2 | Platform users | Manage all users with import, export and activation control | Admin Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
990 | 990 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.10 | RPT-10 | Platform users remaining 20% — import, export and activation control | RPT-10.02 | User import/export APIs if missing | Existing Improvement | Admin | §7.2 | Platform users | Manage all users with import, export and activation control | Admin Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
991 | 991 | M19 | Reports, NFR & delivery gate | UI | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.10 | RPT-10 | Platform users remaining 20% — import, export and activation control | RPT-10.03 | ListUser.js wire dead buttons; verification column | Existing Improvement | Admin | §7.2 | Platform users | Manage all users with import, export and activation control | Admin Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
992 | 992 | M19 | Reports, NFR & delivery gate | QA | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.10 | RPT-10 | Platform users remaining 20% — import, export and activation control | RPT-10.04 | QA: export contains only permitted fields | Regression | Admin | §7.2 | Platform users | Manage all users with import, export and activation control | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
993 | 993 | M19 | Reports, NFR & delivery gate | QA | 19 | Phase 19 — Cross-surface QA, NFR, delivery summary gate (PDF §1 + §18) | 19.1 | QA-01 | One ecosystem proof — patient, appointment, prescription and payment created anywhere are visible everywhere | QA-01.01 | E2E: Reception creates patient+appt → Doctor board → sign eRx → Patient app sees codes → Pharmacy accept OTP → patient sees names+pay → Account ledger S2 and S5 | Regression | QA | §1 + §18 | One connected ecosystem | A patient, an appointment, a prescription and a payment created anywhere in the system are visible everywhere else | All | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
994 | 994 | M19 | Reports, NFR & delivery gate | QA | 19 | Phase 19 — Cross-surface QA, NFR, delivery summary gate (PDF §1 + §18) | 19.1 | QA-01 | One ecosystem proof — patient, appointment, prescription and payment created anywhere are visible everywhere | QA-01.02 | E2E: Patient app books+pays tele → doctor app join → summary+eRx → refill on doctor app | Regression | QA | §1 + §18 | One connected ecosystem | A patient, an appointment, a prescription and a payment created anywhere in the system are visible everywhere else | All | QA | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 1 | Not Started |  | Edit on module sheet
995 | 995 | M19 | Reports, NFR & delivery gate | QA | 19 | Phase 19 — Cross-surface QA, NFR, delivery summary gate (PDF §1 + §18) | 19.1 | QA-01 | One ecosystem proof — patient, appointment, prescription and payment created anywhere are visible everywhere | QA-01.03 | Negative: Admin cannot payout; Account cannot edit repertory | Regression | QA | §1 + §18 | One connected ecosystem | A patient, an appointment, a prescription and a payment created anywhere in the system are visible everywhere else | All | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
996 | 996 | M19 | Reports, NFR & delivery gate | QA | 19 | Phase 19 — Cross-surface QA, NFR, delivery summary gate (PDF §1 + §18) | 19.2 | QA-02 | Delivery summary gate — every area in PDF §18 signed off | QA-02.01 | Traceability review: 01_PDF_Coverage every row has Main Task ID and final Status | Regression | QA | §18 | Summary of delivery | All features listed in this document are included in the delivery scope. | Programme | QA | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 0 | N/A |  | Edit on module sheet
997 | 997 | M19 | Reports, NFR & delivery gate | QA | 19 | Phase 19 — Cross-surface QA, NFR, delivery summary gate (PDF §1 + §18) | 19.2 | QA-02 | Delivery summary gate — every area in PDF §18 signed off | QA-02.02 | Do not ship Velzon demo tickets/KYC/ecommerce as product | Regression | QA | §18 | Summary of delivery | All features listed in this document are included in the delivery scope. | Programme | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
998 | 998 | M19 | Reports, NFR & delivery gate | Web | 19 | Phase 19 — Cross-surface QA, NFR, delivery summary gate (PDF §1 + §18) | 19.3 | NFR-01 | NFR — performance, low-data, reliability, secrets, dual-API freeze | NFR-01.01 | Rotate API secrets; keys in config/KeyVault; directory browsing remains off | Existing Modification | NFR | §2.9 + §3 + §17 | Low-data mode / Reliability monitoring / Secure login | Works on slow connections; failures reported automatically; credentials protected | All | Security | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
999 | 999 | M19 | Reports, NFR & delivery gate | QA | 19 | Phase 19 — Cross-surface QA, NFR, delivery summary gate (PDF §1 + §18) | 19.3 | NFR-01 | NFR — performance, low-data, reliability, secrets, dual-API freeze | NFR-01.02 | Performance: slot lock under concurrent public booking | Regression | NFR | §2.9 + §3 + §17 | Low-data mode / Reliability monitoring / Secure login | Works on slow connections; failures reported automatically; credentials protected | All | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
1000 | 1000 | M19 | Reports, NFR & delivery gate | QA | 19 | Phase 19 — Cross-surface QA, NFR, delivery summary gate (PDF §1 + §18) | 19.3 | NFR-01 | NFR — performance, low-data, reliability, secrets, dual-API freeze | NFR-01.03 | Patient low-data mode QA on 2G profile | Regression | NFR | §2.9 + §3 + §17 | Low-data mode / Reliability monitoring / Secure login | Works on slow connections; failures reported automatically; credentials protected | All | QA | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 1 | Not Started |  | Edit on module sheet

## 03_Web
WEB TRACK MIRROR — live from module sheets. Edit layer Status on the module sheet (Open Module Sheet).
Module Seq | Original Seq | Dev Module Code | Dev Module | Track | Phase | Phase Name | WBS | Main Task ID | Main Task | Sub Task ID | Sub Task | Work Type | Source Module / Area | PDF Section | PDF Feature (exact wording) | PDF Delivery Text | Application Surface | Layer | Assigned To (lead) | Frontend | Frontend Status | Frontend Assigned | Backend | Backend Status | Backend Assigned | Database | Database Status | Database Assigned | API | API Status | API Assigned | Mobile | Mobile Status | Mobile Assigned | Integration | Integration Status | Integration Assigned | Layers Remaining | Overall Status | Notes | Open Module Sheet
1 | 1 | M00 | PRE — Client gates | Web | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.1 | PRE-01 | Decide settlement model — Homeocentrum holds all money (food-delivery / quick-commerce pattern) | PRE-01.01 | Workshop with finance: confirm Homeocentrum is single merchant of record for consult + medicine + subscription | Client Decision | Finance | §9 + §8 | Every transaction passes through Homeocentrum | Built on the principle: every transaction passes through Homeocentrum, in the same way a food-delivery or quick-commerce platform holds all payments centrally. | Account / Gateway | Decision | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 0 | N/A |  | Edit on module sheet
2 | 2 | M00 | PRE — Client gates | Web | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.1 | PRE-01 | Decide settlement model — Homeocentrum holds all money (food-delivery / quick-commerce pattern) | PRE-01.02 | Choose v1 payout mechanic: Homeocentrum-held + NEFT/IMPS vs Razorpay Route / linked accounts | Client Decision | Finance | §9 + §8 | Every transaction passes through Homeocentrum | Built on the principle: every transaction passes through Homeocentrum, in the same way a food-delivery or quick-commerce platform holds all payments centrally. | Account / Gateway | Decision | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | 1 | Not Started |  | Edit on module sheet
3 | 3 | M00 | PRE — Client gates | Web | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.1 | PRE-01 | Decide settlement model — Homeocentrum holds all money (food-delivery / quick-commerce pattern) | PRE-01.03 | Record decision in config (SettlementModel) — engineering must not hardcode a split model | Configuration | Finance | §9 + §8 | Every transaction passes through Homeocentrum | Built on the principle: every transaction passes through Homeocentrum, in the same way a food-delivery or quick-commerce platform holds all payments centrally. | Account / Gateway | Configuration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
4 | 4 | M00 | PRE — Client gates | Web | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.2 | PRE-02 | Decide reception cash policy — clinic retains vs remits to Homeocentrum | PRE-02.01 | OQ: cash collected at reception retained by clinic or remitted to Homeocentrum? | Client Decision | Finance / Reception | §9 | Reception payment collection | Cash, UPI, card or payment link with printed receipt | Account / Reception | Decision | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 0 | N/A |  | Edit on module sheet
5 | 5 | M00 | PRE — Client gates | Web | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.2 | PRE-02 | Decide reception cash policy — clinic retains vs remits to Homeocentrum | PRE-02.02 | Document GST treatment on consult fee, platform fee, and medicine (on which amount, which GSTIN) | Client Decision | Finance / Reception | §9 | Reception payment collection | Cash, UPI, card or payment link with printed receipt | Account / Reception | Decision | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 0 | N/A |  | Edit on module sheet
6 | 6 | M00 | PRE — Client gates | Web | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.2 | PRE-02 | Decide reception cash policy — clinic retains vs remits to Homeocentrum | PRE-02.03 | Confirm commission %, settlement hold T+N days, invoice numbering series — configuration not code | Configuration | Finance / Reception | §9 | Reception payment collection | Cash, UPI, card or payment link with printed receipt | Account / Reception | Configuration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
7 | 7 | M00 | PRE — Client gates | Web | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.3 | PRE-03 | Vendor and legal gates — video SDK, SMS, WhatsApp, push, DPDP copy | PRE-03.01 | Select in-browser + mobile video vendor (Agora / Twilio / Daily / WebRTC self-host) — required for §10 | Client Decision | Platform | §10 + §14 + §17 | Telemedicine + notifications + consent | Video consultation; SMS/WhatsApp/Push/Email; consent records | Shared | Decision | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | 1 | Not Started |  | Edit on module sheet
8 | 8 | M00 | PRE — Client gates | Web | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.3 | PRE-03 | Vendor and legal gates — video SDK, SMS, WhatsApp, push, DPDP copy | PRE-03.02 | Select SMS provider (MSG91 / Twilio / etc.) and confirm DLT templates for appointment/OTP/cancel | Client Decision | Platform | §10 + §14 + §17 | Telemedicine + notifications + consent | Video consultation; SMS/WhatsApp/Push/Email; consent records | Shared | Decision | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | 1 | Not Started |  | Edit on module sheet
9 | 9 | M00 | PRE — Client gates | Web | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.3 | PRE-03 | Vendor and legal gates — video SDK, SMS, WhatsApp, push, DPDP copy | PRE-03.03 | Legal: privacy (data protection, recording, pharmacy consent) and terms (payments, refunds, telemedicine, medicine orders) drafted for §4 + §17 | Client Decision | Platform | §10 + §14 + §17 | Telemedicine + notifications + consent | Video consultation; SMS/WhatsApp/Push/Email; consent records | Shared | Legal | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 0 | N/A |  | Edit on module sheet
10 | 10 | M00 | PRE — Client gates | Web | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.3 | PRE-03 | Vendor and legal gates — video SDK, SMS, WhatsApp, push, DPDP copy | PRE-03.04 | OQ: unpaid-booking slot hold duration vs release immediately if patient does not pay | Client Decision | Platform | §10 + §14 + §17 | Telemedicine + notifications + consent | Video consultation; SMS/WhatsApp/Push/Email; consent records | Shared | Decision | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 0 | N/A |  | Edit on module sheet
11 | 11 | M00 | PRE — Client gates | Web | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.3 | PRE-03 | Vendor and legal gates — video SDK, SMS, WhatsApp, push, DPDP copy | PRE-03.05 | OQ: live-doctor credentialing backfill — auto-Approve existing doctors? Unverified doctors visible only to own clinic? | Client Decision | Platform | §10 + §14 + §17 | Telemedicine + notifications + consent | Video consultation; SMS/WhatsApp/Push/Email; consent records | Shared | Decision | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 0 | N/A |  | Edit on module sheet
12 | 12 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.1 | FND-01 | One connected ecosystem — shared keys so a patient, appointment, prescription and payment created anywhere are visible everywhere | FND-01.01 | Publish shared-key design (DoctorId, PatientId, PatientAppId, CaseId, ErxId, LedgerTxnId, MedicineOrderId) and event list (created/rescheduled/cancelled/paid/signed/accepted) | New | Platform | §1 | One connected ecosystem serving six types of users | A patient, an appointment, a prescription and a payment created anywhere in the system are visible everywhere else — there are no separate systems to reconcile. | Shared | Architecture | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
13 | 13 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.1 | FND-01 | One connected ecosystem — shared keys so a patient, appointment, prescription and payment created anywhere are visible everywhere | FND-01.02 | Add role enum values Patient, Account, PharmacyPartner alongside existing Admin/Doctor/Reception (keep unused Management/Supervisor/Inspector unused) | New | Platform | §1 | One connected ecosystem serving six types of users | A patient, an appointment, a prescription and a payment created anywhere in the system are visible everywhere else — there are no separate systems to reconcile. | Shared | Database + Auth | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
14 | 14 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.1 | FND-01 | One connected ecosystem — shared keys so a patient, appointment, prescription and payment created anywhere are visible everywhere | FND-01.03 | All new domain modules on NigaHomeopathy-API (.NET 8); do not create a third API; classic API only where login/Rx-write/Razorpay already live until ported | Existing Modification | Platform | §1 | One connected ecosystem serving six types of users | A patient, an appointment, a prescription and a payment created anywhere in the system are visible everywhere else — there are no separate systems to reconcile. | Shared | Architecture | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
15 | 19 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.2 | FND-02 | Delivery footprint — 2 mobile apps · 5 web portals · payment · telemedicine · digital prescription · HomeoMeds (programme skeleton) | FND-02.04 | Document the five portals: Patient Website, Doctor Web Portal, Reception Portal, Admin Portal, Account Department (Pharmacy console is HomeoMeds, not a 6th portal in the PDF count) | New | Platform | §1 | Delivery covers | 2 mobile applications · 5 web portals · payment system · telemedicine · digital prescription · online medicine delivery. | Shared | Architecture | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 0 | N/A |  | Edit on module sheet
16 | 20 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.3 | SEC-01 | Secure login — protected credentials for every user type | SEC-01.01 | DB/Migration: hash existing UserMaster passwords (bcrypt/PBKDF2); never store new plaintext | Data Migration | Security | §17 | Secure login | Protected credentials for every user type | All web + later mobile | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
17 | 21 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.3 | SEC-01 | Secure login — protected credentials for every user type | SEC-01.02 | API: Login verifies hash; embed Role + DoctorId claims; keep classic login URL until .NET 8 login is cut over | Existing Modification | Security | §17 | Secure login | Protected credentials for every user type | All web + later mobile | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
18 | 24 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.4 | SEC-02 | Secure password reset — time-limited reset links (stop plaintext email + fake thunk) | SEC-02.01 | DB: PasswordResetToken (UserId, TokenHash, ExpiresAt, UsedAt) | New | Security | §17 | Secure password reset | Time-limited reset links | Admin / Doctor / Reception web | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
19 | 25 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.4 | SEC-02 | Secure password reset — time-limited reset links (stop plaintext email + fake thunk) | SEC-02.02 | API: ForgotPassword sends reset link; ResetPassword consumes token; stop emailing plaintext; ChangePassword for authenticated user | Existing Modification | Security | §17 | Secure password reset | Time-limited reset links | Admin / Doctor / Reception web | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
20 | 28 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.5 | SEC-03 | Session control — proper sign-out across web and mobile | SEC-03.01 | API: POST /Account/Logout; persist UserLoginStatus; optional denylist until token expiry | Existing Improvement | Security | §17 | Session control | Proper sign-out across web and mobile | All | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
21 | 30 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.5 | SEC-03 | Session control — proper sign-out across web and mobile | SEC-03.03 | Contract: mobile apps MUST use the same Logout endpoint (implemented in Phases 16–17) | New | Security | §17 | Session control | Proper sign-out across web and mobile | All | API contract | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
22 | 32 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.6 | SEC-04 | Role-based access — each role sees only what it is permitted to see | SEC-04.01 | Backend: restore GetMenuByRole; add role attributes on new money and PII APIs | Existing Improvement | Security | §17 | Role-based access | Each role sees only what it is permitted to see | Admin / All web | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
23 | 34 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.6 | SEC-04 | Role-based access — each role sees only what it is permitted to see | SEC-04.03 | Separation of duties seed: Account role controls money; Admin controls platform and clinical data — neither can perform the other’s role (PDF §8) | New | Security | §17 | Role-based access | Each role sees only what it is permitted to see | Admin / All web | Configuration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
24 | 36 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.7 | SEC-05 | Patient data protection — health records restricted to the treating doctor and the patient | SEC-05.01 | API: enforce DoctorId ownership on Patient, Appointment, Case, Rx, notes, labs, board backup | Existing Improvement | Security | §17 | Patient data protection | Health records restricted to the treating doctor and the patient | API | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
25 | 37 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.7 | SEC-05 | Patient data protection — health records restricted to the treating doctor and the patient | SEC-05.02 | Disable directory browsing on /attachments and /Blogs; signed-URL or authorised download for documents | Existing Modification | Security | §17 | Patient data protection | Health records restricted to the treating doctor and the patient | API | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
26 | 39 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.8 | SEC-06 | Consent records infrastructure — every consent captured, stored and reviewable | SEC-06.01 | DB: ConsentRecord + ConsentType master (Privacy, Booking, TeleRecording, PharmacyShare, Marketing, Caregiver) | New | Security / Trust | §17 | Consent records | Every consent captured, stored and reviewable | Shared | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
27 | 40 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.8 | SEC-06 | Consent records infrastructure — every consent captured, stored and reviewable | SEC-06.02 | API: Grant / Withdraw / List-mine / Admin-audit (no clinical content in the API response beyond type+time) | New | Security / Trust | §17 | Consent records | Every consent captured, stored and reviewable | Shared | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
28 | 41 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.8 | SEC-06 | Consent records infrastructure — every consent captured, stored and reviewable | SEC-06.03 | Reuse AudioCaseConsentLog pattern; do not fork a second consent model for telemedicine (Phase 11 will write TeleRecording into ConsentRecord) | Existing Improvement | Security / Trust | §17 | Consent records | Every consent captured, stored and reviewable | Shared | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
29 | 43 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.9 | SEC-07 | OTP verification infrastructure — applied to sensitive actions including payouts and pharmacy acceptance | SEC-07.01 | DB: OtpChallenge, OtpAuditLog (Action, EntityType, EntityId, ToMasked, Success, At) | New | Security | §17 + §8 + §12 | OTP verification | Applied to sensitive actions including payouts and pharmacy acceptance | Shared | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
30 | 44 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.9 | SEC-07 | OTP verification infrastructure — applied to sensitive actions including payouts and pharmacy acceptance | SEC-07.02 | API: RequestOtp / VerifyOtp (generic); rate-limit; lockout; SMS provider adapter stub until PRE-03 vendor is live | New | Security | §17 + §8 + §12 | OTP verification | Applied to sensitive actions including payouts and pharmacy acceptance | Shared | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
31 | 45 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.9 | SEC-07 | OTP verification infrastructure — applied to sensitive actions including payouts and pharmacy acceptance | SEC-07.03 | GET /api/Otp/Audit for Account and Admin (masked destination) | New | Security | §17 + §8 + §12 | OTP verification | Applied to sensitive actions including payouts and pharmacy acceptance | Shared | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
32 | 47 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.10 | SEC-08 | Complete audit trail — who did what and when across payments, prescriptions and approvals | SEC-08.01 | DB: AuditEvent (ActorUserId, Role, Action, Entity, OldJson, NewJson, At, CorrelationId) | New | Security | §17 + §9 | Complete audit trail | Who did what, and when, across payments, prescriptions and approvals / Every transaction traceable end to end by Homeocentrum | Shared | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
33 | 48 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.10 | SEC-08 | Complete audit trail — who did what and when across payments, prescriptions and approvals | SEC-08.02 | API middleware: write audit on mutating money/Rx/approval endpoints (start with a helper used by later phases) | New | Security | §17 + §9 | Complete audit trail | Who did what, and when, across payments, prescriptions and approvals / Every transaction traceable end to end by Homeocentrum | Shared | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
34 | 50 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.11 | SEC-09 | Secure documents — prescriptions, reports and uploads protected from unauthorised access | SEC-09.01 | DB: SecureDocument (OwnerType, OwnerId, BlobPath, Mime, Hash, CreatedBy) | New | Security | §17 | Secure documents | Prescriptions, reports and uploads protected from unauthorised access | Shared | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
35 | 51 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.11 | SEC-09 | Secure documents — prescriptions, reports and uploads protected from unauthorised access | SEC-09.02 | API: upload (multipart) + authorised GET; no public folder listing | New | Security | §17 | Secure documents | Prescriptions, reports and uploads protected from unauthorised access | Shared | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
36 | 54 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.1 | ADM-R01 | Keep and harden Admin Repertory sections (do not rebuild) | ADM-R01.02 | ACL: only Admin (and permitted roles) can mutate Repertory sections; Doctor is read-only consumer on Patient Board | Existing Improvement | Repertory | §7.1 | Repertory sections | Manage repertory sections | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
37 | 55 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.1 | ADM-R01 | Keep and harden Admin Repertory sections (do not rebuild) | ADM-R01.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Repertory sections; do not silently switch | Existing | Repertory | §7.1 | Repertory sections | Manage repertory sections | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
38 | 57 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.2 | ADM-R02 | Keep and harden Admin Subsection & rubric tree (do not rebuild) | ADM-R02.02 | ACL: only Admin (and permitted roles) can mutate Subsection & rubric tree; Doctor is read-only consumer on Patient Board | Existing Improvement | Repertory | §7.1 | Subsection & rubric tree | Manage the full rubric hierarchy | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
39 | 58 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.2 | ADM-R02 | Keep and harden Admin Subsection & rubric tree (do not rebuild) | ADM-R02.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Subsection & rubric tree; do not silently switch | Existing | Repertory | §7.1 | Subsection & rubric tree | Manage the full rubric hierarchy | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
40 | 60 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.3 | ADM-R03 | Keep and harden Admin Rubric–remedy mapping (do not rebuild) | ADM-R03.02 | ACL: only Admin (and permitted roles) can mutate Rubric–remedy mapping; Doctor is read-only consumer on Patient Board | Existing Improvement | Repertory | §7.1 | Rubric–remedy mapping | Map remedies to rubrics with author and grade | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
41 | 61 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.3 | ADM-R03 | Keep and harden Admin Rubric–remedy mapping (do not rebuild) | ADM-R03.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Rubric–remedy mapping; do not silently switch | Existing | Repertory | §7.1 | Rubric–remedy mapping | Map remedies to rubrics with author and grade | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
42 | 63 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.4 | ADM-R04 | Keep and harden Admin Remedy-linked rubrics (do not rebuild) | ADM-R04.02 | ACL: only Admin (and permitted roles) can mutate Remedy-linked rubrics; Doctor is read-only consumer on Patient Board | Existing Improvement | Repertory | §7.1 | Remedy-linked rubrics | View all rubrics linked to a remedy | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
43 | 64 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.4 | ADM-R04 | Keep and harden Admin Remedy-linked rubrics (do not rebuild) | ADM-R04.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Remedy-linked rubrics; do not silently switch | Existing | Repertory | §7.1 | Remedy-linked rubrics | View all rubrics linked to a remedy | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
44 | 66 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.5 | ADM-R05 | Keep and harden Admin Language master (do not rebuild) | ADM-R05.02 | ACL: only Admin (and permitted roles) can mutate Language master; Doctor is read-only consumer on Patient Board | Existing Improvement | Repertory | §7.1 | Language master | Manage languages | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
45 | 67 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.5 | ADM-R05 | Keep and harden Admin Language master (do not rebuild) | ADM-R05.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Language master; do not silently switch | Existing | Repertory | §7.1 | Language master | Manage languages | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
46 | 69 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.6 | ADM-R06 | Keep and harden Admin Body part master (do not rebuild) | ADM-R06.02 | ACL: only Admin (and permitted roles) can mutate Body part master; Doctor is read-only consumer on Patient Board | Existing Improvement | Repertory | §7.1 | Body part master | Manage body parts | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
47 | 70 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.6 | ADM-R06 | Keep and harden Admin Body part master (do not rebuild) | ADM-R06.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Body part master; do not silently switch | Existing | Repertory | §7.1 | Body part master | Manage body parts | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
48 | 72 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.7 | ADM-R07 | Keep and harden Admin Intensity master (do not rebuild) | ADM-R07.02 | ACL: only Admin (and permitted roles) can mutate Intensity master; Doctor is read-only consumer on Patient Board | Existing Improvement | Repertory | §7.1 | Intensity master | Manage intensity levels | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
49 | 73 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.7 | ADM-R07 | Keep and harden Admin Intensity master (do not rebuild) | ADM-R07.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Intensity master; do not silently switch | Existing | Repertory | §7.1 | Intensity master | Manage intensity levels | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
50 | 75 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.8 | ADM-R08 | Keep and harden Admin Remedy master (do not rebuild) | ADM-R08.02 | ACL: only Admin (and permitted roles) can mutate Remedy master; Doctor is read-only consumer on Patient Board | Existing Improvement | Repertory | §7.1 | Remedy master | Manage the remedy library | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
51 | 76 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.8 | ADM-R08 | Keep and harden Admin Remedy master (do not rebuild) | ADM-R08.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Remedy master; do not silently switch | Existing | Repertory | §7.1 | Remedy master | Manage the remedy library | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
52 | 78 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.9 | ADM-R09 | Keep and harden Admin Remedy grade master (do not rebuild) | ADM-R09.02 | ACL: only Admin (and permitted roles) can mutate Remedy grade master; Doctor is read-only consumer on Patient Board | Existing Improvement | Repertory | §7.1 | Remedy grade master | Manage remedy grading | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
53 | 79 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.9 | ADM-R09 | Keep and harden Admin Remedy grade master (do not rebuild) | ADM-R09.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Remedy grade master; do not silently switch | Existing | Repertory | §7.1 | Remedy grade master | Manage remedy grading | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
54 | 81 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.10 | ADM-M01 | Keep and harden Admin Author master (do not rebuild) | ADM-M01.02 | ACL: only Admin (and permitted roles) can mutate Author master; Doctor is read-only consumer on Patient Board | Existing Improvement | Materia Medica | §7.1 | Author master | Manage materia medica authors | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
55 | 82 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.10 | ADM-M01 | Keep and harden Admin Author master (do not rebuild) | ADM-M01.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Author master; do not silently switch | Existing | Materia Medica | §7.1 | Author master | Manage materia medica authors | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
56 | 84 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.11 | ADM-M02 | Keep and harden Admin Materia medica master (do not rebuild) | ADM-M02.02 | ACL: only Admin (and permitted roles) can mutate Materia medica master; Doctor is read-only consumer on Patient Board | Existing Improvement | Materia Medica | §7.1 | Materia medica master | Manage the materia medica library | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
57 | 85 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.11 | ADM-M02 | Keep and harden Admin Materia medica master (do not rebuild) | ADM-M02.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Materia medica master; do not silently switch | Existing | Materia Medica | §7.1 | Materia medica master | Manage the materia medica library | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
58 | 87 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.12 | ADM-M03 | Keep and harden Admin Materia medica heads (do not rebuild) | ADM-M03.02 | ACL: only Admin (and permitted roles) can mutate Materia medica heads; Doctor is read-only consumer on Patient Board | Existing Improvement | Materia Medica | §7.1 | Materia medica heads | Manage chapter headings | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
59 | 88 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.12 | ADM-M03 | Keep and harden Admin Materia medica heads (do not rebuild) | ADM-M03.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Materia medica heads; do not silently switch | Existing | Materia Medica | §7.1 | Materia medica heads | Manage chapter headings | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
60 | 90 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.13 | ADM-M04 | Keep and harden Admin Materia medica remedies (do not rebuild) | ADM-M04.02 | ACL: only Admin (and permitted roles) can mutate Materia medica remedies; Doctor is read-only consumer on Patient Board | Existing Improvement | Materia Medica | §7.1 | Materia medica remedies | View remedy-wise materia medica | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
61 | 91 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.13 | ADM-M04 | Keep and harden Admin Materia medica remedies (do not rebuild) | ADM-M04.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Materia medica remedies; do not silently switch | Existing | Materia Medica | §7.1 | Materia medica remedies | View remedy-wise materia medica | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
62 | 93 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.14 | ADM-D01 | Keep and harden Admin Diagnosis system (do not rebuild) | ADM-D01.02 | ACL: only Admin (and permitted roles) can mutate Diagnosis system; Doctor is read-only consumer on Patient Board | Existing Improvement | Diagnosis | §7.1 | Diagnosis system | Manage diagnosis systems | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
63 | 94 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.14 | ADM-D01 | Keep and harden Admin Diagnosis system (do not rebuild) | ADM-D01.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Diagnosis system; do not silently switch | Existing | Diagnosis | §7.1 | Diagnosis system | Manage diagnosis systems | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
64 | 96 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.15 | ADM-D02 | Keep and harden Admin Diagnosis therapeutics (do not rebuild) | ADM-D02.02 | ACL: only Admin (and permitted roles) can mutate Diagnosis therapeutics; Doctor is read-only consumer on Patient Board | Existing Improvement | Diagnosis | §7.1 | Diagnosis therapeutics | Manage therapeutics | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
65 | 97 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.15 | ADM-D02 | Keep and harden Admin Diagnosis therapeutics (do not rebuild) | ADM-D02.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Diagnosis therapeutics; do not silently switch | Existing | Diagnosis | §7.1 | Diagnosis therapeutics | Manage therapeutics | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
66 | 99 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.16 | ADM-D03 | Keep and harden Admin Diagnosis conditions (do not rebuild) | ADM-D03.02 | ACL: only Admin (and permitted roles) can mutate Diagnosis conditions; Doctor is read-only consumer on Patient Board | Existing Improvement | Diagnosis | §7.1 | Diagnosis conditions | Manage conditions and linked rubrics | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
67 | 100 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.16 | ADM-D03 | Keep and harden Admin Diagnosis conditions (do not rebuild) | ADM-D03.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Diagnosis conditions; do not silently switch | Existing | Diagnosis | §7.1 | Diagnosis conditions | Manage conditions and linked rubrics | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
68 | 102 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.17 | ADM-A01 | Keep and harden Admin Drug system (do not rebuild) | ADM-A01.02 | ACL: only Admin (and permitted roles) can mutate Drug system; Doctor is read-only consumer on Patient Board | Existing Improvement | Adverse Effect | §7.1 | Drug system | Manage conventional drug systems | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
69 | 103 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.17 | ADM-A01 | Keep and harden Admin Drug system (do not rebuild) | ADM-A01.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Drug system; do not silently switch | Existing | Adverse Effect | §7.1 | Drug system | Manage conventional drug systems | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
70 | 105 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.18 | ADM-A02 | Keep and harden Admin Drug group (do not rebuild) | ADM-A02.02 | ACL: only Admin (and permitted roles) can mutate Drug group; Doctor is read-only consumer on Patient Board | Existing Improvement | Adverse Effect | §7.1 | Drug group | Manage drug groups | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
71 | 106 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.18 | ADM-A02 | Keep and harden Admin Drug group (do not rebuild) | ADM-A02.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Drug group; do not silently switch | Existing | Adverse Effect | §7.1 | Drug group | Manage drug groups | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
72 | 108 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.19 | ADM-A03 | Keep and harden Admin Allopathic drug & side effects (do not rebuild) | ADM-A03.02 | ACL: only Admin (and permitted roles) can mutate Allopathic drug & side effects; Doctor is read-only consumer on Patient Board | Existing Improvement | Adverse Effect | §7.1 | Allopathic drug & side effects | Manage drugs with side effects and adverse reactions | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
73 | 109 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.19 | ADM-A03 | Keep and harden Admin Allopathic drug & side effects (do not rebuild) | ADM-A03.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Allopathic drug & side effects; do not silently switch | Existing | Adverse Effect | §7.1 | Allopathic drug & side effects | Manage drugs with side effects and adverse reactions | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
74 | 111 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.20 | ADM-Q01 | Keep and harden Admin Question section, group & sub-group (do not rebuild) | ADM-Q01.02 | ACL: only Admin (and permitted roles) can mutate Question section, group & sub-group; Doctor is read-only consumer on Patient Board | Existing Improvement | Clinical Questions | §7.1 | Question section, group & sub-group | Manage the clinical questionnaire structure | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
75 | 112 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.20 | ADM-Q01 | Keep and harden Admin Question section, group & sub-group (do not rebuild) | ADM-Q01.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Question section, group & sub-group; do not silently switch | Existing | Clinical Questions | §7.1 | Question section, group & sub-group | Manage the clinical questionnaire structure | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
76 | 114 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.21 | ADM-Q02 | Keep and harden Admin Clinical question mapping (do not rebuild) | ADM-Q02.02 | ACL: only Admin (and permitted roles) can mutate Clinical question mapping; Doctor is read-only consumer on Patient Board | Existing Improvement | Clinical Questions | §7.1 | Clinical question mapping | Map questions to body parts and rubrics | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
77 | 115 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.21 | ADM-Q02 | Keep and harden Admin Clinical question mapping (do not rebuild) | ADM-Q02.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Clinical question mapping; do not silently switch | Existing | Clinical Questions | §7.1 | Clinical question mapping | Map questions to body parts and rubrics | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
78 | 117 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.22 | ADM-3D1 | Keep and harden Admin 3D mesh key master (do not rebuild) | ADM-3D1.02 | ACL: only Admin (and permitted roles) can mutate 3D mesh key master; Doctor is read-only consumer on Patient Board | Existing Improvement | 3D Body | §7.1 | 3D mesh key master | Manage 3D model references | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
79 | 118 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.22 | ADM-3D1 | Keep and harden Admin 3D mesh key master (do not rebuild) | ADM-3D1.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for 3D mesh key master; do not silently switch | Existing | 3D Body | §7.1 | 3D mesh key master | Manage 3D model references | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
80 | 120 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.23 | ADM-3D2 | Keep and harden Admin 3D section master (do not rebuild) | ADM-3D2.02 | ACL: only Admin (and permitted roles) can mutate 3D section master; Doctor is read-only consumer on Patient Board | Existing Improvement | 3D Body | §7.1 | 3D section master | Manage 3D body sections | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
81 | 121 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.23 | ADM-3D2 | Keep and harden Admin 3D section master (do not rebuild) | ADM-3D2.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for 3D section master; do not silently switch | Existing | 3D Body | §7.1 | 3D section master | Manage 3D body sections | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
82 | 123 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.24 | ADM-3D3 | Keep and harden Admin 3D hotspots (do not rebuild) | ADM-3D3.02 | ACL: only Admin (and permitted roles) can mutate 3D hotspots; Doctor is read-only consumer on Patient Board | Existing Improvement | 3D Body | §7.1 | 3D hotspots | Manage clickable points on the 3D model | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
83 | 124 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.24 | ADM-3D3 | Keep and harden Admin 3D hotspots (do not rebuild) | ADM-3D3.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for 3D hotspots; do not silently switch | Existing | 3D Body | §7.1 | 3D hotspots | Manage clickable points on the 3D model | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
84 | 126 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.25 | ADM-B01 | Business Management — Doctor qualifications (existing, used later by credentialing) | ADM-B01.02 | ACL on qualification APIs | Existing Improvement | Business Management | §7.2 | Doctor qualifications | Manage the qualification list | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
85 | 127 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.25 | ADM-B01 | Business Management — Doctor qualifications (existing, used later by credentialing) | ADM-B01.03 | Confirm UI uses newer API (not classic) for qualifications | Existing | Business Management | §7.2 | Doctor qualifications | Manage the qualification list | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
86 | 129 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.26 | ADM-B02 | Business Management — Lab & imaging test catalog (existing, used by eRx lab orders) | ADM-B02.02 | ACL on catalog mutate | Existing Improvement | Business Management | §7.2 | Lab & imaging test catalog | Manage the test catalogue | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
87 | 130 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.26 | ADM-B02 | Business Management — Lab & imaging test catalog (existing, used by eRx lab orders) | ADM-B02.03 | Confirm classic PatientLab APIs still read this catalogue | Existing | Business Management | §7.2 | Lab & imaging test catalog | Manage the test catalogue | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
88 | 132 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.27 | ADM-B03 | Business Management — Subscription packages (existing S1 SaaS; later tied to Account ledger) | ADM-B03.02 | ACL on package mutate | Existing Improvement | Business Management | §7.2 | Subscription packages | Manage doctor subscription plans | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
89 | 133 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.27 | ADM-B03 | Business Management — Subscription packages (existing S1 SaaS; later tied to Account ledger) | ADM-B03.03 | Note in code: PackageEntryDetail is S1 only — never reuse for S2 consult or S5 medicine | Existing | Business Management | §7.2 | Subscription packages | Manage doctor subscription plans | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | Edit on module sheet
90 | 134 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.28 | ADM-B04 | Business Management — Roles & menu permissions (existing DB, runtime ACL leftover) | ADM-B04.01 | No schema change unless Account/Pharmacy/Patient roles need new MenuMaster rows — seed those menus | Existing Improvement | Business Management | §7.2 | Roles & menu permissions | Control exactly what each role can access | Admin Portal | Database | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | Yes | In Progress | Gourav Nikam | No | N/A |  | No | N/A |  | No | N/A |  | 1 | In Progress |  | Edit on module sheet
91 | 135 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.28 | ADM-B04 | Business Management — Roles & menu permissions (existing DB, runtime ACL leftover) | ADM-B04.02 | Restore GetMenuByRole on .NET 8; seed menus for Account and (later) Pharmacy | Existing Improvement | Business Management | §7.2 | Roles & menu permissions | Control exactly what each role can access | Admin Portal | API | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | Yes | In Progress | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 1 | In Progress |  | Edit on module sheet
92 | 139 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.1 | CLN-01 | Clinical workspace — single screen for the entire consultation | CLN-01.02 | Do not split the board into multiple apps; mobile doctor app will NOT get case-taking (PDF §3) | Existing | Patient Board | §5.3 | Clinical workspace | Single screen for the entire consultation | Doctor Web Portal | Architecture | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 0 | N/A |  | Edit on module sheet
93 | 142 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.2 | CLN-02 | Manual case taking — structured case taking (keep) | CLN-02.02 | ACL: only treating doctor (not Reception) can run full case taking | Existing Improvement | Patient Board | §5.3 | Manual case taking | Structured case taking | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
94 | 143 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.2 | CLN-02 | Manual case taking — structured case taking (keep) | CLN-02.03 | Confirm clipboard/repertorization APIs still on the correct host | Existing | Patient Board | §5.3 | Manual case taking | Structured case taking | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
95 | 145 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.3 | CLN-03 | Body parts & intensity selection (keep) | CLN-03.02 | ACL: doctor-only | Existing Improvement | Patient Board | §5.3 | Body parts & intensity selection | Select affected areas and severity | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
96 | 146 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.3 | CLN-03 | Body parts & intensity selection (keep) | CLN-03.03 | API host unchanged | Existing | Patient Board | §5.3 | Body parts & intensity selection | Select affected areas and severity | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
97 | 148 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.4 | CLN-04 | Clinical questions — guided questions by section, group and sub-group (keep) | CLN-04.02 | ACL doctor-only | Existing Improvement | Patient Board | §5.3 | Clinical questions | Guided questions by section, group and sub-group | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
98 | 149 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.4 | CLN-04 | Clinical questions — guided questions by section, group and sub-group (keep) | CLN-04.03 | API host unchanged | Existing | Patient Board | §5.3 | Clinical questions | Guided questions by section, group and sub-group | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
99 | 151 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.5 | CLN-05 | Diagnosis, therapeutics & pattern search (keep) | CLN-05.02 | ACL doctor-only | Existing Improvement | Patient Board | §5.3 | Diagnosis, therapeutics & pattern search | Search diagnoses and linked therapeutics | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
100 | 152 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.5 | CLN-05 | Diagnosis, therapeutics & pattern search (keep) | CLN-05.03 | API host unchanged | Existing | Patient Board | §5.3 | Diagnosis, therapeutics & pattern search | Search diagnoses and linked therapeutics | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
101 | 154 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.6 | CLN-06 | Repertory rubric search & selection (keep) | CLN-06.02 | ACL doctor-only | Existing Improvement | Patient Board | §5.3 | Repertory rubric search & selection | Search and select from the full repertory | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
102 | 155 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.6 | CLN-06 | Repertory rubric search & selection (keep) | CLN-06.03 | Confirm subsection search host (newer vs classic) documented | Existing | Patient Board | §5.3 | Repertory rubric search & selection | Search and select from the full repertory | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
103 | 156 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.7 | CLN-07 | Manage selected rubrics — review, edit and remove (remaining ~10%) | CLN-07.01 | No new table — clipboard already persisted via board backup / repertorization payload | Existing Improvement | Patient Board | §5.3 | Manage selected rubrics | Review, edit and remove selected rubrics | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
104 | 157 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.7 | CLN-07 | Manage selected rubrics — review, edit and remove (remaining ~10%) | CLN-07.02 | If intensity-on-clipboard is client-only, persist it on backup payload | Existing Improvement | Patient Board | §5.3 | Manage selected rubrics | Review, edit and remove selected rubrics | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
105 | 161 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.8 | CLN-08 | Audio case taking — record and receive suggested rubrics (keep engine; do not rebuild) | CLN-08.02 | Consent: audio consent continues to write AudioCaseConsentLog (later also ConsentRecord) | Existing Improvement | Audio AI | §5.3 | Audio case taking | Record the consultation and receive suggested rubrics automatically | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
106 | 162 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.8 | CLN-08 | Audio case taking — record and receive suggested rubrics (keep engine; do not rebuild) | CLN-08.03 | Confirm audio queue/worker still healthy | Existing | Audio AI | §5.3 | Audio case taking | Record the consultation and receive suggested rubrics automatically | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
107 | 163 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.9 | CLN-09 | Improved rubric accuracy — enhanced accuracy rules for audio-based rubric suggestions | CLN-09.01 | Follow AUDIO_CASE_TAKING_* docs: accuracy rules, aliases, metaphors, benchmark | Existing Improvement | Audio AI | §5.3 | Improved rubric accuracy | Enhanced accuracy rules for audio-based rubric suggestions | Doctor Web Portal + Admin intelligence | Backend | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
108 | 166 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.10 | CLN-10 | Materia medica reference during consultation (remaining ~10%) | CLN-10.01 | No schema change | Existing Improvement | Patient Board | §5.3 | Materia medica reference | Browse materia medica during the consultation | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
109 | 167 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.10 | CLN-10 | Materia medica reference during consultation (remaining ~10%) | CLN-10.02 | Existing MM APIs — add a lightweight get-by-remedy if chatty | Existing Improvement | Patient Board | §5.3 | Materia medica reference | Browse materia medica during the consultation | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
110 | 171 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.11 | CLN-11 | Allopathic drug side-effect lookup (keep) | CLN-11.02 | ACL doctor-only | Existing Improvement | Patient Board | §5.3 | Allopathic drug side-effect lookup | Check side effects of conventional medicines | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
111 | 172 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.11 | CLN-11 | Allopathic drug side-effect lookup (keep) | CLN-11.03 | API host unchanged | Existing | Patient Board | §5.3 | Allopathic drug side-effect lookup | Check side effects of conventional medicines | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
112 | 173 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.12 | CLN-12 | Repertorization & elimination (remaining ~10%) | CLN-12.01 | No schema change | Existing Improvement | Patient Board | §5.3 | Repertorization & elimination | Full repertorization with elimination | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
113 | 174 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.12 | CLN-12 | Repertorization & elimination (remaining ~10%) | CLN-12.02 | Keep existing repertorization APIs; fix any known scoring edge cases | Existing Improvement | Patient Board | §5.3 | Repertorization & elimination | Full repertorization with elimination | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
114 | 177 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.13 | CLN-13 | Center of Gravity — new analysis identifying the central remedy of the case, with reasoning shown | CLN-13.01 | No mandatory new table (algorithm on selected rubrics); optional CogRun log for support | New | Repertorization | §5.3 | Center of Gravity | New analysis identifying the central remedy of the case, with reasoning shown | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
115 | 178 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.13 | CLN-13 | Center of Gravity — new analysis identifying the central remedy of the case, with reasoning shown | CLN-13.02 | POST /api/Repertorization/CenterOfGravity — input rubric ids + intensities; output ranked remedies + reasons | New | Repertorization | §5.3 | Center of Gravity | New analysis identifying the central remedy of the case, with reasoning shown | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
116 | 182 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.14 | CLN-14 | Lab orders & lab entries (keep; later also sit on eRx) | CLN-14.02 | ACL doctor-only | Existing Improvement | Patient Board | §5.3 + §11 | Lab orders & lab entries | Order tests and record results / Tests ordered alongside the prescription | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
117 | 183 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.14 | CLN-14 | Lab orders & lab entries (keep; later also sit on eRx) | CLN-14.03 | API: classic PatientLab still authoritative until ported | Existing | Patient Board | §5.3 + §11 | Lab orders & lab entries | Order tests and record results / Tests ordered alongside the prescription | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
118 | 185 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.15 | CLN-15 | Appointment history notes (keep; split from eRx in Phase 10) | CLN-15.02 | ACL doctor-only | Existing Improvement | Patient Board | §5.3 | Appointment history notes | Notes recorded against each visit | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
119 | 186 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.15 | CLN-15 | Appointment history notes (keep; split from eRx in Phase 10) | CLN-15.03 | Do not dual-write; classic notes stay until Phase 10 extends them | Existing | Patient Board | §5.3 | Appointment history notes | Notes recorded against each visit | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
120 | 187 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.16 | CLN-16 | Complaints & case details — wire Patient Board to existing SaveComplaints / SaveCaseDetails (~20% today) | CLN-16.01 | Use existing tables — no new schema unless fields are missing vs PDF | Existing Improvement | Patient Board | §5.3 | Complaints & case details | Capture and store complaints and case details | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
121 | 188 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.16 | CLN-16 | Complaints & case details — wire Patient Board to existing SaveComplaints / SaveCaseDetails (~20% today) | CLN-16.02 | Keep classic SaveComplaints / SaveCaseDetails; add GET if missing | Existing Improvement | Patient Board | §5.3 | Complaints & case details | Capture and store complaints and case details | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
122 | 191 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.17 | CLN-17 | Patient back history — complete history of visits, notes, prescriptions and payments | CLN-17.01 | No new table — compose from Appointment + notes + Rx + (later) ConsultPayment | Existing Improvement | Patient Board | §5.3 | Patient back history | Complete history of visits, notes, prescriptions and payments | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
123 | 192 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.17 | CLN-17 | Patient back history — complete history of visits, notes, prescriptions and payments | CLN-17.02 | GET patient timeline DTO including payment status when column exists | Existing Improvement | Patient Board | §5.3 | Patient back history | Complete history of visits, notes, prescriptions and payments | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
124 | 195 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.18 | CLN-18 | Export case data — download the full case in Excel or PDF | CLN-18.01 | Reuse ExportCasesToExcel; add PDF generation of the clinical case (doctor copy, includes notes) | Existing Improvement | Patient Board | §5.3 | Export case data | Download the full case in Excel or PDF | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
125 | 199 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.19 | CLN-19 | Session restore — continue exactly where the doctor left off, across multiple patients (keep) | CLN-19.02 | ACL: backup scoped to DoctorId | Existing Improvement | Patient Board | §5.3 | Session restore | Continue exactly where the doctor left off, across multiple patients | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
126 | 200 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.19 | CLN-19 | Session restore — continue exactly where the doctor left off, across multiple patients (keep) | CLN-19.03 | API: PatientBoardBackup on .NET 8 unchanged | Existing | Patient Board | §5.3 | Session restore | Continue exactly where the doctor left off, across multiple patients | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
127 | 201 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.20 | CLN-20 | 3D anatomy viewer — interactive 3D body model linked to rubric search (remaining ~50%) | CLN-20.01 | No new tables — Mesh/Section/Hotspot masters already exist | Existing Improvement | Anatomy | §5.3 | 3D anatomy viewer | Interactive 3D body model linked to rubric search | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
128 | 202 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.20 | CLN-20 | 3D anatomy viewer — interactive 3D body model linked to rubric search (remaining ~50%) | CLN-20.02 | Fix hotspot mapping gaps on newer threeDBodyPart APIs | Existing Improvement | Anatomy | §5.3 | 3D anatomy viewer | Interactive 3D body model linked to rubric search | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
129 | 205 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.1 | DOC-01 | Doctor home dashboard — complete overview of the working day (remaining ~30%) | DOC-01.01 | No new dashboard table | Existing Improvement | Doctor Dashboard | §5.1 | Doctor home dashboard | Complete overview of the working day | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
130 | 206 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.1 | DOC-01 | Doctor home dashboard — complete overview of the working day (remaining ~30%) | DOC-01.02 | Extend dashboard DTOs with paymentStatus / tele flags when columns exist (nullable until Phase 6/11) | Existing Improvement | Doctor Dashboard | §5.1 | Doctor home dashboard | Complete overview of the working day | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
131 | 210 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.2 | DOC-02 | Patient counts & waiting list — live counts by status with quick actions (keep; extend paid/unpaid) | DOC-02.02 | Reception sharing this view is OK until Phase 5 splits chrome | Existing Improvement | Doctor Dashboard | §5.1 | Patient counts & waiting list | Live counts by status with quick actions | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
132 | 211 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.2 | DOC-02 | Patient counts & waiting list — live counts by status with quick actions (keep; extend paid/unpaid) | DOC-02.03 | API: existing dashboard count endpoints | Existing | Doctor Dashboard | §5.1 | Patient counts & waiting list | Live counts by status with quick actions | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
133 | 212 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.3 | DOC-03 | Patient search, list & open case (remaining ~10%) | DOC-03.01 | Use existing Patient + Appointment — add DTO fields | Existing Improvement | Doctor Dashboard | §5.1 | Patient search, list & open case | Find any patient and open their case instantly | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
134 | 213 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.3 | DOC-03 | Patient search, list & open case (remaining ~10%) | DOC-03.02 | Search DTO includes lastVisitAt | Existing Improvement | Doctor Dashboard | §5.1 | Patient search, list & open case | Find any patient and open their case instantly | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
135 | 217 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.4 | DOC-04 | Add new patient — register a patient in seconds (keep) | DOC-04.02 | ACL: doctor/reception of that clinic only | Existing Improvement | Patients | §5.1 | Add new patient | Register a patient in seconds | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
136 | 218 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.4 | DOC-04 | Add new patient — register a patient in seconds (keep) | DOC-04.03 | API unchanged | Existing | Patients | §5.1 | Add new patient | Register a patient in seconds | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
137 | 220 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.5 | DOC-05 | Import patients — bring existing patient records in bulk (keep) | DOC-05.02 | ACL doctor-only (or reception if already allowed) | Existing Improvement | Patients | §5.1 | Import patients | Bring existing patient records in bulk | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
138 | 221 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.5 | DOC-05 | Import patients — bring existing patient records in bulk (keep) | DOC-05.03 | API unchanged | Existing | Patients | §5.1 | Import patients | Bring existing patient records in bulk | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
139 | 222 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.6 | DOC-06 | Export patients — download patient data in Excel, CSV or PDF (keep) | DOC-06.01 | Audit current export formats; add PDF if only Excel/CSV exist today | Existing Improvement | Patients | §5.1 | Export patients | Download patient data in Excel, CSV or PDF | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
140 | 226 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.7 | DOC-07 | Recent activity panel (keep) | DOC-07.02 | ACL scoped to doctor | Existing Improvement | Doctor Dashboard | §5.1 | Recent activity panel | Everything that happened recently, at a glance | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
141 | 227 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.7 | DOC-07 | Recent activity panel (keep) | DOC-07.03 | API unchanged | Existing | Doctor Dashboard | §5.1 | Recent activity panel | Everything that happened recently, at a glance | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
142 | 229 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.8 | DOC-08 | Patient statistics charts (keep; foundation for clinic performance in Phase 18) | DOC-08.02 | ACL doctor-only | Existing Improvement | Doctor Dashboard | §5.1 | Patient statistics charts | Visual practice statistics | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
143 | 230 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.8 | DOC-08 | Patient statistics charts (keep; foundation for clinic performance in Phase 18) | DOC-08.03 | API unchanged | Existing | Doctor Dashboard | §5.1 | Patient statistics charts | Visual practice statistics | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
144 | 231 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.9 | DOC-09 | Manage reception staff — add, edit and remove reception users (backend done, UI absent) | DOC-09.01 | No new API — authorise that the doctor owns the staff record on existing CRUD | Existing Improvement | Staff | §5.1 | Manage reception staff | Add, edit and remove reception users | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
145 | 234 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.10 | DOC-10 | Doctor profile — clinic details, consultation fee, photo, qualifications, working hours, bank details | DOC-10.01 | Extend Doctor / add DoctorPayeeKyc fields (bank, PAN) used later by Account; ConsultFeeConfig may wait until Phase 6 — store fee on profile now if simpler | Existing Improvement | Doctor Profile | §5.1 | Doctor profile | Clinic details, consultation fee, photo, qualifications, working hours, bank details | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
146 | 235 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.10 | DOC-10 | Doctor profile — clinic details, consultation fee, photo, qualifications, working hours, bank details | DOC-10.02 | GET/PUT /api/Profile/Me (doctor DTO); POST photo multipart; do not allow role escalation | Existing Improvement | Doctor Profile | §5.1 | Doctor profile | Clinic details, consultation fee, photo, qualifications, working hours, bank details | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
147 | 239 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.1 | APT-01 | Appointment list & waiting patients — full day view with live status (keep; later payment/tele) | APT-01.02 | ACL doctor/reception of that DoctorId | Existing Improvement | Appointments | §5.2 | Appointment list & waiting patients | Full day view with live status | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
148 | 240 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.1 | APT-01 | Appointment list & waiting patients — full day view with live status (keep; later payment/tele) | APT-01.03 | API unchanged | Existing | Appointments | §5.2 | Appointment list & waiting patients | Full day view with live status | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
149 | 241 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.2 | APT-02 | Create new appointment — persist visit type, consultation mode and fee | APT-02.01 | DB: PatientAppointment.VisitType, ConsultMode; migrate existing rows VisitType=First (do not infer retrospectively) | Existing Improvement | Appointments | §5.2 | Create new appointment | Book with visit type, consultation mode and fee | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
150 | 242 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.2 | APT-02 | Create new appointment — persist visit type, consultation mode and fee | APT-02.02 | API: create/update appointment accepts the new fields; PATCH VisitType | Existing Improvement | Appointments | §5.2 | Create new appointment | Book with visit type, consultation mode and fee | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
151 | 246 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.3 | APT-03 | Appointment status update — move patients through the visit stages (keep) | APT-03.02 | ACL doctor/reception | Existing Improvement | Appointments | §5.2 | Appointment status update | Move patients through the visit stages | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
152 | 247 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.3 | APT-03 | Appointment status update — move patients through the visit stages (keep) | APT-03.03 | API unchanged | Existing | Appointments | §5.2 | Appointment status update | Move patients through the visit stages | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
153 | 249 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.4 | APT-04 | Appointment time update — adjust timings as the day runs (keep; distinct from formal reschedule) | APT-04.02 | Document in UI that Reschedule is the patient-notified path | Existing Improvement | Appointments | §5.2 | Appointment time update | Adjust timings as the day runs | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
154 | 250 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.4 | APT-04 | Appointment time update — adjust timings as the day runs (keep; distinct from formal reschedule) | APT-04.03 | API: keep UpdateAppointmentTime; Reschedule wraps it | Existing | Appointments | §5.2 | Appointment time update | Adjust timings as the day runs | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
155 | 251 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.5 | APT-05 | Reschedule appointment — move to a new slot with automatic patient notification (NEW — not a rename of UpdateAppointmentTime) | APT-05.01 | DB: AppointmentChangeLog (PatientAppId, Action, OldValue, NewValue, ByUserId, ByRole, At) + indexes | New | Appointments | §5.2 + §2.3 + §6 | Reschedule appointment | Move to a new slot with automatic patient notification / Move to another slot without calling the clinic | Doctor Web + Reception + later Patient | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
156 | 252 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.5 | APT-05 | Reschedule appointment — move to a new slot with automatic patient notification (NEW — not a rename of UpdateAppointmentTime) | APT-05.02 | API: POST /api/PatientAppointment/RescheduleAppointment — validate schedule, bookings, not in the past; 409 with alternatives; wrap UpdateAppointmentTime; GET ChangeLog/{id} | New | Appointments | §5.2 + §2.3 + §6 | Reschedule appointment | Move to a new slot with automatic patient notification / Move to another slot without calling the clinic | Doctor Web + Reception + later Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
157 | 254 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.5 | APT-05 | Reschedule appointment — move to a new slot with automatic patient notification (NEW — not a rename of UpdateAppointmentTime) | APT-05.04 | Notifications: SMS + WhatsApp + (later) push — old→new; must not block the transaction if notify fails | New Integration | Appointments | §5.2 + §2.3 + §6 | Reschedule appointment | Move to a new slot with automatic patient notification / Move to another slot without calling the clinic | Doctor Web + Reception + later Patient | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
158 | 256 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.6 | APT-06 | Cancel appointment — reason, free the slot, trigger refund where applicable (NEW CANCELLED status — do NOT reuse DeleteStatus) | APT-06.01 | DB: add CANCELLED to status set; CancelReasonCode, CancelReasonText, CancelledBy, CancelledAt; DeleteStatus remains administrative | New | Appointments | §5.2 + §2.3 + §6 | Cancel appointment | Cancel with reason, free the slot, trigger refund where applicable / Cancel with reason, refund handled per policy | Doctor Web + Reception + later Patient | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
159 | 257 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.6 | APT-06 | Cancel appointment — reason, free the slot, trigger refund where applicable (NEW CANCELLED status — do NOT reuse DeleteStatus) | APT-06.02 | API: POST /api/PatientAppointment/CancelAppointment — reason required (enum; text if Other); free slot; offer waitlist stub; if PAID enqueue refund policy | New | Appointments | §5.2 + §2.3 + §6 | Cancel appointment | Cancel with reason, free the slot, trigger refund where applicable / Cancel with reason, refund handled per policy | Doctor Web + Reception + later Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
160 | 259 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.6 | APT-06 | Cancel appointment — reason, free the slot, trigger refund where applicable (NEW CANCELLED status — do NOT reuse DeleteStatus) | APT-06.04 | Waitlist worker stub: on cancel, offer freed slot (full waitlist capture is Phase 9 GST waitlist) | New Integration | Appointments | §5.2 + §2.3 + §6 | Cancel appointment | Cancel with reason, free the slot, trigger refund where applicable / Cancel with reason, refund handled per policy | Doctor Web + Reception + later Patient | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
161 | 262 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.7 | APT-07 | Daily schedule setup — define working days, hours and break times (promote modal to first-class screen) | APT-07.02 | No new API unless validation (breaks, overlapping hours) is missing — add server-side validation | Existing Improvement | Scheduling | §5.2 | Daily schedule setup | Define working days, hours and break times | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
162 | 265 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.8 | APT-08 | Appointment slot grid — visual slot-by-slot view of the day (keep; public booking reuses this) | APT-08.02 | ACL doctor/reception | Existing Improvement | Scheduling | §5.2 | Appointment slot grid | Visual slot-by-slot view of the day | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
163 | 266 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.8 | APT-08 | Appointment slot grid — visual slot-by-slot view of the day (keep; public booking reuses this) | APT-08.03 | Document GetAppointmentSlots as the public-booking engine — do not fork a second slot calculator | Existing | Scheduling | §5.2 | Appointment slot grid | Visual slot-by-slot view of the day | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
164 | 267 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.9 | APT-09 | Consultation payment status on every appointment (schema now; values live in Phase 6) | APT-09.01 | DB: PatientAppointment.PaymentStatus, PaymentMethod, PayAtClinicAllowed; default UNPAID | New | Appointments | §5.2 + §9 | Consultation payment status | See paid, unpaid or pay-at-clinic on every appointment / Doctor, reception and patient all see the same payment status | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
165 | 268 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.9 | APT-09 | Consultation payment status on every appointment (schema now; values live in Phase 6) | APT-09.02 | API: include PaymentStatus on all appointment DTOs (doctor, reception, later public/patient) | New | Appointments | §5.2 + §9 | Consultation payment status | See paid, unpaid or pay-at-clinic on every appointment / Doctor, reception and patient all see the same payment status | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
166 | 272 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.1 | REC-01 | Reception login — secure staff access (keep) | REC-01.02 | Disabled staff cannot login (after DOC-09) | Existing Improvement | Reception | §6 | Reception login | Secure staff access | Reception Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
167 | 273 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.1 | REC-01 | Reception login — secure staff access (keep) | REC-01.03 | Same Login API as doctor | Existing | Reception | §6 | Reception login | Secure staff access | Reception Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
168 | 274 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.2 | REC-02 | Reception profile — manage own profile details (0% today) | REC-02.01 | Reuse Profile/Me with role=Reception DTO (no new table if UserMaster suffices) | New | Reception | §6 | Reception profile | Manage own profile details | Reception Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
169 | 275 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.2 | REC-02 | Reception profile — manage own profile details (0% today) | REC-02.02 | GET/PUT profile fields allowed for reception; ignore clinic fee/bank | New | Reception | §6 | Reception profile | Manage own profile details | Reception Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
170 | 282 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.4 | REC-04 | Create patient — register a walk-in patient quickly (keep) | REC-04.02 | ACL: own doctor only | Existing Improvement | Reception | §6 | Create patient | Register a walk-in patient quickly | Reception Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
171 | 283 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.4 | REC-04 | Create patient — register a walk-in patient quickly (keep) | REC-04.03 | Same create-patient API | Existing | Reception | §6 | Create patient | Register a walk-in patient quickly | Reception Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
172 | 285 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.5 | REC-05 | Patient search & list — find any patient instantly (keep) | REC-05.02 | Opening a row goes to case paper or appointment, not full repertory | Existing Improvement | Reception | §6 | Patient search & list | Find any patient instantly | Reception Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
173 | 286 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.5 | REC-05 | Patient search & list — find any patient instantly (keep) | REC-05.03 | API unchanged | Existing | Reception | §6 | Patient search & list | Find any patient instantly | Reception Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
174 | 287 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.6 | REC-06 | Create & manage appointments — full appointment management (keep; plus reschedule/cancel from Phase 4) | REC-06.01 | Authorise Reception for Reschedule and Cancel for its own doctor's appointments only | New | Reception | §6 | Create & manage appointments | Full appointment management | Reception Portal | API + SPA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
175 | 292 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.8 | REC-08 | Waiting queue management — manage the live queue and call the next patient | REC-08.01 | No new table required if status+order suffice; optional QueuePosition | Existing Improvement | Reception | §6 | Waiting queue management | Manage the live queue and call the next patient | Reception Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
176 | 293 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.8 | REC-08 | Waiting queue management — manage the live queue and call the next patient | REC-08.02 | Optional CallNext API that sets status and timestamp | Existing Improvement | Reception | §6 | Waiting queue management | Manage the live queue and call the next patient | Reception Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
177 | 297 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.9 | REC-09 | Appointment status update (reception) — update as patients arrive and are seen (keep) | REC-09.02 | ACL own doctor | Existing Improvement | Reception | §6 | Appointment status update | Update as patients arrive and are seen | Reception Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
178 | 298 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.9 | REC-09 | Appointment status update (reception) — update as patients arrive and are seen (keep) | REC-09.03 | Same status API as doctor | Existing | Reception | §6 | Appointment status update | Update as patients arrive and are seen | Reception Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
179 | 300 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.10 | REC-10 | Appointment time update (reception) — adjust timings through the day (keep) | REC-10.02 | ACL own doctor | Existing Improvement | Reception | §6 | Appointment time update | Adjust timings through the day | Reception Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
180 | 301 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.10 | REC-10 | Appointment time update (reception) — adjust timings through the day (keep) | REC-10.03 | Same API | Existing | Reception | §6 | Appointment time update | Adjust timings through the day | Reception Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
181 | 304 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.12 | REC-12 | Log case paper / chief complaint — record the reason for visit before the consultation | REC-12.01 | Reuse complaints table; add CreatedByRole=Reception | New | Reception | §6 | Log case paper / chief complaint | Record the reason for visit before the consultation | Reception Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
182 | 305 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.12 | REC-12 | Log case paper / chief complaint — record the reason for visit before the consultation | REC-12.02 | POST case-paper subset of SaveComplaints; GET on board | New | Reception | §6 | Log case paper / chief complaint | Record the reason for visit before the consultation | Reception Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
183 | 309 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.13 | REC-13 | Collect consultation payment — cash, UPI, card or payment link and issue a receipt (API in Phase 6; UI shell now) | REC-13.02 | Do not write PaymentStatus=PAID from the client — Account/webhook is source of truth (Phase 6) | New | Reception | §6 + §9 | Collect consultation payment | Take cash, UPI, card or payment link and issue a receipt | Reception Portal | Architecture | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
184 | 310 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.1 | PAY-01 | Consultation fee configuration — each doctor’s fee set and displayed to patients | PAY-01.01 | DB: ConsultFeeConfig (DoctorId, InClinicFee, TeleFee, InstantSurcharge, Currency, PayAtClinicEnabled, EffectiveFrom) | New | Payments | §9 | Consultation fee configuration | Each doctor’s fee set and displayed to patients | Doctor profile + Public + Admin | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
185 | 311 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.1 | PAY-01 | Consultation fee configuration — each doctor’s fee set and displayed to patients | PAY-01.02 | API: GET public fee; PUT doctor/admin; history of changes in audit | New | Payments | §9 | Consultation fee configuration | Each doctor’s fee set and displayed to patients | Doctor profile + Public + Admin | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
186 | 314 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.2 | PAY-02 | Automatic payment verification — bank/webhook is source of truth, not the patient’s screen | PAY-02.01 | DB: PaymentOrder, PaymentEvent (raw webhook), idempotency key on payment_id | New | Payments | §9 | Automatic payment verification | Payments confirmed by the bank, not by the patient’s screen — nothing is lost if the app or browser closes | Shared | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
187 | 315 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.2 | PAY-02 | Automatic payment verification — bank/webhook is source of truth, not the patient’s screen | PAY-02.02 | Port Order/GenerateOrderId pattern to .NET 8; move keys to configuration; do not commit secrets | New Integration | Payments | §9 | Automatic payment verification | Payments confirmed by the bank, not by the patient’s screen — nothing is lost if the app or browser closes | Shared | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
188 | 316 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.2 | PAY-02 | Automatic payment verification — bank/webhook is source of truth, not the patient’s screen | PAY-02.03 | Webhook handler payment.captured / payment.failed; signature verify; never trust client-only success | New Integration | Payments | §9 | Automatic payment verification | Payments confirmed by the bank, not by the patient’s screen — nothing is lost if the app or browser closes | Shared | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
189 | 318 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.3 | PAY-03 | Online consultation payment — patient pays by card, UPI, netbanking or wallet | PAY-03.01 | DB: ConsultPayment linked to PaymentOrder + PatientAppId — NOT PackageEntryDetail | New | Payments | §9 + §4 + §2.3 | Online consultation payment | Patient pays by card, UPI, netbanking or wallet / Pay the consultation fee at the time of booking / Pay the consultation fee inside the app | Public web + later Patient app | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
190 | 319 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.3 | PAY-03 | Online consultation payment — patient pays by card, UPI, netbanking or wallet | PAY-03.02 | API: CreateConsultOrder, Verify (optional), status by appointment; amount from ConsultFeeConfig | New | Payments | §9 + §4 + §2.3 | Online consultation payment | Patient pays by card, UPI, netbanking or wallet / Pay the consultation fee at the time of booking / Pay the consultation fee inside the app | Public web + later Patient app | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
191 | 321 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.3 | PAY-03 | Online consultation payment — patient pays by card, UPI, netbanking or wallet | PAY-03.04 | Razorpay Checkout methods: card, UPI, netbanking, wallet as enabled on the account | New Integration | Payments | §9 + §4 + §2.3 | Online consultation payment | Patient pays by card, UPI, netbanking or wallet / Pay the consultation fee at the time of booking / Pay the consultation fee inside the app | Public web + later Patient app | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
192 | 323 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.4 | PAY-04 | Reception payment collection — cash, UPI, card or payment link with printed receipt | PAY-04.01 | Reuse PaymentOrder + ConsultPayment with Method=CASH/UPI_OFFLINE/CARD_POS/PAY_LINK | New | Payments | §9 + §6 | Reception payment collection | Cash, UPI, card or payment link with printed receipt | Reception Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
193 | 324 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.4 | PAY-04 | Reception payment collection — cash, UPI, card or payment link with printed receipt | PAY-04.02 | API: CollectAtReception; generate pay-link; print receipt payload | New | Payments | §9 + §6 | Reception payment collection | Cash, UPI, card or payment link with printed receipt | Reception Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
194 | 326 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.4 | PAY-04 | Reception payment collection — cash, UPI, card or payment link with printed receipt | PAY-04.04 | Pay-link SMS/WhatsApp optional (Phase 12); must still ledger if notify fails | New Integration | Payments | §9 + §6 | Reception payment collection | Cash, UPI, card or payment link with printed receipt | Reception Portal | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
195 | 328 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.5 | PAY-05 | Pay-at-clinic option — book now, pay at the clinic where the doctor allows it | PAY-05.01 | Honor PayAtClinicEnabled on public create-booking and checkout | New | Payments | §9 | Pay-at-clinic option | Book now, pay at the clinic where the doctor allows it | Public + Doctor + Reception | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
196 | 331 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.6 | PAY-06 | Doctor subscription payment — buy and renew subscription packages (complete remaining ~30%) | PAY-06.01 | Reuse PAY-02 webhook for S1 orders; link PackageEntryDetail as S1 only | Existing Improvement | Payments | §9 | Doctor subscription payment | Buy and renew subscription packages | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | 2 | Not Started |  | Edit on module sheet
197 | 334 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.7 | PAY-07 | Medicine payment — pay online or cash on delivery (API contract now; HomeoMeds Phase 14 implements orders) | PAY-07.01 | Extend PaymentOrder with Stream=CONSULT¦SUBSCRIPTION¦MEDICINE so Phase 14 can attach without schema rewrite | New | Payments | §9 + §12 | Medicine payment | Pay online or choose cash on delivery / Both options supported, with status tracking | Shared | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
198 | 335 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.7 | PAY-07 | Medicine payment — pay online or cash on delivery (API contract now; HomeoMeds Phase 14 implements orders) | PAY-07.02 | API stub: CreateMedicineOrder payment + COD status enum — implemented fully in Phase 14 | New | Payments | §9 + §12 | Medicine payment | Pay online or choose cash on delivery / Both options supported, with status tracking | Shared | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
199 | 337 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.8 | PAY-08 | Payment status everywhere — doctor, reception and patient all see the same payment status | PAY-08.01 | Single source: PaymentOrder/ConsultPayment → Appointment.PaymentStatus updated only by webhook or CollectAtReception | New | Payments | §9 | Payment status everywhere | Doctor, reception and patient all see the same payment status | All | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
200 | 340 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.9 | PAY-09 | Refunds — processed and tracked against the original payment | PAY-09.01 | DB: Refund (PaymentOrderId, Amount, Reason, Status, GatewayRefundId, ByUserId, At) | New | Payments | §9 + §8 + §2.8 | Refunds | Processed and tracked against the original payment / Issue and track refunds | Account + Patient | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
201 | 341 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.9 | PAY-09 | Refunds — processed and tracked against the original payment | PAY-09.02 | API: create refund (Account); webhook refund.processed; cancel-appointment policy engine (full/partial/none) | New | Payments | §9 + §8 + §2.8 | Refunds | Processed and tracked against the original payment / Issue and track refunds | Account + Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
202 | 343 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.9 | PAY-09 | Refunds — processed and tracked against the original payment | PAY-09.04 | Razorpay refund API + webhook | New Integration | Payments | §9 + §8 + §2.8 | Refunds | Processed and tracked against the original payment / Issue and track refunds | Account + Patient | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
203 | 345 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.10 | PAY-10 | Payment receipts & invoices — issued for every transaction | PAY-10.01 | DB: Invoice (Number, Series, Stream, PaymentOrderId, GstBreakup, PdfPath) | New | Payments | §9 + §8 | Payment receipts & invoices | Issued for every transaction / Invoice numbering and tax reporting | All | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
204 | 346 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.10 | PAY-10 | Payment receipts & invoices — issued for every transaction | PAY-10.02 | API: get invoice by payment; generate PDF via SecureDocument | New | Payments | §9 + §8 | Payment receipts & invoices | Issued for every transaction / Invoice numbering and tax reporting | All | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
205 | 349 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.11 | PAY-11 | Complete payment audit trail — every transaction traceable end to end by Homeocentrum | PAY-11.01 | Persist raw webhook JSON; correlation id on Appointment and Ledger | New | Payments | §9 + §17 | Complete audit trail | Every transaction traceable end to end by Homeocentrum | Account | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
206 | 350 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.11 | PAY-11 | Complete payment audit trail — every transaction traceable end to end by Homeocentrum | PAY-11.02 | Account query API: trail by appointment / payment / doctor (Phase 7 UI) | New | Payments | §9 + §17 | Complete audit trail | Every transaction traceable end to end by Homeocentrum | Account | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
207 | 352 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.1 | FIN-01 | Unified transaction ledger — every rupee that moves through the platform, in one record | FIN-01.01 | DB: LedgerEntry (Stream, Direction, Amount, Gst, Commission, EntityType, EntityId, PaymentOrderId, At) immutable | New | Account | §8 | Unified transaction ledger | Every rupee that moves through the platform, in one record | Account Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
208 | 353 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.1 | FIN-01 | Unified transaction ledger — every rupee that moves through the platform, in one record | FIN-01.02 | API: GET /account/ledger filters; export; write-only from payment/settlement services | New | Account | §8 | Unified transaction ledger | Every rupee that moves through the platform, in one record | Account Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
209 | 356 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.2 | FIN-02 | Consultation payment reconciliation — online payments and reception collections matched and verified | FIN-02.01 | Reuse ConsultPayment + Appointment; reconciliation query | New | Account | §8 + §7.2 + §16 | Consultation payment reconciliation | Online payments and reception collections matched and verified / Match every booking against every payment | Account + Admin | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
210 | 357 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.2 | FIN-02 | Consultation payment reconciliation — online payments and reception collections matched and verified | FIN-02.02 | GET Admin/Account reconciliation + aggregates | New | Account | §8 + §7.2 + §16 | Consultation payment reconciliation | Online payments and reception collections matched and verified / Match every booking against every payment | Account + Admin | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
211 | 360 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.3 | FIN-03 | Medicine ledger — medicine money tracked separately from consultation money | FIN-03.01 | LedgerEntry stream MEDICINE with SplitSeller/SplitPlatform/SplitDelivery | New | Account | §8 + §12 | Medicine ledger | Medicine money tracked separately from consultation money / Seller, platform and delivery shares recorded separately from consultation money | Account Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
212 | 361 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.3 | FIN-03 | Medicine ledger — medicine money tracked separately from consultation money | FIN-03.02 | GET /account/medicine-ledger | New | Account | §8 + §12 | Medicine ledger | Medicine money tracked separately from consultation money / Seller, platform and delivery shares recorded separately from consultation money | Account Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
213 | 364 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.4 | FIN-04 | Settlement runs — scheduled settlement of amounts due to doctors and pharmacies | FIN-04.01 | DB: SettlementRun, SettlementLine | New | Account | §8 + §16 | Settlement runs | Scheduled settlement of amounts due to doctors and pharmacies | Account Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
214 | 365 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.4 | FIN-04 | Settlement runs — scheduled settlement of amounts due to doctors and pharmacies | FIN-04.02 | API: create run (dry-run + commit); list; detail | New | Account | §8 + §16 | Settlement runs | Scheduled settlement of amounts due to doctors and pharmacies | Account Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
215 | 368 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.5 | FIN-05 | Payout approval — payouts released only after OTP-verified approval | FIN-05.01 | DB: Payout (PayeeType Doctor¦Pharmacy, Amount, Status, SettlementRunId) | New | Account | §8 + §17 | Payout approval | Payouts released only after OTP-verified approval | Account Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
216 | 369 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.5 | FIN-05 | Payout approval — payouts released only after OTP-verified approval | FIN-05.02 | API: ApprovePayout with OTP; reject | New | Account | §8 + §17 | Payout approval | Payouts released only after OTP-verified approval | Account Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
217 | 371 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.5 | FIN-05 | Payout approval — payouts released only after OTP-verified approval | FIN-05.04 | Bank file / Razorpay payout adapter per PRE-01 | New Integration | Account | §8 + §17 | Payout approval | Payouts released only after OTP-verified approval | Account Portal | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
218 | 374 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.6 | FIN-06 | Refund processing — Account issues and tracks refunds (uses PAY-09) | FIN-06.02 | Ledger reverse entries on successful refund | New | Account | §8 | Refund processing | Issue and track refunds | Account Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
219 | 376 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.7 | FIN-07 | Payment exception handling — investigate and resolve every failed or disputed payment | FIN-07.01 | DB: PaymentException state machine | New | Account | §8 + §7.2 | Payment exception handling | Investigate and resolve every failed or disputed payment / Every failed or mismatched payment surfaced for action | Account + Admin | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
220 | 377 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.7 | FIN-07 | Payment exception handling — investigate and resolve every failed or disputed payment | FIN-07.02 | API: list/detail/retry/resolve; created by webhook mismatches | New | Account | §8 + §7.2 | Payment exception handling | Investigate and resolve every failed or disputed payment / Every failed or mismatched payment surfaced for action | Account + Admin | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
221 | 380 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.8 | FIN-08 | GST & invoice reports — invoice numbering and tax reporting | FIN-08.01 | Reuse Invoice; tax config table (GstRate, treatment flags) | New | Account | §8 + §16 | GST & invoice reports | Invoice numbering and tax reporting | Account Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
222 | 381 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.8 | FIN-08 | GST & invoice reports — invoice numbering and tax reporting | FIN-08.02 | GET tax report + CSV | New | Account | §8 + §16 | GST & invoice reports | Invoice numbering and tax reporting | Account Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
223 | 384 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.9 | FIN-09 | Payee records — bank and KYC details for doctors and pharmacies | FIN-09.01 | DB: Payee (DoctorId/PharmacyId, Bank, PAN, KYC status) | New | Account | §8 | Payee records | Bank and KYC details for doctors and pharmacies | Account Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
224 | 385 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.9 | FIN-09 | Payee records — bank and KYC details for doctors and pharmacies | FIN-09.02 | API: list/update; OTP on bank change | New | Account | §8 | Payee records | Bank and KYC details for doctors and pharmacies | Account Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
225 | 388 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.10 | FIN-10 | Clinic collection view — cash and UPI collected at reception, per clinic and per day | FIN-10.01 | Query ConsultPayment Method in CASH/UPI_OFFLINE grouped by DoctorId/date | New | Account | §8 | Clinic collection view | Cash and UPI collected at reception, per clinic and per day | Account Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
226 | 389 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.10 | FIN-10 | Clinic collection view — cash and UPI collected at reception, per clinic and per day | FIN-10.02 | GET clinic-collections | New | Account | §8 | Clinic collection view | Cash and UPI collected at reception, per clinic and per day | Account Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
227 | 392 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.11 | FIN-11 | Separation of duties — Account controls money; Admin controls platform and clinical data | FIN-11.01 | Seed Account role menus: ledger, recon, medicine ledger, exceptions, settlements, payouts, refunds, tax, payees, clinic collections | New | Account | §8 | Separation of duties | The Account department controls money. Admin controls the platform and clinical data. Neither can perform the other’s role, which protects both. | Admin + Account | Configuration | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
228 | 394 | M09 | Trust & verification | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.1 | TRU-01 | Doctor credentialing — doctors upload qualification and registration documents for review | TRU-01.01 | DB: DoctorVerification (Pending/Approved/Rejected/NeedsInfo), DoctorCredentialDocument | New | Trust | §13 + §7.2 | Doctor credentialing | Doctors upload qualification and registration documents for review | Doctor Web + Admin | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
229 | 395 | M09 | Trust & verification | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.1 | TRU-01 | Doctor credentialing — doctors upload qualification and registration documents for review | TRU-01.02 | API: upload documents; MyStatus; RegisterDoctor modified to VerificationStatus=Pending (not auto-practice) | New | Trust | §13 + §7.2 | Doctor credentialing | Doctors upload qualification and registration documents for review | Doctor Web + Admin | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
230 | 398 | M09 | Trust & verification | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.2 | TRU-02 | Verification review — Admin approves, rejects or requests further information | TRU-02.01 | Reuse DoctorVerification | New | Trust | §13 + §7.2 | Verification review | Admin approves, rejects or requests more information before they can practise on the platform | Admin Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
231 | 399 | M09 | Trust & verification | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.2 | TRU-02 | Verification review — Admin approves, rejects or requests further information | TRU-02.02 | API: Queue, {id}, Approve, Reject, RequestInfo | New | Trust | §13 + §7.2 | Verification review | Admin approves, rejects or requests more information before they can practise on the platform | Admin Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
232 | 401 | M09 | Trust & verification | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.2 | TRU-02 | Verification review — Admin approves, rejects or requests further information | TRU-02.04 | Email notify (Phase 12 SMTP already used for activation) | New Integration | Trust | §13 + §7.2 | Verification review | Admin approves, rejects or requests more information before they can practise on the platform | Admin Portal | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
233 | 403 | M09 | Trust & verification | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.3 | TRU-03 | Verified badge — patients see which doctors have been verified | TRU-03.01 | Public doctor DTO includes isVerified | New | Trust | §13 + §2.2 | Verified badge / Credentials & verification | Patients see which doctors have been verified / Verified badge showing the doctor’s credentials are checked | Public + Patient app | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
234 | 406 | M09 | Trust & verification | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.4 | TRU-04 | Practice gate — only verified doctors appear to patients and take paid consultations | TRU-04.01 | Public doctor list filter VerificationStatus=Approved | New | Trust | §13 | Practice gate | Only verified doctors appear to patients and take paid consultations | Public + Payments | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
235 | 407 | M09 | Trust & verification | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.4 | TRU-04 | Practice gate — only verified doctors appear to patients and take paid consultations | TRU-04.02 | CreateConsultOrder rejects unverified doctor for patient-originated bookings | New | Trust | §13 | Practice gate | Only verified doctors appear to patients and take paid consultations | Public + Payments | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
236 | 409 | M09 | Trust & verification | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.5 | TRU-05 | Patient reviews — patients rate and review consultations | TRU-05.01 | DB: Review (PatientAppId, Rating, Text, Status, At) | New | Trust | §13 + §2.8 | Patient reviews / Write a review | Patients rate and review consultations / Rate and review the consultation | Patient + Public | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
237 | 410 | M09 | Trust & verification | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.5 | TRU-05 | Patient reviews — patients rate and review consultations | TRU-05.02 | API: create (patient), list by doctor (public approved), doctor list own | New | Trust | §13 + §2.8 | Patient reviews / Write a review | Patients rate and review consultations / Rate and review the consultation | Patient + Public | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
238 | 413 | M09 | Trust & verification | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.6 | TRU-06 | Review appeal — doctors can appeal a review; patients manage reviews and raise an appeal | TRU-06.01 | DB: ReviewAppeal | New | Trust | §13 + §2.8 | Review appeal / My reviews & appeal | Doctors can appeal a review / Manage reviews and raise an appeal | Doctor + Patient + Admin | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
239 | 414 | M09 | Trust & verification | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.6 | TRU-06 | Review appeal — doctors can appeal a review; patients manage reviews and raise an appeal | TRU-06.02 | API: doctor appeal; patient list/mine; admin resolve | New | Trust | §13 + §2.8 | Review appeal / My reviews & appeal | Doctors can appeal a review / Manage reviews and raise an appeal | Doctor + Patient + Admin | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
240 | 417 | M09 | Trust & verification | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.7 | TRU-07 | Ranking transparency — patients are shown why doctors are ranked as they are | TRU-07.01 | Ranking config (weights) — not a black box hardcoded sort | New | Trust | §13 + §2.2 | Ranking transparency / Ranking explanation | Patients are shown why doctors are ranked as they are / Transparent explanation of why doctors appear in a given order | Public + Patient app | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
241 | 418 | M09 | Trust & verification | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.7 | TRU-07 | Ranking transparency — patients are shown why doctors are ranked as they are | TRU-07.02 | GET doctors + GET ranking-explain/{doctorId} | New | Trust | §13 + §2.2 | Ranking transparency / Ranking explanation | Patients are shown why doctors are ranked as they are / Transparent explanation of why doctors appear in a given order | Public + Patient app | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
242 | 421 | M10 | Patient website | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.1 | WEB-01 | Product home page — complete public website presenting the service | WEB-01.01 | No schema | Existing Improvement | Patient Website | §4 | Product home page | Complete public website presenting the service | Patient Website | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
243 | 422 | M10 | Patient website | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.1 | WEB-01 | Product home page — complete public website presenting the service | WEB-01.02 | Reuse public doctor/fee APIs when live | Existing Improvement | Patient Website | §4 | Product home page | Complete public website presenting the service | Patient Website | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
244 | 428 | M10 | Patient website | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.3 | WEB-03 | Doctor discovery — browse and search verified doctors | WEB-03.01 | Public doctor search indexes (from Doctor + verification + fee + schedule) | New | Patient Website | §4 + §2.2 | Doctor discovery | Browse and search verified doctors | Patient Website | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
245 | 429 | M10 | Patient website | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.3 | WEB-03 | Doctor discovery — browse and search verified doctors | WEB-03.02 | GET /api/Public/Doctors + filters + profile | New | Patient Website | §4 + §2.2 | Doctor discovery | Browse and search verified doctors | Patient Website | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
246 | 432 | M10 | Patient website | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.4 | WEB-04 | Self-service booking — book an appointment online without calling the clinic | WEB-04.01 | Reuse Patient + Appointment; BookingToken; PatientAuth OTP | New | Patient Website | §4 + §2.3 | Self-service booking | Book an appointment online without calling the clinic | Patient Website | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
247 | 433 | M10 | Patient website | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.4 | WEB-04 | Self-service booking — book an appointment online without calling the clinic | WEB-04.02 | Public: Doctors/{id}/Slots, Create, {bookingToken}; POST PatientAuth RequestOtp/VerifyOtp | New | Patient Website | §4 + §2.3 | Self-service booking | Book an appointment online without calling the clinic | Patient Website | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
248 | 438 | M10 | Patient website | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.6 | WEB-06 | Contact & enquiry form — enquiries reach the admin team and are tracked | WEB-06.01 | Reuse EnquiryDetail; add Status/AssignedTo if missing | Existing Improvement | Patient Website | §4 + §15 | Contact & enquiry form | Enquiries reach the admin team and are tracked | Patient Website + Admin | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
249 | 439 | M10 | Patient website | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.6 | WEB-06 | Contact & enquiry form — enquiries reach the admin team and are tracked | WEB-06.02 | Existing enquiry POST; admin list API if missing | Existing Improvement | Patient Website | §4 + §15 | Contact & enquiry form | Enquiries reach the admin team and are tracked | Patient Website + Admin | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
250 | 446 | M10 | Patient website | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.9 | WEB-09 | Doctor self-registration — doctors apply to join the platform online | WEB-09.01 | Documents via TRU-01 tables | Existing Improvement | Patient Website | §4 | Doctor self-registration | Doctors apply to join the platform online | Public | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
251 | 447 | M10 | Patient website | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.9 | WEB-09 | Doctor self-registration — doctors apply to join the platform online | WEB-09.02 | RegisterDoctor sets Pending; does not auto-activate practice for directory | Existing Improvement | Patient Website | §4 | Doctor self-registration | Doctors apply to join the platform online | Public | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
252 | 450 | M10 | Patient website | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.10 | WEB-10 | Email activation — secure account activation by email link | WEB-10.01 | Activation token TTL if missing | Existing Improvement | Auth | §4 | Email activation | Secure account activation by email link | Public | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
253 | 451 | M10 | Patient website | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.10 | WEB-10 | Email activation — secure account activation by email link | WEB-10.02 | Resend activation; do not treat activation as TRU-04 gate | Existing Improvement | Auth | §4 | Email activation | Secure account activation by email link | Public | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
254 | 454 | M05 | Appointments & scheduling | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.11 | WEB-11 | Waitlist offer — get offered a slot when one is freed by a cancellation (patient website + later app) | WEB-11.01 | DB: BookingWaitlist | New | Booking | §2.3 | Waitlist offer | Get offered a slot when one is freed by a cancellation | Patient Website + App | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
255 | 455 | M05 | Appointments & scheduling | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.11 | WEB-11 | Waitlist offer — get offered a slot when one is freed by a cancellation (patient website + later app) | WEB-11.02 | API: join waitlist; worker on CancelAppointment | New | Booking | §2.3 | Waitlist offer | Get offered a slot when one is freed by a cancellation | Patient Website + App | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
256 | 457 | M05 | Appointments & scheduling | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.11 | WEB-11 | Waitlist offer — get offered a slot when one is freed by a cancellation (patient website + later app) | WEB-11.04 | Notify SMS/push when Phase 12 exists | New Integration | Booking | §2.3 | Waitlist offer | Get offered a slot when one is freed by a cancellation | Patient Website + App | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
257 | 461 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.1 | ERX-01 | Potency module — every remedy carries a defined potency from a managed list, no free text | ERX-01.01 | DB: PotencyMaster; PrescriptionRemedyDetail.PotencyId | New | eRx | §11 | Potency module | Every remedy carries a defined potency, selected from a managed list — no free text | Doctor Web + Admin | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
258 | 462 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.1 | ERX-01 | Potency module — every remedy carries a defined potency from a managed list, no free text | ERX-01.02 | API: potency DDL; extend SavePrescriptionDetail | New | eRx | §11 | Potency module | Every remedy carries a defined potency, selected from a managed list — no free text | Doctor Web + Admin | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
259 | 465 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.2 | ERX-02 | Dosage details — frequency, duration and instructions recorded clearly | ERX-02.01 | DB: Frequency, Duration, Instructions on remedy line | New | eRx | §11 | Dosage details | Frequency, duration and instructions recorded clearly | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
260 | 466 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.2 | ERX-02 | Dosage details — frequency, duration and instructions recorded clearly | ERX-02.02 | Extend save/get Rx APIs | New | eRx | §11 | Dosage details | Frequency, duration and instructions recorded clearly | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
261 | 469 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.3 | ERX-03 | Visit notes kept separate from the prescription — private clinical notes never appear on the prescription given to the patient or pharmacy | ERX-03.01 | Extend AppointmentHistoryNote with NoteType, IsErxExcluded | New | eRx | §11 + §5.3 | Visit notes kept separate from the prescription | The doctor’s private clinical notes never appear on the prescription given to the patient or pharmacy | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
262 | 470 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.3 | ERX-03 | Visit notes kept separate from the prescription — private clinical notes never appear on the prescription given to the patient or pharmacy | ERX-03.02 | GET /api/Erx/ByAppointment/{id} returns snapshot without notes | New | eRx | §11 + §5.3 | Visit notes kept separate from the prescription | The doctor’s private clinical notes never appear on the prescription given to the patient or pharmacy | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
263 | 473 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.4 | ERX-04 | Signed digital prescription — issued and locked once signed, so it cannot be altered afterwards | ERX-04.01 | DB: ErxSnapshot, ErxSnapshotItem (codes+names stored; patient API returns codes until pharmacy accept) | New | eRx | §11 + §2.5 + §5.3 | Signed digital prescription | Issued and locked once signed, so it cannot be altered afterwards / Official prescription issued by the doctor | Doctor Web | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
264 | 474 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.4 | ERX-04 | Signed digital prescription — issued and locked once signed, so it cannot be altered afterwards | ERX-04.02 | API: SignErx; GetErx; reject mutate of signed snapshot | New | eRx | §11 + §2.5 + §5.3 | Signed digital prescription | Issued and locked once signed, so it cannot be altered afterwards / Official prescription issued by the doctor | Doctor Web | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
265 | 477 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.5 | ERX-05 | Prescription history — every prescription stored against the patient and visit | ERX-05.01 | GET history by patient; by appointment | New | eRx | §11 | Prescription history | Every prescription stored against the patient and visit | Doctor + Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
266 | 480 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.6 | ERX-06 | Patient view of prescription in app — patient sees the prescription immediately (codes until pharmacy accept) | ERX-06.01 | Patient-authorised GET Erx; apply code protection ERX-08 | New | eRx | §11 + §2.5 | Patient view in app | Patient sees the prescription immediately in the app | Patient App + Website | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
267 | 483 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.7 | ERX-07 | Print & PDF — printable and downloadable prescription | ERX-07.01 | PDF renderer from ErxSnapshot; store via SEC-09 | New | eRx | §11 | Print & PDF | Printable and downloadable prescription | Doctor + Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
268 | 486 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.8 | ERX-08 | Remedy code protection — patient sees remedy codes rather than names until a licensed pharmacy accepts the order | ERX-08.01 | Assign stable remedy codes on snapshot items | New | eRx | §11 | Remedy code protection | The patient sees remedy codes rather than remedy names until a licensed pharmacy accepts the order | Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
269 | 488 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.9 | ERX-09 | Reveal on pharmacy acceptance — names and price revealed; payment QR or link generated (implemented with HomeoMeds; contract now) | ERX-09.01 | API contract: AcceptOrder(OTP) → reveal names; Quote → PayQR | New | eRx | §11 + §12 | Reveal on pharmacy acceptance | Once a pharmacy accepts and verifies by OTP, the remedy names and price are revealed and a payment QR or link is generated | Patient + Pharmacy | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
270 | 489 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.9 | ERX-09 | Reveal on pharmacy acceptance — names and price revealed; payment QR or link generated (implemented with HomeoMeds; contract now) | ERX-09.02 | Implement fully with MED-* in Phase 14 — do not reveal names from doctor sign alone | New | eRx | §11 + §12 | Reveal on pharmacy acceptance | Once a pharmacy accepts and verifies by OTP, the remedy names and price are revealed and a payment QR or link is generated | Patient + Pharmacy | Architecture | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
271 | 490 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.10 | ERX-10 | Repeat prescription / refill — patient requests; doctor approves or rejects from the mobile app (inbox on web too) | ERX-10.01 | DB: RefillRequest | New | eRx | §11 + §3 + §2.7 | Repeat prescription / refill | Patient requests a refill; doctor approves or rejects from the mobile app | Patient + Doctor mobile + Doctor web | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
272 | 491 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.10 | ERX-10 | Repeat prescription / refill — patient requests; doctor approves or rejects from the mobile app (inbox on web too) | ERX-10.02 | API: patient request; doctor inbox; approve/reject | New | eRx | §11 + §3 + §2.7 | Repeat prescription / refill | Patient requests a refill; doctor approves or rejects from the mobile app | Patient + Doctor mobile + Doctor web | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
273 | 494 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.11 | ERX-11 | Lab orders alongside the prescription (keep existing labs on eRx snapshot) | ERX-11.01 | Copy lab orders into ErxSnapshot on sign | Existing Improvement | eRx | §11 | Lab orders | Tests ordered alongside the prescription | Doctor Web | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
274 | 496 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.1 | TEL-01 | Doctor availability — online or offline status and working hours | TEL-01.01 | DB: TeleAvailability (Online/Offline, LastHeartbeat) | New | Telemedicine | §10 + §3 | Doctor availability | Doctor sets online or offline status and working hours | Doctor Web + Doctor App | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
275 | 497 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.1 | TEL-01 | Doctor availability — online or offline status and working hours | TEL-01.02 | API: SET/GET availability; public GET by doctorId | New | Telemedicine | §10 + §3 | Doctor availability | Doctor sets online or offline status and working hours | Doctor Web + Doctor App | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
276 | 500 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.2 | TEL-02 | Telemedicine waiting queue — who is waiting, how long, whether they have paid | TEL-02.01 | Queue query on E-CONSULT + PaymentStatus + join time | New | Telemedicine | §10 + §3 | Telemedicine waiting queue | Doctor sees who is waiting, for how long, and whether they have paid | Doctor Web + App | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
277 | 501 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.2 | TEL-02 | Telemedicine waiting queue — who is waiting, how long, whether they have paid | TEL-02.02 | GET Tele/Queue; POST start session | New | Telemedicine | §10 + §3 | Telemedicine waiting queue | Doctor sees who is waiting, for how long, and whether they have paid | Doctor Web + App | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
278 | 503 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.2 | TEL-02 | Telemedicine waiting queue — who is waiting, how long, whether they have paid | TEL-02.04 | SignalR/poll | New Integration | Telemedicine | §10 + §3 | Telemedicine waiting queue | Doctor sees who is waiting, for how long, and whether they have paid | Doctor Web + App | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
279 | 505 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.3 | TEL-03 | Video consultation in browser — doctor consults directly from the web portal | TEL-03.01 | DB: TeleSession (PatientAppId, RoomId, Status) | New | Telemedicine | §10 | Video consultation in browser | Doctor consults directly from the web portal | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
280 | 506 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.3 | TEL-03 | Video consultation in browser — doctor consults directly from the web portal | TEL-03.02 | API: create/end session; vendor tokens | New | Telemedicine | §10 | Video consultation in browser | Doctor consults directly from the web portal | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
281 | 508 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.3 | TEL-03 | Video consultation in browser — doctor consults directly from the web portal | TEL-03.04 | Video SDK (Agora/Twilio/Daily) | New Integration | Telemedicine | §10 | Video consultation in browser | Doctor consults directly from the web portal | Doctor Web Portal | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
282 | 510 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.4 | TEL-04 | Video consultation on mobile — doctor and patient both consult from the app (apps in 16–17; same session tokens) | TEL-04.01 | Token API must be client-agnostic (web and mobile) | New | Telemedicine | §10 + §2.4 + §3 | Video consultation on mobile | Doctor and patient both consult from the app / Face-to-face consultation from home / Start the video or audio consultation from the phone | Patient App + Doctor App | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
283 | 514 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.6 | TEL-06 | Waiting room — patient waits with live status until the doctor joins | TEL-06.01 | Session status events | New | Telemedicine | §10 + §2.4 | Waiting room | Patient waits with live status / Wait with live status until the doctor joins | Patient | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
284 | 515 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.6 | TEL-06 | Waiting room — patient waits with live status until the doctor joins | TEL-06.02 | GET session status for patient token | New | Telemedicine | §10 + §2.4 | Waiting room | Patient waits with live status / Wait with live status until the doctor joins | Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
285 | 518 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.7 | TEL-07 | Recording consent — consent captured before the consultation; no recording without it | TEL-07.01 | Write ConsentRecord TeleRecording; TeleConsentLog events | New | Telemedicine | §10 + §2.4 + §17 | Recording consent | Consent captured before the consultation; no recording without it / Explicit consent requested before any recording | Patient + Doctor | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
286 | 519 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.7 | TEL-07 | Recording consent — consent captured before the consultation; no recording without it | TEL-07.02 | API: capture consent; session.recordAllowed | New | Telemedicine | §10 + §2.4 + §17 | Recording consent | Consent captured before the consultation; no recording without it / Explicit consent requested before any recording | Patient + Doctor | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
287 | 522 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.8 | TEL-08 | Rejoin after dropped call — either side can rejoin the same consultation | TEL-08.01 | API: Rejoin issues token if Status=Active | New | Telemedicine | §10 + §2.4 | Rejoin after dropped call | Either side can rejoin the same consultation / Rejoin the same consultation if the connection drops | Doctor + Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
288 | 525 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.9 | TEL-09 | Join failure handling — clear fallback if the call cannot connect, with options to retry | TEL-09.01 | Standardise join error codes; log TeleSessionEvent | New | Telemedicine | §10 + §2.4 | Join failure handling / Fallback & join failure handling | Clear fallback if the call cannot connect / Clear guidance if the call fails, with options to retry | Doctor + Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
289 | 528 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.10 | TEL-10 | Case-linked chat — chat attached to the consultation record, not a loose message thread | TEL-10.01 | DB: TeleChatMessage (SessionId, PatientAppId, Body, At) | New | Telemedicine | §10 + §2.4 | Case-linked chat | Chat attached to the consultation record / Chat tied to the consultation, not a loose message thread | Doctor + Patient | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
290 | 529 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.10 | TEL-10 | Case-linked chat — chat attached to the consultation record, not a loose message thread | TEL-10.02 | API: post/list; doctor and patient only | New | Telemedicine | §10 + §2.4 | Case-linked chat | Chat attached to the consultation record / Chat tied to the consultation, not a loose message thread | Doctor + Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
291 | 532 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.11 | TEL-11 | Consultation summary — issued to the patient at the end of the call | TEL-11.01 | DB: ConsultationSummary (PatientAppId, Text, At) | New | Telemedicine | §10 + §2.4 | Consultation summary | Issued to the patient at the end of the call / Written summary available immediately after the call | Patient + Doctor | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
292 | 533 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.11 | TEL-11 | Consultation summary — issued to the patient at the end of the call | TEL-11.02 | API: doctor PUT; patient GET | New | Telemedicine | §10 + §2.4 | Consultation summary | Issued to the patient at the end of the call / Written summary available immediately after the call | Patient + Doctor | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
293 | 536 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.12 | TEL-12 | Instant consultation — patient requests an immediate consultation with an available doctor | TEL-12.01 | DB: InstantConsultRequest, DoctorOffer | New | Telemedicine | §10 + §2.3 | Instant consultation / Instant consult request / Queue & doctor offer | Patient can request an immediate consultation with an available doctor / See position in queue and accept an offered doctor | Patient + Doctor | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
294 | 537 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.12 | TEL-12 | Instant consultation — patient requests an immediate consultation with an available doctor | TEL-12.02 | API: request, match, offer, accept, queue position | New | Telemedicine | §10 + §2.3 | Instant consultation / Instant consult request / Queue & doctor offer | Patient can request an immediate consultation with an available doctor / See position in queue and accept an offered doctor | Patient + Doctor | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
295 | 540 | M13 | Communications | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.1 | COM-01 | SMS — appointment confirmation, registration confirmation, doctor-unavailable, OTP, reschedule and cancellation | COM-01.01 | DB: SmsTemplate, SmsMessageLog; Patient.SmsOptOut | New | Notifications | §14 | SMS | Appointment confirmation, registration confirmation, doctor-unavailable notice, OTP, reschedule and cancellation alerts | Shared | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
296 | 541 | M13 | Communications | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.1 | COM-01 | SMS — appointment confirmation, registration confirmation, doctor-unavailable, OTP, reschedule and cancellation | COM-01.02 | API: Templates CRUD; Send; History; event worker | New | Notifications | §14 | SMS | Appointment confirmation, registration confirmation, doctor-unavailable notice, OTP, reschedule and cancellation alerts | Shared | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
297 | 543 | M13 | Communications | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.1 | COM-01 | SMS — appointment confirmation, registration confirmation, doctor-unavailable, OTP, reschedule and cancellation | COM-01.04 | MSG91/Twilio/etc. from PRE-03 | New Integration | Notifications | §14 | SMS | Appointment confirmation, registration confirmation, doctor-unavailable notice, OTP, reschedule and cancellation alerts | Shared | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
298 | 545 | M13 | Communications | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.2 | COM-02 | WhatsApp — templates, offers, health tips and bulk messaging with delivery reports and opt-out (complete remaining ~50%) | COM-02.01 | Extend WhatsApp log if delivery receipts not stored | Existing Improvement | Notifications | §14 | WhatsApp | Templates, offers, health tips and bulk messaging to patients, with delivery reports and opt-out | Doctor Web | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
299 | 546 | M13 | Communications | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.2 | COM-02 | WhatsApp — templates, offers, health tips and bulk messaging with delivery reports and opt-out (complete remaining ~50%) | COM-02.02 | Finish bulk worker + receipt webhook | Existing Improvement | Notifications | §14 | WhatsApp | Templates, offers, health tips and bulk messaging to patients, with delivery reports and opt-out | Doctor Web | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
300 | 549 | M13 | Communications | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.3 | COM-03 | Push notifications — booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests | COM-03.01 | DB: DeviceToken, AppNotification | New | Notifications | §14 + §2.9 + §3 | Push notifications | Booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests / Patient waiting, new booking, reschedule, cancellation, refill request, payment received | Patient App + Doctor App | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
301 | 550 | M13 | Communications | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.3 | COM-03 | Push notifications — booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests | COM-03.02 | API: Devices/Register; Notifications/Send; list | New | Notifications | §14 + §2.9 + §3 | Push notifications | Booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests / Patient waiting, new booking, reschedule, cancellation, refill request, payment received | Patient App + Doctor App | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
302 | 552 | M13 | Communications | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.3 | COM-03 | Push notifications — booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests | COM-03.04 | FCM + APNs | New Integration | Notifications | §14 + §2.9 + §3 | Push notifications | Booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests / Patient waiting, new booking, reschedule, cancellation, refill request, payment received | Patient App + Doctor App | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
303 | 554 | M13 | Communications | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.4 | COM-04 | Email — registration, activation, password reset, invoices and receipts | COM-04.01 | EmailMessageLog if missing | Existing Improvement | Notifications | §14 | Email | Registration, activation, password reset, invoices and receipts | Shared | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
304 | 555 | M13 | Communications | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.4 | COM-04 | Email — registration, activation, password reset, invoices and receipts | COM-04.02 | Send invoice/receipt email on PAID; keep activation/reset | Existing Improvement | Notifications | §14 | Email | Registration, activation, password reset, invoices and receipts | Shared | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
305 | 558 | M13 | Communications | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.5 | COM-05 | In-app notification centre — all alerts collected in one place for patients and doctors | COM-05.01 | Reuse AppNotification | New | Notifications | §14 + §2.8 | In-app notification centre / Notifications centre | All alerts collected in one place for patients and doctors / All alerts in one place | Patient App + Doctor Web/App | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
306 | 559 | M13 | Communications | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.5 | COM-05 | In-app notification centre — all alerts collected in one place for patients and doctors | COM-05.02 | GET/PATCH notifications | New | Notifications | §14 + §2.8 | In-app notification centre / Notifications centre | All alerts collected in one place for patients and doctors / All alerts in one place | Patient App + Doctor Web/App | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
307 | 562 | M14 | Support & help desk | Web | 13 | Phase 13 — Support & help desk (PDF §15) | 13.1 | SUP-01 | Patient support tickets — patients raise issues from the app and track them | SUP-01.01 | DB: SupportTicket, SupportTicketMessage, SupportTicketAttachment | New | Support | §15 + §2.9 | Patient support tickets / Help centre & support tickets | Patients raise issues from the app and track them to resolution | Patient App + Admin | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
308 | 563 | M14 | Support & help desk | Web | 13 | Phase 13 — Support & help desk (PDF §15) | 13.1 | SUP-01 | Patient support tickets — patients raise issues from the app and track them | SUP-01.02 | API: create/list/mine for patient | New | Support | §15 + §2.9 | Patient support tickets / Help centre & support tickets | Patients raise issues from the app and track them to resolution | Patient App + Admin | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
309 | 566 | M14 | Support & help desk | Web | 13 | Phase 13 — Support & help desk (PDF §15) | 13.2 | SUP-02 | Doctor support tickets — doctors raise issues from the portal | SUP-02.01 | Reuse SupportTicket with ReporterRole=Doctor | New | Support | §15 | Doctor support tickets | Doctors raise issues from the portal | Doctor Web + Admin | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
310 | 569 | M14 | Support & help desk | Web | 13 | Phase 13 — Support & help desk (PDF §15) | 13.3 | SUP-03 | Admin issue queue — all issues in one queue with priority, assignment and status | SUP-03.01 | Extend ticket with Priority, Assignee, SLA | New | Support | §15 + §7.2 | Admin issue queue / Support ticket queue | All issues in one queue with priority, assignment and status / All patient and doctor issues in one queue with assignment and resolution | Admin Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
311 | 570 | M14 | Support & help desk | Web | 13 | Phase 13 — Support & help desk (PDF §15) | 13.3 | SUP-03 | Admin issue queue — all issues in one queue with priority, assignment and status | SUP-03.02 | Admin list/filter/assign/status | New | Support | §15 + §7.2 | Admin issue queue / Support ticket queue | All issues in one queue with priority, assignment and status / All patient and doctor issues in one queue with assignment and resolution | Admin Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
312 | 573 | M14 | Support & help desk | Web | 13 | Phase 13 — Support & help desk (PDF §15) | 13.4 | SUP-04 | Ticket conversation — full message thread with attachments | SUP-04.01 | API: messages CRUD + attachment | New | Support | §15 | Ticket conversation | Full message thread with attachments | Admin + Doctor + Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
313 | 578 | M14 | Support & help desk | Web | 13 | Phase 13 — Support & help desk (PDF §15) | 13.6 | SUP-06 | Help centre — self-service help content for patients | SUP-06.01 | HelpArticle table or reuse blog category=help | New | Support | §15 + §2.9 | Help centre | Self-service help content for patients | Patient Website + App | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
314 | 579 | M14 | Support & help desk | Web | 13 | Phase 13 — Support & help desk (PDF §15) | 13.6 | SUP-06 | Help centre — self-service help content for patients | SUP-06.02 | Public GET help articles | New | Support | §15 + §2.9 | Help centre | Self-service help content for patients | Patient Website + App | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
315 | 582 | M14 | Support & help desk | Web | 13 | Phase 13 — Support & help desk (PDF §15) | 13.7 | SUP-07 | Assisted booking — help for patients who need support booking | SUP-07.01 | Flag BookingChannel=Assisted; AssistedRequest ticket type | New | Support | §15 + §2.9 | Assisted booking | Support for patients who need help booking / Help for patients who need support booking | Support + Reception + Patient | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
316 | 583 | M14 | Support & help desk | Web | 13 | Phase 13 — Support & help desk (PDF §15) | 13.7 | SUP-07 | Assisted booking — help for patients who need support booking | SUP-07.02 | API: request assistance; staff completes WEB-04 create on behalf | New | Support | §15 + §2.9 | Assisted booking | Support for patients who need help booking / Help for patients who need support booking | Support + Reception + Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
317 | 586 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.1 | MED-01 | Pharmacy partner onboarding — licensed premises, licence records, activation checklist | MED-01.01 | DB: PharmacyPartner, PharmacyLicence, activation checklist fields | New | HomeoMeds | §12 + §7.2 | Pharmacy partner onboarding / Pharmacy partner management | Licensed premises registered with licence records and an activation checklist / Onboard and activate licensed pharmacies | Pharmacy + Admin | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
318 | 587 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.1 | MED-01 | Pharmacy partner onboarding — licensed premises, licence records, activation checklist | MED-01.02 | API: onboard, admin activate, pharmacy login role | New | HomeoMeds | §12 + §7.2 | Pharmacy partner onboarding / Pharmacy partner management | Licensed premises registered with licence records and an activation checklist / Onboard and activate licensed pharmacies | Pharmacy + Admin | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
319 | 590 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.2 | MED-02 | Licence gating — expired or suspended licences blocked automatically from receiving orders | MED-02.01 | Job: mark licence expired/suspended; exclude from routing | New | HomeoMeds | §12 | Licence gating | Pharmacies with expired or suspended licences are blocked automatically from receiving orders | Backend | Backend | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
320 | 593 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.3 | MED-03 | Fulfilment consent & pharmacy selection — patient chooses the seller and consents before the prescription is shared | MED-03.01 | Consent + selected PharmacyPartnerId on MedicineOrder | New | HomeoMeds | §12 + §2.7 | Fulfilment consent & pharmacy selection | The patient chooses the seller and consents before the prescription is shared | Patient | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
321 | 594 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.3 | MED-03 | Fulfilment consent & pharmacy selection — patient chooses the seller and consents before the prescription is shared | MED-03.02 | API: list sellers; select; grant consent | New | HomeoMeds | §12 + §2.7 | Fulfilment consent & pharmacy selection | The patient chooses the seller and consents before the prescription is shared | Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
322 | 597 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.4 | MED-04 | Prescription handoff — signed prescription becomes the order directly — no re-entry, no transcription errors | MED-04.01 | DB: MedicineOrder, MedicineOrderItem from ErxSnapshot | New | HomeoMeds | §12 + §2.7 | Prescription handoff / Order start | The signed prescription becomes the order directly — no re-entry, no transcription errors / Start an order directly from the prescription | Patient + Pharmacy | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
323 | 598 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.4 | MED-04 | Prescription handoff — signed prescription becomes the order directly — no re-entry, no transcription errors | MED-04.02 | API: POST order from ErxId | New | HomeoMeds | §12 + §2.7 | Prescription handoff / Order start | The signed prescription becomes the order directly — no re-entry, no transcription errors / Start an order directly from the prescription | Patient + Pharmacy | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
324 | 601 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.5 | MED-05 | Rule-based seller routing — licence validity, service area, working hours and capacity | MED-05.01 | DB: SellerRoutingRule (area, hours, capacity) | New | HomeoMeds | §12 | Rule-based seller routing | Orders routed by licence validity, service area, working hours and capacity | Backend | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
325 | 602 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.5 | MED-05 | Rule-based seller routing — licence validity, service area, working hours and capacity | MED-05.02 | Routing service used by seller list API | New | HomeoMeds | §12 | Rule-based seller routing | Orders routed by licence validity, service area, working hours and capacity | Backend | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
326 | 605 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.6 | MED-06 | Manual stock confirmation — pharmacy confirms availability — no live inventory integration required | MED-06.01 | Accept payload includes stock confirmation; reject reason OUT_OF_STOCK | New | HomeoMeds | §12 | Manual stock confirmation | The pharmacy confirms availability — no live inventory integration required | Pharmacy console | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
327 | 608 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.7 | MED-07 | Pharmacy console — accept or reject, enter price quote, mark ready and dispatched | MED-07.01 | Order status machine: Offered/Accepted/Rejected/Quoted/Paid/Ready/Dispatched/Delivered | New | HomeoMeds | §12 | Pharmacy console | Accept or reject orders, enter the price quote, mark ready and dispatched | Pharmacy console | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
328 | 609 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.7 | MED-07 | Pharmacy console — accept or reject, enter price quote, mark ready and dispatched | MED-07.02 | API: accept(OTP), reject, quote, ready, dispatch | New | HomeoMeds | §12 | Pharmacy console | Accept or reject orders, enter the price quote, mark ready and dispatched | Pharmacy console | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
329 | 611 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.7 | MED-07 | Pharmacy console — accept or reject, enter price quote, mark ready and dispatched | MED-07.04 | OTP on accept | New Integration | HomeoMeds | §12 | Pharmacy console | Accept or reject orders, enter the price quote, mark ready and dispatched | Pharmacy console | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
330 | 613 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.8 | MED-08 | Quote before payment — the patient always sees the price before paying | MED-08.01 | DB: MedicineQuote | New | HomeoMeds | §12 + §2.7 | Quote before payment / Pharmacy selection & quote | The patient always sees the price before paying / Choose a licensed pharmacy and see the price before paying | Patient | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
331 | 614 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.8 | MED-08 | Quote before payment — the patient always sees the price before paying | MED-08.02 | API: quote, patient accept quote, then create medicine payment | New | HomeoMeds | §12 + §2.7 | Quote before payment / Pharmacy selection & quote | The patient always sees the price before paying / Choose a licensed pharmacy and see the price before paying | Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
332 | 617 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.9 | MED-09 | Payment or cash on delivery — both options, with status tracking | MED-09.01 | Wire PAY-07 CreateMedicineOrder; COD status enum | New | HomeoMeds | §12 + §9 | Payment or cash on delivery | Both options supported, with status tracking | Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
333 | 620 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.10 | MED-10 | Order tracking — live status for the patient at every stage | MED-10.01 | DB: MedicineOrderEvent | New | HomeoMeds | §12 + §2.7 | Order tracking | Live status for the patient at every stage / Live status from accepted to delivered | Patient | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
334 | 621 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.10 | MED-10 | Order tracking — live status for the patient at every stage | MED-10.02 | GET tracking by order id (patient) | New | HomeoMeds | §12 + §2.7 | Order tracking | Live status for the patient at every stage / Live status from accepted to delivered | Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
335 | 623 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.10 | MED-10 | Order tracking — live status for the patient at every stage | MED-10.04 | Push on status change | New Integration | HomeoMeds | §12 + §2.7 | Order tracking | Live status for the patient at every stage / Live status from accepted to delivered | Patient | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
336 | 625 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.11 | MED-11 | Medicine ledger shares — seller, platform and delivery recorded (FIN-03 live fill) | MED-11.01 | On captured medicine payment write three-share ledger lines | New | HomeoMeds | §12 + §8 | Medicine ledger | Seller, platform and delivery shares recorded separately from consultation money | Account | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
337 | 627 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.12 | MED-12 | Order exception queue — stuck, rejected or failed orders always surfaced — never silent | MED-12.01 | Exception rows for medicine orders | New | HomeoMeds | §12 | Order exception queue | Stuck, rejected or failed orders are always surfaced to the operations team — never silent | Admin + Account | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
338 | 628 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.12 | MED-12 | Order exception queue — stuck, rejected or failed orders always surfaced — never silent | MED-12.02 | Admin/ops list/detail/retry re-route | New | HomeoMeds | §12 | Order exception queue | Stuck, rejected or failed orders are always surfaced to the operations team — never silent | Admin + Account | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
339 | 631 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.13 | MED-13 | OTP-based control — key actions verified by OTP so Homeocentrum can monitor and trace every transaction | MED-13.01 | Bind OTP actions: PharmacyAccept, (optional) QuoteLock, Payout already FIN-05 | New | HomeoMeds | §12 + §17 | OTP-based control | Key actions verified by OTP so Homeocentrum can monitor and trace every transaction | Pharmacy + Account | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
340 | 633 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.14 | MED-14 | Refill orders — repeat orders raised from an existing prescription | MED-14.01 | On doctor approve, clone order from snapshot; patient one-tap | New | HomeoMeds | §12 + §2.7 + §11 | Refill orders / Order detail & refill | Repeat orders raised from an existing prescription / Full order history and one-tap refill request | Patient + Doctor | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
341 | 638 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.16 | MED-16 | Medicines tab — all medicine orders in one place (API now; app UI in Phase 16) | MED-16.01 | GET /api/Patient/MedicineOrders | New | HomeoMeds | §2.7 | Medicines tab | All medicine orders in one place | Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
342 | 641 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.1 | CON-01 | Family members — add family members under one account | CON-01.01 | DB: FamilyMember | New | Patient identity | §2.1 | Family members | Add family members under one account | Patient App (API now) | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
343 | 642 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.1 | CON-01 | Family members — add family members under one account | CON-01.02 | API: CRUD family; book-as-member | New | Patient identity | §2.1 | Family members | Add family members under one account | Patient App (API now) | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
344 | 645 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.2 | CON-02 | Caregiver authorization — let a family member book and manage on their behalf | CON-02.01 | DB: CaregiverAuth | New | Patient identity | §2.1 | Caregiver authorization | Let a family member book and manage on their behalf | Patient App (API now) | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
345 | 646 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.2 | CON-02 | Caregiver authorization — let a family member book and manage on their behalf | CON-02.02 | API: grant/revoke/list; booking authorisation check | New | Patient identity | §2.1 | Caregiver authorization | Let a family member book and manage on their behalf | Patient App (API now) | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
346 | 648 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.2 | CON-02 | Caregiver authorization — let a family member book and manage on their behalf | CON-02.04 | OTP on grant | New Integration | Patient identity | §2.1 | Caregiver authorization | Let a family member book and manage on their behalf | Patient App (API now) | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
347 | 650 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.3 | CON-03 | Records timeline + consultation note + document upload APIs | CON-03.01 | Reuse appointments + summary + eRx + SecureDocument | New | Patient records | §2.5 | Records timeline / Consultation note / Document upload | Complete visit history in date order / Doctor’s notes for each visit / Upload reports, scans and previous prescriptions | Patient App (API now) | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
348 | 651 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.3 | CON-03 | Records timeline + consultation note + document upload APIs | CON-03.02 | GET timeline; GET consultation note (summary); POST documents | New | Patient records | §2.5 | Records timeline / Consultation note / Document upload | Complete visit history in date order / Doctor’s notes for each visit / Upload reports, scans and previous prescriptions | Patient App (API now) | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
349 | 654 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.4 | CON-04 | Follow-up plan & tasks — clear next steps after each consultation | CON-04.01 | DB: FollowUpPlan, FollowUpTask | New | Continuity | §2.6 | Follow-up plan & tasks | Clear next steps after each consultation | Doctor Web + Patient | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
350 | 655 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.4 | CON-04 | Follow-up plan & tasks — clear next steps after each consultation | CON-04.02 | API: doctor set; patient list/complete | New | Continuity | §2.6 | Follow-up plan & tasks | Clear next steps after each consultation | Doctor Web + Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
351 | 658 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.5 | CON-05 | Symptom diary — record symptoms between visits | CON-05.01 | DB: SymptomDiary | New | Continuity | §2.6 | Symptom diary | Record symptoms between visits | Patient App (API now) | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
352 | 659 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.5 | CON-05 | Symptom diary — record symptoms between visits | CON-05.02 | API: patient CRUD; doctor GET by patient | New | Continuity | §2.6 | Symptom diary | Record symptoms between visits | Patient App (API now) | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
353 | 662 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.6 | CON-06 | Progress tracking — see improvement over time across visits | CON-06.01 | Derived API from diary + appointments | New | Continuity | §2.6 | Progress tracking | See improvement over time across visits | Patient + Doctor | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
354 | 663 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.6 | CON-06 | Progress tracking — see improvement over time across visits | CON-06.02 | GET progress series | New | Continuity | §2.6 | Progress tracking | See improvement over time across visits | Patient + Doctor | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
355 | 666 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.7 | CON-07 | Consent centre & data rights — view, manage and withdraw consents; request data | CON-07.01 | Reuse ConsentRecord; DataRequest table | New | Privacy | §17 + §2.8 | Consent centre & data rights | Patients can view, manage and withdraw consent / View, manage and withdraw consents; request data | Patient App (API now) | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
356 | 667 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.7 | CON-07 | Consent centre & data rights — view, manage and withdraw consents; request data | CON-07.02 | API: list/withdraw; request export/delete | New | Privacy | §17 + §2.8 | Consent centre & data rights | Patients can view, manage and withdraw consent / View, manage and withdraw consents; request data | Patient App (API now) | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
357 | 670 | M08 | Account & finance | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.8 | CON-08 | Patient payments & refunds read model | CON-08.01 | GET /api/Patient/Payments | New | Patient money | §2.8 | Payments & refunds | Full payment history and refund status | Patient App (API now) | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
358 | 672 | M05 | Appointments & scheduling | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.9 | CON-09 | Physical clinic appointment — book an in-person visit as well as online | CON-09.01 | Public/patient create booking accepts ConsultMode=In-clinic; uses in-clinic fee | Existing Improvement | Booking | §2.9 + §5.2 | Physical clinic appointment | Book an in-person visit as well as online | Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
359 | 674 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.10 | CON-10 | Patient profile setup API — name, age, gender, contact and health basics | CON-10.01 | Extend Patient with health-basics JSON/columns | New | Patient identity | §2.1 | Profile setup | Name, age, gender, contact and health basics | Patient App (API now) | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
360 | 675 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.10 | CON-10 | Patient profile setup API — name, age, gender, contact and health basics | CON-10.02 | GET/PUT /api/Patient/Profile | New | Patient identity | §2.1 | Profile setup | Name, age, gender, contact and health basics | Patient App (API now) | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
361 | 957 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.1 | RPT-01 | Admin overview dashboard — platform-wide activity at a glance (replace Velzon ecommerce) | RPT-01.01 | No ecommerce tables | Existing Improvement | Reports | §16 + §7.2 | Admin overview dashboard / Admin dashboard | Platform-wide activity at a glance / Live overview of the whole platform | Admin Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
362 | 958 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.1 | RPT-01 | Admin overview dashboard — platform-wide activity at a glance (replace Velzon ecommerce) | RPT-01.02 | GET /api/AdminDashboard/Overview | Existing Improvement | Reports | §16 + §7.2 | Admin overview dashboard / Admin dashboard | Platform-wide activity at a glance / Live overview of the whole platform | Admin Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
363 | 961 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.2 | RPT-02 | Doctor practice statistics — patient and consultation trends (extend existing charts) | RPT-02.01 | No new warehouse required for v1 | Existing Improvement | Reports | §16 + §5.1 | Doctor practice statistics | Patient and consultation trends | Doctor Web | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
364 | 962 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.2 | RPT-02 | Doctor practice statistics — patient and consultation trends (extend existing charts) | RPT-02.02 | Extend GetPatientStatsCharts with VisitType/ConsultMode | Existing Improvement | Reports | §16 + §5.1 | Doctor practice statistics | Patient and consultation trends | Doctor Web | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
365 | 965 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.3 | RPT-03 | Follow-up analysis — due/overdue patients and follow-up conversion | RPT-03.01 | Queries on VisitType + FollowUpTask | New | Reports | §16 | Follow-up analysis | Which patients are due or overdue for follow-up, and follow-up conversion | Doctor Web | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
366 | 966 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.3 | RPT-03 | Follow-up analysis — due/overdue patients and follow-up conversion | RPT-03.02 | GET FollowUpDue, FollowUpSummary | New | Reports | §16 | Follow-up analysis | Which patients are due or overdue for follow-up, and follow-up conversion | Doctor Web | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
367 | 969 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.4 | RPT-04 | Clinic performance analysis — appointments, slot utilisation, no-shows, cancellations, waiting time and revenue | RPT-04.01 | Aggregate APIs beyond GetPatientStatsCharts | New | Reports | §16 | Clinic performance analysis | Appointments, slot utilisation, no-shows, cancellations, waiting time and revenue | Doctor Web | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
368 | 970 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.4 | RPT-04 | Clinic performance analysis — appointments, slot utilisation, no-shows, cancellations, waiting time and revenue | RPT-04.02 | GET ClinicPerformance | New | Reports | §16 | Clinic performance analysis | Appointments, slot utilisation, no-shows, cancellations, waiting time and revenue | Doctor Web | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
369 | 973 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.5 | RPT-05 | Payment reconciliation report — bookings matched against payments | RPT-05.01 | CSV/PDF export of FIN-02 query | New | Reports | §16 + §7.2 | Payment reconciliation report / Consult booking & payment reconciliation | Bookings matched against payments / Match every booking against every payment | Admin + Account | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
370 | 976 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.6 | RPT-06 | Settlement & payout reports — amounts due and paid to doctors and pharmacies | RPT-06.01 | Export settlement runs + payout register | New | Reports | §16 + §8 | Settlement & payout reports | Amounts due and paid to doctors and pharmacies | Account | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
371 | 979 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.7 | RPT-07 | GST & invoice reports (reporting surface of FIN-08) | RPT-07.01 | Confirm CA format; implement export if not already in FIN-08 | New | Reports | §16 + §8 | GST & invoice reports | Tax reporting | Account | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
372 | 981 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.8 | RPT-08 | Doctor earnings summary — daily, weekly and monthly earnings with payout status (web + same API as DMO-10) | RPT-08.01 | Reuse earnings API | New | Reports | §16 + §3 | Doctor earnings summary | Daily, weekly and monthly earnings with payout status | Doctor Web + App | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
373 | 982 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.8 | RPT-08 | Doctor earnings summary — daily, weekly and monthly earnings with payout status (web + same API as DMO-10) | RPT-08.02 | GET Earnings/Summary already for app — add if missing date buckets | New | Reports | §16 + §3 | Doctor earnings summary | Daily, weekly and monthly earnings with payout status | Doctor Web + App | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
374 | 985 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.9 | RPT-09 | Medicine order reports — order volumes, fulfilment and exceptions | RPT-09.01 | Aggregates on MedicineOrder | New | Reports | §16 + §12 | Medicine order reports | Order volumes, fulfilment and exceptions | Admin + Account | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
375 | 986 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.9 | RPT-09 | Medicine order reports — order volumes, fulfilment and exceptions | RPT-09.02 | GET medicine order report | New | Reports | §16 + §12 | Medicine order reports | Order volumes, fulfilment and exceptions | Admin + Account | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
376 | 989 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.10 | RPT-10 | Platform users remaining 20% — import, export and activation control | RPT-10.01 | VerificationStatus on user/doctor list DTO | Existing Improvement | Admin | §7.2 | Platform users | Manage all users with import, export and activation control | Admin Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
377 | 990 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.10 | RPT-10 | Platform users remaining 20% — import, export and activation control | RPT-10.02 | User import/export APIs if missing | Existing Improvement | Admin | §7.2 | Platform users | Manage all users with import, export and activation control | Admin Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
378 | 998 | M19 | Reports, NFR & delivery gate | Web | 19 | Phase 19 — Cross-surface QA, NFR, delivery summary gate (PDF §1 + §18) | 19.3 | NFR-01 | NFR — performance, low-data, reliability, secrets, dual-API freeze | NFR-01.01 | Rotate API secrets; keys in config/KeyVault; directory browsing remains off | Existing Modification | NFR | §2.9 + §3 + §17 | Low-data mode / Reliability monitoring / Secure login | Works on slow connections; failures reported automatically; credentials protected | All | Security | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet

## 04_UI
UI TRACK MIRROR — live from module sheets. Mark Frontend Status Done on the module sheet; this column updates.
Module Seq | Original Seq | Dev Module Code | Dev Module | Track | Phase | Phase Name | WBS | Main Task ID | Main Task | Sub Task ID | Sub Task | Work Type | Source Module / Area | PDF Section | PDF Feature (exact wording) | PDF Delivery Text | Application Surface | Layer | Assigned To (lead) | Frontend | Frontend Status | Frontend Assigned | Backend | Backend Status | Backend Assigned | Database | Database Status | Database Assigned | API | API Status | API Assigned | Mobile | Mobile Status | Mobile Assigned | Integration | Integration Status | Integration Assigned | Layers Remaining | Overall Status | Notes | Open Module Sheet
1 | 16 | M01 | Foundation & Security | UI | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.2 | FND-02 | Delivery footprint — 2 mobile apps · 5 web portals · payment · telemedicine · digital prescription · HomeoMeds (programme skeleton) | FND-02.01 | Web: add Account layout + home redirect; Pharmacy layout stub; do not build screens yet | New | Platform | §1 | Delivery covers | 2 mobile applications · 5 web portals · payment system · telemedicine · digital prescription · online medicine delivery. | Shared | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
2 | 17 | M01 | Foundation & Security | UI | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.2 | FND-02 | Delivery footprint — 2 mobile apps · 5 web portals · payment · telemedicine · digital prescription · HomeoMeds (programme skeleton) | FND-02.02 | Extend roles.js and AuthProtected with per-route ACL skeleton (deny-by-default for new routes) | Existing Improvement | Platform | §1 | Delivery covers | 2 mobile applications · 5 web portals · payment system · telemedicine · digital prescription · online medicine delivery. | Shared | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
3 | 22 | M01 | Foundation & Security | UI | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.3 | SEC-01 | Secure login — protected credentials for every user type | SEC-01.03 | UI: remove fakeBackend() from App.js production path; login still Formik/Yup | Existing Modification | Security | §17 | Secure login | Protected credentials for every user type | All web + later mobile | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
4 | 26 | M01 | Foundation & Security | UI | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.4 | SEC-02 | Secure password reset — time-limited reset links (stop plaintext email + fake thunk) | SEC-02.03 | UI: replace slices/auth/forgetpwd fake/Firebase with real APIs; /reset-password/:token success/expiry states | Existing Improvement | Security | §17 | Secure password reset | Time-limited reset links | Admin / Doctor / Reception web | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
5 | 29 | M01 | Foundation & Security | UI | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.5 | SEC-03 | Session control — proper sign-out across web and mobile | SEC-03.02 | Web: Logout.js calls API then clears authUser + patient-board session (keep existing board clear) | Existing Improvement | Security | §17 | Session control | Proper sign-out across web and mobile | All | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
6 | 33 | M01 | Foundation & Security | UI | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.6 | SEC-04 | Role-based access — each role sees only what it is permitted to see | SEC-04.02 | Frontend: hide routes the role cannot view; keep Velzon demo routes out of production menus | Existing Improvement | Security | §17 | Role-based access | Each role sees only what it is permitted to see | Admin / All web | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
7 | 136 | M02 | Admin clinical masters | UI | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.28 | ADM-B04 | Business Management — Roles & menu permissions (existing DB, runtime ACL leftover) | ADM-B04.03 | Admin role pages remain; frontend consumes menu API instead of hard-coded LayoutMenuData for domain items | Existing Improvement | Business Management | §7.2 | Roles & menu permissions | Control exactly what each role can access | Admin Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
8 | 138 | M03 | Doctor clinical workspace | UI | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.1 | CLN-01 | Clinical workspace — single screen for the entire consultation | CLN-01.01 | UI: Patient Board header shows appointment, visit type, consult mode placeholders (wired in Phases 4 and 6) | Existing Improvement | Patient Board | §5.3 | Clinical workspace | Single screen for the entire consultation | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
9 | 158 | M03 | Doctor clinical workspace | UI | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.7 | CLN-07 | Manage selected rubrics — review, edit and remove (remaining ~10%) | CLN-07.03 | Clipboard UX: confirm delete; intensity edit; count badge | Existing Improvement | Patient Board | §5.3 | Manage selected rubrics | Review, edit and remove selected rubrics | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
10 | 164 | M03 | Doctor clinical workspace | UI | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.9 | CLN-09 | Improved rubric accuracy — enhanced accuracy rules for audio-based rubric suggestions | CLN-09.02 | Admin: metaphor/alias approve-reject remaining UX | Existing Improvement | Audio AI | §5.3 | Improved rubric accuracy | Enhanced accuracy rules for audio-based rubric suggestions | Doctor Web Portal + Admin intelligence | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
11 | 168 | M03 | Doctor clinical workspace | UI | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.10 | CLN-10 | Materia medica reference during consultation (remaining ~10%) | CLN-10.03 | MM tab: faster head navigation / keep place in case | Existing Improvement | Patient Board | §5.3 | Materia medica reference | Browse materia medica during the consultation | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
12 | 175 | M03 | Doctor clinical workspace | UI | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.12 | CLN-12 | Repertorization & elimination (remaining ~10%) | CLN-12.03 | Repertorize tab stability; then COG sits beside it | Existing Improvement | Patient Board | §5.3 | Repertorization & elimination | Full repertorization with elimination | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
13 | 179 | M03 | Doctor clinical workspace | UI | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.13 | CLN-13 | Center of Gravity — new analysis identifying the central remedy of the case, with reasoning shown | CLN-13.03 | Patient Board → Repertorize tab → Center of Gravity sub-panel (toggle vs classic elimination) | New | Repertorization | §5.3 | Center of Gravity | New analysis identifying the central remedy of the case, with reasoning shown | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
14 | 189 | M03 | Doctor clinical workspace | UI | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.16 | CLN-16 | Complaints & case details — wire Patient Board to existing SaveComplaints / SaveCaseDetails (~20% today) | CLN-16.03 | Patient Board: complaints + case details form that actually POSTs | Existing Improvement | Patient Board | §5.3 | Complaints & case details | Capture and store complaints and case details | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
15 | 193 | M03 | Doctor clinical workspace | UI | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.17 | CLN-17 | Patient back history — complete history of visits, notes, prescriptions and payments | CLN-17.03 | History panel: date-ordered visits; open past eRx; payment badge placeholder | Existing Improvement | Patient Board | §5.3 | Patient back history | Complete history of visits, notes, prescriptions and payments | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
16 | 196 | M03 | Doctor clinical workspace | UI | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.18 | CLN-18 | Export case data — download the full case in Excel or PDF | CLN-18.02 | Patient Board toolbar: Export Excel / Export PDF | New | Patient Board | §5.3 | Export case data | Download the full case in Excel or PDF | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
17 | 203 | M03 | Doctor clinical workspace | UI | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.20 | CLN-20 | 3D anatomy viewer — interactive 3D body model linked to rubric search (remaining ~50%) | CLN-20.03 | Viewer UX: incomplete regions, loading, fallback message | Existing Improvement | Anatomy | §5.3 | 3D anatomy viewer | Interactive 3D body model linked to rubric search | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
18 | 207 | M04 | Doctor daily operations | UI | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.1 | DOC-01 | Doctor home dashboard — complete overview of the working day (remaining ~30%) | DOC-01.03 | Dashboard chrome: keep counts; add slots for Online toggle, tele queue, unpaid badge | Existing Improvement | Doctor Dashboard | §5.1 | Doctor home dashboard | Complete overview of the working day | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
19 | 214 | M04 | Doctor daily operations | UI | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.3 | DOC-03 | Patient search, list & open case (remaining ~10%) | DOC-03.03 | List columns: last visit; later payment/family | Existing Improvement | Doctor Dashboard | §5.1 | Patient search, list & open case | Find any patient and open their case instantly | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
20 | 223 | M04 | Doctor daily operations | UI | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.6 | DOC-06 | Export patients — download patient data in Excel, CSV or PDF (keep) | DOC-06.02 | UI: Excel / CSV / PDF actions labelled as in the delivery document | Existing Improvement | Patients | §5.1 | Export patients | Download patient data in Excel, CSV or PDF | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
21 | 232 | M04 | Doctor daily operations | UI | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.9 | DOC-09 | Manage reception staff — add, edit and remove reception users (backend done, UI absent) | DOC-09.02 | Build /doctor/reception-staff list, add, edit, disable pages; menu entry in doctor chrome | Existing Improvement | Staff | §5.1 | Manage reception staff | Add, edit and remove reception users | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
22 | 236 | M04 | Doctor daily operations | UI | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.10 | DOC-10 | Doctor profile — clinic details, consultation fee, photo, qualifications, working hours, bank details | DOC-10.03 | Replace Velzon /profile for doctor role with clinic/fee/photo/qualifications/hours/bank tabs | Existing Improvement | Doctor Profile | §5.1 | Doctor profile | Clinic details, consultation fee, photo, qualifications, working hours, bank details | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
23 | 243 | M05 | Appointments & scheduling | UI | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.2 | APT-02 | Create new appointment — persist visit type, consultation mode and fee | APT-02.03 | Doctor/Reception new-appointment modal: visit type, consult mode, fee (placeholder until Phase 6 config) | Existing Improvement | Appointments | §5.2 | Create new appointment | Book with visit type, consultation mode and fee | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
24 | 253 | M05 | Appointments & scheduling | UI | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.5 | APT-05 | Reschedule appointment — move to a new slot with automatic patient notification (NEW — not a rename of UpdateAppointmentTime) | APT-05.03 | UI: RescheduleModal shared by Doctor and Reception — old date/time + new slot picker; reason optional | New | Appointments | §5.2 + §2.3 + §6 | Reschedule appointment | Move to a new slot with automatic patient notification / Move to another slot without calling the clinic | Doctor Web + Reception + later Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
25 | 258 | M05 | Appointments & scheduling | UI | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.6 | APT-06 | Cancel appointment — reason, free the slot, trigger refund where applicable (NEW CANCELLED status — do NOT reuse DeleteStatus) | APT-06.03 | UI: CancelAppointmentModal shared by Doctor and Reception; dashboard Cancelled filter | New | Appointments | §5.2 + §2.3 + §6 | Cancel appointment | Cancel with reason, free the slot, trigger refund where applicable / Cancel with reason, refund handled per policy | Doctor Web + Reception + later Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
26 | 261 | M05 | Appointments & scheduling | UI | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.7 | APT-07 | Daily schedule setup — define working days, hours and break times (promote modal to first-class screen) | APT-07.01 | Promote DailyScheduleSetupModal to /doctor/schedule; week grid; copy-day; reuse Get/SaveDailySchedule | Existing Improvement | Scheduling | §5.2 | Daily schedule setup | Define working days, hours and break times | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
27 | 269 | M05 | Appointments & scheduling | UI | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.9 | APT-09 | Consultation payment status on every appointment (schema now; values live in Phase 6) | APT-09.03 | UI: Paid / Unpaid / Pay-at-clinic / Failed badges on doctor appointment list | New | Appointments | §5.2 + §9 | Consultation payment status | See paid, unpaid or pay-at-clinic on every appointment / Doctor, reception and patient all see the same payment status | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
28 | 276 | M06 | Reception portal | UI | 5 | Phase 5 — Reception portal (PDF §6) | 5.2 | REC-02 | Reception profile — manage own profile details (0% today) | REC-02.03 | /profile reception variant | New | Reception | §6 | Reception profile | Manage own profile details | Reception Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
29 | 278 | M06 | Reception portal | UI | 5 | Phase 5 — Reception portal (PDF §6) | 5.3 | REC-03 | Reception home dashboard — purpose-built front-desk dashboard (not only hidden doctor actions) | REC-03.01 | Route /reception (or role-based chrome on existing dashboard) hiding clinical tabs | Existing Improvement | Reception | §6 | Reception home dashboard | Purpose-built front-desk dashboard | Reception Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
30 | 279 | M06 | Reception portal | UI | 5 | Phase 5 — Reception portal (PDF §6) | 5.3 | REC-03 | Reception home dashboard — purpose-built front-desk dashboard (not only hidden doctor actions) | REC-03.02 | Quick actions: new patient, new appointment, collect payment, case paper, schedule | Existing Improvement | Reception | §6 | Reception home dashboard | Purpose-built front-desk dashboard | Reception Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
31 | 288 | M06 | Reception portal | UI | 5 | Phase 5 — Reception portal (PDF §6) | 5.6 | REC-06 | Create & manage appointments — full appointment management (keep; plus reschedule/cancel from Phase 4) | REC-06.02 | Reception UI uses the same Reschedule/Cancel modals as doctor | New | Reception | §6 | Create & manage appointments | Full appointment management | Reception Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
32 | 290 | M06 | Reception portal | UI | 5 | Phase 5 — Reception portal (PDF §6) | 5.7 | REC-07 | New appointment — book on behalf of the patient (keep; same VisitType/ConsultMode/fee as APT-02) | REC-07.01 | Share the extended new-appointment modal with reception chrome | Existing Improvement | Reception | §6 | New appointment | Book on behalf of the patient | Reception Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
33 | 294 | M06 | Reception portal | UI | 5 | Phase 5 — Reception portal (PDF §6) | 5.8 | REC-08 | Waiting queue management — manage the live queue and call the next patient | REC-08.03 | Queue panel: order, wait time, paid/unpaid, Call next | Existing Improvement | Reception | §6 | Waiting queue management | Manage the live queue and call the next patient | Reception Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
34 | 302 | M06 | Reception portal | UI | 5 | Phase 5 — Reception portal (PDF §6) | 5.11 | REC-11 | View doctor schedule — see the doctor’s working schedule (read-only) | REC-11.01 | Frontend only over existing GetDailySchedule — /reception/schedule read-only | New | Reception | §6 | View doctor schedule | See the doctor’s working schedule | Reception Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
35 | 306 | M06 | Reception portal | UI | 5 | Phase 5 — Reception portal (PDF §6) | 5.12 | REC-12 | Log case paper / chief complaint — record the reason for visit before the consultation | REC-12.03 | /reception/case-paper or limited board | New | Reception | §6 | Log case paper / chief complaint | Record the reason for visit before the consultation | Reception Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
36 | 308 | M06 | Reception portal | UI | 5 | Phase 5 — Reception portal (PDF §6) | 5.13 | REC-13 | Collect consultation payment — cash, UPI, card or payment link and issue a receipt (API in Phase 6; UI shell now) | REC-13.01 | Specify receipt fields (amount, method, appointment, GST placeholder) for Phase 6 implementation | New | Reception | §6 + §9 | Collect consultation payment | Take cash, UPI, card or payment link and issue a receipt | Reception Portal | Design | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
37 | 312 | M07 | Payment system | UI | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.1 | PAY-01 | Consultation fee configuration — each doctor’s fee set and displayed to patients | PAY-01.03 | Doctor profile fee tab + later public doctor card | New | Payments | §9 | Consultation fee configuration | Each doctor’s fee set and displayed to patients | Doctor profile + Public + Admin | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
38 | 320 | M07 | Payment system | UI | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.3 | PAY-03 | Online consultation payment — patient pays by card, UPI, netbanking or wallet | PAY-03.03 | Public /book/pay/:bookingId using Razorpay pattern from Widgets.js but consult order API | New | Payments | §9 + §4 + §2.3 | Online consultation payment | Patient pays by card, UPI, netbanking or wallet / Pay the consultation fee at the time of booking / Pay the consultation fee inside the app | Public web + later Patient app | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
39 | 325 | M07 | Payment system | UI | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.4 | PAY-04 | Reception payment collection — cash, UPI, card or payment link with printed receipt | PAY-04.03 | Reception collect modal: amount, method, GST placeholder, print receipt | New | Payments | §9 + §6 | Reception payment collection | Cash, UPI, card or payment link with printed receipt | Reception Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
40 | 329 | M07 | Payment system | UI | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.5 | PAY-05 | Pay-at-clinic option — book now, pay at the clinic where the doctor allows it | PAY-05.02 | UI: public booking shows Pay at clinic vs Pay now; doctor list badge | New | Payments | §9 | Pay-at-clinic option | Book now, pay at the clinic where the doctor allows it | Public + Doctor + Reception | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
41 | 332 | M07 | Payment system | UI | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.6 | PAY-06 | Doctor subscription payment — buy and renew subscription packages (complete remaining ~30%) | PAY-06.02 | Widgets.js: handle failed pay; show invoice when Phase 7 invoice exists | Existing Improvement | Payments | §9 | Doctor subscription payment | Buy and renew subscription packages | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
42 | 338 | M07 | Payment system | UI | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.8 | PAY-08 | Payment status everywhere — doctor, reception and patient all see the same payment status | PAY-08.02 | Surface badges: doctor, reception; public confirmation page; patient app in Phase 16 consumes same API | New | Payments | §9 | Payment status everywhere | Doctor, reception and patient all see the same payment status | All | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
43 | 342 | M07 | Payment system | UI | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.9 | PAY-09 | Refunds — processed and tracked against the original payment | PAY-09.03 | Account refund screen in Phase 7; patient payments list in Phase 16 | New | Payments | §9 + §8 + §2.8 | Refunds | Processed and tracked against the original payment / Issue and track refunds | Account + Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
44 | 347 | M07 | Payment system | UI | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.10 | PAY-10 | Payment receipts & invoices — issued for every transaction | PAY-10.03 | Print/download on reception, doctor (subscription), later patient app | New | Payments | §9 + §8 | Payment receipts & invoices | Issued for every transaction / Invoice numbering and tax reporting | All | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
45 | 354 | M08 | Account & finance | UI | 7 | Phase 7 — Account & finance department (PDF §8) | 7.1 | FIN-01 | Unified transaction ledger — every rupee that moves through the platform, in one record | FIN-01.03 | /account/ledger UI — Account layout sidebar Finance | New | Account | §8 | Unified transaction ledger | Every rupee that moves through the platform, in one record | Account Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
46 | 358 | M08 | Account & finance | UI | 7 | Phase 7 — Account & finance department (PDF §8) | 7.2 | FIN-02 | Consultation payment reconciliation — online payments and reception collections matched and verified | FIN-02.03 | /account/consult-recon and /admin/consult-payments (same data, Account owns, Admin views) | New | Account | §8 + §7.2 + §16 | Consultation payment reconciliation | Online payments and reception collections matched and verified / Match every booking against every payment | Account + Admin | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
47 | 362 | M08 | Account & finance | UI | 7 | Phase 7 — Account & finance department (PDF §8) | 7.3 | FIN-03 | Medicine ledger — medicine money tracked separately from consultation money | FIN-03.03 | /account/medicine-ledger UI (empty until HomeoMeds orders exist — still ship the screen) | New | Account | §8 + §12 | Medicine ledger | Medicine money tracked separately from consultation money / Seller, platform and delivery shares recorded separately from consultation money | Account Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
48 | 366 | M08 | Account & finance | UI | 7 | Phase 7 — Account & finance department (PDF §8) | 7.4 | FIN-04 | Settlement runs — scheduled settlement of amounts due to doctors and pharmacies | FIN-04.03 | /account/settlements | New | Account | §8 + §16 | Settlement runs | Scheduled settlement of amounts due to doctors and pharmacies | Account Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
49 | 370 | M08 | Account & finance | UI | 7 | Phase 7 — Account & finance department (PDF §8) | 7.5 | FIN-05 | Payout approval — payouts released only after OTP-verified approval | FIN-05.03 | /account/payouts | New | Account | §8 + §17 | Payout approval | Payouts released only after OTP-verified approval | Account Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
50 | 373 | M08 | Account & finance | UI | 7 | Phase 7 — Account & finance department (PDF §8) | 7.6 | FIN-06 | Refund processing — Account issues and tracks refunds (uses PAY-09) | FIN-06.01 | UI /account/refunds: original payment, amount, reason, status | New | Account | §8 | Refund processing | Issue and track refunds | Account Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
51 | 378 | M08 | Account & finance | UI | 7 | Phase 7 — Account & finance department (PDF §8) | 7.7 | FIN-07 | Payment exception handling — investigate and resolve every failed or disputed payment | FIN-07.03 | /account/exceptions and /admin/payment-exceptions (same queue) | New | Account | §8 + §7.2 | Payment exception handling | Investigate and resolve every failed or disputed payment / Every failed or mismatched payment surfaced for action | Account + Admin | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
52 | 382 | M08 | Account & finance | UI | 7 | Phase 7 — Account & finance department (PDF §8) | 7.8 | FIN-08 | GST & invoice reports — invoice numbering and tax reporting | FIN-08.03 | /account/tax | New | Account | §8 + §16 | GST & invoice reports | Invoice numbering and tax reporting | Account Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
53 | 386 | M08 | Account & finance | UI | 7 | Phase 7 — Account & finance department (PDF §8) | 7.9 | FIN-09 | Payee records — bank and KYC details for doctors and pharmacies | FIN-09.03 | /account/payees | New | Account | §8 | Payee records | Bank and KYC details for doctors and pharmacies | Account Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
54 | 390 | M08 | Account & finance | UI | 7 | Phase 7 — Account & finance department (PDF §8) | 7.10 | FIN-10 | Clinic collection view — cash and UPI collected at reception, per clinic and per day | FIN-10.03 | /account/clinic-collections | New | Account | §8 | Clinic collection view | Cash and UPI collected at reception, per clinic and per day | Account Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
55 | 396 | M09 | Trust & verification | UI | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.1 | TRU-01 | Doctor credentialing — doctors upload qualification and registration documents for review | TRU-01.03 | Doctor profile credentials tab + document upload | New | Trust | §13 + §7.2 | Doctor credentialing | Doctors upload qualification and registration documents for review | Doctor Web + Admin | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
56 | 400 | M09 | Trust & verification | UI | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.2 | TRU-02 | Verification review — Admin approves, rejects or requests further information | TRU-02.03 | /admin/doctor-credentialing and /:doctorId; verification column on users list | New | Trust | §13 + §7.2 | Verification review | Admin approves, rejects or requests more information before they can practise on the platform | Admin Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
57 | 404 | M09 | Trust & verification | UI | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.3 | TRU-03 | Verified badge — patients see which doctors have been verified | TRU-03.02 | Badge component for website (Phase 9) and patient app (Phase 16) | New | Trust | §13 + §2.2 | Verified badge / Credentials & verification | Patients see which doctors have been verified / Verified badge showing the doctor’s credentials are checked | Public + Patient app | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
58 | 411 | M09 | Trust & verification | UI | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.5 | TRU-05 | Patient reviews — patients rate and review consultations | TRU-05.03 | Public doctor profile reviews; patient app write flow Phase 16 | New | Trust | §13 + §2.8 | Patient reviews / Write a review | Patients rate and review consultations / Rate and review the consultation | Patient + Public | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
59 | 415 | M09 | Trust & verification | UI | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.6 | TRU-06 | Review appeal — doctors can appeal a review; patients manage reviews and raise an appeal | TRU-06.03 | Doctor dashboard my-reviews; admin queue | New | Trust | §13 + §2.8 | Review appeal / My reviews & appeal | Doctors can appeal a review / Manage reviews and raise an appeal | Doctor + Patient + Admin | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
60 | 419 | M09 | Trust & verification | UI | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.7 | TRU-07 | Ranking transparency — patients are shown why doctors are ranked as they are | TRU-07.03 | Search results: Why this order? panel | New | Trust | §13 + §2.2 | Ranking transparency / Ranking explanation | Patients are shown why doctors are ranked as they are / Transparent explanation of why doctors appear in a given order | Public + Patient app | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
61 | 423 | M10 | Patient website | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.1 | WEB-01 | Product home page — complete public website presenting the service | WEB-01.03 | HomeLandingPage: book, verified doctors, pricing teaser, store badges; strip leftover job-board feel | Existing Improvement | Patient Website | §4 | Product home page | Complete public website presenting the service | Patient Website | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
62 | 425 | M10 | Patient website | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.2 | WEB-02 | Consultation & subscription pricing — transparent pricing display | WEB-02.01 | Public doctor card shows in-clinic and tele fee | Existing Improvement | Patient Website | §4 | Consultation & subscription pricing | Transparent pricing display | Patient Website | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
63 | 426 | M10 | Patient website | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.2 | WEB-02 | Consultation & subscription pricing — transparent pricing display | WEB-02.02 | /pricing remains SaaS packages for doctors; label it clearly vs patient consult fees | Existing Improvement | Patient Website | §4 | Consultation & subscription pricing | Transparent pricing display | Patient Website | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
64 | 430 | M10 | Patient website | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.3 | WEB-03 | Doctor discovery — browse and search verified doctors | WEB-03.03 | /book list + filters + doctor profile page | New | Patient Website | §4 + §2.2 | Doctor discovery | Browse and search verified doctors | Patient Website | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
65 | 434 | M10 | Patient website | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.4 | WEB-04 | Self-service booking — book an appointment online without calling the clinic | WEB-04.03 | /book/:doctorId/slots; /book/confirm; booking success | New | Patient Website | §4 + §2.3 | Self-service booking | Book an appointment online without calling the clinic | Patient Website | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
66 | 436 | M10 | Patient website | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.5 | WEB-05 | Online consultation payment on website — pay the fee at the time of booking | WEB-05.01 | /book/pay/:bookingId + success/failure pages | New | Patient Website | §4 + §9 | Online consultation payment | Pay the consultation fee at the time of booking | Patient Website | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | Edit on module sheet
67 | 440 | M10 | Patient website | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.6 | WEB-06 | Contact & enquiry form — enquiries reach the admin team and are tracked | WEB-06.03 | /contact confirmation; /admin/enquiries inbox (not Velzon mailbox) | Existing Improvement | Patient Website | §4 + §15 | Contact & enquiry form | Enquiries reach the admin team and are tracked | Patient Website + Admin | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
68 | 442 | M10 | Patient website | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.7 | WEB-07 | Privacy policy — covering data protection, recording and pharmacy consent | WEB-07.01 | Replace /privacy content with signed legal copy; store PolicyVersion | Existing Improvement | Legal | §4 + §17 | Privacy policy | Covering data protection, recording and pharmacy consent | Patient Website | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
69 | 444 | M10 | Patient website | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.8 | WEB-08 | Terms of service — covering payments, refunds, telemedicine and medicine orders | WEB-08.01 | Replace /terms with signed copy; version stamp on booking/payment | Existing Improvement | Legal | §4 | Terms of service | Covering payments, refunds, telemedicine and medicine orders | Patient Website | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
70 | 448 | M10 | Patient website | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.9 | WEB-09 | Doctor self-registration — doctors apply to join the platform online | WEB-09.03 | /register multipart docs; pending message; status page | Existing Improvement | Patient Website | §4 | Doctor self-registration | Doctors apply to join the platform online | Public | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
71 | 452 | M10 | Patient website | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.10 | WEB-10 | Email activation — secure account activation by email link | WEB-10.03 | Login activation query param UX + expiry copy | Existing Improvement | Auth | §4 | Email activation | Secure account activation by email link | Public | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
72 | 456 | M05 | Appointments & scheduling | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.11 | WEB-11 | Waitlist offer — get offered a slot when one is freed by a cancellation (patient website + later app) | WEB-11.03 | Public waitlist CTA on full days | New | Booking | §2.3 | Waitlist offer | Get offered a slot when one is freed by a cancellation | Patient Website + App | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
73 | 459 | M10 | Patient website | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.12 | WEB-12 | Health articles — educational content to build trust and engagement | WEB-12.01 | Public articles list/detail from existing blog/news APIs | Existing Improvement | Patient Website | §2.2 | Health articles | Educational content to build trust and engagement | Patient Website + App | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
74 | 463 | M11 | Digital prescription (eRx) | UI | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.1 | ERX-01 | Potency module — every remedy carries a defined potency from a managed list, no free text | ERX-01.03 | Rx modal potency picker (6C, 30C, 200C, 1M…) | New | eRx | §11 | Potency module | Every remedy carries a defined potency, selected from a managed list — no free text | Doctor Web + Admin | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
75 | 467 | M11 | Digital prescription (eRx) | UI | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.2 | ERX-02 | Dosage details — frequency, duration and instructions recorded clearly | ERX-02.03 | Rx row UI for the three fields | New | eRx | §11 | Dosage details | Frequency, duration and instructions recorded clearly | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
76 | 471 | M11 | Digital prescription (eRx) | UI | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.3 | ERX-03 | Visit notes kept separate from the prescription — private clinical notes never appear on the prescription given to the patient or pharmacy | ERX-03.03 | Move History Notes out of Rx modal; note types Chief complaint / Follow-up / General | New | eRx | §11 + §5.3 | Visit notes kept separate from the prescription | The doctor’s private clinical notes never appear on the prescription given to the patient or pharmacy | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
77 | 475 | M11 | Digital prescription (eRx) | UI | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.4 | ERX-04 | Signed digital prescription — issued and locked once signed, so it cannot be altered afterwards | ERX-04.03 | Sign button; locked badge on board header | New | eRx | §11 + §2.5 + §5.3 | Signed digital prescription | Issued and locked once signed, so it cannot be altered afterwards / Official prescription issued by the doctor | Doctor Web | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
78 | 478 | M11 | Digital prescription (eRx) | UI | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.5 | ERX-05 | Prescription history — every prescription stored against the patient and visit | ERX-05.02 | Doctor history panel lists signed eRx; patient timeline in Phase 16 | New | eRx | §11 | Prescription history | Every prescription stored against the patient and visit | Doctor + Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
79 | 481 | M11 | Digital prescription (eRx) | UI | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.6 | ERX-06 | Patient view of prescription in app — patient sees the prescription immediately (codes until pharmacy accept) | ERX-06.02 | Web confirmation/records page can show the same payload before the app exists | New | eRx | §11 + §2.5 | Patient view in app | Patient sees the prescription immediately in the app | Patient App + Website | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
80 | 484 | M11 | Digital prescription (eRx) | UI | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.7 | ERX-07 | Print & PDF — printable and downloadable prescription | ERX-07.02 | Print/Download on doctor board and later patient app | New | eRx | §11 | Print & PDF | Printable and downloadable prescription | Doctor + Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
81 | 492 | M11 | Digital prescription (eRx) | UI | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.10 | ERX-10 | Repeat prescription / refill — patient requests; doctor approves or rejects from the mobile app (inbox on web too) | ERX-10.03 | Doctor web inbox; doctor app in Phase 17; patient app in Phase 16 | New | eRx | §11 + §3 + §2.7 | Repeat prescription / refill | Patient requests a refill; doctor approves or rejects from the mobile app | Patient + Doctor mobile + Doctor web | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
82 | 498 | M12 | Telemedicine | UI | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.1 | TEL-01 | Doctor availability — online or offline status and working hours | TEL-01.03 | Dashboard toggle Online for teleconsult | New | Telemedicine | §10 + §3 | Doctor availability | Doctor sets online or offline status and working hours | Doctor Web + Doctor App | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
83 | 502 | M12 | Telemedicine | UI | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.2 | TEL-02 | Telemedicine waiting queue — who is waiting, how long, whether they have paid | TEL-02.03 | Dedicated Tele queue on dashboard (beyond E-CONSULT list) | New | Telemedicine | §10 + §3 | Telemedicine waiting queue | Doctor sees who is waiting, for how long, and whether they have paid | Doctor Web + App | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
84 | 507 | M12 | Telemedicine | UI | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.3 | TEL-03 | Video consultation in browser — doctor consults directly from the web portal | TEL-03.03 | Full-page video room mute/end | New | Telemedicine | §10 | Video consultation in browser | Doctor consults directly from the web portal | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
85 | 512 | M12 | Telemedicine | UI | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.5 | TEL-05 | Device check — camera, microphone and connection tested before joining | TEL-05.01 | Shared device-check component (web); mobile equivalent in Phase 16 | New | Telemedicine | §10 + §2.4 | Device check | Camera, microphone and connection tested before joining | Doctor Web + Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
86 | 516 | M12 | Telemedicine | UI | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.6 | TEL-06 | Waiting room — patient waits with live status until the doctor joins | TEL-06.03 | Waiting room UI on web (and app later) | New | Telemedicine | §10 + §2.4 | Waiting room | Patient waits with live status / Wait with live status until the doctor joins | Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
87 | 520 | M12 | Telemedicine | UI | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.7 | TEL-07 | Recording consent — consent captured before the consultation; no recording without it | TEL-07.03 | Pre-join modal both sides | New | Telemedicine | §10 + §2.4 + §17 | Recording consent | Consent captured before the consultation; no recording without it / Explicit consent requested before any recording | Patient + Doctor | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
88 | 523 | M12 | Telemedicine | UI | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.8 | TEL-08 | Rejoin after dropped call — either side can rejoin the same consultation | TEL-08.02 | UI Rejoin on doctor dashboard and patient waiting/call fail | New | Telemedicine | §10 + §2.4 | Rejoin after dropped call | Either side can rejoin the same consultation / Rejoin the same consultation if the connection drops | Doctor + Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
89 | 526 | M12 | Telemedicine | UI | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.9 | TEL-09 | Join failure handling — clear fallback if the call cannot connect, with options to retry | TEL-09.02 | Fallback UI: retry, rejoin, contact support | New | Telemedicine | §10 + §2.4 | Join failure handling / Fallback & join failure handling | Clear fallback if the call cannot connect / Clear guidance if the call fails, with options to retry | Doctor + Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
90 | 530 | M12 | Telemedicine | UI | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.10 | TEL-10 | Case-linked chat — chat attached to the consultation record, not a loose message thread | TEL-10.03 | In-room chat panel | New | Telemedicine | §10 + §2.4 | Case-linked chat | Chat attached to the consultation record / Chat tied to the consultation, not a loose message thread | Doctor + Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
91 | 534 | M12 | Telemedicine | UI | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.11 | TEL-11 | Consultation summary — issued to the patient at the end of the call | TEL-11.03 | Post-call summary form; patient view | New | Telemedicine | §10 + §2.4 | Consultation summary | Issued to the patient at the end of the call / Written summary available immediately after the call | Patient + Doctor | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
92 | 538 | M12 | Telemedicine | UI | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.12 | TEL-12 | Instant consultation — patient requests an immediate consultation with an available doctor | TEL-12.03 | Patient instant CTA; doctor offer banner | New | Telemedicine | §10 + §2.3 | Instant consultation / Instant consult request / Queue & doctor offer | Patient can request an immediate consultation with an available doctor / See position in queue and accept an offered doctor | Patient + Doctor | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
93 | 542 | M13 | Communications | UI | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.1 | COM-01 | SMS — appointment confirmation, registration confirmation, doctor-unavailable, OTP, reschedule and cancellation | COM-01.03 | Doctor /doctor/sms enable-per-event; admin templates | New | Notifications | §14 | SMS | Appointment confirmation, registration confirmation, doctor-unavailable notice, OTP, reschedule and cancellation alerts | Shared | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
94 | 547 | M13 | Communications | UI | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.2 | COM-02 | WhatsApp — templates, offers, health tips and bulk messaging with delivery reports and opt-out (complete remaining ~50%) | COM-02.03 | WhatsAppModal: campaign status, failures, opt-out | Existing Improvement | Notifications | §14 | WhatsApp | Templates, offers, health tips and bulk messaging to patients, with delivery reports and opt-out | Doctor Web | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
95 | 551 | M13 | Communications | UI | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.3 | COM-03 | Push notifications — booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests | COM-03.03 | Server event hooks (apps consume in 16–17) | New | Notifications | §14 + §2.9 + §3 | Push notifications | Booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests / Patient waiting, new booking, reschedule, cancellation, refill request, payment received | Patient App + Doctor App | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
96 | 556 | M13 | Communications | UI | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.4 | COM-04 | Email — registration, activation, password reset, invoices and receipts | COM-04.03 | No new public page — transactional only | Existing Improvement | Notifications | §14 | Email | Registration, activation, password reset, invoices and receipts | Shared | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
97 | 560 | M13 | Communications | UI | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.5 | COM-05 | In-app notification centre — all alerts collected in one place for patients and doctors | COM-05.03 | Doctor web bell; patient/doctor app centres in 16–17 | New | Notifications | §14 + §2.8 | In-app notification centre / Notifications centre | All alerts collected in one place for patients and doctors / All alerts in one place | Patient App + Doctor Web/App | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
98 | 564 | M14 | Support & help desk | UI | 13 | Phase 13 — Support & help desk (PDF §15) | 13.1 | SUP-01 | Patient support tickets — patients raise issues from the app and track them | SUP-01.03 | Patient app screens in Phase 16; web help optional | New | Support | §15 + §2.9 | Patient support tickets / Help centre & support tickets | Patients raise issues from the app and track them to resolution | Patient App + Admin | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
99 | 567 | M14 | Support & help desk | UI | 13 | Phase 13 — Support & help desk (PDF §15) | 13.2 | SUP-02 | Doctor support tickets — doctors raise issues from the portal | SUP-02.02 | /doctor/support list/create/detail | New | Support | §15 | Doctor support tickets | Doctors raise issues from the portal | Doctor Web + Admin | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
100 | 571 | M14 | Support & help desk | UI | 13 | Phase 13 — Support & help desk (PDF §15) | 13.3 | SUP-03 | Admin issue queue — all issues in one queue with priority, assignment and status | SUP-03.03 | /admin/support-tickets and /:id | New | Support | §15 + §7.2 | Admin issue queue / Support ticket queue | All issues in one queue with priority, assignment and status / All patient and doctor issues in one queue with assignment and resolution | Admin Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
101 | 574 | M14 | Support & help desk | UI | 13 | Phase 13 — Support & help desk (PDF §15) | 13.4 | SUP-04 | Ticket conversation — full message thread with attachments | SUP-04.02 | Detail UI thread | New | Support | §15 | Ticket conversation | Full message thread with attachments | Admin + Doctor + Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
102 | 576 | M14 | Support & help desk | UI | 13 | Phase 13 — Support & help desk (PDF §15) | 13.5 | SUP-05 | Enquiry management — website enquiries tracked (ties WEB-06) | SUP-05.01 | Admin enquiry inbox SLA fields | Existing Improvement | Support | §15 + §4 | Enquiry management | Website enquiries reach the admin team and are tracked | Admin Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
103 | 580 | M14 | Support & help desk | UI | 13 | Phase 13 — Support & help desk (PDF §15) | 13.6 | SUP-06 | Help centre — self-service help content for patients | SUP-06.03 | Help centre list/detail | New | Support | §15 + §2.9 | Help centre | Self-service help content for patients | Patient Website + App | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
104 | 584 | M14 | Support & help desk | UI | 13 | Phase 13 — Support & help desk (PDF §15) | 13.7 | SUP-07 | Assisted booking — help for patients who need support booking | SUP-07.03 | Patient CTA; admin/reception assisted-book wizard | New | Support | §15 + §2.9 | Assisted booking | Support for patients who need help booking / Help for patients who need support booking | Support + Reception + Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
105 | 588 | M15 | HomeoMeds | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.1 | MED-01 | Pharmacy partner onboarding — licensed premises, licence records, activation checklist | MED-01.03 | /pharmacy/onboard; /admin pharmacy partners | New | HomeoMeds | §12 + §7.2 | Pharmacy partner onboarding / Pharmacy partner management | Licensed premises registered with licence records and an activation checklist / Onboard and activate licensed pharmacies | Pharmacy + Admin | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
106 | 591 | M15 | HomeoMeds | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.2 | MED-02 | Licence gating — expired or suspended licences blocked automatically from receiving orders | MED-02.02 | Pharmacy console status banner | New | HomeoMeds | §12 | Licence gating | Pharmacies with expired or suspended licences are blocked automatically from receiving orders | Backend | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
107 | 595 | M15 | HomeoMeds | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.3 | MED-03 | Fulfilment consent & pharmacy selection — patient chooses the seller and consents before the prescription is shared | MED-03.03 | Patient pharmacy pick UI (web optional + app Phase 16) | New | HomeoMeds | §12 + §2.7 | Fulfilment consent & pharmacy selection | The patient chooses the seller and consents before the prescription is shared | Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
108 | 599 | M15 | HomeoMeds | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.4 | MED-04 | Prescription handoff — signed prescription becomes the order directly — no re-entry, no transcription errors | MED-04.03 | Order start from patient eRx screen | New | HomeoMeds | §12 + §2.7 | Prescription handoff / Order start | The signed prescription becomes the order directly — no re-entry, no transcription errors / Start an order directly from the prescription | Patient + Pharmacy | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
109 | 603 | M15 | HomeoMeds | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.5 | MED-05 | Rule-based seller routing — licence validity, service area, working hours and capacity | MED-05.03 | Admin/pharmacy hours and area config UI | New | HomeoMeds | §12 | Rule-based seller routing | Orders routed by licence validity, service area, working hours and capacity | Backend | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
110 | 606 | M15 | HomeoMeds | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.6 | MED-06 | Manual stock confirmation — pharmacy confirms availability — no live inventory integration required | MED-06.02 | Pharmacy UI confirm availability | New | HomeoMeds | §12 | Manual stock confirmation | The pharmacy confirms availability — no live inventory integration required | Pharmacy console | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
111 | 610 | M15 | HomeoMeds | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.7 | MED-07 | Pharmacy console — accept or reject, enter price quote, mark ready and dispatched | MED-07.03 | /pharmacy/orders and detail | New | HomeoMeds | §12 | Pharmacy console | Accept or reject orders, enter the price quote, mark ready and dispatched | Pharmacy console | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
112 | 615 | M15 | HomeoMeds | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.8 | MED-08 | Quote before payment — the patient always sees the price before paying | MED-08.03 | Patient quote screen | New | HomeoMeds | §12 + §2.7 | Quote before payment / Pharmacy selection & quote | The patient always sees the price before paying / Choose a licensed pharmacy and see the price before paying | Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
113 | 618 | M15 | HomeoMeds | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.9 | MED-09 | Payment or cash on delivery — both options, with status tracking | MED-09.02 | Patient pay vs COD UI | New | HomeoMeds | §12 + §9 | Payment or cash on delivery | Both options supported, with status tracking | Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
114 | 622 | M15 | HomeoMeds | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.10 | MED-10 | Order tracking — live status for the patient at every stage | MED-10.03 | Tracking UI | New | HomeoMeds | §12 + §2.7 | Order tracking | Live status for the patient at every stage / Live status from accepted to delivered | Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
115 | 629 | M15 | HomeoMeds | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.12 | MED-12 | Order exception queue — stuck, rejected or failed orders always surfaced — never silent | MED-12.03 | /admin/homemeds-exceptions | New | HomeoMeds | §12 | Order exception queue | Stuck, rejected or failed orders are always surfaced to the operations team — never silent | Admin + Account | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
116 | 634 | M15 | HomeoMeds | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.14 | MED-14 | Refill orders — repeat orders raised from an existing prescription | MED-14.02 | Patient order detail + refill CTA | New | HomeoMeds | §12 + §2.7 + §11 | Refill orders / Order detail & refill | Repeat orders raised from an existing prescription / Full order history and one-tap refill request | Patient + Doctor | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
117 | 636 | M15 | HomeoMeds | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.15 | MED-15 | Order review & consent (patient) — confirm and consent before the prescription is shared | MED-15.01 | Patient review screen before handoff | New | HomeoMeds | §2.7 | Order review & consent | Confirm and consent before the prescription is shared | Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
118 | 639 | M15 | HomeoMeds | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.16 | MED-16 | Medicines tab — all medicine orders in one place (API now; app UI in Phase 16) | MED-16.02 | Optional web list; mobile tab later | New | HomeoMeds | §2.7 | Medicines tab | All medicine orders in one place | Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
119 | 643 | M16 | Patient continuity APIs | UI | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.1 | CON-01 | Family members — add family members under one account | CON-01.03 | Consumed in Phase 16 | New | Patient identity | §2.1 | Family members | Add family members under one account | Patient App (API now) | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
120 | 647 | M16 | Patient continuity APIs | UI | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.2 | CON-02 | Caregiver authorization — let a family member book and manage on their behalf | CON-02.03 | Consumed in Phase 16 | New | Patient identity | §2.1 | Caregiver authorization | Let a family member book and manage on their behalf | Patient App (API now) | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
121 | 652 | M16 | Patient continuity APIs | UI | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.3 | CON-03 | Records timeline + consultation note + document upload APIs | CON-03.03 | Consumed in Phase 16 | New | Patient records | §2.5 | Records timeline / Consultation note / Document upload | Complete visit history in date order / Doctor’s notes for each visit / Upload reports, scans and previous prescriptions | Patient App (API now) | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
122 | 656 | M16 | Patient continuity APIs | UI | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.4 | CON-04 | Follow-up plan & tasks — clear next steps after each consultation | CON-04.03 | Doctor board follow-up panel; app in Phase 16 | New | Continuity | §2.6 | Follow-up plan & tasks | Clear next steps after each consultation | Doctor Web + Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
123 | 660 | M16 | Patient continuity APIs | UI | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.5 | CON-05 | Symptom diary — record symptoms between visits | CON-05.03 | Doctor board read-only; app write Phase 16 | New | Continuity | §2.6 | Symptom diary | Record symptoms between visits | Patient App (API now) | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
124 | 664 | M16 | Patient continuity APIs | UI | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.6 | CON-06 | Progress tracking — see improvement over time across visits | CON-06.03 | Consumed in Phase 16 | New | Continuity | §2.6 | Progress tracking | See improvement over time across visits | Patient + Doctor | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
125 | 668 | M16 | Patient continuity APIs | UI | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.7 | CON-07 | Consent centre & data rights — view, manage and withdraw consents; request data | CON-07.03 | Consumed in Phase 16 | New | Privacy | §17 + §2.8 | Consent centre & data rights | Patients can view, manage and withdraw consent / View, manage and withdraw consents; request data | Patient App (API now) | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
126 | 676 | M16 | Patient continuity APIs | UI | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.10 | CON-10 | Patient profile setup API — name, age, gender, contact and health basics | CON-10.03 | Consumed in Phase 16 | New | Patient identity | §2.1 | Profile setup | Name, age, gender, contact and health basics | Patient App (API now) | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
127 | 959 | M19 | Reports, NFR & delivery gate | UI | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.1 | RPT-01 | Admin overview dashboard — platform-wide activity at a glance (replace Velzon ecommerce) | RPT-01.03 | Replace pages/Admin/Dashboard; getHomeDashboardPath → /admin/dashboard | Existing Improvement | Reports | §16 + §7.2 | Admin overview dashboard / Admin dashboard | Platform-wide activity at a glance / Live overview of the whole platform | Admin Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
128 | 963 | M19 | Reports, NFR & delivery gate | UI | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.2 | RPT-02 | Doctor practice statistics — patient and consultation trends (extend existing charts) | RPT-02.03 | Dashboard charts consume new series | Existing Improvement | Reports | §16 + §5.1 | Doctor practice statistics | Patient and consultation trends | Doctor Web | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
129 | 967 | M19 | Reports, NFR & delivery gate | UI | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.3 | RPT-03 | Follow-up analysis — due/overdue patients and follow-up conversion | RPT-03.03 | /doctor/follow-up-analysis | New | Reports | §16 | Follow-up analysis | Which patients are due or overdue for follow-up, and follow-up conversion | Doctor Web | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
130 | 971 | M19 | Reports, NFR & delivery gate | UI | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.4 | RPT-04 | Clinic performance analysis — appointments, slot utilisation, no-shows, cancellations, waiting time and revenue | RPT-04.03 | /doctor/clinic-performance | New | Reports | §16 | Clinic performance analysis | Appointments, slot utilisation, no-shows, cancellations, waiting time and revenue | Doctor Web | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
131 | 974 | M19 | Reports, NFR & delivery gate | UI | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.5 | RPT-05 | Payment reconciliation report — bookings matched against payments | RPT-05.02 | Report UI on admin/account recon screens | New | Reports | §16 + §7.2 | Payment reconciliation report / Consult booking & payment reconciliation | Bookings matched against payments / Match every booking against every payment | Admin + Account | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
132 | 977 | M19 | Reports, NFR & delivery gate | UI | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.6 | RPT-06 | Settlement & payout reports — amounts due and paid to doctors and pharmacies | RPT-06.02 | Report UI | New | Reports | §16 + §8 | Settlement & payout reports | Amounts due and paid to doctors and pharmacies | Account | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
133 | 983 | M19 | Reports, NFR & delivery gate | UI | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.8 | RPT-08 | Doctor earnings summary — daily, weekly and monthly earnings with payout status (web + same API as DMO-10) | RPT-08.03 | /doctor/earnings | New | Reports | §16 + §3 | Doctor earnings summary | Daily, weekly and monthly earnings with payout status | Doctor Web + App | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
134 | 987 | M19 | Reports, NFR & delivery gate | UI | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.9 | RPT-09 | Medicine order reports — order volumes, fulfilment and exceptions | RPT-09.03 | Admin/account report page | New | Reports | §16 + §12 | Medicine order reports | Order volumes, fulfilment and exceptions | Admin + Account | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
135 | 991 | M19 | Reports, NFR & delivery gate | UI | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.10 | RPT-10 | Platform users remaining 20% — import, export and activation control | RPT-10.03 | ListUser.js wire dead buttons; verification column | Existing Improvement | Admin | §7.2 | Platform users | Manage all users with import, export and activation control | Admin Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet

## 05_Mobile
MOBILE TRACK MIRROR — live from module sheets. Mark Mobile Status on the module sheet.
Module Seq | Original Seq | Dev Module Code | Dev Module | Track | Phase | Phase Name | WBS | Main Task ID | Main Task | Sub Task ID | Sub Task | Work Type | Source Module / Area | PDF Section | PDF Feature (exact wording) | PDF Delivery Text | Application Surface | Layer | Assigned To (lead) | Frontend | Frontend Status | Frontend Assigned | Backend | Backend Status | Backend Assigned | Database | Database Status | Database Assigned | API | API Status | API Assigned | Mobile | Mobile Status | Mobile Assigned | Integration | Integration Status | Integration Assigned | Layers Remaining | Overall Status | Notes | Open Module Sheet
1 | 18 | M01 | Foundation & Security | Mobile | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.2 | FND-02 | Delivery footprint — 2 mobile apps · 5 web portals · payment · telemedicine · digital prescription · HomeoMeds (programme skeleton) | FND-02.03 | Mobile: create Patient app and Doctor app repository/bootstrap (React Native or agreed stack) — empty shells only | New | Platform | §1 | Delivery covers | 2 mobile applications · 5 web portals · payment system · telemedicine · digital prescription · online medicine delivery. | Shared | Mobile | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 1 | Not Started |  | Edit on module sheet
2 | 678 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.1 | PAT-01 | Patient app — language selection on first open | PAT-01.01 | UI: Language selection screens (empty, loading, error, offline) | New | Patient Mobile | §2.1 | Language selection | Choose preferred language on first open | Patient Mobile App | Mobile UI | Pranav Bandekar | Yes | Done | Pranav Bandekar | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Done | Pranav Bandekar | No | N/A |  | 0 | Done |  | Edit on module sheet
3 | 679 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.1 | PAT-01 | Patient app — language selection on first open | PAT-01.02 | Wire to the Phase 8–15 API for: Language selection | New | Patient Mobile | §2.1 | Language selection | Choose preferred language on first open | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
4 | 680 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.1 | PAT-01 | Patient app — language selection on first open | PAT-01.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.1 | Language selection | Choose preferred language on first open | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
5 | 682 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.2 | PAT-02 | Patient app — welcome and introduction | PAT-02.01 | UI: Welcome & introduction screens (empty, loading, error, offline) | New | Patient Mobile | §2.1 | Welcome & introduction | Guided introduction to the app | Patient Mobile App | Mobile UI | Pranav Bandekar | Yes | Done | Pranav Bandekar | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Done | Pranav Bandekar | No | N/A |  | 0 | Done |  | Edit on module sheet
6 | 683 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.2 | PAT-02 | Patient app — welcome and introduction | PAT-02.02 | Wire to the Phase 8–15 API for: Welcome & introduction | New | Patient Mobile | §2.1 | Welcome & introduction | Guided introduction to the app | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
7 | 684 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.2 | PAT-02 | Patient app — welcome and introduction | PAT-02.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.1 | Welcome & introduction | Guided introduction to the app | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
8 | 686 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.3 | PAT-03 | Patient app — mobile number + OTP login (PatientAuth) | PAT-03.01 | UI: Mobile number + OTP login screens (empty, loading, error, offline) | New | Patient Mobile | §2.1 | Mobile number + OTP login | Secure sign-in with no password to remember | Patient Mobile App | Mobile UI | Pranav Bandekar | Yes | Done | Pranav Bandekar | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Done | Pranav Bandekar | No | N/A |  | 0 | Done |  | Edit on module sheet
9 | 687 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.3 | PAT-03 | Patient app — mobile number + OTP login (PatientAuth) | PAT-03.02 | Wire to the Phase 8–15 API for: Mobile number + OTP login | New | Patient Mobile | §2.1 | Mobile number + OTP login | Secure sign-in with no password to remember | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
10 | 688 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.3 | PAT-03 | Patient app — mobile number + OTP login (PatientAuth) | PAT-03.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.1 | Mobile number + OTP login | Secure sign-in with no password to remember | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
11 | 690 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.4 | PAT-04 | Patient app — profile setup | PAT-04.01 | UI: Profile setup screens (empty, loading, error, offline) | New | Patient Mobile | §2.1 | Profile setup | Name, age, gender, contact and health basics | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
12 | 691 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.4 | PAT-04 | Patient app — profile setup | PAT-04.02 | Wire to the Phase 8–15 API for: Profile setup | New | Patient Mobile | §2.1 | Profile setup | Name, age, gender, contact and health basics | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
13 | 692 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.4 | PAT-04 | Patient app — profile setup | PAT-04.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.1 | Profile setup | Name, age, gender, contact and health basics | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
14 | 694 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.5 | PAT-05 | Patient app — privacy consent before data stored | PAT-05.01 | UI: Privacy consent screens (empty, loading, error, offline) | New | Patient Mobile | §2.1 | Privacy consent | Clear consent before any personal data is stored | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
15 | 695 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.5 | PAT-05 | Patient app — privacy consent before data stored | PAT-05.02 | Wire to the Phase 8–15 API for: Privacy consent | New | Patient Mobile | §2.1 | Privacy consent | Clear consent before any personal data is stored | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
16 | 696 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.5 | PAT-05 | Patient app — privacy consent before data stored | PAT-05.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.1 | Privacy consent | Clear consent before any personal data is stored | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
17 | 698 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.6 | PAT-06 | Patient app — family members | PAT-06.01 | UI: Family members screens (empty, loading, error, offline) | New | Patient Mobile | §2.1 | Family members | Add family members under one account | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
18 | 699 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.6 | PAT-06 | Patient app — family members | PAT-06.02 | Wire to the Phase 8–15 API for: Family members | New | Patient Mobile | §2.1 | Family members | Add family members under one account | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
19 | 700 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.6 | PAT-06 | Patient app — family members | PAT-06.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.1 | Family members | Add family members under one account | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
20 | 702 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.7 | PAT-07 | Patient app — caregiver authorization | PAT-07.01 | UI: Caregiver authorization screens (empty, loading, error, offline) | New | Patient Mobile | §2.1 | Caregiver authorization | Let a family member book and manage on their behalf | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
21 | 703 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.7 | PAT-07 | Patient app — caregiver authorization | PAT-07.02 | Wire to the Phase 8–15 API for: Caregiver authorization | New | Patient Mobile | §2.1 | Caregiver authorization | Let a family member book and manage on their behalf | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
22 | 704 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.7 | PAT-07 | Patient app — caregiver authorization | PAT-07.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.1 | Caregiver authorization | Let a family member book and manage on their behalf | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
23 | 706 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.8 | PAT-08 | Patient app — home dashboard | PAT-08.01 | UI: Home dashboard screens (empty, loading, error, offline) | New | Patient Mobile | §2.2 | Home dashboard | Personalised home with upcoming visits and quick actions | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
24 | 707 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.8 | PAT-08 | Patient app — home dashboard | PAT-08.02 | Wire to the Phase 8–15 API for: Home dashboard | New | Patient Mobile | §2.2 | Home dashboard | Personalised home with upcoming visits and quick actions | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
25 | 708 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.8 | PAT-08 | Patient app — home dashboard | PAT-08.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.2 | Home dashboard | Personalised home with upcoming visits and quick actions | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
26 | 710 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.9 | PAT-09 | Patient app — search and care categories | PAT-09.01 | UI: Search & care categories screens (empty, loading, error, offline) | New | Patient Mobile | §2.2 | Search & care categories | Search by name, condition or category of care | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
27 | 711 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.9 | PAT-09 | Patient app — search and care categories | PAT-09.02 | Wire to the Phase 8–15 API for: Search & care categories | New | Patient Mobile | §2.2 | Search & care categories | Search by name, condition or category of care | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
28 | 712 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.9 | PAT-09 | Patient app — search and care categories | PAT-09.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.2 | Search & care categories | Search by name, condition or category of care | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
29 | 714 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.10 | PAT-10 | Patient app — search results | PAT-10.01 | UI: Search results screens (empty, loading, error, offline) | New | Patient Mobile | §2.2 | Search results | Clear list of available doctors | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
30 | 715 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.10 | PAT-10 | Patient app — search results | PAT-10.02 | Wire to the Phase 8–15 API for: Search results | New | Patient Mobile | §2.2 | Search results | Clear list of available doctors | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
31 | 716 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.10 | PAT-10 | Patient app — search results | PAT-10.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.2 | Search results | Clear list of available doctors | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
32 | 718 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.11 | PAT-11 | Patient app — discovery filters | PAT-11.01 | UI: Filters screens (empty, loading, error, offline) | New | Patient Mobile | §2.2 | Filters | Narrow by availability, fee, experience, language and location | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
33 | 719 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.11 | PAT-11 | Patient app — discovery filters | PAT-11.02 | Wire to the Phase 8–15 API for: Filters | New | Patient Mobile | §2.2 | Filters | Narrow by availability, fee, experience, language and location | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
34 | 720 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.11 | PAT-11 | Patient app — discovery filters | PAT-11.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.2 | Filters | Narrow by availability, fee, experience, language and location | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
35 | 722 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.12 | PAT-12 | Patient app — doctor profile | PAT-12.01 | UI: Doctor profile screens (empty, loading, error, offline) | New | Patient Mobile | §2.2 | Doctor profile | Full profile with qualifications, experience and consultation fee | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
36 | 723 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.12 | PAT-12 | Patient app — doctor profile | PAT-12.02 | Wire to the Phase 8–15 API for: Doctor profile | New | Patient Mobile | §2.2 | Doctor profile | Full profile with qualifications, experience and consultation fee | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
37 | 724 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.12 | PAT-12 | Patient app — doctor profile | PAT-12.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.2 | Doctor profile | Full profile with qualifications, experience and consultation fee | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
38 | 726 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.13 | PAT-13 | Patient app — verified badge on doctor | PAT-13.01 | UI: Credentials & verification screens (empty, loading, error, offline) | New | Patient Mobile | §2.2 | Credentials & verification | Verified badge showing the doctor’s credentials are checked | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
39 | 727 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.13 | PAT-13 | Patient app — verified badge on doctor | PAT-13.02 | Wire to the Phase 8–15 API for: Credentials & verification | New | Patient Mobile | §2.2 | Credentials & verification | Verified badge showing the doctor’s credentials are checked | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
40 | 728 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.13 | PAT-13 | Patient app — verified badge on doctor | PAT-13.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.2 | Credentials & verification | Verified badge showing the doctor’s credentials are checked | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
41 | 730 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.14 | PAT-14 | Patient app — ranking explanation | PAT-14.01 | UI: Ranking explanation screens (empty, loading, error, offline) | New | Patient Mobile | §2.2 | Ranking explanation | Transparent explanation of why doctors appear in a given order | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
42 | 731 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.14 | PAT-14 | Patient app — ranking explanation | PAT-14.02 | Wire to the Phase 8–15 API for: Ranking explanation | New | Patient Mobile | §2.2 | Ranking explanation | Transparent explanation of why doctors appear in a given order | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
43 | 732 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.14 | PAT-14 | Patient app — ranking explanation | PAT-14.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.2 | Ranking explanation | Transparent explanation of why doctors appear in a given order | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
44 | 734 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.15 | PAT-15 | Patient app — health articles | PAT-15.01 | UI: Health articles screens (empty, loading, error, offline) | New | Patient Mobile | §2.2 | Health articles | Educational content to build trust and engagement | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
45 | 735 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.15 | PAT-15 | Patient app — health articles | PAT-15.02 | Wire to the Phase 8–15 API for: Health articles | New | Patient Mobile | §2.2 | Health articles | Educational content to build trust and engagement | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
46 | 736 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.15 | PAT-15 | Patient app — health articles | PAT-15.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.2 | Health articles | Educational content to build trust and engagement | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
47 | 738 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.16 | PAT-16 | Patient app — slot picker | PAT-16.01 | UI: Slot picker screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Slot picker | See real available time slots and choose one | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
48 | 739 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.16 | PAT-16 | Patient app — slot picker | PAT-16.02 | Wire to the Phase 8–15 API for: Slot picker | New | Patient Mobile | §2.3 | Slot picker | See real available time slots and choose one | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
49 | 740 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.16 | PAT-16 | Patient app — slot picker | PAT-16.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Slot picker | See real available time slots and choose one | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
50 | 742 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.17 | PAT-17 | Patient app — booking review and consent | PAT-17.01 | UI: Booking review & consent screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Booking review & consent | Confirm details and consent before booking | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
51 | 743 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.17 | PAT-17 | Patient app — booking review and consent | PAT-17.02 | Wire to the Phase 8–15 API for: Booking review & consent | New | Patient Mobile | §2.3 | Booking review & consent | Confirm details and consent before booking | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
52 | 744 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.17 | PAT-17 | Patient app — booking review and consent | PAT-17.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Booking review & consent | Confirm details and consent before booking | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
53 | 746 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.18 | PAT-18 | Patient app — checkout | PAT-18.01 | UI: Checkout screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Checkout | Pay the consultation fee inside the app | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
54 | 747 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.18 | PAT-18 | Patient app — checkout | PAT-18.02 | Wire to the Phase 8–15 API for: Checkout | New | Patient Mobile | §2.3 | Checkout | Pay the consultation fee inside the app | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
55 | 748 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.18 | PAT-18 | Patient app — checkout | PAT-18.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Checkout | Pay the consultation fee inside the app | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
56 | 750 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.19 | PAT-19 | Patient app — payment status | PAT-19.01 | UI: Payment status screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Payment status | Immediate confirmation of paid, pending or failed | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
57 | 751 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.19 | PAT-19 | Patient app — payment status | PAT-19.02 | Wire to the Phase 8–15 API for: Payment status | New | Patient Mobile | §2.3 | Payment status | Immediate confirmation of paid, pending or failed | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
58 | 752 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.19 | PAT-19 | Patient app — payment status | PAT-19.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Payment status | Immediate confirmation of paid, pending or failed | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
59 | 754 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.20 | PAT-20 | Patient app — appointment detail | PAT-20.01 | UI: Appointment detail screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Appointment detail | Full booking details in one place | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
60 | 755 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.20 | PAT-20 | Patient app — appointment detail | PAT-20.02 | Wire to the Phase 8–15 API for: Appointment detail | New | Patient Mobile | §2.3 | Appointment detail | Full booking details in one place | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
61 | 756 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.20 | PAT-20 | Patient app — appointment detail | PAT-20.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Appointment detail | Full booking details in one place | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
62 | 758 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.21 | PAT-21 | Patient app — reschedule | PAT-21.01 | UI: Reschedule appointment screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Reschedule appointment | Move to another slot without calling the clinic | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
63 | 759 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.21 | PAT-21 | Patient app — reschedule | PAT-21.02 | Wire to the Phase 8–15 API for: Reschedule appointment | New | Patient Mobile | §2.3 | Reschedule appointment | Move to another slot without calling the clinic | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
64 | 760 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.21 | PAT-21 | Patient app — reschedule | PAT-21.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Reschedule appointment | Move to another slot without calling the clinic | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
65 | 762 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.22 | PAT-22 | Patient app — cancel | PAT-22.01 | UI: Cancel appointment screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Cancel appointment | Cancel with reason, refund handled per policy | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
66 | 763 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.22 | PAT-22 | Patient app — cancel | PAT-22.02 | Wire to the Phase 8–15 API for: Cancel appointment | New | Patient Mobile | §2.3 | Cancel appointment | Cancel with reason, refund handled per policy | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
67 | 764 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.22 | PAT-22 | Patient app — cancel | PAT-22.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Cancel appointment | Cancel with reason, refund handled per policy | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
68 | 766 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.23 | PAT-23 | Patient app — waitlist offer | PAT-23.01 | UI: Waitlist offer screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Waitlist offer | Get offered a slot when one is freed by a cancellation | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
69 | 767 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.23 | PAT-23 | Patient app — waitlist offer | PAT-23.02 | Wire to the Phase 8–15 API for: Waitlist offer | New | Patient Mobile | §2.3 | Waitlist offer | Get offered a slot when one is freed by a cancellation | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
70 | 768 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.23 | PAT-23 | Patient app — waitlist offer | PAT-23.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Waitlist offer | Get offered a slot when one is freed by a cancellation | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
71 | 770 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.24 | PAT-24 | Patient app — instant consult request | PAT-24.01 | UI: Instant consult request screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Instant consult request | Request an immediate consultation with an available doctor | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
72 | 771 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.24 | PAT-24 | Patient app — instant consult request | PAT-24.02 | Wire to the Phase 8–15 API for: Instant consult request | New | Patient Mobile | §2.3 | Instant consult request | Request an immediate consultation with an available doctor | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
73 | 772 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.24 | PAT-24 | Patient app — instant consult request | PAT-24.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Instant consult request | Request an immediate consultation with an available doctor | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
74 | 774 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.25 | PAT-25 | Patient app — queue and doctor offer | PAT-25.01 | UI: Queue & doctor offer screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Queue & doctor offer | See position in queue and accept an offered doctor | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
75 | 775 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.25 | PAT-25 | Patient app — queue and doctor offer | PAT-25.02 | Wire to the Phase 8–15 API for: Queue & doctor offer | New | Patient Mobile | §2.3 | Queue & doctor offer | See position in queue and accept an offered doctor | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
76 | 776 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.25 | PAT-25 | Patient app — queue and doctor offer | PAT-25.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Queue & doctor offer | See position in queue and accept an offered doctor | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
77 | 778 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.26 | PAT-26 | Patient app — device check | PAT-26.01 | UI: Device check screens (empty, loading, error, offline) | New | Patient Mobile | §2.4 | Device check | Camera, microphone and network checked before the call | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
78 | 779 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.26 | PAT-26 | Patient app — device check | PAT-26.02 | Wire to the Phase 8–15 API for: Device check | New | Patient Mobile | §2.4 | Device check | Camera, microphone and network checked before the call | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
79 | 780 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.26 | PAT-26 | Patient app — device check | PAT-26.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.4 | Device check | Camera, microphone and network checked before the call | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
80 | 782 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.27 | PAT-27 | Patient app — waiting room | PAT-27.01 | UI: Waiting room screens (empty, loading, error, offline) | New | Patient Mobile | §2.4 | Waiting room | Wait with live status until the doctor joins | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
81 | 783 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.27 | PAT-27 | Patient app — waiting room | PAT-27.02 | Wire to the Phase 8–15 API for: Waiting room | New | Patient Mobile | §2.4 | Waiting room | Wait with live status until the doctor joins | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
82 | 784 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.27 | PAT-27 | Patient app — waiting room | PAT-27.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.4 | Waiting room | Wait with live status until the doctor joins | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
83 | 786 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.28 | PAT-28 | Patient app — live video | PAT-28.01 | UI: Live video consultation screens (empty, loading, error, offline) | New | Patient Mobile | §2.4 | Live video consultation | Face-to-face consultation from home | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
84 | 787 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.28 | PAT-28 | Patient app — live video | PAT-28.02 | Wire to the Phase 8–15 API for: Live video consultation | New | Patient Mobile | §2.4 | Live video consultation | Face-to-face consultation from home | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
85 | 788 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.28 | PAT-28 | Patient app — live video | PAT-28.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.4 | Live video consultation | Face-to-face consultation from home | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
86 | 790 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.29 | PAT-29 | Patient app — recording consent | PAT-29.01 | UI: Recording consent screens (empty, loading, error, offline) | New | Patient Mobile | §2.4 | Recording consent | Explicit consent requested before any recording | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
87 | 791 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.29 | PAT-29 | Patient app — recording consent | PAT-29.02 | Wire to the Phase 8–15 API for: Recording consent | New | Patient Mobile | §2.4 | Recording consent | Explicit consent requested before any recording | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
88 | 792 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.29 | PAT-29 | Patient app — recording consent | PAT-29.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.4 | Recording consent | Explicit consent requested before any recording | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
89 | 794 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.30 | PAT-30 | Patient app — join failure fallback | PAT-30.01 | UI: Fallback & join failure handling screens (empty, loading, error, offline) | New | Patient Mobile | §2.4 | Fallback & join failure handling | Clear guidance if the call fails, with options to retry | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
90 | 795 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.30 | PAT-30 | Patient app — join failure fallback | PAT-30.02 | Wire to the Phase 8–15 API for: Fallback & join failure handling | New | Patient Mobile | §2.4 | Fallback & join failure handling | Clear guidance if the call fails, with options to retry | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
91 | 796 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.30 | PAT-30 | Patient app — join failure fallback | PAT-30.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.4 | Fallback & join failure handling | Clear guidance if the call fails, with options to retry | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
92 | 798 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.31 | PAT-31 | Patient app — case-linked chat | PAT-31.01 | UI: Case-linked chat screens (empty, loading, error, offline) | New | Patient Mobile | §2.4 | Case-linked chat | Chat tied to the consultation, not a loose message thread | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
93 | 799 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.31 | PAT-31 | Patient app — case-linked chat | PAT-31.02 | Wire to the Phase 8–15 API for: Case-linked chat | New | Patient Mobile | §2.4 | Case-linked chat | Chat tied to the consultation, not a loose message thread | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
94 | 800 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.31 | PAT-31 | Patient app — case-linked chat | PAT-31.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.4 | Case-linked chat | Chat tied to the consultation, not a loose message thread | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
95 | 802 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.32 | PAT-32 | Patient app — consultation summary | PAT-32.01 | UI: Consultation summary screens (empty, loading, error, offline) | New | Patient Mobile | §2.4 | Consultation summary | Written summary available immediately after the call | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
96 | 803 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.32 | PAT-32 | Patient app — consultation summary | PAT-32.02 | Wire to the Phase 8–15 API for: Consultation summary | New | Patient Mobile | §2.4 | Consultation summary | Written summary available immediately after the call | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
97 | 804 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.32 | PAT-32 | Patient app — consultation summary | PAT-32.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.4 | Consultation summary | Written summary available immediately after the call | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
98 | 806 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.33 | PAT-33 | Patient app — rejoin | PAT-33.01 | UI: Rejoin after dropped call screens (empty, loading, error, offline) | New | Patient Mobile | §2.4 | Rejoin after dropped call | Rejoin the same consultation if the connection drops | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
99 | 807 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.33 | PAT-33 | Patient app — rejoin | PAT-33.02 | Wire to the Phase 8–15 API for: Rejoin after dropped call | New | Patient Mobile | §2.4 | Rejoin after dropped call | Rejoin the same consultation if the connection drops | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
100 | 808 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.33 | PAT-33 | Patient app — rejoin | PAT-33.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.4 | Rejoin after dropped call | Rejoin the same consultation if the connection drops | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
101 | 810 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.34 | PAT-34 | Patient app — records timeline | PAT-34.01 | UI: Records timeline screens (empty, loading, error, offline) | New | Patient Mobile | §2.5 | Records timeline | Complete visit history in date order | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
102 | 811 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.34 | PAT-34 | Patient app — records timeline | PAT-34.02 | Wire to the Phase 8–15 API for: Records timeline | New | Patient Mobile | §2.5 | Records timeline | Complete visit history in date order | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
103 | 812 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.34 | PAT-34 | Patient app — records timeline | PAT-34.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.5 | Records timeline | Complete visit history in date order | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
104 | 814 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.35 | PAT-35 | Patient app — consultation note (summary, not private notes) | PAT-35.01 | UI: Consultation note screens (empty, loading, error, offline) | New | Patient Mobile | §2.5 | Consultation note | Doctor’s notes for each visit | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
105 | 815 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.35 | PAT-35 | Patient app — consultation note (summary, not private notes) | PAT-35.02 | Wire to the Phase 8–15 API for: Consultation note | New | Patient Mobile | §2.5 | Consultation note | Doctor’s notes for each visit | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
106 | 816 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.35 | PAT-35 | Patient app — consultation note (summary, not private notes) | PAT-35.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.5 | Consultation note | Doctor’s notes for each visit | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
107 | 818 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.36 | PAT-36 | Patient app — signed eRx (codes until pharmacy accept) | PAT-36.01 | UI: Signed digital prescription screens (empty, loading, error, offline) | New | Patient Mobile | §2.5 | Signed digital prescription | Official prescription issued by the doctor | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
108 | 819 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.36 | PAT-36 | Patient app — signed eRx (codes until pharmacy accept) | PAT-36.02 | Wire to the Phase 8–15 API for: Signed digital prescription | New | Patient Mobile | §2.5 | Signed digital prescription | Official prescription issued by the doctor | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
109 | 820 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.36 | PAT-36 | Patient app — signed eRx (codes until pharmacy accept) | PAT-36.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.5 | Signed digital prescription | Official prescription issued by the doctor | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
110 | 822 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.37 | PAT-37 | Patient app — document upload | PAT-37.01 | UI: Document upload screens (empty, loading, error, offline) | New | Patient Mobile | §2.5 | Document upload | Upload reports, scans and previous prescriptions | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
111 | 823 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.37 | PAT-37 | Patient app — document upload | PAT-37.02 | Wire to the Phase 8–15 API for: Document upload | New | Patient Mobile | §2.5 | Document upload | Upload reports, scans and previous prescriptions | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
112 | 824 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.37 | PAT-37 | Patient app — document upload | PAT-37.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.5 | Document upload | Upload reports, scans and previous prescriptions | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
113 | 826 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.38 | PAT-38 | Patient app — follow-up plan and tasks | PAT-38.01 | UI: Follow-up plan & tasks screens (empty, loading, error, offline) | New | Patient Mobile | §2.6 | Follow-up plan & tasks | Clear next steps after each consultation | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
114 | 827 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.38 | PAT-38 | Patient app — follow-up plan and tasks | PAT-38.02 | Wire to the Phase 8–15 API for: Follow-up plan & tasks | New | Patient Mobile | §2.6 | Follow-up plan & tasks | Clear next steps after each consultation | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
115 | 828 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.38 | PAT-38 | Patient app — follow-up plan and tasks | PAT-38.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.6 | Follow-up plan & tasks | Clear next steps after each consultation | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
116 | 830 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.39 | PAT-39 | Patient app — symptom diary | PAT-39.01 | UI: Symptom diary screens (empty, loading, error, offline) | New | Patient Mobile | §2.6 | Symptom diary | Record symptoms between visits | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
117 | 831 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.39 | PAT-39 | Patient app — symptom diary | PAT-39.02 | Wire to the Phase 8–15 API for: Symptom diary | New | Patient Mobile | §2.6 | Symptom diary | Record symptoms between visits | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
118 | 832 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.39 | PAT-39 | Patient app — symptom diary | PAT-39.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.6 | Symptom diary | Record symptoms between visits | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
119 | 834 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.40 | PAT-40 | Patient app — progress tracking | PAT-40.01 | UI: Progress tracking screens (empty, loading, error, offline) | New | Patient Mobile | §2.6 | Progress tracking | See improvement over time across visits | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
120 | 835 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.40 | PAT-40 | Patient app — progress tracking | PAT-40.02 | Wire to the Phase 8–15 API for: Progress tracking | New | Patient Mobile | §2.6 | Progress tracking | See improvement over time across visits | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
121 | 836 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.40 | PAT-40 | Patient app — progress tracking | PAT-40.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.6 | Progress tracking | See improvement over time across visits | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
122 | 838 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.41 | PAT-41 | Patient app — medicines tab | PAT-41.01 | UI: Medicines tab screens (empty, loading, error, offline) | New | Patient Mobile | §2.7 | Medicines tab | All medicine orders in one place | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
123 | 839 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.41 | PAT-41 | Patient app — medicines tab | PAT-41.02 | Wire to the Phase 8–15 API for: Medicines tab | New | Patient Mobile | §2.7 | Medicines tab | All medicine orders in one place | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
124 | 840 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.41 | PAT-41 | Patient app — medicines tab | PAT-41.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.7 | Medicines tab | All medicine orders in one place | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
125 | 842 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.42 | PAT-42 | Patient app — start HomeoMeds order from eRx | PAT-42.01 | UI: Order start screens (empty, loading, error, offline) | New | Patient Mobile | §2.7 | Order start | Start an order directly from the prescription | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
126 | 843 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.42 | PAT-42 | Patient app — start HomeoMeds order from eRx | PAT-42.02 | Wire to the Phase 8–15 API for: Order start | New | Patient Mobile | §2.7 | Order start | Start an order directly from the prescription | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
127 | 844 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.42 | PAT-42 | Patient app — start HomeoMeds order from eRx | PAT-42.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.7 | Order start | Start an order directly from the prescription | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
128 | 846 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.43 | PAT-43 | Patient app — pharmacy selection and quote | PAT-43.01 | UI: Pharmacy selection & quote screens (empty, loading, error, offline) | New | Patient Mobile | §2.7 | Pharmacy selection & quote | Choose a licensed pharmacy and see the price before paying | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
129 | 847 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.43 | PAT-43 | Patient app — pharmacy selection and quote | PAT-43.02 | Wire to the Phase 8–15 API for: Pharmacy selection & quote | New | Patient Mobile | §2.7 | Pharmacy selection & quote | Choose a licensed pharmacy and see the price before paying | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
130 | 848 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.43 | PAT-43 | Patient app — pharmacy selection and quote | PAT-43.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.7 | Pharmacy selection & quote | Choose a licensed pharmacy and see the price before paying | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
131 | 850 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.44 | PAT-44 | Patient app — order review and consent | PAT-44.01 | UI: Order review & consent screens (empty, loading, error, offline) | New | Patient Mobile | §2.7 | Order review & consent | Confirm and consent before the prescription is shared | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
132 | 851 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.44 | PAT-44 | Patient app — order review and consent | PAT-44.02 | Wire to the Phase 8–15 API for: Order review & consent | New | Patient Mobile | §2.7 | Order review & consent | Confirm and consent before the prescription is shared | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
133 | 852 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.44 | PAT-44 | Patient app — order review and consent | PAT-44.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.7 | Order review & consent | Confirm and consent before the prescription is shared | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
134 | 854 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.45 | PAT-45 | Patient app — order tracking | PAT-45.01 | UI: Order tracking screens (empty, loading, error, offline) | New | Patient Mobile | §2.7 | Order tracking | Live status from accepted to delivered | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
135 | 855 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.45 | PAT-45 | Patient app — order tracking | PAT-45.02 | Wire to the Phase 8–15 API for: Order tracking | New | Patient Mobile | §2.7 | Order tracking | Live status from accepted to delivered | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
136 | 856 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.45 | PAT-45 | Patient app — order tracking | PAT-45.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.7 | Order tracking | Live status from accepted to delivered | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
137 | 858 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.46 | PAT-46 | Patient app — order detail and refill | PAT-46.01 | UI: Order detail & refill screens (empty, loading, error, offline) | New | Patient Mobile | §2.7 | Order detail & refill | Full order history and one-tap refill request | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
138 | 859 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.46 | PAT-46 | Patient app — order detail and refill | PAT-46.02 | Wire to the Phase 8–15 API for: Order detail & refill | New | Patient Mobile | §2.7 | Order detail & refill | Full order history and one-tap refill request | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
139 | 860 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.46 | PAT-46 | Patient app — order detail and refill | PAT-46.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.7 | Order detail & refill | Full order history and one-tap refill request | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
140 | 862 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.47 | PAT-47 | Patient app — write a review | PAT-47.01 | UI: Write a review screens (empty, loading, error, offline) | New | Patient Mobile | §2.8 | Write a review | Rate and review the consultation | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
141 | 863 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.47 | PAT-47 | Patient app — write a review | PAT-47.02 | Wire to the Phase 8–15 API for: Write a review | New | Patient Mobile | §2.8 | Write a review | Rate and review the consultation | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
142 | 864 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.47 | PAT-47 | Patient app — write a review | PAT-47.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.8 | Write a review | Rate and review the consultation | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
143 | 866 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.48 | PAT-48 | Patient app — my reviews and appeal | PAT-48.01 | UI: My reviews & appeal screens (empty, loading, error, offline) | New | Patient Mobile | §2.8 | My reviews & appeal | Manage reviews and raise an appeal | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
144 | 867 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.48 | PAT-48 | Patient app — my reviews and appeal | PAT-48.02 | Wire to the Phase 8–15 API for: My reviews & appeal | New | Patient Mobile | §2.8 | My reviews & appeal | Manage reviews and raise an appeal | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
145 | 868 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.48 | PAT-48 | Patient app — my reviews and appeal | PAT-48.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.8 | My reviews & appeal | Manage reviews and raise an appeal | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
146 | 870 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.49 | PAT-49 | Patient app — payments and refunds | PAT-49.01 | UI: Payments & refunds screens (empty, loading, error, offline) | New | Patient Mobile | §2.8 | Payments & refunds | Full payment history and refund status | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
147 | 871 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.49 | PAT-49 | Patient app — payments and refunds | PAT-49.02 | Wire to the Phase 8–15 API for: Payments & refunds | New | Patient Mobile | §2.8 | Payments & refunds | Full payment history and refund status | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
148 | 872 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.49 | PAT-49 | Patient app — payments and refunds | PAT-49.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.8 | Payments & refunds | Full payment history and refund status | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
149 | 874 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.50 | PAT-50 | Patient app — profile and settings | PAT-50.01 | UI: Profile & settings screens (empty, loading, error, offline) | New | Patient Mobile | §2.8 | Profile & settings | Manage personal details and preferences | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
150 | 875 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.50 | PAT-50 | Patient app — profile and settings | PAT-50.02 | Wire to the Phase 8–15 API for: Profile & settings | New | Patient Mobile | §2.8 | Profile & settings | Manage personal details and preferences | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
151 | 876 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.50 | PAT-50 | Patient app — profile and settings | PAT-50.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.8 | Profile & settings | Manage personal details and preferences | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
152 | 878 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.51 | PAT-51 | Patient app — consent centre and data rights | PAT-51.01 | UI: Consent centre & data rights screens (empty, loading, error, offline) | New | Patient Mobile | §2.8 | Consent centre & data rights | View, manage and withdraw consents; request data | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
153 | 879 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.51 | PAT-51 | Patient app — consent centre and data rights | PAT-51.02 | Wire to the Phase 8–15 API for: Consent centre & data rights | New | Patient Mobile | §2.8 | Consent centre & data rights | View, manage and withdraw consents; request data | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
154 | 880 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.51 | PAT-51 | Patient app — consent centre and data rights | PAT-51.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.8 | Consent centre & data rights | View, manage and withdraw consents; request data | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
155 | 882 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.52 | PAT-52 | Patient app — notifications centre | PAT-52.01 | UI: Notifications centre screens (empty, loading, error, offline) | New | Patient Mobile | §2.8 | Notifications centre | All alerts in one place | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
156 | 883 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.52 | PAT-52 | Patient app — notifications centre | PAT-52.02 | Wire to the Phase 8–15 API for: Notifications centre | New | Patient Mobile | §2.8 | Notifications centre | All alerts in one place | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
157 | 884 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.52 | PAT-52 | Patient app — notifications centre | PAT-52.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.8 | Notifications centre | All alerts in one place | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
158 | 886 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.53 | PAT-53 | Patient app — help centre and tickets | PAT-53.01 | UI: Help centre & support tickets screens (empty, loading, error, offline) | New | Patient Mobile | §2.9 | Help centre & support tickets | Raise an issue and track it to resolution | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
159 | 887 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.53 | PAT-53 | Patient app — help centre and tickets | PAT-53.02 | Wire to the Phase 8–15 API for: Help centre & support tickets | New | Patient Mobile | §2.9 | Help centre & support tickets | Raise an issue and track it to resolution | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
160 | 888 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.53 | PAT-53 | Patient app — help centre and tickets | PAT-53.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.9 | Help centre & support tickets | Raise an issue and track it to resolution | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
161 | 890 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.54 | PAT-54 | Patient app — physical clinic booking | PAT-54.01 | UI: Physical clinic appointment screens (empty, loading, error, offline) | New | Patient Mobile | §2.9 | Physical clinic appointment | Book an in-person visit as well as online | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
162 | 891 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.54 | PAT-54 | Patient app — physical clinic booking | PAT-54.02 | Wire to the Phase 8–15 API for: Physical clinic appointment | New | Patient Mobile | §2.9 | Physical clinic appointment | Book an in-person visit as well as online | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
163 | 892 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.54 | PAT-54 | Patient app — physical clinic booking | PAT-54.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.9 | Physical clinic appointment | Book an in-person visit as well as online | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
164 | 894 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.55 | PAT-55 | Patient app — assisted booking request | PAT-55.01 | UI: Assisted booking screens (empty, loading, error, offline) | New | Patient Mobile | §2.9 | Assisted booking | Help for patients who need support booking | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
165 | 895 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.55 | PAT-55 | Patient app — assisted booking request | PAT-55.02 | Wire to the Phase 8–15 API for: Assisted booking | New | Patient Mobile | §2.9 | Assisted booking | Help for patients who need support booking | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
166 | 896 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.55 | PAT-55 | Patient app — assisted booking request | PAT-55.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.9 | Assisted booking | Help for patients who need support booking | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
167 | 898 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.56 | PAT-56 | Patient app — low-data mode | PAT-56.01 | UI: Low-data mode screens (empty, loading, error, offline) | New | Patient Mobile | §2.9 | Low-data mode | Works on slow or limited connections | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
168 | 899 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.56 | PAT-56 | Patient app — low-data mode | PAT-56.02 | Wire to the Phase 8–15 API for: Low-data mode | New | Patient Mobile | §2.9 | Low-data mode | Works on slow or limited connections | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
169 | 900 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.56 | PAT-56 | Patient app — low-data mode | PAT-56.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.9 | Low-data mode | Works on slow or limited connections | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
170 | 902 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.57 | PAT-57 | Patient app — push notifications | PAT-57.01 | UI: Push notifications screens (empty, loading, error, offline) | New | Patient Mobile | §2.9 | Push notifications | Booking confirmations, reminders, doctor ready, prescription issued, order updates | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
171 | 903 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.57 | PAT-57 | Patient app — push notifications | PAT-57.02 | Wire to the Phase 8–15 API for: Push notifications | New | Patient Mobile | §2.9 | Push notifications | Booking confirmations, reminders, doctor ready, prescription issued, order updates | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
172 | 904 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.57 | PAT-57 | Patient app — push notifications | PAT-57.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.9 | Push notifications | Booking confirmations, reminders, doctor ready, prescription issued, order updates | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
173 | 906 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.58 | PAT-58 | Patient app — iOS and Android store release, device matrix, and parity QA | PAT-58.01 | CI: iOS + Android release builds; env pointing to .NET 8 | New | Patient Mobile | §2 + §18 | Patient mobile app iOS and Android | iOS and Android — onboarding, discovery, booking, payment, video consultation, records, prescriptions, follow-up, medicines, reviews, support, notifications | Patient Mobile App | Mobile | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 1 | Not Started |  | Edit on module sheet
174 | 908 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.58 | PAT-58 | Patient app — iOS and Android store release, device matrix, and parity QA | PAT-58.03 | Crashlytics/Sentry equivalent for patient app | New Integration | Patient Mobile | §2 + §18 | Patient mobile app iOS and Android | iOS and Android — onboarding, discovery, booking, payment, video consultation, records, prescriptions, follow-up, medicines, reviews, support, notifications | Patient Mobile App | Mobile | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | 2 | Not Started |  | Edit on module sheet
175 | 909 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.1 | DMO-01 | Doctor app — login & identity (same login and same account as the web portal) | DMO-01.01 | Login screen (password or OTP-to-registered mobile) | New | Doctor Mobile | §3 | Login & identity | Same login and same account as the web portal | Doctor Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
176 | 910 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.1 | DMO-01 | Doctor app — login & identity (same login and same account as the web portal) | DMO-01.02 | Call same Login API; store JWT securely (Keychain/Keystore) | New | Doctor Mobile | §3 | Login & identity | Same login and same account as the web portal | Doctor Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
177 | 911 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.1 | DMO-01 | Doctor app — login & identity (same login and same account as the web portal) | DMO-01.03 | Expired session → re-login; no case-taking entry point | New | Doctor Mobile | §3 | Login & identity | Same login and same account as the web portal | Doctor Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
178 | 913 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.2 | DMO-02 | Doctor app — first-run onboarding (guided setup, number confirmation and permissions) | DMO-02.01 | Onboarding screens | New | Doctor Mobile | §3 | First-run onboarding | Guided setup, number confirmation and permissions | Doctor Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
179 | 914 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.2 | DMO-02 | Doctor app — first-run onboarding (guided setup, number confirmation and permissions) | DMO-02.02 | Confirm number against profile | New | Doctor Mobile | §3 | First-run onboarding | Guided setup, number confirmation and permissions | Doctor Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
180 | 915 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.2 | DMO-02 | Doctor app — first-run onboarding (guided setup, number confirmation and permissions) | DMO-02.03 | Skip vs required steps documented | New | Doctor Mobile | §3 | First-run onboarding | Guided setup, number confirmation and permissions | Doctor Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
181 | 917 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.3 | DMO-03 | Doctor app — notification permissions (push, microphone and camera handled properly) | DMO-03.01 | Permission primer + settings CTA | New | Doctor Mobile | §3 | Notification permissions | Push, microphone and camera permissions handled properly | Doctor Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
182 | 918 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.3 | DMO-03 | Doctor app — notification permissions (push, microphone and camera handled properly) | DMO-03.02 | Register FCM/APNs token (COM-03) | New | Doctor Mobile | §3 | Notification permissions | Push, microphone and camera permissions handled properly | Doctor Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
183 | 919 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.3 | DMO-03 | Doctor app — notification permissions (push, microphone and camera handled properly) | DMO-03.03 | Denied-state UX | New | Doctor Mobile | §3 | Notification permissions | Push, microphone and camera permissions handled properly | Doctor Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
184 | 921 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.4 | DMO-04 | Doctor app — today’s queue & schedule (the full day at a glance) | DMO-04.01 | TodayQueue screen | New | Doctor Mobile | §3 | Today’s queue & schedule | The full day at a glance | Doctor Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
185 | 922 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.4 | DMO-04 | Doctor app — today’s queue & schedule (the full day at a glance) | DMO-04.02 | Existing appointment list APIs | New | Doctor Mobile | §3 | Today’s queue & schedule | The full day at a glance | Doctor Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
186 | 923 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.4 | DMO-04 | Doctor app — today’s queue & schedule (the full day at a glance) | DMO-04.03 | Pull-to-refresh; empty Sunday | New | Doctor Mobile | §3 | Today’s queue & schedule | The full day at a glance | Doctor Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
187 | 925 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.5 | DMO-05 | Doctor app — availability toggle (go online or offline, set working hours) | DMO-05.01 | Availability + hours screens | New | Doctor Mobile | §3 | Availability toggle | Go online or offline, set working hours | Doctor Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
188 | 926 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.5 | DMO-05 | Doctor app — availability toggle (go online or offline, set working hours) | DMO-05.02 | TEL-01 + APT-07 APIs (hours read/edit policy: edit hours may stay web-only if product decides — PDF says set working hours so include) | New | Doctor Mobile | §3 | Availability toggle | Go online or offline, set working hours | Doctor Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
189 | 927 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.5 | DMO-05 | Doctor app — availability toggle (go online or offline, set working hours) | DMO-05.03 | Offline banner | New | Doctor Mobile | §3 | Availability toggle | Go online or offline, set working hours | Doctor Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
190 | 929 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.6 | DMO-06 | Doctor app — push notifications (waiting, booking, reschedule, cancellation, refill, payment received) | DMO-06.01 | Notification handling + deep links into queue/refill/join | New | Doctor Mobile | §3 | Push notifications | Patient waiting, new booking, reschedule, cancellation, refill request, payment received | Doctor Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
191 | 930 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.6 | DMO-06 | Doctor app — push notifications (waiting, booking, reschedule, cancellation, refill, payment received) | DMO-06.02 | Device register | New | Doctor Mobile | §3 | Push notifications | Patient waiting, new booking, reschedule, cancellation, refill request, payment received | Doctor Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
192 | 931 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.6 | DMO-06 | Doctor app — push notifications (waiting, booking, reschedule, cancellation, refill, payment received) | DMO-06.03 | Foreground in-app banner | New | Doctor Mobile | §3 | Push notifications | Patient waiting, new booking, reschedule, cancellation, refill request, payment received | Doctor Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
193 | 933 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.7 | DMO-07 | Doctor app — patient context card (name, age, chief complaint and last visit) — NO case-taking | DMO-07.01 | PatientCard read-only | New | Doctor Mobile | §3 | Patient context card | Name, age, chief complaint and last visit before joining | Doctor Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
194 | 934 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.7 | DMO-07 | Doctor app — patient context card (name, age, chief complaint and last visit) — NO case-taking | DMO-07.02 | Context API (name, age, CC, last visit, payment, tele) | New | Doctor Mobile | §3 | Patient context card | Name, age, chief complaint and last visit before joining | Doctor Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
195 | 935 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.7 | DMO-07 | Doctor app — patient context card (name, age, chief complaint and last visit) — NO case-taking | DMO-07.03 | Do not ship case-taking tabs | New | Doctor Mobile | §3 | Patient context card | Name, age, chief complaint and last visit before joining | Doctor Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
196 | 937 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.8 | DMO-08 | Doctor app — join consultation (video or audio from the phone) | DMO-08.01 | VideoRoom | New | Doctor Mobile | §3 | Join consultation | Start the video or audio consultation from the phone | Doctor Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
197 | 938 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.8 | DMO-08 | Doctor app — join consultation (video or audio from the phone) | DMO-08.02 | Tele session tokens | New | Doctor Mobile | §3 | Join consultation | Start the video or audio consultation from the phone | Doctor Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
198 | 939 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.8 | DMO-08 | Doctor app — join consultation (video or audio from the phone) | DMO-08.03 | Audio-only fallback | New | Doctor Mobile | §3 | Join consultation | Start the video or audio consultation from the phone | Doctor Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
199 | 941 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.9 | DMO-09 | Doctor app — refill approval (approve or reject repeat prescription requests) | DMO-09.01 | RefillInbox + RefillDetail | New | Doctor Mobile | §3 + §11 | Refill approval | Approve or reject repeat prescription requests | Doctor Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
200 | 942 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.9 | DMO-09 | Doctor app — refill approval (approve or reject repeat prescription requests) | DMO-09.02 | Approve/Reject APIs | New | Doctor Mobile | §3 + §11 | Refill approval | Approve or reject repeat prescription requests | Doctor Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
201 | 943 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.9 | DMO-09 | Doctor app — refill approval (approve or reject repeat prescription requests) | DMO-09.03 | Show codes vs names per policy (doctor sees names) | New | Doctor Mobile | §3 + §11 | Refill approval | Approve or reject repeat prescription requests | Doctor Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
202 | 945 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.10 | DMO-10 | Doctor app — earnings summary (today, this week, this month, with payout status) | DMO-10.01 | Earnings screens | New | Doctor Mobile | §3 + §16 | Earnings summary | Today, this week and this month, with payout status | Doctor Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
203 | 946 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.10 | DMO-10 | Doctor app — earnings summary (today, this week, this month, with payout status) | DMO-10.02 | GET Earnings/Summary | New | Doctor Mobile | §3 + §16 | Earnings summary | Today, this week and this month, with payout status | Doctor Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
204 | 947 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.10 | DMO-10 | Doctor app — earnings summary (today, this week, this month, with payout status) | DMO-10.03 | Empty first week | New | Doctor Mobile | §3 + §16 | Earnings summary | Today, this week and this month, with payout status | Doctor Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
205 | 949 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.11 | DMO-11 | Doctor app — offline handling (weak connection or expired session) | DMO-11.01 | Offline/error screens | New | Doctor Mobile | §3 | Offline handling | Clear behaviour on weak connection or expired session | Doctor Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
206 | 950 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.11 | DMO-11 | Doctor app — offline handling (weak connection or expired session) | DMO-11.02 | 401 interceptor → logout API | New | Doctor Mobile | §3 | Offline handling | Clear behaviour on weak connection or expired session | Doctor Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
207 | 951 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.11 | DMO-11 | Doctor app — offline handling (weak connection or expired session) | DMO-11.03 | No silent retry of payments | New | Doctor Mobile | §3 | Offline handling | Clear behaviour on weak connection or expired session | Doctor Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | Edit on module sheet
208 | 953 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.12 | DMO-12 | Doctor app — reliability monitoring (failures reported automatically) | DMO-12.01 | Integrate Crashlytics/Sentry; map to doctorId hashed | New Integration | Doctor Mobile | §3 | Reliability monitoring | Failures are reported automatically, not left to a phone call | Doctor Mobile App | Mobile | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | 2 | Not Started |  | Edit on module sheet
209 | 955 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.13 | DMO-13 | Doctor app — iOS and Android parity QA (queue, availability, notifications, context, video, refill, earnings) | DMO-13.01 | Release builds both OS | New | Doctor Mobile | §3 + §18 | Doctor mobile app iOS and Android | iOS and Android — queue, availability, notifications, patient context, video consultation, refill approval, earnings | Doctor Mobile App | Mobile | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 1 | Not Started |  | Edit on module sheet

## 06_QA
QA TRACK MIRROR — live from module sheets. QA rows still have Frontend/API Status where those layers are in scope.
Module Seq | Original Seq | Dev Module Code | Dev Module | Track | Phase | Phase Name | WBS | Main Task ID | Main Task | Sub Task ID | Sub Task | Work Type | Source Module / Area | PDF Section | PDF Feature (exact wording) | PDF Delivery Text | Application Surface | Layer | Assigned To (lead) | Frontend | Frontend Status | Frontend Assigned | Backend | Backend Status | Backend Assigned | Database | Database Status | Database Assigned | API | API Status | API Assigned | Mobile | Mobile Status | Mobile Assigned | Integration | Integration Status | Integration Assigned | Layers Remaining | Overall Status | Notes | Open Module Sheet
1 | 15 | M01 | Foundation & Security | QA | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.1 | FND-01 | One connected ecosystem — shared keys so a patient, appointment, prescription and payment created anywhere are visible everywhere | FND-01.04 | QA: create appointment on Reception → visible on Doctor web; pay on Patient web → same PaymentStatus on Doctor and Account (after Phase 6) | Regression | Platform | §1 | One connected ecosystem serving six types of users | A patient, an appointment, a prescription and a payment created anywhere in the system are visible everywhere else — there are no separate systems to reconcile. | Shared | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
2 | 23 | M01 | Foundation & Security | QA | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.3 | SEC-01 | Secure login — protected credentials for every user type | SEC-01.04 | QA: Admin, Doctor, Reception login; invalid password; deactivated user; SQL injection/brute-force rate limit | Regression | Security | §17 | Secure login | Protected credentials for every user type | All web + later mobile | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
3 | 27 | M01 | Foundation & Security | QA | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.4 | SEC-02 | Secure password reset — time-limited reset links (stop plaintext email + fake thunk) | SEC-02.04 | QA: expired token, reused token, unknown email (no user enumeration), logged-in change password | Regression | Security | §17 | Secure password reset | Time-limited reset links | Admin / Doctor / Reception web | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
4 | 31 | M01 | Foundation & Security | QA | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.5 | SEC-03 | Session control — proper sign-out across web and mobile | SEC-03.04 | QA: logout on one tab; expired session message; 401 interceptor | Regression | Security | §17 | Session control | Proper sign-out across web and mobile | All | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
5 | 35 | M01 | Foundation & Security | QA | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.6 | SEC-04 | Role-based access — each role sees only what it is permitted to see | SEC-04.04 | QA: Reception cannot open repertory masters; Account cannot edit diagnosis; Doctor cannot see platform-wide ledger | Regression | Security | §17 | Role-based access | Each role sees only what it is permitted to see | Admin / All web | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
6 | 38 | M01 | Foundation & Security | QA | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.7 | SEC-05 | Patient data protection — health records restricted to the treating doctor and the patient | SEC-05.03 | QA: IDOR tests (swap PatientAppId / CaseId in requests) | Regression | Security | §17 | Patient data protection | Health records restricted to the treating doctor and the patient | API | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
7 | 42 | M01 | Foundation & Security | QA | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.8 | SEC-06 | Consent records infrastructure — every consent captured, stored and reviewable | SEC-06.04 | QA: grant, withdraw, re-grant; audit log immutable | Regression | Security / Trust | §17 | Consent records | Every consent captured, stored and reviewable | Shared | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
8 | 46 | M01 | Foundation & Security | QA | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.9 | SEC-07 | OTP verification infrastructure — applied to sensitive actions including payouts and pharmacy acceptance | SEC-07.04 | QA: replay OTP, expiry, max attempts, audit completeness | Regression | Security | §17 + §8 + §12 | OTP verification | Applied to sensitive actions including payouts and pharmacy acceptance | Shared | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
9 | 49 | M01 | Foundation & Security | QA | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.10 | SEC-08 | Complete audit trail — who did what and when across payments, prescriptions and approvals | SEC-08.03 | QA: sample sign-prescription / approve-payout (when those exist) produce audit rows | Regression | Security | §17 + §9 | Complete audit trail | Who did what, and when, across payments, prescriptions and approvals / Every transaction traceable end to end by Homeocentrum | Shared | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
10 | 52 | M01 | Foundation & Security | QA | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.11 | SEC-09 | Secure documents — prescriptions, reports and uploads protected from unauthorised access | SEC-09.03 | QA: doctor of record can download; other doctor 403; anonymous 401 | Regression | Security | §17 | Secure documents | Prescriptions, reports and uploads protected from unauthorised access | Shared | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
11 | 53 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.1 | ADM-R01 | Keep and harden Admin Repertory sections (do not rebuild) | ADM-R01.01 | Regression: list / add / edit / (import-export if present) for Repertory sections | Existing | Repertory | §7.1 | Repertory sections | Manage repertory sections | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
12 | 56 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.2 | ADM-R02 | Keep and harden Admin Subsection & rubric tree (do not rebuild) | ADM-R02.01 | Regression: list / add / edit / (import-export if present) for Subsection & rubric tree | Existing | Repertory | §7.1 | Subsection & rubric tree | Manage the full rubric hierarchy | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
13 | 59 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.3 | ADM-R03 | Keep and harden Admin Rubric–remedy mapping (do not rebuild) | ADM-R03.01 | Regression: list / add / edit / (import-export if present) for Rubric–remedy mapping | Existing | Repertory | §7.1 | Rubric–remedy mapping | Map remedies to rubrics with author and grade | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
14 | 62 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.4 | ADM-R04 | Keep and harden Admin Remedy-linked rubrics (do not rebuild) | ADM-R04.01 | Regression: list / add / edit / (import-export if present) for Remedy-linked rubrics | Existing | Repertory | §7.1 | Remedy-linked rubrics | View all rubrics linked to a remedy | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
15 | 65 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.5 | ADM-R05 | Keep and harden Admin Language master (do not rebuild) | ADM-R05.01 | Regression: list / add / edit / (import-export if present) for Language master | Existing | Repertory | §7.1 | Language master | Manage languages | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
16 | 68 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.6 | ADM-R06 | Keep and harden Admin Body part master (do not rebuild) | ADM-R06.01 | Regression: list / add / edit / (import-export if present) for Body part master | Existing | Repertory | §7.1 | Body part master | Manage body parts | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
17 | 71 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.7 | ADM-R07 | Keep and harden Admin Intensity master (do not rebuild) | ADM-R07.01 | Regression: list / add / edit / (import-export if present) for Intensity master | Existing | Repertory | §7.1 | Intensity master | Manage intensity levels | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
18 | 74 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.8 | ADM-R08 | Keep and harden Admin Remedy master (do not rebuild) | ADM-R08.01 | Regression: list / add / edit / (import-export if present) for Remedy master | Existing | Repertory | §7.1 | Remedy master | Manage the remedy library | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
19 | 77 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.9 | ADM-R09 | Keep and harden Admin Remedy grade master (do not rebuild) | ADM-R09.01 | Regression: list / add / edit / (import-export if present) for Remedy grade master | Existing | Repertory | §7.1 | Remedy grade master | Manage remedy grading | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
20 | 80 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.10 | ADM-M01 | Keep and harden Admin Author master (do not rebuild) | ADM-M01.01 | Regression: list / add / edit / (import-export if present) for Author master | Existing | Materia Medica | §7.1 | Author master | Manage materia medica authors | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
21 | 83 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.11 | ADM-M02 | Keep and harden Admin Materia medica master (do not rebuild) | ADM-M02.01 | Regression: list / add / edit / (import-export if present) for Materia medica master | Existing | Materia Medica | §7.1 | Materia medica master | Manage the materia medica library | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
22 | 86 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.12 | ADM-M03 | Keep and harden Admin Materia medica heads (do not rebuild) | ADM-M03.01 | Regression: list / add / edit / (import-export if present) for Materia medica heads | Existing | Materia Medica | §7.1 | Materia medica heads | Manage chapter headings | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
23 | 89 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.13 | ADM-M04 | Keep and harden Admin Materia medica remedies (do not rebuild) | ADM-M04.01 | Regression: list / add / edit / (import-export if present) for Materia medica remedies | Existing | Materia Medica | §7.1 | Materia medica remedies | View remedy-wise materia medica | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
24 | 92 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.14 | ADM-D01 | Keep and harden Admin Diagnosis system (do not rebuild) | ADM-D01.01 | Regression: list / add / edit / (import-export if present) for Diagnosis system | Existing | Diagnosis | §7.1 | Diagnosis system | Manage diagnosis systems | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
25 | 95 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.15 | ADM-D02 | Keep and harden Admin Diagnosis therapeutics (do not rebuild) | ADM-D02.01 | Regression: list / add / edit / (import-export if present) for Diagnosis therapeutics | Existing | Diagnosis | §7.1 | Diagnosis therapeutics | Manage therapeutics | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
26 | 98 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.16 | ADM-D03 | Keep and harden Admin Diagnosis conditions (do not rebuild) | ADM-D03.01 | Regression: list / add / edit / (import-export if present) for Diagnosis conditions | Existing | Diagnosis | §7.1 | Diagnosis conditions | Manage conditions and linked rubrics | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
27 | 101 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.17 | ADM-A01 | Keep and harden Admin Drug system (do not rebuild) | ADM-A01.01 | Regression: list / add / edit / (import-export if present) for Drug system | Existing | Adverse Effect | §7.1 | Drug system | Manage conventional drug systems | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
28 | 104 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.18 | ADM-A02 | Keep and harden Admin Drug group (do not rebuild) | ADM-A02.01 | Regression: list / add / edit / (import-export if present) for Drug group | Existing | Adverse Effect | §7.1 | Drug group | Manage drug groups | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
29 | 107 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.19 | ADM-A03 | Keep and harden Admin Allopathic drug & side effects (do not rebuild) | ADM-A03.01 | Regression: list / add / edit / (import-export if present) for Allopathic drug & side effects | Existing | Adverse Effect | §7.1 | Allopathic drug & side effects | Manage drugs with side effects and adverse reactions | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
30 | 110 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.20 | ADM-Q01 | Keep and harden Admin Question section, group & sub-group (do not rebuild) | ADM-Q01.01 | Regression: list / add / edit / (import-export if present) for Question section, group & sub-group | Existing | Clinical Questions | §7.1 | Question section, group & sub-group | Manage the clinical questionnaire structure | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
31 | 113 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.21 | ADM-Q02 | Keep and harden Admin Clinical question mapping (do not rebuild) | ADM-Q02.01 | Regression: list / add / edit / (import-export if present) for Clinical question mapping | Existing | Clinical Questions | §7.1 | Clinical question mapping | Map questions to body parts and rubrics | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
32 | 116 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.22 | ADM-3D1 | Keep and harden Admin 3D mesh key master (do not rebuild) | ADM-3D1.01 | Regression: list / add / edit / (import-export if present) for 3D mesh key master | Existing | 3D Body | §7.1 | 3D mesh key master | Manage 3D model references | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
33 | 119 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.23 | ADM-3D2 | Keep and harden Admin 3D section master (do not rebuild) | ADM-3D2.01 | Regression: list / add / edit / (import-export if present) for 3D section master | Existing | 3D Body | §7.1 | 3D section master | Manage 3D body sections | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
34 | 122 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.24 | ADM-3D3 | Keep and harden Admin 3D hotspots (do not rebuild) | ADM-3D3.01 | Regression: list / add / edit / (import-export if present) for 3D hotspots | Existing | 3D Body | §7.1 | 3D hotspots | Manage clickable points on the 3D model | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
35 | 125 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.25 | ADM-B01 | Business Management — Doctor qualifications (existing, used later by credentialing) | ADM-B01.01 | Regression: qualifications list/add/edit | Existing | Business Management | §7.2 | Doctor qualifications | Manage the qualification list | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
36 | 128 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.26 | ADM-B02 | Business Management — Lab & imaging test catalog (existing, used by eRx lab orders) | ADM-B02.01 | Regression: lab catalog CRUD and doctor order pick-list | Existing | Business Management | §7.2 | Lab & imaging test catalog | Manage the test catalogue | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
37 | 131 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.27 | ADM-B03 | Business Management — Subscription packages (existing S1 SaaS; later tied to Account ledger) | ADM-B03.01 | Regression: package list/add/edit; doctor Widgets still reads packages | Existing | Business Management | §7.2 | Subscription packages | Manage doctor subscription plans | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
38 | 137 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.28 | ADM-B04 | Business Management — Roles & menu permissions (existing DB, runtime ACL leftover) | ADM-B04.04 | QA: edit role menu → user of that role no longer sees the item | Regression | Business Management | §7.2 | Roles & menu permissions | Control exactly what each role can access | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
39 | 140 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.1 | CLN-01 | Clinical workspace — single screen for the entire consultation | CLN-01.03 | Regression: open case from dashboard still remounts via PatientBoardRoute | Regression | Patient Board | §5.3 | Clinical workspace | Single screen for the entire consultation | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
40 | 141 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.2 | CLN-02 | Manual case taking — structured case taking (keep) | CLN-02.01 | Regression: create case, add rubrics via manual path, repertorize | Existing | Patient Board | §5.3 | Manual case taking | Structured case taking | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
41 | 144 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.3 | CLN-03 | Body parts & intensity selection (keep) | CLN-03.01 | Regression: body part → rubrics; intensity chip | Existing | Patient Board | §5.3 | Body parts & intensity selection | Select affected areas and severity | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
42 | 147 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.4 | CLN-04 | Clinical questions — guided questions by section, group and sub-group (keep) | CLN-04.01 | Regression: full question drill-down | Existing | Patient Board | §5.3 | Clinical questions | Guided questions by section, group and sub-group | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
43 | 150 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.5 | CLN-05 | Diagnosis, therapeutics & pattern search (keep) | CLN-05.01 | Regression: diagnosis search + therapeutics | Existing | Patient Board | §5.3 | Diagnosis, therapeutics & pattern search | Search diagnoses and linked therapeutics | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
44 | 153 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.6 | CLN-06 | Repertory rubric search & selection (keep) | CLN-06.01 | Regression: tree + search + add to clipboard | Existing | Patient Board | §5.3 | Repertory rubric search & selection | Search and select from the full repertory | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
45 | 159 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.7 | CLN-07 | Manage selected rubrics — review, edit and remove (remaining ~10%) | CLN-07.04 | QA: remove, undo-not-required, backup restore still has remaining rubrics | Regression | Patient Board | §5.3 | Manage selected rubrics | Review, edit and remove selected rubrics | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
46 | 160 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.8 | CLN-08 | Audio case taking — record and receive suggested rubrics (keep engine; do not rebuild) | CLN-08.01 | Regression: record, poll, approve/reject suggested rubrics | Existing | Audio AI | §5.3 | Audio case taking | Record the consultation and receive suggested rubrics automatically | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
47 | 165 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.9 | CLN-09 | Improved rubric accuracy — enhanced accuracy rules for audio-based rubric suggestions | CLN-09.03 | QA: golden transcripts → expected rubric IDs within tolerance | Regression | Audio AI | §5.3 | Improved rubric accuracy | Enhanced accuracy rules for audio-based rubric suggestions | Doctor Web Portal + Admin intelligence | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
48 | 169 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.10 | CLN-10 | Materia medica reference during consultation (remaining ~10%) | CLN-10.04 | QA: open MM for a repertorized remedy | Regression | Patient Board | §5.3 | Materia medica reference | Browse materia medica during the consultation | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
49 | 170 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.11 | CLN-11 | Allopathic drug side-effect lookup (keep) | CLN-11.01 | Regression: search drug → side effects | Existing | Patient Board | §5.3 | Allopathic drug side-effect lookup | Check side effects of conventional medicines | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
50 | 176 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.12 | CLN-12 | Repertorization & elimination (remaining ~10%) | CLN-12.04 | QA: known case → expected top remedies | Regression | Patient Board | §5.3 | Repertorization & elimination | Full repertorization with elimination | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
51 | 180 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.13 | CLN-13 | Center of Gravity — new analysis identifying the central remedy of the case, with reasoning shown | CLN-13.04 | QA: same clipboard as classic repertorize; COG reasons cite contributing rubrics; empty clipboard → clear empty state | Regression | Repertorization | §5.3 | Center of Gravity | New analysis identifying the central remedy of the case, with reasoning shown | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
52 | 181 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.14 | CLN-14 | Lab orders & lab entries (keep; later also sit on eRx) | CLN-14.01 | Regression: order lab from catalogue; enter result | Existing | Patient Board | §5.3 + §11 | Lab orders & lab entries | Order tests and record results / Tests ordered alongside the prescription | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
53 | 184 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.15 | CLN-15 | Appointment history notes (keep; split from eRx in Phase 10) | CLN-15.01 | Regression: add/list notes on a visit | Existing | Patient Board | §5.3 | Appointment history notes | Notes recorded against each visit | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
54 | 190 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.16 | CLN-16 | Complaints & case details — wire Patient Board to existing SaveComplaints / SaveCaseDetails (~20% today) | CLN-16.04 | QA: save, reload, second doctor cannot read | Regression | Patient Board | §5.3 | Complaints & case details | Capture and store complaints and case details | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
55 | 194 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.17 | CLN-17 | Patient back history — complete history of visits, notes, prescriptions and payments | CLN-17.04 | QA: multi-visit patient; empty new patient | Regression | Patient Board | §5.3 | Patient back history | Complete history of visits, notes, prescriptions and payments | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
56 | 197 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.18 | CLN-18 | Export case data — download the full case in Excel or PDF | CLN-18.03 | QA: export matches on-screen rubrics + Rx; unauthorised doctor 403 | Regression | Patient Board | §5.3 | Export case data | Download the full case in Excel or PDF | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
57 | 198 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.19 | CLN-19 | Session restore — continue exactly where the doctor left off, across multiple patients (keep) | CLN-19.01 | Regression: backup, restore, 5-session stack | Existing | Patient Board | §5.3 | Session restore | Continue exactly where the doctor left off, across multiple patients | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
58 | 204 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.20 | CLN-20 | 3D anatomy viewer — interactive 3D body model linked to rubric search (remaining ~50%) | CLN-20.04 | QA: click hotspot → subsection search results | Regression | Anatomy | §5.3 | 3D anatomy viewer | Interactive 3D body model linked to rubric search | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
59 | 208 | M04 | Doctor daily operations | QA | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.1 | DOC-01 | Doctor home dashboard — complete overview of the working day (remaining ~30%) | DOC-01.04 | QA: existing buckets still populate; reception still shares layout until Phase 5 reception chrome | Regression | Doctor Dashboard | §5.1 | Doctor home dashboard | Complete overview of the working day | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
60 | 209 | M04 | Doctor daily operations | QA | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.2 | DOC-02 | Patient counts & waiting list — live counts by status with quick actions (keep; extend paid/unpaid) | DOC-02.01 | Regression: each bucket count and click-through | Existing | Doctor Dashboard | §5.1 | Patient counts & waiting list | Live counts by status with quick actions | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
61 | 215 | M04 | Doctor daily operations | QA | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.3 | DOC-03 | Patient search, list & open case (remaining ~10%) | DOC-03.04 | QA: search by name/mobile; open case | Regression | Doctor Dashboard | §5.1 | Patient search, list & open case | Find any patient and open their case instantly | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
62 | 216 | M04 | Doctor daily operations | QA | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.4 | DOC-04 | Add new patient — register a patient in seconds (keep) | DOC-04.01 | Regression: add patient validation and save | Existing | Patients | §5.1 | Add new patient | Register a patient in seconds | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
63 | 219 | M04 | Doctor daily operations | QA | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.5 | DOC-05 | Import patients — bring existing patient records in bulk (keep) | DOC-05.01 | Regression: template + import + error rows | Existing | Patients | §5.1 | Import patients | Bring existing patient records in bulk | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
64 | 224 | M04 | Doctor daily operations | QA | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.6 | DOC-06 | Export patients — download patient data in Excel, CSV or PDF (keep) | DOC-06.03 | QA: another doctor cannot export this list | Regression | Patients | §5.1 | Export patients | Download patient data in Excel, CSV or PDF | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
65 | 225 | M04 | Doctor daily operations | QA | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.7 | DOC-07 | Recent activity panel (keep) | DOC-07.01 | Regression: activity loads | Existing | Doctor Dashboard | §5.1 | Recent activity panel | Everything that happened recently, at a glance | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
66 | 228 | M04 | Doctor daily operations | QA | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.8 | DOC-08 | Patient statistics charts (keep; foundation for clinic performance in Phase 18) | DOC-08.01 | Regression: stats charts date range | Existing | Doctor Dashboard | §5.1 | Patient statistics charts | Visual practice statistics | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
67 | 233 | M04 | Doctor daily operations | QA | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.9 | DOC-09 | Manage reception staff — add, edit and remove reception users (backend done, UI absent) | DOC-09.03 | QA: reception user cannot manage other doctors’ staff; disable prevents login | Regression | Staff | §5.1 | Manage reception staff | Add, edit and remove reception users | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
68 | 237 | M04 | Doctor daily operations | QA | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.10 | DOC-10 | Doctor profile — clinic details, consultation fee, photo, qualifications, working hours, bank details | DOC-10.04 | QA: reception cannot edit doctor bank details; photo displays on public profile later | Regression | Doctor Profile | §5.1 | Doctor profile | Clinic details, consultation fee, photo, qualifications, working hours, bank details | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
69 | 238 | M05 | Appointments & scheduling | QA | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.1 | APT-01 | Appointment list & waiting patients — full day view with live status (keep; later payment/tele) | APT-01.01 | Regression: day list, status colour, open patient | Existing | Appointments | §5.2 | Appointment list & waiting patients | Full day view with live status | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
70 | 244 | M05 | Appointments & scheduling | QA | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.2 | APT-02 | Create new appointment — persist visit type, consultation mode and fee | APT-02.04 | QA: staff-created appointments carry the same fields public booking will use in Phase 9 | Regression | Appointments | §5.2 | Create new appointment | Book with visit type, consultation mode and fee | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
71 | 245 | M05 | Appointments & scheduling | QA | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.3 | APT-03 | Appointment status update — move patients through the visit stages (keep) | APT-03.01 | Regression: each status transition | Existing | Appointments | §5.2 | Appointment status update | Move patients through the visit stages | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
72 | 248 | M05 | Appointments & scheduling | QA | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.4 | APT-04 | Appointment time update — adjust timings as the day runs (keep; distinct from formal reschedule) | APT-04.01 | Regression: UpdateAppointmentTime on dashboard | Existing | Appointments | §5.2 | Appointment time update | Adjust timings as the day runs | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
73 | 255 | M05 | Appointments & scheduling | QA | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.5 | APT-05 | Reschedule appointment — move to a new slot with automatic patient notification (NEW — not a rename of UpdateAppointmentTime) | APT-05.05 | QA: slot taken → 409; patient already booked elsewhere; across a schedule change; reception authorised for own DoctorId only | Regression | Appointments | §5.2 + §2.3 + §6 | Reschedule appointment | Move to a new slot with automatic patient notification / Move to another slot without calling the clinic | Doctor Web + Reception + later Patient | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
74 | 260 | M05 | Appointments & scheduling | QA | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.6 | APT-06 | Cancel appointment — reason, free the slot, trigger refund where applicable (NEW CANCELLED status — do NOT reuse DeleteStatus) | APT-06.05 | QA: reason mandatory; all three roles (later Patient) cancel with correct authorisation; freed slot bookable | Regression | Appointments | §5.2 + §2.3 + §6 | Cancel appointment | Cancel with reason, free the slot, trigger refund where applicable / Cancel with reason, refund handled per policy | Doctor Web + Reception + later Patient | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
75 | 263 | M05 | Appointments & scheduling | QA | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.7 | APT-07 | Daily schedule setup — define working days, hours and break times (promote modal to first-class screen) | APT-07.03 | QA: save week; public slot generator (Phase 9) uses this data; reception read-only is Phase 5 | Regression | Scheduling | §5.2 | Daily schedule setup | Define working days, hours and break times | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
76 | 264 | M05 | Appointments & scheduling | QA | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.8 | APT-08 | Appointment slot grid — visual slot-by-slot view of the day (keep; public booking reuses this) | APT-08.01 | Regression: slot grid vs schedule | Existing | Scheduling | §5.2 | Appointment slot grid | Visual slot-by-slot view of the day | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
77 | 270 | M05 | Appointments & scheduling | QA | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.9 | APT-09 | Consultation payment status on every appointment (schema now; values live in Phase 6) | APT-09.04 | QA: same appointment shows the same badge on doctor and reception | Regression | Appointments | §5.2 + §9 | Consultation payment status | See paid, unpaid or pay-at-clinic on every appointment / Doctor, reception and patient all see the same payment status | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
78 | 271 | M06 | Reception portal | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.1 | REC-01 | Reception login — secure staff access (keep) | REC-01.01 | Regression: reception login with DoctorID claim | Existing | Reception | §6 | Reception login | Secure staff access | Reception Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
79 | 277 | M06 | Reception portal | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.2 | REC-02 | Reception profile — manage own profile details (0% today) | REC-02.04 | QA: cannot edit doctor qualifications or fee | Regression | Reception | §6 | Reception profile | Manage own profile details | Reception Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
80 | 280 | M06 | Reception portal | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.3 | REC-03 | Reception home dashboard — purpose-built front-desk dashboard (not only hidden doctor actions) | REC-03.03 | QA: deep-link to Patient Board full clinical URL is 403 for reception | Regression | Reception | §6 | Reception home dashboard | Purpose-built front-desk dashboard | Reception Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
81 | 281 | M06 | Reception portal | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.4 | REC-04 | Create patient — register a walk-in patient quickly (keep) | REC-04.01 | Regression: reception create patient | Existing | Reception | §6 | Create patient | Register a walk-in patient quickly | Reception Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
82 | 284 | M06 | Reception portal | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.5 | REC-05 | Patient search & list — find any patient instantly (keep) | REC-05.01 | Regression: search by name/mobile | Existing | Reception | §6 | Patient search & list | Find any patient instantly | Reception Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
83 | 289 | M06 | Reception portal | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.6 | REC-06 | Create & manage appointments — full appointment management (keep; plus reschedule/cancel from Phase 4) | REC-06.03 | QA: cannot cancel another clinic’s appointment | Regression | Reception | §6 | Create & manage appointments | Full appointment management | Reception Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
84 | 291 | M06 | Reception portal | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.7 | REC-07 | New appointment — book on behalf of the patient (keep; same VisitType/ConsultMode/fee as APT-02) | REC-07.02 | QA: in-clinic vs E-Consult both creatable from reception | Regression | Reception | §6 | New appointment | Book on behalf of the patient | Reception Portal | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
85 | 295 | M06 | Reception portal | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.8 | REC-08 | Waiting queue management — manage the live queue and call the next patient | REC-08.04 | QA: two waiting patients; call next picks the right one | Regression | Reception | §6 | Waiting queue management | Manage the live queue and call the next patient | Reception Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
86 | 296 | M06 | Reception portal | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.9 | REC-09 | Appointment status update (reception) — update as patients arrive and are seen (keep) | REC-09.01 | Regression: reception status update | Existing | Reception | §6 | Appointment status update | Update as patients arrive and are seen | Reception Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
87 | 299 | M06 | Reception portal | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.10 | REC-10 | Appointment time update (reception) — adjust timings through the day (keep) | REC-10.01 | Regression: reception UpdateAppointmentTime | Existing | Reception | §6 | Appointment time update | Adjust timings through the day | Reception Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
88 | 303 | M06 | Reception portal | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.11 | REC-11 | View doctor schedule — see the doctor’s working schedule (read-only) | REC-11.02 | QA: edit buttons hidden; doctor can still edit on /doctor/schedule | Regression | Reception | §6 | View doctor schedule | See the doctor’s working schedule | Reception Portal | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
89 | 307 | M06 | Reception portal | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.12 | REC-12 | Log case paper / chief complaint — record the reason for visit before the consultation | REC-12.04 | QA: doctor sees CC; reception 403 on repertory APIs | Regression | Reception | §6 | Log case paper / chief complaint | Record the reason for visit before the consultation | Reception Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
90 | 313 | M07 | Payment system | QA | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.1 | PAY-01 | Consultation fee configuration — each doctor’s fee set and displayed to patients | PAY-01.04 | QA: changing fee does not alter already-created unpaid orders without a rule (document the rule) | Regression | Payments | §9 | Consultation fee configuration | Each doctor’s fee set and displayed to patients | Doctor profile + Public + Admin | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
91 | 317 | M07 | Payment system | QA | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.2 | PAY-02 | Automatic payment verification — bank/webhook is source of truth, not the patient’s screen | PAY-02.04 | QA: duplicate webhook; delayed webhook; failed capture; app closed mid-checkout | Regression | Payments | §9 | Automatic payment verification | Payments confirmed by the bank, not by the patient’s screen — nothing is lost if the app or browser closes | Shared | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | 2 | Not Started |  | Edit on module sheet
92 | 322 | M07 | Payment system | QA | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.3 | PAY-03 | Online consultation payment — patient pays by card, UPI, netbanking or wallet | PAY-03.05 | QA: success, failure, pending, double-click create order idempotent | Regression | Payments | §9 + §4 + §2.3 | Online consultation payment | Patient pays by card, UPI, netbanking or wallet / Pay the consultation fee at the time of booking / Pay the consultation fee inside the app | Public web + later Patient app | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
93 | 327 | M07 | Payment system | QA | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.4 | PAY-04 | Reception payment collection — cash, UPI, card or payment link with printed receipt | PAY-04.05 | QA: cash collection visible in clinic collection view after Phase 7; cannot mark PAID without this API | Regression | Payments | §9 + §6 | Reception payment collection | Cash, UPI, card or payment link with printed receipt | Reception Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
94 | 330 | M07 | Payment system | QA | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.5 | PAY-05 | Pay-at-clinic option — book now, pay at the clinic where the doctor allows it | PAY-05.03 | QA: doctor flag off → pay-at-clinic hidden; reception can still collect | Regression | Payments | §9 | Pay-at-clinic option | Book now, pay at the clinic where the doctor allows it | Public + Doctor + Reception | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
95 | 333 | M07 | Payment system | QA | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.6 | PAY-06 | Doctor subscription payment — buy and renew subscription packages (complete remaining ~30%) | PAY-06.03 | QA: renew, fail, webhook delay, last-5-days warning still works | Regression | Payments | §9 | Doctor subscription payment | Buy and renew subscription packages | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
96 | 336 | M07 | Payment system | QA | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.7 | PAY-07 | Medicine payment — pay online or cash on delivery (API contract now; HomeoMeds Phase 14 implements orders) | PAY-07.03 | QA: stream isolation query (consult vs medicine totals differ) | Regression | Payments | §9 + §12 | Medicine payment | Pay online or choose cash on delivery / Both options supported, with status tracking | Shared | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
97 | 339 | M07 | Payment system | QA | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.8 | PAY-08 | Payment status everywhere — doctor, reception and patient all see the same payment status | PAY-08.03 | QA: three roles, one appointment, same enum value | Regression | Payments | §9 | Payment status everywhere | Doctor, reception and patient all see the same payment status | All | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
98 | 344 | M07 | Payment system | QA | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.9 | PAY-09 | Refunds — processed and tracked against the original payment | PAY-09.05 | QA: double refund blocked; cash collection refund is ledger-only per PRE-02 policy | Regression | Payments | §9 + §8 + §2.8 | Refunds | Processed and tracked against the original payment / Issue and track refunds | Account + Patient | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
99 | 348 | M07 | Payment system | QA | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.10 | PAY-10 | Payment receipts & invoices — issued for every transaction | PAY-10.04 | QA: unique invoice numbers; cancelled invoice not reused | Regression | Payments | §9 + §8 | Payment receipts & invoices | Issued for every transaction / Invoice numbering and tax reporting | All | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
100 | 351 | M07 | Payment system | QA | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.11 | PAY-11 | Complete payment audit trail — every transaction traceable end to end by Homeocentrum | PAY-11.03 | QA: missing webhook still shows PENDING not PAID | Regression | Payments | §9 + §17 | Complete audit trail | Every transaction traceable end to end by Homeocentrum | Account | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
101 | 355 | M08 | Account & finance | QA | 7 | Phase 7 — Account & finance department (PDF §8) | 7.1 | FIN-01 | Unified transaction ledger — every rupee that moves through the platform, in one record | FIN-01.04 | QA: consult pay writes S2; subscription writes S1; they never share one row | Regression | Account | §8 | Unified transaction ledger | Every rupee that moves through the platform, in one record | Account Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
102 | 359 | M08 | Account & finance | QA | 7 | Phase 7 — Account & finance department (PDF §8) | 7.2 | FIN-02 | Consultation payment reconciliation — online payments and reception collections matched and verified | FIN-02.04 | QA: unmatched payment appears in exception queue not silent | Regression | Account | §8 + §7.2 + §16 | Consultation payment reconciliation | Online payments and reception collections matched and verified / Match every booking against every payment | Account + Admin | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
103 | 363 | M08 | Account & finance | QA | 7 | Phase 7 — Account & finance department (PDF §8) | 7.3 | FIN-03 | Medicine ledger — medicine money tracked separately from consultation money | FIN-03.04 | QA: S2 consult row never appears on this screen | Regression | Account | §8 + §12 | Medicine ledger | Medicine money tracked separately from consultation money / Seller, platform and delivery shares recorded separately from consultation money | Account Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
104 | 367 | M08 | Account & finance | QA | 7 | Phase 7 — Account & finance department (PDF §8) | 7.4 | FIN-04 | Settlement runs — scheduled settlement of amounts due to doctors and pharmacies | FIN-04.04 | QA: hold days exclude too-new captures; refunds net out | Regression | Account | §8 + §16 | Settlement runs | Scheduled settlement of amounts due to doctors and pharmacies | Account Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
105 | 372 | M08 | Account & finance | QA | 7 | Phase 7 — Account & finance department (PDF §8) | 7.5 | FIN-05 | Payout approval — payouts released only after OTP-verified approval | FIN-05.05 | QA: Account role only; replay OTP; Admin 403 on approve | Regression | Account | §8 + §17 | Payout approval | Payouts released only after OTP-verified approval | Account Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
106 | 375 | M08 | Account & finance | QA | 7 | Phase 7 — Account & finance department (PDF §8) | 7.6 | FIN-06 | Refund processing — Account issues and tracks refunds (uses PAY-09) | FIN-06.03 | QA: partial refund; full refund; cash-policy path | Regression | Account | §8 | Refund processing | Issue and track refunds | Account Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
107 | 379 | M08 | Account & finance | QA | 7 | Phase 7 — Account & finance department (PDF §8) | 7.7 | FIN-07 | Payment exception handling — investigate and resolve every failed or disputed payment | FIN-07.04 | QA: failed webhook creates exception; manual resolve requires Account role + OTP | Regression | Account | §8 + §7.2 | Payment exception handling | Investigate and resolve every failed or disputed payment / Every failed or mismatched payment surfaced for action | Account + Admin | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
108 | 383 | M08 | Account & finance | QA | 7 | Phase 7 — Account & finance department (PDF §8) | 7.8 | FIN-08 | GST & invoice reports — invoice numbering and tax reporting | FIN-08.04 | QA: rates come from config; changing rate does not rewrite old invoices | Regression | Account | §8 + §16 | GST & invoice reports | Invoice numbering and tax reporting | Account Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
109 | 387 | M08 | Account & finance | QA | 7 | Phase 7 — Account & finance department (PDF §8) | 7.9 | FIN-09 | Payee records — bank and KYC details for doctors and pharmacies | FIN-09.04 | QA: missing KYC blocks FIN-05 | Regression | Account | §8 | Payee records | Bank and KYC details for doctors and pharmacies | Account Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
110 | 391 | M08 | Account & finance | QA | 7 | Phase 7 — Account & finance department (PDF §8) | 7.10 | FIN-10 | Clinic collection view — cash and UPI collected at reception, per clinic and per day | FIN-10.04 | QA: online Razorpay consults do not appear as clinic cash | Regression | Account | §8 | Clinic collection view | Cash and UPI collected at reception, per clinic and per day | Account Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
111 | 393 | M08 | Account & finance | QA | 7 | Phase 7 — Account & finance department (PDF §8) | 7.11 | FIN-11 | Separation of duties — Account controls money; Admin controls platform and clinical data | FIN-11.02 | Negative tests: Admin POST ApprovePayout → 403; Account POST repertory section → 403 | Regression | Account | §8 | Separation of duties | The Account department controls money. Admin controls the platform and clinical data. Neither can perform the other’s role, which protects both. | Admin + Account | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
112 | 397 | M09 | Trust & verification | QA | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.1 | TRU-01 | Doctor credentialing — doctors upload qualification and registration documents for review | TRU-01.04 | QA: doctor without docs cannot appear in public directory (Phase 9) | Regression | Trust | §13 + §7.2 | Doctor credentialing | Doctors upload qualification and registration documents for review | Doctor Web + Admin | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
113 | 402 | M09 | Trust & verification | QA | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.2 | TRU-02 | Verification review — Admin approves, rejects or requests further information | TRU-02.05 | QA: reject reason required; request-info reopens Pending | Regression | Trust | §13 + §7.2 | Verification review | Admin approves, rejects or requests more information before they can practise on the platform | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
114 | 405 | M09 | Trust & verification | QA | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.3 | TRU-03 | Verified badge — patients see which doctors have been verified | TRU-03.03 | QA: pending doctor has no badge | Regression | Trust | §13 + §2.2 | Verified badge / Credentials & verification | Patients see which doctors have been verified / Verified badge showing the doctor’s credentials are checked | Public + Patient app | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
115 | 408 | M09 | Trust & verification | QA | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.4 | TRU-04 | Practice gate — only verified doctors appear to patients and take paid consultations | TRU-04.03 | QA: reception can still book own clinic patient for unverified doctor if PRE-03 allows | Regression | Trust | §13 | Practice gate | Only verified doctors appear to patients and take paid consultations | Public + Payments | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
116 | 412 | M09 | Trust & verification | QA | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.5 | TRU-05 | Patient reviews — patients rate and review consultations | TRU-05.04 | QA: duplicate review blocked; incomplete visit blocked | Regression | Trust | §13 + §2.8 | Patient reviews / Write a review | Patients rate and review consultations / Rate and review the consultation | Patient + Public | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
117 | 416 | M09 | Trust & verification | QA | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.6 | TRU-06 | Review appeal — doctors can appeal a review; patients manage reviews and raise an appeal | TRU-06.04 | QA: only treating doctor of that visit can appeal | Regression | Trust | §13 + §2.8 | Review appeal / My reviews & appeal | Doctors can appeal a review / Manage reviews and raise an appeal | Doctor + Patient + Admin | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
118 | 420 | M09 | Trust & verification | QA | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.7 | TRU-07 | Ranking transparency — patients are shown why doctors are ranked as they are | TRU-07.04 | QA: changing weights changes order and explanation together | Regression | Trust | §13 + §2.2 | Ranking transparency / Ranking explanation | Patients are shown why doctors are ranked as they are / Transparent explanation of why doctors appear in a given order | Public + Patient app | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
119 | 424 | M10 | Patient website | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.1 | WEB-01 | Product home page — complete public website presenting the service | WEB-01.04 | QA: mobile viewport; deep link /book | Regression | Patient Website | §4 | Product home page | Complete public website presenting the service | Patient Website | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
120 | 427 | M10 | Patient website | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.2 | WEB-02 | Consultation & subscription pricing — transparent pricing display | WEB-02.03 | QA: fee matches checkout amount | Regression | Patient Website | §4 | Consultation & subscription pricing | Transparent pricing display | Patient Website | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
121 | 431 | M10 | Patient website | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.3 | WEB-03 | Doctor discovery — browse and search verified doctors | WEB-03.04 | QA: unverified excluded; filters combine; empty state | Regression | Patient Website | §4 + §2.2 | Doctor discovery | Browse and search verified doctors | Patient Website | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
122 | 435 | M10 | Patient website | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.4 | WEB-04 | Self-service booking — book an appointment online without calling the clinic | WEB-04.04 | QA: double-book same slot; hold expiry; OTP fail; consent required | Regression | Patient Website | §4 + §2.3 | Self-service booking | Book an appointment online without calling the clinic | Patient Website | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
123 | 437 | M10 | Patient website | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.5 | WEB-05 | Online consultation payment on website — pay the fee at the time of booking | WEB-05.02 | QA: pay-at-clinic skip checkout; failed pay remains PENDING not PAID | Regression | Patient Website | §4 + §9 | Online consultation payment | Pay the consultation fee at the time of booking | Patient Website | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
124 | 441 | M10 | Patient website | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.6 | WEB-06 | Contact & enquiry form — enquiries reach the admin team and are tracked | WEB-06.04 | QA: guest submit → admin sees row | Regression | Patient Website | §4 + §15 | Contact & enquiry form | Enquiries reach the admin team and are tracked | Patient Website + Admin | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
125 | 443 | M10 | Patient website | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.7 | WEB-07 | Privacy policy — covering data protection, recording and pharmacy consent | WEB-07.02 | QA: booking consent shows policy version number | Regression | Legal | §4 + §17 | Privacy policy | Covering data protection, recording and pharmacy consent | Patient Website | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
126 | 445 | M10 | Patient website | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.8 | WEB-08 | Terms of service — covering payments, refunds, telemedicine and medicine orders | WEB-08.02 | QA: terms checkbox required on confirm | Regression | Legal | §4 | Terms of service | Covering payments, refunds, telemedicine and medicine orders | Patient Website | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
127 | 449 | M10 | Patient website | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.9 | WEB-09 | Doctor self-registration — doctors apply to join the platform online | WEB-09.04 | QA: register → admin queue row | Regression | Patient Website | §4 | Doctor self-registration | Doctors apply to join the platform online | Public | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
128 | 453 | M10 | Patient website | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.10 | WEB-10 | Email activation — secure account activation by email link | WEB-10.04 | QA: used link, expired link, resend | Regression | Auth | §4 | Email activation | Secure account activation by email link | Public | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
129 | 458 | M05 | Appointments & scheduling | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.11 | WEB-11 | Waitlist offer — get offered a slot when one is freed by a cancellation (patient website + later app) | WEB-11.05 | QA: two waiters; first gets offer; expiry releases to second | Regression | Booking | §2.3 | Waitlist offer | Get offered a slot when one is freed by a cancellation | Patient Website + App | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
130 | 460 | M10 | Patient website | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.12 | WEB-12 | Health articles — educational content to build trust and engagement | WEB-12.02 | QA: unpublished hidden | Regression | Patient Website | §2.2 | Health articles | Educational content to build trust and engagement | Patient Website + App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
131 | 464 | M11 | Digital prescription (eRx) | QA | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.1 | ERX-01 | Potency module — every remedy carries a defined potency from a managed list, no free text | ERX-01.04 | QA: free text potency rejected | Regression | eRx | §11 | Potency module | Every remedy carries a defined potency, selected from a managed list — no free text | Doctor Web + Admin | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
132 | 468 | M11 | Digital prescription (eRx) | QA | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.2 | ERX-02 | Dosage details — frequency, duration and instructions recorded clearly | ERX-02.04 | QA: all three persist and print | Regression | eRx | §11 | Dosage details | Frequency, duration and instructions recorded clearly | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
133 | 472 | M11 | Digital prescription (eRx) | QA | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.3 | ERX-03 | Visit notes kept separate from the prescription — private clinical notes never appear on the prescription given to the patient or pharmacy | ERX-03.04 | QA: print eRx vs export case PDF (doctor copy still has notes) | Regression | eRx | §11 + §5.3 | Visit notes kept separate from the prescription | The doctor’s private clinical notes never appear on the prescription given to the patient or pharmacy | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
134 | 476 | M11 | Digital prescription (eRx) | QA | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.4 | ERX-04 | Signed digital prescription — issued and locked once signed, so it cannot be altered afterwards | ERX-04.04 | QA: POST save after sign does not change snapshot | Regression | eRx | §11 + §2.5 + §5.3 | Signed digital prescription | Issued and locked once signed, so it cannot be altered afterwards / Official prescription issued by the doctor | Doctor Web | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
135 | 479 | M11 | Digital prescription (eRx) | QA | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.5 | ERX-05 | Prescription history — every prescription stored against the patient and visit | ERX-05.03 | QA: another doctor 403 | Regression | eRx | §11 | Prescription history | Every prescription stored against the patient and visit | Doctor + Patient | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
136 | 482 | M11 | Digital prescription (eRx) | QA | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.6 | ERX-06 | Patient view of prescription in app — patient sees the prescription immediately (codes until pharmacy accept) | ERX-06.03 | QA: doctor names vs patient codes differ until pharmacy OTP accept | Regression | eRx | §11 + §2.5 | Patient view in app | Patient sees the prescription immediately in the app | Patient App + Website | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
137 | 485 | M11 | Digital prescription (eRx) | QA | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.7 | ERX-07 | Print & PDF — printable and downloadable prescription | ERX-07.03 | QA: notes leak test on patient PDF | Regression | eRx | §11 | Print & PDF | Printable and downloadable prescription | Doctor + Patient | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
138 | 487 | M11 | Digital prescription (eRx) | QA | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.8 | ERX-08 | Remedy code protection — patient sees remedy codes rather than names until a licensed pharmacy accepts the order | ERX-08.02 | Patient serializer tests (contract tests) | Regression | eRx | §11 | Remedy code protection | The patient sees remedy codes rather than remedy names until a licensed pharmacy accepts the order | Patient | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
139 | 493 | M11 | Digital prescription (eRx) | QA | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.10 | ERX-10 | Repeat prescription / refill — patient requests; doctor approves or rejects from the mobile app (inbox on web too) | ERX-10.04 | QA: cannot refill unsigned/locked-expired per policy | Regression | eRx | §11 + §3 + §2.7 | Repeat prescription / refill | Patient requests a refill; doctor approves or rejects from the mobile app | Patient + Doctor mobile + Doctor web | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
140 | 495 | M11 | Digital prescription (eRx) | QA | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.11 | ERX-11 | Lab orders alongside the prescription (keep existing labs on eRx snapshot) | ERX-11.02 | QA: labs visible on eRx; result values not required on patient copy | Regression | eRx | §11 | Lab orders | Tests ordered alongside the prescription | Doctor Web | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
141 | 499 | M12 | Telemedicine | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.1 | TEL-01 | Doctor availability — online or offline status and working hours | TEL-01.04 | QA: heartbeat expiry sets offline | Regression | Telemedicine | §10 + §3 | Doctor availability | Doctor sets online or offline status and working hours | Doctor Web + Doctor App | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
142 | 504 | M12 | Telemedicine | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.2 | TEL-02 | Telemedicine waiting queue — who is waiting, how long, whether they have paid | TEL-02.05 | QA: wait time increases; paid badge matches PAY-08 | Regression | Telemedicine | §10 + §3 | Telemedicine waiting queue | Doctor sees who is waiting, for how long, and whether they have paid | Doctor Web + App | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
143 | 509 | M12 | Telemedicine | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.3 | TEL-03 | Video consultation in browser — doctor consults directly from the web portal | TEL-03.05 | QA: replace WhatsApp alert; session ends write timestamp | Regression | Telemedicine | §10 | Video consultation in browser | Doctor consults directly from the web portal | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
144 | 511 | M12 | Telemedicine | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.4 | TEL-04 | Video consultation on mobile — doctor and patient both consult from the app (apps in 16–17; same session tokens) | TEL-04.02 | Contract tests: token TTL, room id = session id | Regression | Telemedicine | §10 + §2.4 + §3 | Video consultation on mobile | Doctor and patient both consult from the app / Face-to-face consultation from home / Start the video or audio consultation from the phone | Patient App + Doctor App | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
145 | 513 | M12 | Telemedicine | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.5 | TEL-05 | Device check — camera, microphone and connection tested before joining | TEL-05.02 | QA: deny camera permission → clear guidance | Regression | Telemedicine | §10 + §2.4 | Device check | Camera, microphone and connection tested before joining | Doctor Web + Patient | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
146 | 517 | M12 | Telemedicine | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.6 | TEL-06 | Waiting room — patient waits with live status until the doctor joins | TEL-06.04 | QA: doctor join transitions patient into the call | Regression | Telemedicine | §10 + §2.4 | Waiting room | Patient waits with live status / Wait with live status until the doctor joins | Patient | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
147 | 521 | M12 | Telemedicine | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.7 | TEL-07 | Recording consent — consent captured before the consultation; no recording without it | TEL-07.04 | QA: decline → no record; audit row still written | Regression | Telemedicine | §10 + §2.4 + §17 | Recording consent | Consent captured before the consultation; no recording without it / Explicit consent requested before any recording | Patient + Doctor | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
148 | 524 | M12 | Telemedicine | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.8 | TEL-08 | Rejoin after dropped call — either side can rejoin the same consultation | TEL-08.03 | QA: after End, rejoin 409 | Regression | Telemedicine | §10 + §2.4 | Rejoin after dropped call | Either side can rejoin the same consultation / Rejoin the same consultation if the connection drops | Doctor + Patient | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
149 | 527 | M12 | Telemedicine | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.9 | TEL-09 | Join failure handling — clear fallback if the call cannot connect, with options to retry | TEL-09.03 | QA: simulated token fail | Regression | Telemedicine | §10 + §2.4 | Join failure handling / Fallback & join failure handling | Clear fallback if the call cannot connect / Clear guidance if the call fails, with options to retry | Doctor + Patient | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
150 | 531 | M12 | Telemedicine | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.10 | TEL-10 | Case-linked chat — chat attached to the consultation record, not a loose message thread | TEL-10.04 | QA: IDOR other session 403 | Regression | Telemedicine | §10 + §2.4 | Case-linked chat | Chat attached to the consultation record / Chat tied to the consultation, not a loose message thread | Doctor + Patient | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
151 | 535 | M12 | Telemedicine | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.11 | TEL-11 | Consultation summary — issued to the patient at the end of the call | TEL-11.04 | QA: private notes not copied into summary by default | Regression | Telemedicine | §10 + §2.4 | Consultation summary | Issued to the patient at the end of the call / Written summary available immediately after the call | Patient + Doctor | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
152 | 539 | M12 | Telemedicine | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.12 | TEL-12 | Instant consultation — patient requests an immediate consultation with an available doctor | TEL-12.04 | QA: no online doctor → empty state; surcharge on checkout | Regression | Telemedicine | §10 + §2.3 | Instant consultation / Instant consult request / Queue & doctor offer | Patient can request an immediate consultation with an available doctor / See position in queue and accept an offered doctor | Patient + Doctor | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
153 | 544 | M13 | Communications | QA | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.1 | COM-01 | SMS — appointment confirmation, registration confirmation, doctor-unavailable, OTP, reschedule and cancellation | COM-01.05 | QA: OTP SMS; reschedule old→new; cancel; doctor unavailable; opt-out honored | Regression | Notifications | §14 | SMS | Appointment confirmation, registration confirmation, doctor-unavailable notice, OTP, reschedule and cancellation alerts | Shared | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
154 | 548 | M13 | Communications | QA | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.2 | COM-02 | WhatsApp — templates, offers, health tips and bulk messaging with delivery reports and opt-out (complete remaining ~50%) | COM-02.04 | QA: opt-in required; template rejected state | Regression | Notifications | §14 | WhatsApp | Templates, offers, health tips and bulk messaging to patients, with delivery reports and opt-out | Doctor Web | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
155 | 553 | M13 | Communications | QA | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.3 | COM-03 | Push notifications — booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests | COM-03.05 | QA: doctor and patient payloads isolated; token refresh | Regression | Notifications | §14 + §2.9 + §3 | Push notifications | Booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests / Patient waiting, new booking, reschedule, cancellation, refill request, payment received | Patient App + Doctor App | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
156 | 557 | M13 | Communications | QA | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.4 | COM-04 | Email — registration, activation, password reset, invoices and receipts | COM-04.04 | QA: reset still has no plaintext password; invoice attached | Regression | Notifications | §14 | Email | Registration, activation, password reset, invoices and receipts | Shared | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
157 | 561 | M13 | Communications | QA | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.5 | COM-05 | In-app notification centre — all alerts collected in one place for patients and doctors | COM-05.04 | QA: mark read; empty state; not Velzon demo route | Regression | Notifications | §14 + §2.8 | In-app notification centre / Notifications centre | All alerts collected in one place for patients and doctors / All alerts in one place | Patient App + Doctor Web/App | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
158 | 565 | M14 | Support & help desk | QA | 13 | Phase 13 — Support & help desk (PDF §15) | 13.1 | SUP-01 | Patient support tickets — patients raise issues from the app and track them | SUP-01.04 | QA: IDOR; attachment via SEC-09 | Regression | Support | §15 + §2.9 | Patient support tickets / Help centre & support tickets | Patients raise issues from the app and track them to resolution | Patient App + Admin | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
159 | 568 | M14 | Support & help desk | QA | 13 | Phase 13 — Support & help desk (PDF §15) | 13.2 | SUP-02 | Doctor support tickets — doctors raise issues from the portal | SUP-02.03 | QA: doctor cannot see another doctor’s tickets | Regression | Support | §15 | Doctor support tickets | Doctors raise issues from the portal | Doctor Web + Admin | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | Edit on module sheet
160 | 572 | M14 | Support & help desk | QA | 13 | Phase 13 — Support & help desk (PDF §15) | 13.3 | SUP-03 | Admin issue queue — all issues in one queue with priority, assignment and status | SUP-03.04 | QA: not using Velzon ticket pages | Regression | Support | §15 + §7.2 | Admin issue queue / Support ticket queue | All issues in one queue with priority, assignment and status / All patient and doctor issues in one queue with assignment and resolution | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
161 | 575 | M14 | Support & help desk | QA | 13 | Phase 13 — Support & help desk (PDF §15) | 13.4 | SUP-04 | Ticket conversation — full message thread with attachments | SUP-04.03 | QA: attachment unauthorised download 403 | Regression | Support | §15 | Ticket conversation | Full message thread with attachments | Admin + Doctor + Patient | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
162 | 577 | M14 | Support & help desk | QA | 13 | Phase 13 — Support & help desk (PDF §15) | 13.5 | SUP-05 | Enquiry management — website enquiries tracked (ties WEB-06) | SUP-05.02 | QA: convert to ticket keeps original enquiry id | Regression | Support | §15 + §4 | Enquiry management | Website enquiries reach the admin team and are tracked | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
163 | 581 | M14 | Support & help desk | QA | 13 | Phase 13 — Support & help desk (PDF §15) | 13.6 | SUP-06 | Help centre — self-service help content for patients | SUP-06.04 | QA: unpublished hidden | Regression | Support | §15 + §2.9 | Help centre | Self-service help content for patients | Patient Website + App | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
164 | 585 | M14 | Support & help desk | QA | 13 | Phase 13 — Support & help desk (PDF §15) | 13.7 | SUP-07 | Assisted booking — help for patients who need support booking | SUP-07.04 | QA: consent still captured; payment still Homeocentrum | Regression | Support | §15 + §2.9 | Assisted booking | Support for patients who need help booking / Help for patients who need support booking | Support + Reception + Patient | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
165 | 589 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.1 | MED-01 | Pharmacy partner onboarding — licensed premises, licence records, activation checklist | MED-01.04 | QA: checklist incomplete blocks activate | Regression | HomeoMeds | §12 + §7.2 | Pharmacy partner onboarding / Pharmacy partner management | Licensed premises registered with licence records and an activation checklist / Onboard and activate licensed pharmacies | Pharmacy + Admin | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
166 | 592 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.2 | MED-02 | Licence gating — expired or suspended licences blocked automatically from receiving orders | MED-02.03 | QA: expire a licence in test → order not offered | Regression | HomeoMeds | §12 | Licence gating | Pharmacies with expired or suspended licences are blocked automatically from receiving orders | Backend | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
167 | 596 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.3 | MED-03 | Fulfilment consent & pharmacy selection — patient chooses the seller and consents before the prescription is shared | MED-03.04 | QA: without consent, handoff API 403 | Regression | HomeoMeds | §12 + §2.7 | Fulfilment consent & pharmacy selection | The patient chooses the seller and consents before the prescription is shared | Patient | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
168 | 600 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.4 | MED-04 | Prescription handoff — signed prescription becomes the order directly — no re-entry, no transcription errors | MED-04.04 | QA: line count mismatch fails sign-off | Regression | HomeoMeds | §12 + §2.7 | Prescription handoff / Order start | The signed prescription becomes the order directly — no re-entry, no transcription errors / Start an order directly from the prescription | Patient + Pharmacy | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
169 | 604 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.5 | MED-05 | Rule-based seller routing — licence validity, service area, working hours and capacity | MED-05.04 | QA: capacity full excluded; hours closed excluded | Regression | HomeoMeds | §12 | Rule-based seller routing | Orders routed by licence validity, service area, working hours and capacity | Backend | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
170 | 607 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.6 | MED-06 | Manual stock confirmation — pharmacy confirms availability — no live inventory integration required | MED-06.03 | QA: no inventory SKU table required | Regression | HomeoMeds | §12 | Manual stock confirmation | The pharmacy confirms availability — no live inventory integration required | Pharmacy console | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
171 | 612 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.7 | MED-07 | Pharmacy console — accept or reject, enter price quote, mark ready and dispatched | MED-07.05 | QA: accept without OTP fails; names still hidden to patient until accept succeeds | Regression | HomeoMeds | §12 | Pharmacy console | Accept or reject orders, enter the price quote, mark ready and dispatched | Pharmacy console | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
172 | 616 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.8 | MED-08 | Quote before payment — the patient always sees the price before paying | MED-08.04 | QA: price change after quote invalidates old quote | Regression | HomeoMeds | §12 + §2.7 | Quote before payment / Pharmacy selection & quote | The patient always sees the price before paying / Choose a licensed pharmacy and see the price before paying | Patient | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
173 | 619 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.9 | MED-09 | Payment or cash on delivery — both options, with status tracking | MED-09.03 | QA: COD vs prepaid ledger split | Regression | HomeoMeds | §12 + §9 | Payment or cash on delivery | Both options supported, with status tracking | Patient | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
174 | 624 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.10 | MED-10 | Order tracking — live status for the patient at every stage | MED-10.05 | QA: dispatched without ready is invalid transition | Regression | HomeoMeds | §12 + §2.7 | Order tracking | Live status for the patient at every stage / Live status from accepted to delivered | Patient | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
175 | 626 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.11 | MED-11 | Medicine ledger shares — seller, platform and delivery recorded (FIN-03 live fill) | MED-11.02 | QA: consult GMV unchanged by a medicine order | Regression | HomeoMeds | §12 + §8 | Medicine ledger | Seller, platform and delivery shares recorded separately from consultation money | Account | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
176 | 630 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.12 | MED-12 | Order exception queue — stuck, rejected or failed orders always surfaced — never silent | MED-12.04 | QA: silent discard impossible (metric + queue) | Regression | HomeoMeds | §12 | Order exception queue | Stuck, rejected or failed orders are always surfaced to the operations team — never silent | Admin + Account | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
177 | 632 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.13 | MED-13 | OTP-based control — key actions verified by OTP so Homeocentrum can monitor and trace every transaction | MED-13.02 | QA: Account OTP audit shows pharmacy accept | Regression | HomeoMeds | §12 + §17 | OTP-based control | Key actions verified by OTP so Homeocentrum can monitor and trace every transaction | Pharmacy + Account | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
178 | 635 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.14 | MED-14 | Refill orders — repeat orders raised from an existing prescription | MED-14.03 | QA: original eRx unchanged | Regression | HomeoMeds | §12 + §2.7 + §11 | Refill orders / Order detail & refill | Repeat orders raised from an existing prescription / Full order history and one-tap refill request | Patient + Doctor | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
179 | 637 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.15 | MED-15 | Order review & consent (patient) — confirm and consent before the prescription is shared | MED-15.02 | QA: back button does not share | Regression | HomeoMeds | §2.7 | Order review & consent | Confirm and consent before the prescription is shared | Patient | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
180 | 640 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.16 | MED-16 | Medicines tab — all medicine orders in one place (API now; app UI in Phase 16) | MED-16.03 | QA: IDOR other patient 403 | Regression | HomeoMeds | §2.7 | Medicines tab | All medicine orders in one place | Patient | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
181 | 644 | M16 | Patient continuity APIs | QA | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.1 | CON-01 | Family members — add family members under one account | CON-01.04 | QA: adult consent rules for minors documented | Regression | Patient identity | §2.1 | Family members | Add family members under one account | Patient App (API now) | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
182 | 649 | M16 | Patient continuity APIs | QA | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.2 | CON-02 | Caregiver authorization — let a family member book and manage on their behalf | CON-02.05 | QA: revoked token cannot book | Regression | Patient identity | §2.1 | Caregiver authorization | Let a family member book and manage on their behalf | Patient App (API now) | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
183 | 653 | M16 | Patient continuity APIs | QA | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.3 | CON-03 | Records timeline + consultation note + document upload APIs | CON-03.04 | QA: notes leak test on timeline JSON | Regression | Patient records | §2.5 | Records timeline / Consultation note / Document upload | Complete visit history in date order / Doctor’s notes for each visit / Upload reports, scans and previous prescriptions | Patient App (API now) | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
184 | 657 | M16 | Patient continuity APIs | QA | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.4 | CON-04 | Follow-up plan & tasks — clear next steps after each consultation | CON-04.04 | QA: overdue flag | Regression | Continuity | §2.6 | Follow-up plan & tasks | Clear next steps after each consultation | Doctor Web + Patient | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
185 | 661 | M16 | Patient continuity APIs | QA | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.5 | CON-05 | Symptom diary — record symptoms between visits | CON-05.04 | QA: IDOR | Regression | Continuity | §2.6 | Symptom diary | Record symptoms between visits | Patient App (API now) | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
186 | 665 | M16 | Patient continuity APIs | QA | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.6 | CON-06 | Progress tracking — see improvement over time across visits | CON-06.04 | QA: no dummy numbers | Regression | Continuity | §2.6 | Progress tracking | See improvement over time across visits | Patient + Doctor | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
187 | 669 | M16 | Patient continuity APIs | QA | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.7 | CON-07 | Consent centre & data rights — view, manage and withdraw consents; request data | CON-07.04 | QA: withdraw marketing stops WhatsApp/SMS offers | Regression | Privacy | §17 + §2.8 | Consent centre & data rights | Patients can view, manage and withdraw consent / View, manage and withdraw consents; request data | Patient App (API now) | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
188 | 671 | M08 | Account & finance | QA | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.8 | CON-08 | Patient payments & refunds read model | CON-08.02 | QA: commission/GST internal lines hidden | Regression | Patient money | §2.8 | Payments & refunds | Full payment history and refund status | Patient App (API now) | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
189 | 673 | M05 | Appointments & scheduling | QA | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.9 | CON-09 | Physical clinic appointment — book an in-person visit as well as online | CON-09.02 | QA: in-clinic does not require device check/video | Regression | Booking | §2.9 + §5.2 | Physical clinic appointment | Book an in-person visit as well as online | Patient | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
190 | 677 | M16 | Patient continuity APIs | QA | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.10 | CON-10 | Patient profile setup API — name, age, gender, contact and health basics | CON-10.04 | QA: cannot escalate to doctor role via profile PUT | Regression | Patient identity | §2.1 | Profile setup | Name, age, gender, contact and health basics | Patient App (API now) | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
191 | 681 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.1 | PAT-01 | Patient app — language selection on first open | PAT-01.04 | QA both platforms: Language selection matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.1 | Language selection | Choose preferred language on first open | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
192 | 685 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.2 | PAT-02 | Patient app — welcome and introduction | PAT-02.04 | QA both platforms: Welcome & introduction matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.1 | Welcome & introduction | Guided introduction to the app | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
193 | 689 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.3 | PAT-03 | Patient app — mobile number + OTP login (PatientAuth) | PAT-03.04 | QA both platforms: Mobile number + OTP login matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.1 | Mobile number + OTP login | Secure sign-in with no password to remember | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
194 | 693 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.4 | PAT-04 | Patient app — profile setup | PAT-04.04 | QA both platforms: Profile setup matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.1 | Profile setup | Name, age, gender, contact and health basics | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
195 | 697 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.5 | PAT-05 | Patient app — privacy consent before data stored | PAT-05.04 | QA both platforms: Privacy consent matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.1 | Privacy consent | Clear consent before any personal data is stored | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
196 | 701 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.6 | PAT-06 | Patient app — family members | PAT-06.04 | QA both platforms: Family members matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.1 | Family members | Add family members under one account | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
197 | 705 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.7 | PAT-07 | Patient app — caregiver authorization | PAT-07.04 | QA both platforms: Caregiver authorization matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.1 | Caregiver authorization | Let a family member book and manage on their behalf | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
198 | 709 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.8 | PAT-08 | Patient app — home dashboard | PAT-08.04 | QA both platforms: Home dashboard matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.2 | Home dashboard | Personalised home with upcoming visits and quick actions | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
199 | 713 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.9 | PAT-09 | Patient app — search and care categories | PAT-09.04 | QA both platforms: Search & care categories matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.2 | Search & care categories | Search by name, condition or category of care | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
200 | 717 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.10 | PAT-10 | Patient app — search results | PAT-10.04 | QA both platforms: Search results matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.2 | Search results | Clear list of available doctors | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
201 | 721 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.11 | PAT-11 | Patient app — discovery filters | PAT-11.04 | QA both platforms: Filters matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.2 | Filters | Narrow by availability, fee, experience, language and location | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
202 | 725 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.12 | PAT-12 | Patient app — doctor profile | PAT-12.04 | QA both platforms: Doctor profile matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.2 | Doctor profile | Full profile with qualifications, experience and consultation fee | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
203 | 729 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.13 | PAT-13 | Patient app — verified badge on doctor | PAT-13.04 | QA both platforms: Credentials & verification matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.2 | Credentials & verification | Verified badge showing the doctor’s credentials are checked | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
204 | 733 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.14 | PAT-14 | Patient app — ranking explanation | PAT-14.04 | QA both platforms: Ranking explanation matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.2 | Ranking explanation | Transparent explanation of why doctors appear in a given order | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
205 | 737 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.15 | PAT-15 | Patient app — health articles | PAT-15.04 | QA both platforms: Health articles matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.2 | Health articles | Educational content to build trust and engagement | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
206 | 741 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.16 | PAT-16 | Patient app — slot picker | PAT-16.04 | QA both platforms: Slot picker matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Slot picker | See real available time slots and choose one | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
207 | 745 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.17 | PAT-17 | Patient app — booking review and consent | PAT-17.04 | QA both platforms: Booking review & consent matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Booking review & consent | Confirm details and consent before booking | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
208 | 749 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.18 | PAT-18 | Patient app — checkout | PAT-18.04 | QA both platforms: Checkout matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Checkout | Pay the consultation fee inside the app | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
209 | 753 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.19 | PAT-19 | Patient app — payment status | PAT-19.04 | QA both platforms: Payment status matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Payment status | Immediate confirmation of paid, pending or failed | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
210 | 757 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.20 | PAT-20 | Patient app — appointment detail | PAT-20.04 | QA both platforms: Appointment detail matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Appointment detail | Full booking details in one place | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
211 | 761 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.21 | PAT-21 | Patient app — reschedule | PAT-21.04 | QA both platforms: Reschedule appointment matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Reschedule appointment | Move to another slot without calling the clinic | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
212 | 765 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.22 | PAT-22 | Patient app — cancel | PAT-22.04 | QA both platforms: Cancel appointment matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Cancel appointment | Cancel with reason, refund handled per policy | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
213 | 769 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.23 | PAT-23 | Patient app — waitlist offer | PAT-23.04 | QA both platforms: Waitlist offer matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Waitlist offer | Get offered a slot when one is freed by a cancellation | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
214 | 773 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.24 | PAT-24 | Patient app — instant consult request | PAT-24.04 | QA both platforms: Instant consult request matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Instant consult request | Request an immediate consultation with an available doctor | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
215 | 777 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.25 | PAT-25 | Patient app — queue and doctor offer | PAT-25.04 | QA both platforms: Queue & doctor offer matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Queue & doctor offer | See position in queue and accept an offered doctor | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
216 | 781 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.26 | PAT-26 | Patient app — device check | PAT-26.04 | QA both platforms: Device check matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.4 | Device check | Camera, microphone and network checked before the call | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
217 | 785 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.27 | PAT-27 | Patient app — waiting room | PAT-27.04 | QA both platforms: Waiting room matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.4 | Waiting room | Wait with live status until the doctor joins | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
218 | 789 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.28 | PAT-28 | Patient app — live video | PAT-28.04 | QA both platforms: Live video consultation matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.4 | Live video consultation | Face-to-face consultation from home | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
219 | 793 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.29 | PAT-29 | Patient app — recording consent | PAT-29.04 | QA both platforms: Recording consent matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.4 | Recording consent | Explicit consent requested before any recording | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
220 | 797 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.30 | PAT-30 | Patient app — join failure fallback | PAT-30.04 | QA both platforms: Fallback & join failure handling matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.4 | Fallback & join failure handling | Clear guidance if the call fails, with options to retry | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
221 | 801 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.31 | PAT-31 | Patient app — case-linked chat | PAT-31.04 | QA both platforms: Case-linked chat matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.4 | Case-linked chat | Chat tied to the consultation, not a loose message thread | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
222 | 805 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.32 | PAT-32 | Patient app — consultation summary | PAT-32.04 | QA both platforms: Consultation summary matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.4 | Consultation summary | Written summary available immediately after the call | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
223 | 809 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.33 | PAT-33 | Patient app — rejoin | PAT-33.04 | QA both platforms: Rejoin after dropped call matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.4 | Rejoin after dropped call | Rejoin the same consultation if the connection drops | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
224 | 813 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.34 | PAT-34 | Patient app — records timeline | PAT-34.04 | QA both platforms: Records timeline matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.5 | Records timeline | Complete visit history in date order | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
225 | 817 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.35 | PAT-35 | Patient app — consultation note (summary, not private notes) | PAT-35.04 | QA both platforms: Consultation note matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.5 | Consultation note | Doctor’s notes for each visit | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
226 | 821 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.36 | PAT-36 | Patient app — signed eRx (codes until pharmacy accept) | PAT-36.04 | QA both platforms: Signed digital prescription matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.5 | Signed digital prescription | Official prescription issued by the doctor | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
227 | 825 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.37 | PAT-37 | Patient app — document upload | PAT-37.04 | QA both platforms: Document upload matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.5 | Document upload | Upload reports, scans and previous prescriptions | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
228 | 829 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.38 | PAT-38 | Patient app — follow-up plan and tasks | PAT-38.04 | QA both platforms: Follow-up plan & tasks matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.6 | Follow-up plan & tasks | Clear next steps after each consultation | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
229 | 833 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.39 | PAT-39 | Patient app — symptom diary | PAT-39.04 | QA both platforms: Symptom diary matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.6 | Symptom diary | Record symptoms between visits | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
230 | 837 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.40 | PAT-40 | Patient app — progress tracking | PAT-40.04 | QA both platforms: Progress tracking matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.6 | Progress tracking | See improvement over time across visits | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
231 | 841 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.41 | PAT-41 | Patient app — medicines tab | PAT-41.04 | QA both platforms: Medicines tab matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.7 | Medicines tab | All medicine orders in one place | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
232 | 845 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.42 | PAT-42 | Patient app — start HomeoMeds order from eRx | PAT-42.04 | QA both platforms: Order start matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.7 | Order start | Start an order directly from the prescription | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
233 | 849 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.43 | PAT-43 | Patient app — pharmacy selection and quote | PAT-43.04 | QA both platforms: Pharmacy selection & quote matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.7 | Pharmacy selection & quote | Choose a licensed pharmacy and see the price before paying | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
234 | 853 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.44 | PAT-44 | Patient app — order review and consent | PAT-44.04 | QA both platforms: Order review & consent matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.7 | Order review & consent | Confirm and consent before the prescription is shared | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
235 | 857 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.45 | PAT-45 | Patient app — order tracking | PAT-45.04 | QA both platforms: Order tracking matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.7 | Order tracking | Live status from accepted to delivered | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
236 | 861 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.46 | PAT-46 | Patient app — order detail and refill | PAT-46.04 | QA both platforms: Order detail & refill matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.7 | Order detail & refill | Full order history and one-tap refill request | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
237 | 865 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.47 | PAT-47 | Patient app — write a review | PAT-47.04 | QA both platforms: Write a review matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.8 | Write a review | Rate and review the consultation | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
238 | 869 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.48 | PAT-48 | Patient app — my reviews and appeal | PAT-48.04 | QA both platforms: My reviews & appeal matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.8 | My reviews & appeal | Manage reviews and raise an appeal | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
239 | 873 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.49 | PAT-49 | Patient app — payments and refunds | PAT-49.04 | QA both platforms: Payments & refunds matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.8 | Payments & refunds | Full payment history and refund status | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
240 | 877 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.50 | PAT-50 | Patient app — profile and settings | PAT-50.04 | QA both platforms: Profile & settings matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.8 | Profile & settings | Manage personal details and preferences | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
241 | 881 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.51 | PAT-51 | Patient app — consent centre and data rights | PAT-51.04 | QA both platforms: Consent centre & data rights matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.8 | Consent centre & data rights | View, manage and withdraw consents; request data | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
242 | 885 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.52 | PAT-52 | Patient app — notifications centre | PAT-52.04 | QA both platforms: Notifications centre matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.8 | Notifications centre | All alerts in one place | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
243 | 889 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.53 | PAT-53 | Patient app — help centre and tickets | PAT-53.04 | QA both platforms: Help centre & support tickets matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.9 | Help centre & support tickets | Raise an issue and track it to resolution | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
244 | 893 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.54 | PAT-54 | Patient app — physical clinic booking | PAT-54.04 | QA both platforms: Physical clinic appointment matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.9 | Physical clinic appointment | Book an in-person visit as well as online | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
245 | 897 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.55 | PAT-55 | Patient app — assisted booking request | PAT-55.04 | QA both platforms: Assisted booking matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.9 | Assisted booking | Help for patients who need support booking | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
246 | 901 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.56 | PAT-56 | Patient app — low-data mode | PAT-56.04 | QA both platforms: Low-data mode matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.9 | Low-data mode | Works on slow or limited connections | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
247 | 905 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.57 | PAT-57 | Patient app — push notifications | PAT-57.04 | QA both platforms: Push notifications matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.9 | Push notifications | Booking confirmations, reminders, doctor ready, prescription issued, order updates | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
248 | 907 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.58 | PAT-58 | Patient app — iOS and Android store release, device matrix, and parity QA | PAT-58.02 | Parity QA spreadsheet: each PAT-01..57 on both OS | Regression | Patient Mobile | §2 + §18 | Patient mobile app iOS and Android | iOS and Android — onboarding, discovery, booking, payment, video consultation, records, prescriptions, follow-up, medicines, reviews, support, notifications | Patient Mobile App | QA | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 1 | Not Started |  | Edit on module sheet
249 | 912 | M18 | Doctor mobile app | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.1 | DMO-01 | Doctor app — login & identity (same login and same account as the web portal) | DMO-01.04 | QA: same DoctorId as web; reception accounts must not open doctor clinical actions | Regression | Doctor Mobile | §3 | Login & identity | Same login and same account as the web portal | Doctor Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
250 | 916 | M18 | Doctor mobile app | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.2 | DMO-02 | Doctor app — first-run onboarding (guided setup, number confirmation and permissions) | DMO-02.04 | QA: number mismatch blocked | Regression | Doctor Mobile | §3 | First-run onboarding | Guided setup, number confirmation and permissions | Doctor Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
251 | 920 | M18 | Doctor mobile app | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.3 | DMO-03 | Doctor app — notification permissions (push, microphone and camera handled properly) | DMO-03.04 | QA: deny each permission independently | Regression | Doctor Mobile | §3 | Notification permissions | Push, microphone and camera permissions handled properly | Doctor Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
252 | 924 | M18 | Doctor mobile app | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.4 | DMO-04 | Doctor app — today’s queue & schedule (the full day at a glance) | DMO-04.04 | QA: parity with web counts | Regression | Doctor Mobile | §3 | Today’s queue & schedule | The full day at a glance | Doctor Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
253 | 928 | M18 | Doctor mobile app | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.5 | DMO-05 | Doctor app — availability toggle (go online or offline, set working hours) | DMO-05.04 | QA: web and app status match within heartbeat | Regression | Doctor Mobile | §3 | Availability toggle | Go online or offline, set working hours | Doctor Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
254 | 932 | M18 | Doctor mobile app | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.6 | DMO-06 | Doctor app — push notifications (waiting, booking, reschedule, cancellation, refill, payment received) | DMO-06.04 | QA: each event type deep link | Regression | Doctor Mobile | §3 | Push notifications | Patient waiting, new booking, reschedule, cancellation, refill request, payment received | Doctor Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
255 | 936 | M18 | Doctor mobile app | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.7 | DMO-07 | Doctor app — patient context card (name, age, chief complaint and last visit) — NO case-taking | DMO-07.04 | QA: repertory endpoints never called from app | Regression | Doctor Mobile | §3 | Patient context card | Name, age, chief complaint and last visit before joining | Doctor Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
256 | 940 | M18 | Doctor mobile app | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.8 | DMO-08 | Doctor app — join consultation (video or audio from the phone) | DMO-08.04 | QA: web patient + app doctor | Regression | Doctor Mobile | §3 | Join consultation | Start the video or audio consultation from the phone | Doctor Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
257 | 944 | M18 | Doctor mobile app | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.9 | DMO-09 | Doctor app — refill approval (approve or reject repeat prescription requests) | DMO-09.04 | QA: reject reason; cannot edit snapshot | Regression | Doctor Mobile | §3 + §11 | Refill approval | Approve or reject repeat prescription requests | Doctor Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
258 | 948 | M18 | Doctor mobile app | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.10 | DMO-10 | Doctor app — earnings summary (today, this week, this month, with payout status) | DMO-10.04 | QA: matches /account figures ± rounding | Regression | Doctor Mobile | §3 + §16 | Earnings summary | Today, this week and this month, with payout status | Doctor Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
259 | 952 | M18 | Doctor mobile app | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.11 | DMO-11 | Doctor app — offline handling (weak connection or expired session) | DMO-11.04 | QA: airplane mode on join | Regression | Doctor Mobile | §3 | Offline handling | Clear behaviour on weak connection or expired session | Doctor Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
260 | 954 | M18 | Doctor mobile app | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.12 | DMO-12 | Doctor app — reliability monitoring (failures reported automatically) | DMO-12.02 | QA: simulated crash + join fail event | Regression | Doctor Mobile | §3 | Reliability monitoring | Failures are reported automatically, not left to a phone call | Doctor Mobile App | QA | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 1 | Not Started |  | Edit on module sheet
261 | 956 | M18 | Doctor mobile app | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.13 | DMO-13 | Doctor app — iOS and Android parity QA (queue, availability, notifications, context, video, refill, earnings) | DMO-13.02 | Parity QA DMO-01..12 both OS | Regression | Doctor Mobile | §3 + §18 | Doctor mobile app iOS and Android | iOS and Android — queue, availability, notifications, patient context, video consultation, refill approval, earnings | Doctor Mobile App | QA | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 1 | Not Started |  | Edit on module sheet
262 | 960 | M19 | Reports, NFR & delivery gate | QA | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.1 | RPT-01 | Admin overview dashboard — platform-wide activity at a glance (replace Velzon ecommerce) | RPT-01.04 | QA: login as admin never shows fake store visits | Regression | Reports | §16 + §7.2 | Admin overview dashboard / Admin dashboard | Platform-wide activity at a glance / Live overview of the whole platform | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
263 | 964 | M19 | Reports, NFR & delivery gate | QA | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.2 | RPT-02 | Doctor practice statistics — patient and consultation trends (extend existing charts) | RPT-02.04 | QA: empty new clinic | Regression | Reports | §16 + §5.1 | Doctor practice statistics | Patient and consultation trends | Doctor Web | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
264 | 968 | M19 | Reports, NFR & delivery gate | QA | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.3 | RPT-03 | Follow-up analysis — due/overdue patients and follow-up conversion | RPT-03.04 | QA: overdue vs due buckets | Regression | Reports | §16 | Follow-up analysis | Which patients are due or overdue for follow-up, and follow-up conversion | Doctor Web | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
265 | 972 | M19 | Reports, NFR & delivery gate | QA | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.4 | RPT-04 | Clinic performance analysis — appointments, slot utilisation, no-shows, cancellations, waiting time and revenue | RPT-04.04 | QA: cancelled excluded from completed; revenue uses ledger not client | Regression | Reports | §16 | Clinic performance analysis | Appointments, slot utilisation, no-shows, cancellations, waiting time and revenue | Doctor Web | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
266 | 975 | M19 | Reports, NFR & delivery gate | QA | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.5 | RPT-05 | Payment reconciliation report — bookings matched against payments | RPT-05.03 | QA: unmatched rows included | Regression | Reports | §16 + §7.2 | Payment reconciliation report / Consult booking & payment reconciliation | Bookings matched against payments / Match every booking against every payment | Admin + Account | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
267 | 978 | M19 | Reports, NFR & delivery gate | QA | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.6 | RPT-06 | Settlement & payout reports — amounts due and paid to doctors and pharmacies | RPT-06.03 | QA: pharmacy lines appear only after HomeoMeds | Regression | Reports | §16 + §8 | Settlement & payout reports | Amounts due and paid to doctors and pharmacies | Account | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
268 | 980 | M19 | Reports, NFR & delivery gate | QA | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.7 | RPT-07 | GST & invoice reports (reporting surface of FIN-08) | RPT-07.02 | QA: number series gaps flagged | Regression | Reports | §16 + §8 | GST & invoice reports | Tax reporting | Account | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
269 | 984 | M19 | Reports, NFR & delivery gate | QA | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.8 | RPT-08 | Doctor earnings summary — daily, weekly and monthly earnings with payout status (web + same API as DMO-10) | RPT-08.04 | QA: payout pending vs paid | Regression | Reports | §16 + §3 | Doctor earnings summary | Daily, weekly and monthly earnings with payout status | Doctor Web + App | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
270 | 988 | M19 | Reports, NFR & delivery gate | QA | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.9 | RPT-09 | Medicine order reports — order volumes, fulfilment and exceptions | RPT-09.04 | QA: cancelled orders not counted as delivered | Regression | Reports | §16 + §12 | Medicine order reports | Order volumes, fulfilment and exceptions | Admin + Account | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
271 | 992 | M19 | Reports, NFR & delivery gate | QA | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.10 | RPT-10 | Platform users remaining 20% — import, export and activation control | RPT-10.04 | QA: export contains only permitted fields | Regression | Admin | §7.2 | Platform users | Manage all users with import, export and activation control | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | Edit on module sheet
272 | 993 | M19 | Reports, NFR & delivery gate | QA | 19 | Phase 19 — Cross-surface QA, NFR, delivery summary gate (PDF §1 + §18) | 19.1 | QA-01 | One ecosystem proof — patient, appointment, prescription and payment created anywhere are visible everywhere | QA-01.01 | E2E: Reception creates patient+appt → Doctor board → sign eRx → Patient app sees codes → Pharmacy accept OTP → patient sees names+pay → Account ledger S2 and S5 | Regression | QA | §1 + §18 | One connected ecosystem | A patient, an appointment, a prescription and a payment created anywhere in the system are visible everywhere else | All | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | Edit on module sheet
273 | 994 | M19 | Reports, NFR & delivery gate | QA | 19 | Phase 19 — Cross-surface QA, NFR, delivery summary gate (PDF §1 + §18) | 19.1 | QA-01 | One ecosystem proof — patient, appointment, prescription and payment created anywhere are visible everywhere | QA-01.02 | E2E: Patient app books+pays tele → doctor app join → summary+eRx → refill on doctor app | Regression | QA | §1 + §18 | One connected ecosystem | A patient, an appointment, a prescription and a payment created anywhere in the system are visible everywhere else | All | QA | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 1 | Not Started |  | Edit on module sheet
274 | 995 | M19 | Reports, NFR & delivery gate | QA | 19 | Phase 19 — Cross-surface QA, NFR, delivery summary gate (PDF §1 + §18) | 19.1 | QA-01 | One ecosystem proof — patient, appointment, prescription and payment created anywhere are visible everywhere | QA-01.03 | Negative: Admin cannot payout; Account cannot edit repertory | Regression | QA | §1 + §18 | One connected ecosystem | A patient, an appointment, a prescription and a payment created anywhere in the system are visible everywhere else | All | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
275 | 996 | M19 | Reports, NFR & delivery gate | QA | 19 | Phase 19 — Cross-surface QA, NFR, delivery summary gate (PDF §1 + §18) | 19.2 | QA-02 | Delivery summary gate — every area in PDF §18 signed off | QA-02.01 | Traceability review: 01_PDF_Coverage every row has Main Task ID and final Status | Regression | QA | §18 | Summary of delivery | All features listed in this document are included in the delivery scope. | Programme | QA | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 0 | N/A |  | Edit on module sheet
276 | 997 | M19 | Reports, NFR & delivery gate | QA | 19 | Phase 19 — Cross-surface QA, NFR, delivery summary gate (PDF §1 + §18) | 19.2 | QA-02 | Delivery summary gate — every area in PDF §18 signed off | QA-02.02 | Do not ship Velzon demo tickets/KYC/ecommerce as product | Regression | QA | §18 | Summary of delivery | All features listed in this document are included in the delivery scope. | Programme | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
277 | 999 | M19 | Reports, NFR & delivery gate | QA | 19 | Phase 19 — Cross-surface QA, NFR, delivery summary gate (PDF §1 + §18) | 19.3 | NFR-01 | NFR — performance, low-data, reliability, secrets, dual-API freeze | NFR-01.02 | Performance: slot lock under concurrent public booking | Regression | NFR | §2.9 + §3 + §17 | Low-data mode / Reliability monitoring / Secure login | Works on slow connections; failures reported automatically; credentials protected | All | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | Edit on module sheet
278 | 1000 | M19 | Reports, NFR & delivery gate | QA | 19 | Phase 19 — Cross-surface QA, NFR, delivery summary gate (PDF §1 + §18) | 19.3 | NFR-01 | NFR — performance, low-data, reliability, secrets, dual-API freeze | NFR-01.03 | Patient low-data mode QA on 2G profile | Regression | NFR | §2.9 + §3 + §17 | Low-data mode / Reliability monitoring / Secure login | Works on slow connections; failures reported automatically; credentials protected | All | QA | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 1 | Not Started |  | Edit on module sheet

## 07_Main_Tasks_by_Module
MAIN TASKS — Overall Status is Done only when every sub-task of this Main Task is Done (all in-scope Frontend/Backend/Database/API/Mobile/Integration statuses Done on the module sheet).
Seq | Dev Module Code | Dev Module | Phase | Main Task ID | Main Task | Work Type(s) | Tracks | Web | UI | Mobile | QA | Sub-tasks | PDF Feature | AS-IS | TO-BE | Overall Status (live)
1 | M00 | PRE — Client gates | PRE | PRE-01 | Decide settlement model — Homeocentrum holds all money (food-delivery / quick-commerce pattern) | Client Decision, Configuration | Web | Yes | — | — | — | 3 | Every transaction passes through Homeocentrum | Only doctor SaaS subscription via client-side Razorpay; no consult/medicine ledger | Written decision: platform-held funds + periodic NEFT (v1) vs Razorpay Route (v2) | In Progress
2 | M00 | PRE — Client gates | PRE | PRE-02 | Decide reception cash policy — clinic retains vs remits to Homeocentrum | Client Decision, Configuration | Web | Yes | — | — | — | 3 | Reception payment collection | No reception collection; no S3 ledger | Policy for cash/UPI at clinic: retain at clinic (still ledgered) or remit | In Progress
3 | M00 | PRE — Client gates | PRE | PRE-03 | Vendor and legal gates — video SDK, SMS, WhatsApp, push, DPDP copy | Client Decision | Web | Yes | — | — | — | 5 | Telemedicine + notifications + consent | WhatsApp Meta Cloud partial; no video SDK; no SMS provider; no FCM; privacy/terms incomplete for DPDP/tele/pharmacy | Named vendors + DPDP-ready legal copy before those phases start | In Progress
4 | M01 | Foundation & Security | 0 | FND-01 | One connected ecosystem — shared keys so a patient, appointment, prescription and payment created anywhere are visible everywhere | New, Existing Modification, Regression | Web, QA | Yes | — | — | Yes | 4 | One connected ecosystem serving six types of users | Doctor/Admin/Reception web only; Patient, Account, Pharmacy roles do not exist; no shared payment or eRx keys | Canonical keys: UserId/DoctorId, PatientId, PatientAppId, CaseId, ErxId, LedgerTxnId, MedicineOrderId — used by every surface | Not Started
5 | M01 | Foundation & Security | 0 | FND-02 | Delivery footprint — 2 mobile apps · 5 web portals · payment · telemedicine · digital prescription · HomeoMeds (programme skeleton) | New, Existing Improvement | Web, UI, Mobile | Yes | Yes | Yes | — | 4 | Delivery covers | 1 web SPA (Admin/Doctor/Reception + marketing). No patient app, doctor app, Account portal, Pharmacy console | Repo/route skeleton: Patient Website, Doctor Web, Reception, Admin, Account (+ Pharmacy console under HomeoMeds); Patient + Doctor mobile later | In Progress
6 | M01 | Foundation & Security | 0 | SEC-01 | Secure login — protected credentials for every user type | Data Migration, Existing Modification, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Secure login | POST /Account/Login on classic API; JWT in sessionStorage; doctor/user passwords compared plaintext; reception hashed on classic; fakeBackend() still mounted | Hashed passwords; Role claim on JWT; disable fake backend for production paths; Patient OTP login is Phase 8 (not password) | Not Started
7 | M01 | Foundation & Security | 0 | SEC-02 | Secure password reset — time-limited reset links (stop plaintext email + fake thunk) | New, Existing Modification, Existing Improvement, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Secure password reset | /forgot-password UI exists; thunk uses fake/Firebase; POST /users/ForgetPassword emails plaintext password | Tokenised reset (hash, TTL); email contains link only; ChangePassword for logged-in user | Not Started
8 | M01 | Foundation & Security | 0 | SEC-03 | Session control — proper sign-out across web and mobile | Existing Improvement, New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Session control | Client clears sessionStorage; no server logout / token revoke; UserLoginStatus unused | POST Logout persists login status; optional token denylist; mobile will call the same API in Phase 16/17 | Not Started
9 | M01 | Foundation & Security | 0 | SEC-04 | Role-based access — each role sees only what it is permitted to see | Existing Improvement, New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Role-based access | RoleMaster + RoleDetail + MenuMaster exist; GetMenuByRole commented out on .NET 8; no per-route frontend ACL — any authenticated URL works | Re-enable GetMenuByRole; AuthProtected deny-by-default; [Authorize(Roles=)] on money/clinical APIs; Account cannot edit repertory; Admin cannot approve payouts | Not Started
10 | M01 | Foundation & Security | 0 | SEC-05 | Patient data protection — health records restricted to the treating doctor and the patient | Existing Improvement, Existing Modification, Regression | Web, QA | Yes | — | — | Yes | 3 | Patient data protection | Many repertory APIs have [Authorize] commented; directory browsing enabled for /attachments and /Blogs; no patient-scoped ACL on case data | Every case/Rx/note/lab query filtered by treating DoctorId (or PatientId for patient token); disable directory browsing | Not Started
11 | M01 | Foundation & Security | 0 | SEC-06 | Consent records infrastructure — every consent captured, stored and reviewable | New, Existing Improvement, Regression | Web, QA | Yes | — | — | Yes | 4 | Consent records | AudioCaseConsentLog exists for audio case taking only | ConsentRecord (PatientId, Type, Version, GrantedAt, WithdrawnAt, SourceSurface) covering privacy, booking, recording, pharmacy share, marketing | Not Started
12 | M01 | Foundation & Security | 0 | SEC-07 | OTP verification infrastructure — applied to sensitive actions including payouts and pharmacy acceptance | New, Regression | Web, QA | Yes | — | — | Yes | 4 | OTP verification | No generic OTP control plane; patient OTP login does not exist | OtpChallenge + OtpAuditLog; Account/Admin can query who/when/entity/success without seeing card data | Not Started
13 | M01 | Foundation & Security | 0 | SEC-08 | Complete audit trail — who did what and when across payments, prescriptions and approvals | New, Regression | Web, QA | Yes | — | — | Yes | 3 | Complete audit trail | No platform-wide audit; no AppointmentChangeLog; no payment webhook store | Append-only AuditEvent for money, eRx sign, credentialing, payout, pharmacy accept; payments get a dedicated trail in Phase 6 | Not Started
14 | M01 | Foundation & Security | 0 | SEC-09 | Secure documents — prescriptions, reports and uploads protected from unauthorised access | New, Regression | Web, QA | Yes | — | — | Yes | 3 | Secure documents | Attachments served with directory browsing; no signed URLs; no patient upload module | Authorised download; virus-scan hook; patient uploads in Phase 15 use this store | Not Started
15 | M02 | Admin clinical masters | 1 | ADM-R01 | Keep and harden Admin Repertory sections (do not rebuild) | Existing, Existing Improvement | Web, QA | Yes | — | — | Yes | 3 | Repertory sections | Admin Repertory section CRUD live (pages/Admin/Repertory) | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | In Progress
16 | M02 | Admin clinical masters | 1 | ADM-R02 | Keep and harden Admin Subsection & rubric tree (do not rebuild) | Existing, Existing Improvement | Web, QA | Yes | — | — | Yes | 3 | Subsection & rubric tree | Hierarchical subsection/rubric tree + Excel import/export live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | In Progress
17 | M02 | Admin clinical masters | 1 | ADM-R03 | Keep and harden Admin Rubric–remedy mapping (do not rebuild) | Existing, Existing Improvement | Web, QA | Yes | — | — | Yes | 3 | Rubric–remedy mapping | Rubric-remedy mapping by author/grade live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | In Progress
18 | M02 | Admin clinical masters | 1 | ADM-R04 | Keep and harden Admin Remedy-linked rubrics (do not rebuild) | Existing, Existing Improvement | Web, QA | Yes | — | — | Yes | 3 | Remedy-linked rubrics | Remedial-rubrics viewer live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | In Progress
19 | M02 | Admin clinical masters | 1 | ADM-R05 | Keep and harden Admin Language master (do not rebuild) | Existing, Existing Improvement | Web, QA | Yes | — | — | Yes | 3 | Language master | Language master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | In Progress
20 | M02 | Admin clinical masters | 1 | ADM-R06 | Keep and harden Admin Body part master (do not rebuild) | Existing, Existing Improvement | Web, QA | Yes | — | — | Yes | 3 | Body part master | Body part master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | In Progress
21 | M02 | Admin clinical masters | 1 | ADM-R07 | Keep and harden Admin Intensity master (do not rebuild) | Existing, Existing Improvement | Web, QA | Yes | — | — | Yes | 3 | Intensity master | Intensity master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | In Progress
22 | M02 | Admin clinical masters | 1 | ADM-R08 | Keep and harden Admin Remedy master (do not rebuild) | Existing, Existing Improvement | Web, QA | Yes | — | — | Yes | 3 | Remedy master | Remedy master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | In Progress
23 | M02 | Admin clinical masters | 1 | ADM-R09 | Keep and harden Admin Remedy grade master (do not rebuild) | Existing, Existing Improvement | Web, QA | Yes | — | — | Yes | 3 | Remedy grade master | Remedy grade master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | In Progress
24 | M02 | Admin clinical masters | 1 | ADM-M01 | Keep and harden Admin Author master (do not rebuild) | Existing, Existing Improvement | Web, QA | Yes | — | — | Yes | 3 | Author master | Author master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | In Progress
25 | M02 | Admin clinical masters | 1 | ADM-M02 | Keep and harden Admin Materia medica master (do not rebuild) | Existing, Existing Improvement | Web, QA | Yes | — | — | Yes | 3 | Materia medica master | MM master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | In Progress
26 | M02 | Admin clinical masters | 1 | ADM-M03 | Keep and harden Admin Materia medica heads (do not rebuild) | Existing, Existing Improvement | Web, QA | Yes | — | — | Yes | 3 | Materia medica heads | MM heads live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | In Progress
27 | M02 | Admin clinical masters | 1 | ADM-M04 | Keep and harden Admin Materia medica remedies (do not rebuild) | Existing, Existing Improvement | Web, QA | Yes | — | — | Yes | 3 | Materia medica remedies | Remedy-wise MM viewer live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | In Progress
28 | M02 | Admin clinical masters | 1 | ADM-D01 | Keep and harden Admin Diagnosis system (do not rebuild) | Existing, Existing Improvement | Web, QA | Yes | — | — | Yes | 3 | Diagnosis system | Diagnosis system CRUD live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | In Progress
29 | M02 | Admin clinical masters | 1 | ADM-D02 | Keep and harden Admin Diagnosis therapeutics (do not rebuild) | Existing, Existing Improvement | Web, QA | Yes | — | — | Yes | 3 | Diagnosis therapeutics | Therapeutics details live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | In Progress
30 | M02 | Admin clinical masters | 1 | ADM-D03 | Keep and harden Admin Diagnosis conditions (do not rebuild) | Existing, Existing Improvement | Web, QA | Yes | — | — | Yes | 3 | Diagnosis conditions | Conditions + keyword→rubric live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | In Progress
31 | M02 | Admin clinical masters | 1 | ADM-A01 | Keep and harden Admin Drug system (do not rebuild) | Existing, Existing Improvement | Web, QA | Yes | — | — | Yes | 3 | Drug system | Drug system CRUD live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | In Progress
32 | M02 | Admin clinical masters | 1 | ADM-A02 | Keep and harden Admin Drug group (do not rebuild) | Existing, Existing Improvement | Web, QA | Yes | — | — | Yes | 3 | Drug group | Drug group CRUD live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | In Progress
33 | M02 | Admin clinical masters | 1 | ADM-A03 | Keep and harden Admin Allopathic drug & side effects (do not rebuild) | Existing, Existing Improvement | Web, QA | Yes | — | — | Yes | 3 | Allopathic drug & side effects | Allopathic drug + serious/other/adverse live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | In Progress
34 | M02 | Admin clinical masters | 1 | ADM-Q01 | Keep and harden Admin Question section, group & sub-group (do not rebuild) | Existing, Existing Improvement | Web, QA | Yes | — | — | Yes | 3 | Question section, group & sub-group | Existance / question group / subgroup CRUD live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | In Progress
35 | M02 | Admin clinical masters | 1 | ADM-Q02 | Keep and harden Admin Clinical question mapping (do not rebuild) | Existing, Existing Improvement | Web, QA | Yes | — | — | Yes | 3 | Clinical question mapping | Clinical questions mapped to body parts and rubrics live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | In Progress
36 | M02 | Admin clinical masters | 1 | ADM-3D1 | Keep and harden Admin 3D mesh key master (do not rebuild) | Existing, Existing Improvement | Web, QA | Yes | — | — | Yes | 3 | 3D mesh key master | Mesh key master on .NET 8 live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | In Progress
37 | M02 | Admin clinical masters | 1 | ADM-3D2 | Keep and harden Admin 3D section master (do not rebuild) | Existing, Existing Improvement | Web, QA | Yes | — | — | Yes | 3 | 3D section master | 3D section master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | In Progress
38 | M02 | Admin clinical masters | 1 | ADM-3D3 | Keep and harden Admin 3D hotspots (do not rebuild) | Existing, Existing Improvement | Web, QA | Yes | — | — | Yes | 3 | 3D hotspots | Hotspot master live; doctor viewer consumes them | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | In Progress
39 | M02 | Admin clinical masters | 1 | ADM-B01 | Business Management — Doctor qualifications (existing, used later by credentialing) | Existing, Existing Improvement | Web, QA | Yes | — | — | Yes | 3 | Doctor qualifications | Qualifications CRUD on newer API live; used by RegisterDoctor | Keep; credentialing Phase 8 will reference QualificationId | In Progress
40 | M02 | Admin clinical masters | 1 | ADM-B02 | Business Management — Lab & imaging test catalog (existing, used by eRx lab orders) | Existing, Existing Improvement | Web, QA | Yes | — | — | Yes | 3 | Lab & imaging test catalog | Labs & imaging CRUD live; Patient Board orders from this catalogue | Keep; eRx Phase 10 continues to use the same catalogue | In Progress
41 | M02 | Admin clinical masters | 1 | ADM-B03 | Business Management — Subscription packages (existing S1 SaaS; later tied to Account ledger) | Existing, Existing Improvement | Web, QA | Yes | — | — | Yes | 3 | Subscription packages | Package CRUD live; Razorpay buy/renew partial (no webhook) | Do not overload PackageEntryDetail for consult/medicine money; Phase 6 ports payment verification | In Progress
42 | M02 | Admin clinical masters | 1 | ADM-B04 | Business Management — Roles & menu permissions (existing DB, runtime ACL leftover) | Existing Improvement, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Roles & menu permissions | Role CRUD screens live; runtime GetMenuByRole commented; no frontend route ACL | This is the product surface for SEC-04; complete wiring here | In Progress
43 | M03 | Doctor clinical workspace | 2 | CLN-01 | Clinical workspace — single screen for the entire consultation | Existing Improvement, Existing, Regression | Web, UI, QA | Yes | Yes | — | Yes | 3 | Clinical workspace | PatientBoard.js (~13.5k) is the workspace; ~90% — missing payment/tele/eRx header status | Keep one screen; add header chips for payment, tele session, signed eRx (chips light up as later phases land) | In Progress
44 | M03 | Doctor clinical workspace | 2 | CLN-02 | Manual case taking — structured case taking (keep) | Existing, Existing Improvement | Web, QA | Yes | — | — | Yes | 3 | Manual case taking | Classic case-taking tabs live | Regression only; do not rebuild | Not Started
45 | M03 | Doctor clinical workspace | 2 | CLN-03 | Body parts & intensity selection (keep) | Existing, Existing Improvement | Web, QA | Yes | — | — | Yes | 3 | Body parts & intensity selection | Body Parts tab + intensity chips live | Regression; intensity master from Phase 1 still drives chips | Not Started
46 | M03 | Doctor clinical workspace | 2 | CLN-04 | Clinical questions — guided questions by section, group and sub-group (keep) | Existing, Existing Improvement | Web, QA | Yes | — | — | Yes | 3 | Clinical questions | Questions tab loads Existance taxonomy live | Regression | Not Started
47 | M03 | Doctor clinical workspace | 2 | CLN-05 | Diagnosis, therapeutics & pattern search (keep) | Existing, Existing Improvement | Web, QA | Yes | — | — | Yes | 3 | Diagnosis, therapeutics & pattern search | Clinical Pattern tab live (13 keyword tabs + therapeutics) | Regression | Not Started
48 | M03 | Doctor clinical workspace | 2 | CLN-06 | Repertory rubric search & selection (keep) | Existing, Existing Improvement | Web, QA | Yes | — | — | Yes | 3 | Repertory rubric search & selection | Repertory tree + search live | Regression; small UX polish allowed but not a rewrite | Not Started
49 | M03 | Doctor clinical workspace | 2 | CLN-07 | Manage selected rubrics — review, edit and remove (remaining ~10%) | Existing Improvement, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Manage selected rubrics | Clipboard exists; confirm-delete / intensity-edit incomplete | Confirm delete; edit intensity on selected rubric; no accidental wipe | Not Started
50 | M03 | Doctor clinical workspace | 2 | CLN-08 | Audio case taking — record and receive suggested rubrics (keep engine; do not rebuild) | Existing, Existing Improvement | Web, QA | Yes | — | — | Yes | 3 | Audio case taking | Whisper + rubric engines + CaseTaking UI live on .NET 8 | Keep; follow existing AUDIO_CASE_TAKING_* docs; accuracy is the next task | Not Started
51 | M03 | Doctor clinical workspace | 2 | CLN-09 | Improved rubric accuracy — enhanced accuracy rules for audio-based rubric suggestions | Existing Improvement, Regression | Web, UI, QA | Yes | Yes | — | Yes | 3 | Improved rubric accuracy | Engine + admin metaphors/aliases exist; accuracy rules still in progress (~50%) | Complete accuracy rules per AUDIO_CASE_TAKING_AI_ENGINE docs; metaphor/alias QA | Not Started
52 | M03 | Doctor clinical workspace | 2 | CLN-10 | Materia medica reference during consultation (remaining ~10%) | Existing Improvement, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Materia medica reference | MM tab + repertorize differential accordion ~90% | Faster head navigation during case; do not rebuild MM masters | Not Started
53 | M03 | Doctor clinical workspace | 2 | CLN-11 | Allopathic drug side-effect lookup (keep) | Existing, Existing Improvement | Web, QA | Yes | — | — | Yes | 3 | Allopathic drug side-effect lookup | Adverse Effect tab live | Regression | Not Started
54 | M03 | Doctor clinical workspace | 2 | CLN-12 | Repertorization & elimination (remaining ~10%) | Existing Improvement, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Repertorization & elimination | Common/uncommon/elimination live ~90% | Stability polish; Center of Gravity is a NEW panel on the same rubrics (next task) | Not Started
55 | M03 | Doctor clinical workspace | 2 | CLN-13 | Center of Gravity — new analysis identifying the central remedy of the case, with reasoning shown | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Center of Gravity | Does not exist | POST /api/Repertorization/CenterOfGravity from selected rubric ids + intensities; UI panel with explainability | Not Started
56 | M03 | Doctor clinical workspace | 2 | CLN-14 | Lab orders & lab entries (keep; later also sit on eRx) | Existing, Existing Improvement | Web, QA | Yes | — | — | Yes | 3 | Lab orders & lab entries | Lab order + result entry on prescription modal live | Keep; when eRx splits notes from Rx, labs stay on the prescription/eRx side | Not Started
57 | M03 | Doctor clinical workspace | 2 | CLN-15 | Appointment history notes (keep; split from eRx in Phase 10) | Existing, Existing Improvement | Web, QA | Yes | — | — | Yes | 3 | Appointment history notes | AppointmentHistoryNote APIs live (classic); currently mixed into Rx modal tabs | Keep save/get; Phase 10 moves UX outside Rx modal and adds NoteType / IsErxExcluded | Not Started
58 | M03 | Doctor clinical workspace | 2 | CLN-16 | Complaints & case details — wire Patient Board to existing SaveComplaints / SaveCaseDetails (~20% today) | Existing Improvement, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Complaints & case details | Classic SaveComplaints / SaveCaseDetails APIs exist; Patient Board does not call them | Call the existing APIs from the board; Reception case-paper (Phase 5) uses a subset | Not Started
59 | M03 | Doctor clinical workspace | 2 | CLN-17 | Patient back history — complete history of visits, notes, prescriptions and payments | Existing Improvement, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Patient back history | History panel ~70%; no payment line (payments do not exist yet) | Timeline: visits, notes, eRx, labs; payment row added when Phase 6 lands (placeholder now) | Not Started
60 | M03 | Doctor clinical workspace | 2 | CLN-18 | Export case data — download the full case in Excel or PDF | Existing Improvement, New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 3 | Export case data | Newer ExportCasesToExcel exists; no Patient Board export UI; no PDF | Toolbar Excel + PDF using existing Excel API + new PDF renderer; exclude private notes from patient-facing PDF (eRx print is Phase 10) | Not Started
61 | M03 | Doctor clinical workspace | 2 | CLN-19 | Session restore — continue exactly where the doctor left off, across multiple patients (keep) | Existing, Existing Improvement | Web, QA | Yes | — | — | Yes | 3 | Session restore | Up to 5 in-memory sessions + DoctorPatientBoardBackup live | Regression; header stack remains | Not Started
62 | M03 | Doctor clinical workspace | 2 | CLN-20 | 3D anatomy viewer — interactive 3D body model linked to rubric search (remaining ~50%) | Existing Improvement, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | 3D anatomy viewer | three.js viewer + hotspot→search live; incomplete mesh coverage / UX | Complete GLB/hotspot coverage; mobile fallback later; admin 3D masters already in Phase 1 | Not Started
63 | M04 | Doctor daily operations | 3 | DOC-01 | Doctor home dashboard — complete overview of the working day (remaining ~30%) | Existing Improvement, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Doctor home dashboard | Widgets + BestSellingProducts ~70%; missing online toggle, tele queue, payment badges, follow-up due | Extend, do not replace; later phases light up tele/payment chips | Not Started
64 | M04 | Doctor daily operations | 3 | DOC-02 | Patient counts & waiting list — live counts by status with quick actions (keep; extend paid/unpaid) | Existing, Existing Improvement | Web, QA | Yes | — | — | Yes | 3 | Patient counts & waiting list | Status buckets WAITING, WALK-IN, NOT ARRIVED, E-CONSULT, REMAINING, COMPLETED live | Keep; add CANCELLED in Phase 4; paid/unpaid badge in Phase 6 | Not Started
65 | M04 | Doctor daily operations | 3 | DOC-03 | Patient search, list & open case (remaining ~10%) | Existing Improvement, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Patient search, list & open case | Search/list/open ~90%; missing last visit, unpaid, family filters | Add last-visit column; unpaid/family after those modules exist | Not Started
66 | M04 | Doctor daily operations | 3 | DOC-04 | Add new patient — register a patient in seconds (keep) | Existing, Existing Improvement | Web, QA | Yes | — | — | Yes | 3 | Add new patient | Create patient live | Regression; public self-registration is a different Patient identity in Phase 9 | Not Started
67 | M04 | Doctor daily operations | 3 | DOC-05 | Import patients — bring existing patient records in bulk (keep) | Existing, Existing Improvement | Web, QA | Yes | — | — | Yes | 3 | Import patients | Import live | Regression | Not Started
68 | M04 | Doctor daily operations | 3 | DOC-06 | Export patients — download patient data in Excel, CSV or PDF (keep) | Existing Improvement, Regression | Web, UI, QA | Yes | Yes | — | Yes | 3 | Export patients | Export live (confirm PDF vs Excel/CSV in QA) | If PDF is missing, add it as Existing Improvement; do not skip the PDF wording in the PDF | Not Started
69 | M04 | Doctor daily operations | 3 | DOC-07 | Recent activity panel (keep) | Existing, Existing Improvement | Web, QA | Yes | — | — | Yes | 3 | Recent activity panel | Recent activity live | Regression; later include payment/tele events when those exist | Not Started
70 | M04 | Doctor daily operations | 3 | DOC-08 | Patient statistics charts (keep; foundation for clinic performance in Phase 18) | Existing, Existing Improvement | Web, QA | Yes | — | — | Yes | 3 | Patient statistics charts | GetPatientStats / GetPatientStatsCharts + ApexCharts live | Keep; clinic performance report extends this in Phase 18 | Not Started
71 | M04 | Doctor daily operations | 3 | DOC-09 | Manage reception staff — add, edit and remove reception users (backend done, UI absent) | Existing Improvement, Regression | Web, UI, QA | Yes | Yes | — | Yes | 3 | Manage reception staff | .NET 8 api/ReceptionStaff CRUD exists; no SPA page | List/add/edit/disable at /doctor/reception-staff; doctor owns the staff record | Not Started
72 | M04 | Doctor daily operations | 3 | DOC-10 | Doctor profile — clinic details, consultation fee, photo, qualifications, working hours, bank details | Existing Improvement, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Doctor profile | /profile is Velzon first_name only (~20%); credentials sit on Doctor entity; no fee/KYC UI | Real doctor profile: clinic, photo, qualifications, consult fee (feeds Phase 6), hours (feeds schedule), bank KYC (feeds Account payees) | Not Started
73 | M05 | Appointments & scheduling | 4 | APT-01 | Appointment list & waiting patients — full day view with live status (keep; later payment/tele) | Existing, Existing Improvement | Web, QA | Yes | — | — | Yes | 3 | Appointment list & waiting patients | Day list + status live | Keep; reschedule/cancel/payment attach to this list | Not Started
74 | M05 | Appointments & scheduling | 4 | APT-02 | Create new appointment — persist visit type, consultation mode and fee | Existing Improvement, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Create new appointment | Create appointment ~90%; Formik modal has no VisitType / ConsultMode / fee | VisitType First/Follow-up; ConsultMode In-clinic / E-Consult; fee display from doctor profile / ConsultFeeConfig | Not Started
75 | M05 | Appointments & scheduling | 4 | APT-03 | Appointment status update — move patients through the visit stages (keep) | Existing, Existing Improvement | Web, QA | Yes | — | — | Yes | 3 | Appointment status update | Status transitions live | Keep; add CANCELLED in APT-06; do not reuse DeleteStatus as cancel | Not Started
76 | M05 | Appointments & scheduling | 4 | APT-04 | Appointment time update — adjust timings as the day runs (keep; distinct from formal reschedule) | Existing, Existing Improvement | Web, QA | Yes | — | — | Yes | 3 | Appointment time update | UpdateAppointmentTime live — changes a time only; no audit/notify | Keep same-day time tweak; formal reschedule (old→new, notify, conflict) is APT-05 | Not Started
77 | M05 | Appointments & scheduling | 4 | APT-05 | Reschedule appointment — move to a new slot with automatic patient notification (NEW — not a rename of UpdateAppointmentTime) | New, New Integration, Regression | Web, UI, QA | Yes | Yes | — | Yes | 5 | Reschedule appointment | Time can be edited; no formal Reschedule (audit, notify, old→new confirm) | POST RescheduleAppointment; AppointmentChangeLog; conflict 409 with alternatives; SMS/WhatsApp fan-out (notify failure must not roll back) | Not Started
78 | M05 | Appointments & scheduling | 4 | APT-06 | Cancel appointment — reason, free the slot, trigger refund where applicable (NEW CANCELLED status — do NOT reuse DeleteStatus) | New, New Integration, Regression | Web, UI, QA | Yes | Yes | — | Yes | 5 | Cancel appointment | No CANCELLED; DeleteStatus is soft-delete only | CANCELLED + reason fields; free slot; waitlist hook; if PAID evaluate refund policy (Phase 6/7) | Not Started
79 | M05 | Appointments & scheduling | 4 | APT-07 | Daily schedule setup — define working days, hours and break times (promote modal to first-class screen) | Existing Improvement, Regression | Web, UI, QA | Yes | Yes | — | Yes | 3 | Daily schedule setup | DailyScheduleSetupModal + GetDailySchedule / SaveDailySchedule exist; not a first-class screen (draft marked 0%) | Promote to /doctor/schedule with week grid and copy-day; reuse existing APIs — do not rebuild | Not Started
80 | M05 | Appointments & scheduling | 4 | APT-08 | Appointment slot grid — visual slot-by-slot view of the day (keep; public booking reuses this) | Existing, Existing Improvement | Web, QA | Yes | — | — | Yes | 3 | Appointment slot grid | Slot picker / grid live | Keep; Phase 9 public APIs reuse the same slot engine | Not Started
81 | M05 | Appointments & scheduling | 4 | APT-09 | Consultation payment status on every appointment (schema now; values live in Phase 6) | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Consultation payment status | No PaymentStatus on appointment | Add PaymentStatus UNPAID / PENDING / PAID / FAILED / PAY_AT_CLINIC / REFUNDED; UI badge; source of truth is webhook in Phase 6 not the client screen | Not Started
82 | M05 | Appointments & scheduling | 9 | WEB-11 | Waitlist offer — get offered a slot when one is freed by a cancellation (patient website + later app) | New, New Integration, Regression | Web, UI, QA | Yes | Yes | — | Yes | 5 | Waitlist offer | Cancel hook stub in Phase 4; no waitlist records | BookingWaitlist; on cancel, offer FIFO; timeout | Not Started
83 | M05 | Appointments & scheduling | 15 | CON-09 | Physical clinic appointment — book an in-person visit as well as online | Existing Improvement, Regression | Web, QA | Yes | — | — | Yes | 2 | Physical clinic appointment | ConsultMode added in APT-02; public booking in WEB-04 | Ensure public/patient booking supports In-clinic as first-class, not tele-only | Not Started
84 | M06 | Reception portal | 5 | REC-01 | Reception login — secure staff access (keep) | Existing, Existing Improvement | Web, QA | Yes | — | — | Yes | 3 | Reception login | Reception logs in via Account; JWT includes DoctorID; uses doctor dashboard layout | Keep login; Phase 0 hashing applies; later dedicated reception chrome | Not Started
85 | M06 | Reception portal | 5 | REC-02 | Reception profile — manage own profile details (0% today) | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Reception profile | No reception-specific profile; shared Velzon /profile | Name, mobile, attached doctor (read-only); cannot edit doctor bank/fee | Not Started
86 | M06 | Reception portal | 5 | REC-03 | Reception home dashboard — purpose-built front-desk dashboard (not only hidden doctor actions) | Existing Improvement, Regression | UI, QA | — | Yes | — | Yes | 3 | Reception home dashboard | Same /doctordashboard with some clinical actions disabled ~90% | Reception-first chrome: queue, collect pay, case paper, no repertory/Rx; optional /reception home route | Not Started
87 | M06 | Reception portal | 5 | REC-04 | Create patient — register a walk-in patient quickly (keep) | Existing, Existing Improvement | Web, QA | Yes | — | — | Yes | 3 | Create patient | Create patient live on shared dashboard | Keep on reception chrome | Not Started
88 | M06 | Reception portal | 5 | REC-05 | Patient search & list — find any patient instantly (keep) | Existing, Existing Improvement | Web, QA | Yes | — | — | Yes | 3 | Patient search & list | Search live | Keep; no opening full clinical board | Not Started
89 | M06 | Reception portal | 5 | REC-06 | Create & manage appointments — full appointment management (keep; plus reschedule/cancel from Phase 4) | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 3 | Create & manage appointments | Create/status/time live; reschedule/cancel missing until Phase 4 APIs | Enable RescheduleAppointment and CancelAppointment for JWT DoctorId; isReceptionUser must not block | Not Started
90 | M06 | Reception portal | 5 | REC-07 | New appointment — book on behalf of the patient (keep; same VisitType/ConsultMode/fee as APT-02) | Existing Improvement, Regression | UI, QA | — | Yes | — | Yes | 2 | New appointment | New appointment modal live; fields incomplete until APT-02 | Same modal fields as doctor so public booking later matches staff-created rows | Not Started
91 | M06 | Reception portal | 5 | REC-08 | Waiting queue management — manage the live queue and call the next patient | Existing Improvement, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Waiting queue management | Status buckets ~60%; no dedicated queue UX / call-next | Dedicated queue: walk-in vs tele; payment state; Call next; notify patient (later push) | Not Started
92 | M06 | Reception portal | 5 | REC-09 | Appointment status update (reception) — update as patients arrive and are seen (keep) | Existing, Existing Improvement | Web, QA | Yes | — | — | Yes | 3 | Appointment status update | Status update live | Keep on reception chrome | Not Started
93 | M06 | Reception portal | 5 | REC-10 | Appointment time update (reception) — adjust timings through the day (keep) | Existing, Existing Improvement | Web, QA | Yes | — | — | Yes | 3 | Appointment time update | Time update live | Keep; formal reschedule remains REC-06 | Not Started
94 | M06 | Reception portal | 5 | REC-11 | View doctor schedule — see the doctor’s working schedule (read-only) | New, Regression | UI, QA | — | Yes | — | Yes | 2 | View doctor schedule | GetDailySchedule exists; no reception view | Read-only /reception/schedule using DoctorID from JWT | Not Started
95 | M06 | Reception portal | 5 | REC-12 | Log case paper / chief complaint — record the reason for visit before the consultation | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Log case paper / chief complaint | Missing; SaveComplaints exists but board is doctor-only | Restricted case-paper form (chief complaint only — no repertory/Rx); audit reception author | Not Started
96 | M06 | Reception portal | 5 | REC-13 | Collect consultation payment — cash, UPI, card or payment link and issue a receipt (API in Phase 6; UI shell now) | New | Web, UI | Yes | Yes | — | — | 2 | Collect consultation payment | Does not exist | UI modal ready; CollectAtReception API lands with payment spine in Phase 6 — do not fake a paid status here | Not Started
97 | M07 | Payment system | 6 | PAY-01 | Consultation fee configuration — each doctor’s fee set and displayed to patients | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Consultation fee configuration | No ConsultFeeConfig; doctor profile work in DOC-10 may have stored a fee field | ConsultFeeConfig (InClinic, EConsult, optional Instant surcharge, PayAtClinicEnabled, GST flags) | Not Started
98 | M07 | Payment system | 6 | PAY-02 | Automatic payment verification — bank/webhook is source of truth, not the patient’s screen | New, New Integration, Regression | Web, QA | Yes | — | — | Yes | 4 | Automatic payment verification | Razorpay checkout for S1 subscription only; no webhook; no signature verify on server | Port Razorpay to .NET 8; keys in config; POST /api/Payments/Webhook/Razorpay anonymous + signature verify; PaymentOrder table | Not Started
99 | M07 | Payment system | 6 | PAY-03 | Online consultation payment — patient pays by card, UPI, netbanking or wallet | New, New Integration, Regression | Web, UI, QA | Yes | Yes | — | Yes | 5 | Online consultation payment | Does not exist (only S1 SaaS) | CreateConsultOrder attached to PatientAppId; Razorpay Checkout; webhook sets PAID; do not overload PackageEntryDetail | Not Started
100 | M07 | Payment system | 6 | PAY-04 | Reception payment collection — cash, UPI, card or payment link with printed receipt | New, New Integration, Regression | Web, UI, QA | Yes | Yes | — | Yes | 5 | Reception payment collection | Does not exist | CollectAtReception writes ledger S3; print receipt; payment-link uses same Razorpay order as online | Not Started
101 | M07 | Payment system | 6 | PAY-05 | Pay-at-clinic option — book now, pay at the clinic where the doctor allows it | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 3 | Pay-at-clinic option | Does not exist | PayAtClinicEnabled on fee config; appointment PaymentStatus=PAY_AT_CLINIC; tele queue may still require PAID (policy) | Not Started
102 | M07 | Payment system | 6 | PAY-06 | Doctor subscription payment — buy and renew subscription packages (complete remaining ~30%) | Existing Improvement, Regression | Web, UI, QA | Yes | Yes | — | Yes | 3 | Doctor subscription payment | Checkout works ~70%; no webhook, refund, invoice, GST, Account ledger | Same webhook spine; write S1 ledger; invoice; failed pay UX; PackageEntryDetail shape UNCHANGED | Not Started
103 | M07 | Payment system | 6 | PAY-07 | Medicine payment — pay online or cash on delivery (API contract now; HomeoMeds Phase 14 implements orders) | New, Regression | Web, QA | Yes | — | — | Yes | 3 | Medicine payment | Does not exist | PaymentOrder.Stream=MEDICINE; COD_PENDING until pharmacy confirms collection; do not mix with consult money | Not Started
104 | M07 | Payment system | 6 | PAY-08 | Payment status everywhere — doctor, reception and patient all see the same payment status | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 3 | Payment status everywhere | No shared status | Single PaymentStatus on appointment/order; all DTOs read it; never a second client-only flag | Not Started
105 | M07 | Payment system | 6 | PAY-09 | Refunds — processed and tracked against the original payment | New, New Integration, Regression | Web, UI, QA | Yes | Yes | — | Yes | 5 | Refunds | Does not exist | Refund entity against original PaymentOrder; Razorpay refund API; cancel-appointment hook; patient sees status | Not Started
106 | M07 | Payment system | 6 | PAY-10 | Payment receipts & invoices — issued for every transaction | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Payment receipts & invoices | No invoice entity | Invoice numbering series from PRE-02; PDF receipt; GST fields; email in Phase 12 | Not Started
107 | M07 | Payment system | 6 | PAY-11 | Complete payment audit trail — every transaction traceable end to end by Homeocentrum | New, Regression | Web, QA | Yes | — | — | Yes | 3 | Complete audit trail | No webhook store | PaymentEvent raw payloads + AuditEvent + OtpAudit for payouts; Account can reconstruct without Razorpay dashboard | Not Started
108 | M08 | Account & finance | 7 | FIN-01 | Unified transaction ledger — every rupee that moves through the platform, in one record | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Unified transaction ledger | Does not exist | Append-only LedgerEntry for S1–S7; filters; OTP audit link; Admin may view, Account owns movement | Not Started
109 | M08 | Account & finance | 7 | FIN-02 | Consultation payment reconciliation — online payments and reception collections matched and verified | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Consultation payment reconciliation | Does not exist | Join booking ↔ payment ↔ appointment; KPI collected/pending/failed/refunded; CSV | Not Started
110 | M08 | Account & finance | 7 | FIN-03 | Medicine ledger — medicine money tracked separately from consultation money | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Medicine ledger | Does not exist | /account/medicine-ledger; Stream=MEDICINE; seller/platform/delivery split columns; filled in Phase 14 | Not Started
111 | M08 | Account & finance | 7 | FIN-04 | Settlement runs — scheduled settlement of amounts due to doctors and pharmacies | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Settlement runs | Does not exist | SettlementRun job T+N hold; net of commission/GST/refunds; pharmacies after Phase 14 | Not Started
112 | M08 | Account & finance | 7 | FIN-05 | Payout approval — payouts released only after OTP-verified approval | New, New Integration, Regression | Web, UI, QA | Yes | Yes | — | Yes | 5 | Payout approval | Does not exist | ApprovePayout requires SEC-07 OTP; Admin cannot approve; NEFT/file or gateway per PRE-01 | Not Started
113 | M08 | Account & finance | 7 | FIN-06 | Refund processing — Account issues and tracks refunds (uses PAY-09) | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 3 | Refund processing | Does not exist | /account/refunds UI on PAY-09 APIs; OTP if policy requires | Not Started
114 | M08 | Account & finance | 7 | FIN-07 | Payment exception handling — investigate and resolve every failed or disputed payment | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Payment exception handling | Does not exist | Exception queue Failed/Partial/Webhook-mismatch/Refund-pending; retry/resolve with OTP on manual reconcile | Not Started
115 | M08 | Account & finance | 7 | FIN-08 | GST & invoice reports — invoice numbering and tax reporting | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | GST & invoice reports | Does not exist | /account/tax export using Invoice table and PRE-02 GST treatment — configuration not hardcoded | Not Started
116 | M08 | Account & finance | 7 | FIN-09 | Payee records — bank and KYC details for doctors and pharmacies | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Payee records | Doctor bank fields added in DOC-10; no Account UI; no pharmacy | /account/payees; OTP on doctor KYC change (fraud); pharmacies after Phase 14 | Not Started
117 | M08 | Account & finance | 7 | FIN-10 | Clinic collection view — cash and UPI collected at reception, per clinic and per day | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Clinic collection view | Does not exist | /account/clinic-collections from CollectAtReception rows; respect PRE-02 retain vs remit | Not Started
118 | M08 | Account & finance | 7 | FIN-11 | Separation of duties — Account controls money; Admin controls platform and clinical data | New, Regression | Web, QA | Yes | — | — | Yes | 2 | Separation of duties | Account role does not exist | Enforce in RBAC: Admin cannot ApprovePayout; Account cannot edit repertory/users’ clinical masters | Not Started
119 | M08 | Account & finance | 15 | CON-08 | Patient payments & refunds read model | New, Regression | Web, QA | Yes | — | — | Yes | 2 | Payments & refunds | Ledger exists for Account | Patient-safe DTO of own consult+medicine payments and refunds — no other patients, no commission internals | Not Started
120 | M09 | Trust & verification | 8 | TRU-01 | Doctor credentialing — doctors upload qualification and registration documents for review | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Doctor credentialing | RegisterDoctor activates immediately; PassingUniversity/CertNo/QualificationId exist; no document store/queue | DoctorCredentialDocument + VerificationStatus Pending; do not auto-activate practice for public directory | Not Started
121 | M09 | Trust & verification | 8 | TRU-02 | Verification review — Admin approves, rejects or requests further information | New, New Integration, Regression | Web, UI, QA | Yes | Yes | — | Yes | 5 | Verification review | Does not exist | /admin/doctor-credentialing list + detail; email notify doctor | Not Started
122 | M09 | Trust & verification | 8 | TRU-03 | Verified badge — patients see which doctors have been verified | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 3 | Verified badge / Credentials & verification | Does not exist | Badge on public doctor card and profile from VerificationStatus=Approved | Not Started
123 | M09 | Trust & verification | 8 | TRU-04 | Practice gate — only verified doctors appear to patients and take paid consultations | New, Regression | Web, QA | Yes | — | — | Yes | 3 | Practice gate | Any activated doctor could theoretically be listed; no public list yet | Public search and CreateConsultOrder require Approved; own-clinic staff booking may still work per PRE-03 | Not Started
124 | M09 | Trust & verification | 8 | TRU-05 | Patient reviews — patients rate and review consultations | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Patient reviews / Write a review | Does not exist | Review linked to PatientAppId; one review per visit; moderation flag optional | Not Started
125 | M09 | Trust & verification | 8 | TRU-06 | Review appeal — doctors can appeal a review; patients manage reviews and raise an appeal | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Review appeal / My reviews & appeal | Does not exist | Appeal entity; admin resolves; patient my-reviews list | Not Started
126 | M09 | Trust & verification | 8 | TRU-07 | Ranking transparency — patients are shown why doctors are ranked as they are | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Ranking transparency / Ranking explanation | Does not exist | Documented ranking factors (verified, availability, fee, reviews, experience) + explain API/UI | Not Started
127 | M10 | Patient website | 9 | WEB-01 | Product home page — complete public website presenting the service | Existing Improvement, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Product home page | HomeoJobLanding ~50%; Velzon leftovers; CTAs incomplete for book/trust/apps | Book CTA, verified doctors, consult+SaaS pricing teaser, app download placeholders | Not Started
128 | M10 | Patient website | 9 | WEB-02 | Consultation & subscription pricing — transparent pricing display | Existing Improvement, Regression | UI, QA | — | Yes | — | Yes | 3 | Consultation & subscription pricing | SaaS package marketing /pricing exists; no consult fee display per doctor | Keep SaaS pricing; add consult fee on doctor cards from ConsultFeeConfig | Not Started
129 | M10 | Patient website | 9 | WEB-03 | Doctor discovery — browse and search verified doctors | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Doctor discovery | Does not exist as a patient product (marketing only) | /book search: name, condition, category; filters availability, fee, experience, language, location | Not Started
130 | M10 | Patient website | 9 | WEB-04 | Self-service booking — book an appointment online without calling the clinic | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Self-service booking | Staff-only appointments | Funnel /book/:id/slots → review+consent → create Patient+Appointment; OTP; rate-limit; respect schedule + unpaid hold policy PRE-03 | Not Started
131 | M10 | Patient website | 9 | WEB-05 | Online consultation payment on website — pay the fee at the time of booking | New, Regression | UI, QA | — | Yes | — | Yes | 2 | Online consultation payment | Does not exist | Checkout uses PAY-03; success/fail pages; pay-at-clinic branch from PAY-05 | Not Started
132 | M10 | Patient website | 9 | WEB-06 | Contact & enquiry form — enquiries reach the admin team and are tracked | Existing Improvement, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Contact & enquiry form | EnquiryDetail API exists; public form partial; admin inbox screen missing | Confirmation + enquiry id; /admin/enquiries inbox; optional convert to SupportTicket | Not Started
133 | M10 | Patient website | 9 | WEB-07 | Privacy policy — covering data protection, recording and pharmacy consent | Existing Improvement, Regression | UI, QA | — | Yes | — | Yes | 2 | Privacy policy | Privacy page partial; not DPDP/tele/pharmacy complete | Publish PRE-03 legal copy: DPDP, recording, pharmacy, data-rights, family/caregiver | Not Started
134 | M10 | Patient website | 9 | WEB-08 | Terms of service — covering payments, refunds, telemedicine and medicine orders | Existing Improvement, Regression | UI, QA | — | Yes | — | Yes | 2 | Terms of service | Terms partial | Payments, refunds, telemedicine, HomeoMeds, codes-before-names | Not Started
135 | M10 | Patient website | 9 | WEB-09 | Doctor self-registration — doctors apply to join the platform online | Existing Improvement, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Doctor self-registration | RegisterDoctor ~90%; activates immediately; no document upload | Document upload; pending-verification message; TRU-01 status Pending | Not Started
136 | M10 | Patient website | 9 | WEB-10 | Email activation — secure account activation by email link | Existing Improvement, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Email activation | ActivateUser via /login?UserId= ~90%; align with verification; expiry/resend incomplete | Token expiry, resend, align with credentialing (activation ≠ verified practice) | Not Started
137 | M10 | Patient website | 9 | WEB-12 | Health articles — educational content to build trust and engagement | Existing Improvement, Regression | UI, QA | — | Yes | — | Yes | 2 | Health articles | Blog/news APIs on classic exist for marketing | Reuse blog/news as health articles on public site and later patient app; admin already has news/blog | Not Started
138 | M11 | Digital prescription (eRx) | 10 | ERX-01 | Potency module — every remedy carries a defined potency from a managed list, no free text | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Potency module | Dose saved as empty free-text dose: '' | PotencyMaster CRUD; PotencyId on PrescriptionRemedyDetail; stop empty Dose | Not Started
139 | M11 | Digital prescription (eRx) | 10 | ERX-02 | Dosage details — frequency, duration and instructions recorded clearly | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Dosage details | Unstructured/empty dose | Frequency, Duration, Instructions fields on each remedy line | Not Started
140 | M11 | Digital prescription (eRx) | 10 | ERX-03 | Visit notes kept separate from the prescription — private clinical notes never appear on the prescription given to the patient or pharmacy | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Visit notes kept separate from the prescription | History notes mixed into Rx modal tabs | Visit Notes panel outside Rx; NoteType; IsErxExcluded; eRx print has remedies+labs only | Not Started
141 | M11 | Digital prescription (eRx) | 10 | ERX-04 | Signed digital prescription — issued and locked once signed, so it cannot be altered afterwards | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Signed digital prescription | SavePrescriptionDetail overwritable; no lock/sign | ErxSnapshot immutable on sign; subsequent edits create a new unsigned draft not a silent mutate | Not Started
142 | M11 | Digital prescription (eRx) | 10 | ERX-05 | Prescription history — every prescription stored against the patient and visit | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 3 | Prescription history | Rx saved per appointment but no signed history product | List snapshots by PatientId; open past visit eRx | Not Started
143 | M11 | Digital prescription (eRx) | 10 | ERX-06 | Patient view of prescription in app — patient sees the prescription immediately (codes until pharmacy accept) | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 3 | Patient view in app | No patient surface | Patient GET eRx by appointment; names redacted until Phase 14 accept; website optional view | Not Started
144 | M11 | Digital prescription (eRx) | 10 | ERX-07 | Print & PDF — printable and downloadable prescription | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 3 | Print & PDF | No eRx PDF | Patient copy without notes; doctor copy may include letterhead; SecureDocument store | Not Started
145 | M11 | Digital prescription (eRx) | 10 | ERX-08 | Remedy code protection — patient sees remedy codes rather than names until a licensed pharmacy accepts the order | New, Regression | Web, QA | Yes | — | — | Yes | 2 | Remedy code protection | Does not exist | Code map on snapshot items; patient serializer strips names; doctor always sees names | Not Started
146 | M11 | Digital prescription (eRx) | 10 | ERX-09 | Reveal on pharmacy acceptance — names and price revealed; payment QR or link generated (implemented with HomeoMeds; contract now) | New | Web | Yes | — | — | — | 2 | Reveal on pharmacy acceptance | Does not exist | Flag PharmacyAccepted on order; patient GET starts returning names; CreateMedicine payment link; full UI in Phase 14 | Not Started
147 | M11 | Digital prescription (eRx) | 10 | ERX-10 | Repeat prescription / refill — patient requests; doctor approves or rejects from the mobile app (inbox on web too) | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Repeat prescription / refill | Does not exist | RefillRequest against ErxSnapshot; doctor inbox; no case-taking on mobile | Not Started
148 | M11 | Digital prescription (eRx) | 10 | ERX-11 | Lab orders alongside the prescription (keep existing labs on eRx snapshot) | Existing Improvement, Regression | Web, QA | Yes | — | — | Yes | 2 | Lab orders | Labs on Rx modal live | Include lab orders in signed snapshot; still not on private notes | Not Started
149 | M12 | Telemedicine | 11 | TEL-01 | Doctor availability — online or offline status and working hours | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Doctor availability | E-CONSULT status + WhatsApp video stub only; no availability | TeleAvailability + heartbeat; working hours reuse daily schedule | Not Started
150 | M12 | Telemedicine | 11 | TEL-02 | Telemedicine waiting queue — who is waiting, how long, whether they have paid | New, New Integration, Regression | Web, UI, QA | Yes | Yes | — | Yes | 5 | Telemedicine waiting queue | E-CONSULT list only | Queue by doctor + Online + paid/confirmed; wait time; Join | Not Started
151 | M12 | Telemedicine | 11 | TEL-03 | Video consultation in browser — doctor consults directly from the web portal | New, New Integration, Regression | Web, UI, QA | Yes | Yes | — | Yes | 5 | Video consultation in browser | SweetAlert WhatsApp stub | /teleconsult/:sessionId in-browser video; replace stub; vendor from PRE-03 | Not Started
152 | M12 | Telemedicine | 11 | TEL-04 | Video consultation on mobile — doctor and patient both consult from the app (apps in 16–17; same session tokens) | New, Regression | Web, QA | Yes | — | — | Yes | 2 | Video consultation on mobile | No apps | Same TeleSession tokens; mobile join implemented in Phases 16–17 against this API | Not Started
153 | M12 | Telemedicine | 11 | TEL-05 | Device check — camera, microphone and connection tested before joining | New, Regression | UI, QA | — | Yes | — | Yes | 2 | Device check | Does not exist | Pre-join device/network check UI; block join on hard fail with guidance | Not Started
154 | M12 | Telemedicine | 11 | TEL-06 | Waiting room — patient waits with live status until the doctor joins | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Waiting room | Does not exist | Waiting room page: position, doctor online, paid, estimated wait | Not Started
155 | M12 | Telemedicine | 11 | TEL-07 | Recording consent — consent captured before the consultation; no recording without it | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Recording consent | AudioCaseConsentLog only for audio case taking | ConsentRecord type TeleRecording; block record if declined; both sides see status | Not Started
156 | M12 | Telemedicine | 11 | TEL-08 | Rejoin after dropped call — either side can rejoin the same consultation | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 3 | Rejoin after dropped call | Does not exist | Session Active until End; rejoin tokens; dashboard Rejoin | Not Started
157 | M12 | Telemedicine | 11 | TEL-09 | Join failure handling — clear fallback if the call cannot connect, with options to retry | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 3 | Join failure handling / Fallback & join failure handling | Does not exist | Error codes; retry; support ticket deep link later; do not silently fail | Not Started
158 | M12 | Telemedicine | 11 | TEL-10 | Case-linked chat — chat attached to the consultation record, not a loose message thread | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Case-linked chat | Does not exist | Messages keyed by TeleSession/PatientAppId; retained with the case | Not Started
159 | M12 | Telemedicine | 11 | TEL-11 | Consultation summary — issued to the patient at the end of the call | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Consultation summary | Does not exist | Doctor submits summary (not private notes); patient sees immediately; may share eRx id | Not Started
160 | M12 | Telemedicine | 11 | TEL-12 | Instant consultation — patient requests an immediate consultation with an available doctor | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Instant consultation / Instant consult request / Queue & doctor offer | Does not exist | Instant request pool; offer doctor; patient accepts; optional surcharge from fee config | Not Started
161 | M13 | Communications | 12 | COM-01 | SMS — appointment confirmation, registration confirmation, doctor-unavailable, OTP, reschedule and cancellation | New, New Integration, Regression | Web, UI, QA | Yes | Yes | — | Yes | 5 | SMS | No SMS provider; WhatsApp exists separately | SmsProvider + templates + DLT; event hooks; DND/opt-out on Patient | Not Started
162 | M13 | Communications | 12 | COM-02 | WhatsApp — templates, offers, health tips and bulk messaging with delivery reports and opt-out (complete remaining ~50%) | Existing Improvement, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | WhatsApp | Meta Cloud send/templates/campaigns live; bulk/opt-in/analytics incomplete | Finish bulk queue UX, template approval states, delivery reports, opt-out | Not Started
163 | M13 | Communications | 12 | COM-03 | Push notifications — booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests | New, New Integration, Regression | Web, UI, QA | Yes | Yes | — | Yes | 5 | Push notifications | Does not exist | DeviceToken + FCM/APNs; event fan-out; apps register tokens in Phases 16–17 | Not Started
164 | M13 | Communications | 12 | COM-04 | Email — registration, activation, password reset, invoices and receipts | Existing Improvement, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Email | SMTP used for activation/forgot (plaintext issue fixed in Phase 0); no invoice email | Template emails for listed events; invoice PDF attach via SEC-09 | Not Started
165 | M13 | Communications | 12 | COM-05 | In-app notification centre — all alerts collected in one place for patients and doctors | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | In-app notification centre / Notifications centre | Does not exist (Velzon notification demo is not product) | AppNotification inbox; mark read; do not use Velzon demo notifications | Not Started
166 | M14 | Support & help desk | 13 | SUP-01 | Patient support tickets — patients raise issues from the app and track them | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Patient support tickets / Help centre & support tickets | Does not exist; EnquiryDetail is not tickets; Velzon tickets demo ignore | SupportTicket reporter=Patient; status track; not Enquiry, not Velzon /apps-tickets-* | Not Started
167 | M14 | Support & help desk | 13 | SUP-02 | Doctor support tickets — doctors raise issues from the portal | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 3 | Doctor support tickets | Does not exist | Same ticket tables; reporter=Doctor | Not Started
168 | M14 | Support & help desk | 13 | SUP-03 | Admin issue queue — all issues in one queue with priority, assignment and status | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Admin issue queue / Support ticket queue | Does not exist | /admin/support-tickets; SLA timestamps; assign | Not Started
169 | M14 | Support & help desk | 13 | SUP-04 | Ticket conversation — full message thread with attachments | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 3 | Ticket conversation | Does not exist | Threaded messages + SEC-09 attachments | Not Started
170 | M14 | Support & help desk | 13 | SUP-05 | Enquiry management — website enquiries tracked (ties WEB-06) | Existing Improvement, Regression | UI, QA | — | Yes | — | Yes | 2 | Enquiry management | API exists; inbox missing | Complete WEB-06 admin inbox if not already; convert enquiry → ticket optional | Not Started
171 | M14 | Support & help desk | 13 | SUP-06 | Help centre — self-service help content for patients | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Help centre | Does not exist | CMS articles or static help; searchable | Not Started
172 | M14 | Support & help desk | 13 | SUP-07 | Assisted booking — help for patients who need support booking | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Assisted booking | Does not exist | Staff (admin/support/reception) can complete public booking on behalf of a patient with audit; patient app CTA to request assistance | Not Started
173 | M15 | HomeoMeds | 14 | MED-01 | Pharmacy partner onboarding — licensed premises, licence records, activation checklist | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Pharmacy partner onboarding / Pharmacy partner management | Does not exist | PharmacyPartner + licences; admin activation; pharmacy console login | Not Started
174 | M15 | HomeoMeds | 14 | MED-02 | Licence gating — expired or suspended licences blocked automatically from receiving orders | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 3 | Licence gating | Does not exist | Scheduler; routing skip; banner on pharmacy console | Not Started
175 | M15 | HomeoMeds | 14 | MED-03 | Fulfilment consent & pharmacy selection — patient chooses the seller and consents before the prescription is shared | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Fulfilment consent & pharmacy selection | Does not exist | ConsentRecord PharmacyShare; patient picks from routed sellers; share only after consent | Not Started
176 | M15 | HomeoMeds | 14 | MED-04 | Prescription handoff — signed prescription becomes the order directly — no re-entry, no transcription errors | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Prescription handoff / Order start | Does not exist | MedicineOrder copied from ErxSnapshot items (codes); pharmacy never types remedies | Not Started
177 | M15 | HomeoMeds | 14 | MED-05 | Rule-based seller routing — licence validity, service area, working hours and capacity | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Rule-based seller routing | Does not exist | SellerRoutingRule engine | Not Started
178 | M15 | HomeoMeds | 14 | MED-06 | Manual stock confirmation — pharmacy confirms availability — no live inventory integration required | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 3 | Manual stock confirmation | Does not exist | Accept/reject with stock flag; do not build inventory master | Not Started
179 | M15 | HomeoMeds | 14 | MED-07 | Pharmacy console — accept or reject, enter price quote, mark ready and dispatched | New, New Integration, Regression | Web, UI, QA | Yes | Yes | — | Yes | 5 | Pharmacy console | Does not exist | /pharmacy/orders list+detail; OTP accept (SEC-07); quote; ready; dispatched | Not Started
180 | M15 | HomeoMeds | 14 | MED-08 | Quote before payment — the patient always sees the price before paying | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Quote before payment / Pharmacy selection & quote | Does not exist | MedicineQuote; patient must confirm quote; then PAY-07 | Not Started
181 | M15 | HomeoMeds | 14 | MED-09 | Payment or cash on delivery — both options, with status tracking | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 3 | Payment or cash on delivery | Stream MEDICINE stub in Phase 6 | Online pay via PAY-02; COD_PENDING until pharmacy confirms collection | Not Started
182 | M15 | HomeoMeds | 14 | MED-10 | Order tracking — live status for the patient at every stage | New, New Integration, Regression | Web, UI, QA | Yes | Yes | — | Yes | 5 | Order tracking | Does not exist | Status timeline events; push updates COM-03 | Not Started
183 | M15 | HomeoMeds | 14 | MED-11 | Medicine ledger shares — seller, platform and delivery recorded (FIN-03 live fill) | New, Regression | Web, QA | Yes | — | — | Yes | 2 | Medicine ledger | Empty medicine ledger screen from Phase 7 | On pay/COD collect, write SplitSeller/Platform/Delivery from config | Not Started
184 | M15 | HomeoMeds | 14 | MED-12 | Order exception queue — stuck, rejected or failed orders always surfaced — never silent | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Order exception queue | Does not exist | HomeoMeds exception queue; SLA; never drop | Not Started
185 | M15 | HomeoMeds | 14 | MED-13 | OTP-based control — key actions verified by OTP so Homeocentrum can monitor and trace every transaction | New, Regression | Web, QA | Yes | — | — | Yes | 2 | OTP-based control | SEC-07 infrastructure exists | OTP on pharmacy accept (and other high-risk); OtpAudit queryable | Not Started
186 | M15 | HomeoMeds | 14 | MED-14 | Refill orders — repeat orders raised from an existing prescription | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 3 | Refill orders / Order detail & refill | ERX-10 refill request exists | Approved refill creates a new MedicineOrder from the same snapshot; one-tap patient | Not Started
187 | M15 | HomeoMeds | 14 | MED-15 | Order review & consent (patient) — confirm and consent before the prescription is shared | New, Regression | UI, QA | — | Yes | — | Yes | 2 | Order review & consent | Covered by MED-03; explicit review screen still required | Review screen listing codes (not names) + pharmacy + consent checkbox | Not Started
188 | M15 | HomeoMeds | 14 | MED-16 | Medicines tab — all medicine orders in one place (API now; app UI in Phase 16) | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 3 | Medicines tab | Does not exist | GET my orders; website optional list; app tab Phase 16 | Not Started
189 | M16 | Patient continuity APIs | 15 | CON-01 | Family members — add family members under one account | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Family members | Does not exist | FamilyMember under Patient account; bookings can be for a member | Not Started
190 | M16 | Patient continuity APIs | 15 | CON-02 | Caregiver authorization — let a family member book and manage on their behalf | New, New Integration, Regression | Web, UI, QA | Yes | Yes | — | Yes | 5 | Caregiver authorization | Does not exist | CaregiverAuth with scopes; OTP; withdrawable via consent centre | Not Started
191 | M16 | Patient continuity APIs | 15 | CON-03 | Records timeline + consultation note + document upload APIs | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Records timeline / Consultation note / Document upload | Doctor history exists; no patient timeline; no patient upload | Patient timeline DTO (visits, summary, eRx codes, labs); consultation note = TEL-11 summary not private notes; uploads via SEC-09 | Not Started
192 | M16 | Patient continuity APIs | 15 | CON-04 | Follow-up plan & tasks — clear next steps after each consultation | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Follow-up plan & tasks | Does not exist (follow-up option in notes does not save) | FollowUpTask created by doctor; patient sees tasks | Not Started
193 | M16 | Patient continuity APIs | 15 | CON-05 | Symptom diary — record symptoms between visits | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Symptom diary | Does not exist | SymptomDiary entries; doctor can read on board | Not Started
194 | M16 | Patient continuity APIs | 15 | CON-06 | Progress tracking — see improvement over time across visits | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Progress tracking | Does not exist | Progress series from diary + visit outcomes; not a fake chart | Not Started
195 | M16 | Patient continuity APIs | 15 | CON-07 | Consent centre & data rights — view, manage and withdraw consents; request data | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Consent centre & data rights | ConsentRecord from Phase 0 | Patient list/withdraw; data export request (DPDP); deletion request workflow | Not Started
196 | M16 | Patient continuity APIs | 15 | CON-10 | Patient profile setup API — name, age, gender, contact and health basics | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Profile setup | Clinic-created Patient exists; no self-serve profile product | Patient profile fields + health basics; used by OTP-verified patient token | Not Started
197 | M17 | Patient mobile app | 16 | PAT-01 | Patient app — language selection on first open | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Language selection | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | In Progress
198 | M17 | Patient mobile app | 16 | PAT-02 | Patient app — welcome and introduction | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Welcome & introduction | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | In Progress
199 | M17 | Patient mobile app | 16 | PAT-03 | Patient app — mobile number + OTP login (PatientAuth) | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Mobile number + OTP login | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | In Progress
200 | M17 | Patient mobile app | 16 | PAT-04 | Patient app — profile setup | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Profile setup | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
201 | M17 | Patient mobile app | 16 | PAT-05 | Patient app — privacy consent before data stored | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Privacy consent | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
202 | M17 | Patient mobile app | 16 | PAT-06 | Patient app — family members | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Family members | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
203 | M17 | Patient mobile app | 16 | PAT-07 | Patient app — caregiver authorization | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Caregiver authorization | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
204 | M17 | Patient mobile app | 16 | PAT-08 | Patient app — home dashboard | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Home dashboard | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
205 | M17 | Patient mobile app | 16 | PAT-09 | Patient app — search and care categories | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Search & care categories | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
206 | M17 | Patient mobile app | 16 | PAT-10 | Patient app — search results | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Search results | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
207 | M17 | Patient mobile app | 16 | PAT-11 | Patient app — discovery filters | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Filters | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
208 | M17 | Patient mobile app | 16 | PAT-12 | Patient app — doctor profile | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Doctor profile | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
209 | M17 | Patient mobile app | 16 | PAT-13 | Patient app — verified badge on doctor | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Credentials & verification | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
210 | M17 | Patient mobile app | 16 | PAT-14 | Patient app — ranking explanation | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Ranking explanation | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
211 | M17 | Patient mobile app | 16 | PAT-15 | Patient app — health articles | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Health articles | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
212 | M17 | Patient mobile app | 16 | PAT-16 | Patient app — slot picker | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Slot picker | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
213 | M17 | Patient mobile app | 16 | PAT-17 | Patient app — booking review and consent | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Booking review & consent | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
214 | M17 | Patient mobile app | 16 | PAT-18 | Patient app — checkout | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Checkout | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
215 | M17 | Patient mobile app | 16 | PAT-19 | Patient app — payment status | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Payment status | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
216 | M17 | Patient mobile app | 16 | PAT-20 | Patient app — appointment detail | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Appointment detail | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
217 | M17 | Patient mobile app | 16 | PAT-21 | Patient app — reschedule | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Reschedule appointment | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
218 | M17 | Patient mobile app | 16 | PAT-22 | Patient app — cancel | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Cancel appointment | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
219 | M17 | Patient mobile app | 16 | PAT-23 | Patient app — waitlist offer | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Waitlist offer | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
220 | M17 | Patient mobile app | 16 | PAT-24 | Patient app — instant consult request | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Instant consult request | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
221 | M17 | Patient mobile app | 16 | PAT-25 | Patient app — queue and doctor offer | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Queue & doctor offer | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
222 | M17 | Patient mobile app | 16 | PAT-26 | Patient app — device check | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Device check | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
223 | M17 | Patient mobile app | 16 | PAT-27 | Patient app — waiting room | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Waiting room | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
224 | M17 | Patient mobile app | 16 | PAT-28 | Patient app — live video | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Live video consultation | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
225 | M17 | Patient mobile app | 16 | PAT-29 | Patient app — recording consent | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Recording consent | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
226 | M17 | Patient mobile app | 16 | PAT-30 | Patient app — join failure fallback | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Fallback & join failure handling | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
227 | M17 | Patient mobile app | 16 | PAT-31 | Patient app — case-linked chat | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Case-linked chat | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
228 | M17 | Patient mobile app | 16 | PAT-32 | Patient app — consultation summary | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Consultation summary | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
229 | M17 | Patient mobile app | 16 | PAT-33 | Patient app — rejoin | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Rejoin after dropped call | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
230 | M17 | Patient mobile app | 16 | PAT-34 | Patient app — records timeline | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Records timeline | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
231 | M17 | Patient mobile app | 16 | PAT-35 | Patient app — consultation note (summary, not private notes) | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Consultation note | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
232 | M17 | Patient mobile app | 16 | PAT-36 | Patient app — signed eRx (codes until pharmacy accept) | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Signed digital prescription | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
233 | M17 | Patient mobile app | 16 | PAT-37 | Patient app — document upload | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Document upload | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
234 | M17 | Patient mobile app | 16 | PAT-38 | Patient app — follow-up plan and tasks | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Follow-up plan & tasks | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
235 | M17 | Patient mobile app | 16 | PAT-39 | Patient app — symptom diary | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Symptom diary | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
236 | M17 | Patient mobile app | 16 | PAT-40 | Patient app — progress tracking | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Progress tracking | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
237 | M17 | Patient mobile app | 16 | PAT-41 | Patient app — medicines tab | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Medicines tab | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
238 | M17 | Patient mobile app | 16 | PAT-42 | Patient app — start HomeoMeds order from eRx | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Order start | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
239 | M17 | Patient mobile app | 16 | PAT-43 | Patient app — pharmacy selection and quote | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Pharmacy selection & quote | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
240 | M17 | Patient mobile app | 16 | PAT-44 | Patient app — order review and consent | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Order review & consent | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
241 | M17 | Patient mobile app | 16 | PAT-45 | Patient app — order tracking | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Order tracking | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
242 | M17 | Patient mobile app | 16 | PAT-46 | Patient app — order detail and refill | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Order detail & refill | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
243 | M17 | Patient mobile app | 16 | PAT-47 | Patient app — write a review | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Write a review | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
244 | M17 | Patient mobile app | 16 | PAT-48 | Patient app — my reviews and appeal | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | My reviews & appeal | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
245 | M17 | Patient mobile app | 16 | PAT-49 | Patient app — payments and refunds | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Payments & refunds | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
246 | M17 | Patient mobile app | 16 | PAT-50 | Patient app — profile and settings | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Profile & settings | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
247 | M17 | Patient mobile app | 16 | PAT-51 | Patient app — consent centre and data rights | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Consent centre & data rights | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
248 | M17 | Patient mobile app | 16 | PAT-52 | Patient app — notifications centre | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Notifications centre | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
249 | M17 | Patient mobile app | 16 | PAT-53 | Patient app — help centre and tickets | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Help centre & support tickets | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
250 | M17 | Patient mobile app | 16 | PAT-54 | Patient app — physical clinic booking | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Physical clinic appointment | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
251 | M17 | Patient mobile app | 16 | PAT-55 | Patient app — assisted booking request | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Assisted booking | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
252 | M17 | Patient mobile app | 16 | PAT-56 | Patient app — low-data mode | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Low-data mode | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
253 | M17 | Patient mobile app | 16 | PAT-57 | Patient app — push notifications | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Push notifications | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
254 | M17 | Patient mobile app | 16 | PAT-58 | Patient app — iOS and Android store release, device matrix, and parity QA | New, Regression, New Integration | Mobile, QA | — | — | Yes | Yes | 3 | Patient mobile app iOS and Android | No app | Store builds; crash-free join; feature parity checklist against every §2 row | Not Started
255 | M18 | Doctor mobile app | 17 | DMO-01 | Doctor app — login & identity (same login and same account as the web portal) | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Login & identity | No doctor app | Same Account login + DoctorId; bind device; no separate doctor identity | Not Started
256 | M18 | Doctor mobile app | 17 | DMO-02 | Doctor app — first-run onboarding (guided setup, number confirmation and permissions) | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | First-run onboarding | No app | Confirm registered mobile; permission primer | Not Started
257 | M18 | Doctor mobile app | 17 | DMO-03 | Doctor app — notification permissions (push, microphone and camera handled properly) | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Notification permissions | No app | OS permission flows; settings deep link if denied | Not Started
258 | M18 | Doctor mobile app | 17 | DMO-04 | Doctor app — today’s queue & schedule (the full day at a glance) | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Today’s queue & schedule | No app | Appointment list APIs; payment + tele flags; no Patient Board | Not Started
259 | M18 | Doctor mobile app | 17 | DMO-05 | Doctor app — availability toggle (go online or offline, set working hours) | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Availability toggle | No app | Same TeleAvailability + schedule APIs as web | Not Started
260 | M18 | Doctor mobile app | 17 | DMO-06 | Doctor app — push notifications (waiting, booking, reschedule, cancellation, refill, payment received) | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Push notifications | No app | Consume COM-03 doctor templates | Not Started
261 | M18 | Doctor mobile app | 17 | DMO-07 | Doctor app — patient context card (name, age, chief complaint and last visit) — NO case-taking | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Patient context card | No app; PDF: detailed case-taking stays on the web portal | Read-only card; explicitly no repertory/audio/Rx compose | Not Started
262 | M18 | Doctor mobile app | 17 | DMO-08 | Doctor app — join consultation (video or audio from the phone) | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Join consultation | No app | Same session tokens as TEL-03/04 | Not Started
263 | M18 | Doctor mobile app | 17 | DMO-09 | Doctor app — refill approval (approve or reject repeat prescription requests) | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Refill approval | No app | ERX-10 inbox; approve only — Patient Board remains web | Not Started
264 | M18 | Doctor mobile app | 17 | DMO-10 | Doctor app — earnings summary (today, this week, this month, with payout status) | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Earnings summary | No app | Account ledger read model for this DoctorId — not a second money system | Not Started
265 | M18 | Doctor mobile app | 17 | DMO-11 | Doctor app — offline handling (weak connection or expired session) | New, Regression | Mobile, QA | — | — | Yes | Yes | 4 | Offline handling | No app | Queued actions policy (do not fake join); session expiry uses SEC-03 | Not Started
266 | M18 | Doctor mobile app | 17 | DMO-12 | Doctor app — reliability monitoring (failures reported automatically) | New Integration, Regression | Mobile, QA | — | — | Yes | Yes | 2 | Reliability monitoring | No app | Crash/error SDK; join failures also as TeleSessionEvent | Not Started
267 | M18 | Doctor mobile app | 17 | DMO-13 | Doctor app — iOS and Android parity QA (queue, availability, notifications, context, video, refill, earnings) | New, Regression | Mobile, QA | — | — | Yes | Yes | 2 | Doctor mobile app iOS and Android | No app | Parity checklist for every §3 row on both OS | Not Started
268 | M19 | Reports, NFR & delivery gate | 18 | RPT-01 | Admin overview dashboard — platform-wide activity at a glance (replace Velzon ecommerce) | Existing Improvement, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Admin overview dashboard / Admin dashboard | Velzon ecommerce dashboard 0% product; login lands /dashboard | True /admin/dashboard KPIs: doctors, credentialing, bookings, GMV, failed payments, tickets, HomeoMeds exceptions; redirect /dashboard away from StoreVisits | Not Started
269 | M19 | Reports, NFR & delivery gate | 18 | RPT-02 | Doctor practice statistics — patient and consultation trends (extend existing charts) | Existing Improvement, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Doctor practice statistics | Patient stats charts live | Keep as foundation; ensure visit type/mode included after APT-02 | Not Started
270 | M19 | Reports, NFR & delivery gate | 18 | RPT-03 | Follow-up analysis — due/overdue patients and follow-up conversion | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Follow-up analysis | Does not exist; follow-up option in notes does not save | /doctor/follow-up-analysis from VisitType + CON-04 tasks | Not Started
271 | M19 | Reports, NFR & delivery gate | 18 | RPT-04 | Clinic performance analysis — appointments, slot utilisation, no-shows, cancellations, waiting time and revenue | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Clinic performance analysis | Does not exist | /doctor/clinic-performance including payment collected and tele duration if timed | Not Started
272 | M19 | Reports, NFR & delivery gate | 18 | RPT-05 | Payment reconciliation report — bookings matched against payments | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 3 | Payment reconciliation report / Consult booking & payment reconciliation | FIN-02 built the queue; this is the report/export | Exportable report from the same reconciliation query | Not Started
273 | M19 | Reports, NFR & delivery gate | 18 | RPT-06 | Settlement & payout reports — amounts due and paid to doctors and pharmacies | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 3 | Settlement & payout reports | FIN-04/05 exist as ops screens | Formal report/export of runs and payouts | Not Started
274 | M19 | Reports, NFR & delivery gate | 18 | RPT-07 | GST & invoice reports (reporting surface of FIN-08) | New, Regression | Web, QA | Yes | — | — | Yes | 2 | GST & invoice reports | FIN-08 built tax screen | Confirm report pack (GSTR-style export as agreed with CA) — configuration | Not Started
275 | M19 | Reports, NFR & delivery gate | 18 | RPT-08 | Doctor earnings summary — daily, weekly and monthly earnings with payout status (web + same API as DMO-10) | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Doctor earnings summary | Does not exist | Web earnings page using same API as doctor app | Not Started
276 | M19 | Reports, NFR & delivery gate | 18 | RPT-09 | Medicine order reports — order volumes, fulfilment and exceptions | New, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Medicine order reports | Does not exist | Volumes, SLA, exception counts from HomeoMeds | Not Started
277 | M19 | Reports, NFR & delivery gate | 18 | RPT-10 | Platform users remaining 20% — import, export and activation control | Existing Improvement, Regression | Web, UI, QA | Yes | Yes | — | Yes | 4 | Platform users | List/Add/Edit live; Import/Export buttons dead; no verification column | Wire Import/Export; verification column; activate/lock; link credentialing | Not Started
278 | M19 | Reports, NFR & delivery gate | 19 | QA-01 | One ecosystem proof — patient, appointment, prescription and payment created anywhere are visible everywhere | Regression | QA | — | — | — | Yes | 3 | One connected ecosystem | Surfaces were built in phases | End-to-end scripts covering all six user types | Not Started
279 | M19 | Reports, NFR & delivery gate | 19 | QA-02 | Delivery summary gate — every area in PDF §18 signed off | Regression | QA | — | — | — | Yes | 2 | Summary of delivery | This register is the scope | Walk the coverage sheet; zero PDF rows with Status≠Done unless formally deferred with client sign | In Progress
280 | M19 | Reports, NFR & delivery gate | 19 | NFR-01 | NFR — performance, low-data, reliability, secrets, dual-API freeze | Existing Modification, Regression | Web, QA | Yes | — | — | Yes | 3 | Low-data mode / Reliability monitoring / Secure login | Known risks: plaintext passwords (fixed P0), secrets in appsettings, dual API drift | Rotate secrets; no new third API; patient low-data verified; doctor reliability SDK live | Not Started

## 08_Dashboard
LIVE DASHBOARD — counts read T_MASTER, which reads the module sheets. Mark Frontend Status = Done on M05 and these numbers change. No refresh.
Integrity
Master rows | 1000
Must equal | 1000
Check | OK — nothing skipped
Overall Status
Status | Count
Not Started | 932
In Progress | 2
Blocked | 0
Done | 57
Deferred | 0
N/A | 9
Function remaining vs complete (Scope = Yes only)
Function | In scope (Yes) | Done | Remaining | % Done
Frontend | 634 | 30 | 604 | 4.732%
Backend | 554 | 56 | 498 | 10.11%
Database | 196 | 0 | 196 | 0%
API | 627 | 55 | 572 | 8.772%
Mobile | 288 | 3 | 285 | 1.042%
Integration | 27 | 0 | 27 | 0%
Track × Overall Status
Track | Not Started | In Progress | Blocked | Done | Deferred | Total
Web | 314 | 2 | 0 | 54 | 0 | 370
UI | 135 | 0 | 0 | 0 | 0 | 135
Mobile | 206 | 0 | 0 | 3 | 0 | 209
QA | 277 | 0 | 0 | 0 | 0 | 277
Module remaining (sum of Layers Remaining on Master)
Code | Dev Module | Sub-tasks | Layer remaining
M00 | PRE — Client gates | 11 | 5
M01 | Foundation & Security | 41 | 73
M02 | Admin clinical masters | 85 | 88
M03 | Doctor clinical workspace | 67 | 162
M04 | Doctor daily operations | 33 | 81
M05 | Appointments & scheduling | 40 | 96
M06 | Reception portal | 39 | 87
M07 | Payment system | 42 | 93
M08 | Account & finance | 44 | 106
M09 | Trust & verification | 27 | 62
M10 | Patient website | 35 | 78
M11 | Digital prescription (eRx) | 35 | 70
M12 | Telemedicine | 44 | 99
M13 | Communications | 22 | 56
M14 | Support & help desk | 24 | 52
M15 | HomeoMeds | 55 | 119
M16 | Patient continuity APIs | 33 | 83
M17 | Patient mobile app | 231 | 568
M18 | Doctor mobile app | 48 | 115
M19 | Reports, NFR & delivery gate | 44 | 89

## M00_PRE_Client_Gates
M00 PRE — Client gates — 11 sub-tasks (Web 11). YELLOW = edit here (Assigned To, Frontend/Backend/Database/API/Mobile/Integration Status + Assigned). Scope Yes/No is fixed. Status N/A = that function is not in this sub-task. Master, Web/UI/Mobile/QA sheets and Dashboard follow these cells live. | [41 empty] | Live copy of 00_Employees column B — do not edit. New names appear here automatically.
Module Seq | Original Seq | Dev Module Code | Dev Module | Track | Phase | Phase Name | WBS | Main Task ID | Main Task | Sub Task ID | Sub Task | Work Type | Source Module / Area | PDF Section | PDF Feature (exact wording) | PDF Delivery Text | Application Surface | Layer | Assigned To (lead) | Frontend | Frontend Status | Frontend Assigned | Backend | Backend Status | Backend Assigned | Database | Database Status | Database Assigned | API | API Status | API Assigned | Mobile | Mobile Status | Mobile Assigned | Integration | Integration Status | Integration Assigned | Layers Remaining | Overall Status | Notes | Open Module Sheet | _EmpList
1 | 1 | M00 | PRE — Client gates | Web | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.1 | PRE-01 | Decide settlement model — Homeocentrum holds all money (food-delivery / quick-commerce pattern) | PRE-01.01 | Workshop with finance: confirm Homeocentrum is single merchant of record for consult + medicine + subscription | Client Decision | Finance | §9 + §8 | Every transaction passes through Homeocentrum | Built on the principle: every transaction passes through Homeocentrum, in the same way a food-delivery or quick-commerce platform holds all payments centrally. | Account / Gateway | Decision | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 0 | N/A |  | EDIT HERE — this module sheet | Unassigned
2 | 2 | M00 | PRE — Client gates | Web | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.1 | PRE-01 | Decide settlement model — Homeocentrum holds all money (food-delivery / quick-commerce pattern) | PRE-01.02 | Choose v1 payout mechanic: Homeocentrum-held + NEFT/IMPS vs Razorpay Route / linked accounts | Client Decision | Finance | §9 + §8 | Every transaction passes through Homeocentrum | Built on the principle: every transaction passes through Homeocentrum, in the same way a food-delivery or quick-commerce platform holds all payments centrally. | Account / Gateway | Decision | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | 1 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
3 | 3 | M00 | PRE — Client gates | Web | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.1 | PRE-01 | Decide settlement model — Homeocentrum holds all money (food-delivery / quick-commerce pattern) | PRE-01.03 | Record decision in config (SettlementModel) — engineering must not hardcode a split model | Configuration | Finance | §9 + §8 | Every transaction passes through Homeocentrum | Built on the principle: every transaction passes through Homeocentrum, in the same way a food-delivery or quick-commerce platform holds all payments centrally. | Account / Gateway | Configuration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet | Digvijay Jadhav
4 | 4 | M00 | PRE — Client gates | Web | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.2 | PRE-02 | Decide reception cash policy — clinic retains vs remits to Homeocentrum | PRE-02.01 | OQ: cash collected at reception retained by clinic or remitted to Homeocentrum? | Client Decision | Finance / Reception | §9 | Reception payment collection | Cash, UPI, card or payment link with printed receipt | Account / Reception | Decision | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 0 | N/A |  | EDIT HERE — this module sheet | Gourav Nikam
5 | 5 | M00 | PRE — Client gates | Web | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.2 | PRE-02 | Decide reception cash policy — clinic retains vs remits to Homeocentrum | PRE-02.02 | Document GST treatment on consult fee, platform fee, and medicine (on which amount, which GSTIN) | Client Decision | Finance / Reception | §9 | Reception payment collection | Cash, UPI, card or payment link with printed receipt | Account / Reception | Decision | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 0 | N/A |  | EDIT HERE — this module sheet
6 | 6 | M00 | PRE — Client gates | Web | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.2 | PRE-02 | Decide reception cash policy — clinic retains vs remits to Homeocentrum | PRE-02.03 | Confirm commission %, settlement hold T+N days, invoice numbering series — configuration not code | Configuration | Finance / Reception | §9 | Reception payment collection | Cash, UPI, card or payment link with printed receipt | Account / Reception | Configuration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
7 | 7 | M00 | PRE — Client gates | Web | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.3 | PRE-03 | Vendor and legal gates — video SDK, SMS, WhatsApp, push, DPDP copy | PRE-03.01 | Select in-browser + mobile video vendor (Agora / Twilio / Daily / WebRTC self-host) — required for §10 | Client Decision | Platform | §10 + §14 + §17 | Telemedicine + notifications + consent | Video consultation; SMS/WhatsApp/Push/Email; consent records | Shared | Decision | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | 1 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
8 | 8 | M00 | PRE — Client gates | Web | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.3 | PRE-03 | Vendor and legal gates — video SDK, SMS, WhatsApp, push, DPDP copy | PRE-03.02 | Select SMS provider (MSG91 / Twilio / etc.) and confirm DLT templates for appointment/OTP/cancel | Client Decision | Platform | §10 + §14 + §17 | Telemedicine + notifications + consent | Video consultation; SMS/WhatsApp/Push/Email; consent records | Shared | Decision | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | 1 | Not Started |  | EDIT HERE — this module sheet
9 | 9 | M00 | PRE — Client gates | Web | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.3 | PRE-03 | Vendor and legal gates — video SDK, SMS, WhatsApp, push, DPDP copy | PRE-03.03 | Legal: privacy (data protection, recording, pharmacy consent) and terms (payments, refunds, telemedicine, medicine orders) drafted for §4 + §17 | Client Decision | Platform | §10 + §14 + §17 | Telemedicine + notifications + consent | Video consultation; SMS/WhatsApp/Push/Email; consent records | Shared | Legal | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 0 | N/A |  | EDIT HERE — this module sheet | Pranav Bandekar
10 | 10 | M00 | PRE — Client gates | Web | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.3 | PRE-03 | Vendor and legal gates — video SDK, SMS, WhatsApp, push, DPDP copy | PRE-03.04 | OQ: unpaid-booking slot hold duration vs release immediately if patient does not pay | Client Decision | Platform | §10 + §14 + §17 | Telemedicine + notifications + consent | Video consultation; SMS/WhatsApp/Push/Email; consent records | Shared | Decision | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 0 | N/A |  | EDIT HERE — this module sheet
11 | 11 | M00 | PRE — Client gates | Web | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.3 | PRE-03 | Vendor and legal gates — video SDK, SMS, WhatsApp, push, DPDP copy | PRE-03.05 | OQ: live-doctor credentialing backfill — auto-Approve existing doctors? Unverified doctors visible only to own clinic? | Client Decision | Platform | §10 + §14 + §17 | Telemedicine + notifications + consent | Video consultation; SMS/WhatsApp/Push/Email; consent records | Shared | Decision | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 0 | N/A |  | EDIT HERE — this module sheet | Gourav Nikam
Gourav Nikam

## M01_Foundation_Security
M01 Foundation & Security — 41 sub-tasks (Web 24 · UI 6 · Mobile 1 · QA 10). YELLOW = edit here (Assigned To, Frontend/Backend/Database/API/Mobile/Integration Status + Assigned). Scope Yes/No is fixed. Status N/A = that function is not in this sub-task. Master, Web/UI/Mobile/QA sheets and Dashboard follow these cells live. | [41 empty] | Live copy of 00_Employees column B — do not edit. New names appear here automatically.
Module Seq | Original Seq | Dev Module Code | Dev Module | Track | Phase | Phase Name | WBS | Main Task ID | Main Task | Sub Task ID | Sub Task | Work Type | Source Module / Area | PDF Section | PDF Feature (exact wording) | PDF Delivery Text | Application Surface | Layer | Assigned To (lead) | Frontend | Frontend Status | Frontend Assigned | Backend | Backend Status | Backend Assigned | Database | Database Status | Database Assigned | API | API Status | API Assigned | Mobile | Mobile Status | Mobile Assigned | Integration | Integration Status | Integration Assigned | Layers Remaining | Overall Status | Notes | Open Module Sheet | _EmpList
1 | 12 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.1 | FND-01 | One connected ecosystem — shared keys so a patient, appointment, prescription and payment created anywhere are visible everywhere | FND-01.01 | Publish shared-key design (DoctorId, PatientId, PatientAppId, CaseId, ErxId, LedgerTxnId, MedicineOrderId) and event list (created/rescheduled/cancelled/paid/signed/accepted) | New | Platform | §1 | One connected ecosystem serving six types of users | A patient, an appointment, a prescription and a payment created anywhere in the system are visible everywhere else — there are no separate systems to reconcile. | Shared | Architecture | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Unassigned
2 | 13 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.1 | FND-01 | One connected ecosystem — shared keys so a patient, appointment, prescription and payment created anywhere are visible everywhere | FND-01.02 | Add role enum values Patient, Account, PharmacyPartner alongside existing Admin/Doctor/Reception (keep unused Management/Supervisor/Inspector unused) | New | Platform | §1 | One connected ecosystem serving six types of users | A patient, an appointment, a prescription and a payment created anywhere in the system are visible everywhere else — there are no separate systems to reconcile. | Shared | Database + Auth | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
3 | 14 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.1 | FND-01 | One connected ecosystem — shared keys so a patient, appointment, prescription and payment created anywhere are visible everywhere | FND-01.03 | All new domain modules on NigaHomeopathy-API (.NET 8); do not create a third API; classic API only where login/Rx-write/Razorpay already live until ported | Existing Modification | Platform | §1 | One connected ecosystem serving six types of users | A patient, an appointment, a prescription and a payment created anywhere in the system are visible everywhere else — there are no separate systems to reconcile. | Shared | Architecture | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Digvijay Jadhav
4 | 15 | M01 | Foundation & Security | QA | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.1 | FND-01 | One connected ecosystem — shared keys so a patient, appointment, prescription and payment created anywhere are visible everywhere | FND-01.04 | QA: create appointment on Reception → visible on Doctor web; pay on Patient web → same PaymentStatus on Doctor and Account (after Phase 6) | Regression | Platform | §1 | One connected ecosystem serving six types of users | A patient, an appointment, a prescription and a payment created anywhere in the system are visible everywhere else — there are no separate systems to reconcile. | Shared | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
5 | 16 | M01 | Foundation & Security | UI | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.2 | FND-02 | Delivery footprint — 2 mobile apps · 5 web portals · payment · telemedicine · digital prescription · HomeoMeds (programme skeleton) | FND-02.01 | Web: add Account layout + home redirect; Pharmacy layout stub; do not build screens yet | New | Platform | §1 | Delivery covers | 2 mobile applications · 5 web portals · payment system · telemedicine · digital prescription · online medicine delivery. | Shared | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
6 | 17 | M01 | Foundation & Security | UI | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.2 | FND-02 | Delivery footprint — 2 mobile apps · 5 web portals · payment · telemedicine · digital prescription · HomeoMeds (programme skeleton) | FND-02.02 | Extend roles.js and AuthProtected with per-route ACL skeleton (deny-by-default for new routes) | Existing Improvement | Platform | §1 | Delivery covers | 2 mobile applications · 5 web portals · payment system · telemedicine · digital prescription · online medicine delivery. | Shared | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
7 | 18 | M01 | Foundation & Security | Mobile | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.2 | FND-02 | Delivery footprint — 2 mobile apps · 5 web portals · payment · telemedicine · digital prescription · HomeoMeds (programme skeleton) | FND-02.03 | Mobile: create Patient app and Doctor app repository/bootstrap (React Native or agreed stack) — empty shells only | New | Platform | §1 | Delivery covers | 2 mobile applications · 5 web portals · payment system · telemedicine · digital prescription · online medicine delivery. | Shared | Mobile | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
8 | 19 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.2 | FND-02 | Delivery footprint — 2 mobile apps · 5 web portals · payment · telemedicine · digital prescription · HomeoMeds (programme skeleton) | FND-02.04 | Document the five portals: Patient Website, Doctor Web Portal, Reception Portal, Admin Portal, Account Department (Pharmacy console is HomeoMeds, not a 6th portal in the PDF count) | New | Platform | §1 | Delivery covers | 2 mobile applications · 5 web portals · payment system · telemedicine · digital prescription · online medicine delivery. | Shared | Architecture | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 0 | N/A |  | EDIT HERE — this module sheet
9 | 20 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.3 | SEC-01 | Secure login — protected credentials for every user type | SEC-01.01 | DB/Migration: hash existing UserMaster passwords (bcrypt/PBKDF2); never store new plaintext | Data Migration | Security | §17 | Secure login | Protected credentials for every user type | All web + later mobile | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Pranav Bandekar
10 | 21 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.3 | SEC-01 | Secure login — protected credentials for every user type | SEC-01.02 | API: Login verifies hash; embed Role + DoctorId claims; keep classic login URL until .NET 8 login is cut over | Existing Modification | Security | §17 | Secure login | Protected credentials for every user type | All web + later mobile | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
11 | 22 | M01 | Foundation & Security | UI | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.3 | SEC-01 | Secure login — protected credentials for every user type | SEC-01.03 | UI: remove fakeBackend() from App.js production path; login still Formik/Yup | Existing Modification | Security | §17 | Secure login | Protected credentials for every user type | All web + later mobile | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
12 | 23 | M01 | Foundation & Security | QA | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.3 | SEC-01 | Secure login — protected credentials for every user type | SEC-01.04 | QA: Admin, Doctor, Reception login; invalid password; deactivated user; SQL injection/brute-force rate limit | Regression | Security | §17 | Secure login | Protected credentials for every user type | All web + later mobile | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
13 | 24 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.4 | SEC-02 | Secure password reset — time-limited reset links (stop plaintext email + fake thunk) | SEC-02.01 | DB: PasswordResetToken (UserId, TokenHash, ExpiresAt, UsedAt) | New | Security | §17 | Secure password reset | Time-limited reset links | Admin / Doctor / Reception web | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
14 | 25 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.4 | SEC-02 | Secure password reset — time-limited reset links (stop plaintext email + fake thunk) | SEC-02.02 | API: ForgotPassword sends reset link; ResetPassword consumes token; stop emailing plaintext; ChangePassword for authenticated user | Existing Modification | Security | §17 | Secure password reset | Time-limited reset links | Admin / Doctor / Reception web | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
15 | 26 | M01 | Foundation & Security | UI | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.4 | SEC-02 | Secure password reset — time-limited reset links (stop plaintext email + fake thunk) | SEC-02.03 | UI: replace slices/auth/forgetpwd fake/Firebase with real APIs; /reset-password/:token success/expiry states | Existing Improvement | Security | §17 | Secure password reset | Time-limited reset links | Admin / Doctor / Reception web | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
16 | 27 | M01 | Foundation & Security | QA | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.4 | SEC-02 | Secure password reset — time-limited reset links (stop plaintext email + fake thunk) | SEC-02.04 | QA: expired token, reused token, unknown email (no user enumeration), logged-in change password | Regression | Security | §17 | Secure password reset | Time-limited reset links | Admin / Doctor / Reception web | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
17 | 28 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.5 | SEC-03 | Session control — proper sign-out across web and mobile | SEC-03.01 | API: POST /Account/Logout; persist UserLoginStatus; optional denylist until token expiry | Existing Improvement | Security | §17 | Session control | Proper sign-out across web and mobile | All | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
18 | 29 | M01 | Foundation & Security | UI | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.5 | SEC-03 | Session control — proper sign-out across web and mobile | SEC-03.02 | Web: Logout.js calls API then clears authUser + patient-board session (keep existing board clear) | Existing Improvement | Security | §17 | Session control | Proper sign-out across web and mobile | All | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
19 | 30 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.5 | SEC-03 | Session control — proper sign-out across web and mobile | SEC-03.03 | Contract: mobile apps MUST use the same Logout endpoint (implemented in Phases 16–17) | New | Security | §17 | Session control | Proper sign-out across web and mobile | All | API contract | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
20 | 31 | M01 | Foundation & Security | QA | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.5 | SEC-03 | Session control — proper sign-out across web and mobile | SEC-03.04 | QA: logout on one tab; expired session message; 401 interceptor | Regression | Security | §17 | Session control | Proper sign-out across web and mobile | All | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
21 | 32 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.6 | SEC-04 | Role-based access — each role sees only what it is permitted to see | SEC-04.01 | Backend: restore GetMenuByRole; add role attributes on new money and PII APIs | Existing Improvement | Security | §17 | Role-based access | Each role sees only what it is permitted to see | Admin / All web | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
22 | 33 | M01 | Foundation & Security | UI | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.6 | SEC-04 | Role-based access — each role sees only what it is permitted to see | SEC-04.02 | Frontend: hide routes the role cannot view; keep Velzon demo routes out of production menus | Existing Improvement | Security | §17 | Role-based access | Each role sees only what it is permitted to see | Admin / All web | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
23 | 34 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.6 | SEC-04 | Role-based access — each role sees only what it is permitted to see | SEC-04.03 | Separation of duties seed: Account role controls money; Admin controls platform and clinical data — neither can perform the other’s role (PDF §8) | New | Security | §17 | Role-based access | Each role sees only what it is permitted to see | Admin / All web | Configuration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
24 | 35 | M01 | Foundation & Security | QA | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.6 | SEC-04 | Role-based access — each role sees only what it is permitted to see | SEC-04.04 | QA: Reception cannot open repertory masters; Account cannot edit diagnosis; Doctor cannot see platform-wide ledger | Regression | Security | §17 | Role-based access | Each role sees only what it is permitted to see | Admin / All web | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
25 | 36 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.7 | SEC-05 | Patient data protection — health records restricted to the treating doctor and the patient | SEC-05.01 | API: enforce DoctorId ownership on Patient, Appointment, Case, Rx, notes, labs, board backup | Existing Improvement | Security | §17 | Patient data protection | Health records restricted to the treating doctor and the patient | API | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
26 | 37 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.7 | SEC-05 | Patient data protection — health records restricted to the treating doctor and the patient | SEC-05.02 | Disable directory browsing on /attachments and /Blogs; signed-URL or authorised download for documents | Existing Modification | Security | §17 | Patient data protection | Health records restricted to the treating doctor and the patient | API | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
27 | 38 | M01 | Foundation & Security | QA | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.7 | SEC-05 | Patient data protection — health records restricted to the treating doctor and the patient | SEC-05.03 | QA: IDOR tests (swap PatientAppId / CaseId in requests) | Regression | Security | §17 | Patient data protection | Health records restricted to the treating doctor and the patient | API | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
28 | 39 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.8 | SEC-06 | Consent records infrastructure — every consent captured, stored and reviewable | SEC-06.01 | DB: ConsentRecord + ConsentType master (Privacy, Booking, TeleRecording, PharmacyShare, Marketing, Caregiver) | New | Security / Trust | §17 | Consent records | Every consent captured, stored and reviewable | Shared | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
29 | 40 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.8 | SEC-06 | Consent records infrastructure — every consent captured, stored and reviewable | SEC-06.02 | API: Grant / Withdraw / List-mine / Admin-audit (no clinical content in the API response beyond type+time) | New | Security / Trust | §17 | Consent records | Every consent captured, stored and reviewable | Shared | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
30 | 41 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.8 | SEC-06 | Consent records infrastructure — every consent captured, stored and reviewable | SEC-06.03 | Reuse AudioCaseConsentLog pattern; do not fork a second consent model for telemedicine (Phase 11 will write TeleRecording into ConsentRecord) | Existing Improvement | Security / Trust | §17 | Consent records | Every consent captured, stored and reviewable | Shared | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
31 | 42 | M01 | Foundation & Security | QA | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.8 | SEC-06 | Consent records infrastructure — every consent captured, stored and reviewable | SEC-06.04 | QA: grant, withdraw, re-grant; audit log immutable | Regression | Security / Trust | §17 | Consent records | Every consent captured, stored and reviewable | Shared | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
32 | 43 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.9 | SEC-07 | OTP verification infrastructure — applied to sensitive actions including payouts and pharmacy acceptance | SEC-07.01 | DB: OtpChallenge, OtpAuditLog (Action, EntityType, EntityId, ToMasked, Success, At) | New | Security | §17 + §8 + §12 | OTP verification | Applied to sensitive actions including payouts and pharmacy acceptance | Shared | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
33 | 44 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.9 | SEC-07 | OTP verification infrastructure — applied to sensitive actions including payouts and pharmacy acceptance | SEC-07.02 | API: RequestOtp / VerifyOtp (generic); rate-limit; lockout; SMS provider adapter stub until PRE-03 vendor is live | New | Security | §17 + §8 + §12 | OTP verification | Applied to sensitive actions including payouts and pharmacy acceptance | Shared | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | EDIT HERE — this module sheet
34 | 45 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.9 | SEC-07 | OTP verification infrastructure — applied to sensitive actions including payouts and pharmacy acceptance | SEC-07.03 | GET /api/Otp/Audit for Account and Admin (masked destination) | New | Security | §17 + §8 + §12 | OTP verification | Applied to sensitive actions including payouts and pharmacy acceptance | Shared | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
35 | 46 | M01 | Foundation & Security | QA | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.9 | SEC-07 | OTP verification infrastructure — applied to sensitive actions including payouts and pharmacy acceptance | SEC-07.04 | QA: replay OTP, expiry, max attempts, audit completeness | Regression | Security | §17 + §8 + §12 | OTP verification | Applied to sensitive actions including payouts and pharmacy acceptance | Shared | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
36 | 47 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.10 | SEC-08 | Complete audit trail — who did what and when across payments, prescriptions and approvals | SEC-08.01 | DB: AuditEvent (ActorUserId, Role, Action, Entity, OldJson, NewJson, At, CorrelationId) | New | Security | §17 + §9 | Complete audit trail | Who did what, and when, across payments, prescriptions and approvals / Every transaction traceable end to end by Homeocentrum | Shared | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
37 | 48 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.10 | SEC-08 | Complete audit trail — who did what and when across payments, prescriptions and approvals | SEC-08.02 | API middleware: write audit on mutating money/Rx/approval endpoints (start with a helper used by later phases) | New | Security | §17 + §9 | Complete audit trail | Who did what, and when, across payments, prescriptions and approvals / Every transaction traceable end to end by Homeocentrum | Shared | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
38 | 49 | M01 | Foundation & Security | QA | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.10 | SEC-08 | Complete audit trail — who did what and when across payments, prescriptions and approvals | SEC-08.03 | QA: sample sign-prescription / approve-payout (when those exist) produce audit rows | Regression | Security | §17 + §9 | Complete audit trail | Who did what, and when, across payments, prescriptions and approvals / Every transaction traceable end to end by Homeocentrum | Shared | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
39 | 50 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.11 | SEC-09 | Secure documents — prescriptions, reports and uploads protected from unauthorised access | SEC-09.01 | DB: SecureDocument (OwnerType, OwnerId, BlobPath, Mime, Hash, CreatedBy) | New | Security | §17 | Secure documents | Prescriptions, reports and uploads protected from unauthorised access | Shared | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
40 | 51 | M01 | Foundation & Security | Web | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.11 | SEC-09 | Secure documents — prescriptions, reports and uploads protected from unauthorised access | SEC-09.02 | API: upload (multipart) + authorised GET; no public folder listing | New | Security | §17 | Secure documents | Prescriptions, reports and uploads protected from unauthorised access | Shared | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
41 | 52 | M01 | Foundation & Security | QA | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.11 | SEC-09 | Secure documents — prescriptions, reports and uploads protected from unauthorised access | SEC-09.03 | QA: doctor of record can download; other doctor 403; anonymous 401 | Regression | Security | §17 | Secure documents | Prescriptions, reports and uploads protected from unauthorised access | Shared | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet

## M02_Admin_Clinical
M02 Admin clinical masters — 85 sub-tasks (Web 56 · UI 1 · QA 28). YELLOW = edit here (Assigned To, Frontend/Backend/Database/API/Mobile/Integration Status + Assigned). Scope Yes/No is fixed. Status N/A = that function is not in this sub-task. Master, Web/UI/Mobile/QA sheets and Dashboard follow these cells live. | [41 empty] | Live copy of 00_Employees column B — do not edit. New names appear here automatically.
Module Seq | Original Seq | Dev Module Code | Dev Module | Track | Phase | Phase Name | WBS | Main Task ID | Main Task | Sub Task ID | Sub Task | Work Type | Source Module / Area | PDF Section | PDF Feature (exact wording) | PDF Delivery Text | Application Surface | Layer | Assigned To (lead) | Frontend | Frontend Status | Frontend Assigned | Backend | Backend Status | Backend Assigned | Database | Database Status | Database Assigned | API | API Status | API Assigned | Mobile | Mobile Status | Mobile Assigned | Integration | Integration Status | Integration Assigned | Layers Remaining | Overall Status | Notes | Open Module Sheet | _EmpList
1 | 53 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.1 | ADM-R01 | Keep and harden Admin Repertory sections (do not rebuild) | ADM-R01.01 | Regression: list / add / edit / (import-export if present) for Repertory sections | Existing | Repertory | §7.1 | Repertory sections | Manage repertory sections | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Unassigned
2 | 54 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.1 | ADM-R01 | Keep and harden Admin Repertory sections (do not rebuild) | ADM-R01.02 | ACL: only Admin (and permitted roles) can mutate Repertory sections; Doctor is read-only consumer on Patient Board | Existing Improvement | Repertory | §7.1 | Repertory sections | Manage repertory sections | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | EDIT HERE — this module sheet | Gourav Nikam
3 | 55 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.1 | ADM-R01 | Keep and harden Admin Repertory sections (do not rebuild) | ADM-R01.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Repertory sections; do not silently switch | Existing | Repertory | §7.1 | Repertory sections | Manage repertory sections | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | EDIT HERE — this module sheet | Digvijay Jadhav
4 | 56 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.2 | ADM-R02 | Keep and harden Admin Subsection & rubric tree (do not rebuild) | ADM-R02.01 | Regression: list / add / edit / (import-export if present) for Subsection & rubric tree | Existing | Repertory | §7.1 | Subsection & rubric tree | Manage the full rubric hierarchy | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
5 | 57 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.2 | ADM-R02 | Keep and harden Admin Subsection & rubric tree (do not rebuild) | ADM-R02.02 | ACL: only Admin (and permitted roles) can mutate Subsection & rubric tree; Doctor is read-only consumer on Patient Board | Existing Improvement | Repertory | §7.1 | Subsection & rubric tree | Manage the full rubric hierarchy | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | EDIT HERE — this module sheet
6 | 58 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.2 | ADM-R02 | Keep and harden Admin Subsection & rubric tree (do not rebuild) | ADM-R02.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Subsection & rubric tree; do not silently switch | Existing | Repertory | §7.1 | Subsection & rubric tree | Manage the full rubric hierarchy | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | EDIT HERE — this module sheet | Gourav Nikam
7 | 59 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.3 | ADM-R03 | Keep and harden Admin Rubric–remedy mapping (do not rebuild) | ADM-R03.01 | Regression: list / add / edit / (import-export if present) for Rubric–remedy mapping | Existing | Repertory | §7.1 | Rubric–remedy mapping | Map remedies to rubrics with author and grade | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
8 | 60 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.3 | ADM-R03 | Keep and harden Admin Rubric–remedy mapping (do not rebuild) | ADM-R03.02 | ACL: only Admin (and permitted roles) can mutate Rubric–remedy mapping; Doctor is read-only consumer on Patient Board | Existing Improvement | Repertory | §7.1 | Rubric–remedy mapping | Map remedies to rubrics with author and grade | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | EDIT HERE — this module sheet
9 | 61 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.3 | ADM-R03 | Keep and harden Admin Rubric–remedy mapping (do not rebuild) | ADM-R03.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Rubric–remedy mapping; do not silently switch | Existing | Repertory | §7.1 | Rubric–remedy mapping | Map remedies to rubrics with author and grade | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | EDIT HERE — this module sheet | Pranav Bandekar
10 | 62 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.4 | ADM-R04 | Keep and harden Admin Remedy-linked rubrics (do not rebuild) | ADM-R04.01 | Regression: list / add / edit / (import-export if present) for Remedy-linked rubrics | Existing | Repertory | §7.1 | Remedy-linked rubrics | View all rubrics linked to a remedy | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
11 | 63 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.4 | ADM-R04 | Keep and harden Admin Remedy-linked rubrics (do not rebuild) | ADM-R04.02 | ACL: only Admin (and permitted roles) can mutate Remedy-linked rubrics; Doctor is read-only consumer on Patient Board | Existing Improvement | Repertory | §7.1 | Remedy-linked rubrics | View all rubrics linked to a remedy | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | EDIT HERE — this module sheet | Gourav Nikam
12 | 64 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.4 | ADM-R04 | Keep and harden Admin Remedy-linked rubrics (do not rebuild) | ADM-R04.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Remedy-linked rubrics; do not silently switch | Existing | Repertory | §7.1 | Remedy-linked rubrics | View all rubrics linked to a remedy | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | EDIT HERE — this module sheet
13 | 65 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.5 | ADM-R05 | Keep and harden Admin Language master (do not rebuild) | ADM-R05.01 | Regression: list / add / edit / (import-export if present) for Language master | Existing | Repertory | §7.1 | Language master | Manage languages | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
14 | 66 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.5 | ADM-R05 | Keep and harden Admin Language master (do not rebuild) | ADM-R05.02 | ACL: only Admin (and permitted roles) can mutate Language master; Doctor is read-only consumer on Patient Board | Existing Improvement | Repertory | §7.1 | Language master | Manage languages | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | EDIT HERE — this module sheet | Gourav Nikam
15 | 67 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.5 | ADM-R05 | Keep and harden Admin Language master (do not rebuild) | ADM-R05.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Language master; do not silently switch | Existing | Repertory | §7.1 | Language master | Manage languages | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | EDIT HERE — this module sheet
16 | 68 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.6 | ADM-R06 | Keep and harden Admin Body part master (do not rebuild) | ADM-R06.01 | Regression: list / add / edit / (import-export if present) for Body part master | Existing | Repertory | §7.1 | Body part master | Manage body parts | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
17 | 69 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.6 | ADM-R06 | Keep and harden Admin Body part master (do not rebuild) | ADM-R06.02 | ACL: only Admin (and permitted roles) can mutate Body part master; Doctor is read-only consumer on Patient Board | Existing Improvement | Repertory | §7.1 | Body part master | Manage body parts | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | EDIT HERE — this module sheet
18 | 70 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.6 | ADM-R06 | Keep and harden Admin Body part master (do not rebuild) | ADM-R06.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Body part master; do not silently switch | Existing | Repertory | §7.1 | Body part master | Manage body parts | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | EDIT HERE — this module sheet
19 | 71 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.7 | ADM-R07 | Keep and harden Admin Intensity master (do not rebuild) | ADM-R07.01 | Regression: list / add / edit / (import-export if present) for Intensity master | Existing | Repertory | §7.1 | Intensity master | Manage intensity levels | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
20 | 72 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.7 | ADM-R07 | Keep and harden Admin Intensity master (do not rebuild) | ADM-R07.02 | ACL: only Admin (and permitted roles) can mutate Intensity master; Doctor is read-only consumer on Patient Board | Existing Improvement | Repertory | §7.1 | Intensity master | Manage intensity levels | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | EDIT HERE — this module sheet
21 | 73 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.7 | ADM-R07 | Keep and harden Admin Intensity master (do not rebuild) | ADM-R07.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Intensity master; do not silently switch | Existing | Repertory | §7.1 | Intensity master | Manage intensity levels | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | EDIT HERE — this module sheet
22 | 74 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.8 | ADM-R08 | Keep and harden Admin Remedy master (do not rebuild) | ADM-R08.01 | Regression: list / add / edit / (import-export if present) for Remedy master | Existing | Repertory | §7.1 | Remedy master | Manage the remedy library | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
23 | 75 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.8 | ADM-R08 | Keep and harden Admin Remedy master (do not rebuild) | ADM-R08.02 | ACL: only Admin (and permitted roles) can mutate Remedy master; Doctor is read-only consumer on Patient Board | Existing Improvement | Repertory | §7.1 | Remedy master | Manage the remedy library | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | EDIT HERE — this module sheet
24 | 76 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.8 | ADM-R08 | Keep and harden Admin Remedy master (do not rebuild) | ADM-R08.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Remedy master; do not silently switch | Existing | Repertory | §7.1 | Remedy master | Manage the remedy library | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | EDIT HERE — this module sheet
25 | 77 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.9 | ADM-R09 | Keep and harden Admin Remedy grade master (do not rebuild) | ADM-R09.01 | Regression: list / add / edit / (import-export if present) for Remedy grade master | Existing | Repertory | §7.1 | Remedy grade master | Manage remedy grading | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
26 | 78 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.9 | ADM-R09 | Keep and harden Admin Remedy grade master (do not rebuild) | ADM-R09.02 | ACL: only Admin (and permitted roles) can mutate Remedy grade master; Doctor is read-only consumer on Patient Board | Existing Improvement | Repertory | §7.1 | Remedy grade master | Manage remedy grading | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | EDIT HERE — this module sheet
27 | 79 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.9 | ADM-R09 | Keep and harden Admin Remedy grade master (do not rebuild) | ADM-R09.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Remedy grade master; do not silently switch | Existing | Repertory | §7.1 | Remedy grade master | Manage remedy grading | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | EDIT HERE — this module sheet
28 | 80 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.10 | ADM-M01 | Keep and harden Admin Author master (do not rebuild) | ADM-M01.01 | Regression: list / add / edit / (import-export if present) for Author master | Existing | Materia Medica | §7.1 | Author master | Manage materia medica authors | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
29 | 81 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.10 | ADM-M01 | Keep and harden Admin Author master (do not rebuild) | ADM-M01.02 | ACL: only Admin (and permitted roles) can mutate Author master; Doctor is read-only consumer on Patient Board | Existing Improvement | Materia Medica | §7.1 | Author master | Manage materia medica authors | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | EDIT HERE — this module sheet
30 | 82 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.10 | ADM-M01 | Keep and harden Admin Author master (do not rebuild) | ADM-M01.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Author master; do not silently switch | Existing | Materia Medica | §7.1 | Author master | Manage materia medica authors | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | EDIT HERE — this module sheet
31 | 83 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.11 | ADM-M02 | Keep and harden Admin Materia medica master (do not rebuild) | ADM-M02.01 | Regression: list / add / edit / (import-export if present) for Materia medica master | Existing | Materia Medica | §7.1 | Materia medica master | Manage the materia medica library | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
32 | 84 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.11 | ADM-M02 | Keep and harden Admin Materia medica master (do not rebuild) | ADM-M02.02 | ACL: only Admin (and permitted roles) can mutate Materia medica master; Doctor is read-only consumer on Patient Board | Existing Improvement | Materia Medica | §7.1 | Materia medica master | Manage the materia medica library | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | EDIT HERE — this module sheet
33 | 85 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.11 | ADM-M02 | Keep and harden Admin Materia medica master (do not rebuild) | ADM-M02.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Materia medica master; do not silently switch | Existing | Materia Medica | §7.1 | Materia medica master | Manage the materia medica library | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | EDIT HERE — this module sheet
34 | 86 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.12 | ADM-M03 | Keep and harden Admin Materia medica heads (do not rebuild) | ADM-M03.01 | Regression: list / add / edit / (import-export if present) for Materia medica heads | Existing | Materia Medica | §7.1 | Materia medica heads | Manage chapter headings | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
35 | 87 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.12 | ADM-M03 | Keep and harden Admin Materia medica heads (do not rebuild) | ADM-M03.02 | ACL: only Admin (and permitted roles) can mutate Materia medica heads; Doctor is read-only consumer on Patient Board | Existing Improvement | Materia Medica | §7.1 | Materia medica heads | Manage chapter headings | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | EDIT HERE — this module sheet
36 | 88 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.12 | ADM-M03 | Keep and harden Admin Materia medica heads (do not rebuild) | ADM-M03.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Materia medica heads; do not silently switch | Existing | Materia Medica | §7.1 | Materia medica heads | Manage chapter headings | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | EDIT HERE — this module sheet
37 | 89 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.13 | ADM-M04 | Keep and harden Admin Materia medica remedies (do not rebuild) | ADM-M04.01 | Regression: list / add / edit / (import-export if present) for Materia medica remedies | Existing | Materia Medica | §7.1 | Materia medica remedies | View remedy-wise materia medica | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
38 | 90 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.13 | ADM-M04 | Keep and harden Admin Materia medica remedies (do not rebuild) | ADM-M04.02 | ACL: only Admin (and permitted roles) can mutate Materia medica remedies; Doctor is read-only consumer on Patient Board | Existing Improvement | Materia Medica | §7.1 | Materia medica remedies | View remedy-wise materia medica | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | EDIT HERE — this module sheet
39 | 91 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.13 | ADM-M04 | Keep and harden Admin Materia medica remedies (do not rebuild) | ADM-M04.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Materia medica remedies; do not silently switch | Existing | Materia Medica | §7.1 | Materia medica remedies | View remedy-wise materia medica | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | EDIT HERE — this module sheet
40 | 92 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.14 | ADM-D01 | Keep and harden Admin Diagnosis system (do not rebuild) | ADM-D01.01 | Regression: list / add / edit / (import-export if present) for Diagnosis system | Existing | Diagnosis | §7.1 | Diagnosis system | Manage diagnosis systems | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
41 | 93 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.14 | ADM-D01 | Keep and harden Admin Diagnosis system (do not rebuild) | ADM-D01.02 | ACL: only Admin (and permitted roles) can mutate Diagnosis system; Doctor is read-only consumer on Patient Board | Existing Improvement | Diagnosis | §7.1 | Diagnosis system | Manage diagnosis systems | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | EDIT HERE — this module sheet
42 | 94 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.14 | ADM-D01 | Keep and harden Admin Diagnosis system (do not rebuild) | ADM-D01.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Diagnosis system; do not silently switch | Existing | Diagnosis | §7.1 | Diagnosis system | Manage diagnosis systems | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | EDIT HERE — this module sheet
43 | 95 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.15 | ADM-D02 | Keep and harden Admin Diagnosis therapeutics (do not rebuild) | ADM-D02.01 | Regression: list / add / edit / (import-export if present) for Diagnosis therapeutics | Existing | Diagnosis | §7.1 | Diagnosis therapeutics | Manage therapeutics | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
44 | 96 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.15 | ADM-D02 | Keep and harden Admin Diagnosis therapeutics (do not rebuild) | ADM-D02.02 | ACL: only Admin (and permitted roles) can mutate Diagnosis therapeutics; Doctor is read-only consumer on Patient Board | Existing Improvement | Diagnosis | §7.1 | Diagnosis therapeutics | Manage therapeutics | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | EDIT HERE — this module sheet
45 | 97 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.15 | ADM-D02 | Keep and harden Admin Diagnosis therapeutics (do not rebuild) | ADM-D02.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Diagnosis therapeutics; do not silently switch | Existing | Diagnosis | §7.1 | Diagnosis therapeutics | Manage therapeutics | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | EDIT HERE — this module sheet
46 | 98 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.16 | ADM-D03 | Keep and harden Admin Diagnosis conditions (do not rebuild) | ADM-D03.01 | Regression: list / add / edit / (import-export if present) for Diagnosis conditions | Existing | Diagnosis | §7.1 | Diagnosis conditions | Manage conditions and linked rubrics | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
47 | 99 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.16 | ADM-D03 | Keep and harden Admin Diagnosis conditions (do not rebuild) | ADM-D03.02 | ACL: only Admin (and permitted roles) can mutate Diagnosis conditions; Doctor is read-only consumer on Patient Board | Existing Improvement | Diagnosis | §7.1 | Diagnosis conditions | Manage conditions and linked rubrics | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | EDIT HERE — this module sheet
48 | 100 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.16 | ADM-D03 | Keep and harden Admin Diagnosis conditions (do not rebuild) | ADM-D03.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Diagnosis conditions; do not silently switch | Existing | Diagnosis | §7.1 | Diagnosis conditions | Manage conditions and linked rubrics | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | EDIT HERE — this module sheet
49 | 101 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.17 | ADM-A01 | Keep and harden Admin Drug system (do not rebuild) | ADM-A01.01 | Regression: list / add / edit / (import-export if present) for Drug system | Existing | Adverse Effect | §7.1 | Drug system | Manage conventional drug systems | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
50 | 102 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.17 | ADM-A01 | Keep and harden Admin Drug system (do not rebuild) | ADM-A01.02 | ACL: only Admin (and permitted roles) can mutate Drug system; Doctor is read-only consumer on Patient Board | Existing Improvement | Adverse Effect | §7.1 | Drug system | Manage conventional drug systems | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | EDIT HERE — this module sheet
51 | 103 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.17 | ADM-A01 | Keep and harden Admin Drug system (do not rebuild) | ADM-A01.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Drug system; do not silently switch | Existing | Adverse Effect | §7.1 | Drug system | Manage conventional drug systems | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | EDIT HERE — this module sheet
52 | 104 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.18 | ADM-A02 | Keep and harden Admin Drug group (do not rebuild) | ADM-A02.01 | Regression: list / add / edit / (import-export if present) for Drug group | Existing | Adverse Effect | §7.1 | Drug group | Manage drug groups | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
53 | 105 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.18 | ADM-A02 | Keep and harden Admin Drug group (do not rebuild) | ADM-A02.02 | ACL: only Admin (and permitted roles) can mutate Drug group; Doctor is read-only consumer on Patient Board | Existing Improvement | Adverse Effect | §7.1 | Drug group | Manage drug groups | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | EDIT HERE — this module sheet
54 | 106 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.18 | ADM-A02 | Keep and harden Admin Drug group (do not rebuild) | ADM-A02.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Drug group; do not silently switch | Existing | Adverse Effect | §7.1 | Drug group | Manage drug groups | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | EDIT HERE — this module sheet
55 | 107 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.19 | ADM-A03 | Keep and harden Admin Allopathic drug & side effects (do not rebuild) | ADM-A03.01 | Regression: list / add / edit / (import-export if present) for Allopathic drug & side effects | Existing | Adverse Effect | §7.1 | Allopathic drug & side effects | Manage drugs with side effects and adverse reactions | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
56 | 108 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.19 | ADM-A03 | Keep and harden Admin Allopathic drug & side effects (do not rebuild) | ADM-A03.02 | ACL: only Admin (and permitted roles) can mutate Allopathic drug & side effects; Doctor is read-only consumer on Patient Board | Existing Improvement | Adverse Effect | §7.1 | Allopathic drug & side effects | Manage drugs with side effects and adverse reactions | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | EDIT HERE — this module sheet
57 | 109 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.19 | ADM-A03 | Keep and harden Admin Allopathic drug & side effects (do not rebuild) | ADM-A03.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Allopathic drug & side effects; do not silently switch | Existing | Adverse Effect | §7.1 | Allopathic drug & side effects | Manage drugs with side effects and adverse reactions | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | EDIT HERE — this module sheet
58 | 110 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.20 | ADM-Q01 | Keep and harden Admin Question section, group & sub-group (do not rebuild) | ADM-Q01.01 | Regression: list / add / edit / (import-export if present) for Question section, group & sub-group | Existing | Clinical Questions | §7.1 | Question section, group & sub-group | Manage the clinical questionnaire structure | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
59 | 111 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.20 | ADM-Q01 | Keep and harden Admin Question section, group & sub-group (do not rebuild) | ADM-Q01.02 | ACL: only Admin (and permitted roles) can mutate Question section, group & sub-group; Doctor is read-only consumer on Patient Board | Existing Improvement | Clinical Questions | §7.1 | Question section, group & sub-group | Manage the clinical questionnaire structure | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | EDIT HERE — this module sheet
60 | 112 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.20 | ADM-Q01 | Keep and harden Admin Question section, group & sub-group (do not rebuild) | ADM-Q01.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Question section, group & sub-group; do not silently switch | Existing | Clinical Questions | §7.1 | Question section, group & sub-group | Manage the clinical questionnaire structure | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | EDIT HERE — this module sheet
61 | 113 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.21 | ADM-Q02 | Keep and harden Admin Clinical question mapping (do not rebuild) | ADM-Q02.01 | Regression: list / add / edit / (import-export if present) for Clinical question mapping | Existing | Clinical Questions | §7.1 | Clinical question mapping | Map questions to body parts and rubrics | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
62 | 114 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.21 | ADM-Q02 | Keep and harden Admin Clinical question mapping (do not rebuild) | ADM-Q02.02 | ACL: only Admin (and permitted roles) can mutate Clinical question mapping; Doctor is read-only consumer on Patient Board | Existing Improvement | Clinical Questions | §7.1 | Clinical question mapping | Map questions to body parts and rubrics | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | EDIT HERE — this module sheet
63 | 115 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.21 | ADM-Q02 | Keep and harden Admin Clinical question mapping (do not rebuild) | ADM-Q02.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Clinical question mapping; do not silently switch | Existing | Clinical Questions | §7.1 | Clinical question mapping | Map questions to body parts and rubrics | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | EDIT HERE — this module sheet
64 | 116 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.22 | ADM-3D1 | Keep and harden Admin 3D mesh key master (do not rebuild) | ADM-3D1.01 | Regression: list / add / edit / (import-export if present) for 3D mesh key master | Existing | 3D Body | §7.1 | 3D mesh key master | Manage 3D model references | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
65 | 117 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.22 | ADM-3D1 | Keep and harden Admin 3D mesh key master (do not rebuild) | ADM-3D1.02 | ACL: only Admin (and permitted roles) can mutate 3D mesh key master; Doctor is read-only consumer on Patient Board | Existing Improvement | 3D Body | §7.1 | 3D mesh key master | Manage 3D model references | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | EDIT HERE — this module sheet
66 | 118 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.22 | ADM-3D1 | Keep and harden Admin 3D mesh key master (do not rebuild) | ADM-3D1.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for 3D mesh key master; do not silently switch | Existing | 3D Body | §7.1 | 3D mesh key master | Manage 3D model references | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | EDIT HERE — this module sheet
67 | 119 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.23 | ADM-3D2 | Keep and harden Admin 3D section master (do not rebuild) | ADM-3D2.01 | Regression: list / add / edit / (import-export if present) for 3D section master | Existing | 3D Body | §7.1 | 3D section master | Manage 3D body sections | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
68 | 120 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.23 | ADM-3D2 | Keep and harden Admin 3D section master (do not rebuild) | ADM-3D2.02 | ACL: only Admin (and permitted roles) can mutate 3D section master; Doctor is read-only consumer on Patient Board | Existing Improvement | 3D Body | §7.1 | 3D section master | Manage 3D body sections | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | EDIT HERE — this module sheet
69 | 121 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.23 | ADM-3D2 | Keep and harden Admin 3D section master (do not rebuild) | ADM-3D2.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for 3D section master; do not silently switch | Existing | 3D Body | §7.1 | 3D section master | Manage 3D body sections | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | EDIT HERE — this module sheet
70 | 122 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.24 | ADM-3D3 | Keep and harden Admin 3D hotspots (do not rebuild) | ADM-3D3.01 | Regression: list / add / edit / (import-export if present) for 3D hotspots | Existing | 3D Body | §7.1 | 3D hotspots | Manage clickable points on the 3D model | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
71 | 123 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.24 | ADM-3D3 | Keep and harden Admin 3D hotspots (do not rebuild) | ADM-3D3.02 | ACL: only Admin (and permitted roles) can mutate 3D hotspots; Doctor is read-only consumer on Patient Board | Existing Improvement | 3D Body | §7.1 | 3D hotspots | Manage clickable points on the 3D model | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | EDIT HERE — this module sheet
72 | 124 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.24 | ADM-3D3 | Keep and harden Admin 3D hotspots (do not rebuild) | ADM-3D3.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for 3D hotspots; do not silently switch | Existing | 3D Body | §7.1 | 3D hotspots | Manage clickable points on the 3D model | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | EDIT HERE — this module sheet
73 | 125 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.25 | ADM-B01 | Business Management — Doctor qualifications (existing, used later by credentialing) | ADM-B01.01 | Regression: qualifications list/add/edit | Existing | Business Management | §7.2 | Doctor qualifications | Manage the qualification list | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
74 | 126 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.25 | ADM-B01 | Business Management — Doctor qualifications (existing, used later by credentialing) | ADM-B01.02 | ACL on qualification APIs | Existing Improvement | Business Management | §7.2 | Doctor qualifications | Manage the qualification list | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | EDIT HERE — this module sheet
75 | 127 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.25 | ADM-B01 | Business Management — Doctor qualifications (existing, used later by credentialing) | ADM-B01.03 | Confirm UI uses newer API (not classic) for qualifications | Existing | Business Management | §7.2 | Doctor qualifications | Manage the qualification list | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | EDIT HERE — this module sheet
76 | 128 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.26 | ADM-B02 | Business Management — Lab & imaging test catalog (existing, used by eRx lab orders) | ADM-B02.01 | Regression: lab catalog CRUD and doctor order pick-list | Existing | Business Management | §7.2 | Lab & imaging test catalog | Manage the test catalogue | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
77 | 129 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.26 | ADM-B02 | Business Management — Lab & imaging test catalog (existing, used by eRx lab orders) | ADM-B02.02 | ACL on catalog mutate | Existing Improvement | Business Management | §7.2 | Lab & imaging test catalog | Manage the test catalogue | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | EDIT HERE — this module sheet
78 | 130 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.26 | ADM-B02 | Business Management — Lab & imaging test catalog (existing, used by eRx lab orders) | ADM-B02.03 | Confirm classic PatientLab APIs still read this catalogue | Existing | Business Management | §7.2 | Lab & imaging test catalog | Manage the test catalogue | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | EDIT HERE — this module sheet
79 | 131 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.27 | ADM-B03 | Business Management — Subscription packages (existing S1 SaaS; later tied to Account ledger) | ADM-B03.01 | Regression: package list/add/edit; doctor Widgets still reads packages | Existing | Business Management | §7.2 | Subscription packages | Manage doctor subscription plans | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
80 | 132 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.27 | ADM-B03 | Business Management — Subscription packages (existing S1 SaaS; later tied to Account ledger) | ADM-B03.02 | ACL on package mutate | Existing Improvement | Business Management | §7.2 | Subscription packages | Manage doctor subscription plans | Admin Portal | Security | Gourav Nikam | Yes | Done | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | EDIT HERE — this module sheet
81 | 133 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.27 | ADM-B03 | Business Management — Subscription packages (existing S1 SaaS; later tied to Account ledger) | ADM-B03.03 | Note in code: PackageEntryDetail is S1 only — never reuse for S2 consult or S5 medicine | Existing | Business Management | §7.2 | Subscription packages | Manage doctor subscription plans | Admin Portal | API hygiene | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 0 | Done |  | EDIT HERE — this module sheet
82 | 134 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.28 | ADM-B04 | Business Management — Roles & menu permissions (existing DB, runtime ACL leftover) | ADM-B04.01 | No schema change unless Account/Pharmacy/Patient roles need new MenuMaster rows — seed those menus | Existing Improvement | Business Management | §7.2 | Roles & menu permissions | Control exactly what each role can access | Admin Portal | Database | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | Yes | In Progress | Gourav Nikam | No | N/A |  | No | N/A |  | No | N/A |  | 1 | In Progress |  | EDIT HERE — this module sheet
83 | 135 | M02 | Admin clinical masters | Web | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.28 | ADM-B04 | Business Management — Roles & menu permissions (existing DB, runtime ACL leftover) | ADM-B04.02 | Restore GetMenuByRole on .NET 8; seed menus for Account and (later) Pharmacy | Existing Improvement | Business Management | §7.2 | Roles & menu permissions | Control exactly what each role can access | Admin Portal | API | Gourav Nikam | No | N/A |  | Yes | Done | Gourav Nikam | Yes | In Progress | Gourav Nikam | Yes | Done | Gourav Nikam | No | N/A |  | No | N/A |  | 1 | In Progress |  | EDIT HERE — this module sheet
84 | 136 | M02 | Admin clinical masters | UI | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.28 | ADM-B04 | Business Management — Roles & menu permissions (existing DB, runtime ACL leftover) | ADM-B04.03 | Admin role pages remain; frontend consumes menu API instead of hard-coded LayoutMenuData for domain items | Existing Improvement | Business Management | §7.2 | Roles & menu permissions | Control exactly what each role can access | Admin Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
85 | 137 | M02 | Admin clinical masters | QA | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.28 | ADM-B04 | Business Management — Roles & menu permissions (existing DB, runtime ACL leftover) | ADM-B04.04 | QA: edit role menu → user of that role no longer sees the item | Regression | Business Management | §7.2 | Roles & menu permissions | Control exactly what each role can access | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet

## M03_Clinical_Workspace
M03 Doctor clinical workspace — 67 sub-tasks (Web 37 · UI 10 · QA 20). YELLOW = edit here (Assigned To, Frontend/Backend/Database/API/Mobile/Integration Status + Assigned). Scope Yes/No is fixed. Status N/A = that function is not in this sub-task. Master, Web/UI/Mobile/QA sheets and Dashboard follow these cells live. | [41 empty] | Live copy of 00_Employees column B — do not edit. New names appear here automatically.
Module Seq | Original Seq | Dev Module Code | Dev Module | Track | Phase | Phase Name | WBS | Main Task ID | Main Task | Sub Task ID | Sub Task | Work Type | Source Module / Area | PDF Section | PDF Feature (exact wording) | PDF Delivery Text | Application Surface | Layer | Assigned To (lead) | Frontend | Frontend Status | Frontend Assigned | Backend | Backend Status | Backend Assigned | Database | Database Status | Database Assigned | API | API Status | API Assigned | Mobile | Mobile Status | Mobile Assigned | Integration | Integration Status | Integration Assigned | Layers Remaining | Overall Status | Notes | Open Module Sheet | _EmpList
1 | 138 | M03 | Doctor clinical workspace | UI | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.1 | CLN-01 | Clinical workspace — single screen for the entire consultation | CLN-01.01 | UI: Patient Board header shows appointment, visit type, consult mode placeholders (wired in Phases 4 and 6) | Existing Improvement | Patient Board | §5.3 | Clinical workspace | Single screen for the entire consultation | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet | Unassigned
2 | 139 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.1 | CLN-01 | Clinical workspace — single screen for the entire consultation | CLN-01.02 | Do not split the board into multiple apps; mobile doctor app will NOT get case-taking (PDF §3) | Existing | Patient Board | §5.3 | Clinical workspace | Single screen for the entire consultation | Doctor Web Portal | Architecture | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 0 | N/A |  | EDIT HERE — this module sheet | Gourav Nikam
3 | 140 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.1 | CLN-01 | Clinical workspace — single screen for the entire consultation | CLN-01.03 | Regression: open case from dashboard still remounts via PatientBoardRoute | Regression | Patient Board | §5.3 | Clinical workspace | Single screen for the entire consultation | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet | Digvijay Jadhav
4 | 141 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.2 | CLN-02 | Manual case taking — structured case taking (keep) | CLN-02.01 | Regression: create case, add rubrics via manual path, repertorize | Existing | Patient Board | §5.3 | Manual case taking | Structured case taking | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
5 | 142 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.2 | CLN-02 | Manual case taking — structured case taking (keep) | CLN-02.02 | ACL: only treating doctor (not Reception) can run full case taking | Existing Improvement | Patient Board | §5.3 | Manual case taking | Structured case taking | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
6 | 143 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.2 | CLN-02 | Manual case taking — structured case taking (keep) | CLN-02.03 | Confirm clipboard/repertorization APIs still on the correct host | Existing | Patient Board | §5.3 | Manual case taking | Structured case taking | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
7 | 144 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.3 | CLN-03 | Body parts & intensity selection (keep) | CLN-03.01 | Regression: body part → rubrics; intensity chip | Existing | Patient Board | §5.3 | Body parts & intensity selection | Select affected areas and severity | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
8 | 145 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.3 | CLN-03 | Body parts & intensity selection (keep) | CLN-03.02 | ACL: doctor-only | Existing Improvement | Patient Board | §5.3 | Body parts & intensity selection | Select affected areas and severity | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
9 | 146 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.3 | CLN-03 | Body parts & intensity selection (keep) | CLN-03.03 | API host unchanged | Existing | Patient Board | §5.3 | Body parts & intensity selection | Select affected areas and severity | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Pranav Bandekar
10 | 147 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.4 | CLN-04 | Clinical questions — guided questions by section, group and sub-group (keep) | CLN-04.01 | Regression: full question drill-down | Existing | Patient Board | §5.3 | Clinical questions | Guided questions by section, group and sub-group | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
11 | 148 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.4 | CLN-04 | Clinical questions — guided questions by section, group and sub-group (keep) | CLN-04.02 | ACL doctor-only | Existing Improvement | Patient Board | §5.3 | Clinical questions | Guided questions by section, group and sub-group | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
12 | 149 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.4 | CLN-04 | Clinical questions — guided questions by section, group and sub-group (keep) | CLN-04.03 | API host unchanged | Existing | Patient Board | §5.3 | Clinical questions | Guided questions by section, group and sub-group | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
13 | 150 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.5 | CLN-05 | Diagnosis, therapeutics & pattern search (keep) | CLN-05.01 | Regression: diagnosis search + therapeutics | Existing | Patient Board | §5.3 | Diagnosis, therapeutics & pattern search | Search diagnoses and linked therapeutics | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
14 | 151 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.5 | CLN-05 | Diagnosis, therapeutics & pattern search (keep) | CLN-05.02 | ACL doctor-only | Existing Improvement | Patient Board | §5.3 | Diagnosis, therapeutics & pattern search | Search diagnoses and linked therapeutics | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
15 | 152 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.5 | CLN-05 | Diagnosis, therapeutics & pattern search (keep) | CLN-05.03 | API host unchanged | Existing | Patient Board | §5.3 | Diagnosis, therapeutics & pattern search | Search diagnoses and linked therapeutics | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
16 | 153 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.6 | CLN-06 | Repertory rubric search & selection (keep) | CLN-06.01 | Regression: tree + search + add to clipboard | Existing | Patient Board | §5.3 | Repertory rubric search & selection | Search and select from the full repertory | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
17 | 154 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.6 | CLN-06 | Repertory rubric search & selection (keep) | CLN-06.02 | ACL doctor-only | Existing Improvement | Patient Board | §5.3 | Repertory rubric search & selection | Search and select from the full repertory | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
18 | 155 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.6 | CLN-06 | Repertory rubric search & selection (keep) | CLN-06.03 | Confirm subsection search host (newer vs classic) documented | Existing | Patient Board | §5.3 | Repertory rubric search & selection | Search and select from the full repertory | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
19 | 156 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.7 | CLN-07 | Manage selected rubrics — review, edit and remove (remaining ~10%) | CLN-07.01 | No new table — clipboard already persisted via board backup / repertorization payload | Existing Improvement | Patient Board | §5.3 | Manage selected rubrics | Review, edit and remove selected rubrics | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
20 | 157 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.7 | CLN-07 | Manage selected rubrics — review, edit and remove (remaining ~10%) | CLN-07.02 | If intensity-on-clipboard is client-only, persist it on backup payload | Existing Improvement | Patient Board | §5.3 | Manage selected rubrics | Review, edit and remove selected rubrics | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
21 | 158 | M03 | Doctor clinical workspace | UI | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.7 | CLN-07 | Manage selected rubrics — review, edit and remove (remaining ~10%) | CLN-07.03 | Clipboard UX: confirm delete; intensity edit; count badge | Existing Improvement | Patient Board | §5.3 | Manage selected rubrics | Review, edit and remove selected rubrics | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
22 | 159 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.7 | CLN-07 | Manage selected rubrics — review, edit and remove (remaining ~10%) | CLN-07.04 | QA: remove, undo-not-required, backup restore still has remaining rubrics | Regression | Patient Board | §5.3 | Manage selected rubrics | Review, edit and remove selected rubrics | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
23 | 160 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.8 | CLN-08 | Audio case taking — record and receive suggested rubrics (keep engine; do not rebuild) | CLN-08.01 | Regression: record, poll, approve/reject suggested rubrics | Existing | Audio AI | §5.3 | Audio case taking | Record the consultation and receive suggested rubrics automatically | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
24 | 161 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.8 | CLN-08 | Audio case taking — record and receive suggested rubrics (keep engine; do not rebuild) | CLN-08.02 | Consent: audio consent continues to write AudioCaseConsentLog (later also ConsentRecord) | Existing Improvement | Audio AI | §5.3 | Audio case taking | Record the consultation and receive suggested rubrics automatically | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
25 | 162 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.8 | CLN-08 | Audio case taking — record and receive suggested rubrics (keep engine; do not rebuild) | CLN-08.03 | Confirm audio queue/worker still healthy | Existing | Audio AI | §5.3 | Audio case taking | Record the consultation and receive suggested rubrics automatically | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
26 | 163 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.9 | CLN-09 | Improved rubric accuracy — enhanced accuracy rules for audio-based rubric suggestions | CLN-09.01 | Follow AUDIO_CASE_TAKING_* docs: accuracy rules, aliases, metaphors, benchmark | Existing Improvement | Audio AI | §5.3 | Improved rubric accuracy | Enhanced accuracy rules for audio-based rubric suggestions | Doctor Web Portal + Admin intelligence | Backend | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
27 | 164 | M03 | Doctor clinical workspace | UI | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.9 | CLN-09 | Improved rubric accuracy — enhanced accuracy rules for audio-based rubric suggestions | CLN-09.02 | Admin: metaphor/alias approve-reject remaining UX | Existing Improvement | Audio AI | §5.3 | Improved rubric accuracy | Enhanced accuracy rules for audio-based rubric suggestions | Doctor Web Portal + Admin intelligence | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
28 | 165 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.9 | CLN-09 | Improved rubric accuracy — enhanced accuracy rules for audio-based rubric suggestions | CLN-09.03 | QA: golden transcripts → expected rubric IDs within tolerance | Regression | Audio AI | §5.3 | Improved rubric accuracy | Enhanced accuracy rules for audio-based rubric suggestions | Doctor Web Portal + Admin intelligence | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
29 | 166 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.10 | CLN-10 | Materia medica reference during consultation (remaining ~10%) | CLN-10.01 | No schema change | Existing Improvement | Patient Board | §5.3 | Materia medica reference | Browse materia medica during the consultation | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
30 | 167 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.10 | CLN-10 | Materia medica reference during consultation (remaining ~10%) | CLN-10.02 | Existing MM APIs — add a lightweight get-by-remedy if chatty | Existing Improvement | Patient Board | §5.3 | Materia medica reference | Browse materia medica during the consultation | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
31 | 168 | M03 | Doctor clinical workspace | UI | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.10 | CLN-10 | Materia medica reference during consultation (remaining ~10%) | CLN-10.03 | MM tab: faster head navigation / keep place in case | Existing Improvement | Patient Board | §5.3 | Materia medica reference | Browse materia medica during the consultation | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
32 | 169 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.10 | CLN-10 | Materia medica reference during consultation (remaining ~10%) | CLN-10.04 | QA: open MM for a repertorized remedy | Regression | Patient Board | §5.3 | Materia medica reference | Browse materia medica during the consultation | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
33 | 170 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.11 | CLN-11 | Allopathic drug side-effect lookup (keep) | CLN-11.01 | Regression: search drug → side effects | Existing | Patient Board | §5.3 | Allopathic drug side-effect lookup | Check side effects of conventional medicines | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
34 | 171 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.11 | CLN-11 | Allopathic drug side-effect lookup (keep) | CLN-11.02 | ACL doctor-only | Existing Improvement | Patient Board | §5.3 | Allopathic drug side-effect lookup | Check side effects of conventional medicines | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
35 | 172 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.11 | CLN-11 | Allopathic drug side-effect lookup (keep) | CLN-11.03 | API host unchanged | Existing | Patient Board | §5.3 | Allopathic drug side-effect lookup | Check side effects of conventional medicines | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
36 | 173 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.12 | CLN-12 | Repertorization & elimination (remaining ~10%) | CLN-12.01 | No schema change | Existing Improvement | Patient Board | §5.3 | Repertorization & elimination | Full repertorization with elimination | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
37 | 174 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.12 | CLN-12 | Repertorization & elimination (remaining ~10%) | CLN-12.02 | Keep existing repertorization APIs; fix any known scoring edge cases | Existing Improvement | Patient Board | §5.3 | Repertorization & elimination | Full repertorization with elimination | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
38 | 175 | M03 | Doctor clinical workspace | UI | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.12 | CLN-12 | Repertorization & elimination (remaining ~10%) | CLN-12.03 | Repertorize tab stability; then COG sits beside it | Existing Improvement | Patient Board | §5.3 | Repertorization & elimination | Full repertorization with elimination | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
39 | 176 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.12 | CLN-12 | Repertorization & elimination (remaining ~10%) | CLN-12.04 | QA: known case → expected top remedies | Regression | Patient Board | §5.3 | Repertorization & elimination | Full repertorization with elimination | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
40 | 177 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.13 | CLN-13 | Center of Gravity — new analysis identifying the central remedy of the case, with reasoning shown | CLN-13.01 | No mandatory new table (algorithm on selected rubrics); optional CogRun log for support | New | Repertorization | §5.3 | Center of Gravity | New analysis identifying the central remedy of the case, with reasoning shown | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
41 | 178 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.13 | CLN-13 | Center of Gravity — new analysis identifying the central remedy of the case, with reasoning shown | CLN-13.02 | POST /api/Repertorization/CenterOfGravity — input rubric ids + intensities; output ranked remedies + reasons | New | Repertorization | §5.3 | Center of Gravity | New analysis identifying the central remedy of the case, with reasoning shown | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
42 | 179 | M03 | Doctor clinical workspace | UI | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.13 | CLN-13 | Center of Gravity — new analysis identifying the central remedy of the case, with reasoning shown | CLN-13.03 | Patient Board → Repertorize tab → Center of Gravity sub-panel (toggle vs classic elimination) | New | Repertorization | §5.3 | Center of Gravity | New analysis identifying the central remedy of the case, with reasoning shown | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
43 | 180 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.13 | CLN-13 | Center of Gravity — new analysis identifying the central remedy of the case, with reasoning shown | CLN-13.04 | QA: same clipboard as classic repertorize; COG reasons cite contributing rubrics; empty clipboard → clear empty state | Regression | Repertorization | §5.3 | Center of Gravity | New analysis identifying the central remedy of the case, with reasoning shown | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
44 | 181 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.14 | CLN-14 | Lab orders & lab entries (keep; later also sit on eRx) | CLN-14.01 | Regression: order lab from catalogue; enter result | Existing | Patient Board | §5.3 + §11 | Lab orders & lab entries | Order tests and record results / Tests ordered alongside the prescription | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
45 | 182 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.14 | CLN-14 | Lab orders & lab entries (keep; later also sit on eRx) | CLN-14.02 | ACL doctor-only | Existing Improvement | Patient Board | §5.3 + §11 | Lab orders & lab entries | Order tests and record results / Tests ordered alongside the prescription | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
46 | 183 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.14 | CLN-14 | Lab orders & lab entries (keep; later also sit on eRx) | CLN-14.03 | API: classic PatientLab still authoritative until ported | Existing | Patient Board | §5.3 + §11 | Lab orders & lab entries | Order tests and record results / Tests ordered alongside the prescription | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
47 | 184 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.15 | CLN-15 | Appointment history notes (keep; split from eRx in Phase 10) | CLN-15.01 | Regression: add/list notes on a visit | Existing | Patient Board | §5.3 | Appointment history notes | Notes recorded against each visit | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
48 | 185 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.15 | CLN-15 | Appointment history notes (keep; split from eRx in Phase 10) | CLN-15.02 | ACL doctor-only | Existing Improvement | Patient Board | §5.3 | Appointment history notes | Notes recorded against each visit | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
49 | 186 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.15 | CLN-15 | Appointment history notes (keep; split from eRx in Phase 10) | CLN-15.03 | Do not dual-write; classic notes stay until Phase 10 extends them | Existing | Patient Board | §5.3 | Appointment history notes | Notes recorded against each visit | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
50 | 187 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.16 | CLN-16 | Complaints & case details — wire Patient Board to existing SaveComplaints / SaveCaseDetails (~20% today) | CLN-16.01 | Use existing tables — no new schema unless fields are missing vs PDF | Existing Improvement | Patient Board | §5.3 | Complaints & case details | Capture and store complaints and case details | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
51 | 188 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.16 | CLN-16 | Complaints & case details — wire Patient Board to existing SaveComplaints / SaveCaseDetails (~20% today) | CLN-16.02 | Keep classic SaveComplaints / SaveCaseDetails; add GET if missing | Existing Improvement | Patient Board | §5.3 | Complaints & case details | Capture and store complaints and case details | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
52 | 189 | M03 | Doctor clinical workspace | UI | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.16 | CLN-16 | Complaints & case details — wire Patient Board to existing SaveComplaints / SaveCaseDetails (~20% today) | CLN-16.03 | Patient Board: complaints + case details form that actually POSTs | Existing Improvement | Patient Board | §5.3 | Complaints & case details | Capture and store complaints and case details | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
53 | 190 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.16 | CLN-16 | Complaints & case details — wire Patient Board to existing SaveComplaints / SaveCaseDetails (~20% today) | CLN-16.04 | QA: save, reload, second doctor cannot read | Regression | Patient Board | §5.3 | Complaints & case details | Capture and store complaints and case details | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
54 | 191 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.17 | CLN-17 | Patient back history — complete history of visits, notes, prescriptions and payments | CLN-17.01 | No new table — compose from Appointment + notes + Rx + (later) ConsultPayment | Existing Improvement | Patient Board | §5.3 | Patient back history | Complete history of visits, notes, prescriptions and payments | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
55 | 192 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.17 | CLN-17 | Patient back history — complete history of visits, notes, prescriptions and payments | CLN-17.02 | GET patient timeline DTO including payment status when column exists | Existing Improvement | Patient Board | §5.3 | Patient back history | Complete history of visits, notes, prescriptions and payments | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
56 | 193 | M03 | Doctor clinical workspace | UI | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.17 | CLN-17 | Patient back history — complete history of visits, notes, prescriptions and payments | CLN-17.03 | History panel: date-ordered visits; open past eRx; payment badge placeholder | Existing Improvement | Patient Board | §5.3 | Patient back history | Complete history of visits, notes, prescriptions and payments | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
57 | 194 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.17 | CLN-17 | Patient back history — complete history of visits, notes, prescriptions and payments | CLN-17.04 | QA: multi-visit patient; empty new patient | Regression | Patient Board | §5.3 | Patient back history | Complete history of visits, notes, prescriptions and payments | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
58 | 195 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.18 | CLN-18 | Export case data — download the full case in Excel or PDF | CLN-18.01 | Reuse ExportCasesToExcel; add PDF generation of the clinical case (doctor copy, includes notes) | Existing Improvement | Patient Board | §5.3 | Export case data | Download the full case in Excel or PDF | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
59 | 196 | M03 | Doctor clinical workspace | UI | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.18 | CLN-18 | Export case data — download the full case in Excel or PDF | CLN-18.02 | Patient Board toolbar: Export Excel / Export PDF | New | Patient Board | §5.3 | Export case data | Download the full case in Excel or PDF | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
60 | 197 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.18 | CLN-18 | Export case data — download the full case in Excel or PDF | CLN-18.03 | QA: export matches on-screen rubrics + Rx; unauthorised doctor 403 | Regression | Patient Board | §5.3 | Export case data | Download the full case in Excel or PDF | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
61 | 198 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.19 | CLN-19 | Session restore — continue exactly where the doctor left off, across multiple patients (keep) | CLN-19.01 | Regression: backup, restore, 5-session stack | Existing | Patient Board | §5.3 | Session restore | Continue exactly where the doctor left off, across multiple patients | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
62 | 199 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.19 | CLN-19 | Session restore — continue exactly where the doctor left off, across multiple patients (keep) | CLN-19.02 | ACL: backup scoped to DoctorId | Existing Improvement | Patient Board | §5.3 | Session restore | Continue exactly where the doctor left off, across multiple patients | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
63 | 200 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.19 | CLN-19 | Session restore — continue exactly where the doctor left off, across multiple patients (keep) | CLN-19.03 | API: PatientBoardBackup on .NET 8 unchanged | Existing | Patient Board | §5.3 | Session restore | Continue exactly where the doctor left off, across multiple patients | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
64 | 201 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.20 | CLN-20 | 3D anatomy viewer — interactive 3D body model linked to rubric search (remaining ~50%) | CLN-20.01 | No new tables — Mesh/Section/Hotspot masters already exist | Existing Improvement | Anatomy | §5.3 | 3D anatomy viewer | Interactive 3D body model linked to rubric search | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
65 | 202 | M03 | Doctor clinical workspace | Web | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.20 | CLN-20 | 3D anatomy viewer — interactive 3D body model linked to rubric search (remaining ~50%) | CLN-20.02 | Fix hotspot mapping gaps on newer threeDBodyPart APIs | Existing Improvement | Anatomy | §5.3 | 3D anatomy viewer | Interactive 3D body model linked to rubric search | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
66 | 203 | M03 | Doctor clinical workspace | UI | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.20 | CLN-20 | 3D anatomy viewer — interactive 3D body model linked to rubric search (remaining ~50%) | CLN-20.03 | Viewer UX: incomplete regions, loading, fallback message | Existing Improvement | Anatomy | §5.3 | 3D anatomy viewer | Interactive 3D body model linked to rubric search | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
67 | 204 | M03 | Doctor clinical workspace | QA | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.20 | CLN-20 | 3D anatomy viewer — interactive 3D body model linked to rubric search (remaining ~50%) | CLN-20.04 | QA: click hotspot → subsection search results | Regression | Anatomy | §5.3 | 3D anatomy viewer | Interactive 3D body model linked to rubric search | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet

## M04_Doctor_Daily_Ops
M04 Doctor daily operations — 33 sub-tasks (Web 18 · UI 5 · QA 10). YELLOW = edit here (Assigned To, Frontend/Backend/Database/API/Mobile/Integration Status + Assigned). Scope Yes/No is fixed. Status N/A = that function is not in this sub-task. Master, Web/UI/Mobile/QA sheets and Dashboard follow these cells live. | [41 empty] | Live copy of 00_Employees column B — do not edit. New names appear here automatically.
Module Seq | Original Seq | Dev Module Code | Dev Module | Track | Phase | Phase Name | WBS | Main Task ID | Main Task | Sub Task ID | Sub Task | Work Type | Source Module / Area | PDF Section | PDF Feature (exact wording) | PDF Delivery Text | Application Surface | Layer | Assigned To (lead) | Frontend | Frontend Status | Frontend Assigned | Backend | Backend Status | Backend Assigned | Database | Database Status | Database Assigned | API | API Status | API Assigned | Mobile | Mobile Status | Mobile Assigned | Integration | Integration Status | Integration Assigned | Layers Remaining | Overall Status | Notes | Open Module Sheet | _EmpList
1 | 205 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.1 | DOC-01 | Doctor home dashboard — complete overview of the working day (remaining ~30%) | DOC-01.01 | No new dashboard table | Existing Improvement | Doctor Dashboard | §5.1 | Doctor home dashboard | Complete overview of the working day | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Unassigned
2 | 206 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.1 | DOC-01 | Doctor home dashboard — complete overview of the working day (remaining ~30%) | DOC-01.02 | Extend dashboard DTOs with paymentStatus / tele flags when columns exist (nullable until Phase 6/11) | Existing Improvement | Doctor Dashboard | §5.1 | Doctor home dashboard | Complete overview of the working day | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
3 | 207 | M04 | Doctor daily operations | UI | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.1 | DOC-01 | Doctor home dashboard — complete overview of the working day (remaining ~30%) | DOC-01.03 | Dashboard chrome: keep counts; add slots for Online toggle, tele queue, unpaid badge | Existing Improvement | Doctor Dashboard | §5.1 | Doctor home dashboard | Complete overview of the working day | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Digvijay Jadhav
4 | 208 | M04 | Doctor daily operations | QA | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.1 | DOC-01 | Doctor home dashboard — complete overview of the working day (remaining ~30%) | DOC-01.04 | QA: existing buckets still populate; reception still shares layout until Phase 5 reception chrome | Regression | Doctor Dashboard | §5.1 | Doctor home dashboard | Complete overview of the working day | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
5 | 209 | M04 | Doctor daily operations | QA | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.2 | DOC-02 | Patient counts & waiting list — live counts by status with quick actions (keep; extend paid/unpaid) | DOC-02.01 | Regression: each bucket count and click-through | Existing | Doctor Dashboard | §5.1 | Patient counts & waiting list | Live counts by status with quick actions | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
6 | 210 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.2 | DOC-02 | Patient counts & waiting list — live counts by status with quick actions (keep; extend paid/unpaid) | DOC-02.02 | Reception sharing this view is OK until Phase 5 splits chrome | Existing Improvement | Doctor Dashboard | §5.1 | Patient counts & waiting list | Live counts by status with quick actions | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
7 | 211 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.2 | DOC-02 | Patient counts & waiting list — live counts by status with quick actions (keep; extend paid/unpaid) | DOC-02.03 | API: existing dashboard count endpoints | Existing | Doctor Dashboard | §5.1 | Patient counts & waiting list | Live counts by status with quick actions | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
8 | 212 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.3 | DOC-03 | Patient search, list & open case (remaining ~10%) | DOC-03.01 | Use existing Patient + Appointment — add DTO fields | Existing Improvement | Doctor Dashboard | §5.1 | Patient search, list & open case | Find any patient and open their case instantly | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
9 | 213 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.3 | DOC-03 | Patient search, list & open case (remaining ~10%) | DOC-03.02 | Search DTO includes lastVisitAt | Existing Improvement | Doctor Dashboard | §5.1 | Patient search, list & open case | Find any patient and open their case instantly | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Pranav Bandekar
10 | 214 | M04 | Doctor daily operations | UI | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.3 | DOC-03 | Patient search, list & open case (remaining ~10%) | DOC-03.03 | List columns: last visit; later payment/family | Existing Improvement | Doctor Dashboard | §5.1 | Patient search, list & open case | Find any patient and open their case instantly | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
11 | 215 | M04 | Doctor daily operations | QA | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.3 | DOC-03 | Patient search, list & open case (remaining ~10%) | DOC-03.04 | QA: search by name/mobile; open case | Regression | Doctor Dashboard | §5.1 | Patient search, list & open case | Find any patient and open their case instantly | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
12 | 216 | M04 | Doctor daily operations | QA | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.4 | DOC-04 | Add new patient — register a patient in seconds (keep) | DOC-04.01 | Regression: add patient validation and save | Existing | Patients | §5.1 | Add new patient | Register a patient in seconds | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
13 | 217 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.4 | DOC-04 | Add new patient — register a patient in seconds (keep) | DOC-04.02 | ACL: doctor/reception of that clinic only | Existing Improvement | Patients | §5.1 | Add new patient | Register a patient in seconds | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
14 | 218 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.4 | DOC-04 | Add new patient — register a patient in seconds (keep) | DOC-04.03 | API unchanged | Existing | Patients | §5.1 | Add new patient | Register a patient in seconds | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
15 | 219 | M04 | Doctor daily operations | QA | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.5 | DOC-05 | Import patients — bring existing patient records in bulk (keep) | DOC-05.01 | Regression: template + import + error rows | Existing | Patients | §5.1 | Import patients | Bring existing patient records in bulk | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
16 | 220 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.5 | DOC-05 | Import patients — bring existing patient records in bulk (keep) | DOC-05.02 | ACL doctor-only (or reception if already allowed) | Existing Improvement | Patients | §5.1 | Import patients | Bring existing patient records in bulk | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
17 | 221 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.5 | DOC-05 | Import patients — bring existing patient records in bulk (keep) | DOC-05.03 | API unchanged | Existing | Patients | §5.1 | Import patients | Bring existing patient records in bulk | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
18 | 222 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.6 | DOC-06 | Export patients — download patient data in Excel, CSV or PDF (keep) | DOC-06.01 | Audit current export formats; add PDF if only Excel/CSV exist today | Existing Improvement | Patients | §5.1 | Export patients | Download patient data in Excel, CSV or PDF | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
19 | 223 | M04 | Doctor daily operations | UI | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.6 | DOC-06 | Export patients — download patient data in Excel, CSV or PDF (keep) | DOC-06.02 | UI: Excel / CSV / PDF actions labelled as in the delivery document | Existing Improvement | Patients | §5.1 | Export patients | Download patient data in Excel, CSV or PDF | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
20 | 224 | M04 | Doctor daily operations | QA | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.6 | DOC-06 | Export patients — download patient data in Excel, CSV or PDF (keep) | DOC-06.03 | QA: another doctor cannot export this list | Regression | Patients | §5.1 | Export patients | Download patient data in Excel, CSV or PDF | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
21 | 225 | M04 | Doctor daily operations | QA | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.7 | DOC-07 | Recent activity panel (keep) | DOC-07.01 | Regression: activity loads | Existing | Doctor Dashboard | §5.1 | Recent activity panel | Everything that happened recently, at a glance | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
22 | 226 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.7 | DOC-07 | Recent activity panel (keep) | DOC-07.02 | ACL scoped to doctor | Existing Improvement | Doctor Dashboard | §5.1 | Recent activity panel | Everything that happened recently, at a glance | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
23 | 227 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.7 | DOC-07 | Recent activity panel (keep) | DOC-07.03 | API unchanged | Existing | Doctor Dashboard | §5.1 | Recent activity panel | Everything that happened recently, at a glance | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
24 | 228 | M04 | Doctor daily operations | QA | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.8 | DOC-08 | Patient statistics charts (keep; foundation for clinic performance in Phase 18) | DOC-08.01 | Regression: stats charts date range | Existing | Doctor Dashboard | §5.1 | Patient statistics charts | Visual practice statistics | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
25 | 229 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.8 | DOC-08 | Patient statistics charts (keep; foundation for clinic performance in Phase 18) | DOC-08.02 | ACL doctor-only | Existing Improvement | Doctor Dashboard | §5.1 | Patient statistics charts | Visual practice statistics | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
26 | 230 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.8 | DOC-08 | Patient statistics charts (keep; foundation for clinic performance in Phase 18) | DOC-08.03 | API unchanged | Existing | Doctor Dashboard | §5.1 | Patient statistics charts | Visual practice statistics | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
27 | 231 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.9 | DOC-09 | Manage reception staff — add, edit and remove reception users (backend done, UI absent) | DOC-09.01 | No new API — authorise that the doctor owns the staff record on existing CRUD | Existing Improvement | Staff | §5.1 | Manage reception staff | Add, edit and remove reception users | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
28 | 232 | M04 | Doctor daily operations | UI | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.9 | DOC-09 | Manage reception staff — add, edit and remove reception users (backend done, UI absent) | DOC-09.02 | Build /doctor/reception-staff list, add, edit, disable pages; menu entry in doctor chrome | Existing Improvement | Staff | §5.1 | Manage reception staff | Add, edit and remove reception users | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
29 | 233 | M04 | Doctor daily operations | QA | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.9 | DOC-09 | Manage reception staff — add, edit and remove reception users (backend done, UI absent) | DOC-09.03 | QA: reception user cannot manage other doctors’ staff; disable prevents login | Regression | Staff | §5.1 | Manage reception staff | Add, edit and remove reception users | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
30 | 234 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.10 | DOC-10 | Doctor profile — clinic details, consultation fee, photo, qualifications, working hours, bank details | DOC-10.01 | Extend Doctor / add DoctorPayeeKyc fields (bank, PAN) used later by Account; ConsultFeeConfig may wait until Phase 6 — store fee on profile now if simpler | Existing Improvement | Doctor Profile | §5.1 | Doctor profile | Clinic details, consultation fee, photo, qualifications, working hours, bank details | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
31 | 235 | M04 | Doctor daily operations | Web | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.10 | DOC-10 | Doctor profile — clinic details, consultation fee, photo, qualifications, working hours, bank details | DOC-10.02 | GET/PUT /api/Profile/Me (doctor DTO); POST photo multipart; do not allow role escalation | Existing Improvement | Doctor Profile | §5.1 | Doctor profile | Clinic details, consultation fee, photo, qualifications, working hours, bank details | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
32 | 236 | M04 | Doctor daily operations | UI | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.10 | DOC-10 | Doctor profile — clinic details, consultation fee, photo, qualifications, working hours, bank details | DOC-10.03 | Replace Velzon /profile for doctor role with clinic/fee/photo/qualifications/hours/bank tabs | Existing Improvement | Doctor Profile | §5.1 | Doctor profile | Clinic details, consultation fee, photo, qualifications, working hours, bank details | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
33 | 237 | M04 | Doctor daily operations | QA | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.10 | DOC-10 | Doctor profile — clinic details, consultation fee, photo, qualifications, working hours, bank details | DOC-10.04 | QA: reception cannot edit doctor bank details; photo displays on public profile later | Regression | Doctor Profile | §5.1 | Doctor profile | Clinic details, consultation fee, photo, qualifications, working hours, bank details | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet

## M05_Appointments
M05 Appointments & scheduling — 40 sub-tasks (Web 23 · UI 6 · QA 11). YELLOW = edit here (Assigned To, Frontend/Backend/Database/API/Mobile/Integration Status + Assigned). Scope Yes/No is fixed. Status N/A = that function is not in this sub-task. Master, Web/UI/Mobile/QA sheets and Dashboard follow these cells live. | [41 empty] | Live copy of 00_Employees column B — do not edit. New names appear here automatically.
Module Seq | Original Seq | Dev Module Code | Dev Module | Track | Phase | Phase Name | WBS | Main Task ID | Main Task | Sub Task ID | Sub Task | Work Type | Source Module / Area | PDF Section | PDF Feature (exact wording) | PDF Delivery Text | Application Surface | Layer | Assigned To (lead) | Frontend | Frontend Status | Frontend Assigned | Backend | Backend Status | Backend Assigned | Database | Database Status | Database Assigned | API | API Status | API Assigned | Mobile | Mobile Status | Mobile Assigned | Integration | Integration Status | Integration Assigned | Layers Remaining | Overall Status | Notes | Open Module Sheet | _EmpList
1 | 238 | M05 | Appointments & scheduling | QA | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.1 | APT-01 | Appointment list & waiting patients — full day view with live status (keep; later payment/tele) | APT-01.01 | Regression: day list, status colour, open patient | Existing | Appointments | §5.2 | Appointment list & waiting patients | Full day view with live status | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Unassigned
2 | 239 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.1 | APT-01 | Appointment list & waiting patients — full day view with live status (keep; later payment/tele) | APT-01.02 | ACL doctor/reception of that DoctorId | Existing Improvement | Appointments | §5.2 | Appointment list & waiting patients | Full day view with live status | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
3 | 240 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.1 | APT-01 | Appointment list & waiting patients — full day view with live status (keep; later payment/tele) | APT-01.03 | API unchanged | Existing | Appointments | §5.2 | Appointment list & waiting patients | Full day view with live status | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Digvijay Jadhav
4 | 241 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.2 | APT-02 | Create new appointment — persist visit type, consultation mode and fee | APT-02.01 | DB: PatientAppointment.VisitType, ConsultMode; migrate existing rows VisitType=First (do not infer retrospectively) | Existing Improvement | Appointments | §5.2 | Create new appointment | Book with visit type, consultation mode and fee | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
5 | 242 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.2 | APT-02 | Create new appointment — persist visit type, consultation mode and fee | APT-02.02 | API: create/update appointment accepts the new fields; PATCH VisitType | Existing Improvement | Appointments | §5.2 | Create new appointment | Book with visit type, consultation mode and fee | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
6 | 243 | M05 | Appointments & scheduling | UI | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.2 | APT-02 | Create new appointment — persist visit type, consultation mode and fee | APT-02.03 | Doctor/Reception new-appointment modal: visit type, consult mode, fee (placeholder until Phase 6 config) | Existing Improvement | Appointments | §5.2 | Create new appointment | Book with visit type, consultation mode and fee | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
7 | 244 | M05 | Appointments & scheduling | QA | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.2 | APT-02 | Create new appointment — persist visit type, consultation mode and fee | APT-02.04 | QA: staff-created appointments carry the same fields public booking will use in Phase 9 | Regression | Appointments | §5.2 | Create new appointment | Book with visit type, consultation mode and fee | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
8 | 245 | M05 | Appointments & scheduling | QA | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.3 | APT-03 | Appointment status update — move patients through the visit stages (keep) | APT-03.01 | Regression: each status transition | Existing | Appointments | §5.2 | Appointment status update | Move patients through the visit stages | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
9 | 246 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.3 | APT-03 | Appointment status update — move patients through the visit stages (keep) | APT-03.02 | ACL doctor/reception | Existing Improvement | Appointments | §5.2 | Appointment status update | Move patients through the visit stages | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Pranav Bandekar
10 | 247 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.3 | APT-03 | Appointment status update — move patients through the visit stages (keep) | APT-03.03 | API unchanged | Existing | Appointments | §5.2 | Appointment status update | Move patients through the visit stages | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
11 | 248 | M05 | Appointments & scheduling | QA | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.4 | APT-04 | Appointment time update — adjust timings as the day runs (keep; distinct from formal reschedule) | APT-04.01 | Regression: UpdateAppointmentTime on dashboard | Existing | Appointments | §5.2 | Appointment time update | Adjust timings as the day runs | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
12 | 249 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.4 | APT-04 | Appointment time update — adjust timings as the day runs (keep; distinct from formal reschedule) | APT-04.02 | Document in UI that Reschedule is the patient-notified path | Existing Improvement | Appointments | §5.2 | Appointment time update | Adjust timings as the day runs | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
13 | 250 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.4 | APT-04 | Appointment time update — adjust timings as the day runs (keep; distinct from formal reschedule) | APT-04.03 | API: keep UpdateAppointmentTime; Reschedule wraps it | Existing | Appointments | §5.2 | Appointment time update | Adjust timings as the day runs | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
14 | 251 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.5 | APT-05 | Reschedule appointment — move to a new slot with automatic patient notification (NEW — not a rename of UpdateAppointmentTime) | APT-05.01 | DB: AppointmentChangeLog (PatientAppId, Action, OldValue, NewValue, ByUserId, ByRole, At) + indexes | New | Appointments | §5.2 + §2.3 + §6 | Reschedule appointment | Move to a new slot with automatic patient notification / Move to another slot without calling the clinic | Doctor Web + Reception + later Patient | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
15 | 252 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.5 | APT-05 | Reschedule appointment — move to a new slot with automatic patient notification (NEW — not a rename of UpdateAppointmentTime) | APT-05.02 | API: POST /api/PatientAppointment/RescheduleAppointment — validate schedule, bookings, not in the past; 409 with alternatives; wrap UpdateAppointmentTime; GET ChangeLog/{id} | New | Appointments | §5.2 + §2.3 + §6 | Reschedule appointment | Move to a new slot with automatic patient notification / Move to another slot without calling the clinic | Doctor Web + Reception + later Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
16 | 253 | M05 | Appointments & scheduling | UI | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.5 | APT-05 | Reschedule appointment — move to a new slot with automatic patient notification (NEW — not a rename of UpdateAppointmentTime) | APT-05.03 | UI: RescheduleModal shared by Doctor and Reception — old date/time + new slot picker; reason optional | New | Appointments | §5.2 + §2.3 + §6 | Reschedule appointment | Move to a new slot with automatic patient notification / Move to another slot without calling the clinic | Doctor Web + Reception + later Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
17 | 254 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.5 | APT-05 | Reschedule appointment — move to a new slot with automatic patient notification (NEW — not a rename of UpdateAppointmentTime) | APT-05.04 | Notifications: SMS + WhatsApp + (later) push — old→new; must not block the transaction if notify fails | New Integration | Appointments | §5.2 + §2.3 + §6 | Reschedule appointment | Move to a new slot with automatic patient notification / Move to another slot without calling the clinic | Doctor Web + Reception + later Patient | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | EDIT HERE — this module sheet
18 | 255 | M05 | Appointments & scheduling | QA | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.5 | APT-05 | Reschedule appointment — move to a new slot with automatic patient notification (NEW — not a rename of UpdateAppointmentTime) | APT-05.05 | QA: slot taken → 409; patient already booked elsewhere; across a schedule change; reception authorised for own DoctorId only | Regression | Appointments | §5.2 + §2.3 + §6 | Reschedule appointment | Move to a new slot with automatic patient notification / Move to another slot without calling the clinic | Doctor Web + Reception + later Patient | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
19 | 256 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.6 | APT-06 | Cancel appointment — reason, free the slot, trigger refund where applicable (NEW CANCELLED status — do NOT reuse DeleteStatus) | APT-06.01 | DB: add CANCELLED to status set; CancelReasonCode, CancelReasonText, CancelledBy, CancelledAt; DeleteStatus remains administrative | New | Appointments | §5.2 + §2.3 + §6 | Cancel appointment | Cancel with reason, free the slot, trigger refund where applicable / Cancel with reason, refund handled per policy | Doctor Web + Reception + later Patient | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
20 | 257 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.6 | APT-06 | Cancel appointment — reason, free the slot, trigger refund where applicable (NEW CANCELLED status — do NOT reuse DeleteStatus) | APT-06.02 | API: POST /api/PatientAppointment/CancelAppointment — reason required (enum; text if Other); free slot; offer waitlist stub; if PAID enqueue refund policy | New | Appointments | §5.2 + §2.3 + §6 | Cancel appointment | Cancel with reason, free the slot, trigger refund where applicable / Cancel with reason, refund handled per policy | Doctor Web + Reception + later Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
21 | 258 | M05 | Appointments & scheduling | UI | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.6 | APT-06 | Cancel appointment — reason, free the slot, trigger refund where applicable (NEW CANCELLED status — do NOT reuse DeleteStatus) | APT-06.03 | UI: CancelAppointmentModal shared by Doctor and Reception; dashboard Cancelled filter | New | Appointments | §5.2 + §2.3 + §6 | Cancel appointment | Cancel with reason, free the slot, trigger refund where applicable / Cancel with reason, refund handled per policy | Doctor Web + Reception + later Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
22 | 259 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.6 | APT-06 | Cancel appointment — reason, free the slot, trigger refund where applicable (NEW CANCELLED status — do NOT reuse DeleteStatus) | APT-06.04 | Waitlist worker stub: on cancel, offer freed slot (full waitlist capture is Phase 9 GST waitlist) | New Integration | Appointments | §5.2 + §2.3 + §6 | Cancel appointment | Cancel with reason, free the slot, trigger refund where applicable / Cancel with reason, refund handled per policy | Doctor Web + Reception + later Patient | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | EDIT HERE — this module sheet
23 | 260 | M05 | Appointments & scheduling | QA | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.6 | APT-06 | Cancel appointment — reason, free the slot, trigger refund where applicable (NEW CANCELLED status — do NOT reuse DeleteStatus) | APT-06.05 | QA: reason mandatory; all three roles (later Patient) cancel with correct authorisation; freed slot bookable | Regression | Appointments | §5.2 + §2.3 + §6 | Cancel appointment | Cancel with reason, free the slot, trigger refund where applicable / Cancel with reason, refund handled per policy | Doctor Web + Reception + later Patient | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
24 | 261 | M05 | Appointments & scheduling | UI | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.7 | APT-07 | Daily schedule setup — define working days, hours and break times (promote modal to first-class screen) | APT-07.01 | Promote DailyScheduleSetupModal to /doctor/schedule; week grid; copy-day; reuse Get/SaveDailySchedule | Existing Improvement | Scheduling | §5.2 | Daily schedule setup | Define working days, hours and break times | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
25 | 262 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.7 | APT-07 | Daily schedule setup — define working days, hours and break times (promote modal to first-class screen) | APT-07.02 | No new API unless validation (breaks, overlapping hours) is missing — add server-side validation | Existing Improvement | Scheduling | §5.2 | Daily schedule setup | Define working days, hours and break times | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
26 | 263 | M05 | Appointments & scheduling | QA | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.7 | APT-07 | Daily schedule setup — define working days, hours and break times (promote modal to first-class screen) | APT-07.03 | QA: save week; public slot generator (Phase 9) uses this data; reception read-only is Phase 5 | Regression | Scheduling | §5.2 | Daily schedule setup | Define working days, hours and break times | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
27 | 264 | M05 | Appointments & scheduling | QA | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.8 | APT-08 | Appointment slot grid — visual slot-by-slot view of the day (keep; public booking reuses this) | APT-08.01 | Regression: slot grid vs schedule | Existing | Scheduling | §5.2 | Appointment slot grid | Visual slot-by-slot view of the day | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
28 | 265 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.8 | APT-08 | Appointment slot grid — visual slot-by-slot view of the day (keep; public booking reuses this) | APT-08.02 | ACL doctor/reception | Existing Improvement | Scheduling | §5.2 | Appointment slot grid | Visual slot-by-slot view of the day | Doctor Web Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
29 | 266 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.8 | APT-08 | Appointment slot grid — visual slot-by-slot view of the day (keep; public booking reuses this) | APT-08.03 | Document GetAppointmentSlots as the public-booking engine — do not fork a second slot calculator | Existing | Scheduling | §5.2 | Appointment slot grid | Visual slot-by-slot view of the day | Doctor Web Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
30 | 267 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.9 | APT-09 | Consultation payment status on every appointment (schema now; values live in Phase 6) | APT-09.01 | DB: PatientAppointment.PaymentStatus, PaymentMethod, PayAtClinicAllowed; default UNPAID | New | Appointments | §5.2 + §9 | Consultation payment status | See paid, unpaid or pay-at-clinic on every appointment / Doctor, reception and patient all see the same payment status | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
31 | 268 | M05 | Appointments & scheduling | Web | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.9 | APT-09 | Consultation payment status on every appointment (schema now; values live in Phase 6) | APT-09.02 | API: include PaymentStatus on all appointment DTOs (doctor, reception, later public/patient) | New | Appointments | §5.2 + §9 | Consultation payment status | See paid, unpaid or pay-at-clinic on every appointment / Doctor, reception and patient all see the same payment status | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
32 | 269 | M05 | Appointments & scheduling | UI | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.9 | APT-09 | Consultation payment status on every appointment (schema now; values live in Phase 6) | APT-09.03 | UI: Paid / Unpaid / Pay-at-clinic / Failed badges on doctor appointment list | New | Appointments | §5.2 + §9 | Consultation payment status | See paid, unpaid or pay-at-clinic on every appointment / Doctor, reception and patient all see the same payment status | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
33 | 270 | M05 | Appointments & scheduling | QA | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.9 | APT-09 | Consultation payment status on every appointment (schema now; values live in Phase 6) | APT-09.04 | QA: same appointment shows the same badge on doctor and reception | Regression | Appointments | §5.2 + §9 | Consultation payment status | See paid, unpaid or pay-at-clinic on every appointment / Doctor, reception and patient all see the same payment status | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
34 | 454 | M05 | Appointments & scheduling | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.11 | WEB-11 | Waitlist offer — get offered a slot when one is freed by a cancellation (patient website + later app) | WEB-11.01 | DB: BookingWaitlist | New | Booking | §2.3 | Waitlist offer | Get offered a slot when one is freed by a cancellation | Patient Website + App | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
35 | 455 | M05 | Appointments & scheduling | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.11 | WEB-11 | Waitlist offer — get offered a slot when one is freed by a cancellation (patient website + later app) | WEB-11.02 | API: join waitlist; worker on CancelAppointment | New | Booking | §2.3 | Waitlist offer | Get offered a slot when one is freed by a cancellation | Patient Website + App | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
36 | 456 | M05 | Appointments & scheduling | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.11 | WEB-11 | Waitlist offer — get offered a slot when one is freed by a cancellation (patient website + later app) | WEB-11.03 | Public waitlist CTA on full days | New | Booking | §2.3 | Waitlist offer | Get offered a slot when one is freed by a cancellation | Patient Website + App | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
37 | 457 | M05 | Appointments & scheduling | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.11 | WEB-11 | Waitlist offer — get offered a slot when one is freed by a cancellation (patient website + later app) | WEB-11.04 | Notify SMS/push when Phase 12 exists | New Integration | Booking | §2.3 | Waitlist offer | Get offered a slot when one is freed by a cancellation | Patient Website + App | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | EDIT HERE — this module sheet
38 | 458 | M05 | Appointments & scheduling | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.11 | WEB-11 | Waitlist offer — get offered a slot when one is freed by a cancellation (patient website + later app) | WEB-11.05 | QA: two waiters; first gets offer; expiry releases to second | Regression | Booking | §2.3 | Waitlist offer | Get offered a slot when one is freed by a cancellation | Patient Website + App | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
39 | 672 | M05 | Appointments & scheduling | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.9 | CON-09 | Physical clinic appointment — book an in-person visit as well as online | CON-09.01 | Public/patient create booking accepts ConsultMode=In-clinic; uses in-clinic fee | Existing Improvement | Booking | §2.9 + §5.2 | Physical clinic appointment | Book an in-person visit as well as online | Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
40 | 673 | M05 | Appointments & scheduling | QA | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.9 | CON-09 | Physical clinic appointment — book an in-person visit as well as online | CON-09.02 | QA: in-clinic does not require device check/video | Regression | Booking | §2.9 + §5.2 | Physical clinic appointment | Book an in-person visit as well as online | Patient | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet

## M06_Reception
M06 Reception portal — 39 sub-tasks (Web 18 · UI 9 · QA 12). YELLOW = edit here (Assigned To, Frontend/Backend/Database/API/Mobile/Integration Status + Assigned). Scope Yes/No is fixed. Status N/A = that function is not in this sub-task. Master, Web/UI/Mobile/QA sheets and Dashboard follow these cells live. | [41 empty] | Live copy of 00_Employees column B — do not edit. New names appear here automatically.
Module Seq | Original Seq | Dev Module Code | Dev Module | Track | Phase | Phase Name | WBS | Main Task ID | Main Task | Sub Task ID | Sub Task | Work Type | Source Module / Area | PDF Section | PDF Feature (exact wording) | PDF Delivery Text | Application Surface | Layer | Assigned To (lead) | Frontend | Frontend Status | Frontend Assigned | Backend | Backend Status | Backend Assigned | Database | Database Status | Database Assigned | API | API Status | API Assigned | Mobile | Mobile Status | Mobile Assigned | Integration | Integration Status | Integration Assigned | Layers Remaining | Overall Status | Notes | Open Module Sheet | _EmpList
1 | 271 | M06 | Reception portal | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.1 | REC-01 | Reception login — secure staff access (keep) | REC-01.01 | Regression: reception login with DoctorID claim | Existing | Reception | §6 | Reception login | Secure staff access | Reception Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Unassigned
2 | 272 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.1 | REC-01 | Reception login — secure staff access (keep) | REC-01.02 | Disabled staff cannot login (after DOC-09) | Existing Improvement | Reception | §6 | Reception login | Secure staff access | Reception Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
3 | 273 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.1 | REC-01 | Reception login — secure staff access (keep) | REC-01.03 | Same Login API as doctor | Existing | Reception | §6 | Reception login | Secure staff access | Reception Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Digvijay Jadhav
4 | 274 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.2 | REC-02 | Reception profile — manage own profile details (0% today) | REC-02.01 | Reuse Profile/Me with role=Reception DTO (no new table if UserMaster suffices) | New | Reception | §6 | Reception profile | Manage own profile details | Reception Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
5 | 275 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.2 | REC-02 | Reception profile — manage own profile details (0% today) | REC-02.02 | GET/PUT profile fields allowed for reception; ignore clinic fee/bank | New | Reception | §6 | Reception profile | Manage own profile details | Reception Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
6 | 276 | M06 | Reception portal | UI | 5 | Phase 5 — Reception portal (PDF §6) | 5.2 | REC-02 | Reception profile — manage own profile details (0% today) | REC-02.03 | /profile reception variant | New | Reception | §6 | Reception profile | Manage own profile details | Reception Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
7 | 277 | M06 | Reception portal | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.2 | REC-02 | Reception profile — manage own profile details (0% today) | REC-02.04 | QA: cannot edit doctor qualifications or fee | Regression | Reception | §6 | Reception profile | Manage own profile details | Reception Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
8 | 278 | M06 | Reception portal | UI | 5 | Phase 5 — Reception portal (PDF §6) | 5.3 | REC-03 | Reception home dashboard — purpose-built front-desk dashboard (not only hidden doctor actions) | REC-03.01 | Route /reception (or role-based chrome on existing dashboard) hiding clinical tabs | Existing Improvement | Reception | §6 | Reception home dashboard | Purpose-built front-desk dashboard | Reception Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
9 | 279 | M06 | Reception portal | UI | 5 | Phase 5 — Reception portal (PDF §6) | 5.3 | REC-03 | Reception home dashboard — purpose-built front-desk dashboard (not only hidden doctor actions) | REC-03.02 | Quick actions: new patient, new appointment, collect payment, case paper, schedule | Existing Improvement | Reception | §6 | Reception home dashboard | Purpose-built front-desk dashboard | Reception Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet | Pranav Bandekar
10 | 280 | M06 | Reception portal | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.3 | REC-03 | Reception home dashboard — purpose-built front-desk dashboard (not only hidden doctor actions) | REC-03.03 | QA: deep-link to Patient Board full clinical URL is 403 for reception | Regression | Reception | §6 | Reception home dashboard | Purpose-built front-desk dashboard | Reception Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
11 | 281 | M06 | Reception portal | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.4 | REC-04 | Create patient — register a walk-in patient quickly (keep) | REC-04.01 | Regression: reception create patient | Existing | Reception | §6 | Create patient | Register a walk-in patient quickly | Reception Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
12 | 282 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.4 | REC-04 | Create patient — register a walk-in patient quickly (keep) | REC-04.02 | ACL: own doctor only | Existing Improvement | Reception | §6 | Create patient | Register a walk-in patient quickly | Reception Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
13 | 283 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.4 | REC-04 | Create patient — register a walk-in patient quickly (keep) | REC-04.03 | Same create-patient API | Existing | Reception | §6 | Create patient | Register a walk-in patient quickly | Reception Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
14 | 284 | M06 | Reception portal | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.5 | REC-05 | Patient search & list — find any patient instantly (keep) | REC-05.01 | Regression: search by name/mobile | Existing | Reception | §6 | Patient search & list | Find any patient instantly | Reception Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
15 | 285 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.5 | REC-05 | Patient search & list — find any patient instantly (keep) | REC-05.02 | Opening a row goes to case paper or appointment, not full repertory | Existing Improvement | Reception | §6 | Patient search & list | Find any patient instantly | Reception Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
16 | 286 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.5 | REC-05 | Patient search & list — find any patient instantly (keep) | REC-05.03 | API unchanged | Existing | Reception | §6 | Patient search & list | Find any patient instantly | Reception Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
17 | 287 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.6 | REC-06 | Create & manage appointments — full appointment management (keep; plus reschedule/cancel from Phase 4) | REC-06.01 | Authorise Reception for Reschedule and Cancel for its own doctor's appointments only | New | Reception | §6 | Create & manage appointments | Full appointment management | Reception Portal | API + SPA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
18 | 288 | M06 | Reception portal | UI | 5 | Phase 5 — Reception portal (PDF §6) | 5.6 | REC-06 | Create & manage appointments — full appointment management (keep; plus reschedule/cancel from Phase 4) | REC-06.02 | Reception UI uses the same Reschedule/Cancel modals as doctor | New | Reception | §6 | Create & manage appointments | Full appointment management | Reception Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
19 | 289 | M06 | Reception portal | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.6 | REC-06 | Create & manage appointments — full appointment management (keep; plus reschedule/cancel from Phase 4) | REC-06.03 | QA: cannot cancel another clinic’s appointment | Regression | Reception | §6 | Create & manage appointments | Full appointment management | Reception Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
20 | 290 | M06 | Reception portal | UI | 5 | Phase 5 — Reception portal (PDF §6) | 5.7 | REC-07 | New appointment — book on behalf of the patient (keep; same VisitType/ConsultMode/fee as APT-02) | REC-07.01 | Share the extended new-appointment modal with reception chrome | Existing Improvement | Reception | §6 | New appointment | Book on behalf of the patient | Reception Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
21 | 291 | M06 | Reception portal | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.7 | REC-07 | New appointment — book on behalf of the patient (keep; same VisitType/ConsultMode/fee as APT-02) | REC-07.02 | QA: in-clinic vs E-Consult both creatable from reception | Regression | Reception | §6 | New appointment | Book on behalf of the patient | Reception Portal | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
22 | 292 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.8 | REC-08 | Waiting queue management — manage the live queue and call the next patient | REC-08.01 | No new table required if status+order suffice; optional QueuePosition | Existing Improvement | Reception | §6 | Waiting queue management | Manage the live queue and call the next patient | Reception Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
23 | 293 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.8 | REC-08 | Waiting queue management — manage the live queue and call the next patient | REC-08.02 | Optional CallNext API that sets status and timestamp | Existing Improvement | Reception | §6 | Waiting queue management | Manage the live queue and call the next patient | Reception Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
24 | 294 | M06 | Reception portal | UI | 5 | Phase 5 — Reception portal (PDF §6) | 5.8 | REC-08 | Waiting queue management — manage the live queue and call the next patient | REC-08.03 | Queue panel: order, wait time, paid/unpaid, Call next | Existing Improvement | Reception | §6 | Waiting queue management | Manage the live queue and call the next patient | Reception Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
25 | 295 | M06 | Reception portal | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.8 | REC-08 | Waiting queue management — manage the live queue and call the next patient | REC-08.04 | QA: two waiting patients; call next picks the right one | Regression | Reception | §6 | Waiting queue management | Manage the live queue and call the next patient | Reception Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
26 | 296 | M06 | Reception portal | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.9 | REC-09 | Appointment status update (reception) — update as patients arrive and are seen (keep) | REC-09.01 | Regression: reception status update | Existing | Reception | §6 | Appointment status update | Update as patients arrive and are seen | Reception Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
27 | 297 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.9 | REC-09 | Appointment status update (reception) — update as patients arrive and are seen (keep) | REC-09.02 | ACL own doctor | Existing Improvement | Reception | §6 | Appointment status update | Update as patients arrive and are seen | Reception Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
28 | 298 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.9 | REC-09 | Appointment status update (reception) — update as patients arrive and are seen (keep) | REC-09.03 | Same status API as doctor | Existing | Reception | §6 | Appointment status update | Update as patients arrive and are seen | Reception Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
29 | 299 | M06 | Reception portal | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.10 | REC-10 | Appointment time update (reception) — adjust timings through the day (keep) | REC-10.01 | Regression: reception UpdateAppointmentTime | Existing | Reception | §6 | Appointment time update | Adjust timings through the day | Reception Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
30 | 300 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.10 | REC-10 | Appointment time update (reception) — adjust timings through the day (keep) | REC-10.02 | ACL own doctor | Existing Improvement | Reception | §6 | Appointment time update | Adjust timings through the day | Reception Portal | Security | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
31 | 301 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.10 | REC-10 | Appointment time update (reception) — adjust timings through the day (keep) | REC-10.03 | Same API | Existing | Reception | §6 | Appointment time update | Adjust timings through the day | Reception Portal | API hygiene | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
32 | 302 | M06 | Reception portal | UI | 5 | Phase 5 — Reception portal (PDF §6) | 5.11 | REC-11 | View doctor schedule — see the doctor’s working schedule (read-only) | REC-11.01 | Frontend only over existing GetDailySchedule — /reception/schedule read-only | New | Reception | §6 | View doctor schedule | See the doctor’s working schedule | Reception Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
33 | 303 | M06 | Reception portal | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.11 | REC-11 | View doctor schedule — see the doctor’s working schedule (read-only) | REC-11.02 | QA: edit buttons hidden; doctor can still edit on /doctor/schedule | Regression | Reception | §6 | View doctor schedule | See the doctor’s working schedule | Reception Portal | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
34 | 304 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.12 | REC-12 | Log case paper / chief complaint — record the reason for visit before the consultation | REC-12.01 | Reuse complaints table; add CreatedByRole=Reception | New | Reception | §6 | Log case paper / chief complaint | Record the reason for visit before the consultation | Reception Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
35 | 305 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.12 | REC-12 | Log case paper / chief complaint — record the reason for visit before the consultation | REC-12.02 | POST case-paper subset of SaveComplaints; GET on board | New | Reception | §6 | Log case paper / chief complaint | Record the reason for visit before the consultation | Reception Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
36 | 306 | M06 | Reception portal | UI | 5 | Phase 5 — Reception portal (PDF §6) | 5.12 | REC-12 | Log case paper / chief complaint — record the reason for visit before the consultation | REC-12.03 | /reception/case-paper or limited board | New | Reception | §6 | Log case paper / chief complaint | Record the reason for visit before the consultation | Reception Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
37 | 307 | M06 | Reception portal | QA | 5 | Phase 5 — Reception portal (PDF §6) | 5.12 | REC-12 | Log case paper / chief complaint — record the reason for visit before the consultation | REC-12.04 | QA: doctor sees CC; reception 403 on repertory APIs | Regression | Reception | §6 | Log case paper / chief complaint | Record the reason for visit before the consultation | Reception Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
38 | 308 | M06 | Reception portal | UI | 5 | Phase 5 — Reception portal (PDF §6) | 5.13 | REC-13 | Collect consultation payment — cash, UPI, card or payment link and issue a receipt (API in Phase 6; UI shell now) | REC-13.01 | Specify receipt fields (amount, method, appointment, GST placeholder) for Phase 6 implementation | New | Reception | §6 + §9 | Collect consultation payment | Take cash, UPI, card or payment link and issue a receipt | Reception Portal | Design | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
39 | 309 | M06 | Reception portal | Web | 5 | Phase 5 — Reception portal (PDF §6) | 5.13 | REC-13 | Collect consultation payment — cash, UPI, card or payment link and issue a receipt (API in Phase 6; UI shell now) | REC-13.02 | Do not write PaymentStatus=PAID from the client — Account/webhook is source of truth (Phase 6) | New | Reception | §6 + §9 | Collect consultation payment | Take cash, UPI, card or payment link and issue a receipt | Reception Portal | Architecture | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet

## M07_Payments
M07 Payment system — 42 sub-tasks (Web 23 · UI 8 · QA 11). YELLOW = edit here (Assigned To, Frontend/Backend/Database/API/Mobile/Integration Status + Assigned). Scope Yes/No is fixed. Status N/A = that function is not in this sub-task. Master, Web/UI/Mobile/QA sheets and Dashboard follow these cells live. | [41 empty] | Live copy of 00_Employees column B — do not edit. New names appear here automatically.
Module Seq | Original Seq | Dev Module Code | Dev Module | Track | Phase | Phase Name | WBS | Main Task ID | Main Task | Sub Task ID | Sub Task | Work Type | Source Module / Area | PDF Section | PDF Feature (exact wording) | PDF Delivery Text | Application Surface | Layer | Assigned To (lead) | Frontend | Frontend Status | Frontend Assigned | Backend | Backend Status | Backend Assigned | Database | Database Status | Database Assigned | API | API Status | API Assigned | Mobile | Mobile Status | Mobile Assigned | Integration | Integration Status | Integration Assigned | Layers Remaining | Overall Status | Notes | Open Module Sheet | _EmpList
1 | 310 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.1 | PAY-01 | Consultation fee configuration — each doctor’s fee set and displayed to patients | PAY-01.01 | DB: ConsultFeeConfig (DoctorId, InClinicFee, TeleFee, InstantSurcharge, Currency, PayAtClinicEnabled, EffectiveFrom) | New | Payments | §9 | Consultation fee configuration | Each doctor’s fee set and displayed to patients | Doctor profile + Public + Admin | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Unassigned
2 | 311 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.1 | PAY-01 | Consultation fee configuration — each doctor’s fee set and displayed to patients | PAY-01.02 | API: GET public fee; PUT doctor/admin; history of changes in audit | New | Payments | §9 | Consultation fee configuration | Each doctor’s fee set and displayed to patients | Doctor profile + Public + Admin | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
3 | 312 | M07 | Payment system | UI | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.1 | PAY-01 | Consultation fee configuration — each doctor’s fee set and displayed to patients | PAY-01.03 | Doctor profile fee tab + later public doctor card | New | Payments | §9 | Consultation fee configuration | Each doctor’s fee set and displayed to patients | Doctor profile + Public + Admin | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Digvijay Jadhav
4 | 313 | M07 | Payment system | QA | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.1 | PAY-01 | Consultation fee configuration — each doctor’s fee set and displayed to patients | PAY-01.04 | QA: changing fee does not alter already-created unpaid orders without a rule (document the rule) | Regression | Payments | §9 | Consultation fee configuration | Each doctor’s fee set and displayed to patients | Doctor profile + Public + Admin | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
5 | 314 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.2 | PAY-02 | Automatic payment verification — bank/webhook is source of truth, not the patient’s screen | PAY-02.01 | DB: PaymentOrder, PaymentEvent (raw webhook), idempotency key on payment_id | New | Payments | §9 | Automatic payment verification | Payments confirmed by the bank, not by the patient’s screen — nothing is lost if the app or browser closes | Shared | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
6 | 315 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.2 | PAY-02 | Automatic payment verification — bank/webhook is source of truth, not the patient’s screen | PAY-02.02 | Port Order/GenerateOrderId pattern to .NET 8; move keys to configuration; do not commit secrets | New Integration | Payments | §9 | Automatic payment verification | Payments confirmed by the bank, not by the patient’s screen — nothing is lost if the app or browser closes | Shared | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
7 | 316 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.2 | PAY-02 | Automatic payment verification — bank/webhook is source of truth, not the patient’s screen | PAY-02.03 | Webhook handler payment.captured / payment.failed; signature verify; never trust client-only success | New Integration | Payments | §9 | Automatic payment verification | Payments confirmed by the bank, not by the patient’s screen — nothing is lost if the app or browser closes | Shared | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
8 | 317 | M07 | Payment system | QA | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.2 | PAY-02 | Automatic payment verification — bank/webhook is source of truth, not the patient’s screen | PAY-02.04 | QA: duplicate webhook; delayed webhook; failed capture; app closed mid-checkout | Regression | Payments | §9 | Automatic payment verification | Payments confirmed by the bank, not by the patient’s screen — nothing is lost if the app or browser closes | Shared | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | 2 | Not Started |  | EDIT HERE — this module sheet
9 | 318 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.3 | PAY-03 | Online consultation payment — patient pays by card, UPI, netbanking or wallet | PAY-03.01 | DB: ConsultPayment linked to PaymentOrder + PatientAppId — NOT PackageEntryDetail | New | Payments | §9 + §4 + §2.3 | Online consultation payment | Patient pays by card, UPI, netbanking or wallet / Pay the consultation fee at the time of booking / Pay the consultation fee inside the app | Public web + later Patient app | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Pranav Bandekar
10 | 319 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.3 | PAY-03 | Online consultation payment — patient pays by card, UPI, netbanking or wallet | PAY-03.02 | API: CreateConsultOrder, Verify (optional), status by appointment; amount from ConsultFeeConfig | New | Payments | §9 + §4 + §2.3 | Online consultation payment | Patient pays by card, UPI, netbanking or wallet / Pay the consultation fee at the time of booking / Pay the consultation fee inside the app | Public web + later Patient app | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
11 | 320 | M07 | Payment system | UI | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.3 | PAY-03 | Online consultation payment — patient pays by card, UPI, netbanking or wallet | PAY-03.03 | Public /book/pay/:bookingId using Razorpay pattern from Widgets.js but consult order API | New | Payments | §9 + §4 + §2.3 | Online consultation payment | Patient pays by card, UPI, netbanking or wallet / Pay the consultation fee at the time of booking / Pay the consultation fee inside the app | Public web + later Patient app | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
12 | 321 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.3 | PAY-03 | Online consultation payment — patient pays by card, UPI, netbanking or wallet | PAY-03.04 | Razorpay Checkout methods: card, UPI, netbanking, wallet as enabled on the account | New Integration | Payments | §9 + §4 + §2.3 | Online consultation payment | Patient pays by card, UPI, netbanking or wallet / Pay the consultation fee at the time of booking / Pay the consultation fee inside the app | Public web + later Patient app | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | EDIT HERE — this module sheet
13 | 322 | M07 | Payment system | QA | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.3 | PAY-03 | Online consultation payment — patient pays by card, UPI, netbanking or wallet | PAY-03.05 | QA: success, failure, pending, double-click create order idempotent | Regression | Payments | §9 + §4 + §2.3 | Online consultation payment | Patient pays by card, UPI, netbanking or wallet / Pay the consultation fee at the time of booking / Pay the consultation fee inside the app | Public web + later Patient app | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
14 | 323 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.4 | PAY-04 | Reception payment collection — cash, UPI, card or payment link with printed receipt | PAY-04.01 | Reuse PaymentOrder + ConsultPayment with Method=CASH/UPI_OFFLINE/CARD_POS/PAY_LINK | New | Payments | §9 + §6 | Reception payment collection | Cash, UPI, card or payment link with printed receipt | Reception Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
15 | 324 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.4 | PAY-04 | Reception payment collection — cash, UPI, card or payment link with printed receipt | PAY-04.02 | API: CollectAtReception; generate pay-link; print receipt payload | New | Payments | §9 + §6 | Reception payment collection | Cash, UPI, card or payment link with printed receipt | Reception Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
16 | 325 | M07 | Payment system | UI | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.4 | PAY-04 | Reception payment collection — cash, UPI, card or payment link with printed receipt | PAY-04.03 | Reception collect modal: amount, method, GST placeholder, print receipt | New | Payments | §9 + §6 | Reception payment collection | Cash, UPI, card or payment link with printed receipt | Reception Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
17 | 326 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.4 | PAY-04 | Reception payment collection — cash, UPI, card or payment link with printed receipt | PAY-04.04 | Pay-link SMS/WhatsApp optional (Phase 12); must still ledger if notify fails | New Integration | Payments | §9 + §6 | Reception payment collection | Cash, UPI, card or payment link with printed receipt | Reception Portal | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | EDIT HERE — this module sheet
18 | 327 | M07 | Payment system | QA | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.4 | PAY-04 | Reception payment collection — cash, UPI, card or payment link with printed receipt | PAY-04.05 | QA: cash collection visible in clinic collection view after Phase 7; cannot mark PAID without this API | Regression | Payments | §9 + §6 | Reception payment collection | Cash, UPI, card or payment link with printed receipt | Reception Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
19 | 328 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.5 | PAY-05 | Pay-at-clinic option — book now, pay at the clinic where the doctor allows it | PAY-05.01 | Honor PayAtClinicEnabled on public create-booking and checkout | New | Payments | §9 | Pay-at-clinic option | Book now, pay at the clinic where the doctor allows it | Public + Doctor + Reception | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
20 | 329 | M07 | Payment system | UI | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.5 | PAY-05 | Pay-at-clinic option — book now, pay at the clinic where the doctor allows it | PAY-05.02 | UI: public booking shows Pay at clinic vs Pay now; doctor list badge | New | Payments | §9 | Pay-at-clinic option | Book now, pay at the clinic where the doctor allows it | Public + Doctor + Reception | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
21 | 330 | M07 | Payment system | QA | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.5 | PAY-05 | Pay-at-clinic option — book now, pay at the clinic where the doctor allows it | PAY-05.03 | QA: doctor flag off → pay-at-clinic hidden; reception can still collect | Regression | Payments | §9 | Pay-at-clinic option | Book now, pay at the clinic where the doctor allows it | Public + Doctor + Reception | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
22 | 331 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.6 | PAY-06 | Doctor subscription payment — buy and renew subscription packages (complete remaining ~30%) | PAY-06.01 | Reuse PAY-02 webhook for S1 orders; link PackageEntryDetail as S1 only | Existing Improvement | Payments | §9 | Doctor subscription payment | Buy and renew subscription packages | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | 2 | Not Started |  | EDIT HERE — this module sheet
23 | 332 | M07 | Payment system | UI | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.6 | PAY-06 | Doctor subscription payment — buy and renew subscription packages (complete remaining ~30%) | PAY-06.02 | Widgets.js: handle failed pay; show invoice when Phase 7 invoice exists | Existing Improvement | Payments | §9 | Doctor subscription payment | Buy and renew subscription packages | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
24 | 333 | M07 | Payment system | QA | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.6 | PAY-06 | Doctor subscription payment — buy and renew subscription packages (complete remaining ~30%) | PAY-06.03 | QA: renew, fail, webhook delay, last-5-days warning still works | Regression | Payments | §9 | Doctor subscription payment | Buy and renew subscription packages | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
25 | 334 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.7 | PAY-07 | Medicine payment — pay online or cash on delivery (API contract now; HomeoMeds Phase 14 implements orders) | PAY-07.01 | Extend PaymentOrder with Stream=CONSULT¦SUBSCRIPTION¦MEDICINE so Phase 14 can attach without schema rewrite | New | Payments | §9 + §12 | Medicine payment | Pay online or choose cash on delivery / Both options supported, with status tracking | Shared | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
26 | 335 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.7 | PAY-07 | Medicine payment — pay online or cash on delivery (API contract now; HomeoMeds Phase 14 implements orders) | PAY-07.02 | API stub: CreateMedicineOrder payment + COD status enum — implemented fully in Phase 14 | New | Payments | §9 + §12 | Medicine payment | Pay online or choose cash on delivery / Both options supported, with status tracking | Shared | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
27 | 336 | M07 | Payment system | QA | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.7 | PAY-07 | Medicine payment — pay online or cash on delivery (API contract now; HomeoMeds Phase 14 implements orders) | PAY-07.03 | QA: stream isolation query (consult vs medicine totals differ) | Regression | Payments | §9 + §12 | Medicine payment | Pay online or choose cash on delivery / Both options supported, with status tracking | Shared | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
28 | 337 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.8 | PAY-08 | Payment status everywhere — doctor, reception and patient all see the same payment status | PAY-08.01 | Single source: PaymentOrder/ConsultPayment → Appointment.PaymentStatus updated only by webhook or CollectAtReception | New | Payments | §9 | Payment status everywhere | Doctor, reception and patient all see the same payment status | All | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
29 | 338 | M07 | Payment system | UI | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.8 | PAY-08 | Payment status everywhere — doctor, reception and patient all see the same payment status | PAY-08.02 | Surface badges: doctor, reception; public confirmation page; patient app in Phase 16 consumes same API | New | Payments | §9 | Payment status everywhere | Doctor, reception and patient all see the same payment status | All | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
30 | 339 | M07 | Payment system | QA | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.8 | PAY-08 | Payment status everywhere — doctor, reception and patient all see the same payment status | PAY-08.03 | QA: three roles, one appointment, same enum value | Regression | Payments | §9 | Payment status everywhere | Doctor, reception and patient all see the same payment status | All | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
31 | 340 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.9 | PAY-09 | Refunds — processed and tracked against the original payment | PAY-09.01 | DB: Refund (PaymentOrderId, Amount, Reason, Status, GatewayRefundId, ByUserId, At) | New | Payments | §9 + §8 + §2.8 | Refunds | Processed and tracked against the original payment / Issue and track refunds | Account + Patient | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
32 | 341 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.9 | PAY-09 | Refunds — processed and tracked against the original payment | PAY-09.02 | API: create refund (Account); webhook refund.processed; cancel-appointment policy engine (full/partial/none) | New | Payments | §9 + §8 + §2.8 | Refunds | Processed and tracked against the original payment / Issue and track refunds | Account + Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
33 | 342 | M07 | Payment system | UI | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.9 | PAY-09 | Refunds — processed and tracked against the original payment | PAY-09.03 | Account refund screen in Phase 7; patient payments list in Phase 16 | New | Payments | §9 + §8 + §2.8 | Refunds | Processed and tracked against the original payment / Issue and track refunds | Account + Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
34 | 343 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.9 | PAY-09 | Refunds — processed and tracked against the original payment | PAY-09.04 | Razorpay refund API + webhook | New Integration | Payments | §9 + §8 + §2.8 | Refunds | Processed and tracked against the original payment / Issue and track refunds | Account + Patient | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | EDIT HERE — this module sheet
35 | 344 | M07 | Payment system | QA | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.9 | PAY-09 | Refunds — processed and tracked against the original payment | PAY-09.05 | QA: double refund blocked; cash collection refund is ledger-only per PRE-02 policy | Regression | Payments | §9 + §8 + §2.8 | Refunds | Processed and tracked against the original payment / Issue and track refunds | Account + Patient | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
36 | 345 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.10 | PAY-10 | Payment receipts & invoices — issued for every transaction | PAY-10.01 | DB: Invoice (Number, Series, Stream, PaymentOrderId, GstBreakup, PdfPath) | New | Payments | §9 + §8 | Payment receipts & invoices | Issued for every transaction / Invoice numbering and tax reporting | All | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
37 | 346 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.10 | PAY-10 | Payment receipts & invoices — issued for every transaction | PAY-10.02 | API: get invoice by payment; generate PDF via SecureDocument | New | Payments | §9 + §8 | Payment receipts & invoices | Issued for every transaction / Invoice numbering and tax reporting | All | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
38 | 347 | M07 | Payment system | UI | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.10 | PAY-10 | Payment receipts & invoices — issued for every transaction | PAY-10.03 | Print/download on reception, doctor (subscription), later patient app | New | Payments | §9 + §8 | Payment receipts & invoices | Issued for every transaction / Invoice numbering and tax reporting | All | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
39 | 348 | M07 | Payment system | QA | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.10 | PAY-10 | Payment receipts & invoices — issued for every transaction | PAY-10.04 | QA: unique invoice numbers; cancelled invoice not reused | Regression | Payments | §9 + §8 | Payment receipts & invoices | Issued for every transaction / Invoice numbering and tax reporting | All | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
40 | 349 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.11 | PAY-11 | Complete payment audit trail — every transaction traceable end to end by Homeocentrum | PAY-11.01 | Persist raw webhook JSON; correlation id on Appointment and Ledger | New | Payments | §9 + §17 | Complete audit trail | Every transaction traceable end to end by Homeocentrum | Account | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
41 | 350 | M07 | Payment system | Web | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.11 | PAY-11 | Complete payment audit trail — every transaction traceable end to end by Homeocentrum | PAY-11.02 | Account query API: trail by appointment / payment / doctor (Phase 7 UI) | New | Payments | §9 + §17 | Complete audit trail | Every transaction traceable end to end by Homeocentrum | Account | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
42 | 351 | M07 | Payment system | QA | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.11 | PAY-11 | Complete payment audit trail — every transaction traceable end to end by Homeocentrum | PAY-11.03 | QA: missing webhook still shows PENDING not PAID | Regression | Payments | §9 + §17 | Complete audit trail | Every transaction traceable end to end by Homeocentrum | Account | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet

## M08_Account_Finance
M08 Account & finance — 44 sub-tasks (Web 22 · UI 10 · QA 12). YELLOW = edit here (Assigned To, Frontend/Backend/Database/API/Mobile/Integration Status + Assigned). Scope Yes/No is fixed. Status N/A = that function is not in this sub-task. Master, Web/UI/Mobile/QA sheets and Dashboard follow these cells live. | [41 empty] | Live copy of 00_Employees column B — do not edit. New names appear here automatically.
Module Seq | Original Seq | Dev Module Code | Dev Module | Track | Phase | Phase Name | WBS | Main Task ID | Main Task | Sub Task ID | Sub Task | Work Type | Source Module / Area | PDF Section | PDF Feature (exact wording) | PDF Delivery Text | Application Surface | Layer | Assigned To (lead) | Frontend | Frontend Status | Frontend Assigned | Backend | Backend Status | Backend Assigned | Database | Database Status | Database Assigned | API | API Status | API Assigned | Mobile | Mobile Status | Mobile Assigned | Integration | Integration Status | Integration Assigned | Layers Remaining | Overall Status | Notes | Open Module Sheet | _EmpList
1 | 352 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.1 | FIN-01 | Unified transaction ledger — every rupee that moves through the platform, in one record | FIN-01.01 | DB: LedgerEntry (Stream, Direction, Amount, Gst, Commission, EntityType, EntityId, PaymentOrderId, At) immutable | New | Account | §8 | Unified transaction ledger | Every rupee that moves through the platform, in one record | Account Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Unassigned
2 | 353 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.1 | FIN-01 | Unified transaction ledger — every rupee that moves through the platform, in one record | FIN-01.02 | API: GET /account/ledger filters; export; write-only from payment/settlement services | New | Account | §8 | Unified transaction ledger | Every rupee that moves through the platform, in one record | Account Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
3 | 354 | M08 | Account & finance | UI | 7 | Phase 7 — Account & finance department (PDF §8) | 7.1 | FIN-01 | Unified transaction ledger — every rupee that moves through the platform, in one record | FIN-01.03 | /account/ledger UI — Account layout sidebar Finance | New | Account | §8 | Unified transaction ledger | Every rupee that moves through the platform, in one record | Account Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Digvijay Jadhav
4 | 355 | M08 | Account & finance | QA | 7 | Phase 7 — Account & finance department (PDF §8) | 7.1 | FIN-01 | Unified transaction ledger — every rupee that moves through the platform, in one record | FIN-01.04 | QA: consult pay writes S2; subscription writes S1; they never share one row | Regression | Account | §8 | Unified transaction ledger | Every rupee that moves through the platform, in one record | Account Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
5 | 356 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.2 | FIN-02 | Consultation payment reconciliation — online payments and reception collections matched and verified | FIN-02.01 | Reuse ConsultPayment + Appointment; reconciliation query | New | Account | §8 + §7.2 + §16 | Consultation payment reconciliation | Online payments and reception collections matched and verified / Match every booking against every payment | Account + Admin | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
6 | 357 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.2 | FIN-02 | Consultation payment reconciliation — online payments and reception collections matched and verified | FIN-02.02 | GET Admin/Account reconciliation + aggregates | New | Account | §8 + §7.2 + §16 | Consultation payment reconciliation | Online payments and reception collections matched and verified / Match every booking against every payment | Account + Admin | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
7 | 358 | M08 | Account & finance | UI | 7 | Phase 7 — Account & finance department (PDF §8) | 7.2 | FIN-02 | Consultation payment reconciliation — online payments and reception collections matched and verified | FIN-02.03 | /account/consult-recon and /admin/consult-payments (same data, Account owns, Admin views) | New | Account | §8 + §7.2 + §16 | Consultation payment reconciliation | Online payments and reception collections matched and verified / Match every booking against every payment | Account + Admin | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
8 | 359 | M08 | Account & finance | QA | 7 | Phase 7 — Account & finance department (PDF §8) | 7.2 | FIN-02 | Consultation payment reconciliation — online payments and reception collections matched and verified | FIN-02.04 | QA: unmatched payment appears in exception queue not silent | Regression | Account | §8 + §7.2 + §16 | Consultation payment reconciliation | Online payments and reception collections matched and verified / Match every booking against every payment | Account + Admin | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
9 | 360 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.3 | FIN-03 | Medicine ledger — medicine money tracked separately from consultation money | FIN-03.01 | LedgerEntry stream MEDICINE with SplitSeller/SplitPlatform/SplitDelivery | New | Account | §8 + §12 | Medicine ledger | Medicine money tracked separately from consultation money / Seller, platform and delivery shares recorded separately from consultation money | Account Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Pranav Bandekar
10 | 361 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.3 | FIN-03 | Medicine ledger — medicine money tracked separately from consultation money | FIN-03.02 | GET /account/medicine-ledger | New | Account | §8 + §12 | Medicine ledger | Medicine money tracked separately from consultation money / Seller, platform and delivery shares recorded separately from consultation money | Account Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
11 | 362 | M08 | Account & finance | UI | 7 | Phase 7 — Account & finance department (PDF §8) | 7.3 | FIN-03 | Medicine ledger — medicine money tracked separately from consultation money | FIN-03.03 | /account/medicine-ledger UI (empty until HomeoMeds orders exist — still ship the screen) | New | Account | §8 + §12 | Medicine ledger | Medicine money tracked separately from consultation money / Seller, platform and delivery shares recorded separately from consultation money | Account Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
12 | 363 | M08 | Account & finance | QA | 7 | Phase 7 — Account & finance department (PDF §8) | 7.3 | FIN-03 | Medicine ledger — medicine money tracked separately from consultation money | FIN-03.04 | QA: S2 consult row never appears on this screen | Regression | Account | §8 + §12 | Medicine ledger | Medicine money tracked separately from consultation money / Seller, platform and delivery shares recorded separately from consultation money | Account Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
13 | 364 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.4 | FIN-04 | Settlement runs — scheduled settlement of amounts due to doctors and pharmacies | FIN-04.01 | DB: SettlementRun, SettlementLine | New | Account | §8 + §16 | Settlement runs | Scheduled settlement of amounts due to doctors and pharmacies | Account Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
14 | 365 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.4 | FIN-04 | Settlement runs — scheduled settlement of amounts due to doctors and pharmacies | FIN-04.02 | API: create run (dry-run + commit); list; detail | New | Account | §8 + §16 | Settlement runs | Scheduled settlement of amounts due to doctors and pharmacies | Account Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
15 | 366 | M08 | Account & finance | UI | 7 | Phase 7 — Account & finance department (PDF §8) | 7.4 | FIN-04 | Settlement runs — scheduled settlement of amounts due to doctors and pharmacies | FIN-04.03 | /account/settlements | New | Account | §8 + §16 | Settlement runs | Scheduled settlement of amounts due to doctors and pharmacies | Account Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
16 | 367 | M08 | Account & finance | QA | 7 | Phase 7 — Account & finance department (PDF §8) | 7.4 | FIN-04 | Settlement runs — scheduled settlement of amounts due to doctors and pharmacies | FIN-04.04 | QA: hold days exclude too-new captures; refunds net out | Regression | Account | §8 + §16 | Settlement runs | Scheduled settlement of amounts due to doctors and pharmacies | Account Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
17 | 368 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.5 | FIN-05 | Payout approval — payouts released only after OTP-verified approval | FIN-05.01 | DB: Payout (PayeeType Doctor¦Pharmacy, Amount, Status, SettlementRunId) | New | Account | §8 + §17 | Payout approval | Payouts released only after OTP-verified approval | Account Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
18 | 369 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.5 | FIN-05 | Payout approval — payouts released only after OTP-verified approval | FIN-05.02 | API: ApprovePayout with OTP; reject | New | Account | §8 + §17 | Payout approval | Payouts released only after OTP-verified approval | Account Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
19 | 370 | M08 | Account & finance | UI | 7 | Phase 7 — Account & finance department (PDF §8) | 7.5 | FIN-05 | Payout approval — payouts released only after OTP-verified approval | FIN-05.03 | /account/payouts | New | Account | §8 + §17 | Payout approval | Payouts released only after OTP-verified approval | Account Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
20 | 371 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.5 | FIN-05 | Payout approval — payouts released only after OTP-verified approval | FIN-05.04 | Bank file / Razorpay payout adapter per PRE-01 | New Integration | Account | §8 + §17 | Payout approval | Payouts released only after OTP-verified approval | Account Portal | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | EDIT HERE — this module sheet
21 | 372 | M08 | Account & finance | QA | 7 | Phase 7 — Account & finance department (PDF §8) | 7.5 | FIN-05 | Payout approval — payouts released only after OTP-verified approval | FIN-05.05 | QA: Account role only; replay OTP; Admin 403 on approve | Regression | Account | §8 + §17 | Payout approval | Payouts released only after OTP-verified approval | Account Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
22 | 373 | M08 | Account & finance | UI | 7 | Phase 7 — Account & finance department (PDF §8) | 7.6 | FIN-06 | Refund processing — Account issues and tracks refunds (uses PAY-09) | FIN-06.01 | UI /account/refunds: original payment, amount, reason, status | New | Account | §8 | Refund processing | Issue and track refunds | Account Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
23 | 374 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.6 | FIN-06 | Refund processing — Account issues and tracks refunds (uses PAY-09) | FIN-06.02 | Ledger reverse entries on successful refund | New | Account | §8 | Refund processing | Issue and track refunds | Account Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
24 | 375 | M08 | Account & finance | QA | 7 | Phase 7 — Account & finance department (PDF §8) | 7.6 | FIN-06 | Refund processing — Account issues and tracks refunds (uses PAY-09) | FIN-06.03 | QA: partial refund; full refund; cash-policy path | Regression | Account | §8 | Refund processing | Issue and track refunds | Account Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
25 | 376 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.7 | FIN-07 | Payment exception handling — investigate and resolve every failed or disputed payment | FIN-07.01 | DB: PaymentException state machine | New | Account | §8 + §7.2 | Payment exception handling | Investigate and resolve every failed or disputed payment / Every failed or mismatched payment surfaced for action | Account + Admin | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
26 | 377 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.7 | FIN-07 | Payment exception handling — investigate and resolve every failed or disputed payment | FIN-07.02 | API: list/detail/retry/resolve; created by webhook mismatches | New | Account | §8 + §7.2 | Payment exception handling | Investigate and resolve every failed or disputed payment / Every failed or mismatched payment surfaced for action | Account + Admin | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
27 | 378 | M08 | Account & finance | UI | 7 | Phase 7 — Account & finance department (PDF §8) | 7.7 | FIN-07 | Payment exception handling — investigate and resolve every failed or disputed payment | FIN-07.03 | /account/exceptions and /admin/payment-exceptions (same queue) | New | Account | §8 + §7.2 | Payment exception handling | Investigate and resolve every failed or disputed payment / Every failed or mismatched payment surfaced for action | Account + Admin | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
28 | 379 | M08 | Account & finance | QA | 7 | Phase 7 — Account & finance department (PDF §8) | 7.7 | FIN-07 | Payment exception handling — investigate and resolve every failed or disputed payment | FIN-07.04 | QA: failed webhook creates exception; manual resolve requires Account role + OTP | Regression | Account | §8 + §7.2 | Payment exception handling | Investigate and resolve every failed or disputed payment / Every failed or mismatched payment surfaced for action | Account + Admin | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
29 | 380 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.8 | FIN-08 | GST & invoice reports — invoice numbering and tax reporting | FIN-08.01 | Reuse Invoice; tax config table (GstRate, treatment flags) | New | Account | §8 + §16 | GST & invoice reports | Invoice numbering and tax reporting | Account Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
30 | 381 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.8 | FIN-08 | GST & invoice reports — invoice numbering and tax reporting | FIN-08.02 | GET tax report + CSV | New | Account | §8 + §16 | GST & invoice reports | Invoice numbering and tax reporting | Account Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
31 | 382 | M08 | Account & finance | UI | 7 | Phase 7 — Account & finance department (PDF §8) | 7.8 | FIN-08 | GST & invoice reports — invoice numbering and tax reporting | FIN-08.03 | /account/tax | New | Account | §8 + §16 | GST & invoice reports | Invoice numbering and tax reporting | Account Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
32 | 383 | M08 | Account & finance | QA | 7 | Phase 7 — Account & finance department (PDF §8) | 7.8 | FIN-08 | GST & invoice reports — invoice numbering and tax reporting | FIN-08.04 | QA: rates come from config; changing rate does not rewrite old invoices | Regression | Account | §8 + §16 | GST & invoice reports | Invoice numbering and tax reporting | Account Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
33 | 384 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.9 | FIN-09 | Payee records — bank and KYC details for doctors and pharmacies | FIN-09.01 | DB: Payee (DoctorId/PharmacyId, Bank, PAN, KYC status) | New | Account | §8 | Payee records | Bank and KYC details for doctors and pharmacies | Account Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
34 | 385 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.9 | FIN-09 | Payee records — bank and KYC details for doctors and pharmacies | FIN-09.02 | API: list/update; OTP on bank change | New | Account | §8 | Payee records | Bank and KYC details for doctors and pharmacies | Account Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
35 | 386 | M08 | Account & finance | UI | 7 | Phase 7 — Account & finance department (PDF §8) | 7.9 | FIN-09 | Payee records — bank and KYC details for doctors and pharmacies | FIN-09.03 | /account/payees | New | Account | §8 | Payee records | Bank and KYC details for doctors and pharmacies | Account Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
36 | 387 | M08 | Account & finance | QA | 7 | Phase 7 — Account & finance department (PDF §8) | 7.9 | FIN-09 | Payee records — bank and KYC details for doctors and pharmacies | FIN-09.04 | QA: missing KYC blocks FIN-05 | Regression | Account | §8 | Payee records | Bank and KYC details for doctors and pharmacies | Account Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
37 | 388 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.10 | FIN-10 | Clinic collection view — cash and UPI collected at reception, per clinic and per day | FIN-10.01 | Query ConsultPayment Method in CASH/UPI_OFFLINE grouped by DoctorId/date | New | Account | §8 | Clinic collection view | Cash and UPI collected at reception, per clinic and per day | Account Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
38 | 389 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.10 | FIN-10 | Clinic collection view — cash and UPI collected at reception, per clinic and per day | FIN-10.02 | GET clinic-collections | New | Account | §8 | Clinic collection view | Cash and UPI collected at reception, per clinic and per day | Account Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
39 | 390 | M08 | Account & finance | UI | 7 | Phase 7 — Account & finance department (PDF §8) | 7.10 | FIN-10 | Clinic collection view — cash and UPI collected at reception, per clinic and per day | FIN-10.03 | /account/clinic-collections | New | Account | §8 | Clinic collection view | Cash and UPI collected at reception, per clinic and per day | Account Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
40 | 391 | M08 | Account & finance | QA | 7 | Phase 7 — Account & finance department (PDF §8) | 7.10 | FIN-10 | Clinic collection view — cash and UPI collected at reception, per clinic and per day | FIN-10.04 | QA: online Razorpay consults do not appear as clinic cash | Regression | Account | §8 | Clinic collection view | Cash and UPI collected at reception, per clinic and per day | Account Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
41 | 392 | M08 | Account & finance | Web | 7 | Phase 7 — Account & finance department (PDF §8) | 7.11 | FIN-11 | Separation of duties — Account controls money; Admin controls platform and clinical data | FIN-11.01 | Seed Account role menus: ledger, recon, medicine ledger, exceptions, settlements, payouts, refunds, tax, payees, clinic collections | New | Account | §8 | Separation of duties | The Account department controls money. Admin controls the platform and clinical data. Neither can perform the other’s role, which protects both. | Admin + Account | Configuration | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
42 | 393 | M08 | Account & finance | QA | 7 | Phase 7 — Account & finance department (PDF §8) | 7.11 | FIN-11 | Separation of duties — Account controls money; Admin controls platform and clinical data | FIN-11.02 | Negative tests: Admin POST ApprovePayout → 403; Account POST repertory section → 403 | Regression | Account | §8 | Separation of duties | The Account department controls money. Admin controls the platform and clinical data. Neither can perform the other’s role, which protects both. | Admin + Account | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
43 | 670 | M08 | Account & finance | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.8 | CON-08 | Patient payments & refunds read model | CON-08.01 | GET /api/Patient/Payments | New | Patient money | §2.8 | Payments & refunds | Full payment history and refund status | Patient App (API now) | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
44 | 671 | M08 | Account & finance | QA | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.8 | CON-08 | Patient payments & refunds read model | CON-08.02 | QA: commission/GST internal lines hidden | Regression | Patient money | §2.8 | Payments & refunds | Full payment history and refund status | Patient App (API now) | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet

## M09_Trust
M09 Trust & verification — 27 sub-tasks (Web 14 · UI 6 · QA 7). YELLOW = edit here (Assigned To, Frontend/Backend/Database/API/Mobile/Integration Status + Assigned). Scope Yes/No is fixed. Status N/A = that function is not in this sub-task. Master, Web/UI/Mobile/QA sheets and Dashboard follow these cells live. | [41 empty] | Live copy of 00_Employees column B — do not edit. New names appear here automatically.
Module Seq | Original Seq | Dev Module Code | Dev Module | Track | Phase | Phase Name | WBS | Main Task ID | Main Task | Sub Task ID | Sub Task | Work Type | Source Module / Area | PDF Section | PDF Feature (exact wording) | PDF Delivery Text | Application Surface | Layer | Assigned To (lead) | Frontend | Frontend Status | Frontend Assigned | Backend | Backend Status | Backend Assigned | Database | Database Status | Database Assigned | API | API Status | API Assigned | Mobile | Mobile Status | Mobile Assigned | Integration | Integration Status | Integration Assigned | Layers Remaining | Overall Status | Notes | Open Module Sheet | _EmpList
1 | 394 | M09 | Trust & verification | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.1 | TRU-01 | Doctor credentialing — doctors upload qualification and registration documents for review | TRU-01.01 | DB: DoctorVerification (Pending/Approved/Rejected/NeedsInfo), DoctorCredentialDocument | New | Trust | §13 + §7.2 | Doctor credentialing | Doctors upload qualification and registration documents for review | Doctor Web + Admin | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Unassigned
2 | 395 | M09 | Trust & verification | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.1 | TRU-01 | Doctor credentialing — doctors upload qualification and registration documents for review | TRU-01.02 | API: upload documents; MyStatus; RegisterDoctor modified to VerificationStatus=Pending (not auto-practice) | New | Trust | §13 + §7.2 | Doctor credentialing | Doctors upload qualification and registration documents for review | Doctor Web + Admin | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
3 | 396 | M09 | Trust & verification | UI | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.1 | TRU-01 | Doctor credentialing — doctors upload qualification and registration documents for review | TRU-01.03 | Doctor profile credentials tab + document upload | New | Trust | §13 + §7.2 | Doctor credentialing | Doctors upload qualification and registration documents for review | Doctor Web + Admin | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Digvijay Jadhav
4 | 397 | M09 | Trust & verification | QA | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.1 | TRU-01 | Doctor credentialing — doctors upload qualification and registration documents for review | TRU-01.04 | QA: doctor without docs cannot appear in public directory (Phase 9) | Regression | Trust | §13 + §7.2 | Doctor credentialing | Doctors upload qualification and registration documents for review | Doctor Web + Admin | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
5 | 398 | M09 | Trust & verification | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.2 | TRU-02 | Verification review — Admin approves, rejects or requests further information | TRU-02.01 | Reuse DoctorVerification | New | Trust | §13 + §7.2 | Verification review | Admin approves, rejects or requests more information before they can practise on the platform | Admin Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
6 | 399 | M09 | Trust & verification | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.2 | TRU-02 | Verification review — Admin approves, rejects or requests further information | TRU-02.02 | API: Queue, {id}, Approve, Reject, RequestInfo | New | Trust | §13 + §7.2 | Verification review | Admin approves, rejects or requests more information before they can practise on the platform | Admin Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
7 | 400 | M09 | Trust & verification | UI | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.2 | TRU-02 | Verification review — Admin approves, rejects or requests further information | TRU-02.03 | /admin/doctor-credentialing and /:doctorId; verification column on users list | New | Trust | §13 + §7.2 | Verification review | Admin approves, rejects or requests more information before they can practise on the platform | Admin Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
8 | 401 | M09 | Trust & verification | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.2 | TRU-02 | Verification review — Admin approves, rejects or requests further information | TRU-02.04 | Email notify (Phase 12 SMTP already used for activation) | New Integration | Trust | §13 + §7.2 | Verification review | Admin approves, rejects or requests more information before they can practise on the platform | Admin Portal | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | EDIT HERE — this module sheet
9 | 402 | M09 | Trust & verification | QA | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.2 | TRU-02 | Verification review — Admin approves, rejects or requests further information | TRU-02.05 | QA: reject reason required; request-info reopens Pending | Regression | Trust | §13 + §7.2 | Verification review | Admin approves, rejects or requests more information before they can practise on the platform | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Pranav Bandekar
10 | 403 | M09 | Trust & verification | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.3 | TRU-03 | Verified badge — patients see which doctors have been verified | TRU-03.01 | Public doctor DTO includes isVerified | New | Trust | §13 + §2.2 | Verified badge / Credentials & verification | Patients see which doctors have been verified / Verified badge showing the doctor’s credentials are checked | Public + Patient app | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
11 | 404 | M09 | Trust & verification | UI | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.3 | TRU-03 | Verified badge — patients see which doctors have been verified | TRU-03.02 | Badge component for website (Phase 9) and patient app (Phase 16) | New | Trust | §13 + §2.2 | Verified badge / Credentials & verification | Patients see which doctors have been verified / Verified badge showing the doctor’s credentials are checked | Public + Patient app | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
12 | 405 | M09 | Trust & verification | QA | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.3 | TRU-03 | Verified badge — patients see which doctors have been verified | TRU-03.03 | QA: pending doctor has no badge | Regression | Trust | §13 + §2.2 | Verified badge / Credentials & verification | Patients see which doctors have been verified / Verified badge showing the doctor’s credentials are checked | Public + Patient app | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
13 | 406 | M09 | Trust & verification | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.4 | TRU-04 | Practice gate — only verified doctors appear to patients and take paid consultations | TRU-04.01 | Public doctor list filter VerificationStatus=Approved | New | Trust | §13 | Practice gate | Only verified doctors appear to patients and take paid consultations | Public + Payments | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
14 | 407 | M09 | Trust & verification | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.4 | TRU-04 | Practice gate — only verified doctors appear to patients and take paid consultations | TRU-04.02 | CreateConsultOrder rejects unverified doctor for patient-originated bookings | New | Trust | §13 | Practice gate | Only verified doctors appear to patients and take paid consultations | Public + Payments | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
15 | 408 | M09 | Trust & verification | QA | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.4 | TRU-04 | Practice gate — only verified doctors appear to patients and take paid consultations | TRU-04.03 | QA: reception can still book own clinic patient for unverified doctor if PRE-03 allows | Regression | Trust | §13 | Practice gate | Only verified doctors appear to patients and take paid consultations | Public + Payments | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
16 | 409 | M09 | Trust & verification | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.5 | TRU-05 | Patient reviews — patients rate and review consultations | TRU-05.01 | DB: Review (PatientAppId, Rating, Text, Status, At) | New | Trust | §13 + §2.8 | Patient reviews / Write a review | Patients rate and review consultations / Rate and review the consultation | Patient + Public | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
17 | 410 | M09 | Trust & verification | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.5 | TRU-05 | Patient reviews — patients rate and review consultations | TRU-05.02 | API: create (patient), list by doctor (public approved), doctor list own | New | Trust | §13 + §2.8 | Patient reviews / Write a review | Patients rate and review consultations / Rate and review the consultation | Patient + Public | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
18 | 411 | M09 | Trust & verification | UI | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.5 | TRU-05 | Patient reviews — patients rate and review consultations | TRU-05.03 | Public doctor profile reviews; patient app write flow Phase 16 | New | Trust | §13 + §2.8 | Patient reviews / Write a review | Patients rate and review consultations / Rate and review the consultation | Patient + Public | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
19 | 412 | M09 | Trust & verification | QA | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.5 | TRU-05 | Patient reviews — patients rate and review consultations | TRU-05.04 | QA: duplicate review blocked; incomplete visit blocked | Regression | Trust | §13 + §2.8 | Patient reviews / Write a review | Patients rate and review consultations / Rate and review the consultation | Patient + Public | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
20 | 413 | M09 | Trust & verification | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.6 | TRU-06 | Review appeal — doctors can appeal a review; patients manage reviews and raise an appeal | TRU-06.01 | DB: ReviewAppeal | New | Trust | §13 + §2.8 | Review appeal / My reviews & appeal | Doctors can appeal a review / Manage reviews and raise an appeal | Doctor + Patient + Admin | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
21 | 414 | M09 | Trust & verification | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.6 | TRU-06 | Review appeal — doctors can appeal a review; patients manage reviews and raise an appeal | TRU-06.02 | API: doctor appeal; patient list/mine; admin resolve | New | Trust | §13 + §2.8 | Review appeal / My reviews & appeal | Doctors can appeal a review / Manage reviews and raise an appeal | Doctor + Patient + Admin | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
22 | 415 | M09 | Trust & verification | UI | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.6 | TRU-06 | Review appeal — doctors can appeal a review; patients manage reviews and raise an appeal | TRU-06.03 | Doctor dashboard my-reviews; admin queue | New | Trust | §13 + §2.8 | Review appeal / My reviews & appeal | Doctors can appeal a review / Manage reviews and raise an appeal | Doctor + Patient + Admin | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
23 | 416 | M09 | Trust & verification | QA | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.6 | TRU-06 | Review appeal — doctors can appeal a review; patients manage reviews and raise an appeal | TRU-06.04 | QA: only treating doctor of that visit can appeal | Regression | Trust | §13 + §2.8 | Review appeal / My reviews & appeal | Doctors can appeal a review / Manage reviews and raise an appeal | Doctor + Patient + Admin | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
24 | 417 | M09 | Trust & verification | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.7 | TRU-07 | Ranking transparency — patients are shown why doctors are ranked as they are | TRU-07.01 | Ranking config (weights) — not a black box hardcoded sort | New | Trust | §13 + §2.2 | Ranking transparency / Ranking explanation | Patients are shown why doctors are ranked as they are / Transparent explanation of why doctors appear in a given order | Public + Patient app | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
25 | 418 | M09 | Trust & verification | Web | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.7 | TRU-07 | Ranking transparency — patients are shown why doctors are ranked as they are | TRU-07.02 | GET doctors + GET ranking-explain/{doctorId} | New | Trust | §13 + §2.2 | Ranking transparency / Ranking explanation | Patients are shown why doctors are ranked as they are / Transparent explanation of why doctors appear in a given order | Public + Patient app | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
26 | 419 | M09 | Trust & verification | UI | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.7 | TRU-07 | Ranking transparency — patients are shown why doctors are ranked as they are | TRU-07.03 | Search results: Why this order? panel | New | Trust | §13 + §2.2 | Ranking transparency / Ranking explanation | Patients are shown why doctors are ranked as they are / Transparent explanation of why doctors appear in a given order | Public + Patient app | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
27 | 420 | M09 | Trust & verification | QA | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.7 | TRU-07 | Ranking transparency — patients are shown why doctors are ranked as they are | TRU-07.04 | QA: changing weights changes order and explanation together | Regression | Trust | §13 + §2.2 | Ranking transparency / Ranking explanation | Patients are shown why doctors are ranked as they are / Transparent explanation of why doctors appear in a given order | Public + Patient app | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet

## M10_Patient_Website
M10 Patient website — 35 sub-tasks (Web 12 · UI 12 · QA 11). YELLOW = edit here (Assigned To, Frontend/Backend/Database/API/Mobile/Integration Status + Assigned). Scope Yes/No is fixed. Status N/A = that function is not in this sub-task. Master, Web/UI/Mobile/QA sheets and Dashboard follow these cells live. | [41 empty] | Live copy of 00_Employees column B — do not edit. New names appear here automatically.
Module Seq | Original Seq | Dev Module Code | Dev Module | Track | Phase | Phase Name | WBS | Main Task ID | Main Task | Sub Task ID | Sub Task | Work Type | Source Module / Area | PDF Section | PDF Feature (exact wording) | PDF Delivery Text | Application Surface | Layer | Assigned To (lead) | Frontend | Frontend Status | Frontend Assigned | Backend | Backend Status | Backend Assigned | Database | Database Status | Database Assigned | API | API Status | API Assigned | Mobile | Mobile Status | Mobile Assigned | Integration | Integration Status | Integration Assigned | Layers Remaining | Overall Status | Notes | Open Module Sheet | _EmpList
1 | 421 | M10 | Patient website | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.1 | WEB-01 | Product home page — complete public website presenting the service | WEB-01.01 | No schema | Existing Improvement | Patient Website | §4 | Product home page | Complete public website presenting the service | Patient Website | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Unassigned
2 | 422 | M10 | Patient website | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.1 | WEB-01 | Product home page — complete public website presenting the service | WEB-01.02 | Reuse public doctor/fee APIs when live | Existing Improvement | Patient Website | §4 | Product home page | Complete public website presenting the service | Patient Website | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
3 | 423 | M10 | Patient website | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.1 | WEB-01 | Product home page — complete public website presenting the service | WEB-01.03 | HomeLandingPage: book, verified doctors, pricing teaser, store badges; strip leftover job-board feel | Existing Improvement | Patient Website | §4 | Product home page | Complete public website presenting the service | Patient Website | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Digvijay Jadhav
4 | 424 | M10 | Patient website | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.1 | WEB-01 | Product home page — complete public website presenting the service | WEB-01.04 | QA: mobile viewport; deep link /book | Regression | Patient Website | §4 | Product home page | Complete public website presenting the service | Patient Website | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
5 | 425 | M10 | Patient website | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.2 | WEB-02 | Consultation & subscription pricing — transparent pricing display | WEB-02.01 | Public doctor card shows in-clinic and tele fee | Existing Improvement | Patient Website | §4 | Consultation & subscription pricing | Transparent pricing display | Patient Website | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
6 | 426 | M10 | Patient website | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.2 | WEB-02 | Consultation & subscription pricing — transparent pricing display | WEB-02.02 | /pricing remains SaaS packages for doctors; label it clearly vs patient consult fees | Existing Improvement | Patient Website | §4 | Consultation & subscription pricing | Transparent pricing display | Patient Website | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
7 | 427 | M10 | Patient website | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.2 | WEB-02 | Consultation & subscription pricing — transparent pricing display | WEB-02.03 | QA: fee matches checkout amount | Regression | Patient Website | §4 | Consultation & subscription pricing | Transparent pricing display | Patient Website | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
8 | 428 | M10 | Patient website | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.3 | WEB-03 | Doctor discovery — browse and search verified doctors | WEB-03.01 | Public doctor search indexes (from Doctor + verification + fee + schedule) | New | Patient Website | §4 + §2.2 | Doctor discovery | Browse and search verified doctors | Patient Website | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
9 | 429 | M10 | Patient website | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.3 | WEB-03 | Doctor discovery — browse and search verified doctors | WEB-03.02 | GET /api/Public/Doctors + filters + profile | New | Patient Website | §4 + §2.2 | Doctor discovery | Browse and search verified doctors | Patient Website | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Pranav Bandekar
10 | 430 | M10 | Patient website | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.3 | WEB-03 | Doctor discovery — browse and search verified doctors | WEB-03.03 | /book list + filters + doctor profile page | New | Patient Website | §4 + §2.2 | Doctor discovery | Browse and search verified doctors | Patient Website | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
11 | 431 | M10 | Patient website | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.3 | WEB-03 | Doctor discovery — browse and search verified doctors | WEB-03.04 | QA: unverified excluded; filters combine; empty state | Regression | Patient Website | §4 + §2.2 | Doctor discovery | Browse and search verified doctors | Patient Website | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
12 | 432 | M10 | Patient website | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.4 | WEB-04 | Self-service booking — book an appointment online without calling the clinic | WEB-04.01 | Reuse Patient + Appointment; BookingToken; PatientAuth OTP | New | Patient Website | §4 + §2.3 | Self-service booking | Book an appointment online without calling the clinic | Patient Website | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
13 | 433 | M10 | Patient website | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.4 | WEB-04 | Self-service booking — book an appointment online without calling the clinic | WEB-04.02 | Public: Doctors/{id}/Slots, Create, {bookingToken}; POST PatientAuth RequestOtp/VerifyOtp | New | Patient Website | §4 + §2.3 | Self-service booking | Book an appointment online without calling the clinic | Patient Website | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
14 | 434 | M10 | Patient website | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.4 | WEB-04 | Self-service booking — book an appointment online without calling the clinic | WEB-04.03 | /book/:doctorId/slots; /book/confirm; booking success | New | Patient Website | §4 + §2.3 | Self-service booking | Book an appointment online without calling the clinic | Patient Website | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
15 | 435 | M10 | Patient website | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.4 | WEB-04 | Self-service booking — book an appointment online without calling the clinic | WEB-04.04 | QA: double-book same slot; hold expiry; OTP fail; consent required | Regression | Patient Website | §4 + §2.3 | Self-service booking | Book an appointment online without calling the clinic | Patient Website | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
16 | 436 | M10 | Patient website | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.5 | WEB-05 | Online consultation payment on website — pay the fee at the time of booking | WEB-05.01 | /book/pay/:bookingId + success/failure pages | New | Patient Website | §4 + §9 | Online consultation payment | Pay the consultation fee at the time of booking | Patient Website | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | EDIT HERE — this module sheet
17 | 437 | M10 | Patient website | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.5 | WEB-05 | Online consultation payment on website — pay the fee at the time of booking | WEB-05.02 | QA: pay-at-clinic skip checkout; failed pay remains PENDING not PAID | Regression | Patient Website | §4 + §9 | Online consultation payment | Pay the consultation fee at the time of booking | Patient Website | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
18 | 438 | M10 | Patient website | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.6 | WEB-06 | Contact & enquiry form — enquiries reach the admin team and are tracked | WEB-06.01 | Reuse EnquiryDetail; add Status/AssignedTo if missing | Existing Improvement | Patient Website | §4 + §15 | Contact & enquiry form | Enquiries reach the admin team and are tracked | Patient Website + Admin | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
19 | 439 | M10 | Patient website | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.6 | WEB-06 | Contact & enquiry form — enquiries reach the admin team and are tracked | WEB-06.02 | Existing enquiry POST; admin list API if missing | Existing Improvement | Patient Website | §4 + §15 | Contact & enquiry form | Enquiries reach the admin team and are tracked | Patient Website + Admin | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
20 | 440 | M10 | Patient website | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.6 | WEB-06 | Contact & enquiry form — enquiries reach the admin team and are tracked | WEB-06.03 | /contact confirmation; /admin/enquiries inbox (not Velzon mailbox) | Existing Improvement | Patient Website | §4 + §15 | Contact & enquiry form | Enquiries reach the admin team and are tracked | Patient Website + Admin | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
21 | 441 | M10 | Patient website | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.6 | WEB-06 | Contact & enquiry form — enquiries reach the admin team and are tracked | WEB-06.04 | QA: guest submit → admin sees row | Regression | Patient Website | §4 + §15 | Contact & enquiry form | Enquiries reach the admin team and are tracked | Patient Website + Admin | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
22 | 442 | M10 | Patient website | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.7 | WEB-07 | Privacy policy — covering data protection, recording and pharmacy consent | WEB-07.01 | Replace /privacy content with signed legal copy; store PolicyVersion | Existing Improvement | Legal | §4 + §17 | Privacy policy | Covering data protection, recording and pharmacy consent | Patient Website | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
23 | 443 | M10 | Patient website | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.7 | WEB-07 | Privacy policy — covering data protection, recording and pharmacy consent | WEB-07.02 | QA: booking consent shows policy version number | Regression | Legal | §4 + §17 | Privacy policy | Covering data protection, recording and pharmacy consent | Patient Website | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
24 | 444 | M10 | Patient website | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.8 | WEB-08 | Terms of service — covering payments, refunds, telemedicine and medicine orders | WEB-08.01 | Replace /terms with signed copy; version stamp on booking/payment | Existing Improvement | Legal | §4 | Terms of service | Covering payments, refunds, telemedicine and medicine orders | Patient Website | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
25 | 445 | M10 | Patient website | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.8 | WEB-08 | Terms of service — covering payments, refunds, telemedicine and medicine orders | WEB-08.02 | QA: terms checkbox required on confirm | Regression | Legal | §4 | Terms of service | Covering payments, refunds, telemedicine and medicine orders | Patient Website | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
26 | 446 | M10 | Patient website | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.9 | WEB-09 | Doctor self-registration — doctors apply to join the platform online | WEB-09.01 | Documents via TRU-01 tables | Existing Improvement | Patient Website | §4 | Doctor self-registration | Doctors apply to join the platform online | Public | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
27 | 447 | M10 | Patient website | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.9 | WEB-09 | Doctor self-registration — doctors apply to join the platform online | WEB-09.02 | RegisterDoctor sets Pending; does not auto-activate practice for directory | Existing Improvement | Patient Website | §4 | Doctor self-registration | Doctors apply to join the platform online | Public | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
28 | 448 | M10 | Patient website | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.9 | WEB-09 | Doctor self-registration — doctors apply to join the platform online | WEB-09.03 | /register multipart docs; pending message; status page | Existing Improvement | Patient Website | §4 | Doctor self-registration | Doctors apply to join the platform online | Public | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
29 | 449 | M10 | Patient website | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.9 | WEB-09 | Doctor self-registration — doctors apply to join the platform online | WEB-09.04 | QA: register → admin queue row | Regression | Patient Website | §4 | Doctor self-registration | Doctors apply to join the platform online | Public | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
30 | 450 | M10 | Patient website | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.10 | WEB-10 | Email activation — secure account activation by email link | WEB-10.01 | Activation token TTL if missing | Existing Improvement | Auth | §4 | Email activation | Secure account activation by email link | Public | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
31 | 451 | M10 | Patient website | Web | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.10 | WEB-10 | Email activation — secure account activation by email link | WEB-10.02 | Resend activation; do not treat activation as TRU-04 gate | Existing Improvement | Auth | §4 | Email activation | Secure account activation by email link | Public | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
32 | 452 | M10 | Patient website | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.10 | WEB-10 | Email activation — secure account activation by email link | WEB-10.03 | Login activation query param UX + expiry copy | Existing Improvement | Auth | §4 | Email activation | Secure account activation by email link | Public | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
33 | 453 | M10 | Patient website | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.10 | WEB-10 | Email activation — secure account activation by email link | WEB-10.04 | QA: used link, expired link, resend | Regression | Auth | §4 | Email activation | Secure account activation by email link | Public | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
34 | 459 | M10 | Patient website | UI | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.12 | WEB-12 | Health articles — educational content to build trust and engagement | WEB-12.01 | Public articles list/detail from existing blog/news APIs | Existing Improvement | Patient Website | §2.2 | Health articles | Educational content to build trust and engagement | Patient Website + App | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
35 | 460 | M10 | Patient website | QA | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.12 | WEB-12 | Health articles — educational content to build trust and engagement | WEB-12.02 | QA: unpublished hidden | Regression | Patient Website | §2.2 | Health articles | Educational content to build trust and engagement | Patient Website + App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet

## M11_Digital_eRx
M11 Digital prescription (eRx) — 35 sub-tasks (Web 17 · UI 8 · QA 10). YELLOW = edit here (Assigned To, Frontend/Backend/Database/API/Mobile/Integration Status + Assigned). Scope Yes/No is fixed. Status N/A = that function is not in this sub-task. Master, Web/UI/Mobile/QA sheets and Dashboard follow these cells live. | [41 empty] | Live copy of 00_Employees column B — do not edit. New names appear here automatically.
Module Seq | Original Seq | Dev Module Code | Dev Module | Track | Phase | Phase Name | WBS | Main Task ID | Main Task | Sub Task ID | Sub Task | Work Type | Source Module / Area | PDF Section | PDF Feature (exact wording) | PDF Delivery Text | Application Surface | Layer | Assigned To (lead) | Frontend | Frontend Status | Frontend Assigned | Backend | Backend Status | Backend Assigned | Database | Database Status | Database Assigned | API | API Status | API Assigned | Mobile | Mobile Status | Mobile Assigned | Integration | Integration Status | Integration Assigned | Layers Remaining | Overall Status | Notes | Open Module Sheet | _EmpList
1 | 461 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.1 | ERX-01 | Potency module — every remedy carries a defined potency from a managed list, no free text | ERX-01.01 | DB: PotencyMaster; PrescriptionRemedyDetail.PotencyId | New | eRx | §11 | Potency module | Every remedy carries a defined potency, selected from a managed list — no free text | Doctor Web + Admin | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Unassigned
2 | 462 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.1 | ERX-01 | Potency module — every remedy carries a defined potency from a managed list, no free text | ERX-01.02 | API: potency DDL; extend SavePrescriptionDetail | New | eRx | §11 | Potency module | Every remedy carries a defined potency, selected from a managed list — no free text | Doctor Web + Admin | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
3 | 463 | M11 | Digital prescription (eRx) | UI | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.1 | ERX-01 | Potency module — every remedy carries a defined potency from a managed list, no free text | ERX-01.03 | Rx modal potency picker (6C, 30C, 200C, 1M…) | New | eRx | §11 | Potency module | Every remedy carries a defined potency, selected from a managed list — no free text | Doctor Web + Admin | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Digvijay Jadhav
4 | 464 | M11 | Digital prescription (eRx) | QA | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.1 | ERX-01 | Potency module — every remedy carries a defined potency from a managed list, no free text | ERX-01.04 | QA: free text potency rejected | Regression | eRx | §11 | Potency module | Every remedy carries a defined potency, selected from a managed list — no free text | Doctor Web + Admin | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
5 | 465 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.2 | ERX-02 | Dosage details — frequency, duration and instructions recorded clearly | ERX-02.01 | DB: Frequency, Duration, Instructions on remedy line | New | eRx | §11 | Dosage details | Frequency, duration and instructions recorded clearly | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
6 | 466 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.2 | ERX-02 | Dosage details — frequency, duration and instructions recorded clearly | ERX-02.02 | Extend save/get Rx APIs | New | eRx | §11 | Dosage details | Frequency, duration and instructions recorded clearly | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
7 | 467 | M11 | Digital prescription (eRx) | UI | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.2 | ERX-02 | Dosage details — frequency, duration and instructions recorded clearly | ERX-02.03 | Rx row UI for the three fields | New | eRx | §11 | Dosage details | Frequency, duration and instructions recorded clearly | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
8 | 468 | M11 | Digital prescription (eRx) | QA | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.2 | ERX-02 | Dosage details — frequency, duration and instructions recorded clearly | ERX-02.04 | QA: all three persist and print | Regression | eRx | §11 | Dosage details | Frequency, duration and instructions recorded clearly | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
9 | 469 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.3 | ERX-03 | Visit notes kept separate from the prescription — private clinical notes never appear on the prescription given to the patient or pharmacy | ERX-03.01 | Extend AppointmentHistoryNote with NoteType, IsErxExcluded | New | eRx | §11 + §5.3 | Visit notes kept separate from the prescription | The doctor’s private clinical notes never appear on the prescription given to the patient or pharmacy | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Pranav Bandekar
10 | 470 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.3 | ERX-03 | Visit notes kept separate from the prescription — private clinical notes never appear on the prescription given to the patient or pharmacy | ERX-03.02 | GET /api/Erx/ByAppointment/{id} returns snapshot without notes | New | eRx | §11 + §5.3 | Visit notes kept separate from the prescription | The doctor’s private clinical notes never appear on the prescription given to the patient or pharmacy | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
11 | 471 | M11 | Digital prescription (eRx) | UI | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.3 | ERX-03 | Visit notes kept separate from the prescription — private clinical notes never appear on the prescription given to the patient or pharmacy | ERX-03.03 | Move History Notes out of Rx modal; note types Chief complaint / Follow-up / General | New | eRx | §11 + §5.3 | Visit notes kept separate from the prescription | The doctor’s private clinical notes never appear on the prescription given to the patient or pharmacy | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
12 | 472 | M11 | Digital prescription (eRx) | QA | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.3 | ERX-03 | Visit notes kept separate from the prescription — private clinical notes never appear on the prescription given to the patient or pharmacy | ERX-03.04 | QA: print eRx vs export case PDF (doctor copy still has notes) | Regression | eRx | §11 + §5.3 | Visit notes kept separate from the prescription | The doctor’s private clinical notes never appear on the prescription given to the patient or pharmacy | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
13 | 473 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.4 | ERX-04 | Signed digital prescription — issued and locked once signed, so it cannot be altered afterwards | ERX-04.01 | DB: ErxSnapshot, ErxSnapshotItem (codes+names stored; patient API returns codes until pharmacy accept) | New | eRx | §11 + §2.5 + §5.3 | Signed digital prescription | Issued and locked once signed, so it cannot be altered afterwards / Official prescription issued by the doctor | Doctor Web | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
14 | 474 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.4 | ERX-04 | Signed digital prescription — issued and locked once signed, so it cannot be altered afterwards | ERX-04.02 | API: SignErx; GetErx; reject mutate of signed snapshot | New | eRx | §11 + §2.5 + §5.3 | Signed digital prescription | Issued and locked once signed, so it cannot be altered afterwards / Official prescription issued by the doctor | Doctor Web | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
15 | 475 | M11 | Digital prescription (eRx) | UI | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.4 | ERX-04 | Signed digital prescription — issued and locked once signed, so it cannot be altered afterwards | ERX-04.03 | Sign button; locked badge on board header | New | eRx | §11 + §2.5 + §5.3 | Signed digital prescription | Issued and locked once signed, so it cannot be altered afterwards / Official prescription issued by the doctor | Doctor Web | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
16 | 476 | M11 | Digital prescription (eRx) | QA | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.4 | ERX-04 | Signed digital prescription — issued and locked once signed, so it cannot be altered afterwards | ERX-04.04 | QA: POST save after sign does not change snapshot | Regression | eRx | §11 + §2.5 + §5.3 | Signed digital prescription | Issued and locked once signed, so it cannot be altered afterwards / Official prescription issued by the doctor | Doctor Web | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
17 | 477 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.5 | ERX-05 | Prescription history — every prescription stored against the patient and visit | ERX-05.01 | GET history by patient; by appointment | New | eRx | §11 | Prescription history | Every prescription stored against the patient and visit | Doctor + Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
18 | 478 | M11 | Digital prescription (eRx) | UI | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.5 | ERX-05 | Prescription history — every prescription stored against the patient and visit | ERX-05.02 | Doctor history panel lists signed eRx; patient timeline in Phase 16 | New | eRx | §11 | Prescription history | Every prescription stored against the patient and visit | Doctor + Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
19 | 479 | M11 | Digital prescription (eRx) | QA | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.5 | ERX-05 | Prescription history — every prescription stored against the patient and visit | ERX-05.03 | QA: another doctor 403 | Regression | eRx | §11 | Prescription history | Every prescription stored against the patient and visit | Doctor + Patient | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
20 | 480 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.6 | ERX-06 | Patient view of prescription in app — patient sees the prescription immediately (codes until pharmacy accept) | ERX-06.01 | Patient-authorised GET Erx; apply code protection ERX-08 | New | eRx | §11 + §2.5 | Patient view in app | Patient sees the prescription immediately in the app | Patient App + Website | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
21 | 481 | M11 | Digital prescription (eRx) | UI | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.6 | ERX-06 | Patient view of prescription in app — patient sees the prescription immediately (codes until pharmacy accept) | ERX-06.02 | Web confirmation/records page can show the same payload before the app exists | New | eRx | §11 + §2.5 | Patient view in app | Patient sees the prescription immediately in the app | Patient App + Website | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
22 | 482 | M11 | Digital prescription (eRx) | QA | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.6 | ERX-06 | Patient view of prescription in app — patient sees the prescription immediately (codes until pharmacy accept) | ERX-06.03 | QA: doctor names vs patient codes differ until pharmacy OTP accept | Regression | eRx | §11 + §2.5 | Patient view in app | Patient sees the prescription immediately in the app | Patient App + Website | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
23 | 483 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.7 | ERX-07 | Print & PDF — printable and downloadable prescription | ERX-07.01 | PDF renderer from ErxSnapshot; store via SEC-09 | New | eRx | §11 | Print & PDF | Printable and downloadable prescription | Doctor + Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
24 | 484 | M11 | Digital prescription (eRx) | UI | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.7 | ERX-07 | Print & PDF — printable and downloadable prescription | ERX-07.02 | Print/Download on doctor board and later patient app | New | eRx | §11 | Print & PDF | Printable and downloadable prescription | Doctor + Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
25 | 485 | M11 | Digital prescription (eRx) | QA | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.7 | ERX-07 | Print & PDF — printable and downloadable prescription | ERX-07.03 | QA: notes leak test on patient PDF | Regression | eRx | §11 | Print & PDF | Printable and downloadable prescription | Doctor + Patient | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
26 | 486 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.8 | ERX-08 | Remedy code protection — patient sees remedy codes rather than names until a licensed pharmacy accepts the order | ERX-08.01 | Assign stable remedy codes on snapshot items | New | eRx | §11 | Remedy code protection | The patient sees remedy codes rather than remedy names until a licensed pharmacy accepts the order | Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
27 | 487 | M11 | Digital prescription (eRx) | QA | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.8 | ERX-08 | Remedy code protection — patient sees remedy codes rather than names until a licensed pharmacy accepts the order | ERX-08.02 | Patient serializer tests (contract tests) | Regression | eRx | §11 | Remedy code protection | The patient sees remedy codes rather than remedy names until a licensed pharmacy accepts the order | Patient | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
28 | 488 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.9 | ERX-09 | Reveal on pharmacy acceptance — names and price revealed; payment QR or link generated (implemented with HomeoMeds; contract now) | ERX-09.01 | API contract: AcceptOrder(OTP) → reveal names; Quote → PayQR | New | eRx | §11 + §12 | Reveal on pharmacy acceptance | Once a pharmacy accepts and verifies by OTP, the remedy names and price are revealed and a payment QR or link is generated | Patient + Pharmacy | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
29 | 489 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.9 | ERX-09 | Reveal on pharmacy acceptance — names and price revealed; payment QR or link generated (implemented with HomeoMeds; contract now) | ERX-09.02 | Implement fully with MED-* in Phase 14 — do not reveal names from doctor sign alone | New | eRx | §11 + §12 | Reveal on pharmacy acceptance | Once a pharmacy accepts and verifies by OTP, the remedy names and price are revealed and a payment QR or link is generated | Patient + Pharmacy | Architecture | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
30 | 490 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.10 | ERX-10 | Repeat prescription / refill — patient requests; doctor approves or rejects from the mobile app (inbox on web too) | ERX-10.01 | DB: RefillRequest | New | eRx | §11 + §3 + §2.7 | Repeat prescription / refill | Patient requests a refill; doctor approves or rejects from the mobile app | Patient + Doctor mobile + Doctor web | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
31 | 491 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.10 | ERX-10 | Repeat prescription / refill — patient requests; doctor approves or rejects from the mobile app (inbox on web too) | ERX-10.02 | API: patient request; doctor inbox; approve/reject | New | eRx | §11 + §3 + §2.7 | Repeat prescription / refill | Patient requests a refill; doctor approves or rejects from the mobile app | Patient + Doctor mobile + Doctor web | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
32 | 492 | M11 | Digital prescription (eRx) | UI | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.10 | ERX-10 | Repeat prescription / refill — patient requests; doctor approves or rejects from the mobile app (inbox on web too) | ERX-10.03 | Doctor web inbox; doctor app in Phase 17; patient app in Phase 16 | New | eRx | §11 + §3 + §2.7 | Repeat prescription / refill | Patient requests a refill; doctor approves or rejects from the mobile app | Patient + Doctor mobile + Doctor web | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
33 | 493 | M11 | Digital prescription (eRx) | QA | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.10 | ERX-10 | Repeat prescription / refill — patient requests; doctor approves or rejects from the mobile app (inbox on web too) | ERX-10.04 | QA: cannot refill unsigned/locked-expired per policy | Regression | eRx | §11 + §3 + §2.7 | Repeat prescription / refill | Patient requests a refill; doctor approves or rejects from the mobile app | Patient + Doctor mobile + Doctor web | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
34 | 494 | M11 | Digital prescription (eRx) | Web | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.11 | ERX-11 | Lab orders alongside the prescription (keep existing labs on eRx snapshot) | ERX-11.01 | Copy lab orders into ErxSnapshot on sign | Existing Improvement | eRx | §11 | Lab orders | Tests ordered alongside the prescription | Doctor Web | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
35 | 495 | M11 | Digital prescription (eRx) | QA | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.11 | ERX-11 | Lab orders alongside the prescription (keep existing labs on eRx snapshot) | ERX-11.02 | QA: labs visible on eRx; result values not required on patient copy | Regression | eRx | §11 | Lab orders | Tests ordered alongside the prescription | Doctor Web | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet

## M12_Telemedicine
M12 Telemedicine — 44 sub-tasks (Web 21 · UI 11 · QA 12). YELLOW = edit here (Assigned To, Frontend/Backend/Database/API/Mobile/Integration Status + Assigned). Scope Yes/No is fixed. Status N/A = that function is not in this sub-task. Master, Web/UI/Mobile/QA sheets and Dashboard follow these cells live. | [41 empty] | Live copy of 00_Employees column B — do not edit. New names appear here automatically.
Module Seq | Original Seq | Dev Module Code | Dev Module | Track | Phase | Phase Name | WBS | Main Task ID | Main Task | Sub Task ID | Sub Task | Work Type | Source Module / Area | PDF Section | PDF Feature (exact wording) | PDF Delivery Text | Application Surface | Layer | Assigned To (lead) | Frontend | Frontend Status | Frontend Assigned | Backend | Backend Status | Backend Assigned | Database | Database Status | Database Assigned | API | API Status | API Assigned | Mobile | Mobile Status | Mobile Assigned | Integration | Integration Status | Integration Assigned | Layers Remaining | Overall Status | Notes | Open Module Sheet | _EmpList
1 | 496 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.1 | TEL-01 | Doctor availability — online or offline status and working hours | TEL-01.01 | DB: TeleAvailability (Online/Offline, LastHeartbeat) | New | Telemedicine | §10 + §3 | Doctor availability | Doctor sets online or offline status and working hours | Doctor Web + Doctor App | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Unassigned
2 | 497 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.1 | TEL-01 | Doctor availability — online or offline status and working hours | TEL-01.02 | API: SET/GET availability; public GET by doctorId | New | Telemedicine | §10 + §3 | Doctor availability | Doctor sets online or offline status and working hours | Doctor Web + Doctor App | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
3 | 498 | M12 | Telemedicine | UI | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.1 | TEL-01 | Doctor availability — online or offline status and working hours | TEL-01.03 | Dashboard toggle Online for teleconsult | New | Telemedicine | §10 + §3 | Doctor availability | Doctor sets online or offline status and working hours | Doctor Web + Doctor App | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Digvijay Jadhav
4 | 499 | M12 | Telemedicine | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.1 | TEL-01 | Doctor availability — online or offline status and working hours | TEL-01.04 | QA: heartbeat expiry sets offline | Regression | Telemedicine | §10 + §3 | Doctor availability | Doctor sets online or offline status and working hours | Doctor Web + Doctor App | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
5 | 500 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.2 | TEL-02 | Telemedicine waiting queue — who is waiting, how long, whether they have paid | TEL-02.01 | Queue query on E-CONSULT + PaymentStatus + join time | New | Telemedicine | §10 + §3 | Telemedicine waiting queue | Doctor sees who is waiting, for how long, and whether they have paid | Doctor Web + App | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
6 | 501 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.2 | TEL-02 | Telemedicine waiting queue — who is waiting, how long, whether they have paid | TEL-02.02 | GET Tele/Queue; POST start session | New | Telemedicine | §10 + §3 | Telemedicine waiting queue | Doctor sees who is waiting, for how long, and whether they have paid | Doctor Web + App | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
7 | 502 | M12 | Telemedicine | UI | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.2 | TEL-02 | Telemedicine waiting queue — who is waiting, how long, whether they have paid | TEL-02.03 | Dedicated Tele queue on dashboard (beyond E-CONSULT list) | New | Telemedicine | §10 + §3 | Telemedicine waiting queue | Doctor sees who is waiting, for how long, and whether they have paid | Doctor Web + App | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
8 | 503 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.2 | TEL-02 | Telemedicine waiting queue — who is waiting, how long, whether they have paid | TEL-02.04 | SignalR/poll | New Integration | Telemedicine | §10 + §3 | Telemedicine waiting queue | Doctor sees who is waiting, for how long, and whether they have paid | Doctor Web + App | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | EDIT HERE — this module sheet
9 | 504 | M12 | Telemedicine | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.2 | TEL-02 | Telemedicine waiting queue — who is waiting, how long, whether they have paid | TEL-02.05 | QA: wait time increases; paid badge matches PAY-08 | Regression | Telemedicine | §10 + §3 | Telemedicine waiting queue | Doctor sees who is waiting, for how long, and whether they have paid | Doctor Web + App | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Pranav Bandekar
10 | 505 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.3 | TEL-03 | Video consultation in browser — doctor consults directly from the web portal | TEL-03.01 | DB: TeleSession (PatientAppId, RoomId, Status) | New | Telemedicine | §10 | Video consultation in browser | Doctor consults directly from the web portal | Doctor Web Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
11 | 506 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.3 | TEL-03 | Video consultation in browser — doctor consults directly from the web portal | TEL-03.02 | API: create/end session; vendor tokens | New | Telemedicine | §10 | Video consultation in browser | Doctor consults directly from the web portal | Doctor Web Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
12 | 507 | M12 | Telemedicine | UI | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.3 | TEL-03 | Video consultation in browser — doctor consults directly from the web portal | TEL-03.03 | Full-page video room mute/end | New | Telemedicine | §10 | Video consultation in browser | Doctor consults directly from the web portal | Doctor Web Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
13 | 508 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.3 | TEL-03 | Video consultation in browser — doctor consults directly from the web portal | TEL-03.04 | Video SDK (Agora/Twilio/Daily) | New Integration | Telemedicine | §10 | Video consultation in browser | Doctor consults directly from the web portal | Doctor Web Portal | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | EDIT HERE — this module sheet
14 | 509 | M12 | Telemedicine | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.3 | TEL-03 | Video consultation in browser — doctor consults directly from the web portal | TEL-03.05 | QA: replace WhatsApp alert; session ends write timestamp | Regression | Telemedicine | §10 | Video consultation in browser | Doctor consults directly from the web portal | Doctor Web Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
15 | 510 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.4 | TEL-04 | Video consultation on mobile — doctor and patient both consult from the app (apps in 16–17; same session tokens) | TEL-04.01 | Token API must be client-agnostic (web and mobile) | New | Telemedicine | §10 + §2.4 + §3 | Video consultation on mobile | Doctor and patient both consult from the app / Face-to-face consultation from home / Start the video or audio consultation from the phone | Patient App + Doctor App | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
16 | 511 | M12 | Telemedicine | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.4 | TEL-04 | Video consultation on mobile — doctor and patient both consult from the app (apps in 16–17; same session tokens) | TEL-04.02 | Contract tests: token TTL, room id = session id | Regression | Telemedicine | §10 + §2.4 + §3 | Video consultation on mobile | Doctor and patient both consult from the app / Face-to-face consultation from home / Start the video or audio consultation from the phone | Patient App + Doctor App | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
17 | 512 | M12 | Telemedicine | UI | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.5 | TEL-05 | Device check — camera, microphone and connection tested before joining | TEL-05.01 | Shared device-check component (web); mobile equivalent in Phase 16 | New | Telemedicine | §10 + §2.4 | Device check | Camera, microphone and connection tested before joining | Doctor Web + Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
18 | 513 | M12 | Telemedicine | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.5 | TEL-05 | Device check — camera, microphone and connection tested before joining | TEL-05.02 | QA: deny camera permission → clear guidance | Regression | Telemedicine | §10 + §2.4 | Device check | Camera, microphone and connection tested before joining | Doctor Web + Patient | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
19 | 514 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.6 | TEL-06 | Waiting room — patient waits with live status until the doctor joins | TEL-06.01 | Session status events | New | Telemedicine | §10 + §2.4 | Waiting room | Patient waits with live status / Wait with live status until the doctor joins | Patient | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
20 | 515 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.6 | TEL-06 | Waiting room — patient waits with live status until the doctor joins | TEL-06.02 | GET session status for patient token | New | Telemedicine | §10 + §2.4 | Waiting room | Patient waits with live status / Wait with live status until the doctor joins | Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
21 | 516 | M12 | Telemedicine | UI | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.6 | TEL-06 | Waiting room — patient waits with live status until the doctor joins | TEL-06.03 | Waiting room UI on web (and app later) | New | Telemedicine | §10 + §2.4 | Waiting room | Patient waits with live status / Wait with live status until the doctor joins | Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
22 | 517 | M12 | Telemedicine | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.6 | TEL-06 | Waiting room — patient waits with live status until the doctor joins | TEL-06.04 | QA: doctor join transitions patient into the call | Regression | Telemedicine | §10 + §2.4 | Waiting room | Patient waits with live status / Wait with live status until the doctor joins | Patient | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
23 | 518 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.7 | TEL-07 | Recording consent — consent captured before the consultation; no recording without it | TEL-07.01 | Write ConsentRecord TeleRecording; TeleConsentLog events | New | Telemedicine | §10 + §2.4 + §17 | Recording consent | Consent captured before the consultation; no recording without it / Explicit consent requested before any recording | Patient + Doctor | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
24 | 519 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.7 | TEL-07 | Recording consent — consent captured before the consultation; no recording without it | TEL-07.02 | API: capture consent; session.recordAllowed | New | Telemedicine | §10 + §2.4 + §17 | Recording consent | Consent captured before the consultation; no recording without it / Explicit consent requested before any recording | Patient + Doctor | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
25 | 520 | M12 | Telemedicine | UI | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.7 | TEL-07 | Recording consent — consent captured before the consultation; no recording without it | TEL-07.03 | Pre-join modal both sides | New | Telemedicine | §10 + §2.4 + §17 | Recording consent | Consent captured before the consultation; no recording without it / Explicit consent requested before any recording | Patient + Doctor | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
26 | 521 | M12 | Telemedicine | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.7 | TEL-07 | Recording consent — consent captured before the consultation; no recording without it | TEL-07.04 | QA: decline → no record; audit row still written | Regression | Telemedicine | §10 + §2.4 + §17 | Recording consent | Consent captured before the consultation; no recording without it / Explicit consent requested before any recording | Patient + Doctor | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
27 | 522 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.8 | TEL-08 | Rejoin after dropped call — either side can rejoin the same consultation | TEL-08.01 | API: Rejoin issues token if Status=Active | New | Telemedicine | §10 + §2.4 | Rejoin after dropped call | Either side can rejoin the same consultation / Rejoin the same consultation if the connection drops | Doctor + Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
28 | 523 | M12 | Telemedicine | UI | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.8 | TEL-08 | Rejoin after dropped call — either side can rejoin the same consultation | TEL-08.02 | UI Rejoin on doctor dashboard and patient waiting/call fail | New | Telemedicine | §10 + §2.4 | Rejoin after dropped call | Either side can rejoin the same consultation / Rejoin the same consultation if the connection drops | Doctor + Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
29 | 524 | M12 | Telemedicine | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.8 | TEL-08 | Rejoin after dropped call — either side can rejoin the same consultation | TEL-08.03 | QA: after End, rejoin 409 | Regression | Telemedicine | §10 + §2.4 | Rejoin after dropped call | Either side can rejoin the same consultation / Rejoin the same consultation if the connection drops | Doctor + Patient | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
30 | 525 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.9 | TEL-09 | Join failure handling — clear fallback if the call cannot connect, with options to retry | TEL-09.01 | Standardise join error codes; log TeleSessionEvent | New | Telemedicine | §10 + §2.4 | Join failure handling / Fallback & join failure handling | Clear fallback if the call cannot connect / Clear guidance if the call fails, with options to retry | Doctor + Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
31 | 526 | M12 | Telemedicine | UI | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.9 | TEL-09 | Join failure handling — clear fallback if the call cannot connect, with options to retry | TEL-09.02 | Fallback UI: retry, rejoin, contact support | New | Telemedicine | §10 + §2.4 | Join failure handling / Fallback & join failure handling | Clear fallback if the call cannot connect / Clear guidance if the call fails, with options to retry | Doctor + Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
32 | 527 | M12 | Telemedicine | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.9 | TEL-09 | Join failure handling — clear fallback if the call cannot connect, with options to retry | TEL-09.03 | QA: simulated token fail | Regression | Telemedicine | §10 + §2.4 | Join failure handling / Fallback & join failure handling | Clear fallback if the call cannot connect / Clear guidance if the call fails, with options to retry | Doctor + Patient | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
33 | 528 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.10 | TEL-10 | Case-linked chat — chat attached to the consultation record, not a loose message thread | TEL-10.01 | DB: TeleChatMessage (SessionId, PatientAppId, Body, At) | New | Telemedicine | §10 + §2.4 | Case-linked chat | Chat attached to the consultation record / Chat tied to the consultation, not a loose message thread | Doctor + Patient | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
34 | 529 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.10 | TEL-10 | Case-linked chat — chat attached to the consultation record, not a loose message thread | TEL-10.02 | API: post/list; doctor and patient only | New | Telemedicine | §10 + §2.4 | Case-linked chat | Chat attached to the consultation record / Chat tied to the consultation, not a loose message thread | Doctor + Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
35 | 530 | M12 | Telemedicine | UI | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.10 | TEL-10 | Case-linked chat — chat attached to the consultation record, not a loose message thread | TEL-10.03 | In-room chat panel | New | Telemedicine | §10 + §2.4 | Case-linked chat | Chat attached to the consultation record / Chat tied to the consultation, not a loose message thread | Doctor + Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
36 | 531 | M12 | Telemedicine | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.10 | TEL-10 | Case-linked chat — chat attached to the consultation record, not a loose message thread | TEL-10.04 | QA: IDOR other session 403 | Regression | Telemedicine | §10 + §2.4 | Case-linked chat | Chat attached to the consultation record / Chat tied to the consultation, not a loose message thread | Doctor + Patient | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
37 | 532 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.11 | TEL-11 | Consultation summary — issued to the patient at the end of the call | TEL-11.01 | DB: ConsultationSummary (PatientAppId, Text, At) | New | Telemedicine | §10 + §2.4 | Consultation summary | Issued to the patient at the end of the call / Written summary available immediately after the call | Patient + Doctor | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
38 | 533 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.11 | TEL-11 | Consultation summary — issued to the patient at the end of the call | TEL-11.02 | API: doctor PUT; patient GET | New | Telemedicine | §10 + §2.4 | Consultation summary | Issued to the patient at the end of the call / Written summary available immediately after the call | Patient + Doctor | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
39 | 534 | M12 | Telemedicine | UI | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.11 | TEL-11 | Consultation summary — issued to the patient at the end of the call | TEL-11.03 | Post-call summary form; patient view | New | Telemedicine | §10 + §2.4 | Consultation summary | Issued to the patient at the end of the call / Written summary available immediately after the call | Patient + Doctor | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
40 | 535 | M12 | Telemedicine | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.11 | TEL-11 | Consultation summary — issued to the patient at the end of the call | TEL-11.04 | QA: private notes not copied into summary by default | Regression | Telemedicine | §10 + §2.4 | Consultation summary | Issued to the patient at the end of the call / Written summary available immediately after the call | Patient + Doctor | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
41 | 536 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.12 | TEL-12 | Instant consultation — patient requests an immediate consultation with an available doctor | TEL-12.01 | DB: InstantConsultRequest, DoctorOffer | New | Telemedicine | §10 + §2.3 | Instant consultation / Instant consult request / Queue & doctor offer | Patient can request an immediate consultation with an available doctor / See position in queue and accept an offered doctor | Patient + Doctor | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
42 | 537 | M12 | Telemedicine | Web | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.12 | TEL-12 | Instant consultation — patient requests an immediate consultation with an available doctor | TEL-12.02 | API: request, match, offer, accept, queue position | New | Telemedicine | §10 + §2.3 | Instant consultation / Instant consult request / Queue & doctor offer | Patient can request an immediate consultation with an available doctor / See position in queue and accept an offered doctor | Patient + Doctor | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
43 | 538 | M12 | Telemedicine | UI | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.12 | TEL-12 | Instant consultation — patient requests an immediate consultation with an available doctor | TEL-12.03 | Patient instant CTA; doctor offer banner | New | Telemedicine | §10 + §2.3 | Instant consultation / Instant consult request / Queue & doctor offer | Patient can request an immediate consultation with an available doctor / See position in queue and accept an offered doctor | Patient + Doctor | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
44 | 539 | M12 | Telemedicine | QA | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.12 | TEL-12 | Instant consultation — patient requests an immediate consultation with an available doctor | TEL-12.04 | QA: no online doctor → empty state; surcharge on checkout | Regression | Telemedicine | §10 + §2.3 | Instant consultation / Instant consult request / Queue & doctor offer | Patient can request an immediate consultation with an available doctor / See position in queue and accept an offered doctor | Patient + Doctor | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet

## M13_Communications
M13 Communications — 22 sub-tasks (Web 12 · UI 5 · QA 5). YELLOW = edit here (Assigned To, Frontend/Backend/Database/API/Mobile/Integration Status + Assigned). Scope Yes/No is fixed. Status N/A = that function is not in this sub-task. Master, Web/UI/Mobile/QA sheets and Dashboard follow these cells live. | [41 empty] | Live copy of 00_Employees column B — do not edit. New names appear here automatically.
Module Seq | Original Seq | Dev Module Code | Dev Module | Track | Phase | Phase Name | WBS | Main Task ID | Main Task | Sub Task ID | Sub Task | Work Type | Source Module / Area | PDF Section | PDF Feature (exact wording) | PDF Delivery Text | Application Surface | Layer | Assigned To (lead) | Frontend | Frontend Status | Frontend Assigned | Backend | Backend Status | Backend Assigned | Database | Database Status | Database Assigned | API | API Status | API Assigned | Mobile | Mobile Status | Mobile Assigned | Integration | Integration Status | Integration Assigned | Layers Remaining | Overall Status | Notes | Open Module Sheet | _EmpList
1 | 540 | M13 | Communications | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.1 | COM-01 | SMS — appointment confirmation, registration confirmation, doctor-unavailable, OTP, reschedule and cancellation | COM-01.01 | DB: SmsTemplate, SmsMessageLog; Patient.SmsOptOut | New | Notifications | §14 | SMS | Appointment confirmation, registration confirmation, doctor-unavailable notice, OTP, reschedule and cancellation alerts | Shared | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Unassigned
2 | 541 | M13 | Communications | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.1 | COM-01 | SMS — appointment confirmation, registration confirmation, doctor-unavailable, OTP, reschedule and cancellation | COM-01.02 | API: Templates CRUD; Send; History; event worker | New | Notifications | §14 | SMS | Appointment confirmation, registration confirmation, doctor-unavailable notice, OTP, reschedule and cancellation alerts | Shared | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
3 | 542 | M13 | Communications | UI | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.1 | COM-01 | SMS — appointment confirmation, registration confirmation, doctor-unavailable, OTP, reschedule and cancellation | COM-01.03 | Doctor /doctor/sms enable-per-event; admin templates | New | Notifications | §14 | SMS | Appointment confirmation, registration confirmation, doctor-unavailable notice, OTP, reschedule and cancellation alerts | Shared | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Digvijay Jadhav
4 | 543 | M13 | Communications | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.1 | COM-01 | SMS — appointment confirmation, registration confirmation, doctor-unavailable, OTP, reschedule and cancellation | COM-01.04 | MSG91/Twilio/etc. from PRE-03 | New Integration | Notifications | §14 | SMS | Appointment confirmation, registration confirmation, doctor-unavailable notice, OTP, reschedule and cancellation alerts | Shared | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
5 | 544 | M13 | Communications | QA | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.1 | COM-01 | SMS — appointment confirmation, registration confirmation, doctor-unavailable, OTP, reschedule and cancellation | COM-01.05 | QA: OTP SMS; reschedule old→new; cancel; doctor unavailable; opt-out honored | Regression | Notifications | §14 | SMS | Appointment confirmation, registration confirmation, doctor-unavailable notice, OTP, reschedule and cancellation alerts | Shared | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
6 | 545 | M13 | Communications | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.2 | COM-02 | WhatsApp — templates, offers, health tips and bulk messaging with delivery reports and opt-out (complete remaining ~50%) | COM-02.01 | Extend WhatsApp log if delivery receipts not stored | Existing Improvement | Notifications | §14 | WhatsApp | Templates, offers, health tips and bulk messaging to patients, with delivery reports and opt-out | Doctor Web | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
7 | 546 | M13 | Communications | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.2 | COM-02 | WhatsApp — templates, offers, health tips and bulk messaging with delivery reports and opt-out (complete remaining ~50%) | COM-02.02 | Finish bulk worker + receipt webhook | Existing Improvement | Notifications | §14 | WhatsApp | Templates, offers, health tips and bulk messaging to patients, with delivery reports and opt-out | Doctor Web | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
8 | 547 | M13 | Communications | UI | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.2 | COM-02 | WhatsApp — templates, offers, health tips and bulk messaging with delivery reports and opt-out (complete remaining ~50%) | COM-02.03 | WhatsAppModal: campaign status, failures, opt-out | Existing Improvement | Notifications | §14 | WhatsApp | Templates, offers, health tips and bulk messaging to patients, with delivery reports and opt-out | Doctor Web | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
9 | 548 | M13 | Communications | QA | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.2 | COM-02 | WhatsApp — templates, offers, health tips and bulk messaging with delivery reports and opt-out (complete remaining ~50%) | COM-02.04 | QA: opt-in required; template rejected state | Regression | Notifications | §14 | WhatsApp | Templates, offers, health tips and bulk messaging to patients, with delivery reports and opt-out | Doctor Web | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Pranav Bandekar
10 | 549 | M13 | Communications | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.3 | COM-03 | Push notifications — booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests | COM-03.01 | DB: DeviceToken, AppNotification | New | Notifications | §14 + §2.9 + §3 | Push notifications | Booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests / Patient waiting, new booking, reschedule, cancellation, refill request, payment received | Patient App + Doctor App | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
11 | 550 | M13 | Communications | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.3 | COM-03 | Push notifications — booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests | COM-03.02 | API: Devices/Register; Notifications/Send; list | New | Notifications | §14 + §2.9 + §3 | Push notifications | Booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests / Patient waiting, new booking, reschedule, cancellation, refill request, payment received | Patient App + Doctor App | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
12 | 551 | M13 | Communications | UI | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.3 | COM-03 | Push notifications — booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests | COM-03.03 | Server event hooks (apps consume in 16–17) | New | Notifications | §14 + §2.9 + §3 | Push notifications | Booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests / Patient waiting, new booking, reschedule, cancellation, refill request, payment received | Patient App + Doctor App | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
13 | 552 | M13 | Communications | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.3 | COM-03 | Push notifications — booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests | COM-03.04 | FCM + APNs | New Integration | Notifications | §14 + §2.9 + §3 | Push notifications | Booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests / Patient waiting, new booking, reschedule, cancellation, refill request, payment received | Patient App + Doctor App | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | EDIT HERE — this module sheet
14 | 553 | M13 | Communications | QA | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.3 | COM-03 | Push notifications — booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests | COM-03.05 | QA: doctor and patient payloads isolated; token refresh | Regression | Notifications | §14 + §2.9 + §3 | Push notifications | Booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests / Patient waiting, new booking, reschedule, cancellation, refill request, payment received | Patient App + Doctor App | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
15 | 554 | M13 | Communications | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.4 | COM-04 | Email — registration, activation, password reset, invoices and receipts | COM-04.01 | EmailMessageLog if missing | Existing Improvement | Notifications | §14 | Email | Registration, activation, password reset, invoices and receipts | Shared | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
16 | 555 | M13 | Communications | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.4 | COM-04 | Email — registration, activation, password reset, invoices and receipts | COM-04.02 | Send invoice/receipt email on PAID; keep activation/reset | Existing Improvement | Notifications | §14 | Email | Registration, activation, password reset, invoices and receipts | Shared | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
17 | 556 | M13 | Communications | UI | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.4 | COM-04 | Email — registration, activation, password reset, invoices and receipts | COM-04.03 | No new public page — transactional only | Existing Improvement | Notifications | §14 | Email | Registration, activation, password reset, invoices and receipts | Shared | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
18 | 557 | M13 | Communications | QA | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.4 | COM-04 | Email — registration, activation, password reset, invoices and receipts | COM-04.04 | QA: reset still has no plaintext password; invoice attached | Regression | Notifications | §14 | Email | Registration, activation, password reset, invoices and receipts | Shared | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
19 | 558 | M13 | Communications | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.5 | COM-05 | In-app notification centre — all alerts collected in one place for patients and doctors | COM-05.01 | Reuse AppNotification | New | Notifications | §14 + §2.8 | In-app notification centre / Notifications centre | All alerts collected in one place for patients and doctors / All alerts in one place | Patient App + Doctor Web/App | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
20 | 559 | M13 | Communications | Web | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.5 | COM-05 | In-app notification centre — all alerts collected in one place for patients and doctors | COM-05.02 | GET/PATCH notifications | New | Notifications | §14 + §2.8 | In-app notification centre / Notifications centre | All alerts collected in one place for patients and doctors / All alerts in one place | Patient App + Doctor Web/App | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
21 | 560 | M13 | Communications | UI | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.5 | COM-05 | In-app notification centre — all alerts collected in one place for patients and doctors | COM-05.03 | Doctor web bell; patient/doctor app centres in 16–17 | New | Notifications | §14 + §2.8 | In-app notification centre / Notifications centre | All alerts collected in one place for patients and doctors / All alerts in one place | Patient App + Doctor Web/App | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
22 | 561 | M13 | Communications | QA | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.5 | COM-05 | In-app notification centre — all alerts collected in one place for patients and doctors | COM-05.04 | QA: mark read; empty state; not Velzon demo route | Regression | Notifications | §14 + §2.8 | In-app notification centre / Notifications centre | All alerts collected in one place for patients and doctors / All alerts in one place | Patient App + Doctor Web/App | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet

## M14_Support
M14 Support & help desk — 24 sub-tasks (Web 10 · UI 7 · QA 7). YELLOW = edit here (Assigned To, Frontend/Backend/Database/API/Mobile/Integration Status + Assigned). Scope Yes/No is fixed. Status N/A = that function is not in this sub-task. Master, Web/UI/Mobile/QA sheets and Dashboard follow these cells live. | [41 empty] | Live copy of 00_Employees column B — do not edit. New names appear here automatically.
Module Seq | Original Seq | Dev Module Code | Dev Module | Track | Phase | Phase Name | WBS | Main Task ID | Main Task | Sub Task ID | Sub Task | Work Type | Source Module / Area | PDF Section | PDF Feature (exact wording) | PDF Delivery Text | Application Surface | Layer | Assigned To (lead) | Frontend | Frontend Status | Frontend Assigned | Backend | Backend Status | Backend Assigned | Database | Database Status | Database Assigned | API | API Status | API Assigned | Mobile | Mobile Status | Mobile Assigned | Integration | Integration Status | Integration Assigned | Layers Remaining | Overall Status | Notes | Open Module Sheet | _EmpList
1 | 562 | M14 | Support & help desk | Web | 13 | Phase 13 — Support & help desk (PDF §15) | 13.1 | SUP-01 | Patient support tickets — patients raise issues from the app and track them | SUP-01.01 | DB: SupportTicket, SupportTicketMessage, SupportTicketAttachment | New | Support | §15 + §2.9 | Patient support tickets / Help centre & support tickets | Patients raise issues from the app and track them to resolution | Patient App + Admin | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Unassigned
2 | 563 | M14 | Support & help desk | Web | 13 | Phase 13 — Support & help desk (PDF §15) | 13.1 | SUP-01 | Patient support tickets — patients raise issues from the app and track them | SUP-01.02 | API: create/list/mine for patient | New | Support | §15 + §2.9 | Patient support tickets / Help centre & support tickets | Patients raise issues from the app and track them to resolution | Patient App + Admin | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
3 | 564 | M14 | Support & help desk | UI | 13 | Phase 13 — Support & help desk (PDF §15) | 13.1 | SUP-01 | Patient support tickets — patients raise issues from the app and track them | SUP-01.03 | Patient app screens in Phase 16; web help optional | New | Support | §15 + §2.9 | Patient support tickets / Help centre & support tickets | Patients raise issues from the app and track them to resolution | Patient App + Admin | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Digvijay Jadhav
4 | 565 | M14 | Support & help desk | QA | 13 | Phase 13 — Support & help desk (PDF §15) | 13.1 | SUP-01 | Patient support tickets — patients raise issues from the app and track them | SUP-01.04 | QA: IDOR; attachment via SEC-09 | Regression | Support | §15 + §2.9 | Patient support tickets / Help centre & support tickets | Patients raise issues from the app and track them to resolution | Patient App + Admin | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
5 | 566 | M14 | Support & help desk | Web | 13 | Phase 13 — Support & help desk (PDF §15) | 13.2 | SUP-02 | Doctor support tickets — doctors raise issues from the portal | SUP-02.01 | Reuse SupportTicket with ReporterRole=Doctor | New | Support | §15 | Doctor support tickets | Doctors raise issues from the portal | Doctor Web + Admin | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
6 | 567 | M14 | Support & help desk | UI | 13 | Phase 13 — Support & help desk (PDF §15) | 13.2 | SUP-02 | Doctor support tickets — doctors raise issues from the portal | SUP-02.02 | /doctor/support list/create/detail | New | Support | §15 | Doctor support tickets | Doctors raise issues from the portal | Doctor Web + Admin | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
7 | 568 | M14 | Support & help desk | QA | 13 | Phase 13 — Support & help desk (PDF §15) | 13.2 | SUP-02 | Doctor support tickets — doctors raise issues from the portal | SUP-02.03 | QA: doctor cannot see another doctor’s tickets | Regression | Support | §15 | Doctor support tickets | Doctors raise issues from the portal | Doctor Web + Admin | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
8 | 569 | M14 | Support & help desk | Web | 13 | Phase 13 — Support & help desk (PDF §15) | 13.3 | SUP-03 | Admin issue queue — all issues in one queue with priority, assignment and status | SUP-03.01 | Extend ticket with Priority, Assignee, SLA | New | Support | §15 + §7.2 | Admin issue queue / Support ticket queue | All issues in one queue with priority, assignment and status / All patient and doctor issues in one queue with assignment and resolution | Admin Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
9 | 570 | M14 | Support & help desk | Web | 13 | Phase 13 — Support & help desk (PDF §15) | 13.3 | SUP-03 | Admin issue queue — all issues in one queue with priority, assignment and status | SUP-03.02 | Admin list/filter/assign/status | New | Support | §15 + §7.2 | Admin issue queue / Support ticket queue | All issues in one queue with priority, assignment and status / All patient and doctor issues in one queue with assignment and resolution | Admin Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Pranav Bandekar
10 | 571 | M14 | Support & help desk | UI | 13 | Phase 13 — Support & help desk (PDF §15) | 13.3 | SUP-03 | Admin issue queue — all issues in one queue with priority, assignment and status | SUP-03.03 | /admin/support-tickets and /:id | New | Support | §15 + §7.2 | Admin issue queue / Support ticket queue | All issues in one queue with priority, assignment and status / All patient and doctor issues in one queue with assignment and resolution | Admin Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
11 | 572 | M14 | Support & help desk | QA | 13 | Phase 13 — Support & help desk (PDF §15) | 13.3 | SUP-03 | Admin issue queue — all issues in one queue with priority, assignment and status | SUP-03.04 | QA: not using Velzon ticket pages | Regression | Support | §15 + §7.2 | Admin issue queue / Support ticket queue | All issues in one queue with priority, assignment and status / All patient and doctor issues in one queue with assignment and resolution | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
12 | 573 | M14 | Support & help desk | Web | 13 | Phase 13 — Support & help desk (PDF §15) | 13.4 | SUP-04 | Ticket conversation — full message thread with attachments | SUP-04.01 | API: messages CRUD + attachment | New | Support | §15 | Ticket conversation | Full message thread with attachments | Admin + Doctor + Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
13 | 574 | M14 | Support & help desk | UI | 13 | Phase 13 — Support & help desk (PDF §15) | 13.4 | SUP-04 | Ticket conversation — full message thread with attachments | SUP-04.02 | Detail UI thread | New | Support | §15 | Ticket conversation | Full message thread with attachments | Admin + Doctor + Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
14 | 575 | M14 | Support & help desk | QA | 13 | Phase 13 — Support & help desk (PDF §15) | 13.4 | SUP-04 | Ticket conversation — full message thread with attachments | SUP-04.03 | QA: attachment unauthorised download 403 | Regression | Support | §15 | Ticket conversation | Full message thread with attachments | Admin + Doctor + Patient | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
15 | 576 | M14 | Support & help desk | UI | 13 | Phase 13 — Support & help desk (PDF §15) | 13.5 | SUP-05 | Enquiry management — website enquiries tracked (ties WEB-06) | SUP-05.01 | Admin enquiry inbox SLA fields | Existing Improvement | Support | §15 + §4 | Enquiry management | Website enquiries reach the admin team and are tracked | Admin Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
16 | 577 | M14 | Support & help desk | QA | 13 | Phase 13 — Support & help desk (PDF §15) | 13.5 | SUP-05 | Enquiry management — website enquiries tracked (ties WEB-06) | SUP-05.02 | QA: convert to ticket keeps original enquiry id | Regression | Support | §15 + §4 | Enquiry management | Website enquiries reach the admin team and are tracked | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
17 | 578 | M14 | Support & help desk | Web | 13 | Phase 13 — Support & help desk (PDF §15) | 13.6 | SUP-06 | Help centre — self-service help content for patients | SUP-06.01 | HelpArticle table or reuse blog category=help | New | Support | §15 + §2.9 | Help centre | Self-service help content for patients | Patient Website + App | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
18 | 579 | M14 | Support & help desk | Web | 13 | Phase 13 — Support & help desk (PDF §15) | 13.6 | SUP-06 | Help centre — self-service help content for patients | SUP-06.02 | Public GET help articles | New | Support | §15 + §2.9 | Help centre | Self-service help content for patients | Patient Website + App | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
19 | 580 | M14 | Support & help desk | UI | 13 | Phase 13 — Support & help desk (PDF §15) | 13.6 | SUP-06 | Help centre — self-service help content for patients | SUP-06.03 | Help centre list/detail | New | Support | §15 + §2.9 | Help centre | Self-service help content for patients | Patient Website + App | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
20 | 581 | M14 | Support & help desk | QA | 13 | Phase 13 — Support & help desk (PDF §15) | 13.6 | SUP-06 | Help centre — self-service help content for patients | SUP-06.04 | QA: unpublished hidden | Regression | Support | §15 + §2.9 | Help centre | Self-service help content for patients | Patient Website + App | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
21 | 582 | M14 | Support & help desk | Web | 13 | Phase 13 — Support & help desk (PDF §15) | 13.7 | SUP-07 | Assisted booking — help for patients who need support booking | SUP-07.01 | Flag BookingChannel=Assisted; AssistedRequest ticket type | New | Support | §15 + §2.9 | Assisted booking | Support for patients who need help booking / Help for patients who need support booking | Support + Reception + Patient | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
22 | 583 | M14 | Support & help desk | Web | 13 | Phase 13 — Support & help desk (PDF §15) | 13.7 | SUP-07 | Assisted booking — help for patients who need support booking | SUP-07.02 | API: request assistance; staff completes WEB-04 create on behalf | New | Support | §15 + §2.9 | Assisted booking | Support for patients who need help booking / Help for patients who need support booking | Support + Reception + Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
23 | 584 | M14 | Support & help desk | UI | 13 | Phase 13 — Support & help desk (PDF §15) | 13.7 | SUP-07 | Assisted booking — help for patients who need support booking | SUP-07.03 | Patient CTA; admin/reception assisted-book wizard | New | Support | §15 + §2.9 | Assisted booking | Support for patients who need help booking / Help for patients who need support booking | Support + Reception + Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
24 | 585 | M14 | Support & help desk | QA | 13 | Phase 13 — Support & help desk (PDF §15) | 13.7 | SUP-07 | Assisted booking — help for patients who need support booking | SUP-07.04 | QA: consent still captured; payment still Homeocentrum | Regression | Support | §15 + §2.9 | Assisted booking | Support for patients who need help booking / Help for patients who need support booking | Support + Reception + Patient | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet

## M15_HomeoMeds
M15 HomeoMeds — 55 sub-tasks (Web 25 · UI 14 · QA 16). YELLOW = edit here (Assigned To, Frontend/Backend/Database/API/Mobile/Integration Status + Assigned). Scope Yes/No is fixed. Status N/A = that function is not in this sub-task. Master, Web/UI/Mobile/QA sheets and Dashboard follow these cells live. | [41 empty] | Live copy of 00_Employees column B — do not edit. New names appear here automatically.
Module Seq | Original Seq | Dev Module Code | Dev Module | Track | Phase | Phase Name | WBS | Main Task ID | Main Task | Sub Task ID | Sub Task | Work Type | Source Module / Area | PDF Section | PDF Feature (exact wording) | PDF Delivery Text | Application Surface | Layer | Assigned To (lead) | Frontend | Frontend Status | Frontend Assigned | Backend | Backend Status | Backend Assigned | Database | Database Status | Database Assigned | API | API Status | API Assigned | Mobile | Mobile Status | Mobile Assigned | Integration | Integration Status | Integration Assigned | Layers Remaining | Overall Status | Notes | Open Module Sheet | _EmpList
1 | 586 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.1 | MED-01 | Pharmacy partner onboarding — licensed premises, licence records, activation checklist | MED-01.01 | DB: PharmacyPartner, PharmacyLicence, activation checklist fields | New | HomeoMeds | §12 + §7.2 | Pharmacy partner onboarding / Pharmacy partner management | Licensed premises registered with licence records and an activation checklist / Onboard and activate licensed pharmacies | Pharmacy + Admin | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Unassigned
2 | 587 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.1 | MED-01 | Pharmacy partner onboarding — licensed premises, licence records, activation checklist | MED-01.02 | API: onboard, admin activate, pharmacy login role | New | HomeoMeds | §12 + §7.2 | Pharmacy partner onboarding / Pharmacy partner management | Licensed premises registered with licence records and an activation checklist / Onboard and activate licensed pharmacies | Pharmacy + Admin | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
3 | 588 | M15 | HomeoMeds | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.1 | MED-01 | Pharmacy partner onboarding — licensed premises, licence records, activation checklist | MED-01.03 | /pharmacy/onboard; /admin pharmacy partners | New | HomeoMeds | §12 + §7.2 | Pharmacy partner onboarding / Pharmacy partner management | Licensed premises registered with licence records and an activation checklist / Onboard and activate licensed pharmacies | Pharmacy + Admin | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Digvijay Jadhav
4 | 589 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.1 | MED-01 | Pharmacy partner onboarding — licensed premises, licence records, activation checklist | MED-01.04 | QA: checklist incomplete blocks activate | Regression | HomeoMeds | §12 + §7.2 | Pharmacy partner onboarding / Pharmacy partner management | Licensed premises registered with licence records and an activation checklist / Onboard and activate licensed pharmacies | Pharmacy + Admin | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
5 | 590 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.2 | MED-02 | Licence gating — expired or suspended licences blocked automatically from receiving orders | MED-02.01 | Job: mark licence expired/suspended; exclude from routing | New | HomeoMeds | §12 | Licence gating | Pharmacies with expired or suspended licences are blocked automatically from receiving orders | Backend | Backend | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
6 | 591 | M15 | HomeoMeds | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.2 | MED-02 | Licence gating — expired or suspended licences blocked automatically from receiving orders | MED-02.02 | Pharmacy console status banner | New | HomeoMeds | §12 | Licence gating | Pharmacies with expired or suspended licences are blocked automatically from receiving orders | Backend | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
7 | 592 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.2 | MED-02 | Licence gating — expired or suspended licences blocked automatically from receiving orders | MED-02.03 | QA: expire a licence in test → order not offered | Regression | HomeoMeds | §12 | Licence gating | Pharmacies with expired or suspended licences are blocked automatically from receiving orders | Backend | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
8 | 593 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.3 | MED-03 | Fulfilment consent & pharmacy selection — patient chooses the seller and consents before the prescription is shared | MED-03.01 | Consent + selected PharmacyPartnerId on MedicineOrder | New | HomeoMeds | §12 + §2.7 | Fulfilment consent & pharmacy selection | The patient chooses the seller and consents before the prescription is shared | Patient | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
9 | 594 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.3 | MED-03 | Fulfilment consent & pharmacy selection — patient chooses the seller and consents before the prescription is shared | MED-03.02 | API: list sellers; select; grant consent | New | HomeoMeds | §12 + §2.7 | Fulfilment consent & pharmacy selection | The patient chooses the seller and consents before the prescription is shared | Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Pranav Bandekar
10 | 595 | M15 | HomeoMeds | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.3 | MED-03 | Fulfilment consent & pharmacy selection — patient chooses the seller and consents before the prescription is shared | MED-03.03 | Patient pharmacy pick UI (web optional + app Phase 16) | New | HomeoMeds | §12 + §2.7 | Fulfilment consent & pharmacy selection | The patient chooses the seller and consents before the prescription is shared | Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
11 | 596 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.3 | MED-03 | Fulfilment consent & pharmacy selection — patient chooses the seller and consents before the prescription is shared | MED-03.04 | QA: without consent, handoff API 403 | Regression | HomeoMeds | §12 + §2.7 | Fulfilment consent & pharmacy selection | The patient chooses the seller and consents before the prescription is shared | Patient | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
12 | 597 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.4 | MED-04 | Prescription handoff — signed prescription becomes the order directly — no re-entry, no transcription errors | MED-04.01 | DB: MedicineOrder, MedicineOrderItem from ErxSnapshot | New | HomeoMeds | §12 + §2.7 | Prescription handoff / Order start | The signed prescription becomes the order directly — no re-entry, no transcription errors / Start an order directly from the prescription | Patient + Pharmacy | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
13 | 598 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.4 | MED-04 | Prescription handoff — signed prescription becomes the order directly — no re-entry, no transcription errors | MED-04.02 | API: POST order from ErxId | New | HomeoMeds | §12 + §2.7 | Prescription handoff / Order start | The signed prescription becomes the order directly — no re-entry, no transcription errors / Start an order directly from the prescription | Patient + Pharmacy | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
14 | 599 | M15 | HomeoMeds | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.4 | MED-04 | Prescription handoff — signed prescription becomes the order directly — no re-entry, no transcription errors | MED-04.03 | Order start from patient eRx screen | New | HomeoMeds | §12 + §2.7 | Prescription handoff / Order start | The signed prescription becomes the order directly — no re-entry, no transcription errors / Start an order directly from the prescription | Patient + Pharmacy | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
15 | 600 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.4 | MED-04 | Prescription handoff — signed prescription becomes the order directly — no re-entry, no transcription errors | MED-04.04 | QA: line count mismatch fails sign-off | Regression | HomeoMeds | §12 + §2.7 | Prescription handoff / Order start | The signed prescription becomes the order directly — no re-entry, no transcription errors / Start an order directly from the prescription | Patient + Pharmacy | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
16 | 601 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.5 | MED-05 | Rule-based seller routing — licence validity, service area, working hours and capacity | MED-05.01 | DB: SellerRoutingRule (area, hours, capacity) | New | HomeoMeds | §12 | Rule-based seller routing | Orders routed by licence validity, service area, working hours and capacity | Backend | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
17 | 602 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.5 | MED-05 | Rule-based seller routing — licence validity, service area, working hours and capacity | MED-05.02 | Routing service used by seller list API | New | HomeoMeds | §12 | Rule-based seller routing | Orders routed by licence validity, service area, working hours and capacity | Backend | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
18 | 603 | M15 | HomeoMeds | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.5 | MED-05 | Rule-based seller routing — licence validity, service area, working hours and capacity | MED-05.03 | Admin/pharmacy hours and area config UI | New | HomeoMeds | §12 | Rule-based seller routing | Orders routed by licence validity, service area, working hours and capacity | Backend | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
19 | 604 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.5 | MED-05 | Rule-based seller routing — licence validity, service area, working hours and capacity | MED-05.04 | QA: capacity full excluded; hours closed excluded | Regression | HomeoMeds | §12 | Rule-based seller routing | Orders routed by licence validity, service area, working hours and capacity | Backend | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
20 | 605 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.6 | MED-06 | Manual stock confirmation — pharmacy confirms availability — no live inventory integration required | MED-06.01 | Accept payload includes stock confirmation; reject reason OUT_OF_STOCK | New | HomeoMeds | §12 | Manual stock confirmation | The pharmacy confirms availability — no live inventory integration required | Pharmacy console | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
21 | 606 | M15 | HomeoMeds | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.6 | MED-06 | Manual stock confirmation — pharmacy confirms availability — no live inventory integration required | MED-06.02 | Pharmacy UI confirm availability | New | HomeoMeds | §12 | Manual stock confirmation | The pharmacy confirms availability — no live inventory integration required | Pharmacy console | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
22 | 607 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.6 | MED-06 | Manual stock confirmation — pharmacy confirms availability — no live inventory integration required | MED-06.03 | QA: no inventory SKU table required | Regression | HomeoMeds | §12 | Manual stock confirmation | The pharmacy confirms availability — no live inventory integration required | Pharmacy console | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
23 | 608 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.7 | MED-07 | Pharmacy console — accept or reject, enter price quote, mark ready and dispatched | MED-07.01 | Order status machine: Offered/Accepted/Rejected/Quoted/Paid/Ready/Dispatched/Delivered | New | HomeoMeds | §12 | Pharmacy console | Accept or reject orders, enter the price quote, mark ready and dispatched | Pharmacy console | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
24 | 609 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.7 | MED-07 | Pharmacy console — accept or reject, enter price quote, mark ready and dispatched | MED-07.02 | API: accept(OTP), reject, quote, ready, dispatch | New | HomeoMeds | §12 | Pharmacy console | Accept or reject orders, enter the price quote, mark ready and dispatched | Pharmacy console | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
25 | 610 | M15 | HomeoMeds | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.7 | MED-07 | Pharmacy console — accept or reject, enter price quote, mark ready and dispatched | MED-07.03 | /pharmacy/orders and detail | New | HomeoMeds | §12 | Pharmacy console | Accept or reject orders, enter the price quote, mark ready and dispatched | Pharmacy console | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
26 | 611 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.7 | MED-07 | Pharmacy console — accept or reject, enter price quote, mark ready and dispatched | MED-07.04 | OTP on accept | New Integration | HomeoMeds | §12 | Pharmacy console | Accept or reject orders, enter the price quote, mark ready and dispatched | Pharmacy console | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | EDIT HERE — this module sheet
27 | 612 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.7 | MED-07 | Pharmacy console — accept or reject, enter price quote, mark ready and dispatched | MED-07.05 | QA: accept without OTP fails; names still hidden to patient until accept succeeds | Regression | HomeoMeds | §12 | Pharmacy console | Accept or reject orders, enter the price quote, mark ready and dispatched | Pharmacy console | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
28 | 613 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.8 | MED-08 | Quote before payment — the patient always sees the price before paying | MED-08.01 | DB: MedicineQuote | New | HomeoMeds | §12 + §2.7 | Quote before payment / Pharmacy selection & quote | The patient always sees the price before paying / Choose a licensed pharmacy and see the price before paying | Patient | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
29 | 614 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.8 | MED-08 | Quote before payment — the patient always sees the price before paying | MED-08.02 | API: quote, patient accept quote, then create medicine payment | New | HomeoMeds | §12 + §2.7 | Quote before payment / Pharmacy selection & quote | The patient always sees the price before paying / Choose a licensed pharmacy and see the price before paying | Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
30 | 615 | M15 | HomeoMeds | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.8 | MED-08 | Quote before payment — the patient always sees the price before paying | MED-08.03 | Patient quote screen | New | HomeoMeds | §12 + §2.7 | Quote before payment / Pharmacy selection & quote | The patient always sees the price before paying / Choose a licensed pharmacy and see the price before paying | Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
31 | 616 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.8 | MED-08 | Quote before payment — the patient always sees the price before paying | MED-08.04 | QA: price change after quote invalidates old quote | Regression | HomeoMeds | §12 + §2.7 | Quote before payment / Pharmacy selection & quote | The patient always sees the price before paying / Choose a licensed pharmacy and see the price before paying | Patient | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
32 | 617 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.9 | MED-09 | Payment or cash on delivery — both options, with status tracking | MED-09.01 | Wire PAY-07 CreateMedicineOrder; COD status enum | New | HomeoMeds | §12 + §9 | Payment or cash on delivery | Both options supported, with status tracking | Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | EDIT HERE — this module sheet
33 | 618 | M15 | HomeoMeds | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.9 | MED-09 | Payment or cash on delivery — both options, with status tracking | MED-09.02 | Patient pay vs COD UI | New | HomeoMeds | §12 + §9 | Payment or cash on delivery | Both options supported, with status tracking | Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
34 | 619 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.9 | MED-09 | Payment or cash on delivery — both options, with status tracking | MED-09.03 | QA: COD vs prepaid ledger split | Regression | HomeoMeds | §12 + §9 | Payment or cash on delivery | Both options supported, with status tracking | Patient | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
35 | 620 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.10 | MED-10 | Order tracking — live status for the patient at every stage | MED-10.01 | DB: MedicineOrderEvent | New | HomeoMeds | §12 + §2.7 | Order tracking | Live status for the patient at every stage / Live status from accepted to delivered | Patient | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
36 | 621 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.10 | MED-10 | Order tracking — live status for the patient at every stage | MED-10.02 | GET tracking by order id (patient) | New | HomeoMeds | §12 + §2.7 | Order tracking | Live status for the patient at every stage / Live status from accepted to delivered | Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
37 | 622 | M15 | HomeoMeds | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.10 | MED-10 | Order tracking — live status for the patient at every stage | MED-10.03 | Tracking UI | New | HomeoMeds | §12 + §2.7 | Order tracking | Live status for the patient at every stage / Live status from accepted to delivered | Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
38 | 623 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.10 | MED-10 | Order tracking — live status for the patient at every stage | MED-10.04 | Push on status change | New Integration | HomeoMeds | §12 + §2.7 | Order tracking | Live status for the patient at every stage / Live status from accepted to delivered | Patient | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | EDIT HERE — this module sheet
39 | 624 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.10 | MED-10 | Order tracking — live status for the patient at every stage | MED-10.05 | QA: dispatched without ready is invalid transition | Regression | HomeoMeds | §12 + §2.7 | Order tracking | Live status for the patient at every stage / Live status from accepted to delivered | Patient | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
40 | 625 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.11 | MED-11 | Medicine ledger shares — seller, platform and delivery recorded (FIN-03 live fill) | MED-11.01 | On captured medicine payment write three-share ledger lines | New | HomeoMeds | §12 + §8 | Medicine ledger | Seller, platform and delivery shares recorded separately from consultation money | Account | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
41 | 626 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.11 | MED-11 | Medicine ledger shares — seller, platform and delivery recorded (FIN-03 live fill) | MED-11.02 | QA: consult GMV unchanged by a medicine order | Regression | HomeoMeds | §12 + §8 | Medicine ledger | Seller, platform and delivery shares recorded separately from consultation money | Account | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
42 | 627 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.12 | MED-12 | Order exception queue — stuck, rejected or failed orders always surfaced — never silent | MED-12.01 | Exception rows for medicine orders | New | HomeoMeds | §12 | Order exception queue | Stuck, rejected or failed orders are always surfaced to the operations team — never silent | Admin + Account | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
43 | 628 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.12 | MED-12 | Order exception queue — stuck, rejected or failed orders always surfaced — never silent | MED-12.02 | Admin/ops list/detail/retry re-route | New | HomeoMeds | §12 | Order exception queue | Stuck, rejected or failed orders are always surfaced to the operations team — never silent | Admin + Account | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
44 | 629 | M15 | HomeoMeds | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.12 | MED-12 | Order exception queue — stuck, rejected or failed orders always surfaced — never silent | MED-12.03 | /admin/homemeds-exceptions | New | HomeoMeds | §12 | Order exception queue | Stuck, rejected or failed orders are always surfaced to the operations team — never silent | Admin + Account | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
45 | 630 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.12 | MED-12 | Order exception queue — stuck, rejected or failed orders always surfaced — never silent | MED-12.04 | QA: silent discard impossible (metric + queue) | Regression | HomeoMeds | §12 | Order exception queue | Stuck, rejected or failed orders are always surfaced to the operations team — never silent | Admin + Account | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
46 | 631 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.13 | MED-13 | OTP-based control — key actions verified by OTP so Homeocentrum can monitor and trace every transaction | MED-13.01 | Bind OTP actions: PharmacyAccept, (optional) QuoteLock, Payout already FIN-05 | New | HomeoMeds | §12 + §17 | OTP-based control | Key actions verified by OTP so Homeocentrum can monitor and trace every transaction | Pharmacy + Account | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
47 | 632 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.13 | MED-13 | OTP-based control — key actions verified by OTP so Homeocentrum can monitor and trace every transaction | MED-13.02 | QA: Account OTP audit shows pharmacy accept | Regression | HomeoMeds | §12 + §17 | OTP-based control | Key actions verified by OTP so Homeocentrum can monitor and trace every transaction | Pharmacy + Account | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
48 | 633 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.14 | MED-14 | Refill orders — repeat orders raised from an existing prescription | MED-14.01 | On doctor approve, clone order from snapshot; patient one-tap | New | HomeoMeds | §12 + §2.7 + §11 | Refill orders / Order detail & refill | Repeat orders raised from an existing prescription / Full order history and one-tap refill request | Patient + Doctor | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
49 | 634 | M15 | HomeoMeds | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.14 | MED-14 | Refill orders — repeat orders raised from an existing prescription | MED-14.02 | Patient order detail + refill CTA | New | HomeoMeds | §12 + §2.7 + §11 | Refill orders / Order detail & refill | Repeat orders raised from an existing prescription / Full order history and one-tap refill request | Patient + Doctor | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
50 | 635 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.14 | MED-14 | Refill orders — repeat orders raised from an existing prescription | MED-14.03 | QA: original eRx unchanged | Regression | HomeoMeds | §12 + §2.7 + §11 | Refill orders / Order detail & refill | Repeat orders raised from an existing prescription / Full order history and one-tap refill request | Patient + Doctor | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
51 | 636 | M15 | HomeoMeds | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.15 | MED-15 | Order review & consent (patient) — confirm and consent before the prescription is shared | MED-15.01 | Patient review screen before handoff | New | HomeoMeds | §2.7 | Order review & consent | Confirm and consent before the prescription is shared | Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
52 | 637 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.15 | MED-15 | Order review & consent (patient) — confirm and consent before the prescription is shared | MED-15.02 | QA: back button does not share | Regression | HomeoMeds | §2.7 | Order review & consent | Confirm and consent before the prescription is shared | Patient | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
53 | 638 | M15 | HomeoMeds | Web | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.16 | MED-16 | Medicines tab — all medicine orders in one place (API now; app UI in Phase 16) | MED-16.01 | GET /api/Patient/MedicineOrders | New | HomeoMeds | §2.7 | Medicines tab | All medicine orders in one place | Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
54 | 639 | M15 | HomeoMeds | UI | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.16 | MED-16 | Medicines tab — all medicine orders in one place (API now; app UI in Phase 16) | MED-16.02 | Optional web list; mobile tab later | New | HomeoMeds | §2.7 | Medicines tab | All medicine orders in one place | Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
55 | 640 | M15 | HomeoMeds | QA | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.16 | MED-16 | Medicines tab — all medicine orders in one place (API now; app UI in Phase 16) | MED-16.03 | QA: IDOR other patient 403 | Regression | HomeoMeds | §2.7 | Medicines tab | All medicine orders in one place | Patient | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet

## M16_Patient_APIs
M16 Patient continuity APIs — 33 sub-tasks (Web 17 · UI 8 · QA 8). YELLOW = edit here (Assigned To, Frontend/Backend/Database/API/Mobile/Integration Status + Assigned). Scope Yes/No is fixed. Status N/A = that function is not in this sub-task. Master, Web/UI/Mobile/QA sheets and Dashboard follow these cells live. | [41 empty] | Live copy of 00_Employees column B — do not edit. New names appear here automatically.
Module Seq | Original Seq | Dev Module Code | Dev Module | Track | Phase | Phase Name | WBS | Main Task ID | Main Task | Sub Task ID | Sub Task | Work Type | Source Module / Area | PDF Section | PDF Feature (exact wording) | PDF Delivery Text | Application Surface | Layer | Assigned To (lead) | Frontend | Frontend Status | Frontend Assigned | Backend | Backend Status | Backend Assigned | Database | Database Status | Database Assigned | API | API Status | API Assigned | Mobile | Mobile Status | Mobile Assigned | Integration | Integration Status | Integration Assigned | Layers Remaining | Overall Status | Notes | Open Module Sheet | _EmpList
1 | 641 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.1 | CON-01 | Family members — add family members under one account | CON-01.01 | DB: FamilyMember | New | Patient identity | §2.1 | Family members | Add family members under one account | Patient App (API now) | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Unassigned
2 | 642 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.1 | CON-01 | Family members — add family members under one account | CON-01.02 | API: CRUD family; book-as-member | New | Patient identity | §2.1 | Family members | Add family members under one account | Patient App (API now) | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
3 | 643 | M16 | Patient continuity APIs | UI | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.1 | CON-01 | Family members — add family members under one account | CON-01.03 | Consumed in Phase 16 | New | Patient identity | §2.1 | Family members | Add family members under one account | Patient App (API now) | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Digvijay Jadhav
4 | 644 | M16 | Patient continuity APIs | QA | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.1 | CON-01 | Family members — add family members under one account | CON-01.04 | QA: adult consent rules for minors documented | Regression | Patient identity | §2.1 | Family members | Add family members under one account | Patient App (API now) | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
5 | 645 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.2 | CON-02 | Caregiver authorization — let a family member book and manage on their behalf | CON-02.01 | DB: CaregiverAuth | New | Patient identity | §2.1 | Caregiver authorization | Let a family member book and manage on their behalf | Patient App (API now) | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
6 | 646 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.2 | CON-02 | Caregiver authorization — let a family member book and manage on their behalf | CON-02.02 | API: grant/revoke/list; booking authorisation check | New | Patient identity | §2.1 | Caregiver authorization | Let a family member book and manage on their behalf | Patient App (API now) | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
7 | 647 | M16 | Patient continuity APIs | UI | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.2 | CON-02 | Caregiver authorization — let a family member book and manage on their behalf | CON-02.03 | Consumed in Phase 16 | New | Patient identity | §2.1 | Caregiver authorization | Let a family member book and manage on their behalf | Patient App (API now) | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
8 | 648 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.2 | CON-02 | Caregiver authorization — let a family member book and manage on their behalf | CON-02.04 | OTP on grant | New Integration | Patient identity | §2.1 | Caregiver authorization | Let a family member book and manage on their behalf | Patient App (API now) | Integration | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | 3 | Not Started |  | EDIT HERE — this module sheet
9 | 649 | M16 | Patient continuity APIs | QA | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.2 | CON-02 | Caregiver authorization — let a family member book and manage on their behalf | CON-02.05 | QA: revoked token cannot book | Regression | Patient identity | §2.1 | Caregiver authorization | Let a family member book and manage on their behalf | Patient App (API now) | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Pranav Bandekar
10 | 650 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.3 | CON-03 | Records timeline + consultation note + document upload APIs | CON-03.01 | Reuse appointments + summary + eRx + SecureDocument | New | Patient records | §2.5 | Records timeline / Consultation note / Document upload | Complete visit history in date order / Doctor’s notes for each visit / Upload reports, scans and previous prescriptions | Patient App (API now) | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
11 | 651 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.3 | CON-03 | Records timeline + consultation note + document upload APIs | CON-03.02 | GET timeline; GET consultation note (summary); POST documents | New | Patient records | §2.5 | Records timeline / Consultation note / Document upload | Complete visit history in date order / Doctor’s notes for each visit / Upload reports, scans and previous prescriptions | Patient App (API now) | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
12 | 652 | M16 | Patient continuity APIs | UI | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.3 | CON-03 | Records timeline + consultation note + document upload APIs | CON-03.03 | Consumed in Phase 16 | New | Patient records | §2.5 | Records timeline / Consultation note / Document upload | Complete visit history in date order / Doctor’s notes for each visit / Upload reports, scans and previous prescriptions | Patient App (API now) | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
13 | 653 | M16 | Patient continuity APIs | QA | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.3 | CON-03 | Records timeline + consultation note + document upload APIs | CON-03.04 | QA: notes leak test on timeline JSON | Regression | Patient records | §2.5 | Records timeline / Consultation note / Document upload | Complete visit history in date order / Doctor’s notes for each visit / Upload reports, scans and previous prescriptions | Patient App (API now) | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
14 | 654 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.4 | CON-04 | Follow-up plan & tasks — clear next steps after each consultation | CON-04.01 | DB: FollowUpPlan, FollowUpTask | New | Continuity | §2.6 | Follow-up plan & tasks | Clear next steps after each consultation | Doctor Web + Patient | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
15 | 655 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.4 | CON-04 | Follow-up plan & tasks — clear next steps after each consultation | CON-04.02 | API: doctor set; patient list/complete | New | Continuity | §2.6 | Follow-up plan & tasks | Clear next steps after each consultation | Doctor Web + Patient | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
16 | 656 | M16 | Patient continuity APIs | UI | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.4 | CON-04 | Follow-up plan & tasks — clear next steps after each consultation | CON-04.03 | Doctor board follow-up panel; app in Phase 16 | New | Continuity | §2.6 | Follow-up plan & tasks | Clear next steps after each consultation | Doctor Web + Patient | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
17 | 657 | M16 | Patient continuity APIs | QA | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.4 | CON-04 | Follow-up plan & tasks — clear next steps after each consultation | CON-04.04 | QA: overdue flag | Regression | Continuity | §2.6 | Follow-up plan & tasks | Clear next steps after each consultation | Doctor Web + Patient | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
18 | 658 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.5 | CON-05 | Symptom diary — record symptoms between visits | CON-05.01 | DB: SymptomDiary | New | Continuity | §2.6 | Symptom diary | Record symptoms between visits | Patient App (API now) | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
19 | 659 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.5 | CON-05 | Symptom diary — record symptoms between visits | CON-05.02 | API: patient CRUD; doctor GET by patient | New | Continuity | §2.6 | Symptom diary | Record symptoms between visits | Patient App (API now) | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
20 | 660 | M16 | Patient continuity APIs | UI | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.5 | CON-05 | Symptom diary — record symptoms between visits | CON-05.03 | Doctor board read-only; app write Phase 16 | New | Continuity | §2.6 | Symptom diary | Record symptoms between visits | Patient App (API now) | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
21 | 661 | M16 | Patient continuity APIs | QA | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.5 | CON-05 | Symptom diary — record symptoms between visits | CON-05.04 | QA: IDOR | Regression | Continuity | §2.6 | Symptom diary | Record symptoms between visits | Patient App (API now) | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
22 | 662 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.6 | CON-06 | Progress tracking — see improvement over time across visits | CON-06.01 | Derived API from diary + appointments | New | Continuity | §2.6 | Progress tracking | See improvement over time across visits | Patient + Doctor | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
23 | 663 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.6 | CON-06 | Progress tracking — see improvement over time across visits | CON-06.02 | GET progress series | New | Continuity | §2.6 | Progress tracking | See improvement over time across visits | Patient + Doctor | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
24 | 664 | M16 | Patient continuity APIs | UI | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.6 | CON-06 | Progress tracking — see improvement over time across visits | CON-06.03 | Consumed in Phase 16 | New | Continuity | §2.6 | Progress tracking | See improvement over time across visits | Patient + Doctor | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
25 | 665 | M16 | Patient continuity APIs | QA | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.6 | CON-06 | Progress tracking — see improvement over time across visits | CON-06.04 | QA: no dummy numbers | Regression | Continuity | §2.6 | Progress tracking | See improvement over time across visits | Patient + Doctor | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
26 | 666 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.7 | CON-07 | Consent centre & data rights — view, manage and withdraw consents; request data | CON-07.01 | Reuse ConsentRecord; DataRequest table | New | Privacy | §17 + §2.8 | Consent centre & data rights | Patients can view, manage and withdraw consent / View, manage and withdraw consents; request data | Patient App (API now) | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
27 | 667 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.7 | CON-07 | Consent centre & data rights — view, manage and withdraw consents; request data | CON-07.02 | API: list/withdraw; request export/delete | New | Privacy | §17 + §2.8 | Consent centre & data rights | Patients can view, manage and withdraw consent / View, manage and withdraw consents; request data | Patient App (API now) | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
28 | 668 | M16 | Patient continuity APIs | UI | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.7 | CON-07 | Consent centre & data rights — view, manage and withdraw consents; request data | CON-07.03 | Consumed in Phase 16 | New | Privacy | §17 + §2.8 | Consent centre & data rights | Patients can view, manage and withdraw consent / View, manage and withdraw consents; request data | Patient App (API now) | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
29 | 669 | M16 | Patient continuity APIs | QA | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.7 | CON-07 | Consent centre & data rights — view, manage and withdraw consents; request data | CON-07.04 | QA: withdraw marketing stops WhatsApp/SMS offers | Regression | Privacy | §17 + §2.8 | Consent centre & data rights | Patients can view, manage and withdraw consent / View, manage and withdraw consents; request data | Patient App (API now) | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
30 | 674 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.10 | CON-10 | Patient profile setup API — name, age, gender, contact and health basics | CON-10.01 | Extend Patient with health-basics JSON/columns | New | Patient identity | §2.1 | Profile setup | Name, age, gender, contact and health basics | Patient App (API now) | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
31 | 675 | M16 | Patient continuity APIs | Web | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.10 | CON-10 | Patient profile setup API — name, age, gender, contact and health basics | CON-10.02 | GET/PUT /api/Patient/Profile | New | Patient identity | §2.1 | Profile setup | Name, age, gender, contact and health basics | Patient App (API now) | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
32 | 676 | M16 | Patient continuity APIs | UI | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.10 | CON-10 | Patient profile setup API — name, age, gender, contact and health basics | CON-10.03 | Consumed in Phase 16 | New | Patient identity | §2.1 | Profile setup | Name, age, gender, contact and health basics | Patient App (API now) | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
33 | 677 | M16 | Patient continuity APIs | QA | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.10 | CON-10 | Patient profile setup API — name, age, gender, contact and health basics | CON-10.04 | QA: cannot escalate to doctor role via profile PUT | Regression | Patient identity | §2.1 | Profile setup | Name, age, gender, contact and health basics | Patient App (API now) | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet

## M17_Patient_Mobile
M17 Patient mobile app — 231 sub-tasks (Mobile 173 · QA 58). YELLOW = edit here (Assigned To, Frontend/Backend/Database/API/Mobile/Integration Status + Assigned). Scope Yes/No is fixed. Status N/A = that function is not in this sub-task. Master, Web/UI/Mobile/QA sheets and Dashboard follow these cells live. | [41 empty] | Live copy of 00_Employees column B — do not edit. New names appear here automatically.
Module Seq | Original Seq | Dev Module Code | Dev Module | Track | Phase | Phase Name | WBS | Main Task ID | Main Task | Sub Task ID | Sub Task | Work Type | Source Module / Area | PDF Section | PDF Feature (exact wording) | PDF Delivery Text | Application Surface | Layer | Assigned To (lead) | Frontend | Frontend Status | Frontend Assigned | Backend | Backend Status | Backend Assigned | Database | Database Status | Database Assigned | API | API Status | API Assigned | Mobile | Mobile Status | Mobile Assigned | Integration | Integration Status | Integration Assigned | Layers Remaining | Overall Status | Notes | Open Module Sheet | _EmpList
1 | 678 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.1 | PAT-01 | Patient app — language selection on first open | PAT-01.01 | UI: Language selection screens (empty, loading, error, offline) | New | Patient Mobile | §2.1 | Language selection | Choose preferred language on first open | Patient Mobile App | Mobile UI | Pranav Bandekar | Yes | Done | Pranav Bandekar | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Done | Pranav Bandekar | No | N/A |  | 0 | Done |  | EDIT HERE — this module sheet | Unassigned
2 | 679 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.1 | PAT-01 | Patient app — language selection on first open | PAT-01.02 | Wire to the Phase 8–15 API for: Language selection | New | Patient Mobile | §2.1 | Language selection | Choose preferred language on first open | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
3 | 680 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.1 | PAT-01 | Patient app — language selection on first open | PAT-01.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.1 | Language selection | Choose preferred language on first open | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Digvijay Jadhav
4 | 681 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.1 | PAT-01 | Patient app — language selection on first open | PAT-01.04 | QA both platforms: Language selection matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.1 | Language selection | Choose preferred language on first open | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
5 | 682 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.2 | PAT-02 | Patient app — welcome and introduction | PAT-02.01 | UI: Welcome & introduction screens (empty, loading, error, offline) | New | Patient Mobile | §2.1 | Welcome & introduction | Guided introduction to the app | Patient Mobile App | Mobile UI | Pranav Bandekar | Yes | Done | Pranav Bandekar | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Done | Pranav Bandekar | No | N/A |  | 0 | Done |  | EDIT HERE — this module sheet
6 | 683 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.2 | PAT-02 | Patient app — welcome and introduction | PAT-02.02 | Wire to the Phase 8–15 API for: Welcome & introduction | New | Patient Mobile | §2.1 | Welcome & introduction | Guided introduction to the app | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
7 | 684 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.2 | PAT-02 | Patient app — welcome and introduction | PAT-02.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.1 | Welcome & introduction | Guided introduction to the app | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
8 | 685 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.2 | PAT-02 | Patient app — welcome and introduction | PAT-02.04 | QA both platforms: Welcome & introduction matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.1 | Welcome & introduction | Guided introduction to the app | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
9 | 686 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.3 | PAT-03 | Patient app — mobile number + OTP login (PatientAuth) | PAT-03.01 | UI: Mobile number + OTP login screens (empty, loading, error, offline) | New | Patient Mobile | §2.1 | Mobile number + OTP login | Secure sign-in with no password to remember | Patient Mobile App | Mobile UI | Pranav Bandekar | Yes | Done | Pranav Bandekar | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Done | Pranav Bandekar | No | N/A |  | 0 | Done |  | EDIT HERE — this module sheet | Pranav Bandekar
10 | 687 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.3 | PAT-03 | Patient app — mobile number + OTP login (PatientAuth) | PAT-03.02 | Wire to the Phase 8–15 API for: Mobile number + OTP login | New | Patient Mobile | §2.1 | Mobile number + OTP login | Secure sign-in with no password to remember | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
11 | 688 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.3 | PAT-03 | Patient app — mobile number + OTP login (PatientAuth) | PAT-03.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.1 | Mobile number + OTP login | Secure sign-in with no password to remember | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
12 | 689 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.3 | PAT-03 | Patient app — mobile number + OTP login (PatientAuth) | PAT-03.04 | QA both platforms: Mobile number + OTP login matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.1 | Mobile number + OTP login | Secure sign-in with no password to remember | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
13 | 690 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.4 | PAT-04 | Patient app — profile setup | PAT-04.01 | UI: Profile setup screens (empty, loading, error, offline) | New | Patient Mobile | §2.1 | Profile setup | Name, age, gender, contact and health basics | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
14 | 691 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.4 | PAT-04 | Patient app — profile setup | PAT-04.02 | Wire to the Phase 8–15 API for: Profile setup | New | Patient Mobile | §2.1 | Profile setup | Name, age, gender, contact and health basics | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
15 | 692 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.4 | PAT-04 | Patient app — profile setup | PAT-04.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.1 | Profile setup | Name, age, gender, contact and health basics | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
16 | 693 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.4 | PAT-04 | Patient app — profile setup | PAT-04.04 | QA both platforms: Profile setup matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.1 | Profile setup | Name, age, gender, contact and health basics | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
17 | 694 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.5 | PAT-05 | Patient app — privacy consent before data stored | PAT-05.01 | UI: Privacy consent screens (empty, loading, error, offline) | New | Patient Mobile | §2.1 | Privacy consent | Clear consent before any personal data is stored | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
18 | 695 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.5 | PAT-05 | Patient app — privacy consent before data stored | PAT-05.02 | Wire to the Phase 8–15 API for: Privacy consent | New | Patient Mobile | §2.1 | Privacy consent | Clear consent before any personal data is stored | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
19 | 696 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.5 | PAT-05 | Patient app — privacy consent before data stored | PAT-05.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.1 | Privacy consent | Clear consent before any personal data is stored | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
20 | 697 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.5 | PAT-05 | Patient app — privacy consent before data stored | PAT-05.04 | QA both platforms: Privacy consent matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.1 | Privacy consent | Clear consent before any personal data is stored | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
21 | 698 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.6 | PAT-06 | Patient app — family members | PAT-06.01 | UI: Family members screens (empty, loading, error, offline) | New | Patient Mobile | §2.1 | Family members | Add family members under one account | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
22 | 699 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.6 | PAT-06 | Patient app — family members | PAT-06.02 | Wire to the Phase 8–15 API for: Family members | New | Patient Mobile | §2.1 | Family members | Add family members under one account | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
23 | 700 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.6 | PAT-06 | Patient app — family members | PAT-06.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.1 | Family members | Add family members under one account | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
24 | 701 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.6 | PAT-06 | Patient app — family members | PAT-06.04 | QA both platforms: Family members matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.1 | Family members | Add family members under one account | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
25 | 702 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.7 | PAT-07 | Patient app — caregiver authorization | PAT-07.01 | UI: Caregiver authorization screens (empty, loading, error, offline) | New | Patient Mobile | §2.1 | Caregiver authorization | Let a family member book and manage on their behalf | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
26 | 703 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.7 | PAT-07 | Patient app — caregiver authorization | PAT-07.02 | Wire to the Phase 8–15 API for: Caregiver authorization | New | Patient Mobile | §2.1 | Caregiver authorization | Let a family member book and manage on their behalf | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
27 | 704 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.7 | PAT-07 | Patient app — caregiver authorization | PAT-07.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.1 | Caregiver authorization | Let a family member book and manage on their behalf | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
28 | 705 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.7 | PAT-07 | Patient app — caregiver authorization | PAT-07.04 | QA both platforms: Caregiver authorization matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.1 | Caregiver authorization | Let a family member book and manage on their behalf | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
29 | 706 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.8 | PAT-08 | Patient app — home dashboard | PAT-08.01 | UI: Home dashboard screens (empty, loading, error, offline) | New | Patient Mobile | §2.2 | Home dashboard | Personalised home with upcoming visits and quick actions | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
30 | 707 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.8 | PAT-08 | Patient app — home dashboard | PAT-08.02 | Wire to the Phase 8–15 API for: Home dashboard | New | Patient Mobile | §2.2 | Home dashboard | Personalised home with upcoming visits and quick actions | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
31 | 708 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.8 | PAT-08 | Patient app — home dashboard | PAT-08.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.2 | Home dashboard | Personalised home with upcoming visits and quick actions | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
32 | 709 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.8 | PAT-08 | Patient app — home dashboard | PAT-08.04 | QA both platforms: Home dashboard matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.2 | Home dashboard | Personalised home with upcoming visits and quick actions | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
33 | 710 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.9 | PAT-09 | Patient app — search and care categories | PAT-09.01 | UI: Search & care categories screens (empty, loading, error, offline) | New | Patient Mobile | §2.2 | Search & care categories | Search by name, condition or category of care | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
34 | 711 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.9 | PAT-09 | Patient app — search and care categories | PAT-09.02 | Wire to the Phase 8–15 API for: Search & care categories | New | Patient Mobile | §2.2 | Search & care categories | Search by name, condition or category of care | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
35 | 712 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.9 | PAT-09 | Patient app — search and care categories | PAT-09.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.2 | Search & care categories | Search by name, condition or category of care | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
36 | 713 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.9 | PAT-09 | Patient app — search and care categories | PAT-09.04 | QA both platforms: Search & care categories matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.2 | Search & care categories | Search by name, condition or category of care | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
37 | 714 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.10 | PAT-10 | Patient app — search results | PAT-10.01 | UI: Search results screens (empty, loading, error, offline) | New | Patient Mobile | §2.2 | Search results | Clear list of available doctors | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
38 | 715 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.10 | PAT-10 | Patient app — search results | PAT-10.02 | Wire to the Phase 8–15 API for: Search results | New | Patient Mobile | §2.2 | Search results | Clear list of available doctors | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
39 | 716 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.10 | PAT-10 | Patient app — search results | PAT-10.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.2 | Search results | Clear list of available doctors | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
40 | 717 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.10 | PAT-10 | Patient app — search results | PAT-10.04 | QA both platforms: Search results matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.2 | Search results | Clear list of available doctors | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
41 | 718 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.11 | PAT-11 | Patient app — discovery filters | PAT-11.01 | UI: Filters screens (empty, loading, error, offline) | New | Patient Mobile | §2.2 | Filters | Narrow by availability, fee, experience, language and location | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
42 | 719 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.11 | PAT-11 | Patient app — discovery filters | PAT-11.02 | Wire to the Phase 8–15 API for: Filters | New | Patient Mobile | §2.2 | Filters | Narrow by availability, fee, experience, language and location | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
43 | 720 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.11 | PAT-11 | Patient app — discovery filters | PAT-11.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.2 | Filters | Narrow by availability, fee, experience, language and location | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
44 | 721 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.11 | PAT-11 | Patient app — discovery filters | PAT-11.04 | QA both platforms: Filters matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.2 | Filters | Narrow by availability, fee, experience, language and location | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
45 | 722 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.12 | PAT-12 | Patient app — doctor profile | PAT-12.01 | UI: Doctor profile screens (empty, loading, error, offline) | New | Patient Mobile | §2.2 | Doctor profile | Full profile with qualifications, experience and consultation fee | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
46 | 723 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.12 | PAT-12 | Patient app — doctor profile | PAT-12.02 | Wire to the Phase 8–15 API for: Doctor profile | New | Patient Mobile | §2.2 | Doctor profile | Full profile with qualifications, experience and consultation fee | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
47 | 724 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.12 | PAT-12 | Patient app — doctor profile | PAT-12.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.2 | Doctor profile | Full profile with qualifications, experience and consultation fee | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
48 | 725 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.12 | PAT-12 | Patient app — doctor profile | PAT-12.04 | QA both platforms: Doctor profile matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.2 | Doctor profile | Full profile with qualifications, experience and consultation fee | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
49 | 726 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.13 | PAT-13 | Patient app — verified badge on doctor | PAT-13.01 | UI: Credentials & verification screens (empty, loading, error, offline) | New | Patient Mobile | §2.2 | Credentials & verification | Verified badge showing the doctor’s credentials are checked | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
50 | 727 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.13 | PAT-13 | Patient app — verified badge on doctor | PAT-13.02 | Wire to the Phase 8–15 API for: Credentials & verification | New | Patient Mobile | §2.2 | Credentials & verification | Verified badge showing the doctor’s credentials are checked | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
51 | 728 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.13 | PAT-13 | Patient app — verified badge on doctor | PAT-13.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.2 | Credentials & verification | Verified badge showing the doctor’s credentials are checked | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
52 | 729 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.13 | PAT-13 | Patient app — verified badge on doctor | PAT-13.04 | QA both platforms: Credentials & verification matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.2 | Credentials & verification | Verified badge showing the doctor’s credentials are checked | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
53 | 730 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.14 | PAT-14 | Patient app — ranking explanation | PAT-14.01 | UI: Ranking explanation screens (empty, loading, error, offline) | New | Patient Mobile | §2.2 | Ranking explanation | Transparent explanation of why doctors appear in a given order | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
54 | 731 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.14 | PAT-14 | Patient app — ranking explanation | PAT-14.02 | Wire to the Phase 8–15 API for: Ranking explanation | New | Patient Mobile | §2.2 | Ranking explanation | Transparent explanation of why doctors appear in a given order | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
55 | 732 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.14 | PAT-14 | Patient app — ranking explanation | PAT-14.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.2 | Ranking explanation | Transparent explanation of why doctors appear in a given order | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
56 | 733 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.14 | PAT-14 | Patient app — ranking explanation | PAT-14.04 | QA both platforms: Ranking explanation matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.2 | Ranking explanation | Transparent explanation of why doctors appear in a given order | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
57 | 734 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.15 | PAT-15 | Patient app — health articles | PAT-15.01 | UI: Health articles screens (empty, loading, error, offline) | New | Patient Mobile | §2.2 | Health articles | Educational content to build trust and engagement | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
58 | 735 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.15 | PAT-15 | Patient app — health articles | PAT-15.02 | Wire to the Phase 8–15 API for: Health articles | New | Patient Mobile | §2.2 | Health articles | Educational content to build trust and engagement | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
59 | 736 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.15 | PAT-15 | Patient app — health articles | PAT-15.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.2 | Health articles | Educational content to build trust and engagement | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
60 | 737 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.15 | PAT-15 | Patient app — health articles | PAT-15.04 | QA both platforms: Health articles matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.2 | Health articles | Educational content to build trust and engagement | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
61 | 738 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.16 | PAT-16 | Patient app — slot picker | PAT-16.01 | UI: Slot picker screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Slot picker | See real available time slots and choose one | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
62 | 739 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.16 | PAT-16 | Patient app — slot picker | PAT-16.02 | Wire to the Phase 8–15 API for: Slot picker | New | Patient Mobile | §2.3 | Slot picker | See real available time slots and choose one | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
63 | 740 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.16 | PAT-16 | Patient app — slot picker | PAT-16.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Slot picker | See real available time slots and choose one | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
64 | 741 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.16 | PAT-16 | Patient app — slot picker | PAT-16.04 | QA both platforms: Slot picker matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Slot picker | See real available time slots and choose one | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
65 | 742 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.17 | PAT-17 | Patient app — booking review and consent | PAT-17.01 | UI: Booking review & consent screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Booking review & consent | Confirm details and consent before booking | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
66 | 743 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.17 | PAT-17 | Patient app — booking review and consent | PAT-17.02 | Wire to the Phase 8–15 API for: Booking review & consent | New | Patient Mobile | §2.3 | Booking review & consent | Confirm details and consent before booking | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
67 | 744 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.17 | PAT-17 | Patient app — booking review and consent | PAT-17.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Booking review & consent | Confirm details and consent before booking | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
68 | 745 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.17 | PAT-17 | Patient app — booking review and consent | PAT-17.04 | QA both platforms: Booking review & consent matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Booking review & consent | Confirm details and consent before booking | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
69 | 746 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.18 | PAT-18 | Patient app — checkout | PAT-18.01 | UI: Checkout screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Checkout | Pay the consultation fee inside the app | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
70 | 747 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.18 | PAT-18 | Patient app — checkout | PAT-18.02 | Wire to the Phase 8–15 API for: Checkout | New | Patient Mobile | §2.3 | Checkout | Pay the consultation fee inside the app | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
71 | 748 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.18 | PAT-18 | Patient app — checkout | PAT-18.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Checkout | Pay the consultation fee inside the app | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
72 | 749 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.18 | PAT-18 | Patient app — checkout | PAT-18.04 | QA both platforms: Checkout matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Checkout | Pay the consultation fee inside the app | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
73 | 750 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.19 | PAT-19 | Patient app — payment status | PAT-19.01 | UI: Payment status screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Payment status | Immediate confirmation of paid, pending or failed | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
74 | 751 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.19 | PAT-19 | Patient app — payment status | PAT-19.02 | Wire to the Phase 8–15 API for: Payment status | New | Patient Mobile | §2.3 | Payment status | Immediate confirmation of paid, pending or failed | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
75 | 752 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.19 | PAT-19 | Patient app — payment status | PAT-19.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Payment status | Immediate confirmation of paid, pending or failed | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
76 | 753 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.19 | PAT-19 | Patient app — payment status | PAT-19.04 | QA both platforms: Payment status matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Payment status | Immediate confirmation of paid, pending or failed | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
77 | 754 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.20 | PAT-20 | Patient app — appointment detail | PAT-20.01 | UI: Appointment detail screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Appointment detail | Full booking details in one place | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
78 | 755 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.20 | PAT-20 | Patient app — appointment detail | PAT-20.02 | Wire to the Phase 8–15 API for: Appointment detail | New | Patient Mobile | §2.3 | Appointment detail | Full booking details in one place | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
79 | 756 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.20 | PAT-20 | Patient app — appointment detail | PAT-20.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Appointment detail | Full booking details in one place | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
80 | 757 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.20 | PAT-20 | Patient app — appointment detail | PAT-20.04 | QA both platforms: Appointment detail matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Appointment detail | Full booking details in one place | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
81 | 758 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.21 | PAT-21 | Patient app — reschedule | PAT-21.01 | UI: Reschedule appointment screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Reschedule appointment | Move to another slot without calling the clinic | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
82 | 759 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.21 | PAT-21 | Patient app — reschedule | PAT-21.02 | Wire to the Phase 8–15 API for: Reschedule appointment | New | Patient Mobile | §2.3 | Reschedule appointment | Move to another slot without calling the clinic | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
83 | 760 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.21 | PAT-21 | Patient app — reschedule | PAT-21.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Reschedule appointment | Move to another slot without calling the clinic | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
84 | 761 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.21 | PAT-21 | Patient app — reschedule | PAT-21.04 | QA both platforms: Reschedule appointment matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Reschedule appointment | Move to another slot without calling the clinic | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
85 | 762 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.22 | PAT-22 | Patient app — cancel | PAT-22.01 | UI: Cancel appointment screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Cancel appointment | Cancel with reason, refund handled per policy | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
86 | 763 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.22 | PAT-22 | Patient app — cancel | PAT-22.02 | Wire to the Phase 8–15 API for: Cancel appointment | New | Patient Mobile | §2.3 | Cancel appointment | Cancel with reason, refund handled per policy | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
87 | 764 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.22 | PAT-22 | Patient app — cancel | PAT-22.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Cancel appointment | Cancel with reason, refund handled per policy | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
88 | 765 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.22 | PAT-22 | Patient app — cancel | PAT-22.04 | QA both platforms: Cancel appointment matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Cancel appointment | Cancel with reason, refund handled per policy | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
89 | 766 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.23 | PAT-23 | Patient app — waitlist offer | PAT-23.01 | UI: Waitlist offer screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Waitlist offer | Get offered a slot when one is freed by a cancellation | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
90 | 767 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.23 | PAT-23 | Patient app — waitlist offer | PAT-23.02 | Wire to the Phase 8–15 API for: Waitlist offer | New | Patient Mobile | §2.3 | Waitlist offer | Get offered a slot when one is freed by a cancellation | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
91 | 768 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.23 | PAT-23 | Patient app — waitlist offer | PAT-23.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Waitlist offer | Get offered a slot when one is freed by a cancellation | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
92 | 769 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.23 | PAT-23 | Patient app — waitlist offer | PAT-23.04 | QA both platforms: Waitlist offer matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Waitlist offer | Get offered a slot when one is freed by a cancellation | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
93 | 770 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.24 | PAT-24 | Patient app — instant consult request | PAT-24.01 | UI: Instant consult request screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Instant consult request | Request an immediate consultation with an available doctor | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
94 | 771 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.24 | PAT-24 | Patient app — instant consult request | PAT-24.02 | Wire to the Phase 8–15 API for: Instant consult request | New | Patient Mobile | §2.3 | Instant consult request | Request an immediate consultation with an available doctor | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
95 | 772 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.24 | PAT-24 | Patient app — instant consult request | PAT-24.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Instant consult request | Request an immediate consultation with an available doctor | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
96 | 773 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.24 | PAT-24 | Patient app — instant consult request | PAT-24.04 | QA both platforms: Instant consult request matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Instant consult request | Request an immediate consultation with an available doctor | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
97 | 774 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.25 | PAT-25 | Patient app — queue and doctor offer | PAT-25.01 | UI: Queue & doctor offer screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Queue & doctor offer | See position in queue and accept an offered doctor | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
98 | 775 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.25 | PAT-25 | Patient app — queue and doctor offer | PAT-25.02 | Wire to the Phase 8–15 API for: Queue & doctor offer | New | Patient Mobile | §2.3 | Queue & doctor offer | See position in queue and accept an offered doctor | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
99 | 776 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.25 | PAT-25 | Patient app — queue and doctor offer | PAT-25.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Queue & doctor offer | See position in queue and accept an offered doctor | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
100 | 777 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.25 | PAT-25 | Patient app — queue and doctor offer | PAT-25.04 | QA both platforms: Queue & doctor offer matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Queue & doctor offer | See position in queue and accept an offered doctor | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
101 | 778 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.26 | PAT-26 | Patient app — device check | PAT-26.01 | UI: Device check screens (empty, loading, error, offline) | New | Patient Mobile | §2.4 | Device check | Camera, microphone and network checked before the call | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
102 | 779 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.26 | PAT-26 | Patient app — device check | PAT-26.02 | Wire to the Phase 8–15 API for: Device check | New | Patient Mobile | §2.4 | Device check | Camera, microphone and network checked before the call | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
103 | 780 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.26 | PAT-26 | Patient app — device check | PAT-26.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.4 | Device check | Camera, microphone and network checked before the call | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
104 | 781 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.26 | PAT-26 | Patient app — device check | PAT-26.04 | QA both platforms: Device check matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.4 | Device check | Camera, microphone and network checked before the call | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
105 | 782 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.27 | PAT-27 | Patient app — waiting room | PAT-27.01 | UI: Waiting room screens (empty, loading, error, offline) | New | Patient Mobile | §2.4 | Waiting room | Wait with live status until the doctor joins | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
106 | 783 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.27 | PAT-27 | Patient app — waiting room | PAT-27.02 | Wire to the Phase 8–15 API for: Waiting room | New | Patient Mobile | §2.4 | Waiting room | Wait with live status until the doctor joins | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
107 | 784 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.27 | PAT-27 | Patient app — waiting room | PAT-27.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.4 | Waiting room | Wait with live status until the doctor joins | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
108 | 785 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.27 | PAT-27 | Patient app — waiting room | PAT-27.04 | QA both platforms: Waiting room matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.4 | Waiting room | Wait with live status until the doctor joins | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
109 | 786 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.28 | PAT-28 | Patient app — live video | PAT-28.01 | UI: Live video consultation screens (empty, loading, error, offline) | New | Patient Mobile | §2.4 | Live video consultation | Face-to-face consultation from home | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
110 | 787 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.28 | PAT-28 | Patient app — live video | PAT-28.02 | Wire to the Phase 8–15 API for: Live video consultation | New | Patient Mobile | §2.4 | Live video consultation | Face-to-face consultation from home | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
111 | 788 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.28 | PAT-28 | Patient app — live video | PAT-28.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.4 | Live video consultation | Face-to-face consultation from home | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
112 | 789 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.28 | PAT-28 | Patient app — live video | PAT-28.04 | QA both platforms: Live video consultation matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.4 | Live video consultation | Face-to-face consultation from home | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
113 | 790 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.29 | PAT-29 | Patient app — recording consent | PAT-29.01 | UI: Recording consent screens (empty, loading, error, offline) | New | Patient Mobile | §2.4 | Recording consent | Explicit consent requested before any recording | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
114 | 791 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.29 | PAT-29 | Patient app — recording consent | PAT-29.02 | Wire to the Phase 8–15 API for: Recording consent | New | Patient Mobile | §2.4 | Recording consent | Explicit consent requested before any recording | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
115 | 792 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.29 | PAT-29 | Patient app — recording consent | PAT-29.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.4 | Recording consent | Explicit consent requested before any recording | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
116 | 793 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.29 | PAT-29 | Patient app — recording consent | PAT-29.04 | QA both platforms: Recording consent matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.4 | Recording consent | Explicit consent requested before any recording | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
117 | 794 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.30 | PAT-30 | Patient app — join failure fallback | PAT-30.01 | UI: Fallback & join failure handling screens (empty, loading, error, offline) | New | Patient Mobile | §2.4 | Fallback & join failure handling | Clear guidance if the call fails, with options to retry | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
118 | 795 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.30 | PAT-30 | Patient app — join failure fallback | PAT-30.02 | Wire to the Phase 8–15 API for: Fallback & join failure handling | New | Patient Mobile | §2.4 | Fallback & join failure handling | Clear guidance if the call fails, with options to retry | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
119 | 796 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.30 | PAT-30 | Patient app — join failure fallback | PAT-30.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.4 | Fallback & join failure handling | Clear guidance if the call fails, with options to retry | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
120 | 797 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.30 | PAT-30 | Patient app — join failure fallback | PAT-30.04 | QA both platforms: Fallback & join failure handling matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.4 | Fallback & join failure handling | Clear guidance if the call fails, with options to retry | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
121 | 798 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.31 | PAT-31 | Patient app — case-linked chat | PAT-31.01 | UI: Case-linked chat screens (empty, loading, error, offline) | New | Patient Mobile | §2.4 | Case-linked chat | Chat tied to the consultation, not a loose message thread | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
122 | 799 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.31 | PAT-31 | Patient app — case-linked chat | PAT-31.02 | Wire to the Phase 8–15 API for: Case-linked chat | New | Patient Mobile | §2.4 | Case-linked chat | Chat tied to the consultation, not a loose message thread | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
123 | 800 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.31 | PAT-31 | Patient app — case-linked chat | PAT-31.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.4 | Case-linked chat | Chat tied to the consultation, not a loose message thread | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
124 | 801 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.31 | PAT-31 | Patient app — case-linked chat | PAT-31.04 | QA both platforms: Case-linked chat matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.4 | Case-linked chat | Chat tied to the consultation, not a loose message thread | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
125 | 802 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.32 | PAT-32 | Patient app — consultation summary | PAT-32.01 | UI: Consultation summary screens (empty, loading, error, offline) | New | Patient Mobile | §2.4 | Consultation summary | Written summary available immediately after the call | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
126 | 803 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.32 | PAT-32 | Patient app — consultation summary | PAT-32.02 | Wire to the Phase 8–15 API for: Consultation summary | New | Patient Mobile | §2.4 | Consultation summary | Written summary available immediately after the call | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
127 | 804 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.32 | PAT-32 | Patient app — consultation summary | PAT-32.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.4 | Consultation summary | Written summary available immediately after the call | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
128 | 805 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.32 | PAT-32 | Patient app — consultation summary | PAT-32.04 | QA both platforms: Consultation summary matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.4 | Consultation summary | Written summary available immediately after the call | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
129 | 806 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.33 | PAT-33 | Patient app — rejoin | PAT-33.01 | UI: Rejoin after dropped call screens (empty, loading, error, offline) | New | Patient Mobile | §2.4 | Rejoin after dropped call | Rejoin the same consultation if the connection drops | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
130 | 807 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.33 | PAT-33 | Patient app — rejoin | PAT-33.02 | Wire to the Phase 8–15 API for: Rejoin after dropped call | New | Patient Mobile | §2.4 | Rejoin after dropped call | Rejoin the same consultation if the connection drops | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
131 | 808 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.33 | PAT-33 | Patient app — rejoin | PAT-33.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.4 | Rejoin after dropped call | Rejoin the same consultation if the connection drops | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
132 | 809 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.33 | PAT-33 | Patient app — rejoin | PAT-33.04 | QA both platforms: Rejoin after dropped call matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.4 | Rejoin after dropped call | Rejoin the same consultation if the connection drops | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
133 | 810 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.34 | PAT-34 | Patient app — records timeline | PAT-34.01 | UI: Records timeline screens (empty, loading, error, offline) | New | Patient Mobile | §2.5 | Records timeline | Complete visit history in date order | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
134 | 811 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.34 | PAT-34 | Patient app — records timeline | PAT-34.02 | Wire to the Phase 8–15 API for: Records timeline | New | Patient Mobile | §2.5 | Records timeline | Complete visit history in date order | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
135 | 812 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.34 | PAT-34 | Patient app — records timeline | PAT-34.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.5 | Records timeline | Complete visit history in date order | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
136 | 813 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.34 | PAT-34 | Patient app — records timeline | PAT-34.04 | QA both platforms: Records timeline matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.5 | Records timeline | Complete visit history in date order | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
137 | 814 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.35 | PAT-35 | Patient app — consultation note (summary, not private notes) | PAT-35.01 | UI: Consultation note screens (empty, loading, error, offline) | New | Patient Mobile | §2.5 | Consultation note | Doctor’s notes for each visit | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
138 | 815 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.35 | PAT-35 | Patient app — consultation note (summary, not private notes) | PAT-35.02 | Wire to the Phase 8–15 API for: Consultation note | New | Patient Mobile | §2.5 | Consultation note | Doctor’s notes for each visit | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
139 | 816 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.35 | PAT-35 | Patient app — consultation note (summary, not private notes) | PAT-35.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.5 | Consultation note | Doctor’s notes for each visit | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
140 | 817 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.35 | PAT-35 | Patient app — consultation note (summary, not private notes) | PAT-35.04 | QA both platforms: Consultation note matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.5 | Consultation note | Doctor’s notes for each visit | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
141 | 818 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.36 | PAT-36 | Patient app — signed eRx (codes until pharmacy accept) | PAT-36.01 | UI: Signed digital prescription screens (empty, loading, error, offline) | New | Patient Mobile | §2.5 | Signed digital prescription | Official prescription issued by the doctor | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
142 | 819 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.36 | PAT-36 | Patient app — signed eRx (codes until pharmacy accept) | PAT-36.02 | Wire to the Phase 8–15 API for: Signed digital prescription | New | Patient Mobile | §2.5 | Signed digital prescription | Official prescription issued by the doctor | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
143 | 820 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.36 | PAT-36 | Patient app — signed eRx (codes until pharmacy accept) | PAT-36.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.5 | Signed digital prescription | Official prescription issued by the doctor | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
144 | 821 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.36 | PAT-36 | Patient app — signed eRx (codes until pharmacy accept) | PAT-36.04 | QA both platforms: Signed digital prescription matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.5 | Signed digital prescription | Official prescription issued by the doctor | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
145 | 822 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.37 | PAT-37 | Patient app — document upload | PAT-37.01 | UI: Document upload screens (empty, loading, error, offline) | New | Patient Mobile | §2.5 | Document upload | Upload reports, scans and previous prescriptions | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
146 | 823 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.37 | PAT-37 | Patient app — document upload | PAT-37.02 | Wire to the Phase 8–15 API for: Document upload | New | Patient Mobile | §2.5 | Document upload | Upload reports, scans and previous prescriptions | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
147 | 824 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.37 | PAT-37 | Patient app — document upload | PAT-37.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.5 | Document upload | Upload reports, scans and previous prescriptions | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
148 | 825 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.37 | PAT-37 | Patient app — document upload | PAT-37.04 | QA both platforms: Document upload matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.5 | Document upload | Upload reports, scans and previous prescriptions | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
149 | 826 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.38 | PAT-38 | Patient app — follow-up plan and tasks | PAT-38.01 | UI: Follow-up plan & tasks screens (empty, loading, error, offline) | New | Patient Mobile | §2.6 | Follow-up plan & tasks | Clear next steps after each consultation | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
150 | 827 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.38 | PAT-38 | Patient app — follow-up plan and tasks | PAT-38.02 | Wire to the Phase 8–15 API for: Follow-up plan & tasks | New | Patient Mobile | §2.6 | Follow-up plan & tasks | Clear next steps after each consultation | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
151 | 828 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.38 | PAT-38 | Patient app — follow-up plan and tasks | PAT-38.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.6 | Follow-up plan & tasks | Clear next steps after each consultation | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
152 | 829 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.38 | PAT-38 | Patient app — follow-up plan and tasks | PAT-38.04 | QA both platforms: Follow-up plan & tasks matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.6 | Follow-up plan & tasks | Clear next steps after each consultation | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
153 | 830 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.39 | PAT-39 | Patient app — symptom diary | PAT-39.01 | UI: Symptom diary screens (empty, loading, error, offline) | New | Patient Mobile | §2.6 | Symptom diary | Record symptoms between visits | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
154 | 831 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.39 | PAT-39 | Patient app — symptom diary | PAT-39.02 | Wire to the Phase 8–15 API for: Symptom diary | New | Patient Mobile | §2.6 | Symptom diary | Record symptoms between visits | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
155 | 832 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.39 | PAT-39 | Patient app — symptom diary | PAT-39.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.6 | Symptom diary | Record symptoms between visits | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
156 | 833 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.39 | PAT-39 | Patient app — symptom diary | PAT-39.04 | QA both platforms: Symptom diary matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.6 | Symptom diary | Record symptoms between visits | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
157 | 834 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.40 | PAT-40 | Patient app — progress tracking | PAT-40.01 | UI: Progress tracking screens (empty, loading, error, offline) | New | Patient Mobile | §2.6 | Progress tracking | See improvement over time across visits | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
158 | 835 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.40 | PAT-40 | Patient app — progress tracking | PAT-40.02 | Wire to the Phase 8–15 API for: Progress tracking | New | Patient Mobile | §2.6 | Progress tracking | See improvement over time across visits | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
159 | 836 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.40 | PAT-40 | Patient app — progress tracking | PAT-40.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.6 | Progress tracking | See improvement over time across visits | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
160 | 837 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.40 | PAT-40 | Patient app — progress tracking | PAT-40.04 | QA both platforms: Progress tracking matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.6 | Progress tracking | See improvement over time across visits | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
161 | 838 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.41 | PAT-41 | Patient app — medicines tab | PAT-41.01 | UI: Medicines tab screens (empty, loading, error, offline) | New | Patient Mobile | §2.7 | Medicines tab | All medicine orders in one place | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
162 | 839 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.41 | PAT-41 | Patient app — medicines tab | PAT-41.02 | Wire to the Phase 8–15 API for: Medicines tab | New | Patient Mobile | §2.7 | Medicines tab | All medicine orders in one place | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
163 | 840 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.41 | PAT-41 | Patient app — medicines tab | PAT-41.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.7 | Medicines tab | All medicine orders in one place | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
164 | 841 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.41 | PAT-41 | Patient app — medicines tab | PAT-41.04 | QA both platforms: Medicines tab matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.7 | Medicines tab | All medicine orders in one place | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
165 | 842 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.42 | PAT-42 | Patient app — start HomeoMeds order from eRx | PAT-42.01 | UI: Order start screens (empty, loading, error, offline) | New | Patient Mobile | §2.7 | Order start | Start an order directly from the prescription | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
166 | 843 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.42 | PAT-42 | Patient app — start HomeoMeds order from eRx | PAT-42.02 | Wire to the Phase 8–15 API for: Order start | New | Patient Mobile | §2.7 | Order start | Start an order directly from the prescription | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
167 | 844 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.42 | PAT-42 | Patient app — start HomeoMeds order from eRx | PAT-42.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.7 | Order start | Start an order directly from the prescription | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
168 | 845 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.42 | PAT-42 | Patient app — start HomeoMeds order from eRx | PAT-42.04 | QA both platforms: Order start matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.7 | Order start | Start an order directly from the prescription | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
169 | 846 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.43 | PAT-43 | Patient app — pharmacy selection and quote | PAT-43.01 | UI: Pharmacy selection & quote screens (empty, loading, error, offline) | New | Patient Mobile | §2.7 | Pharmacy selection & quote | Choose a licensed pharmacy and see the price before paying | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
170 | 847 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.43 | PAT-43 | Patient app — pharmacy selection and quote | PAT-43.02 | Wire to the Phase 8–15 API for: Pharmacy selection & quote | New | Patient Mobile | §2.7 | Pharmacy selection & quote | Choose a licensed pharmacy and see the price before paying | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
171 | 848 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.43 | PAT-43 | Patient app — pharmacy selection and quote | PAT-43.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.7 | Pharmacy selection & quote | Choose a licensed pharmacy and see the price before paying | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
172 | 849 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.43 | PAT-43 | Patient app — pharmacy selection and quote | PAT-43.04 | QA both platforms: Pharmacy selection & quote matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.7 | Pharmacy selection & quote | Choose a licensed pharmacy and see the price before paying | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
173 | 850 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.44 | PAT-44 | Patient app — order review and consent | PAT-44.01 | UI: Order review & consent screens (empty, loading, error, offline) | New | Patient Mobile | §2.7 | Order review & consent | Confirm and consent before the prescription is shared | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
174 | 851 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.44 | PAT-44 | Patient app — order review and consent | PAT-44.02 | Wire to the Phase 8–15 API for: Order review & consent | New | Patient Mobile | §2.7 | Order review & consent | Confirm and consent before the prescription is shared | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
175 | 852 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.44 | PAT-44 | Patient app — order review and consent | PAT-44.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.7 | Order review & consent | Confirm and consent before the prescription is shared | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
176 | 853 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.44 | PAT-44 | Patient app — order review and consent | PAT-44.04 | QA both platforms: Order review & consent matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.7 | Order review & consent | Confirm and consent before the prescription is shared | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
177 | 854 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.45 | PAT-45 | Patient app — order tracking | PAT-45.01 | UI: Order tracking screens (empty, loading, error, offline) | New | Patient Mobile | §2.7 | Order tracking | Live status from accepted to delivered | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
178 | 855 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.45 | PAT-45 | Patient app — order tracking | PAT-45.02 | Wire to the Phase 8–15 API for: Order tracking | New | Patient Mobile | §2.7 | Order tracking | Live status from accepted to delivered | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
179 | 856 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.45 | PAT-45 | Patient app — order tracking | PAT-45.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.7 | Order tracking | Live status from accepted to delivered | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
180 | 857 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.45 | PAT-45 | Patient app — order tracking | PAT-45.04 | QA both platforms: Order tracking matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.7 | Order tracking | Live status from accepted to delivered | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
181 | 858 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.46 | PAT-46 | Patient app — order detail and refill | PAT-46.01 | UI: Order detail & refill screens (empty, loading, error, offline) | New | Patient Mobile | §2.7 | Order detail & refill | Full order history and one-tap refill request | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
182 | 859 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.46 | PAT-46 | Patient app — order detail and refill | PAT-46.02 | Wire to the Phase 8–15 API for: Order detail & refill | New | Patient Mobile | §2.7 | Order detail & refill | Full order history and one-tap refill request | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
183 | 860 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.46 | PAT-46 | Patient app — order detail and refill | PAT-46.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.7 | Order detail & refill | Full order history and one-tap refill request | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
184 | 861 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.46 | PAT-46 | Patient app — order detail and refill | PAT-46.04 | QA both platforms: Order detail & refill matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.7 | Order detail & refill | Full order history and one-tap refill request | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
185 | 862 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.47 | PAT-47 | Patient app — write a review | PAT-47.01 | UI: Write a review screens (empty, loading, error, offline) | New | Patient Mobile | §2.8 | Write a review | Rate and review the consultation | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
186 | 863 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.47 | PAT-47 | Patient app — write a review | PAT-47.02 | Wire to the Phase 8–15 API for: Write a review | New | Patient Mobile | §2.8 | Write a review | Rate and review the consultation | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
187 | 864 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.47 | PAT-47 | Patient app — write a review | PAT-47.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.8 | Write a review | Rate and review the consultation | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
188 | 865 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.47 | PAT-47 | Patient app — write a review | PAT-47.04 | QA both platforms: Write a review matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.8 | Write a review | Rate and review the consultation | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
189 | 866 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.48 | PAT-48 | Patient app — my reviews and appeal | PAT-48.01 | UI: My reviews & appeal screens (empty, loading, error, offline) | New | Patient Mobile | §2.8 | My reviews & appeal | Manage reviews and raise an appeal | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
190 | 867 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.48 | PAT-48 | Patient app — my reviews and appeal | PAT-48.02 | Wire to the Phase 8–15 API for: My reviews & appeal | New | Patient Mobile | §2.8 | My reviews & appeal | Manage reviews and raise an appeal | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
191 | 868 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.48 | PAT-48 | Patient app — my reviews and appeal | PAT-48.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.8 | My reviews & appeal | Manage reviews and raise an appeal | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
192 | 869 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.48 | PAT-48 | Patient app — my reviews and appeal | PAT-48.04 | QA both platforms: My reviews & appeal matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.8 | My reviews & appeal | Manage reviews and raise an appeal | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
193 | 870 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.49 | PAT-49 | Patient app — payments and refunds | PAT-49.01 | UI: Payments & refunds screens (empty, loading, error, offline) | New | Patient Mobile | §2.8 | Payments & refunds | Full payment history and refund status | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
194 | 871 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.49 | PAT-49 | Patient app — payments and refunds | PAT-49.02 | Wire to the Phase 8–15 API for: Payments & refunds | New | Patient Mobile | §2.8 | Payments & refunds | Full payment history and refund status | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
195 | 872 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.49 | PAT-49 | Patient app — payments and refunds | PAT-49.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.8 | Payments & refunds | Full payment history and refund status | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
196 | 873 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.49 | PAT-49 | Patient app — payments and refunds | PAT-49.04 | QA both platforms: Payments & refunds matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.8 | Payments & refunds | Full payment history and refund status | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
197 | 874 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.50 | PAT-50 | Patient app — profile and settings | PAT-50.01 | UI: Profile & settings screens (empty, loading, error, offline) | New | Patient Mobile | §2.8 | Profile & settings | Manage personal details and preferences | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
198 | 875 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.50 | PAT-50 | Patient app — profile and settings | PAT-50.02 | Wire to the Phase 8–15 API for: Profile & settings | New | Patient Mobile | §2.8 | Profile & settings | Manage personal details and preferences | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
199 | 876 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.50 | PAT-50 | Patient app — profile and settings | PAT-50.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.8 | Profile & settings | Manage personal details and preferences | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
200 | 877 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.50 | PAT-50 | Patient app — profile and settings | PAT-50.04 | QA both platforms: Profile & settings matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.8 | Profile & settings | Manage personal details and preferences | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
201 | 878 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.51 | PAT-51 | Patient app — consent centre and data rights | PAT-51.01 | UI: Consent centre & data rights screens (empty, loading, error, offline) | New | Patient Mobile | §2.8 | Consent centre & data rights | View, manage and withdraw consents; request data | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
202 | 879 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.51 | PAT-51 | Patient app — consent centre and data rights | PAT-51.02 | Wire to the Phase 8–15 API for: Consent centre & data rights | New | Patient Mobile | §2.8 | Consent centre & data rights | View, manage and withdraw consents; request data | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
203 | 880 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.51 | PAT-51 | Patient app — consent centre and data rights | PAT-51.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.8 | Consent centre & data rights | View, manage and withdraw consents; request data | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
204 | 881 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.51 | PAT-51 | Patient app — consent centre and data rights | PAT-51.04 | QA both platforms: Consent centre & data rights matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.8 | Consent centre & data rights | View, manage and withdraw consents; request data | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
205 | 882 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.52 | PAT-52 | Patient app — notifications centre | PAT-52.01 | UI: Notifications centre screens (empty, loading, error, offline) | New | Patient Mobile | §2.8 | Notifications centre | All alerts in one place | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
206 | 883 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.52 | PAT-52 | Patient app — notifications centre | PAT-52.02 | Wire to the Phase 8–15 API for: Notifications centre | New | Patient Mobile | §2.8 | Notifications centre | All alerts in one place | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
207 | 884 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.52 | PAT-52 | Patient app — notifications centre | PAT-52.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.8 | Notifications centre | All alerts in one place | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
208 | 885 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.52 | PAT-52 | Patient app — notifications centre | PAT-52.04 | QA both platforms: Notifications centre matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.8 | Notifications centre | All alerts in one place | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
209 | 886 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.53 | PAT-53 | Patient app — help centre and tickets | PAT-53.01 | UI: Help centre & support tickets screens (empty, loading, error, offline) | New | Patient Mobile | §2.9 | Help centre & support tickets | Raise an issue and track it to resolution | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
210 | 887 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.53 | PAT-53 | Patient app — help centre and tickets | PAT-53.02 | Wire to the Phase 8–15 API for: Help centre & support tickets | New | Patient Mobile | §2.9 | Help centre & support tickets | Raise an issue and track it to resolution | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
211 | 888 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.53 | PAT-53 | Patient app — help centre and tickets | PAT-53.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.9 | Help centre & support tickets | Raise an issue and track it to resolution | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
212 | 889 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.53 | PAT-53 | Patient app — help centre and tickets | PAT-53.04 | QA both platforms: Help centre & support tickets matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.9 | Help centre & support tickets | Raise an issue and track it to resolution | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
213 | 890 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.54 | PAT-54 | Patient app — physical clinic booking | PAT-54.01 | UI: Physical clinic appointment screens (empty, loading, error, offline) | New | Patient Mobile | §2.9 | Physical clinic appointment | Book an in-person visit as well as online | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
214 | 891 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.54 | PAT-54 | Patient app — physical clinic booking | PAT-54.02 | Wire to the Phase 8–15 API for: Physical clinic appointment | New | Patient Mobile | §2.9 | Physical clinic appointment | Book an in-person visit as well as online | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
215 | 892 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.54 | PAT-54 | Patient app — physical clinic booking | PAT-54.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.9 | Physical clinic appointment | Book an in-person visit as well as online | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
216 | 893 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.54 | PAT-54 | Patient app — physical clinic booking | PAT-54.04 | QA both platforms: Physical clinic appointment matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.9 | Physical clinic appointment | Book an in-person visit as well as online | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
217 | 894 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.55 | PAT-55 | Patient app — assisted booking request | PAT-55.01 | UI: Assisted booking screens (empty, loading, error, offline) | New | Patient Mobile | §2.9 | Assisted booking | Help for patients who need support booking | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
218 | 895 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.55 | PAT-55 | Patient app — assisted booking request | PAT-55.02 | Wire to the Phase 8–15 API for: Assisted booking | New | Patient Mobile | §2.9 | Assisted booking | Help for patients who need support booking | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
219 | 896 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.55 | PAT-55 | Patient app — assisted booking request | PAT-55.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.9 | Assisted booking | Help for patients who need support booking | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
220 | 897 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.55 | PAT-55 | Patient app — assisted booking request | PAT-55.04 | QA both platforms: Assisted booking matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.9 | Assisted booking | Help for patients who need support booking | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
221 | 898 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.56 | PAT-56 | Patient app — low-data mode | PAT-56.01 | UI: Low-data mode screens (empty, loading, error, offline) | New | Patient Mobile | §2.9 | Low-data mode | Works on slow or limited connections | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
222 | 899 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.56 | PAT-56 | Patient app — low-data mode | PAT-56.02 | Wire to the Phase 8–15 API for: Low-data mode | New | Patient Mobile | §2.9 | Low-data mode | Works on slow or limited connections | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
223 | 900 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.56 | PAT-56 | Patient app — low-data mode | PAT-56.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.9 | Low-data mode | Works on slow or limited connections | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
224 | 901 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.56 | PAT-56 | Patient app — low-data mode | PAT-56.04 | QA both platforms: Low-data mode matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.9 | Low-data mode | Works on slow or limited connections | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
225 | 902 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.57 | PAT-57 | Patient app — push notifications | PAT-57.01 | UI: Push notifications screens (empty, loading, error, offline) | New | Patient Mobile | §2.9 | Push notifications | Booking confirmations, reminders, doctor ready, prescription issued, order updates | Patient Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
226 | 903 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.57 | PAT-57 | Patient app — push notifications | PAT-57.02 | Wire to the Phase 8–15 API for: Push notifications | New | Patient Mobile | §2.9 | Push notifications | Booking confirmations, reminders, doctor ready, prescription issued, order updates | Patient Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
227 | 904 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.57 | PAT-57 | Patient app — push notifications | PAT-57.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.9 | Push notifications | Booking confirmations, reminders, doctor ready, prescription issued, order updates | Patient Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
228 | 905 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.57 | PAT-57 | Patient app — push notifications | PAT-57.04 | QA both platforms: Push notifications matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.9 | Push notifications | Booking confirmations, reminders, doctor ready, prescription issued, order updates | Patient Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
229 | 906 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.58 | PAT-58 | Patient app — iOS and Android store release, device matrix, and parity QA | PAT-58.01 | CI: iOS + Android release builds; env pointing to .NET 8 | New | Patient Mobile | §2 + §18 | Patient mobile app iOS and Android | iOS and Android — onboarding, discovery, booking, payment, video consultation, records, prescriptions, follow-up, medicines, reviews, support, notifications | Patient Mobile App | Mobile | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
230 | 907 | M17 | Patient mobile app | QA | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.58 | PAT-58 | Patient app — iOS and Android store release, device matrix, and parity QA | PAT-58.02 | Parity QA spreadsheet: each PAT-01..57 on both OS | Regression | Patient Mobile | §2 + §18 | Patient mobile app iOS and Android | iOS and Android — onboarding, discovery, booking, payment, video consultation, records, prescriptions, follow-up, medicines, reviews, support, notifications | Patient Mobile App | QA | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
231 | 908 | M17 | Patient mobile app | Mobile | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.58 | PAT-58 | Patient app — iOS and Android store release, device matrix, and parity QA | PAT-58.03 | Crashlytics/Sentry equivalent for patient app | New Integration | Patient Mobile | §2 + §18 | Patient mobile app iOS and Android | iOS and Android — onboarding, discovery, booking, payment, video consultation, records, prescriptions, follow-up, medicines, reviews, support, notifications | Patient Mobile App | Mobile | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | 2 | Not Started |  | EDIT HERE — this module sheet

## M18_Doctor_Mobile
M18 Doctor mobile app — 48 sub-tasks (Mobile 35 · QA 13). YELLOW = edit here (Assigned To, Frontend/Backend/Database/API/Mobile/Integration Status + Assigned). Scope Yes/No is fixed. Status N/A = that function is not in this sub-task. Master, Web/UI/Mobile/QA sheets and Dashboard follow these cells live. | [41 empty] | Live copy of 00_Employees column B — do not edit. New names appear here automatically.
Module Seq | Original Seq | Dev Module Code | Dev Module | Track | Phase | Phase Name | WBS | Main Task ID | Main Task | Sub Task ID | Sub Task | Work Type | Source Module / Area | PDF Section | PDF Feature (exact wording) | PDF Delivery Text | Application Surface | Layer | Assigned To (lead) | Frontend | Frontend Status | Frontend Assigned | Backend | Backend Status | Backend Assigned | Database | Database Status | Database Assigned | API | API Status | API Assigned | Mobile | Mobile Status | Mobile Assigned | Integration | Integration Status | Integration Assigned | Layers Remaining | Overall Status | Notes | Open Module Sheet | _EmpList
1 | 909 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.1 | DMO-01 | Doctor app — login & identity (same login and same account as the web portal) | DMO-01.01 | Login screen (password or OTP-to-registered mobile) | New | Doctor Mobile | §3 | Login & identity | Same login and same account as the web portal | Doctor Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Unassigned
2 | 910 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.1 | DMO-01 | Doctor app — login & identity (same login and same account as the web portal) | DMO-01.02 | Call same Login API; store JWT securely (Keychain/Keystore) | New | Doctor Mobile | §3 | Login & identity | Same login and same account as the web portal | Doctor Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
3 | 911 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.1 | DMO-01 | Doctor app — login & identity (same login and same account as the web portal) | DMO-01.03 | Expired session → re-login; no case-taking entry point | New | Doctor Mobile | §3 | Login & identity | Same login and same account as the web portal | Doctor Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Digvijay Jadhav
4 | 912 | M18 | Doctor mobile app | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.1 | DMO-01 | Doctor app — login & identity (same login and same account as the web portal) | DMO-01.04 | QA: same DoctorId as web; reception accounts must not open doctor clinical actions | Regression | Doctor Mobile | §3 | Login & identity | Same login and same account as the web portal | Doctor Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
5 | 913 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.2 | DMO-02 | Doctor app — first-run onboarding (guided setup, number confirmation and permissions) | DMO-02.01 | Onboarding screens | New | Doctor Mobile | §3 | First-run onboarding | Guided setup, number confirmation and permissions | Doctor Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
6 | 914 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.2 | DMO-02 | Doctor app — first-run onboarding (guided setup, number confirmation and permissions) | DMO-02.02 | Confirm number against profile | New | Doctor Mobile | §3 | First-run onboarding | Guided setup, number confirmation and permissions | Doctor Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
7 | 915 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.2 | DMO-02 | Doctor app — first-run onboarding (guided setup, number confirmation and permissions) | DMO-02.03 | Skip vs required steps documented | New | Doctor Mobile | §3 | First-run onboarding | Guided setup, number confirmation and permissions | Doctor Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
8 | 916 | M18 | Doctor mobile app | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.2 | DMO-02 | Doctor app — first-run onboarding (guided setup, number confirmation and permissions) | DMO-02.04 | QA: number mismatch blocked | Regression | Doctor Mobile | §3 | First-run onboarding | Guided setup, number confirmation and permissions | Doctor Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
9 | 917 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.3 | DMO-03 | Doctor app — notification permissions (push, microphone and camera handled properly) | DMO-03.01 | Permission primer + settings CTA | New | Doctor Mobile | §3 | Notification permissions | Push, microphone and camera permissions handled properly | Doctor Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Pranav Bandekar
10 | 918 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.3 | DMO-03 | Doctor app — notification permissions (push, microphone and camera handled properly) | DMO-03.02 | Register FCM/APNs token (COM-03) | New | Doctor Mobile | §3 | Notification permissions | Push, microphone and camera permissions handled properly | Doctor Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
11 | 919 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.3 | DMO-03 | Doctor app — notification permissions (push, microphone and camera handled properly) | DMO-03.03 | Denied-state UX | New | Doctor Mobile | §3 | Notification permissions | Push, microphone and camera permissions handled properly | Doctor Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
12 | 920 | M18 | Doctor mobile app | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.3 | DMO-03 | Doctor app — notification permissions (push, microphone and camera handled properly) | DMO-03.04 | QA: deny each permission independently | Regression | Doctor Mobile | §3 | Notification permissions | Push, microphone and camera permissions handled properly | Doctor Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
13 | 921 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.4 | DMO-04 | Doctor app — today’s queue & schedule (the full day at a glance) | DMO-04.01 | TodayQueue screen | New | Doctor Mobile | §3 | Today’s queue & schedule | The full day at a glance | Doctor Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
14 | 922 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.4 | DMO-04 | Doctor app — today’s queue & schedule (the full day at a glance) | DMO-04.02 | Existing appointment list APIs | New | Doctor Mobile | §3 | Today’s queue & schedule | The full day at a glance | Doctor Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
15 | 923 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.4 | DMO-04 | Doctor app — today’s queue & schedule (the full day at a glance) | DMO-04.03 | Pull-to-refresh; empty Sunday | New | Doctor Mobile | §3 | Today’s queue & schedule | The full day at a glance | Doctor Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
16 | 924 | M18 | Doctor mobile app | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.4 | DMO-04 | Doctor app — today’s queue & schedule (the full day at a glance) | DMO-04.04 | QA: parity with web counts | Regression | Doctor Mobile | §3 | Today’s queue & schedule | The full day at a glance | Doctor Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
17 | 925 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.5 | DMO-05 | Doctor app — availability toggle (go online or offline, set working hours) | DMO-05.01 | Availability + hours screens | New | Doctor Mobile | §3 | Availability toggle | Go online or offline, set working hours | Doctor Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
18 | 926 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.5 | DMO-05 | Doctor app — availability toggle (go online or offline, set working hours) | DMO-05.02 | TEL-01 + APT-07 APIs (hours read/edit policy: edit hours may stay web-only if product decides — PDF says set working hours so include) | New | Doctor Mobile | §3 | Availability toggle | Go online or offline, set working hours | Doctor Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
19 | 927 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.5 | DMO-05 | Doctor app — availability toggle (go online or offline, set working hours) | DMO-05.03 | Offline banner | New | Doctor Mobile | §3 | Availability toggle | Go online or offline, set working hours | Doctor Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
20 | 928 | M18 | Doctor mobile app | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.5 | DMO-05 | Doctor app — availability toggle (go online or offline, set working hours) | DMO-05.04 | QA: web and app status match within heartbeat | Regression | Doctor Mobile | §3 | Availability toggle | Go online or offline, set working hours | Doctor Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
21 | 929 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.6 | DMO-06 | Doctor app — push notifications (waiting, booking, reschedule, cancellation, refill, payment received) | DMO-06.01 | Notification handling + deep links into queue/refill/join | New | Doctor Mobile | §3 | Push notifications | Patient waiting, new booking, reschedule, cancellation, refill request, payment received | Doctor Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
22 | 930 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.6 | DMO-06 | Doctor app — push notifications (waiting, booking, reschedule, cancellation, refill, payment received) | DMO-06.02 | Device register | New | Doctor Mobile | §3 | Push notifications | Patient waiting, new booking, reschedule, cancellation, refill request, payment received | Doctor Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
23 | 931 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.6 | DMO-06 | Doctor app — push notifications (waiting, booking, reschedule, cancellation, refill, payment received) | DMO-06.03 | Foreground in-app banner | New | Doctor Mobile | §3 | Push notifications | Patient waiting, new booking, reschedule, cancellation, refill request, payment received | Doctor Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
24 | 932 | M18 | Doctor mobile app | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.6 | DMO-06 | Doctor app — push notifications (waiting, booking, reschedule, cancellation, refill, payment received) | DMO-06.04 | QA: each event type deep link | Regression | Doctor Mobile | §3 | Push notifications | Patient waiting, new booking, reschedule, cancellation, refill request, payment received | Doctor Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
25 | 933 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.7 | DMO-07 | Doctor app — patient context card (name, age, chief complaint and last visit) — NO case-taking | DMO-07.01 | PatientCard read-only | New | Doctor Mobile | §3 | Patient context card | Name, age, chief complaint and last visit before joining | Doctor Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
26 | 934 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.7 | DMO-07 | Doctor app — patient context card (name, age, chief complaint and last visit) — NO case-taking | DMO-07.02 | Context API (name, age, CC, last visit, payment, tele) | New | Doctor Mobile | §3 | Patient context card | Name, age, chief complaint and last visit before joining | Doctor Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
27 | 935 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.7 | DMO-07 | Doctor app — patient context card (name, age, chief complaint and last visit) — NO case-taking | DMO-07.03 | Do not ship case-taking tabs | New | Doctor Mobile | §3 | Patient context card | Name, age, chief complaint and last visit before joining | Doctor Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
28 | 936 | M18 | Doctor mobile app | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.7 | DMO-07 | Doctor app — patient context card (name, age, chief complaint and last visit) — NO case-taking | DMO-07.04 | QA: repertory endpoints never called from app | Regression | Doctor Mobile | §3 | Patient context card | Name, age, chief complaint and last visit before joining | Doctor Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
29 | 937 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.8 | DMO-08 | Doctor app — join consultation (video or audio from the phone) | DMO-08.01 | VideoRoom | New | Doctor Mobile | §3 | Join consultation | Start the video or audio consultation from the phone | Doctor Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
30 | 938 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.8 | DMO-08 | Doctor app — join consultation (video or audio from the phone) | DMO-08.02 | Tele session tokens | New | Doctor Mobile | §3 | Join consultation | Start the video or audio consultation from the phone | Doctor Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
31 | 939 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.8 | DMO-08 | Doctor app — join consultation (video or audio from the phone) | DMO-08.03 | Audio-only fallback | New | Doctor Mobile | §3 | Join consultation | Start the video or audio consultation from the phone | Doctor Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
32 | 940 | M18 | Doctor mobile app | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.8 | DMO-08 | Doctor app — join consultation (video or audio from the phone) | DMO-08.04 | QA: web patient + app doctor | Regression | Doctor Mobile | §3 | Join consultation | Start the video or audio consultation from the phone | Doctor Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
33 | 941 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.9 | DMO-09 | Doctor app — refill approval (approve or reject repeat prescription requests) | DMO-09.01 | RefillInbox + RefillDetail | New | Doctor Mobile | §3 + §11 | Refill approval | Approve or reject repeat prescription requests | Doctor Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
34 | 942 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.9 | DMO-09 | Doctor app — refill approval (approve or reject repeat prescription requests) | DMO-09.02 | Approve/Reject APIs | New | Doctor Mobile | §3 + §11 | Refill approval | Approve or reject repeat prescription requests | Doctor Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
35 | 943 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.9 | DMO-09 | Doctor app — refill approval (approve or reject repeat prescription requests) | DMO-09.03 | Show codes vs names per policy (doctor sees names) | New | Doctor Mobile | §3 + §11 | Refill approval | Approve or reject repeat prescription requests | Doctor Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
36 | 944 | M18 | Doctor mobile app | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.9 | DMO-09 | Doctor app — refill approval (approve or reject repeat prescription requests) | DMO-09.04 | QA: reject reason; cannot edit snapshot | Regression | Doctor Mobile | §3 + §11 | Refill approval | Approve or reject repeat prescription requests | Doctor Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
37 | 945 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.10 | DMO-10 | Doctor app — earnings summary (today, this week, this month, with payout status) | DMO-10.01 | Earnings screens | New | Doctor Mobile | §3 + §16 | Earnings summary | Today, this week and this month, with payout status | Doctor Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
38 | 946 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.10 | DMO-10 | Doctor app — earnings summary (today, this week, this month, with payout status) | DMO-10.02 | GET Earnings/Summary | New | Doctor Mobile | §3 + §16 | Earnings summary | Today, this week and this month, with payout status | Doctor Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
39 | 947 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.10 | DMO-10 | Doctor app — earnings summary (today, this week, this month, with payout status) | DMO-10.03 | Empty first week | New | Doctor Mobile | §3 + §16 | Earnings summary | Today, this week and this month, with payout status | Doctor Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
40 | 948 | M18 | Doctor mobile app | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.10 | DMO-10 | Doctor app — earnings summary (today, this week, this month, with payout status) | DMO-10.04 | QA: matches /account figures ± rounding | Regression | Doctor Mobile | §3 + §16 | Earnings summary | Today, this week and this month, with payout status | Doctor Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
41 | 949 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.11 | DMO-11 | Doctor app — offline handling (weak connection or expired session) | DMO-11.01 | Offline/error screens | New | Doctor Mobile | §3 | Offline handling | Clear behaviour on weak connection or expired session | Doctor Mobile App | Mobile UI | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
42 | 950 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.11 | DMO-11 | Doctor app — offline handling (weak connection or expired session) | DMO-11.02 | 401 interceptor → logout API | New | Doctor Mobile | §3 | Offline handling | Clear behaviour on weak connection or expired session | Doctor Mobile App | Mobile client | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
43 | 951 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.11 | DMO-11 | Doctor app — offline handling (weak connection or expired session) | DMO-11.03 | No silent retry of payments | New | Doctor Mobile | §3 | Offline handling | Clear behaviour on weak connection or expired session | Doctor Mobile App | Mobile UX | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
44 | 952 | M18 | Doctor mobile app | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.11 | DMO-11 | Doctor app — offline handling (weak connection or expired session) | DMO-11.04 | QA: airplane mode on join | Regression | Doctor Mobile | §3 | Offline handling | Clear behaviour on weak connection or expired session | Doctor Mobile App | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
45 | 953 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.12 | DMO-12 | Doctor app — reliability monitoring (failures reported automatically) | DMO-12.01 | Integrate Crashlytics/Sentry; map to doctorId hashed | New Integration | Doctor Mobile | §3 | Reliability monitoring | Failures are reported automatically, not left to a phone call | Doctor Mobile App | Mobile | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | 2 | Not Started |  | EDIT HERE — this module sheet
46 | 954 | M18 | Doctor mobile app | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.12 | DMO-12 | Doctor app — reliability monitoring (failures reported automatically) | DMO-12.02 | QA: simulated crash + join fail event | Regression | Doctor Mobile | §3 | Reliability monitoring | Failures are reported automatically, not left to a phone call | Doctor Mobile App | QA | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
47 | 955 | M18 | Doctor mobile app | Mobile | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.13 | DMO-13 | Doctor app — iOS and Android parity QA (queue, availability, notifications, context, video, refill, earnings) | DMO-13.01 | Release builds both OS | New | Doctor Mobile | §3 + §18 | Doctor mobile app iOS and Android | iOS and Android — queue, availability, notifications, patient context, video consultation, refill approval, earnings | Doctor Mobile App | Mobile | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
48 | 956 | M18 | Doctor mobile app | QA | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.13 | DMO-13 | Doctor app — iOS and Android parity QA (queue, availability, notifications, context, video, refill, earnings) | DMO-13.02 | Parity QA DMO-01..12 both OS | Regression | Doctor Mobile | §3 + §18 | Doctor mobile app iOS and Android | iOS and Android — queue, availability, notifications, patient context, video consultation, refill approval, earnings | Doctor Mobile App | QA | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet

## M19_Reports_NFR_Gate
M19 Reports, NFR & delivery gate — 44 sub-tasks (Web 18 · UI 9 · QA 17). YELLOW = edit here (Assigned To, Frontend/Backend/Database/API/Mobile/Integration Status + Assigned). Scope Yes/No is fixed. Status N/A = that function is not in this sub-task. Master, Web/UI/Mobile/QA sheets and Dashboard follow these cells live. | [41 empty] | Live copy of 00_Employees column B — do not edit. New names appear here automatically.
Module Seq | Original Seq | Dev Module Code | Dev Module | Track | Phase | Phase Name | WBS | Main Task ID | Main Task | Sub Task ID | Sub Task | Work Type | Source Module / Area | PDF Section | PDF Feature (exact wording) | PDF Delivery Text | Application Surface | Layer | Assigned To (lead) | Frontend | Frontend Status | Frontend Assigned | Backend | Backend Status | Backend Assigned | Database | Database Status | Database Assigned | API | API Status | API Assigned | Mobile | Mobile Status | Mobile Assigned | Integration | Integration Status | Integration Assigned | Layers Remaining | Overall Status | Notes | Open Module Sheet | _EmpList
1 | 957 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.1 | RPT-01 | Admin overview dashboard — platform-wide activity at a glance (replace Velzon ecommerce) | RPT-01.01 | No ecommerce tables | Existing Improvement | Reports | §16 + §7.2 | Admin overview dashboard / Admin dashboard | Platform-wide activity at a glance / Live overview of the whole platform | Admin Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Unassigned
2 | 958 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.1 | RPT-01 | Admin overview dashboard — platform-wide activity at a glance (replace Velzon ecommerce) | RPT-01.02 | GET /api/AdminDashboard/Overview | Existing Improvement | Reports | §16 + §7.2 | Admin overview dashboard / Admin dashboard | Platform-wide activity at a glance / Live overview of the whole platform | Admin Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
3 | 959 | M19 | Reports, NFR & delivery gate | UI | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.1 | RPT-01 | Admin overview dashboard — platform-wide activity at a glance (replace Velzon ecommerce) | RPT-01.03 | Replace pages/Admin/Dashboard; getHomeDashboardPath → /admin/dashboard | Existing Improvement | Reports | §16 + §7.2 | Admin overview dashboard / Admin dashboard | Platform-wide activity at a glance / Live overview of the whole platform | Admin Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Digvijay Jadhav
4 | 960 | M19 | Reports, NFR & delivery gate | QA | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.1 | RPT-01 | Admin overview dashboard — platform-wide activity at a glance (replace Velzon ecommerce) | RPT-01.04 | QA: login as admin never shows fake store visits | Regression | Reports | §16 + §7.2 | Admin overview dashboard / Admin dashboard | Platform-wide activity at a glance / Live overview of the whole platform | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
5 | 961 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.2 | RPT-02 | Doctor practice statistics — patient and consultation trends (extend existing charts) | RPT-02.01 | No new warehouse required for v1 | Existing Improvement | Reports | §16 + §5.1 | Doctor practice statistics | Patient and consultation trends | Doctor Web | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
6 | 962 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.2 | RPT-02 | Doctor practice statistics — patient and consultation trends (extend existing charts) | RPT-02.02 | Extend GetPatientStatsCharts with VisitType/ConsultMode | Existing Improvement | Reports | §16 + §5.1 | Doctor practice statistics | Patient and consultation trends | Doctor Web | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
7 | 963 | M19 | Reports, NFR & delivery gate | UI | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.2 | RPT-02 | Doctor practice statistics — patient and consultation trends (extend existing charts) | RPT-02.03 | Dashboard charts consume new series | Existing Improvement | Reports | §16 + §5.1 | Doctor practice statistics | Patient and consultation trends | Doctor Web | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
8 | 964 | M19 | Reports, NFR & delivery gate | QA | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.2 | RPT-02 | Doctor practice statistics — patient and consultation trends (extend existing charts) | RPT-02.04 | QA: empty new clinic | Regression | Reports | §16 + §5.1 | Doctor practice statistics | Patient and consultation trends | Doctor Web | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
9 | 965 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.3 | RPT-03 | Follow-up analysis — due/overdue patients and follow-up conversion | RPT-03.01 | Queries on VisitType + FollowUpTask | New | Reports | §16 | Follow-up analysis | Which patients are due or overdue for follow-up, and follow-up conversion | Doctor Web | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Pranav Bandekar
10 | 966 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.3 | RPT-03 | Follow-up analysis — due/overdue patients and follow-up conversion | RPT-03.02 | GET FollowUpDue, FollowUpSummary | New | Reports | §16 | Follow-up analysis | Which patients are due or overdue for follow-up, and follow-up conversion | Doctor Web | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
11 | 967 | M19 | Reports, NFR & delivery gate | UI | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.3 | RPT-03 | Follow-up analysis — due/overdue patients and follow-up conversion | RPT-03.03 | /doctor/follow-up-analysis | New | Reports | §16 | Follow-up analysis | Which patients are due or overdue for follow-up, and follow-up conversion | Doctor Web | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
12 | 968 | M19 | Reports, NFR & delivery gate | QA | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.3 | RPT-03 | Follow-up analysis — due/overdue patients and follow-up conversion | RPT-03.04 | QA: overdue vs due buckets | Regression | Reports | §16 | Follow-up analysis | Which patients are due or overdue for follow-up, and follow-up conversion | Doctor Web | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
13 | 969 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.4 | RPT-04 | Clinic performance analysis — appointments, slot utilisation, no-shows, cancellations, waiting time and revenue | RPT-04.01 | Aggregate APIs beyond GetPatientStatsCharts | New | Reports | §16 | Clinic performance analysis | Appointments, slot utilisation, no-shows, cancellations, waiting time and revenue | Doctor Web | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
14 | 970 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.4 | RPT-04 | Clinic performance analysis — appointments, slot utilisation, no-shows, cancellations, waiting time and revenue | RPT-04.02 | GET ClinicPerformance | New | Reports | §16 | Clinic performance analysis | Appointments, slot utilisation, no-shows, cancellations, waiting time and revenue | Doctor Web | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet | Gourav Nikam
15 | 971 | M19 | Reports, NFR & delivery gate | UI | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.4 | RPT-04 | Clinic performance analysis — appointments, slot utilisation, no-shows, cancellations, waiting time and revenue | RPT-04.03 | /doctor/clinic-performance | New | Reports | §16 | Clinic performance analysis | Appointments, slot utilisation, no-shows, cancellations, waiting time and revenue | Doctor Web | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
16 | 972 | M19 | Reports, NFR & delivery gate | QA | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.4 | RPT-04 | Clinic performance analysis — appointments, slot utilisation, no-shows, cancellations, waiting time and revenue | RPT-04.04 | QA: cancelled excluded from completed; revenue uses ledger not client | Regression | Reports | §16 | Clinic performance analysis | Appointments, slot utilisation, no-shows, cancellations, waiting time and revenue | Doctor Web | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
17 | 973 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.5 | RPT-05 | Payment reconciliation report — bookings matched against payments | RPT-05.01 | CSV/PDF export of FIN-02 query | New | Reports | §16 + §7.2 | Payment reconciliation report / Consult booking & payment reconciliation | Bookings matched against payments / Match every booking against every payment | Admin + Account | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
18 | 974 | M19 | Reports, NFR & delivery gate | UI | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.5 | RPT-05 | Payment reconciliation report — bookings matched against payments | RPT-05.02 | Report UI on admin/account recon screens | New | Reports | §16 + §7.2 | Payment reconciliation report / Consult booking & payment reconciliation | Bookings matched against payments / Match every booking against every payment | Admin + Account | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
19 | 975 | M19 | Reports, NFR & delivery gate | QA | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.5 | RPT-05 | Payment reconciliation report — bookings matched against payments | RPT-05.03 | QA: unmatched rows included | Regression | Reports | §16 + §7.2 | Payment reconciliation report / Consult booking & payment reconciliation | Bookings matched against payments / Match every booking against every payment | Admin + Account | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
20 | 976 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.6 | RPT-06 | Settlement & payout reports — amounts due and paid to doctors and pharmacies | RPT-06.01 | Export settlement runs + payout register | New | Reports | §16 + §8 | Settlement & payout reports | Amounts due and paid to doctors and pharmacies | Account | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
21 | 977 | M19 | Reports, NFR & delivery gate | UI | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.6 | RPT-06 | Settlement & payout reports — amounts due and paid to doctors and pharmacies | RPT-06.02 | Report UI | New | Reports | §16 + §8 | Settlement & payout reports | Amounts due and paid to doctors and pharmacies | Account | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
22 | 978 | M19 | Reports, NFR & delivery gate | QA | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.6 | RPT-06 | Settlement & payout reports — amounts due and paid to doctors and pharmacies | RPT-06.03 | QA: pharmacy lines appear only after HomeoMeds | Regression | Reports | §16 + §8 | Settlement & payout reports | Amounts due and paid to doctors and pharmacies | Account | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
23 | 979 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.7 | RPT-07 | GST & invoice reports (reporting surface of FIN-08) | RPT-07.01 | Confirm CA format; implement export if not already in FIN-08 | New | Reports | §16 + §8 | GST & invoice reports | Tax reporting | Account | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
24 | 980 | M19 | Reports, NFR & delivery gate | QA | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.7 | RPT-07 | GST & invoice reports (reporting surface of FIN-08) | RPT-07.02 | QA: number series gaps flagged | Regression | Reports | §16 + §8 | GST & invoice reports | Tax reporting | Account | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
25 | 981 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.8 | RPT-08 | Doctor earnings summary — daily, weekly and monthly earnings with payout status (web + same API as DMO-10) | RPT-08.01 | Reuse earnings API | New | Reports | §16 + §3 | Doctor earnings summary | Daily, weekly and monthly earnings with payout status | Doctor Web + App | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
26 | 982 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.8 | RPT-08 | Doctor earnings summary — daily, weekly and monthly earnings with payout status (web + same API as DMO-10) | RPT-08.02 | GET Earnings/Summary already for app — add if missing date buckets | New | Reports | §16 + §3 | Doctor earnings summary | Daily, weekly and monthly earnings with payout status | Doctor Web + App | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
27 | 983 | M19 | Reports, NFR & delivery gate | UI | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.8 | RPT-08 | Doctor earnings summary — daily, weekly and monthly earnings with payout status (web + same API as DMO-10) | RPT-08.03 | /doctor/earnings | New | Reports | §16 + §3 | Doctor earnings summary | Daily, weekly and monthly earnings with payout status | Doctor Web + App | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
28 | 984 | M19 | Reports, NFR & delivery gate | QA | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.8 | RPT-08 | Doctor earnings summary — daily, weekly and monthly earnings with payout status (web + same API as DMO-10) | RPT-08.04 | QA: payout pending vs paid | Regression | Reports | §16 + §3 | Doctor earnings summary | Daily, weekly and monthly earnings with payout status | Doctor Web + App | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
29 | 985 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.9 | RPT-09 | Medicine order reports — order volumes, fulfilment and exceptions | RPT-09.01 | Aggregates on MedicineOrder | New | Reports | §16 + §12 | Medicine order reports | Order volumes, fulfilment and exceptions | Admin + Account | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
30 | 986 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.9 | RPT-09 | Medicine order reports — order volumes, fulfilment and exceptions | RPT-09.02 | GET medicine order report | New | Reports | §16 + §12 | Medicine order reports | Order volumes, fulfilment and exceptions | Admin + Account | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
31 | 987 | M19 | Reports, NFR & delivery gate | UI | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.9 | RPT-09 | Medicine order reports — order volumes, fulfilment and exceptions | RPT-09.03 | Admin/account report page | New | Reports | §16 + §12 | Medicine order reports | Order volumes, fulfilment and exceptions | Admin + Account | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
32 | 988 | M19 | Reports, NFR & delivery gate | QA | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.9 | RPT-09 | Medicine order reports — order volumes, fulfilment and exceptions | RPT-09.04 | QA: cancelled orders not counted as delivered | Regression | Reports | §16 + §12 | Medicine order reports | Order volumes, fulfilment and exceptions | Admin + Account | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
33 | 989 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.10 | RPT-10 | Platform users remaining 20% — import, export and activation control | RPT-10.01 | VerificationStatus on user/doctor list DTO | Existing Improvement | Admin | §7.2 | Platform users | Manage all users with import, export and activation control | Admin Portal | Database | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
34 | 990 | M19 | Reports, NFR & delivery gate | Web | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.10 | RPT-10 | Platform users remaining 20% — import, export and activation control | RPT-10.02 | User import/export APIs if missing | Existing Improvement | Admin | §7.2 | Platform users | Manage all users with import, export and activation control | Admin Portal | API | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
35 | 991 | M19 | Reports, NFR & delivery gate | UI | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.10 | RPT-10 | Platform users remaining 20% — import, export and activation control | RPT-10.03 | ListUser.js wire dead buttons; verification column | Existing Improvement | Admin | §7.2 | Platform users | Manage all users with import, export and activation control | Admin Portal | Web SPA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 2 | Not Started |  | EDIT HERE — this module sheet
36 | 992 | M19 | Reports, NFR & delivery gate | QA | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.10 | RPT-10 | Platform users remaining 20% — import, export and activation control | RPT-10.04 | QA: export contains only permitted fields | Regression | Admin | §7.2 | Platform users | Manage all users with import, export and activation control | Admin Portal | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
37 | 993 | M19 | Reports, NFR & delivery gate | QA | 19 | Phase 19 — Cross-surface QA, NFR, delivery summary gate (PDF §1 + §18) | 19.1 | QA-01 | One ecosystem proof — patient, appointment, prescription and payment created anywhere are visible everywhere | QA-01.01 | E2E: Reception creates patient+appt → Doctor board → sign eRx → Patient app sees codes → Pharmacy accept OTP → patient sees names+pay → Account ledger S2 and S5 | Regression | QA | §1 + §18 | One connected ecosystem | A patient, an appointment, a prescription and a payment created anywhere in the system are visible everywhere else | All | QA | Unassigned | Yes | Not Started | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 3 | Not Started |  | EDIT HERE — this module sheet
38 | 994 | M19 | Reports, NFR & delivery gate | QA | 19 | Phase 19 — Cross-surface QA, NFR, delivery summary gate (PDF §1 + §18) | 19.1 | QA-01 | One ecosystem proof — patient, appointment, prescription and payment created anywhere are visible everywhere | QA-01.02 | E2E: Patient app books+pays tele → doctor app join → summary+eRx → refill on doctor app | Regression | QA | §1 + §18 | One connected ecosystem | A patient, an appointment, a prescription and a payment created anywhere in the system are visible everywhere else | All | QA | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
39 | 995 | M19 | Reports, NFR & delivery gate | QA | 19 | Phase 19 — Cross-surface QA, NFR, delivery summary gate (PDF §1 + §18) | 19.1 | QA-01 | One ecosystem proof — patient, appointment, prescription and payment created anywhere are visible everywhere | QA-01.03 | Negative: Admin cannot payout; Account cannot edit repertory | Regression | QA | §1 + §18 | One connected ecosystem | A patient, an appointment, a prescription and a payment created anywhere in the system are visible everywhere else | All | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
40 | 996 | M19 | Reports, NFR & delivery gate | QA | 19 | Phase 19 — Cross-surface QA, NFR, delivery summary gate (PDF §1 + §18) | 19.2 | QA-02 | Delivery summary gate — every area in PDF §18 signed off | QA-02.01 | Traceability review: 01_PDF_Coverage every row has Main Task ID and final Status | Regression | QA | §18 | Summary of delivery | All features listed in this document are included in the delivery scope. | Programme | QA | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 0 | N/A |  | EDIT HERE — this module sheet
41 | 997 | M19 | Reports, NFR & delivery gate | QA | 19 | Phase 19 — Cross-surface QA, NFR, delivery summary gate (PDF §1 + §18) | 19.2 | QA-02 | Delivery summary gate — every area in PDF §18 signed off | QA-02.02 | Do not ship Velzon demo tickets/KYC/ecommerce as product | Regression | QA | §18 | Summary of delivery | All features listed in this document are included in the delivery scope. | Programme | QA | Unassigned | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
42 | 998 | M19 | Reports, NFR & delivery gate | Web | 19 | Phase 19 — Cross-surface QA, NFR, delivery summary gate (PDF §1 + §18) | 19.3 | NFR-01 | NFR — performance, low-data, reliability, secrets, dual-API freeze | NFR-01.01 | Rotate API secrets; keys in config/KeyVault; directory browsing remains off | Existing Modification | NFR | §2.9 + §3 + §17 | Low-data mode / Reliability monitoring / Secure login | Works on slow connections; failures reported automatically; credentials protected | All | Security | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
43 | 999 | M19 | Reports, NFR & delivery gate | QA | 19 | Phase 19 — Cross-surface QA, NFR, delivery summary gate (PDF §1 + §18) | 19.3 | NFR-01 | NFR — performance, low-data, reliability, secrets, dual-API freeze | NFR-01.02 | Performance: slot lock under concurrent public booking | Regression | NFR | §2.9 + §3 + §17 | Low-data mode / Reliability monitoring / Secure login | Works on slow connections; failures reported automatically; credentials protected | All | QA | Unassigned | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet
44 | 1000 | M19 | Reports, NFR & delivery gate | QA | 19 | Phase 19 — Cross-surface QA, NFR, delivery summary gate (PDF §1 + §18) | 19.3 | NFR-01 | NFR — performance, low-data, reliability, secrets, dual-API freeze | NFR-01.03 | Patient low-data mode QA on 2G profile | Regression | NFR | §2.9 + §3 + §17 | Low-data mode / Reliability monitoring / Secure login | Works on slow connections; failures reported automatically; credentials protected | All | QA | Unassigned | No | N/A |  | No | N/A |  | No | N/A |  | No | N/A |  | Yes | Not Started | Unassigned | No | N/A |  | 1 | Not Started |  | EDIT HERE — this module sheet

## ModMap (hidden)
Code | Sheet
M00 | M00_PRE_Client_Gates
M01 | M01_Foundation_Security
M02 | M02_Admin_Clinical
M03 | M03_Clinical_Workspace
M04 | M04_Doctor_Daily_Ops
M05 | M05_Appointments
M06 | M06_Reception
M07 | M07_Payments
M08 | M08_Account_Finance
M09 | M09_Trust
M10 | M10_Patient_Website
M11 | M11_Digital_eRx
M12 | M12_Telemedicine
M13 | M13_Communications
M14 | M14_Support
M15 | M15_HomeoMeds
M16 | M16_Patient_APIs
M17 | M17_Patient_Mobile
M18 | M18_Doctor_Mobile
M19 | M19_Reports_NFR_Gate