## 00_Cover
HOMEOCENTRUM — FEATURE DELIVERY TASK REGISTER
Source: Homeocentrum_Feature_Delivery_Document.pdf · Prepared for Homeocentrum / NIGA · 29 August 2026
How to use this workbook for development
1. Develop strictly by Seq on sheet 03_Sequential_Register. Do not skip a Seq because a later PDF section looks more exciting (Patient App is Phase 16 because it consumes APIs built in Phases 0–15).
2. One PDF feature = one Main Task. Sub Tasks are the actual development steps (DB → API → UI/Mobile → Integration → QA).
3. Work Type tells you whether to KEEP, IMPROVE, CHANGE, or BUILD NEW. Existing = do not rebuild. Existing Improvement = finish what is stub/partial. Existing Modification = behaviour must change. New = not in the three repos today.
4. Depends On must be Done (or explicitly waived) before starting a row. Status dropdown: Not Started / In Progress / Blocked / Done / Deferred.
5. Sheet 01_PDF_Coverage is the line-by-line trace to the PDF. If a PDF feature is missing there, it is a defect in this register — add it before coding.
6. Shared APIs are built once on the earliest surface (usually Doctor/Admin/Account). Later Patient Website and Mobile rows are clients of those APIs, not a second money or appointment system.
7. Five web portals in the PDF: Patient Website, Doctor Web, Reception, Admin, Account. Two mobile apps: Patient, Doctor. Pharmacy console is part of HomeoMeds (PDF §12), not a sixth portal in the §1 count.
8. All new domain modules go on NigaHomeopathy-API (.NET 8). Do not create a third API. Classic API stays only where login / Rx write / Razorpay already live until ported (Phase 6 ports payments).
9. Account controls money. Admin controls platform and clinical data. Neither performs the other’s role (PDF §8).
10. Webhook/bank is payment source of truth — never the patient’s screen (PDF §9).
Development sequence (why this order)
Phase | Name | Why this phase sits here
PRE | Client gates | Settlement model, cash policy, GST, vendors, legal copy — block money and telemedicine if unsigned.
0 | Foundation | Shared keys, six roles, login/reset/session/RBAC, consent, OTP, audit, secure documents (PDF §1 + §17).
1 | Admin clinical masters | Keep live repertory/MM/diagnosis/drugs/questions/3D (PDF §7.1) — do not rebuild.
2 | Doctor clinical workspace | Patient Board remaining work + Center of Gravity (PDF §5.3).
3 | Doctor daily ops | Dashboard, patients, reception staff UI, real doctor profile (PDF §5.1).
4 | Appointments | Visit type/mode, formal reschedule/cancel, schedule screen, payment status column (PDF §5.2).
5 | Reception portal | Front-desk chrome, queue, case paper, schedule view (PDF §6).
6 | Payment system | Homeocentrum merchant of record, webhook, consult pay, reception collect, refunds, invoices (PDF §9).
7 | Account department | Ledger, recon, settlements, OTP payouts, SoD (PDF §8).
8 | Trust | Credentialing and practice gate BEFORE public directory (PDF §13).
9 | Patient website | Discovery, self-booking, public pay, legal, waitlist (PDF §4).
10 | Digital prescription | Potency, signed lock, notes≠eRx, codes (PDF §11).
11 | Telemedicine | Availability, video, consent, rejoin, instant (PDF §10).
12 | Communications | SMS, WhatsApp remaining, push, email, in-app (PDF §14).
13 | Support | Tickets, enquiry inbox, help, assisted booking (PDF §15).
14 | HomeoMeds | Pharmacy network, routing, quotes, COD, exceptions (PDF §12).
15 | Patient continuity APIs | Family, caregiver, diary, follow-up, consent centre — before the app.
16 | Patient mobile | Every PDF §2 row as a screen on those APIs.
17 | Doctor mobile | Every PDF §3 row — no case-taking on phone.
18 | Reports | Every PDF §16 report after data exists.
19 | Delivery gate | E2E ecosystem proof + §18 summary sign-off.
Work Type legend
Existing | Live in Admin/Doctor/Reception today. Keep. Regression + ACL only — do not rebuild.
Existing Improvement | Screen or API exists but is stub, fake-wired, partial, or missing a role surface.
Existing Modification | Exists but behaviour must change (plaintext passwords, auto-activate doctors, client-only Razorpay success).
New | No product screen/API in the three repos.
New Integration | Vendor/gateway (Razorpay webhook, video SDK, SMS, FCM/APNs).
Configuration | Rates, flags, templates — not hardcoded.
Data Migration | Additive schema / password hash backfill.
Client Decision | Blocks engineering until signed (PRE phase).
Regression | Prove an Existing or earlier-phase surface still works.
Generated counts — Main tasks: 280 · Sub tasks: 1000 · PDF feature lines mapped: 280

## 01_PDF_Coverage
LINE-BY-LINE TRACEABILITY — every feature row in Homeocentrum_Feature_Delivery_Document.pdf. Do not start Phase 19 until every row is Done or Deferred-with-sign.
Seq | PDF Section | PDF Feature (exact) | PDF Delivery Text | Work Type | Phase | Main Task ID | AS-IS in codebase | Status
1 | §9 + §8 | Every transaction passes through Homeocentrum | Built on the principle: every transaction passes through Homeocentrum, in the same way a food-delivery or quick-commerce platform holds all payments centrally. | Client Decision | PRE | PRE-01 | Only doctor SaaS subscription via client-side Razorpay; no consult/medicine ledger | Not Started
2 | §9 | Reception payment collection | Cash, UPI, card or payment link with printed receipt | Client Decision | PRE | PRE-02 | No reception collection; no S3 ledger | Not Started
3 | §10 + §14 + §17 | Telemedicine + notifications + consent | Video consultation; SMS/WhatsApp/Push/Email; consent records | Client Decision | PRE | PRE-03 | WhatsApp Meta Cloud partial; no video SDK; no SMS provider; no FCM; privacy/terms incomplete for DPDP/tele/pharmacy | Not Started
4 | §1 | One connected ecosystem serving six types of users | A patient, an appointment, a prescription and a payment created anywhere in the system are visible everywhere else — there are no separate systems to reconcile. | New | 0 | FND-01 | Doctor/Admin/Reception web only; Patient, Account, Pharmacy roles do not exist; no shared payment or eRx keys | Not Started
5 | §1 | Delivery covers | 2 mobile applications · 5 web portals · payment system · telemedicine · digital prescription · online medicine delivery. | New | 0 | FND-02 | 1 web SPA (Admin/Doctor/Reception + marketing). No patient app, doctor app, Account portal, Pharmacy console | Not Started
6 | §17 | Secure login | Protected credentials for every user type | Existing Modification | 0 | SEC-01 | POST /Account/Login on classic API; JWT in sessionStorage; doctor/user passwords compared plaintext; reception hashed on classic; fakeBackend() still mounted | Not Started
7 | §17 | Secure password reset | Time-limited reset links | Existing Modification | 0 | SEC-02 | /forgot-password UI exists; thunk uses fake/Firebase; POST /users/ForgetPassword emails plaintext password | Not Started
8 | §17 | Session control | Proper sign-out across web and mobile | Existing Improvement | 0 | SEC-03 | Client clears sessionStorage; no server logout / token revoke; UserLoginStatus unused | Not Started
9 | §17 | Role-based access | Each role sees only what it is permitted to see | Existing Improvement | 0 | SEC-04 | RoleMaster + RoleDetail + MenuMaster exist; GetMenuByRole commented out on .NET 8; no per-route frontend ACL — any authenticated URL works | Not Started
10 | §17 | Patient data protection | Health records restricted to the treating doctor and the patient | Existing Improvement | 0 | SEC-05 | Many repertory APIs have [Authorize] commented; directory browsing enabled for /attachments and /Blogs; no patient-scoped ACL on case data | Not Started
11 | §17 | Consent records | Every consent captured, stored and reviewable | New | 0 | SEC-06 | AudioCaseConsentLog exists for audio case taking only | Not Started
12 | §17 + §8 + §12 | OTP verification | Applied to sensitive actions including payouts and pharmacy acceptance | New | 0 | SEC-07 | No generic OTP control plane; patient OTP login does not exist | Not Started
13 | §17 + §9 | Complete audit trail | Who did what, and when, across payments, prescriptions and approvals / Every transaction traceable end to end by Homeocentrum | New | 0 | SEC-08 | No platform-wide audit; no AppointmentChangeLog; no payment webhook store | Not Started
14 | §17 | Secure documents | Prescriptions, reports and uploads protected from unauthorised access | New | 0 | SEC-09 | Attachments served with directory browsing; no signed URLs; no patient upload module | Not Started
15 | §7.1 | Repertory sections | Manage repertory sections | Existing | 1 | ADM-R01 | Admin Repertory section CRUD live (pages/Admin/Repertory) | Not Started
16 | §7.1 | Subsection & rubric tree | Manage the full rubric hierarchy | Existing | 1 | ADM-R02 | Hierarchical subsection/rubric tree + Excel import/export live | Not Started
17 | §7.1 | Rubric–remedy mapping | Map remedies to rubrics with author and grade | Existing | 1 | ADM-R03 | Rubric-remedy mapping by author/grade live | Not Started
18 | §7.1 | Remedy-linked rubrics | View all rubrics linked to a remedy | Existing | 1 | ADM-R04 | Remedial-rubrics viewer live | Not Started
19 | §7.1 | Language master | Manage languages | Existing | 1 | ADM-R05 | Language master live | Not Started
20 | §7.1 | Body part master | Manage body parts | Existing | 1 | ADM-R06 | Body part master live | Not Started
21 | §7.1 | Intensity master | Manage intensity levels | Existing | 1 | ADM-R07 | Intensity master live | Not Started
22 | §7.1 | Remedy master | Manage the remedy library | Existing | 1 | ADM-R08 | Remedy master live | Not Started
23 | §7.1 | Remedy grade master | Manage remedy grading | Existing | 1 | ADM-R09 | Remedy grade master live | Not Started
24 | §7.1 | Author master | Manage materia medica authors | Existing | 1 | ADM-M01 | Author master live | Not Started
25 | §7.1 | Materia medica master | Manage the materia medica library | Existing | 1 | ADM-M02 | MM master live | Not Started
26 | §7.1 | Materia medica heads | Manage chapter headings | Existing | 1 | ADM-M03 | MM heads live | Not Started
27 | §7.1 | Materia medica remedies | View remedy-wise materia medica | Existing | 1 | ADM-M04 | Remedy-wise MM viewer live | Not Started
28 | §7.1 | Diagnosis system | Manage diagnosis systems | Existing | 1 | ADM-D01 | Diagnosis system CRUD live | Not Started
29 | §7.1 | Diagnosis therapeutics | Manage therapeutics | Existing | 1 | ADM-D02 | Therapeutics details live | Not Started
30 | §7.1 | Diagnosis conditions | Manage conditions and linked rubrics | Existing | 1 | ADM-D03 | Conditions + keyword→rubric live | Not Started
31 | §7.1 | Drug system | Manage conventional drug systems | Existing | 1 | ADM-A01 | Drug system CRUD live | Not Started
32 | §7.1 | Drug group | Manage drug groups | Existing | 1 | ADM-A02 | Drug group CRUD live | Not Started
33 | §7.1 | Allopathic drug & side effects | Manage drugs with side effects and adverse reactions | Existing | 1 | ADM-A03 | Allopathic drug + serious/other/adverse live | Not Started
34 | §7.1 | Question section, group & sub-group | Manage the clinical questionnaire structure | Existing | 1 | ADM-Q01 | Existance / question group / subgroup CRUD live | Not Started
35 | §7.1 | Clinical question mapping | Map questions to body parts and rubrics | Existing | 1 | ADM-Q02 | Clinical questions mapped to body parts and rubrics live | Not Started
36 | §7.1 | 3D mesh key master | Manage 3D model references | Existing | 1 | ADM-3D1 | Mesh key master on .NET 8 live | Not Started
37 | §7.1 | 3D section master | Manage 3D body sections | Existing | 1 | ADM-3D2 | 3D section master live | Not Started
38 | §7.1 | 3D hotspots | Manage clickable points on the 3D model | Existing | 1 | ADM-3D3 | Hotspot master live; doctor viewer consumes them | Not Started
39 | §7.2 | Doctor qualifications | Manage the qualification list | Existing | 1 | ADM-B01 | Qualifications CRUD on newer API live; used by RegisterDoctor | Not Started
40 | §7.2 | Lab & imaging test catalog | Manage the test catalogue | Existing | 1 | ADM-B02 | Labs & imaging CRUD live; Patient Board orders from this catalogue | Not Started
41 | §7.2 | Subscription packages | Manage doctor subscription plans | Existing | 1 | ADM-B03 | Package CRUD live; Razorpay buy/renew partial (no webhook) | Not Started
42 | §7.2 | Roles & menu permissions | Control exactly what each role can access | Existing Improvement | 1 | ADM-B04 | Role CRUD screens live; runtime GetMenuByRole commented; no frontend route ACL | Not Started
43 | §5.3 | Clinical workspace | Single screen for the entire consultation | Existing Improvement | 2 | CLN-01 | PatientBoard.js (~13.5k) is the workspace; ~90% — missing payment/tele/eRx header status | Not Started
44 | §5.3 | Manual case taking | Structured case taking | Existing | 2 | CLN-02 | Classic case-taking tabs live | Not Started
45 | §5.3 | Body parts & intensity selection | Select affected areas and severity | Existing | 2 | CLN-03 | Body Parts tab + intensity chips live | Not Started
46 | §5.3 | Clinical questions | Guided questions by section, group and sub-group | Existing | 2 | CLN-04 | Questions tab loads Existance taxonomy live | Not Started
47 | §5.3 | Diagnosis, therapeutics & pattern search | Search diagnoses and linked therapeutics | Existing | 2 | CLN-05 | Clinical Pattern tab live (13 keyword tabs + therapeutics) | Not Started
48 | §5.3 | Repertory rubric search & selection | Search and select from the full repertory | Existing | 2 | CLN-06 | Repertory tree + search live | Not Started
49 | §5.3 | Manage selected rubrics | Review, edit and remove selected rubrics | Existing Improvement | 2 | CLN-07 | Clipboard exists; confirm-delete / intensity-edit incomplete | Not Started
50 | §5.3 | Audio case taking | Record the consultation and receive suggested rubrics automatically | Existing | 2 | CLN-08 | Whisper + rubric engines + CaseTaking UI live on .NET 8 | Not Started
51 | §5.3 | Improved rubric accuracy | Enhanced accuracy rules for audio-based rubric suggestions | Existing Improvement | 2 | CLN-09 | Engine + admin metaphors/aliases exist; accuracy rules still in progress (~50%) | Not Started
52 | §5.3 | Materia medica reference | Browse materia medica during the consultation | Existing Improvement | 2 | CLN-10 | MM tab + repertorize differential accordion ~90% | Not Started
53 | §5.3 | Allopathic drug side-effect lookup | Check side effects of conventional medicines | Existing | 2 | CLN-11 | Adverse Effect tab live | Not Started
54 | §5.3 | Repertorization & elimination | Full repertorization with elimination | Existing Improvement | 2 | CLN-12 | Common/uncommon/elimination live ~90% | Not Started
55 | §5.3 | Center of Gravity | New analysis identifying the central remedy of the case, with reasoning shown | New | 2 | CLN-13 | Does not exist | Not Started
56 | §5.3 + §11 | Lab orders & lab entries | Order tests and record results / Tests ordered alongside the prescription | Existing | 2 | CLN-14 | Lab order + result entry on prescription modal live | Not Started
57 | §5.3 | Appointment history notes | Notes recorded against each visit | Existing | 2 | CLN-15 | AppointmentHistoryNote APIs live (classic); currently mixed into Rx modal tabs | Not Started
58 | §5.3 | Complaints & case details | Capture and store complaints and case details | Existing Improvement | 2 | CLN-16 | Classic SaveComplaints / SaveCaseDetails APIs exist; Patient Board does not call them | Not Started
59 | §5.3 | Patient back history | Complete history of visits, notes, prescriptions and payments | Existing Improvement | 2 | CLN-17 | History panel ~70%; no payment line (payments do not exist yet) | Not Started
60 | §5.3 | Export case data | Download the full case in Excel or PDF | Existing Improvement | 2 | CLN-18 | Newer ExportCasesToExcel exists; no Patient Board export UI; no PDF | Not Started
61 | §5.3 | Session restore | Continue exactly where the doctor left off, across multiple patients | Existing | 2 | CLN-19 | Up to 5 in-memory sessions + DoctorPatientBoardBackup live | Not Started
62 | §5.3 | 3D anatomy viewer | Interactive 3D body model linked to rubric search | Existing Improvement | 2 | CLN-20 | three.js viewer + hotspot→search live; incomplete mesh coverage / UX | Not Started
63 | §5.1 | Doctor home dashboard | Complete overview of the working day | Existing Improvement | 3 | DOC-01 | Widgets + BestSellingProducts ~70%; missing online toggle, tele queue, payment badges, follow-up due | Not Started
64 | §5.1 | Patient counts & waiting list | Live counts by status with quick actions | Existing | 3 | DOC-02 | Status buckets WAITING, WALK-IN, NOT ARRIVED, E-CONSULT, REMAINING, COMPLETED live | Not Started
65 | §5.1 | Patient search, list & open case | Find any patient and open their case instantly | Existing Improvement | 3 | DOC-03 | Search/list/open ~90%; missing last visit, unpaid, family filters | Not Started
66 | §5.1 | Add new patient | Register a patient in seconds | Existing | 3 | DOC-04 | Create patient live | Not Started
67 | §5.1 | Import patients | Bring existing patient records in bulk | Existing | 3 | DOC-05 | Import live | Not Started
68 | §5.1 | Export patients | Download patient data in Excel, CSV or PDF | Existing Improvement | 3 | DOC-06 | Export live (confirm PDF vs Excel/CSV in QA) | Not Started
69 | §5.1 | Recent activity panel | Everything that happened recently, at a glance | Existing | 3 | DOC-07 | Recent activity live | Not Started
70 | §5.1 | Patient statistics charts | Visual practice statistics | Existing | 3 | DOC-08 | GetPatientStats / GetPatientStatsCharts + ApexCharts live | Not Started
71 | §5.1 | Manage reception staff | Add, edit and remove reception users | Existing Improvement | 3 | DOC-09 | .NET 8 api/ReceptionStaff CRUD exists; no SPA page | Not Started
72 | §5.1 | Doctor profile | Clinic details, consultation fee, photo, qualifications, working hours, bank details | Existing Improvement | 3 | DOC-10 | /profile is Velzon first_name only (~20%); credentials sit on Doctor entity; no fee/KYC UI | Not Started
73 | §5.2 | Appointment list & waiting patients | Full day view with live status | Existing | 4 | APT-01 | Day list + status live | Not Started
74 | §5.2 | Create new appointment | Book with visit type, consultation mode and fee | Existing Improvement | 4 | APT-02 | Create appointment ~90%; Formik modal has no VisitType / ConsultMode / fee | Not Started
75 | §5.2 | Appointment status update | Move patients through the visit stages | Existing | 4 | APT-03 | Status transitions live | Not Started
76 | §5.2 | Appointment time update | Adjust timings as the day runs | Existing | 4 | APT-04 | UpdateAppointmentTime live — changes a time only; no audit/notify | Not Started
77 | §5.2 + §2.3 + §6 | Reschedule appointment | Move to a new slot with automatic patient notification / Move to another slot without calling the clinic | New | 4 | APT-05 | Time can be edited; no formal Reschedule (audit, notify, old→new confirm) | Not Started
78 | §5.2 + §2.3 + §6 | Cancel appointment | Cancel with reason, free the slot, trigger refund where applicable / Cancel with reason, refund handled per policy | New | 4 | APT-06 | No CANCELLED; DeleteStatus is soft-delete only | Not Started
79 | §5.2 | Daily schedule setup | Define working days, hours and break times | Existing Improvement | 4 | APT-07 | DailyScheduleSetupModal + GetDailySchedule / SaveDailySchedule exist; not a first-class screen (draft marked 0%) | Not Started
80 | §5.2 | Appointment slot grid | Visual slot-by-slot view of the day | Existing | 4 | APT-08 | Slot picker / grid live | Not Started
81 | §5.2 + §9 | Consultation payment status | See paid, unpaid or pay-at-clinic on every appointment / Doctor, reception and patient all see the same payment status | New | 4 | APT-09 | No PaymentStatus on appointment | Not Started
82 | §6 | Reception login | Secure staff access | Existing | 5 | REC-01 | Reception logs in via Account; JWT includes DoctorID; uses doctor dashboard layout | Not Started
83 | §6 | Reception profile | Manage own profile details | New | 5 | REC-02 | No reception-specific profile; shared Velzon /profile | Not Started
84 | §6 | Reception home dashboard | Purpose-built front-desk dashboard | Existing Improvement | 5 | REC-03 | Same /doctordashboard with some clinical actions disabled ~90% | Not Started
85 | §6 | Create patient | Register a walk-in patient quickly | Existing | 5 | REC-04 | Create patient live on shared dashboard | Not Started
86 | §6 | Patient search & list | Find any patient instantly | Existing | 5 | REC-05 | Search live | Not Started
87 | §6 | Create & manage appointments | Full appointment management | Existing Improvement | 5 | REC-06 | Create/status/time live; reschedule/cancel missing until Phase 4 APIs | Not Started
88 | §6 | New appointment | Book on behalf of the patient | Existing Improvement | 5 | REC-07 | New appointment modal live; fields incomplete until APT-02 | Not Started
89 | §6 | Waiting queue management | Manage the live queue and call the next patient | Existing Improvement | 5 | REC-08 | Status buckets ~60%; no dedicated queue UX / call-next | Not Started
90 | §6 | Appointment status update | Update as patients arrive and are seen | Existing | 5 | REC-09 | Status update live | Not Started
91 | §6 | Appointment time update | Adjust timings through the day | Existing | 5 | REC-10 | Time update live | Not Started
92 | §6 | View doctor schedule | See the doctor’s working schedule | New | 5 | REC-11 | GetDailySchedule exists; no reception view | Not Started
93 | §6 | Log case paper / chief complaint | Record the reason for visit before the consultation | New | 5 | REC-12 | Missing; SaveComplaints exists but board is doctor-only | Not Started
94 | §6 + §9 | Collect consultation payment | Take cash, UPI, card or payment link and issue a receipt | New | 5 | REC-13 | Does not exist | Not Started
95 | §9 | Consultation fee configuration | Each doctor’s fee set and displayed to patients | New | 6 | PAY-01 | No ConsultFeeConfig; doctor profile work in DOC-10 may have stored a fee field | Not Started
96 | §9 | Automatic payment verification | Payments confirmed by the bank, not by the patient’s screen — nothing is lost if the app or browser closes | New Integration | 6 | PAY-02 | Razorpay checkout for S1 subscription only; no webhook; no signature verify on server | Not Started
97 | §9 + §4 + §2.3 | Online consultation payment | Patient pays by card, UPI, netbanking or wallet / Pay the consultation fee at the time of booking / Pay the consultation fee inside the app | New | 6 | PAY-03 | Does not exist (only S1 SaaS) | Not Started
98 | §9 + §6 | Reception payment collection | Cash, UPI, card or payment link with printed receipt | New | 6 | PAY-04 | Does not exist | Not Started
99 | §9 | Pay-at-clinic option | Book now, pay at the clinic where the doctor allows it | New | 6 | PAY-05 | Does not exist | Not Started
100 | §9 | Doctor subscription payment | Buy and renew subscription packages | Existing Improvement | 6 | PAY-06 | Checkout works ~70%; no webhook, refund, invoice, GST, Account ledger | Not Started
101 | §9 + §12 | Medicine payment | Pay online or choose cash on delivery / Both options supported, with status tracking | New | 6 | PAY-07 | Does not exist | Not Started
102 | §9 | Payment status everywhere | Doctor, reception and patient all see the same payment status | New | 6 | PAY-08 | No shared status | Not Started
103 | §9 + §8 + §2.8 | Refunds | Processed and tracked against the original payment / Issue and track refunds | New | 6 | PAY-09 | Does not exist | Not Started
104 | §9 + §8 | Payment receipts & invoices | Issued for every transaction / Invoice numbering and tax reporting | New | 6 | PAY-10 | No invoice entity | Not Started
105 | §9 + §17 | Complete audit trail | Every transaction traceable end to end by Homeocentrum | New | 6 | PAY-11 | No webhook store | Not Started
106 | §8 | Unified transaction ledger | Every rupee that moves through the platform, in one record | New | 7 | FIN-01 | Does not exist | Not Started
107 | §8 + §7.2 + §16 | Consultation payment reconciliation | Online payments and reception collections matched and verified / Match every booking against every payment | New | 7 | FIN-02 | Does not exist | Not Started
108 | §8 + §12 | Medicine ledger | Medicine money tracked separately from consultation money / Seller, platform and delivery shares recorded separately from consultation money | New | 7 | FIN-03 | Does not exist | Not Started
109 | §8 + §16 | Settlement runs | Scheduled settlement of amounts due to doctors and pharmacies | New | 7 | FIN-04 | Does not exist | Not Started
110 | §8 + §17 | Payout approval | Payouts released only after OTP-verified approval | New | 7 | FIN-05 | Does not exist | Not Started
111 | §8 | Refund processing | Issue and track refunds | New | 7 | FIN-06 | Does not exist | Not Started
112 | §8 + §7.2 | Payment exception handling | Investigate and resolve every failed or disputed payment / Every failed or mismatched payment surfaced for action | New | 7 | FIN-07 | Does not exist | Not Started
113 | §8 + §16 | GST & invoice reports | Invoice numbering and tax reporting | New | 7 | FIN-08 | Does not exist | Not Started
114 | §8 | Payee records | Bank and KYC details for doctors and pharmacies | New | 7 | FIN-09 | Doctor bank fields added in DOC-10; no Account UI; no pharmacy | Not Started
115 | §8 | Clinic collection view | Cash and UPI collected at reception, per clinic and per day | New | 7 | FIN-10 | Does not exist | Not Started
116 | §8 | Separation of duties | The Account department controls money. Admin controls the platform and clinical data. Neither can perform the other’s role, which protects both. | New | 7 | FIN-11 | Account role does not exist | Not Started
117 | §13 + §7.2 | Doctor credentialing | Doctors upload qualification and registration documents for review | New | 8 | TRU-01 | RegisterDoctor activates immediately; PassingUniversity/CertNo/QualificationId exist; no document store/queue | Not Started
118 | §13 + §7.2 | Verification review | Admin approves, rejects or requests more information before they can practise on the platform | New | 8 | TRU-02 | Does not exist | Not Started
119 | §13 + §2.2 | Verified badge / Credentials & verification | Patients see which doctors have been verified / Verified badge showing the doctor’s credentials are checked | New | 8 | TRU-03 | Does not exist | Not Started
120 | §13 | Practice gate | Only verified doctors appear to patients and take paid consultations | New | 8 | TRU-04 | Any activated doctor could theoretically be listed; no public list yet | Not Started
121 | §13 + §2.8 | Patient reviews / Write a review | Patients rate and review consultations / Rate and review the consultation | New | 8 | TRU-05 | Does not exist | Not Started
122 | §13 + §2.8 | Review appeal / My reviews & appeal | Doctors can appeal a review / Manage reviews and raise an appeal | New | 8 | TRU-06 | Does not exist | Not Started
123 | §13 + §2.2 | Ranking transparency / Ranking explanation | Patients are shown why doctors are ranked as they are / Transparent explanation of why doctors appear in a given order | New | 8 | TRU-07 | Does not exist | Not Started
124 | §4 | Product home page | Complete public website presenting the service | Existing Improvement | 9 | WEB-01 | HomeoJobLanding ~50%; Velzon leftovers; CTAs incomplete for book/trust/apps | Not Started
125 | §4 | Consultation & subscription pricing | Transparent pricing display | Existing Improvement | 9 | WEB-02 | SaaS package marketing /pricing exists; no consult fee display per doctor | Not Started
126 | §4 + §2.2 | Doctor discovery | Browse and search verified doctors | New | 9 | WEB-03 | Does not exist as a patient product (marketing only) | Not Started
127 | §4 + §2.3 | Self-service booking | Book an appointment online without calling the clinic | New | 9 | WEB-04 | Staff-only appointments | Not Started
128 | §4 + §9 | Online consultation payment | Pay the consultation fee at the time of booking | New | 9 | WEB-05 | Does not exist | Not Started
129 | §4 + §15 | Contact & enquiry form | Enquiries reach the admin team and are tracked | Existing Improvement | 9 | WEB-06 | EnquiryDetail API exists; public form partial; admin inbox screen missing | Not Started
130 | §4 + §17 | Privacy policy | Covering data protection, recording and pharmacy consent | Existing Improvement | 9 | WEB-07 | Privacy page partial; not DPDP/tele/pharmacy complete | Not Started
131 | §4 | Terms of service | Covering payments, refunds, telemedicine and medicine orders | Existing Improvement | 9 | WEB-08 | Terms partial | Not Started
132 | §4 | Doctor self-registration | Doctors apply to join the platform online | Existing Improvement | 9 | WEB-09 | RegisterDoctor ~90%; activates immediately; no document upload | Not Started
133 | §4 | Email activation | Secure account activation by email link | Existing Improvement | 9 | WEB-10 | ActivateUser via /login?UserId= ~90%; align with verification; expiry/resend incomplete | Not Started
134 | §2.3 | Waitlist offer | Get offered a slot when one is freed by a cancellation | New | 9 | WEB-11 | Cancel hook stub in Phase 4; no waitlist records | Not Started
135 | §2.2 | Health articles | Educational content to build trust and engagement | Existing Improvement | 9 | WEB-12 | Blog/news APIs on classic exist for marketing | Not Started
136 | §11 | Potency module | Every remedy carries a defined potency, selected from a managed list — no free text | New | 10 | ERX-01 | Dose saved as empty free-text dose: '' | Not Started
137 | §11 | Dosage details | Frequency, duration and instructions recorded clearly | New | 10 | ERX-02 | Unstructured/empty dose | Not Started
138 | §11 + §5.3 | Visit notes kept separate from the prescription | The doctor’s private clinical notes never appear on the prescription given to the patient or pharmacy | New | 10 | ERX-03 | History notes mixed into Rx modal tabs | Not Started
139 | §11 + §2.5 + §5.3 | Signed digital prescription | Issued and locked once signed, so it cannot be altered afterwards / Official prescription issued by the doctor | New | 10 | ERX-04 | SavePrescriptionDetail overwritable; no lock/sign | Not Started
140 | §11 | Prescription history | Every prescription stored against the patient and visit | New | 10 | ERX-05 | Rx saved per appointment but no signed history product | Not Started
141 | §11 + §2.5 | Patient view in app | Patient sees the prescription immediately in the app | New | 10 | ERX-06 | No patient surface | Not Started
142 | §11 | Print & PDF | Printable and downloadable prescription | New | 10 | ERX-07 | No eRx PDF | Not Started
143 | §11 | Remedy code protection | The patient sees remedy codes rather than remedy names until a licensed pharmacy accepts the order | New | 10 | ERX-08 | Does not exist | Not Started
144 | §11 + §12 | Reveal on pharmacy acceptance | Once a pharmacy accepts and verifies by OTP, the remedy names and price are revealed and a payment QR or link is generated | New | 10 | ERX-09 | Does not exist | Not Started
145 | §11 + §3 + §2.7 | Repeat prescription / refill | Patient requests a refill; doctor approves or rejects from the mobile app | New | 10 | ERX-10 | Does not exist | Not Started
146 | §11 | Lab orders | Tests ordered alongside the prescription | Existing Improvement | 10 | ERX-11 | Labs on Rx modal live | Not Started
147 | §10 + §3 | Doctor availability | Doctor sets online or offline status and working hours | New | 11 | TEL-01 | E-CONSULT status + WhatsApp video stub only; no availability | Not Started
148 | §10 + §3 | Telemedicine waiting queue | Doctor sees who is waiting, for how long, and whether they have paid | New | 11 | TEL-02 | E-CONSULT list only | Not Started
149 | §10 | Video consultation in browser | Doctor consults directly from the web portal | New Integration | 11 | TEL-03 | SweetAlert WhatsApp stub | Not Started
150 | §10 + §2.4 + §3 | Video consultation on mobile | Doctor and patient both consult from the app / Face-to-face consultation from home / Start the video or audio consultation from the phone | New | 11 | TEL-04 | No apps | Not Started
151 | §10 + §2.4 | Device check | Camera, microphone and connection tested before joining | New | 11 | TEL-05 | Does not exist | Not Started
152 | §10 + §2.4 | Waiting room | Patient waits with live status / Wait with live status until the doctor joins | New | 11 | TEL-06 | Does not exist | Not Started
153 | §10 + §2.4 + §17 | Recording consent | Consent captured before the consultation; no recording without it / Explicit consent requested before any recording | New | 11 | TEL-07 | AudioCaseConsentLog only for audio case taking | Not Started
154 | §10 + §2.4 | Rejoin after dropped call | Either side can rejoin the same consultation / Rejoin the same consultation if the connection drops | New | 11 | TEL-08 | Does not exist | Not Started
155 | §10 + §2.4 | Join failure handling / Fallback & join failure handling | Clear fallback if the call cannot connect / Clear guidance if the call fails, with options to retry | New | 11 | TEL-09 | Does not exist | Not Started
156 | §10 + §2.4 | Case-linked chat | Chat attached to the consultation record / Chat tied to the consultation, not a loose message thread | New | 11 | TEL-10 | Does not exist | Not Started
157 | §10 + §2.4 | Consultation summary | Issued to the patient at the end of the call / Written summary available immediately after the call | New | 11 | TEL-11 | Does not exist | Not Started
158 | §10 + §2.3 | Instant consultation / Instant consult request / Queue & doctor offer | Patient can request an immediate consultation with an available doctor / See position in queue and accept an offered doctor | New | 11 | TEL-12 | Does not exist | Not Started
159 | §14 | SMS | Appointment confirmation, registration confirmation, doctor-unavailable notice, OTP, reschedule and cancellation alerts | New Integration | 12 | COM-01 | No SMS provider; WhatsApp exists separately | Not Started
160 | §14 | WhatsApp | Templates, offers, health tips and bulk messaging to patients, with delivery reports and opt-out | Existing Improvement | 12 | COM-02 | Meta Cloud send/templates/campaigns live; bulk/opt-in/analytics incomplete | Not Started
161 | §14 + §2.9 + §3 | Push notifications | Booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests / Patient waiting, new booking, reschedule, cancellation, refill request, payment received | New Integration | 12 | COM-03 | Does not exist | Not Started
162 | §14 | Email | Registration, activation, password reset, invoices and receipts | Existing Improvement | 12 | COM-04 | SMTP used for activation/forgot (plaintext issue fixed in Phase 0); no invoice email | Not Started
163 | §14 + §2.8 | In-app notification centre / Notifications centre | All alerts collected in one place for patients and doctors / All alerts in one place | New | 12 | COM-05 | Does not exist (Velzon notification demo is not product) | Not Started
164 | §15 + §2.9 | Patient support tickets / Help centre & support tickets | Patients raise issues from the app and track them to resolution | New | 13 | SUP-01 | Does not exist; EnquiryDetail is not tickets; Velzon tickets demo ignore | Not Started
165 | §15 | Doctor support tickets | Doctors raise issues from the portal | New | 13 | SUP-02 | Does not exist | Not Started
166 | §15 + §7.2 | Admin issue queue / Support ticket queue | All issues in one queue with priority, assignment and status / All patient and doctor issues in one queue with assignment and resolution | New | 13 | SUP-03 | Does not exist | Not Started
167 | §15 | Ticket conversation | Full message thread with attachments | New | 13 | SUP-04 | Does not exist | Not Started
168 | §15 + §4 | Enquiry management | Website enquiries reach the admin team and are tracked | Existing Improvement | 13 | SUP-05 | API exists; inbox missing | Not Started
169 | §15 + §2.9 | Help centre | Self-service help content for patients | New | 13 | SUP-06 | Does not exist | Not Started
170 | §15 + §2.9 | Assisted booking | Support for patients who need help booking / Help for patients who need support booking | New | 13 | SUP-07 | Does not exist | Not Started
171 | §12 + §7.2 | Pharmacy partner onboarding / Pharmacy partner management | Licensed premises registered with licence records and an activation checklist / Onboard and activate licensed pharmacies | New | 14 | MED-01 | Does not exist | Not Started
172 | §12 | Licence gating | Pharmacies with expired or suspended licences are blocked automatically from receiving orders | New | 14 | MED-02 | Does not exist | Not Started
173 | §12 + §2.7 | Fulfilment consent & pharmacy selection | The patient chooses the seller and consents before the prescription is shared | New | 14 | MED-03 | Does not exist | Not Started
174 | §12 + §2.7 | Prescription handoff / Order start | The signed prescription becomes the order directly — no re-entry, no transcription errors / Start an order directly from the prescription | New | 14 | MED-04 | Does not exist | Not Started
175 | §12 | Rule-based seller routing | Orders routed by licence validity, service area, working hours and capacity | New | 14 | MED-05 | Does not exist | Not Started
176 | §12 | Manual stock confirmation | The pharmacy confirms availability — no live inventory integration required | New | 14 | MED-06 | Does not exist | Not Started
177 | §12 | Pharmacy console | Accept or reject orders, enter the price quote, mark ready and dispatched | New | 14 | MED-07 | Does not exist | Not Started
178 | §12 + §2.7 | Quote before payment / Pharmacy selection & quote | The patient always sees the price before paying / Choose a licensed pharmacy and see the price before paying | New | 14 | MED-08 | Does not exist | Not Started
179 | §12 + §9 | Payment or cash on delivery | Both options supported, with status tracking | New | 14 | MED-09 | Stream MEDICINE stub in Phase 6 | Not Started
180 | §12 + §2.7 | Order tracking | Live status for the patient at every stage / Live status from accepted to delivered | New | 14 | MED-10 | Does not exist | Not Started
181 | §12 + §8 | Medicine ledger | Seller, platform and delivery shares recorded separately from consultation money | New | 14 | MED-11 | Empty medicine ledger screen from Phase 7 | Not Started
182 | §12 | Order exception queue | Stuck, rejected or failed orders are always surfaced to the operations team — never silent | New | 14 | MED-12 | Does not exist | Not Started
183 | §12 + §17 | OTP-based control | Key actions verified by OTP so Homeocentrum can monitor and trace every transaction | New | 14 | MED-13 | SEC-07 infrastructure exists | Not Started
184 | §12 + §2.7 + §11 | Refill orders / Order detail & refill | Repeat orders raised from an existing prescription / Full order history and one-tap refill request | New | 14 | MED-14 | ERX-10 refill request exists | Not Started
185 | §2.7 | Order review & consent | Confirm and consent before the prescription is shared | New | 14 | MED-15 | Covered by MED-03; explicit review screen still required | Not Started
186 | §2.7 | Medicines tab | All medicine orders in one place | New | 14 | MED-16 | Does not exist | Not Started
187 | §2.1 | Family members | Add family members under one account | New | 15 | CON-01 | Does not exist | Not Started
188 | §2.1 | Caregiver authorization | Let a family member book and manage on their behalf | New | 15 | CON-02 | Does not exist | Not Started
189 | §2.5 | Records timeline / Consultation note / Document upload | Complete visit history in date order / Doctor’s notes for each visit / Upload reports, scans and previous prescriptions | New | 15 | CON-03 | Doctor history exists; no patient timeline; no patient upload | Not Started
190 | §2.6 | Follow-up plan & tasks | Clear next steps after each consultation | New | 15 | CON-04 | Does not exist (follow-up option in notes does not save) | Not Started
191 | §2.6 | Symptom diary | Record symptoms between visits | New | 15 | CON-05 | Does not exist | Not Started
192 | §2.6 | Progress tracking | See improvement over time across visits | New | 15 | CON-06 | Does not exist | Not Started
193 | §17 + §2.8 | Consent centre & data rights | Patients can view, manage and withdraw consent / View, manage and withdraw consents; request data | New | 15 | CON-07 | ConsentRecord from Phase 0 | Not Started
194 | §2.8 | Payments & refunds | Full payment history and refund status | New | 15 | CON-08 | Ledger exists for Account | Not Started
195 | §2.9 + §5.2 | Physical clinic appointment | Book an in-person visit as well as online | Existing Improvement | 15 | CON-09 | ConsultMode added in APT-02; public booking in WEB-04 | Not Started
196 | §2.1 | Profile setup | Name, age, gender, contact and health basics | New | 15 | CON-10 | Clinic-created Patient exists; no self-serve profile product | Not Started
197 | §2.1 | Language selection | Choose preferred language on first open | New | 16 | PAT-01 | No patient app in repos | Not Started
198 | §2.1 | Welcome & introduction | Guided introduction to the app | New | 16 | PAT-02 | No patient app in repos | Not Started
199 | §2.1 | Mobile number + OTP login | Secure sign-in with no password to remember | New | 16 | PAT-03 | No patient app in repos | Not Started
200 | §2.1 | Profile setup | Name, age, gender, contact and health basics | New | 16 | PAT-04 | No patient app in repos | Not Started
201 | §2.1 | Privacy consent | Clear consent before any personal data is stored | New | 16 | PAT-05 | No patient app in repos | Not Started
202 | §2.1 | Family members | Add family members under one account | New | 16 | PAT-06 | No patient app in repos | Not Started
203 | §2.1 | Caregiver authorization | Let a family member book and manage on their behalf | New | 16 | PAT-07 | No patient app in repos | Not Started
204 | §2.2 | Home dashboard | Personalised home with upcoming visits and quick actions | New | 16 | PAT-08 | No patient app in repos | Not Started
205 | §2.2 | Search & care categories | Search by name, condition or category of care | New | 16 | PAT-09 | No patient app in repos | Not Started
206 | §2.2 | Search results | Clear list of available doctors | New | 16 | PAT-10 | No patient app in repos | Not Started
207 | §2.2 | Filters | Narrow by availability, fee, experience, language and location | New | 16 | PAT-11 | No patient app in repos | Not Started
208 | §2.2 | Doctor profile | Full profile with qualifications, experience and consultation fee | New | 16 | PAT-12 | No patient app in repos | Not Started
209 | §2.2 | Credentials & verification | Verified badge showing the doctor’s credentials are checked | New | 16 | PAT-13 | No patient app in repos | Not Started
210 | §2.2 | Ranking explanation | Transparent explanation of why doctors appear in a given order | New | 16 | PAT-14 | No patient app in repos | Not Started
211 | §2.2 | Health articles | Educational content to build trust and engagement | New | 16 | PAT-15 | No patient app in repos | Not Started
212 | §2.3 | Slot picker | See real available time slots and choose one | New | 16 | PAT-16 | No patient app in repos | Not Started
213 | §2.3 | Booking review & consent | Confirm details and consent before booking | New | 16 | PAT-17 | No patient app in repos | Not Started
214 | §2.3 | Checkout | Pay the consultation fee inside the app | New | 16 | PAT-18 | No patient app in repos | Not Started
215 | §2.3 | Payment status | Immediate confirmation of paid, pending or failed | New | 16 | PAT-19 | No patient app in repos | Not Started
216 | §2.3 | Appointment detail | Full booking details in one place | New | 16 | PAT-20 | No patient app in repos | Not Started
217 | §2.3 | Reschedule appointment | Move to another slot without calling the clinic | New | 16 | PAT-21 | No patient app in repos | Not Started
218 | §2.3 | Cancel appointment | Cancel with reason, refund handled per policy | New | 16 | PAT-22 | No patient app in repos | Not Started
219 | §2.3 | Waitlist offer | Get offered a slot when one is freed by a cancellation | New | 16 | PAT-23 | No patient app in repos | Not Started
220 | §2.3 | Instant consult request | Request an immediate consultation with an available doctor | New | 16 | PAT-24 | No patient app in repos | Not Started
221 | §2.3 | Queue & doctor offer | See position in queue and accept an offered doctor | New | 16 | PAT-25 | No patient app in repos | Not Started
222 | §2.4 | Device check | Camera, microphone and network checked before the call | New | 16 | PAT-26 | No patient app in repos | Not Started
223 | §2.4 | Waiting room | Wait with live status until the doctor joins | New | 16 | PAT-27 | No patient app in repos | Not Started
224 | §2.4 | Live video consultation | Face-to-face consultation from home | New | 16 | PAT-28 | No patient app in repos | Not Started
225 | §2.4 | Recording consent | Explicit consent requested before any recording | New | 16 | PAT-29 | No patient app in repos | Not Started
226 | §2.4 | Fallback & join failure handling | Clear guidance if the call fails, with options to retry | New | 16 | PAT-30 | No patient app in repos | Not Started
227 | §2.4 | Case-linked chat | Chat tied to the consultation, not a loose message thread | New | 16 | PAT-31 | No patient app in repos | Not Started
228 | §2.4 | Consultation summary | Written summary available immediately after the call | New | 16 | PAT-32 | No patient app in repos | Not Started
229 | §2.4 | Rejoin after dropped call | Rejoin the same consultation if the connection drops | New | 16 | PAT-33 | No patient app in repos | Not Started
230 | §2.5 | Records timeline | Complete visit history in date order | New | 16 | PAT-34 | No patient app in repos | Not Started
231 | §2.5 | Consultation note | Doctor’s notes for each visit | New | 16 | PAT-35 | No patient app in repos | Not Started
232 | §2.5 | Signed digital prescription | Official prescription issued by the doctor | New | 16 | PAT-36 | No patient app in repos | Not Started
233 | §2.5 | Document upload | Upload reports, scans and previous prescriptions | New | 16 | PAT-37 | No patient app in repos | Not Started
234 | §2.6 | Follow-up plan & tasks | Clear next steps after each consultation | New | 16 | PAT-38 | No patient app in repos | Not Started
235 | §2.6 | Symptom diary | Record symptoms between visits | New | 16 | PAT-39 | No patient app in repos | Not Started
236 | §2.6 | Progress tracking | See improvement over time across visits | New | 16 | PAT-40 | No patient app in repos | Not Started
237 | §2.7 | Medicines tab | All medicine orders in one place | New | 16 | PAT-41 | No patient app in repos | Not Started
238 | §2.7 | Order start | Start an order directly from the prescription | New | 16 | PAT-42 | No patient app in repos | Not Started
239 | §2.7 | Pharmacy selection & quote | Choose a licensed pharmacy and see the price before paying | New | 16 | PAT-43 | No patient app in repos | Not Started
240 | §2.7 | Order review & consent | Confirm and consent before the prescription is shared | New | 16 | PAT-44 | No patient app in repos | Not Started
241 | §2.7 | Order tracking | Live status from accepted to delivered | New | 16 | PAT-45 | No patient app in repos | Not Started
242 | §2.7 | Order detail & refill | Full order history and one-tap refill request | New | 16 | PAT-46 | No patient app in repos | Not Started
243 | §2.8 | Write a review | Rate and review the consultation | New | 16 | PAT-47 | No patient app in repos | Not Started
244 | §2.8 | My reviews & appeal | Manage reviews and raise an appeal | New | 16 | PAT-48 | No patient app in repos | Not Started
245 | §2.8 | Payments & refunds | Full payment history and refund status | New | 16 | PAT-49 | No patient app in repos | Not Started
246 | §2.8 | Profile & settings | Manage personal details and preferences | New | 16 | PAT-50 | No patient app in repos | Not Started
247 | §2.8 | Consent centre & data rights | View, manage and withdraw consents; request data | New | 16 | PAT-51 | No patient app in repos | Not Started
248 | §2.8 | Notifications centre | All alerts in one place | New | 16 | PAT-52 | No patient app in repos | Not Started
249 | §2.9 | Help centre & support tickets | Raise an issue and track it to resolution | New | 16 | PAT-53 | No patient app in repos | Not Started
250 | §2.9 | Physical clinic appointment | Book an in-person visit as well as online | New | 16 | PAT-54 | No patient app in repos | Not Started
251 | §2.9 | Assisted booking | Help for patients who need support booking | New | 16 | PAT-55 | No patient app in repos | Not Started
252 | §2.9 | Low-data mode | Works on slow or limited connections | New | 16 | PAT-56 | No patient app in repos | Not Started
253 | §2.9 | Push notifications | Booking confirmations, reminders, doctor ready, prescription issued, order updates | New | 16 | PAT-57 | No patient app in repos | Not Started
254 | §2 + §18 | Patient mobile app iOS and Android | iOS and Android — onboarding, discovery, booking, payment, video consultation, records, prescriptions, follow-up, medicines, reviews, support, notifications | New | 16 | PAT-58 | No app | Not Started
255 | §3 | Login & identity | Same login and same account as the web portal | New | 17 | DMO-01 | No doctor app | Not Started
256 | §3 | First-run onboarding | Guided setup, number confirmation and permissions | New | 17 | DMO-02 | No app | Not Started
257 | §3 | Notification permissions | Push, microphone and camera permissions handled properly | New | 17 | DMO-03 | No app | Not Started
258 | §3 | Today’s queue & schedule | The full day at a glance | New | 17 | DMO-04 | No app | Not Started
259 | §3 | Availability toggle | Go online or offline, set working hours | New | 17 | DMO-05 | No app | Not Started
260 | §3 | Push notifications | Patient waiting, new booking, reschedule, cancellation, refill request, payment received | New | 17 | DMO-06 | No app | Not Started
261 | §3 | Patient context card | Name, age, chief complaint and last visit before joining | New | 17 | DMO-07 | No app; PDF: detailed case-taking stays on the web portal | Not Started
262 | §3 | Join consultation | Start the video or audio consultation from the phone | New | 17 | DMO-08 | No app | Not Started
263 | §3 + §11 | Refill approval | Approve or reject repeat prescription requests | New | 17 | DMO-09 | No app | Not Started
264 | §3 + §16 | Earnings summary | Today, this week and this month, with payout status | New | 17 | DMO-10 | No app | Not Started
265 | §3 | Offline handling | Clear behaviour on weak connection or expired session | New | 17 | DMO-11 | No app | Not Started
266 | §3 | Reliability monitoring | Failures are reported automatically, not left to a phone call | New Integration | 17 | DMO-12 | No app | Not Started
267 | §3 + §18 | Doctor mobile app iOS and Android | iOS and Android — queue, availability, notifications, patient context, video consultation, refill approval, earnings | New | 17 | DMO-13 | No app | Not Started
268 | §16 + §7.2 | Admin overview dashboard / Admin dashboard | Platform-wide activity at a glance / Live overview of the whole platform | Existing Improvement | 18 | RPT-01 | Velzon ecommerce dashboard 0% product; login lands /dashboard | Not Started
269 | §16 + §5.1 | Doctor practice statistics | Patient and consultation trends | Existing Improvement | 18 | RPT-02 | Patient stats charts live | Not Started
270 | §16 | Follow-up analysis | Which patients are due or overdue for follow-up, and follow-up conversion | New | 18 | RPT-03 | Does not exist; follow-up option in notes does not save | Not Started
271 | §16 | Clinic performance analysis | Appointments, slot utilisation, no-shows, cancellations, waiting time and revenue | New | 18 | RPT-04 | Does not exist | Not Started
272 | §16 + §7.2 | Payment reconciliation report / Consult booking & payment reconciliation | Bookings matched against payments / Match every booking against every payment | New | 18 | RPT-05 | FIN-02 built the queue; this is the report/export | Not Started
273 | §16 + §8 | Settlement & payout reports | Amounts due and paid to doctors and pharmacies | New | 18 | RPT-06 | FIN-04/05 exist as ops screens | Not Started
274 | §16 + §8 | GST & invoice reports | Tax reporting | New | 18 | RPT-07 | FIN-08 built tax screen | Not Started
275 | §16 + §3 | Doctor earnings summary | Daily, weekly and monthly earnings with payout status | New | 18 | RPT-08 | Does not exist | Not Started
276 | §16 + §12 | Medicine order reports | Order volumes, fulfilment and exceptions | New | 18 | RPT-09 | Does not exist | Not Started
277 | §7.2 | Platform users | Manage all users with import, export and activation control | Existing Improvement | 18 | RPT-10 | List/Add/Edit live; Import/Export buttons dead; no verification column | Not Started
278 | §1 + §18 | One connected ecosystem | A patient, an appointment, a prescription and a payment created anywhere in the system are visible everywhere else | Regression | 19 | QA-01 | Surfaces were built in phases | Not Started
279 | §18 | Summary of delivery | All features listed in this document are included in the delivery scope. | Regression | 19 | QA-02 | This register is the scope | Not Started
280 | §2.9 + §3 + §17 | Low-data mode / Reliability monitoring / Secure login | Works on slow connections; failures reported automatically; credentials protected | Existing Improvement | 19 | NFR-01 | Known risks: plaintext passwords (fixed P0), secrets in appsettings, dual API drift | Not Started

## 02_Main_Tasks
MAIN TASK INDEX — one row per PDF feature. Open 03_Sequential_Register and filter Main Task ID to execute sub-tasks in order.
Seq | Phase | Phase Name | WBS | Main Task ID | Main Task | Work Type | Module | PDF Section | PDF Feature | Surface | Sub-task count | Priority | AS-IS | TO-BE | Status
1 | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.1 | PRE-01 | Decide settlement model — Homeocentrum holds all money (food-delivery / quick-commerce pattern) | Client Decision | Finance | §9 + §8 | Every transaction passes through Homeocentrum | Account / Gateway | 3 | P0 | Only doctor SaaS subscription via client-side Razorpay; no consult/medicine ledger | Written decision: platform-held funds + periodic NEFT (v1) vs Razorpay Route (v2) | Not Started
2 | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.2 | PRE-02 | Decide reception cash policy — clinic retains vs remits to Homeocentrum | Client Decision | Finance / Reception | §9 | Reception payment collection | Account / Reception | 3 | P0 | No reception collection; no S3 ledger | Policy for cash/UPI at clinic: retain at clinic (still ledgered) or remit | Not Started
3 | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.3 | PRE-03 | Vendor and legal gates — video SDK, SMS, WhatsApp, push, DPDP copy | Client Decision | Platform | §10 + §14 + §17 | Telemedicine + notifications + consent | Shared | 5 | P0 | WhatsApp Meta Cloud partial; no video SDK; no SMS provider; no FCM; privacy/terms incomplete for DPDP/tele/pharmacy | Named vendors + DPDP-ready legal copy before those phases start | Not Started
4 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.1 | FND-01 | One connected ecosystem — shared keys so a patient, appointment, prescription and payment created anywhere are visible everywhere | New | Platform | §1 | One connected ecosystem serving six types of users | Shared | 4 | P0 | Doctor/Admin/Reception web only; Patient, Account, Pharmacy roles do not exist; no shared payment or eRx keys | Canonical keys: UserId/DoctorId, PatientId, PatientAppId, CaseId, ErxId, LedgerTxnId, MedicineOrderId — used by every surface | Not Started
5 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.2 | FND-02 | Delivery footprint — 2 mobile apps · 5 web portals · payment · telemedicine · digital prescription · HomeoMeds (programme skeleton) | New | Platform | §1 | Delivery covers | Shared | 4 | P0 | 1 web SPA (Admin/Doctor/Reception + marketing). No patient app, doctor app, Account portal, Pharmacy console | Repo/route skeleton: Patient Website, Doctor Web, Reception, Admin, Account (+ Pharmacy console under HomeoMeds); Patient + Doctor mobile later | Not Started
6 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.3 | SEC-01 | Secure login — protected credentials for every user type | Data Migration | Security | §17 | Secure login | All web + later mobile | 4 | P0 | POST /Account/Login on classic API; JWT in sessionStorage; doctor/user passwords compared plaintext; reception hashed on classic; fakeBackend() still mounted | Hashed passwords; Role claim on JWT; disable fake backend for production paths; Patient OTP login is Phase 8 (not password) | Not Started
7 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.4 | SEC-02 | Secure password reset — time-limited reset links (stop plaintext email + fake thunk) | New | Security | §17 | Secure password reset | Admin / Doctor / Reception web | 4 | P0 | /forgot-password UI exists; thunk uses fake/Firebase; POST /users/ForgetPassword emails plaintext password | Tokenised reset (hash, TTL); email contains link only; ChangePassword for logged-in user | Not Started
8 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.5 | SEC-03 | Session control — proper sign-out across web and mobile | Existing Improvement | Security | §17 | Session control | All | 4 | P0 | Client clears sessionStorage; no server logout / token revoke; UserLoginStatus unused | POST Logout persists login status; optional token denylist; mobile will call the same API in Phase 16/17 | Not Started
9 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.6 | SEC-04 | Role-based access — each role sees only what it is permitted to see | Existing Improvement | Security | §17 | Role-based access | Admin / All web | 4 | P0 | RoleMaster + RoleDetail + MenuMaster exist; GetMenuByRole commented out on .NET 8; no per-route frontend ACL — any authenticated URL works | Re-enable GetMenuByRole; AuthProtected deny-by-default; [Authorize(Roles=)] on money/clinical APIs; Account cannot edit repertory; Admin cannot approve payouts | Not Started
10 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.7 | SEC-05 | Patient data protection — health records restricted to the treating doctor and the patient | Existing Improvement | Security | §17 | Patient data protection | API | 3 | P0 | Many repertory APIs have [Authorize] commented; directory browsing enabled for /attachments and /Blogs; no patient-scoped ACL on case data | Every case/Rx/note/lab query filtered by treating DoctorId (or PatientId for patient token); disable directory browsing | Not Started
11 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.8 | SEC-06 | Consent records infrastructure — every consent captured, stored and reviewable | New | Security / Trust | §17 | Consent records | Shared | 4 | P0 | AudioCaseConsentLog exists for audio case taking only | ConsentRecord (PatientId, Type, Version, GrantedAt, WithdrawnAt, SourceSurface) covering privacy, booking, recording, pharmacy share, marketing | Not Started
12 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.9 | SEC-07 | OTP verification infrastructure — applied to sensitive actions including payouts and pharmacy acceptance | New | Security | §17 + §8 + §12 | OTP verification | Shared | 4 | P0 | No generic OTP control plane; patient OTP login does not exist | OtpChallenge + OtpAuditLog; Account/Admin can query who/when/entity/success without seeing card data | Not Started
13 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.10 | SEC-08 | Complete audit trail — who did what and when across payments, prescriptions and approvals | New | Security | §17 + §9 | Complete audit trail | Shared | 3 | P0 | No platform-wide audit; no AppointmentChangeLog; no payment webhook store | Append-only AuditEvent for money, eRx sign, credentialing, payout, pharmacy accept; payments get a dedicated trail in Phase 6 | Not Started
14 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.11 | SEC-09 | Secure documents — prescriptions, reports and uploads protected from unauthorised access | New | Security | §17 | Secure documents | Shared | 3 | P1 | Attachments served with directory browsing; no signed URLs; no patient upload module | Authorised download; virus-scan hook; patient uploads in Phase 15 use this store | Not Started
15 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.1 | ADM-R01 | Keep and harden Admin Repertory sections (do not rebuild) | Existing | Repertory | §7.1 | Repertory sections | Admin Portal | 3 | P2 | Admin Repertory section CRUD live (pages/Admin/Repertory) | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
16 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.2 | ADM-R02 | Keep and harden Admin Subsection & rubric tree (do not rebuild) | Existing | Repertory | §7.1 | Subsection & rubric tree | Admin Portal | 3 | P2 | Hierarchical subsection/rubric tree + Excel import/export live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
17 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.3 | ADM-R03 | Keep and harden Admin Rubric–remedy mapping (do not rebuild) | Existing | Repertory | §7.1 | Rubric–remedy mapping | Admin Portal | 3 | P2 | Rubric-remedy mapping by author/grade live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
18 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.4 | ADM-R04 | Keep and harden Admin Remedy-linked rubrics (do not rebuild) | Existing | Repertory | §7.1 | Remedy-linked rubrics | Admin Portal | 3 | P2 | Remedial-rubrics viewer live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
19 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.5 | ADM-R05 | Keep and harden Admin Language master (do not rebuild) | Existing | Repertory | §7.1 | Language master | Admin Portal | 3 | P2 | Language master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
20 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.6 | ADM-R06 | Keep and harden Admin Body part master (do not rebuild) | Existing | Repertory | §7.1 | Body part master | Admin Portal | 3 | P2 | Body part master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
21 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.7 | ADM-R07 | Keep and harden Admin Intensity master (do not rebuild) | Existing | Repertory | §7.1 | Intensity master | Admin Portal | 3 | P2 | Intensity master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
22 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.8 | ADM-R08 | Keep and harden Admin Remedy master (do not rebuild) | Existing | Repertory | §7.1 | Remedy master | Admin Portal | 3 | P2 | Remedy master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
23 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.9 | ADM-R09 | Keep and harden Admin Remedy grade master (do not rebuild) | Existing | Repertory | §7.1 | Remedy grade master | Admin Portal | 3 | P2 | Remedy grade master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
24 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.10 | ADM-M01 | Keep and harden Admin Author master (do not rebuild) | Existing | Materia Medica | §7.1 | Author master | Admin Portal | 3 | P2 | Author master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
25 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.11 | ADM-M02 | Keep and harden Admin Materia medica master (do not rebuild) | Existing | Materia Medica | §7.1 | Materia medica master | Admin Portal | 3 | P2 | MM master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
26 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.12 | ADM-M03 | Keep and harden Admin Materia medica heads (do not rebuild) | Existing | Materia Medica | §7.1 | Materia medica heads | Admin Portal | 3 | P2 | MM heads live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
27 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.13 | ADM-M04 | Keep and harden Admin Materia medica remedies (do not rebuild) | Existing | Materia Medica | §7.1 | Materia medica remedies | Admin Portal | 3 | P2 | Remedy-wise MM viewer live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
28 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.14 | ADM-D01 | Keep and harden Admin Diagnosis system (do not rebuild) | Existing | Diagnosis | §7.1 | Diagnosis system | Admin Portal | 3 | P2 | Diagnosis system CRUD live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
29 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.15 | ADM-D02 | Keep and harden Admin Diagnosis therapeutics (do not rebuild) | Existing | Diagnosis | §7.1 | Diagnosis therapeutics | Admin Portal | 3 | P2 | Therapeutics details live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
30 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.16 | ADM-D03 | Keep and harden Admin Diagnosis conditions (do not rebuild) | Existing | Diagnosis | §7.1 | Diagnosis conditions | Admin Portal | 3 | P2 | Conditions + keyword→rubric live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
31 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.17 | ADM-A01 | Keep and harden Admin Drug system (do not rebuild) | Existing | Adverse Effect | §7.1 | Drug system | Admin Portal | 3 | P2 | Drug system CRUD live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
32 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.18 | ADM-A02 | Keep and harden Admin Drug group (do not rebuild) | Existing | Adverse Effect | §7.1 | Drug group | Admin Portal | 3 | P2 | Drug group CRUD live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
33 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.19 | ADM-A03 | Keep and harden Admin Allopathic drug & side effects (do not rebuild) | Existing | Adverse Effect | §7.1 | Allopathic drug & side effects | Admin Portal | 3 | P2 | Allopathic drug + serious/other/adverse live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
34 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.20 | ADM-Q01 | Keep and harden Admin Question section, group & sub-group (do not rebuild) | Existing | Clinical Questions | §7.1 | Question section, group & sub-group | Admin Portal | 3 | P2 | Existance / question group / subgroup CRUD live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
35 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.21 | ADM-Q02 | Keep and harden Admin Clinical question mapping (do not rebuild) | Existing | Clinical Questions | §7.1 | Clinical question mapping | Admin Portal | 3 | P2 | Clinical questions mapped to body parts and rubrics live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
36 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.22 | ADM-3D1 | Keep and harden Admin 3D mesh key master (do not rebuild) | Existing | 3D Body | §7.1 | 3D mesh key master | Admin Portal | 3 | P2 | Mesh key master on .NET 8 live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
37 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.23 | ADM-3D2 | Keep and harden Admin 3D section master (do not rebuild) | Existing | 3D Body | §7.1 | 3D section master | Admin Portal | 3 | P2 | 3D section master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
38 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.24 | ADM-3D3 | Keep and harden Admin 3D hotspots (do not rebuild) | Existing | 3D Body | §7.1 | 3D hotspots | Admin Portal | 3 | P2 | Hotspot master live; doctor viewer consumes them | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Not Started
39 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.25 | ADM-B01 | Business Management — Doctor qualifications (existing, used later by credentialing) | Existing | Business Management | §7.2 | Doctor qualifications | Admin Portal | 3 | P2 | Qualifications CRUD on newer API live; used by RegisterDoctor | Keep; credentialing Phase 8 will reference QualificationId | Not Started
40 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.26 | ADM-B02 | Business Management — Lab & imaging test catalog (existing, used by eRx lab orders) | Existing | Business Management | §7.2 | Lab & imaging test catalog | Admin Portal | 3 | P2 | Labs & imaging CRUD live; Patient Board orders from this catalogue | Keep; eRx Phase 10 continues to use the same catalogue | Not Started
41 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.27 | ADM-B03 | Business Management — Subscription packages (existing S1 SaaS; later tied to Account ledger) | Existing | Business Management | §7.2 | Subscription packages | Admin Portal | 3 | P2 | Package CRUD live; Razorpay buy/renew partial (no webhook) | Do not overload PackageEntryDetail for consult/medicine money; Phase 6 ports payment verification | Not Started
42 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.28 | ADM-B04 | Business Management — Roles & menu permissions (existing DB, runtime ACL leftover) | Existing Improvement | Business Management | §7.2 | Roles & menu permissions | Admin Portal | 4 | P1 | Role CRUD screens live; runtime GetMenuByRole commented; no frontend route ACL | This is the product surface for SEC-04; complete wiring here | Not Started
43 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.1 | CLN-01 | Clinical workspace — single screen for the entire consultation | Existing Improvement | Patient Board | §5.3 | Clinical workspace | Doctor Web Portal | 3 | P1 | PatientBoard.js (~13.5k) is the workspace; ~90% — missing payment/tele/eRx header status | Keep one screen; add header chips for payment, tele session, signed eRx (chips light up as later phases land) | Not Started
44 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.2 | CLN-02 | Manual case taking — structured case taking (keep) | Existing | Patient Board | §5.3 | Manual case taking | Doctor Web Portal | 3 | P2 | Classic case-taking tabs live | Regression only; do not rebuild | Not Started
45 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.3 | CLN-03 | Body parts & intensity selection (keep) | Existing | Patient Board | §5.3 | Body parts & intensity selection | Doctor Web Portal | 3 | P2 | Body Parts tab + intensity chips live | Regression; intensity master from Phase 1 still drives chips | Not Started
46 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.4 | CLN-04 | Clinical questions — guided questions by section, group and sub-group (keep) | Existing | Patient Board | §5.3 | Clinical questions | Doctor Web Portal | 3 | P2 | Questions tab loads Existance taxonomy live | Regression | Not Started
47 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.5 | CLN-05 | Diagnosis, therapeutics & pattern search (keep) | Existing | Patient Board | §5.3 | Diagnosis, therapeutics & pattern search | Doctor Web Portal | 3 | P2 | Clinical Pattern tab live (13 keyword tabs + therapeutics) | Regression | Not Started
48 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.6 | CLN-06 | Repertory rubric search & selection (keep) | Existing | Patient Board | §5.3 | Repertory rubric search & selection | Doctor Web Portal | 3 | P2 | Repertory tree + search live | Regression; small UX polish allowed but not a rewrite | Not Started
49 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.7 | CLN-07 | Manage selected rubrics — review, edit and remove (remaining ~10%) | Existing Improvement | Patient Board | §5.3 | Manage selected rubrics | Doctor Web Portal | 4 | P1 | Clipboard exists; confirm-delete / intensity-edit incomplete | Confirm delete; edit intensity on selected rubric; no accidental wipe | Not Started
50 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.8 | CLN-08 | Audio case taking — record and receive suggested rubrics (keep engine; do not rebuild) | Existing | Audio AI | §5.3 | Audio case taking | Doctor Web Portal | 3 | P1 | Whisper + rubric engines + CaseTaking UI live on .NET 8 | Keep; follow existing AUDIO_CASE_TAKING_* docs; accuracy is the next task | Not Started
51 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.9 | CLN-09 | Improved rubric accuracy — enhanced accuracy rules for audio-based rubric suggestions | Existing Improvement | Audio AI | §5.3 | Improved rubric accuracy | Doctor Web Portal + Admin intelligence | 3 | P1 | Engine + admin metaphors/aliases exist; accuracy rules still in progress (~50%) | Complete accuracy rules per AUDIO_CASE_TAKING_AI_ENGINE docs; metaphor/alias QA | Not Started
52 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.10 | CLN-10 | Materia medica reference during consultation (remaining ~10%) | Existing Improvement | Patient Board | §5.3 | Materia medica reference | Doctor Web Portal | 4 | P2 | MM tab + repertorize differential accordion ~90% | Faster head navigation during case; do not rebuild MM masters | Not Started
53 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.11 | CLN-11 | Allopathic drug side-effect lookup (keep) | Existing | Patient Board | §5.3 | Allopathic drug side-effect lookup | Doctor Web Portal | 3 | P2 | Adverse Effect tab live | Regression | Not Started
54 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.12 | CLN-12 | Repertorization & elimination (remaining ~10%) | Existing Improvement | Patient Board | §5.3 | Repertorization & elimination | Doctor Web Portal | 4 | P1 | Common/uncommon/elimination live ~90% | Stability polish; Center of Gravity is a NEW panel on the same rubrics (next task) | Not Started
55 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.13 | CLN-13 | Center of Gravity — new analysis identifying the central remedy of the case, with reasoning shown | New | Repertorization | §5.3 | Center of Gravity | Doctor Web Portal | 4 | P1 | Does not exist | POST /api/Repertorization/CenterOfGravity from selected rubric ids + intensities; UI panel with explainability | Not Started
56 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.14 | CLN-14 | Lab orders & lab entries (keep; later also sit on eRx) | Existing | Patient Board | §5.3 + §11 | Lab orders & lab entries | Doctor Web Portal | 3 | P2 | Lab order + result entry on prescription modal live | Keep; when eRx splits notes from Rx, labs stay on the prescription/eRx side | Not Started
57 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.15 | CLN-15 | Appointment history notes (keep; split from eRx in Phase 10) | Existing | Patient Board | §5.3 | Appointment history notes | Doctor Web Portal | 3 | P1 | AppointmentHistoryNote APIs live (classic); currently mixed into Rx modal tabs | Keep save/get; Phase 10 moves UX outside Rx modal and adds NoteType / IsErxExcluded | Not Started
58 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.16 | CLN-16 | Complaints & case details — wire Patient Board to existing SaveComplaints / SaveCaseDetails (~20% today) | Existing Improvement | Patient Board | §5.3 | Complaints & case details | Doctor Web Portal | 4 | P1 | Classic SaveComplaints / SaveCaseDetails APIs exist; Patient Board does not call them | Call the existing APIs from the board; Reception case-paper (Phase 5) uses a subset | Not Started
59 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.17 | CLN-17 | Patient back history — complete history of visits, notes, prescriptions and payments | Existing Improvement | Patient Board | §5.3 | Patient back history | Doctor Web Portal | 4 | P1 | History panel ~70%; no payment line (payments do not exist yet) | Timeline: visits, notes, eRx, labs; payment row added when Phase 6 lands (placeholder now) | Not Started
60 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.18 | CLN-18 | Export case data — download the full case in Excel or PDF | Existing Improvement | Patient Board | §5.3 | Export case data | Doctor Web Portal | 3 | P1 | Newer ExportCasesToExcel exists; no Patient Board export UI; no PDF | Toolbar Excel + PDF using existing Excel API + new PDF renderer; exclude private notes from patient-facing PDF (eRx print is Phase 10) | Not Started
61 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.19 | CLN-19 | Session restore — continue exactly where the doctor left off, across multiple patients (keep) | Existing | Patient Board | §5.3 | Session restore | Doctor Web Portal | 3 | P2 | Up to 5 in-memory sessions + DoctorPatientBoardBackup live | Regression; header stack remains | Not Started
62 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.20 | CLN-20 | 3D anatomy viewer — interactive 3D body model linked to rubric search (remaining ~50%) | Existing Improvement | Anatomy | §5.3 | 3D anatomy viewer | Doctor Web Portal | 4 | P2 | three.js viewer + hotspot→search live; incomplete mesh coverage / UX | Complete GLB/hotspot coverage; mobile fallback later; admin 3D masters already in Phase 1 | Not Started
63 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.1 | DOC-01 | Doctor home dashboard — complete overview of the working day (remaining ~30%) | Existing Improvement | Doctor Dashboard | §5.1 | Doctor home dashboard | Doctor Web Portal | 4 | P1 | Widgets + BestSellingProducts ~70%; missing online toggle, tele queue, payment badges, follow-up due | Extend, do not replace; later phases light up tele/payment chips | Not Started
64 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.2 | DOC-02 | Patient counts & waiting list — live counts by status with quick actions (keep; extend paid/unpaid) | Existing | Doctor Dashboard | §5.1 | Patient counts & waiting list | Doctor Web Portal | 3 | P1 | Status buckets WAITING, WALK-IN, NOT ARRIVED, E-CONSULT, REMAINING, COMPLETED live | Keep; add CANCELLED in Phase 4; paid/unpaid badge in Phase 6 | Not Started
65 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.3 | DOC-03 | Patient search, list & open case (remaining ~10%) | Existing Improvement | Doctor Dashboard | §5.1 | Patient search, list & open case | Doctor Web Portal | 4 | P1 | Search/list/open ~90%; missing last visit, unpaid, family filters | Add last-visit column; unpaid/family after those modules exist | Not Started
66 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.4 | DOC-04 | Add new patient — register a patient in seconds (keep) | Existing | Patients | §5.1 | Add new patient | Doctor Web Portal | 3 | P1 | Create patient live | Regression; public self-registration is a different Patient identity in Phase 9 | Not Started
67 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.5 | DOC-05 | Import patients — bring existing patient records in bulk (keep) | Existing | Patients | §5.1 | Import patients | Doctor Web Portal | 3 | P2 | Import live | Regression | Not Started
68 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.6 | DOC-06 | Export patients — download patient data in Excel, CSV or PDF (keep) | Existing Improvement | Patients | §5.1 | Export patients | Doctor Web Portal | 3 | P2 | Export live (confirm PDF vs Excel/CSV in QA) | If PDF is missing, add it as Existing Improvement; do not skip the PDF wording in the PDF | Not Started
69 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.7 | DOC-07 | Recent activity panel (keep) | Existing | Doctor Dashboard | §5.1 | Recent activity panel | Doctor Web Portal | 3 | P2 | Recent activity live | Regression; later include payment/tele events when those exist | Not Started
70 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.8 | DOC-08 | Patient statistics charts (keep; foundation for clinic performance in Phase 18) | Existing | Doctor Dashboard | §5.1 | Patient statistics charts | Doctor Web Portal | 3 | P2 | GetPatientStats / GetPatientStatsCharts + ApexCharts live | Keep; clinic performance report extends this in Phase 18 | Not Started
71 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.9 | DOC-09 | Manage reception staff — add, edit and remove reception users (backend done, UI absent) | Existing Improvement | Staff | §5.1 | Manage reception staff | Doctor Web Portal | 3 | P1 | .NET 8 api/ReceptionStaff CRUD exists; no SPA page | List/add/edit/disable at /doctor/reception-staff; doctor owns the staff record | Not Started
72 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.10 | DOC-10 | Doctor profile — clinic details, consultation fee, photo, qualifications, working hours, bank details | Existing Improvement | Doctor Profile | §5.1 | Doctor profile | Doctor Web Portal | 4 | P0 | /profile is Velzon first_name only (~20%); credentials sit on Doctor entity; no fee/KYC UI | Real doctor profile: clinic, photo, qualifications, consult fee (feeds Phase 6), hours (feeds schedule), bank KYC (feeds Account payees) | Not Started
73 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.1 | APT-01 | Appointment list & waiting patients — full day view with live status (keep; later payment/tele) | Existing | Appointments | §5.2 | Appointment list & waiting patients | Doctor Web Portal | 3 | P1 | Day list + status live | Keep; reschedule/cancel/payment attach to this list | Not Started
74 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.2 | APT-02 | Create new appointment — persist visit type, consultation mode and fee | Existing Improvement | Appointments | §5.2 | Create new appointment | Doctor Web Portal | 4 | P0 | Create appointment ~90%; Formik modal has no VisitType / ConsultMode / fee | VisitType First/Follow-up; ConsultMode In-clinic / E-Consult; fee display from doctor profile / ConsultFeeConfig | Not Started
75 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.3 | APT-03 | Appointment status update — move patients through the visit stages (keep) | Existing | Appointments | §5.2 | Appointment status update | Doctor Web Portal | 3 | P1 | Status transitions live | Keep; add CANCELLED in APT-06; do not reuse DeleteStatus as cancel | Not Started
76 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.4 | APT-04 | Appointment time update — adjust timings as the day runs (keep; distinct from formal reschedule) | Existing | Appointments | §5.2 | Appointment time update | Doctor Web Portal | 3 | P1 | UpdateAppointmentTime live — changes a time only; no audit/notify | Keep same-day time tweak; formal reschedule (old→new, notify, conflict) is APT-05 | Not Started
77 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.5 | APT-05 | Reschedule appointment — move to a new slot with automatic patient notification (NEW — not a rename of UpdateAppointmentTime) | New | Appointments | §5.2 + §2.3 + §6 | Reschedule appointment | Doctor Web + Reception + later Patient | 5 | P0 | Time can be edited; no formal Reschedule (audit, notify, old→new confirm) | POST RescheduleAppointment; AppointmentChangeLog; conflict 409 with alternatives; SMS/WhatsApp fan-out (notify failure must not roll back) | Not Started
78 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.6 | APT-06 | Cancel appointment — reason, free the slot, trigger refund where applicable (NEW CANCELLED status — do NOT reuse DeleteStatus) | New | Appointments | §5.2 + §2.3 + §6 | Cancel appointment | Doctor Web + Reception + later Patient | 5 | P0 | No CANCELLED; DeleteStatus is soft-delete only | CANCELLED + reason fields; free slot; waitlist hook; if PAID evaluate refund policy (Phase 6/7) | Not Started
79 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.7 | APT-07 | Daily schedule setup — define working days, hours and break times (promote modal to first-class screen) | Existing Improvement | Scheduling | §5.2 | Daily schedule setup | Doctor Web Portal | 3 | P0 | DailyScheduleSetupModal + GetDailySchedule / SaveDailySchedule exist; not a first-class screen (draft marked 0%) | Promote to /doctor/schedule with week grid and copy-day; reuse existing APIs — do not rebuild | Not Started
80 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.8 | APT-08 | Appointment slot grid — visual slot-by-slot view of the day (keep; public booking reuses this) | Existing | Scheduling | §5.2 | Appointment slot grid | Doctor Web Portal | 3 | P0 | Slot picker / grid live | Keep; Phase 9 public APIs reuse the same slot engine | Not Started
81 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.9 | APT-09 | Consultation payment status on every appointment (schema now; values live in Phase 6) | New | Appointments | §5.2 + §9 | Consultation payment status | Doctor Web Portal | 4 | P0 | No PaymentStatus on appointment | Add PaymentStatus UNPAID / PENDING / PAID / FAILED / PAY_AT_CLINIC / REFUNDED; UI badge; source of truth is webhook in Phase 6 not the client screen | Not Started
82 | 5 | Phase 5 — Reception portal (PDF §6) | 5.1 | REC-01 | Reception login — secure staff access (keep) | Existing | Reception | §6 | Reception login | Reception Portal | 3 | P1 | Reception logs in via Account; JWT includes DoctorID; uses doctor dashboard layout | Keep login; Phase 0 hashing applies; later dedicated reception chrome | Not Started
83 | 5 | Phase 5 — Reception portal (PDF §6) | 5.2 | REC-02 | Reception profile — manage own profile details (0% today) | New | Reception | §6 | Reception profile | Reception Portal | 4 | P1 | No reception-specific profile; shared Velzon /profile | Name, mobile, attached doctor (read-only); cannot edit doctor bank/fee | Not Started
84 | 5 | Phase 5 — Reception portal (PDF §6) | 5.3 | REC-03 | Reception home dashboard — purpose-built front-desk dashboard (not only hidden doctor actions) | Existing Improvement | Reception | §6 | Reception home dashboard | Reception Portal | 3 | P1 | Same /doctordashboard with some clinical actions disabled ~90% | Reception-first chrome: queue, collect pay, case paper, no repertory/Rx; optional /reception home route | Not Started
85 | 5 | Phase 5 — Reception portal (PDF §6) | 5.4 | REC-04 | Create patient — register a walk-in patient quickly (keep) | Existing | Reception | §6 | Create patient | Reception Portal | 3 | P1 | Create patient live on shared dashboard | Keep on reception chrome | Not Started
86 | 5 | Phase 5 — Reception portal (PDF §6) | 5.5 | REC-05 | Patient search & list — find any patient instantly (keep) | Existing | Reception | §6 | Patient search & list | Reception Portal | 3 | P1 | Search live | Keep; no opening full clinical board | Not Started
87 | 5 | Phase 5 — Reception portal (PDF §6) | 5.6 | REC-06 | Create & manage appointments — full appointment management (keep; plus reschedule/cancel from Phase 4) | New | Reception | §6 | Create & manage appointments | Reception Portal | 3 | P0 | Create/status/time live; reschedule/cancel missing until Phase 4 APIs | Enable RescheduleAppointment and CancelAppointment for JWT DoctorId; isReceptionUser must not block | Not Started
88 | 5 | Phase 5 — Reception portal (PDF §6) | 5.7 | REC-07 | New appointment — book on behalf of the patient (keep; same VisitType/ConsultMode/fee as APT-02) | Existing Improvement | Reception | §6 | New appointment | Reception Portal | 2 | P1 | New appointment modal live; fields incomplete until APT-02 | Same modal fields as doctor so public booking later matches staff-created rows | Not Started
89 | 5 | Phase 5 — Reception portal (PDF §6) | 5.8 | REC-08 | Waiting queue management — manage the live queue and call the next patient | Existing Improvement | Reception | §6 | Waiting queue management | Reception Portal | 4 | P1 | Status buckets ~60%; no dedicated queue UX / call-next | Dedicated queue: walk-in vs tele; payment state; Call next; notify patient (later push) | Not Started
90 | 5 | Phase 5 — Reception portal (PDF §6) | 5.9 | REC-09 | Appointment status update (reception) — update as patients arrive and are seen (keep) | Existing | Reception | §6 | Appointment status update | Reception Portal | 3 | P1 | Status update live | Keep on reception chrome | Not Started
91 | 5 | Phase 5 — Reception portal (PDF §6) | 5.10 | REC-10 | Appointment time update (reception) — adjust timings through the day (keep) | Existing | Reception | §6 | Appointment time update | Reception Portal | 3 | P2 | Time update live | Keep; formal reschedule remains REC-06 | Not Started
92 | 5 | Phase 5 — Reception portal (PDF §6) | 5.11 | REC-11 | View doctor schedule — see the doctor’s working schedule (read-only) | New | Reception | §6 | View doctor schedule | Reception Portal | 2 | P1 | GetDailySchedule exists; no reception view | Read-only /reception/schedule using DoctorID from JWT | Not Started
93 | 5 | Phase 5 — Reception portal (PDF §6) | 5.12 | REC-12 | Log case paper / chief complaint — record the reason for visit before the consultation | New | Reception | §6 | Log case paper / chief complaint | Reception Portal | 4 | P1 | Missing; SaveComplaints exists but board is doctor-only | Restricted case-paper form (chief complaint only — no repertory/Rx); audit reception author | Not Started
94 | 5 | Phase 5 — Reception portal (PDF §6) | 5.13 | REC-13 | Collect consultation payment — cash, UPI, card or payment link and issue a receipt (API in Phase 6; UI shell now) | New | Reception | §6 + §9 | Collect consultation payment | Reception Portal | 2 | P0 | Does not exist | UI modal ready; CollectAtReception API lands with payment spine in Phase 6 — do not fake a paid status here | Not Started
95 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.1 | PAY-01 | Consultation fee configuration — each doctor’s fee set and displayed to patients | New | Payments | §9 | Consultation fee configuration | Doctor profile + Public + Admin | 4 | P0 | No ConsultFeeConfig; doctor profile work in DOC-10 may have stored a fee field | ConsultFeeConfig (InClinic, EConsult, optional Instant surcharge, PayAtClinicEnabled, GST flags) | Not Started
96 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.2 | PAY-02 | Automatic payment verification — bank/webhook is source of truth, not the patient’s screen | New | Payments | §9 | Automatic payment verification | Shared | 4 | P0 | Razorpay checkout for S1 subscription only; no webhook; no signature verify on server | Port Razorpay to .NET 8; keys in config; POST /api/Payments/Webhook/Razorpay anonymous + signature verify; PaymentOrder table | Not Started
97 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.3 | PAY-03 | Online consultation payment — patient pays by card, UPI, netbanking or wallet | New | Payments | §9 + §4 + §2.3 | Online consultation payment | Public web + later Patient app | 5 | P0 | Does not exist (only S1 SaaS) | CreateConsultOrder attached to PatientAppId; Razorpay Checkout; webhook sets PAID; do not overload PackageEntryDetail | Not Started
98 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.4 | PAY-04 | Reception payment collection — cash, UPI, card or payment link with printed receipt | New | Payments | §9 + §6 | Reception payment collection | Reception Portal | 5 | P0 | Does not exist | CollectAtReception writes ledger S3; print receipt; payment-link uses same Razorpay order as online | Not Started
99 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.5 | PAY-05 | Pay-at-clinic option — book now, pay at the clinic where the doctor allows it | New | Payments | §9 | Pay-at-clinic option | Public + Doctor + Reception | 3 | P1 | Does not exist | PayAtClinicEnabled on fee config; appointment PaymentStatus=PAY_AT_CLINIC; tele queue may still require PAID (policy) | Not Started
100 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.6 | PAY-06 | Doctor subscription payment — buy and renew subscription packages (complete remaining ~30%) | Existing Improvement | Payments | §9 | Doctor subscription payment | Doctor Web Portal | 3 | P1 | Checkout works ~70%; no webhook, refund, invoice, GST, Account ledger | Same webhook spine; write S1 ledger; invoice; failed pay UX; PackageEntryDetail shape UNCHANGED | Not Started
101 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.7 | PAY-07 | Medicine payment — pay online or cash on delivery (API contract now; HomeoMeds Phase 14 implements orders) | New | Payments | §9 + §12 | Medicine payment | Shared | 3 | P1 | Does not exist | PaymentOrder.Stream=MEDICINE; COD_PENDING until pharmacy confirms collection; do not mix with consult money | Not Started
102 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.8 | PAY-08 | Payment status everywhere — doctor, reception and patient all see the same payment status | New | Payments | §9 | Payment status everywhere | All | 3 | P0 | No shared status | Single PaymentStatus on appointment/order; all DTOs read it; never a second client-only flag | Not Started
103 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.9 | PAY-09 | Refunds — processed and tracked against the original payment | New | Payments | §9 + §8 + §2.8 | Refunds | Account + Patient | 5 | P0 | Does not exist | Refund entity against original PaymentOrder; Razorpay refund API; cancel-appointment hook; patient sees status | Not Started
104 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.10 | PAY-10 | Payment receipts & invoices — issued for every transaction | New | Payments | §9 + §8 | Payment receipts & invoices | All | 4 | P1 | No invoice entity | Invoice numbering series from PRE-02; PDF receipt; GST fields; email in Phase 12 | Not Started
105 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.11 | PAY-11 | Complete payment audit trail — every transaction traceable end to end by Homeocentrum | New | Payments | §9 + §17 | Complete audit trail | Account | 3 | P0 | No webhook store | PaymentEvent raw payloads + AuditEvent + OtpAudit for payouts; Account can reconstruct without Razorpay dashboard | Not Started
106 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.1 | FIN-01 | Unified transaction ledger — every rupee that moves through the platform, in one record | New | Account | §8 | Unified transaction ledger | Account Portal | 4 | P0 | Does not exist | Append-only LedgerEntry for S1–S7; filters; OTP audit link; Admin may view, Account owns movement | Not Started
107 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.2 | FIN-02 | Consultation payment reconciliation — online payments and reception collections matched and verified | New | Account | §8 + §7.2 + §16 | Consultation payment reconciliation | Account + Admin | 4 | P0 | Does not exist | Join booking ↔ payment ↔ appointment; KPI collected/pending/failed/refunded; CSV | Not Started
108 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.3 | FIN-03 | Medicine ledger — medicine money tracked separately from consultation money | New | Account | §8 + §12 | Medicine ledger | Account Portal | 4 | P1 | Does not exist | /account/medicine-ledger; Stream=MEDICINE; seller/platform/delivery split columns; filled in Phase 14 | Not Started
109 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.4 | FIN-04 | Settlement runs — scheduled settlement of amounts due to doctors and pharmacies | New | Account | §8 + §16 | Settlement runs | Account Portal | 4 | P0 | Does not exist | SettlementRun job T+N hold; net of commission/GST/refunds; pharmacies after Phase 14 | Not Started
110 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.5 | FIN-05 | Payout approval — payouts released only after OTP-verified approval | New | Account | §8 + §17 | Payout approval | Account Portal | 5 | P0 | Does not exist | ApprovePayout requires SEC-07 OTP; Admin cannot approve; NEFT/file or gateway per PRE-01 | Not Started
111 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.6 | FIN-06 | Refund processing — Account issues and tracks refunds (uses PAY-09) | New | Account | §8 | Refund processing | Account Portal | 3 | P0 | Does not exist | /account/refunds UI on PAY-09 APIs; OTP if policy requires | Not Started
112 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.7 | FIN-07 | Payment exception handling — investigate and resolve every failed or disputed payment | New | Account | §8 + §7.2 | Payment exception handling | Account + Admin | 4 | P0 | Does not exist | Exception queue Failed/Partial/Webhook-mismatch/Refund-pending; retry/resolve with OTP on manual reconcile | Not Started
113 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.8 | FIN-08 | GST & invoice reports — invoice numbering and tax reporting | New | Account | §8 + §16 | GST & invoice reports | Account Portal | 4 | P1 | Does not exist | /account/tax export using Invoice table and PRE-02 GST treatment — configuration not hardcoded | Not Started
114 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.9 | FIN-09 | Payee records — bank and KYC details for doctors and pharmacies | New | Account | §8 | Payee records | Account Portal | 4 | P1 | Doctor bank fields added in DOC-10; no Account UI; no pharmacy | /account/payees; OTP on doctor KYC change (fraud); pharmacies after Phase 14 | Not Started
115 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.10 | FIN-10 | Clinic collection view — cash and UPI collected at reception, per clinic and per day | New | Account | §8 | Clinic collection view | Account Portal | 4 | P1 | Does not exist | /account/clinic-collections from CollectAtReception rows; respect PRE-02 retain vs remit | Not Started
116 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.11 | FIN-11 | Separation of duties — Account controls money; Admin controls platform and clinical data | New | Account | §8 | Separation of duties | Admin + Account | 2 | P0 | Account role does not exist | Enforce in RBAC: Admin cannot ApprovePayout; Account cannot edit repertory/users’ clinical masters | Not Started
117 | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.1 | TRU-01 | Doctor credentialing — doctors upload qualification and registration documents for review | New | Trust | §13 + §7.2 | Doctor credentialing | Doctor Web + Admin | 4 | P0 | RegisterDoctor activates immediately; PassingUniversity/CertNo/QualificationId exist; no document store/queue | DoctorCredentialDocument + VerificationStatus Pending; do not auto-activate practice for public directory | Not Started
118 | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.2 | TRU-02 | Verification review — Admin approves, rejects or requests further information | New | Trust | §13 + §7.2 | Verification review | Admin Portal | 5 | P0 | Does not exist | /admin/doctor-credentialing list + detail; email notify doctor | Not Started
119 | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.3 | TRU-03 | Verified badge — patients see which doctors have been verified | New | Trust | §13 + §2.2 | Verified badge / Credentials & verification | Public + Patient app | 3 | P0 | Does not exist | Badge on public doctor card and profile from VerificationStatus=Approved | Not Started
120 | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.4 | TRU-04 | Practice gate — only verified doctors appear to patients and take paid consultations | New | Trust | §13 | Practice gate | Public + Payments | 3 | P0 | Any activated doctor could theoretically be listed; no public list yet | Public search and CreateConsultOrder require Approved; own-clinic staff booking may still work per PRE-03 | Not Started
121 | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.5 | TRU-05 | Patient reviews — patients rate and review consultations | New | Trust | §13 + §2.8 | Patient reviews / Write a review | Patient + Public | 4 | P1 | Does not exist | Review linked to PatientAppId; one review per visit; moderation flag optional | Not Started
122 | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.6 | TRU-06 | Review appeal — doctors can appeal a review; patients manage reviews and raise an appeal | New | Trust | §13 + §2.8 | Review appeal / My reviews & appeal | Doctor + Patient + Admin | 4 | P2 | Does not exist | Appeal entity; admin resolves; patient my-reviews list | Not Started
123 | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.7 | TRU-07 | Ranking transparency — patients are shown why doctors are ranked as they are | New | Trust | §13 + §2.2 | Ranking transparency / Ranking explanation | Public + Patient app | 4 | P1 | Does not exist | Documented ranking factors (verified, availability, fee, reviews, experience) + explain API/UI | Not Started
124 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.1 | WEB-01 | Product home page — complete public website presenting the service | Existing Improvement | Patient Website | §4 | Product home page | Patient Website | 4 | P1 | HomeoJobLanding ~50%; Velzon leftovers; CTAs incomplete for book/trust/apps | Book CTA, verified doctors, consult+SaaS pricing teaser, app download placeholders | Not Started
125 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.2 | WEB-02 | Consultation & subscription pricing — transparent pricing display | Existing Improvement | Patient Website | §4 | Consultation & subscription pricing | Patient Website | 3 | P1 | SaaS package marketing /pricing exists; no consult fee display per doctor | Keep SaaS pricing; add consult fee on doctor cards from ConsultFeeConfig | Not Started
126 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.3 | WEB-03 | Doctor discovery — browse and search verified doctors | New | Patient Website | §4 + §2.2 | Doctor discovery | Patient Website | 4 | P0 | Does not exist as a patient product (marketing only) | /book search: name, condition, category; filters availability, fee, experience, language, location | Not Started
127 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.4 | WEB-04 | Self-service booking — book an appointment online without calling the clinic | New | Patient Website | §4 + §2.3 | Self-service booking | Patient Website | 4 | P0 | Staff-only appointments | Funnel /book/:id/slots → review+consent → create Patient+Appointment; OTP; rate-limit; respect schedule + unpaid hold policy PRE-03 | Not Started
128 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.5 | WEB-05 | Online consultation payment on website — pay the fee at the time of booking | New | Patient Website | §4 + §9 | Online consultation payment | Patient Website | 2 | P0 | Does not exist | Checkout uses PAY-03; success/fail pages; pay-at-clinic branch from PAY-05 | Not Started
129 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.6 | WEB-06 | Contact & enquiry form — enquiries reach the admin team and are tracked | Existing Improvement | Patient Website | §4 + §15 | Contact & enquiry form | Patient Website + Admin | 4 | P1 | EnquiryDetail API exists; public form partial; admin inbox screen missing | Confirmation + enquiry id; /admin/enquiries inbox; optional convert to SupportTicket | Not Started
130 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.7 | WEB-07 | Privacy policy — covering data protection, recording and pharmacy consent | Existing Improvement | Legal | §4 + §17 | Privacy policy | Patient Website | 2 | P0 | Privacy page partial; not DPDP/tele/pharmacy complete | Publish PRE-03 legal copy: DPDP, recording, pharmacy, data-rights, family/caregiver | Not Started
131 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.8 | WEB-08 | Terms of service — covering payments, refunds, telemedicine and medicine orders | Existing Improvement | Legal | §4 | Terms of service | Patient Website | 2 | P0 | Terms partial | Payments, refunds, telemedicine, HomeoMeds, codes-before-names | Not Started
132 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.9 | WEB-09 | Doctor self-registration — doctors apply to join the platform online | Existing Improvement | Patient Website | §4 | Doctor self-registration | Public | 4 | P0 | RegisterDoctor ~90%; activates immediately; no document upload | Document upload; pending-verification message; TRU-01 status Pending | Not Started
133 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.10 | WEB-10 | Email activation — secure account activation by email link | Existing Improvement | Auth | §4 | Email activation | Public | 4 | P1 | ActivateUser via /login?UserId= ~90%; align with verification; expiry/resend incomplete | Token expiry, resend, align with credentialing (activation ≠ verified practice) | Not Started
134 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.11 | WEB-11 | Waitlist offer — get offered a slot when one is freed by a cancellation (patient website + later app) | New | Booking | §2.3 | Waitlist offer | Patient Website + App | 5 | P2 | Cancel hook stub in Phase 4; no waitlist records | BookingWaitlist; on cancel, offer FIFO; timeout | Not Started
135 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.12 | WEB-12 | Health articles — educational content to build trust and engagement | Existing Improvement | Patient Website | §2.2 | Health articles | Patient Website + App | 2 | P2 | Blog/news APIs on classic exist for marketing | Reuse blog/news as health articles on public site and later patient app; admin already has news/blog | Not Started
136 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.1 | ERX-01 | Potency module — every remedy carries a defined potency from a managed list, no free text | New | eRx | §11 | Potency module | Doctor Web + Admin | 4 | P0 | Dose saved as empty free-text dose: '' | PotencyMaster CRUD; PotencyId on PrescriptionRemedyDetail; stop empty Dose | Not Started
137 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.2 | ERX-02 | Dosage details — frequency, duration and instructions recorded clearly | New | eRx | §11 | Dosage details | Doctor Web Portal | 4 | P0 | Unstructured/empty dose | Frequency, Duration, Instructions fields on each remedy line | Not Started
138 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.3 | ERX-03 | Visit notes kept separate from the prescription — private clinical notes never appear on the prescription given to the patient or pharmacy | New | eRx | §11 + §5.3 | Visit notes kept separate from the prescription | Doctor Web Portal | 4 | P0 | History notes mixed into Rx modal tabs | Visit Notes panel outside Rx; NoteType; IsErxExcluded; eRx print has remedies+labs only | Not Started
139 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.4 | ERX-04 | Signed digital prescription — issued and locked once signed, so it cannot be altered afterwards | New | eRx | §11 + §2.5 + §5.3 | Signed digital prescription | Doctor Web | 4 | P0 | SavePrescriptionDetail overwritable; no lock/sign | ErxSnapshot immutable on sign; subsequent edits create a new unsigned draft not a silent mutate | Not Started
140 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.5 | ERX-05 | Prescription history — every prescription stored against the patient and visit | New | eRx | §11 | Prescription history | Doctor + Patient | 3 | P1 | Rx saved per appointment but no signed history product | List snapshots by PatientId; open past visit eRx | Not Started
141 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.6 | ERX-06 | Patient view of prescription in app — patient sees the prescription immediately (codes until pharmacy accept) | New | eRx | §11 + §2.5 | Patient view in app | Patient App + Website | 3 | P0 | No patient surface | Patient GET eRx by appointment; names redacted until Phase 14 accept; website optional view | Not Started
142 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.7 | ERX-07 | Print & PDF — printable and downloadable prescription | New | eRx | §11 | Print & PDF | Doctor + Patient | 3 | P1 | No eRx PDF | Patient copy without notes; doctor copy may include letterhead; SecureDocument store | Not Started
143 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.8 | ERX-08 | Remedy code protection — patient sees remedy codes rather than names until a licensed pharmacy accepts the order | New | eRx | §11 | Remedy code protection | Patient | 2 | P0 | Does not exist | Code map on snapshot items; patient serializer strips names; doctor always sees names | Not Started
144 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.9 | ERX-09 | Reveal on pharmacy acceptance — names and price revealed; payment QR or link generated (implemented with HomeoMeds; contract now) | New | eRx | §11 + §12 | Reveal on pharmacy acceptance | Patient + Pharmacy | 2 | P0 | Does not exist | Flag PharmacyAccepted on order; patient GET starts returning names; CreateMedicine payment link; full UI in Phase 14 | Not Started
145 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.10 | ERX-10 | Repeat prescription / refill — patient requests; doctor approves or rejects from the mobile app (inbox on web too) | New | eRx | §11 + §3 + §2.7 | Repeat prescription / refill | Patient + Doctor mobile + Doctor web | 4 | P1 | Does not exist | RefillRequest against ErxSnapshot; doctor inbox; no case-taking on mobile | Not Started
146 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.11 | ERX-11 | Lab orders alongside the prescription (keep existing labs on eRx snapshot) | Existing Improvement | eRx | §11 | Lab orders | Doctor Web | 2 | P1 | Labs on Rx modal live | Include lab orders in signed snapshot; still not on private notes | Not Started
147 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.1 | TEL-01 | Doctor availability — online or offline status and working hours | New | Telemedicine | §10 + §3 | Doctor availability | Doctor Web + Doctor App | 4 | P0 | E-CONSULT status + WhatsApp video stub only; no availability | TeleAvailability + heartbeat; working hours reuse daily schedule | Not Started
148 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.2 | TEL-02 | Telemedicine waiting queue — who is waiting, how long, whether they have paid | New | Telemedicine | §10 + §3 | Telemedicine waiting queue | Doctor Web + App | 5 | P0 | E-CONSULT list only | Queue by doctor + Online + paid/confirmed; wait time; Join | Not Started
149 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.3 | TEL-03 | Video consultation in browser — doctor consults directly from the web portal | New | Telemedicine | §10 | Video consultation in browser | Doctor Web Portal | 5 | P0 | SweetAlert WhatsApp stub | /teleconsult/:sessionId in-browser video; replace stub; vendor from PRE-03 | Not Started
150 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.4 | TEL-04 | Video consultation on mobile — doctor and patient both consult from the app (apps in 16–17; same session tokens) | New | Telemedicine | §10 + §2.4 + §3 | Video consultation on mobile | Patient App + Doctor App | 2 | P0 | No apps | Same TeleSession tokens; mobile join implemented in Phases 16–17 against this API | Not Started
151 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.5 | TEL-05 | Device check — camera, microphone and connection tested before joining | New | Telemedicine | §10 + §2.4 | Device check | Doctor Web + Patient | 2 | P1 | Does not exist | Pre-join device/network check UI; block join on hard fail with guidance | Not Started
152 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.6 | TEL-06 | Waiting room — patient waits with live status until the doctor joins | New | Telemedicine | §10 + §2.4 | Waiting room | Patient | 4 | P1 | Does not exist | Waiting room page: position, doctor online, paid, estimated wait | Not Started
153 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.7 | TEL-07 | Recording consent — consent captured before the consultation; no recording without it | New | Telemedicine | §10 + §2.4 + §17 | Recording consent | Patient + Doctor | 4 | P0 | AudioCaseConsentLog only for audio case taking | ConsentRecord type TeleRecording; block record if declined; both sides see status | Not Started
154 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.8 | TEL-08 | Rejoin after dropped call — either side can rejoin the same consultation | New | Telemedicine | §10 + §2.4 | Rejoin after dropped call | Doctor + Patient | 3 | P0 | Does not exist | Session Active until End; rejoin tokens; dashboard Rejoin | Not Started
155 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.9 | TEL-09 | Join failure handling — clear fallback if the call cannot connect, with options to retry | New | Telemedicine | §10 + §2.4 | Join failure handling / Fallback & join failure handling | Doctor + Patient | 3 | P1 | Does not exist | Error codes; retry; support ticket deep link later; do not silently fail | Not Started
156 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.10 | TEL-10 | Case-linked chat — chat attached to the consultation record, not a loose message thread | New | Telemedicine | §10 + §2.4 | Case-linked chat | Doctor + Patient | 4 | P1 | Does not exist | Messages keyed by TeleSession/PatientAppId; retained with the case | Not Started
157 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.11 | TEL-11 | Consultation summary — issued to the patient at the end of the call | New | Telemedicine | §10 + §2.4 | Consultation summary | Patient + Doctor | 4 | P1 | Does not exist | Doctor submits summary (not private notes); patient sees immediately; may share eRx id | Not Started
158 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.12 | TEL-12 | Instant consultation — patient requests an immediate consultation with an available doctor | New | Telemedicine | §10 + §2.3 | Instant consultation / Instant consult request / Queue & doctor offer | Patient + Doctor | 4 | P1 | Does not exist | Instant request pool; offer doctor; patient accepts; optional surcharge from fee config | Not Started
159 | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.1 | COM-01 | SMS — appointment confirmation, registration confirmation, doctor-unavailable, OTP, reschedule and cancellation | New | Notifications | §14 | SMS | Shared | 5 | P0 | No SMS provider; WhatsApp exists separately | SmsProvider + templates + DLT; event hooks; DND/opt-out on Patient | Not Started
160 | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.2 | COM-02 | WhatsApp — templates, offers, health tips and bulk messaging with delivery reports and opt-out (complete remaining ~50%) | Existing Improvement | Notifications | §14 | WhatsApp | Doctor Web | 4 | P1 | Meta Cloud send/templates/campaigns live; bulk/opt-in/analytics incomplete | Finish bulk queue UX, template approval states, delivery reports, opt-out | Not Started
161 | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.3 | COM-03 | Push notifications — booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests | New | Notifications | §14 + §2.9 + §3 | Push notifications | Patient App + Doctor App | 5 | P0 | Does not exist | DeviceToken + FCM/APNs; event fan-out; apps register tokens in Phases 16–17 | Not Started
162 | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.4 | COM-04 | Email — registration, activation, password reset, invoices and receipts | Existing Improvement | Notifications | §14 | Email | Shared | 4 | P1 | SMTP used for activation/forgot (plaintext issue fixed in Phase 0); no invoice email | Template emails for listed events; invoice PDF attach via SEC-09 | Not Started
163 | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.5 | COM-05 | In-app notification centre — all alerts collected in one place for patients and doctors | New | Notifications | §14 + §2.8 | In-app notification centre / Notifications centre | Patient App + Doctor Web/App | 4 | P1 | Does not exist (Velzon notification demo is not product) | AppNotification inbox; mark read; do not use Velzon demo notifications | Not Started
164 | 13 | Phase 13 — Support & help desk (PDF §15) | 13.1 | SUP-01 | Patient support tickets — patients raise issues from the app and track them | New | Support | §15 + §2.9 | Patient support tickets / Help centre & support tickets | Patient App + Admin | 4 | P1 | Does not exist; EnquiryDetail is not tickets; Velzon tickets demo ignore | SupportTicket reporter=Patient; status track; not Enquiry, not Velzon /apps-tickets-* | Not Started
165 | 13 | Phase 13 — Support & help desk (PDF §15) | 13.2 | SUP-02 | Doctor support tickets — doctors raise issues from the portal | New | Support | §15 | Doctor support tickets | Doctor Web + Admin | 3 | P1 | Does not exist | Same ticket tables; reporter=Doctor | Not Started
166 | 13 | Phase 13 — Support & help desk (PDF §15) | 13.3 | SUP-03 | Admin issue queue — all issues in one queue with priority, assignment and status | New | Support | §15 + §7.2 | Admin issue queue / Support ticket queue | Admin Portal | 4 | P1 | Does not exist | /admin/support-tickets; SLA timestamps; assign | Not Started
167 | 13 | Phase 13 — Support & help desk (PDF §15) | 13.4 | SUP-04 | Ticket conversation — full message thread with attachments | New | Support | §15 | Ticket conversation | Admin + Doctor + Patient | 3 | P1 | Does not exist | Threaded messages + SEC-09 attachments | Not Started
168 | 13 | Phase 13 — Support & help desk (PDF §15) | 13.5 | SUP-05 | Enquiry management — website enquiries tracked (ties WEB-06) | Existing Improvement | Support | §15 + §4 | Enquiry management | Admin Portal | 2 | P1 | API exists; inbox missing | Complete WEB-06 admin inbox if not already; convert enquiry → ticket optional | Not Started
169 | 13 | Phase 13 — Support & help desk (PDF §15) | 13.6 | SUP-06 | Help centre — self-service help content for patients | New | Support | §15 + §2.9 | Help centre | Patient Website + App | 4 | P2 | Does not exist | CMS articles or static help; searchable | Not Started
170 | 13 | Phase 13 — Support & help desk (PDF §15) | 13.7 | SUP-07 | Assisted booking — help for patients who need support booking | New | Support | §15 + §2.9 | Assisted booking | Support + Reception + Patient | 4 | P2 | Does not exist | Staff (admin/support/reception) can complete public booking on behalf of a patient with audit; patient app CTA to request assistance | Not Started
171 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.1 | MED-01 | Pharmacy partner onboarding — licensed premises, licence records, activation checklist | New | HomeoMeds | §12 + §7.2 | Pharmacy partner onboarding / Pharmacy partner management | Pharmacy + Admin | 4 | P0 | Does not exist | PharmacyPartner + licences; admin activation; pharmacy console login | Not Started
172 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.2 | MED-02 | Licence gating — expired or suspended licences blocked automatically from receiving orders | New | HomeoMeds | §12 | Licence gating | Backend | 3 | P0 | Does not exist | Scheduler; routing skip; banner on pharmacy console | Not Started
173 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.3 | MED-03 | Fulfilment consent & pharmacy selection — patient chooses the seller and consents before the prescription is shared | New | HomeoMeds | §12 + §2.7 | Fulfilment consent & pharmacy selection | Patient | 4 | P0 | Does not exist | ConsentRecord PharmacyShare; patient picks from routed sellers; share only after consent | Not Started
174 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.4 | MED-04 | Prescription handoff — signed prescription becomes the order directly — no re-entry, no transcription errors | New | HomeoMeds | §12 + §2.7 | Prescription handoff / Order start | Patient + Pharmacy | 4 | P0 | Does not exist | MedicineOrder copied from ErxSnapshot items (codes); pharmacy never types remedies | Not Started
175 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.5 | MED-05 | Rule-based seller routing — licence validity, service area, working hours and capacity | New | HomeoMeds | §12 | Rule-based seller routing | Backend | 4 | P0 | Does not exist | SellerRoutingRule engine | Not Started
176 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.6 | MED-06 | Manual stock confirmation — pharmacy confirms availability — no live inventory integration required | New | HomeoMeds | §12 | Manual stock confirmation | Pharmacy console | 3 | P0 | Does not exist | Accept/reject with stock flag; do not build inventory master | Not Started
177 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.7 | MED-07 | Pharmacy console — accept or reject, enter price quote, mark ready and dispatched | New | HomeoMeds | §12 | Pharmacy console | Pharmacy console | 5 | P0 | Does not exist | /pharmacy/orders list+detail; OTP accept (SEC-07); quote; ready; dispatched | Not Started
178 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.8 | MED-08 | Quote before payment — the patient always sees the price before paying | New | HomeoMeds | §12 + §2.7 | Quote before payment / Pharmacy selection & quote | Patient | 4 | P0 | Does not exist | MedicineQuote; patient must confirm quote; then PAY-07 | Not Started
179 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.9 | MED-09 | Payment or cash on delivery — both options, with status tracking | New | HomeoMeds | §12 + §9 | Payment or cash on delivery | Patient | 3 | P0 | Stream MEDICINE stub in Phase 6 | Online pay via PAY-02; COD_PENDING until pharmacy confirms collection | Not Started
180 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.10 | MED-10 | Order tracking — live status for the patient at every stage | New | HomeoMeds | §12 + §2.7 | Order tracking | Patient | 5 | P1 | Does not exist | Status timeline events; push updates COM-03 | Not Started
181 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.11 | MED-11 | Medicine ledger shares — seller, platform and delivery recorded (FIN-03 live fill) | New | HomeoMeds | §12 + §8 | Medicine ledger | Account | 2 | P0 | Empty medicine ledger screen from Phase 7 | On pay/COD collect, write SplitSeller/Platform/Delivery from config | Not Started
182 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.12 | MED-12 | Order exception queue — stuck, rejected or failed orders always surfaced — never silent | New | HomeoMeds | §12 | Order exception queue | Admin + Account | 4 | P0 | Does not exist | HomeoMeds exception queue; SLA; never drop | Not Started
183 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.13 | MED-13 | OTP-based control — key actions verified by OTP so Homeocentrum can monitor and trace every transaction | New | HomeoMeds | §12 + §17 | OTP-based control | Pharmacy + Account | 2 | P0 | SEC-07 infrastructure exists | OTP on pharmacy accept (and other high-risk); OtpAudit queryable | Not Started
184 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.14 | MED-14 | Refill orders — repeat orders raised from an existing prescription | New | HomeoMeds | §12 + §2.7 + §11 | Refill orders / Order detail & refill | Patient + Doctor | 3 | P1 | ERX-10 refill request exists | Approved refill creates a new MedicineOrder from the same snapshot; one-tap patient | Not Started
185 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.15 | MED-15 | Order review & consent (patient) — confirm and consent before the prescription is shared | New | HomeoMeds | §2.7 | Order review & consent | Patient | 2 | P0 | Covered by MED-03; explicit review screen still required | Review screen listing codes (not names) + pharmacy + consent checkbox | Not Started
186 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.16 | MED-16 | Medicines tab — all medicine orders in one place (API now; app UI in Phase 16) | New | HomeoMeds | §2.7 | Medicines tab | Patient | 3 | P1 | Does not exist | GET my orders; website optional list; app tab Phase 16 | Not Started
187 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.1 | CON-01 | Family members — add family members under one account | New | Patient identity | §2.1 | Family members | Patient App (API now) | 4 | P0 | Does not exist | FamilyMember under Patient account; bookings can be for a member | Not Started
188 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.2 | CON-02 | Caregiver authorization — let a family member book and manage on their behalf | New | Patient identity | §2.1 | Caregiver authorization | Patient App (API now) | 5 | P0 | Does not exist | CaregiverAuth with scopes; OTP; withdrawable via consent centre | Not Started
189 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.3 | CON-03 | Records timeline + consultation note + document upload APIs | New | Patient records | §2.5 | Records timeline / Consultation note / Document upload | Patient App (API now) | 4 | P0 | Doctor history exists; no patient timeline; no patient upload | Patient timeline DTO (visits, summary, eRx codes, labs); consultation note = TEL-11 summary not private notes; uploads via SEC-09 | Not Started
190 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.4 | CON-04 | Follow-up plan & tasks — clear next steps after each consultation | New | Continuity | §2.6 | Follow-up plan & tasks | Doctor Web + Patient | 4 | P1 | Does not exist (follow-up option in notes does not save) | FollowUpTask created by doctor; patient sees tasks | Not Started
191 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.5 | CON-05 | Symptom diary — record symptoms between visits | New | Continuity | §2.6 | Symptom diary | Patient App (API now) | 4 | P1 | Does not exist | SymptomDiary entries; doctor can read on board | Not Started
192 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.6 | CON-06 | Progress tracking — see improvement over time across visits | New | Continuity | §2.6 | Progress tracking | Patient + Doctor | 4 | P2 | Does not exist | Progress series from diary + visit outcomes; not a fake chart | Not Started
193 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.7 | CON-07 | Consent centre & data rights — view, manage and withdraw consents; request data | New | Privacy | §17 + §2.8 | Consent centre & data rights | Patient App (API now) | 4 | P0 | ConsentRecord from Phase 0 | Patient list/withdraw; data export request (DPDP); deletion request workflow | Not Started
194 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.8 | CON-08 | Patient payments & refunds read model | New | Patient money | §2.8 | Payments & refunds | Patient App (API now) | 2 | P1 | Ledger exists for Account | Patient-safe DTO of own consult+medicine payments and refunds — no other patients, no commission internals | Not Started
195 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.9 | CON-09 | Physical clinic appointment — book an in-person visit as well as online | Existing Improvement | Booking | §2.9 + §5.2 | Physical clinic appointment | Patient | 2 | P1 | ConsultMode added in APT-02; public booking in WEB-04 | Ensure public/patient booking supports In-clinic as first-class, not tele-only | Not Started
196 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.10 | CON-10 | Patient profile setup API — name, age, gender, contact and health basics | New | Patient identity | §2.1 | Profile setup | Patient App (API now) | 4 | P0 | Clinic-created Patient exists; no self-serve profile product | Patient profile fields + health basics; used by OTP-verified patient token | Not Started
197 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.1 | PAT-01 | Patient app — language selection on first open | New | Patient Mobile | §2.1 | Language selection | Patient Mobile App | 4 | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
198 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.2 | PAT-02 | Patient app — welcome and introduction | New | Patient Mobile | §2.1 | Welcome & introduction | Patient Mobile App | 4 | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
199 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.3 | PAT-03 | Patient app — mobile number + OTP login (PatientAuth) | New | Patient Mobile | §2.1 | Mobile number + OTP login | Patient Mobile App | 4 | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
200 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.4 | PAT-04 | Patient app — profile setup | New | Patient Mobile | §2.1 | Profile setup | Patient Mobile App | 4 | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
201 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.5 | PAT-05 | Patient app — privacy consent before data stored | New | Patient Mobile | §2.1 | Privacy consent | Patient Mobile App | 4 | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
202 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.6 | PAT-06 | Patient app — family members | New | Patient Mobile | §2.1 | Family members | Patient Mobile App | 4 | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
203 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.7 | PAT-07 | Patient app — caregiver authorization | New | Patient Mobile | §2.1 | Caregiver authorization | Patient Mobile App | 4 | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
204 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.8 | PAT-08 | Patient app — home dashboard | New | Patient Mobile | §2.2 | Home dashboard | Patient Mobile App | 4 | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
205 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.9 | PAT-09 | Patient app — search and care categories | New | Patient Mobile | §2.2 | Search & care categories | Patient Mobile App | 4 | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
206 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.10 | PAT-10 | Patient app — search results | New | Patient Mobile | §2.2 | Search results | Patient Mobile App | 4 | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
207 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.11 | PAT-11 | Patient app — discovery filters | New | Patient Mobile | §2.2 | Filters | Patient Mobile App | 4 | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
208 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.12 | PAT-12 | Patient app — doctor profile | New | Patient Mobile | §2.2 | Doctor profile | Patient Mobile App | 4 | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
209 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.13 | PAT-13 | Patient app — verified badge on doctor | New | Patient Mobile | §2.2 | Credentials & verification | Patient Mobile App | 4 | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
210 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.14 | PAT-14 | Patient app — ranking explanation | New | Patient Mobile | §2.2 | Ranking explanation | Patient Mobile App | 4 | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
211 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.15 | PAT-15 | Patient app — health articles | New | Patient Mobile | §2.2 | Health articles | Patient Mobile App | 4 | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
212 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.16 | PAT-16 | Patient app — slot picker | New | Patient Mobile | §2.3 | Slot picker | Patient Mobile App | 4 | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
213 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.17 | PAT-17 | Patient app — booking review and consent | New | Patient Mobile | §2.3 | Booking review & consent | Patient Mobile App | 4 | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
214 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.18 | PAT-18 | Patient app — checkout | New | Patient Mobile | §2.3 | Checkout | Patient Mobile App | 4 | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
215 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.19 | PAT-19 | Patient app — payment status | New | Patient Mobile | §2.3 | Payment status | Patient Mobile App | 4 | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
216 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.20 | PAT-20 | Patient app — appointment detail | New | Patient Mobile | §2.3 | Appointment detail | Patient Mobile App | 4 | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
217 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.21 | PAT-21 | Patient app — reschedule | New | Patient Mobile | §2.3 | Reschedule appointment | Patient Mobile App | 4 | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
218 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.22 | PAT-22 | Patient app — cancel | New | Patient Mobile | §2.3 | Cancel appointment | Patient Mobile App | 4 | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
219 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.23 | PAT-23 | Patient app — waitlist offer | New | Patient Mobile | §2.3 | Waitlist offer | Patient Mobile App | 4 | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
220 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.24 | PAT-24 | Patient app — instant consult request | New | Patient Mobile | §2.3 | Instant consult request | Patient Mobile App | 4 | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
221 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.25 | PAT-25 | Patient app — queue and doctor offer | New | Patient Mobile | §2.3 | Queue & doctor offer | Patient Mobile App | 4 | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
222 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.26 | PAT-26 | Patient app — device check | New | Patient Mobile | §2.4 | Device check | Patient Mobile App | 4 | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
223 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.27 | PAT-27 | Patient app — waiting room | New | Patient Mobile | §2.4 | Waiting room | Patient Mobile App | 4 | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
224 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.28 | PAT-28 | Patient app — live video | New | Patient Mobile | §2.4 | Live video consultation | Patient Mobile App | 4 | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
225 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.29 | PAT-29 | Patient app — recording consent | New | Patient Mobile | §2.4 | Recording consent | Patient Mobile App | 4 | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
226 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.30 | PAT-30 | Patient app — join failure fallback | New | Patient Mobile | §2.4 | Fallback & join failure handling | Patient Mobile App | 4 | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
227 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.31 | PAT-31 | Patient app — case-linked chat | New | Patient Mobile | §2.4 | Case-linked chat | Patient Mobile App | 4 | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
228 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.32 | PAT-32 | Patient app — consultation summary | New | Patient Mobile | §2.4 | Consultation summary | Patient Mobile App | 4 | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
229 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.33 | PAT-33 | Patient app — rejoin | New | Patient Mobile | §2.4 | Rejoin after dropped call | Patient Mobile App | 4 | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
230 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.34 | PAT-34 | Patient app — records timeline | New | Patient Mobile | §2.5 | Records timeline | Patient Mobile App | 4 | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
231 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.35 | PAT-35 | Patient app — consultation note (summary, not private notes) | New | Patient Mobile | §2.5 | Consultation note | Patient Mobile App | 4 | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
232 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.36 | PAT-36 | Patient app — signed eRx (codes until pharmacy accept) | New | Patient Mobile | §2.5 | Signed digital prescription | Patient Mobile App | 4 | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
233 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.37 | PAT-37 | Patient app — document upload | New | Patient Mobile | §2.5 | Document upload | Patient Mobile App | 4 | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
234 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.38 | PAT-38 | Patient app — follow-up plan and tasks | New | Patient Mobile | §2.6 | Follow-up plan & tasks | Patient Mobile App | 4 | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
235 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.39 | PAT-39 | Patient app — symptom diary | New | Patient Mobile | §2.6 | Symptom diary | Patient Mobile App | 4 | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
236 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.40 | PAT-40 | Patient app — progress tracking | New | Patient Mobile | §2.6 | Progress tracking | Patient Mobile App | 4 | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
237 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.41 | PAT-41 | Patient app — medicines tab | New | Patient Mobile | §2.7 | Medicines tab | Patient Mobile App | 4 | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
238 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.42 | PAT-42 | Patient app — start HomeoMeds order from eRx | New | Patient Mobile | §2.7 | Order start | Patient Mobile App | 4 | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
239 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.43 | PAT-43 | Patient app — pharmacy selection and quote | New | Patient Mobile | §2.7 | Pharmacy selection & quote | Patient Mobile App | 4 | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
240 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.44 | PAT-44 | Patient app — order review and consent | New | Patient Mobile | §2.7 | Order review & consent | Patient Mobile App | 4 | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
241 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.45 | PAT-45 | Patient app — order tracking | New | Patient Mobile | §2.7 | Order tracking | Patient Mobile App | 4 | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
242 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.46 | PAT-46 | Patient app — order detail and refill | New | Patient Mobile | §2.7 | Order detail & refill | Patient Mobile App | 4 | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
243 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.47 | PAT-47 | Patient app — write a review | New | Patient Mobile | §2.8 | Write a review | Patient Mobile App | 4 | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
244 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.48 | PAT-48 | Patient app — my reviews and appeal | New | Patient Mobile | §2.8 | My reviews & appeal | Patient Mobile App | 4 | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
245 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.49 | PAT-49 | Patient app — payments and refunds | New | Patient Mobile | §2.8 | Payments & refunds | Patient Mobile App | 4 | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
246 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.50 | PAT-50 | Patient app — profile and settings | New | Patient Mobile | §2.8 | Profile & settings | Patient Mobile App | 4 | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
247 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.51 | PAT-51 | Patient app — consent centre and data rights | New | Patient Mobile | §2.8 | Consent centre & data rights | Patient Mobile App | 4 | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
248 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.52 | PAT-52 | Patient app — notifications centre | New | Patient Mobile | §2.8 | Notifications centre | Patient Mobile App | 4 | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
249 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.53 | PAT-53 | Patient app — help centre and tickets | New | Patient Mobile | §2.9 | Help centre & support tickets | Patient Mobile App | 4 | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
250 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.54 | PAT-54 | Patient app — physical clinic booking | New | Patient Mobile | §2.9 | Physical clinic appointment | Patient Mobile App | 4 | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
251 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.55 | PAT-55 | Patient app — assisted booking request | New | Patient Mobile | §2.9 | Assisted booking | Patient Mobile App | 4 | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
252 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.56 | PAT-56 | Patient app — low-data mode | New | Patient Mobile | §2.9 | Low-data mode | Patient Mobile App | 4 | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
253 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.57 | PAT-57 | Patient app — push notifications | New | Patient Mobile | §2.9 | Push notifications | Patient Mobile App | 4 | P1 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | Not Started
254 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.58 | PAT-58 | Patient app — iOS and Android store release, device matrix, and parity QA | New | Patient Mobile | §2 + §18 | Patient mobile app iOS and Android | Patient Mobile App | 3 | P0 | No app | Store builds; crash-free join; feature parity checklist against every §2 row | Not Started
255 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.1 | DMO-01 | Doctor app — login & identity (same login and same account as the web portal) | New | Doctor Mobile | §3 | Login & identity | Doctor Mobile App | 4 | P0 | No doctor app | Same Account login + DoctorId; bind device; no separate doctor identity | Not Started
256 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.2 | DMO-02 | Doctor app — first-run onboarding (guided setup, number confirmation and permissions) | New | Doctor Mobile | §3 | First-run onboarding | Doctor Mobile App | 4 | P1 | No app | Confirm registered mobile; permission primer | Not Started
257 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.3 | DMO-03 | Doctor app — notification permissions (push, microphone and camera handled properly) | New | Doctor Mobile | §3 | Notification permissions | Doctor Mobile App | 4 | P0 | No app | OS permission flows; settings deep link if denied | Not Started
258 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.4 | DMO-04 | Doctor app — today’s queue & schedule (the full day at a glance) | New | Doctor Mobile | §3 | Today’s queue & schedule | Doctor Mobile App | 4 | P0 | No app | Appointment list APIs; payment + tele flags; no Patient Board | Not Started
259 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.5 | DMO-05 | Doctor app — availability toggle (go online or offline, set working hours) | New | Doctor Mobile | §3 | Availability toggle | Doctor Mobile App | 4 | P0 | No app | Same TeleAvailability + schedule APIs as web | Not Started
260 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.6 | DMO-06 | Doctor app — push notifications (waiting, booking, reschedule, cancellation, refill, payment received) | New | Doctor Mobile | §3 | Push notifications | Doctor Mobile App | 4 | P0 | No app | Consume COM-03 doctor templates | Not Started
261 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.7 | DMO-07 | Doctor app — patient context card (name, age, chief complaint and last visit) — NO case-taking | New | Doctor Mobile | §3 | Patient context card | Doctor Mobile App | 4 | P0 | No app; PDF: detailed case-taking stays on the web portal | Read-only card; explicitly no repertory/audio/Rx compose | Not Started
262 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.8 | DMO-08 | Doctor app — join consultation (video or audio from the phone) | New | Doctor Mobile | §3 | Join consultation | Doctor Mobile App | 4 | P0 | No app | Same session tokens as TEL-03/04 | Not Started
263 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.9 | DMO-09 | Doctor app — refill approval (approve or reject repeat prescription requests) | New | Doctor Mobile | §3 + §11 | Refill approval | Doctor Mobile App | 4 | P0 | No app | ERX-10 inbox; approve only — Patient Board remains web | Not Started
264 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.10 | DMO-10 | Doctor app — earnings summary (today, this week, this month, with payout status) | New | Doctor Mobile | §3 + §16 | Earnings summary | Doctor Mobile App | 4 | P1 | No app | Account ledger read model for this DoctorId — not a second money system | Not Started
265 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.11 | DMO-11 | Doctor app — offline handling (weak connection or expired session) | New | Doctor Mobile | §3 | Offline handling | Doctor Mobile App | 4 | P1 | No app | Queued actions policy (do not fake join); session expiry uses SEC-03 | Not Started
266 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.12 | DMO-12 | Doctor app — reliability monitoring (failures reported automatically) | New Integration | Doctor Mobile | §3 | Reliability monitoring | Doctor Mobile App | 2 | P1 | No app | Crash/error SDK; join failures also as TeleSessionEvent | Not Started
267 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.13 | DMO-13 | Doctor app — iOS and Android parity QA (queue, availability, notifications, context, video, refill, earnings) | New | Doctor Mobile | §3 + §18 | Doctor mobile app iOS and Android | Doctor Mobile App | 2 | P0 | No app | Parity checklist for every §3 row on both OS | Not Started
268 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.1 | RPT-01 | Admin overview dashboard — platform-wide activity at a glance (replace Velzon ecommerce) | Existing Improvement | Reports | §16 + §7.2 | Admin overview dashboard / Admin dashboard | Admin Portal | 4 | P0 | Velzon ecommerce dashboard 0% product; login lands /dashboard | True /admin/dashboard KPIs: doctors, credentialing, bookings, GMV, failed payments, tickets, HomeoMeds exceptions; redirect /dashboard away from StoreVisits | Not Started
269 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.2 | RPT-02 | Doctor practice statistics — patient and consultation trends (extend existing charts) | Existing Improvement | Reports | §16 + §5.1 | Doctor practice statistics | Doctor Web | 4 | P1 | Patient stats charts live | Keep as foundation; ensure visit type/mode included after APT-02 | Not Started
270 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.3 | RPT-03 | Follow-up analysis — due/overdue patients and follow-up conversion | New | Reports | §16 | Follow-up analysis | Doctor Web | 4 | P1 | Does not exist; follow-up option in notes does not save | /doctor/follow-up-analysis from VisitType + CON-04 tasks | Not Started
271 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.4 | RPT-04 | Clinic performance analysis — appointments, slot utilisation, no-shows, cancellations, waiting time and revenue | New | Reports | §16 | Clinic performance analysis | Doctor Web | 4 | P1 | Does not exist | /doctor/clinic-performance including payment collected and tele duration if timed | Not Started
272 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.5 | RPT-05 | Payment reconciliation report — bookings matched against payments | New | Reports | §16 + §7.2 | Payment reconciliation report / Consult booking & payment reconciliation | Admin + Account | 3 | P1 | FIN-02 built the queue; this is the report/export | Exportable report from the same reconciliation query | Not Started
273 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.6 | RPT-06 | Settlement & payout reports — amounts due and paid to doctors and pharmacies | New | Reports | §16 + §8 | Settlement & payout reports | Account | 3 | P1 | FIN-04/05 exist as ops screens | Formal report/export of runs and payouts | Not Started
274 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.7 | RPT-07 | GST & invoice reports (reporting surface of FIN-08) | New | Reports | §16 + §8 | GST & invoice reports | Account | 2 | P1 | FIN-08 built tax screen | Confirm report pack (GSTR-style export as agreed with CA) — configuration | Not Started
275 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.8 | RPT-08 | Doctor earnings summary — daily, weekly and monthly earnings with payout status (web + same API as DMO-10) | New | Reports | §16 + §3 | Doctor earnings summary | Doctor Web + App | 4 | P1 | Does not exist | Web earnings page using same API as doctor app | Not Started
276 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.9 | RPT-09 | Medicine order reports — order volumes, fulfilment and exceptions | New | Reports | §16 + §12 | Medicine order reports | Admin + Account | 4 | P1 | Does not exist | Volumes, SLA, exception counts from HomeoMeds | Not Started
277 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.10 | RPT-10 | Platform users remaining 20% — import, export and activation control | Existing Improvement | Admin | §7.2 | Platform users | Admin Portal | 4 | P1 | List/Add/Edit live; Import/Export buttons dead; no verification column | Wire Import/Export; verification column; activate/lock; link credentialing | Not Started
278 | 19 | Phase 19 — Cross-surface QA, NFR, delivery summary gate (PDF §1 + §18) | 19.1 | QA-01 | One ecosystem proof — patient, appointment, prescription and payment created anywhere are visible everywhere | Regression | QA | §1 + §18 | One connected ecosystem | All | 3 | P0 | Surfaces were built in phases | End-to-end scripts covering all six user types | Not Started
279 | 19 | Phase 19 — Cross-surface QA, NFR, delivery summary gate (PDF §1 + §18) | 19.2 | QA-02 | Delivery summary gate — every area in PDF §18 signed off | Regression | QA | §18 | Summary of delivery | Programme | 2 | P0 | This register is the scope | Walk the coverage sheet; zero PDF rows with Status≠Done unless formally deferred with client sign | Not Started
280 | 19 | Phase 19 — Cross-surface QA, NFR, delivery summary gate (PDF §1 + §18) | 19.3 | NFR-01 | NFR — performance, low-data, reliability, secrets, dual-API freeze | Existing Modification | NFR | §2.9 + §3 + §17 | Low-data mode / Reliability monitoring / Secure login | All | 3 | P0 | Known risks: plaintext passwords (fixed P0), secrets in appsettings, dual API drift | Rotate secrets; no new third API; patient low-data verified; doctor reliability SDK live | Not Started

## 03_Sequential_Register
SEQUENTIAL DEVELOPMENT REGISTER — execute top to bottom by Seq. Filter Phase / Work Type / Surface as needed. Status is the only column developers should edit daily.
Seq | Phase | Phase Name | WBS | Main Task ID | Main Task | Sub Task ID | Sub Task | Work Type | Module / Area | PDF Section | PDF Feature (exact wording) | PDF Delivery Text | Application Surface | Layer | Frontend | Backend | Database | API | Mobile | Integration | Priority | Effort Band | Depends On | Existing Capability (AS-IS) | Gap / Change Required (TO-BE) | Acceptance Criteria | Status | Owner | Notes
1 | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.1 | PRE-01 | Decide settlement model — Homeocentrum holds all money (food-delivery / quick-commerce pattern) | PRE-01.01 | Workshop with finance: confirm Homeocentrum is single merchant of record for consult + medicine + subscription | Client Decision | Finance | §9 + §8 | Every transaction passes through Homeocentrum | Built on the principle: every transaction passes through Homeocentrum, in the same way a food-delivery or quick-commerce platform holds all payments centrally. | Account / Gateway | Decision | No | No | No | No | No | No | P0 | S | — | Only doctor SaaS subscription via client-side Razorpay; no consult/medicine ledger | Written decision: platform-held funds + periodic NEFT (v1) vs Razorpay Route (v2) | Signed decision recorded; payout architecture unblocked | Not Started
2 | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.1 | PRE-01 | Decide settlement model — Homeocentrum holds all money (food-delivery / quick-commerce pattern) | PRE-01.02 | Choose v1 payout mechanic: Homeocentrum-held + NEFT/IMPS vs Razorpay Route / linked accounts | Client Decision | Finance | §9 + §8 | Every transaction passes through Homeocentrum | Built on the principle: every transaction passes through Homeocentrum, in the same way a food-delivery or quick-commerce platform holds all payments centrally. | Account / Gateway | Decision | No | No | No | No | No | Yes | P0 | S | PRE-01.01 | Only doctor SaaS subscription via client-side Razorpay; no consult/medicine ledger | Written decision: platform-held funds + periodic NEFT (v1) vs Razorpay Route (v2) | Signed decision recorded; payout architecture unblocked | Not Started
3 | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.1 | PRE-01 | Decide settlement model — Homeocentrum holds all money (food-delivery / quick-commerce pattern) | PRE-01.03 | Record decision in config (SettlementModel) — engineering must not hardcode a split model | Configuration | Finance | §9 + §8 | Every transaction passes through Homeocentrum | Built on the principle: every transaction passes through Homeocentrum, in the same way a food-delivery or quick-commerce platform holds all payments centrally. | Account / Gateway | Configuration | No | Yes | No | No | No | No | P0 | S | PRE-01.02 | Only doctor SaaS subscription via client-side Razorpay; no consult/medicine ledger | Written decision: platform-held funds + periodic NEFT (v1) vs Razorpay Route (v2) | Signed decision recorded; payout architecture unblocked | Not Started
4 | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.2 | PRE-02 | Decide reception cash policy — clinic retains vs remits to Homeocentrum | PRE-02.01 | OQ: cash collected at reception retained by clinic or remitted to Homeocentrum? | Client Decision | Finance / Reception | §9 | Reception payment collection | Cash, UPI, card or payment link with printed receipt | Account / Reception | Decision | No | No | No | No | No | No | P0 | S | — | No reception collection; no S3 ledger | Policy for cash/UPI at clinic: retain at clinic (still ledgered) or remit | Written policy; clinic collection view can be designed | Not Started
5 | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.2 | PRE-02 | Decide reception cash policy — clinic retains vs remits to Homeocentrum | PRE-02.02 | Document GST treatment on consult fee, platform fee, and medicine (on which amount, which GSTIN) | Client Decision | Finance / Reception | §9 | Reception payment collection | Cash, UPI, card or payment link with printed receipt | Account / Reception | Decision | No | No | No | No | No | No | P0 | S | PRE-02.01 | No reception collection; no S3 ledger | Policy for cash/UPI at clinic: retain at clinic (still ledgered) or remit | Written policy; clinic collection view can be designed | Not Started
6 | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.2 | PRE-02 | Decide reception cash policy — clinic retains vs remits to Homeocentrum | PRE-02.03 | Confirm commission %, settlement hold T+N days, invoice numbering series — configuration not code | Configuration | Finance / Reception | §9 | Reception payment collection | Cash, UPI, card or payment link with printed receipt | Account / Reception | Configuration | No | Yes | No | No | No | No | P0 | S | PRE-02.02 | No reception collection; no S3 ledger | Policy for cash/UPI at clinic: retain at clinic (still ledgered) or remit | Written policy; clinic collection view can be designed | Not Started
7 | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.3 | PRE-03 | Vendor and legal gates — video SDK, SMS, WhatsApp, push, DPDP copy | PRE-03.01 | Select in-browser + mobile video vendor (Agora / Twilio / Daily / WebRTC self-host) — required for §10 | Client Decision | Platform | §10 + §14 + §17 | Telemedicine + notifications + consent | Video consultation; SMS/WhatsApp/Push/Email; consent records | Shared | Decision | No | No | No | No | No | Yes | P0 | S | — | WhatsApp Meta Cloud partial; no video SDK; no SMS provider; no FCM; privacy/terms incomplete for DPDP/tele/pharmacy | Named vendors + DPDP-ready legal copy before those phases start | Vendors contracted or shortlisted; legal pages drafted | Not Started
8 | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.3 | PRE-03 | Vendor and legal gates — video SDK, SMS, WhatsApp, push, DPDP copy | PRE-03.02 | Select SMS provider (MSG91 / Twilio / etc.) and confirm DLT templates for appointment/OTP/cancel | Client Decision | Platform | §10 + §14 + §17 | Telemedicine + notifications + consent | Video consultation; SMS/WhatsApp/Push/Email; consent records | Shared | Decision | No | No | No | No | No | Yes | P0 | S | PRE-03.01 | WhatsApp Meta Cloud partial; no video SDK; no SMS provider; no FCM; privacy/terms incomplete for DPDP/tele/pharmacy | Named vendors + DPDP-ready legal copy before those phases start | Vendors contracted or shortlisted; legal pages drafted | Not Started
9 | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.3 | PRE-03 | Vendor and legal gates — video SDK, SMS, WhatsApp, push, DPDP copy | PRE-03.03 | Legal: privacy (data protection, recording, pharmacy consent) and terms (payments, refunds, telemedicine, medicine orders) drafted for §4 + §17 | Client Decision | Platform | §10 + §14 + §17 | Telemedicine + notifications + consent | Video consultation; SMS/WhatsApp/Push/Email; consent records | Shared | Legal | No | No | No | No | No | No | P0 | M | PRE-03.02 | WhatsApp Meta Cloud partial; no video SDK; no SMS provider; no FCM; privacy/terms incomplete for DPDP/tele/pharmacy | Named vendors + DPDP-ready legal copy before those phases start | Vendors contracted or shortlisted; legal pages drafted | Not Started
10 | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.3 | PRE-03 | Vendor and legal gates — video SDK, SMS, WhatsApp, push, DPDP copy | PRE-03.04 | OQ: unpaid-booking slot hold duration vs release immediately if patient does not pay | Client Decision | Platform | §10 + §14 + §17 | Telemedicine + notifications + consent | Video consultation; SMS/WhatsApp/Push/Email; consent records | Shared | Decision | No | No | No | No | No | No | P0 | S | PRE-03.03 | WhatsApp Meta Cloud partial; no video SDK; no SMS provider; no FCM; privacy/terms incomplete for DPDP/tele/pharmacy | Named vendors + DPDP-ready legal copy before those phases start | Vendors contracted or shortlisted; legal pages drafted | Not Started
11 | PRE | PRE — Client gates (must sign before Phase 6 money spine) | PRE.3 | PRE-03 | Vendor and legal gates — video SDK, SMS, WhatsApp, push, DPDP copy | PRE-03.05 | OQ: live-doctor credentialing backfill — auto-Approve existing doctors? Unverified doctors visible only to own clinic? | Client Decision | Platform | §10 + §14 + §17 | Telemedicine + notifications + consent | Video consultation; SMS/WhatsApp/Push/Email; consent records | Shared | Decision | No | No | No | No | No | No | P0 | S | PRE-03.04 | WhatsApp Meta Cloud partial; no video SDK; no SMS provider; no FCM; privacy/terms incomplete for DPDP/tele/pharmacy | Named vendors + DPDP-ready legal copy before those phases start | Vendors contracted or shortlisted; legal pages drafted | Not Started
12 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.1 | FND-01 | One connected ecosystem — shared keys so a patient, appointment, prescription and payment created anywhere are visible everywhere | FND-01.01 | Publish shared-key design (DoctorId, PatientId, PatientAppId, CaseId, ErxId, LedgerTxnId, MedicineOrderId) and event list (created/rescheduled/cancelled/paid/signed/accepted) | New | Platform | §1 | One connected ecosystem serving six types of users | A patient, an appointment, a prescription and a payment created anywhere in the system are visible everywhere else — there are no separate systems to reconcile. | Shared | Architecture | No | Yes | Yes | No | No | No | P0 | M | — | Doctor/Admin/Reception web only; Patient, Account, Pharmacy roles do not exist; no shared payment or eRx keys | Canonical keys: UserId/DoctorId, PatientId, PatientAppId, CaseId, ErxId, LedgerTxnId, MedicineOrderId — used by every surface | Any write on one surface is readable on all authorised surfaces within SLA; no dual ledgers | Not Started
13 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.1 | FND-01 | One connected ecosystem — shared keys so a patient, appointment, prescription and payment created anywhere are visible everywhere | FND-01.02 | Add role enum values Patient, Account, PharmacyPartner alongside existing Admin/Doctor/Reception (keep unused Management/Supervisor/Inspector unused) | New | Platform | §1 | One connected ecosystem serving six types of users | A patient, an appointment, a prescription and a payment created anywhere in the system are visible everywhere else — there are no separate systems to reconcile. | Shared | Database + Auth | Yes | Yes | Yes | No | No | No | P0 | S | FND-01.01 | Doctor/Admin/Reception web only; Patient, Account, Pharmacy roles do not exist; no shared payment or eRx keys | Canonical keys: UserId/DoctorId, PatientId, PatientAppId, CaseId, ErxId, LedgerTxnId, MedicineOrderId — used by every surface | Any write on one surface is readable on all authorised surfaces within SLA; no dual ledgers | Not Started
14 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.1 | FND-01 | One connected ecosystem — shared keys so a patient, appointment, prescription and payment created anywhere are visible everywhere | FND-01.03 | All new domain modules on NigaHomeopathy-API (.NET 8); do not create a third API; classic API only where login/Rx-write/Razorpay already live until ported | Existing Modification | Platform | §1 | One connected ecosystem serving six types of users | A patient, an appointment, a prescription and a payment created anywhere in the system are visible everywhere else — there are no separate systems to reconcile. | Shared | Architecture | No | Yes | No | Yes | No | No | P0 | S | FND-01.02 | Dual API api.homeocentrum.com + api1.homeocentrum.com | New work on .NET 8; port Razorpay off classic OrderController as part of Phase 6 | Any write on one surface is readable on all authorised surfaces within SLA; no dual ledgers | Not Started
15 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.1 | FND-01 | One connected ecosystem — shared keys so a patient, appointment, prescription and payment created anywhere are visible everywhere | FND-01.04 | QA: create appointment on Reception → visible on Doctor web; pay on Patient web → same PaymentStatus on Doctor and Account (after Phase 6) | Regression | Platform | §1 | One connected ecosystem serving six types of users | A patient, an appointment, a prescription and a payment created anywhere in the system are visible everywhere else — there are no separate systems to reconcile. | Shared | QA | Yes | Yes | No | Yes | No | No | P2 | S | FND-01.03 | Doctor/Admin/Reception web only; Patient, Account, Pharmacy roles do not exist; no shared payment or eRx keys | Canonical keys: UserId/DoctorId, PatientId, PatientAppId, CaseId, ErxId, LedgerTxnId, MedicineOrderId — used by every surface | Any write on one surface is readable on all authorised surfaces within SLA; no dual ledgers | Not Started
16 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.2 | FND-02 | Delivery footprint — 2 mobile apps · 5 web portals · payment · telemedicine · digital prescription · HomeoMeds (programme skeleton) | FND-02.01 | Web: add Account layout + home redirect; Pharmacy layout stub; do not build screens yet | New | Platform | §1 | Delivery covers | 2 mobile applications · 5 web portals · payment system · telemedicine · digital prescription · online medicine delivery. | Shared | Web SPA | Yes | No | No | No | No | No | P0 | M | — | 1 web SPA (Admin/Doctor/Reception + marketing). No patient app, doctor app, Account portal, Pharmacy console | Repo/route skeleton: Patient Website, Doctor Web, Reception, Admin, Account (+ Pharmacy console under HomeoMeds); Patient + Doctor mobile later | Five web portal shells routable by role; mobile apps scheduled in Phases 16–17 not started here | Not Started
17 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.2 | FND-02 | Delivery footprint — 2 mobile apps · 5 web portals · payment · telemedicine · digital prescription · HomeoMeds (programme skeleton) | FND-02.02 | Extend roles.js and AuthProtected with per-route ACL skeleton (deny-by-default for new routes) | Existing Improvement | Platform | §1 | Delivery covers | 2 mobile applications · 5 web portals · payment system · telemedicine · digital prescription · online medicine delivery. | Shared | Web SPA | Yes | No | No | No | No | No | P0 | M | FND-02.01 | 1 web SPA (Admin/Doctor/Reception + marketing). No patient app, doctor app, Account portal, Pharmacy console | Repo/route skeleton: Patient Website, Doctor Web, Reception, Admin, Account (+ Pharmacy console under HomeoMeds); Patient + Doctor mobile later | Five web portal shells routable by role; mobile apps scheduled in Phases 16–17 not started here | Not Started
18 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.2 | FND-02 | Delivery footprint — 2 mobile apps · 5 web portals · payment · telemedicine · digital prescription · HomeoMeds (programme skeleton) | FND-02.03 | Mobile: create Patient app and Doctor app repository/bootstrap (React Native or agreed stack) — empty shells only | New | Platform | §1 | Delivery covers | 2 mobile applications · 5 web portals · payment system · telemedicine · digital prescription · online medicine delivery. | Shared | Mobile | No | No | No | No | Yes | No | P0 | L | FND-02.02 | 1 web SPA (Admin/Doctor/Reception + marketing). No patient app, doctor app, Account portal, Pharmacy console | Repo/route skeleton: Patient Website, Doctor Web, Reception, Admin, Account (+ Pharmacy console under HomeoMeds); Patient + Doctor mobile later | Five web portal shells routable by role; mobile apps scheduled in Phases 16–17 not started here | Not Started
19 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.2 | FND-02 | Delivery footprint — 2 mobile apps · 5 web portals · payment · telemedicine · digital prescription · HomeoMeds (programme skeleton) | FND-02.04 | Document the five portals: Patient Website, Doctor Web Portal, Reception Portal, Admin Portal, Account Department (Pharmacy console is HomeoMeds, not a 6th portal in the PDF count) | New | Platform | §1 | Delivery covers | 2 mobile applications · 5 web portals · payment system · telemedicine · digital prescription · online medicine delivery. | Shared | Architecture | No | No | No | No | No | No | P0 | S | FND-02.03 | 1 web SPA (Admin/Doctor/Reception + marketing). No patient app, doctor app, Account portal, Pharmacy console | Repo/route skeleton: Patient Website, Doctor Web, Reception, Admin, Account (+ Pharmacy console under HomeoMeds); Patient + Doctor mobile later | Five web portal shells routable by role; mobile apps scheduled in Phases 16–17 not started here | Not Started
20 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.3 | SEC-01 | Secure login — protected credentials for every user type | SEC-01.01 | DB/Migration: hash existing UserMaster passwords (bcrypt/PBKDF2); never store new plaintext | Data Migration | Security | §17 | Secure login | Protected credentials for every user type | All web + later mobile | Database | No | Yes | Yes | No | No | No | P0 | M | — | POST /Account/Login on classic API; JWT in sessionStorage; doctor/user passwords compared plaintext; reception hashed on classic; fakeBackend() still mounted | Hashed passwords; Role claim on JWT; disable fake backend for production paths; Patient OTP login is Phase 8 (not password) | No plaintext password compare; every role including future Patient/Account/Pharmacy authenticates through a protected path | Not Started
21 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.3 | SEC-01 | Secure login — protected credentials for every user type | SEC-01.02 | API: Login verifies hash; embed Role + DoctorId claims; keep classic login URL until .NET 8 login is cut over | Existing Modification | Security | §17 | Secure login | Protected credentials for every user type | All web + later mobile | API | No | Yes | No | Yes | No | No | P0 | M | SEC-01.01 | POST /Account/Login on classic API; JWT in sessionStorage; doctor/user passwords compared plaintext; reception hashed on classic; fakeBackend() still mounted | Hashed passwords; Role claim on JWT; disable fake backend for production paths; Patient OTP login is Phase 8 (not password) | No plaintext password compare; every role including future Patient/Account/Pharmacy authenticates through a protected path | Not Started
22 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.3 | SEC-01 | Secure login — protected credentials for every user type | SEC-01.03 | UI: remove fakeBackend() from App.js production path; login still Formik/Yup | Existing Modification | Security | §17 | Secure login | Protected credentials for every user type | All web + later mobile | Web SPA | Yes | No | No | No | No | No | P0 | S | SEC-01.02 | POST /Account/Login on classic API; JWT in sessionStorage; doctor/user passwords compared plaintext; reception hashed on classic; fakeBackend() still mounted | Hashed passwords; Role claim on JWT; disable fake backend for production paths; Patient OTP login is Phase 8 (not password) | No plaintext password compare; every role including future Patient/Account/Pharmacy authenticates through a protected path | Not Started
23 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.3 | SEC-01 | Secure login — protected credentials for every user type | SEC-01.04 | QA: Admin, Doctor, Reception login; invalid password; deactivated user; SQL injection/brute-force rate limit | Regression | Security | §17 | Secure login | Protected credentials for every user type | All web + later mobile | QA | Yes | Yes | No | Yes | No | No | P0 | S | SEC-01.03 | POST /Account/Login on classic API; JWT in sessionStorage; doctor/user passwords compared plaintext; reception hashed on classic; fakeBackend() still mounted | Hashed passwords; Role claim on JWT; disable fake backend for production paths; Patient OTP login is Phase 8 (not password) | No plaintext password compare; every role including future Patient/Account/Pharmacy authenticates through a protected path | Not Started
24 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.4 | SEC-02 | Secure password reset — time-limited reset links (stop plaintext email + fake thunk) | SEC-02.01 | DB: PasswordResetToken (UserId, TokenHash, ExpiresAt, UsedAt) | New | Security | §17 | Secure password reset | Time-limited reset links | Admin / Doctor / Reception web | Database | No | Yes | Yes | No | No | No | P0 | S | — | /forgot-password UI exists; thunk uses fake/Firebase; POST /users/ForgetPassword emails plaintext password | Tokenised reset (hash, TTL); email contains link only; ChangePassword for logged-in user | Reset email never contains the password; token expires; used token cannot be reused | Not Started
25 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.4 | SEC-02 | Secure password reset — time-limited reset links (stop plaintext email + fake thunk) | SEC-02.02 | API: ForgotPassword sends reset link; ResetPassword consumes token; stop emailing plaintext; ChangePassword for authenticated user | Existing Modification | Security | §17 | Secure password reset | Time-limited reset links | Admin / Doctor / Reception web | API | No | Yes | No | Yes | No | No | P0 | M | SEC-02.01 | /forgot-password UI exists; thunk uses fake/Firebase; POST /users/ForgetPassword emails plaintext password | Tokenised reset (hash, TTL); email contains link only; ChangePassword for logged-in user | Reset email never contains the password; token expires; used token cannot be reused | Not Started
26 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.4 | SEC-02 | Secure password reset — time-limited reset links (stop plaintext email + fake thunk) | SEC-02.03 | UI: replace slices/auth/forgetpwd fake/Firebase with real APIs; /reset-password/:token success/expiry states | Existing Improvement | Security | §17 | Secure password reset | Time-limited reset links | Admin / Doctor / Reception web | Web SPA | Yes | No | No | Yes | No | No | P0 | M | SEC-02.02 | /forgot-password UI exists; thunk uses fake/Firebase; POST /users/ForgetPassword emails plaintext password | Tokenised reset (hash, TTL); email contains link only; ChangePassword for logged-in user | Reset email never contains the password; token expires; used token cannot be reused | Not Started
27 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.4 | SEC-02 | Secure password reset — time-limited reset links (stop plaintext email + fake thunk) | SEC-02.04 | QA: expired token, reused token, unknown email (no user enumeration), logged-in change password | Regression | Security | §17 | Secure password reset | Time-limited reset links | Admin / Doctor / Reception web | QA | Yes | Yes | No | No | No | No | P0 | S | SEC-02.03 | /forgot-password UI exists; thunk uses fake/Firebase; POST /users/ForgetPassword emails plaintext password | Tokenised reset (hash, TTL); email contains link only; ChangePassword for logged-in user | Reset email never contains the password; token expires; used token cannot be reused | Not Started
28 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.5 | SEC-03 | Session control — proper sign-out across web and mobile | SEC-03.01 | API: POST /Account/Logout; persist UserLoginStatus; optional denylist until token expiry | Existing Improvement | Security | §17 | Session control | Proper sign-out across web and mobile | All | API | No | Yes | Yes | Yes | No | No | P0 | S | — | Client clears sessionStorage; no server logout / token revoke; UserLoginStatus unused | POST Logout persists login status; optional token denylist; mobile will call the same API in Phase 16/17 | After logout the JWT cannot call protected APIs; board session cleared (already on client) | Not Started
29 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.5 | SEC-03 | Session control — proper sign-out across web and mobile | SEC-03.02 | Web: Logout.js calls API then clears authUser + patient-board session (keep existing board clear) | Existing Improvement | Security | §17 | Session control | Proper sign-out across web and mobile | All | Web SPA | Yes | No | No | Yes | No | No | P0 | S | SEC-03.01 | Client clears sessionStorage; no server logout / token revoke; UserLoginStatus unused | POST Logout persists login status; optional token denylist; mobile will call the same API in Phase 16/17 | After logout the JWT cannot call protected APIs; board session cleared (already on client) | Not Started
30 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.5 | SEC-03 | Session control — proper sign-out across web and mobile | SEC-03.03 | Contract: mobile apps MUST use the same Logout endpoint (implemented in Phases 16–17) | New | Security | §17 | Session control | Proper sign-out across web and mobile | All | API contract | No | No | No | Yes | Yes | No | P0 | S | SEC-03.02 | Client clears sessionStorage; no server logout / token revoke; UserLoginStatus unused | POST Logout persists login status; optional token denylist; mobile will call the same API in Phase 16/17 | After logout the JWT cannot call protected APIs; board session cleared (already on client) | Not Started
31 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.5 | SEC-03 | Session control — proper sign-out across web and mobile | SEC-03.04 | QA: logout on one tab; expired session message; 401 interceptor | Regression | Security | §17 | Session control | Proper sign-out across web and mobile | All | QA | Yes | Yes | No | No | No | No | P0 | S | SEC-03.03 | Client clears sessionStorage; no server logout / token revoke; UserLoginStatus unused | POST Logout persists login status; optional token denylist; mobile will call the same API in Phase 16/17 | After logout the JWT cannot call protected APIs; board session cleared (already on client) | Not Started
32 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.6 | SEC-04 | Role-based access — each role sees only what it is permitted to see | SEC-04.01 | Backend: restore GetMenuByRole; add role attributes on new money and PII APIs | Existing Improvement | Security | §17 | Role-based access | Each role sees only what it is permitted to see | Admin / All web | API | No | Yes | No | Yes | No | No | P0 | M | — | RoleMaster + RoleDetail + MenuMaster exist; GetMenuByRole commented out on .NET 8; no per-route frontend ACL — any authenticated URL works | Re-enable GetMenuByRole; AuthProtected deny-by-default; [Authorize(Roles=)] on money/clinical APIs; Account cannot edit repertory; Admin cannot approve payouts | Unknown URL for a role returns 403/redirect; admin menus match DB permissions | Not Started
33 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.6 | SEC-04 | Role-based access — each role sees only what it is permitted to see | SEC-04.02 | Frontend: hide routes the role cannot view; keep Velzon demo routes out of production menus | Existing Improvement | Security | §17 | Role-based access | Each role sees only what it is permitted to see | Admin / All web | Web SPA | Yes | No | No | No | No | No | P0 | M | SEC-04.01 | RoleMaster + RoleDetail + MenuMaster exist; GetMenuByRole commented out on .NET 8; no per-route frontend ACL — any authenticated URL works | Re-enable GetMenuByRole; AuthProtected deny-by-default; [Authorize(Roles=)] on money/clinical APIs; Account cannot edit repertory; Admin cannot approve payouts | Unknown URL for a role returns 403/redirect; admin menus match DB permissions | Not Started
34 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.6 | SEC-04 | Role-based access — each role sees only what it is permitted to see | SEC-04.03 | Separation of duties seed: Account role controls money; Admin controls platform and clinical data — neither can perform the other’s role (PDF §8) | New | Security | §17 | Role-based access | Each role sees only what it is permitted to see | Admin / All web | Configuration | No | Yes | Yes | No | No | No | P0 | S | SEC-04.02 | RoleMaster + RoleDetail + MenuMaster exist; GetMenuByRole commented out on .NET 8; no per-route frontend ACL — any authenticated URL works | Re-enable GetMenuByRole; AuthProtected deny-by-default; [Authorize(Roles=)] on money/clinical APIs; Account cannot edit repertory; Admin cannot approve payouts | Unknown URL for a role returns 403/redirect; admin menus match DB permissions | Not Started |  | PDF: 'the Account department controls money. Admin controls the platform and clinical data.'
35 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.6 | SEC-04 | Role-based access — each role sees only what it is permitted to see | SEC-04.04 | QA: Reception cannot open repertory masters; Account cannot edit diagnosis; Doctor cannot see platform-wide ledger | Regression | Security | §17 | Role-based access | Each role sees only what it is permitted to see | Admin / All web | QA | Yes | Yes | No | No | No | No | P0 | S | SEC-04.03 | RoleMaster + RoleDetail + MenuMaster exist; GetMenuByRole commented out on .NET 8; no per-route frontend ACL — any authenticated URL works | Re-enable GetMenuByRole; AuthProtected deny-by-default; [Authorize(Roles=)] on money/clinical APIs; Account cannot edit repertory; Admin cannot approve payouts | Unknown URL for a role returns 403/redirect; admin menus match DB permissions | Not Started
36 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.7 | SEC-05 | Patient data protection — health records restricted to the treating doctor and the patient | SEC-05.01 | API: enforce DoctorId ownership on Patient, Appointment, Case, Rx, notes, labs, board backup | Existing Improvement | Security | §17 | Patient data protection | Health records restricted to the treating doctor and the patient | API | API | No | Yes | No | Yes | No | No | P0 | L | — | Many repertory APIs have [Authorize] commented; directory browsing enabled for /attachments and /Blogs; no patient-scoped ACL on case data | Every case/Rx/note/lab query filtered by treating DoctorId (or PatientId for patient token); disable directory browsing | Doctor A cannot read Doctor B’s patient board payload; unauthenticated attachment URLs fail | Not Started
37 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.7 | SEC-05 | Patient data protection — health records restricted to the treating doctor and the patient | SEC-05.02 | Disable directory browsing on /attachments and /Blogs; signed-URL or authorised download for documents | Existing Modification | Security | §17 | Patient data protection | Health records restricted to the treating doctor and the patient | API | API | No | Yes | No | No | No | No | P0 | S | SEC-05.01 | Many repertory APIs have [Authorize] commented; directory browsing enabled for /attachments and /Blogs; no patient-scoped ACL on case data | Every case/Rx/note/lab query filtered by treating DoctorId (or PatientId for patient token); disable directory browsing | Doctor A cannot read Doctor B’s patient board payload; unauthenticated attachment URLs fail | Not Started
38 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.7 | SEC-05 | Patient data protection — health records restricted to the treating doctor and the patient | SEC-05.03 | QA: IDOR tests (swap PatientAppId / CaseId in requests) | Regression | Security | §17 | Patient data protection | Health records restricted to the treating doctor and the patient | API | QA | No | Yes | No | Yes | No | No | P0 | M | SEC-05.02 | Many repertory APIs have [Authorize] commented; directory browsing enabled for /attachments and /Blogs; no patient-scoped ACL on case data | Every case/Rx/note/lab query filtered by treating DoctorId (or PatientId for patient token); disable directory browsing | Doctor A cannot read Doctor B’s patient board payload; unauthenticated attachment URLs fail | Not Started
39 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.8 | SEC-06 | Consent records infrastructure — every consent captured, stored and reviewable | SEC-06.01 | DB: ConsentRecord + ConsentType master (Privacy, Booking, TeleRecording, PharmacyShare, Marketing, Caregiver) | New | Security / Trust | §17 | Consent records | Every consent captured, stored and reviewable | Shared | Database | No | Yes | Yes | No | No | No | P0 | S | — | AudioCaseConsentLog exists for audio case taking only | ConsentRecord (PatientId, Type, Version, GrantedAt, WithdrawnAt, SourceSurface) covering privacy, booking, recording, pharmacy share, marketing | Any later feature that needs consent writes this table; withdrawal is queryable | Not Started
40 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.8 | SEC-06 | Consent records infrastructure — every consent captured, stored and reviewable | SEC-06.02 | API: Grant / Withdraw / List-mine / Admin-audit (no clinical content in the API response beyond type+time) | New | Security / Trust | §17 | Consent records | Every consent captured, stored and reviewable | Shared | API | No | Yes | No | Yes | No | No | P0 | M | SEC-06.01 | AudioCaseConsentLog exists for audio case taking only | ConsentRecord (PatientId, Type, Version, GrantedAt, WithdrawnAt, SourceSurface) covering privacy, booking, recording, pharmacy share, marketing | Any later feature that needs consent writes this table; withdrawal is queryable | Not Started
41 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.8 | SEC-06 | Consent records infrastructure — every consent captured, stored and reviewable | SEC-06.03 | Reuse AudioCaseConsentLog pattern; do not fork a second consent model for telemedicine (Phase 11 will write TeleRecording into ConsentRecord) | Existing Improvement | Security / Trust | §17 | Consent records | Every consent captured, stored and reviewable | Shared | API | No | Yes | No | No | No | No | P0 | S | SEC-06.02 | AudioCaseConsentLog exists for audio case taking only | ConsentRecord (PatientId, Type, Version, GrantedAt, WithdrawnAt, SourceSurface) covering privacy, booking, recording, pharmacy share, marketing | Any later feature that needs consent writes this table; withdrawal is queryable | Not Started
42 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.8 | SEC-06 | Consent records infrastructure — every consent captured, stored and reviewable | SEC-06.04 | QA: grant, withdraw, re-grant; audit log immutable | Regression | Security / Trust | §17 | Consent records | Every consent captured, stored and reviewable | Shared | QA | No | Yes | No | No | No | No | P0 | S | SEC-06.03 | AudioCaseConsentLog exists for audio case taking only | ConsentRecord (PatientId, Type, Version, GrantedAt, WithdrawnAt, SourceSurface) covering privacy, booking, recording, pharmacy share, marketing | Any later feature that needs consent writes this table; withdrawal is queryable | Not Started
43 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.9 | SEC-07 | OTP verification infrastructure — applied to sensitive actions including payouts and pharmacy acceptance | SEC-07.01 | DB: OtpChallenge, OtpAuditLog (Action, EntityType, EntityId, ToMasked, Success, At) | New | Security | §17 + §8 + §12 | OTP verification | Applied to sensitive actions including payouts and pharmacy acceptance | Shared | Database | No | Yes | Yes | No | No | No | P0 | S | — | No generic OTP control plane; patient OTP login does not exist | OtpChallenge + OtpAuditLog; Account/Admin can query who/when/entity/success without seeing card data | Payout and pharmacy-accept cannot complete without a successful OTP; failures are auditable | Not Started
44 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.9 | SEC-07 | OTP verification infrastructure — applied to sensitive actions including payouts and pharmacy acceptance | SEC-07.02 | API: RequestOtp / VerifyOtp (generic); rate-limit; lockout; SMS provider adapter stub until PRE-03 vendor is live | New | Security | §17 + §8 + §12 | OTP verification | Applied to sensitive actions including payouts and pharmacy acceptance | Shared | API | No | Yes | No | Yes | No | Yes | P0 | M | SEC-07.01 | No generic OTP control plane; patient OTP login does not exist | OtpChallenge + OtpAuditLog; Account/Admin can query who/when/entity/success without seeing card data | Payout and pharmacy-accept cannot complete without a successful OTP; failures are auditable | Not Started
45 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.9 | SEC-07 | OTP verification infrastructure — applied to sensitive actions including payouts and pharmacy acceptance | SEC-07.03 | GET /api/Otp/Audit for Account and Admin (masked destination) | New | Security | §17 + §8 + §12 | OTP verification | Applied to sensitive actions including payouts and pharmacy acceptance | Shared | API | No | Yes | No | Yes | No | No | P0 | S | SEC-07.02 | No generic OTP control plane; patient OTP login does not exist | OtpChallenge + OtpAuditLog; Account/Admin can query who/when/entity/success without seeing card data | Payout and pharmacy-accept cannot complete without a successful OTP; failures are auditable | Not Started
46 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.9 | SEC-07 | OTP verification infrastructure — applied to sensitive actions including payouts and pharmacy acceptance | SEC-07.04 | QA: replay OTP, expiry, max attempts, audit completeness | Regression | Security | §17 + §8 + §12 | OTP verification | Applied to sensitive actions including payouts and pharmacy acceptance | Shared | QA | No | Yes | No | No | No | No | P0 | S | SEC-07.03 | No generic OTP control plane; patient OTP login does not exist | OtpChallenge + OtpAuditLog; Account/Admin can query who/when/entity/success without seeing card data | Payout and pharmacy-accept cannot complete without a successful OTP; failures are auditable | Not Started
47 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.10 | SEC-08 | Complete audit trail — who did what and when across payments, prescriptions and approvals | SEC-08.01 | DB: AuditEvent (ActorUserId, Role, Action, Entity, OldJson, NewJson, At, CorrelationId) | New | Security | §17 + §9 | Complete audit trail | Who did what, and when, across payments, prescriptions and approvals / Every transaction traceable end to end by Homeocentrum | Shared | Database | No | Yes | Yes | No | No | No | P0 | S | — | No platform-wide audit; no AppointmentChangeLog; no payment webhook store | Append-only AuditEvent for money, eRx sign, credentialing, payout, pharmacy accept; payments get a dedicated trail in Phase 6 | Account can reconstruct any sensitive action without calling a doctor | Not Started
48 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.10 | SEC-08 | Complete audit trail — who did what and when across payments, prescriptions and approvals | SEC-08.02 | API middleware: write audit on mutating money/Rx/approval endpoints (start with a helper used by later phases) | New | Security | §17 + §9 | Complete audit trail | Who did what, and when, across payments, prescriptions and approvals / Every transaction traceable end to end by Homeocentrum | Shared | API | No | Yes | No | No | No | No | P0 | M | SEC-08.01 | No platform-wide audit; no AppointmentChangeLog; no payment webhook store | Append-only AuditEvent for money, eRx sign, credentialing, payout, pharmacy accept; payments get a dedicated trail in Phase 6 | Account can reconstruct any sensitive action without calling a doctor | Not Started
49 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.10 | SEC-08 | Complete audit trail — who did what and when across payments, prescriptions and approvals | SEC-08.03 | QA: sample sign-prescription / approve-payout (when those exist) produce audit rows | Regression | Security | §17 + §9 | Complete audit trail | Who did what, and when, across payments, prescriptions and approvals / Every transaction traceable end to end by Homeocentrum | Shared | QA | No | Yes | No | No | No | No | P2 | S | SEC-08.02 | No platform-wide audit; no AppointmentChangeLog; no payment webhook store | Append-only AuditEvent for money, eRx sign, credentialing, payout, pharmacy accept; payments get a dedicated trail in Phase 6 | Account can reconstruct any sensitive action without calling a doctor | Not Started
50 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.11 | SEC-09 | Secure documents — prescriptions, reports and uploads protected from unauthorised access | SEC-09.01 | DB: SecureDocument (OwnerType, OwnerId, BlobPath, Mime, Hash, CreatedBy) | New | Security | §17 | Secure documents | Prescriptions, reports and uploads protected from unauthorised access | Shared | Database | No | Yes | Yes | No | No | No | P1 | S | — | Attachments served with directory browsing; no signed URLs; no patient upload module | Authorised download; virus-scan hook; patient uploads in Phase 15 use this store | Guessable URL does not leak a prescription PDF | Not Started
51 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.11 | SEC-09 | Secure documents — prescriptions, reports and uploads protected from unauthorised access | SEC-09.02 | API: upload (multipart) + authorised GET; no public folder listing | New | Security | §17 | Secure documents | Prescriptions, reports and uploads protected from unauthorised access | Shared | API | No | Yes | No | Yes | No | No | P1 | M | SEC-09.01 | Attachments served with directory browsing; no signed URLs; no patient upload module | Authorised download; virus-scan hook; patient uploads in Phase 15 use this store | Guessable URL does not leak a prescription PDF | Not Started
52 | 0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 0.11 | SEC-09 | Secure documents — prescriptions, reports and uploads protected from unauthorised access | SEC-09.03 | QA: doctor of record can download; other doctor 403; anonymous 401 | Regression | Security | §17 | Secure documents | Prescriptions, reports and uploads protected from unauthorised access | Shared | QA | No | Yes | No | No | No | No | P1 | S | SEC-09.02 | Attachments served with directory browsing; no signed URLs; no patient upload module | Authorised download; virus-scan hook; patient uploads in Phase 15 use this store | Guessable URL does not leak a prescription PDF | Not Started
53 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.1 | ADM-R01 | Keep and harden Admin Repertory sections (do not rebuild) | ADM-R01.01 | Regression: list / add / edit / (import-export if present) for Repertory sections | Existing | Repertory | §7.1 | Repertory sections | Manage repertory sections | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | Admin Repertory section CRUD live (pages/Admin/Repertory) | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Repertory sections still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
54 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.1 | ADM-R01 | Keep and harden Admin Repertory sections (do not rebuild) | ADM-R01.02 | ACL: only Admin (and permitted roles) can mutate Repertory sections; Doctor is read-only consumer on Patient Board | Existing Improvement | Repertory | §7.1 | Repertory sections | Manage repertory sections | Admin Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | ADM-R01.01 | Admin Repertory section CRUD live (pages/Admin/Repertory) | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Repertory sections still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
55 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.1 | ADM-R01 | Keep and harden Admin Repertory sections (do not rebuild) | ADM-R01.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Repertory sections; do not silently switch | Existing | Repertory | §7.1 | Repertory sections | Manage repertory sections | Admin Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | ADM-R01.02 | Admin Repertory section CRUD live (pages/Admin/Repertory) | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Repertory sections still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
56 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.2 | ADM-R02 | Keep and harden Admin Subsection & rubric tree (do not rebuild) | ADM-R02.01 | Regression: list / add / edit / (import-export if present) for Subsection & rubric tree | Existing | Repertory | §7.1 | Subsection & rubric tree | Manage the full rubric hierarchy | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | Hierarchical subsection/rubric tree + Excel import/export live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Subsection & rubric tree still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
57 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.2 | ADM-R02 | Keep and harden Admin Subsection & rubric tree (do not rebuild) | ADM-R02.02 | ACL: only Admin (and permitted roles) can mutate Subsection & rubric tree; Doctor is read-only consumer on Patient Board | Existing Improvement | Repertory | §7.1 | Subsection & rubric tree | Manage the full rubric hierarchy | Admin Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | ADM-R02.01 | Hierarchical subsection/rubric tree + Excel import/export live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Subsection & rubric tree still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
58 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.2 | ADM-R02 | Keep and harden Admin Subsection & rubric tree (do not rebuild) | ADM-R02.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Subsection & rubric tree; do not silently switch | Existing | Repertory | §7.1 | Subsection & rubric tree | Manage the full rubric hierarchy | Admin Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | ADM-R02.02 | Hierarchical subsection/rubric tree + Excel import/export live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Subsection & rubric tree still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
59 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.3 | ADM-R03 | Keep and harden Admin Rubric–remedy mapping (do not rebuild) | ADM-R03.01 | Regression: list / add / edit / (import-export if present) for Rubric–remedy mapping | Existing | Repertory | §7.1 | Rubric–remedy mapping | Map remedies to rubrics with author and grade | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | Rubric-remedy mapping by author/grade live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Rubric–remedy mapping still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
60 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.3 | ADM-R03 | Keep and harden Admin Rubric–remedy mapping (do not rebuild) | ADM-R03.02 | ACL: only Admin (and permitted roles) can mutate Rubric–remedy mapping; Doctor is read-only consumer on Patient Board | Existing Improvement | Repertory | §7.1 | Rubric–remedy mapping | Map remedies to rubrics with author and grade | Admin Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | ADM-R03.01 | Rubric-remedy mapping by author/grade live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Rubric–remedy mapping still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
61 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.3 | ADM-R03 | Keep and harden Admin Rubric–remedy mapping (do not rebuild) | ADM-R03.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Rubric–remedy mapping; do not silently switch | Existing | Repertory | §7.1 | Rubric–remedy mapping | Map remedies to rubrics with author and grade | Admin Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | ADM-R03.02 | Rubric-remedy mapping by author/grade live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Rubric–remedy mapping still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
62 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.4 | ADM-R04 | Keep and harden Admin Remedy-linked rubrics (do not rebuild) | ADM-R04.01 | Regression: list / add / edit / (import-export if present) for Remedy-linked rubrics | Existing | Repertory | §7.1 | Remedy-linked rubrics | View all rubrics linked to a remedy | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | Remedial-rubrics viewer live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Remedy-linked rubrics still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
63 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.4 | ADM-R04 | Keep and harden Admin Remedy-linked rubrics (do not rebuild) | ADM-R04.02 | ACL: only Admin (and permitted roles) can mutate Remedy-linked rubrics; Doctor is read-only consumer on Patient Board | Existing Improvement | Repertory | §7.1 | Remedy-linked rubrics | View all rubrics linked to a remedy | Admin Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | ADM-R04.01 | Remedial-rubrics viewer live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Remedy-linked rubrics still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
64 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.4 | ADM-R04 | Keep and harden Admin Remedy-linked rubrics (do not rebuild) | ADM-R04.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Remedy-linked rubrics; do not silently switch | Existing | Repertory | §7.1 | Remedy-linked rubrics | View all rubrics linked to a remedy | Admin Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | ADM-R04.02 | Remedial-rubrics viewer live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Remedy-linked rubrics still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
65 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.5 | ADM-R05 | Keep and harden Admin Language master (do not rebuild) | ADM-R05.01 | Regression: list / add / edit / (import-export if present) for Language master | Existing | Repertory | §7.1 | Language master | Manage languages | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | Language master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Language master still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
66 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.5 | ADM-R05 | Keep and harden Admin Language master (do not rebuild) | ADM-R05.02 | ACL: only Admin (and permitted roles) can mutate Language master; Doctor is read-only consumer on Patient Board | Existing Improvement | Repertory | §7.1 | Language master | Manage languages | Admin Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | ADM-R05.01 | Language master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Language master still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
67 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.5 | ADM-R05 | Keep and harden Admin Language master (do not rebuild) | ADM-R05.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Language master; do not silently switch | Existing | Repertory | §7.1 | Language master | Manage languages | Admin Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | ADM-R05.02 | Language master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Language master still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
68 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.6 | ADM-R06 | Keep and harden Admin Body part master (do not rebuild) | ADM-R06.01 | Regression: list / add / edit / (import-export if present) for Body part master | Existing | Repertory | §7.1 | Body part master | Manage body parts | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | Body part master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Body part master still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
69 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.6 | ADM-R06 | Keep and harden Admin Body part master (do not rebuild) | ADM-R06.02 | ACL: only Admin (and permitted roles) can mutate Body part master; Doctor is read-only consumer on Patient Board | Existing Improvement | Repertory | §7.1 | Body part master | Manage body parts | Admin Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | ADM-R06.01 | Body part master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Body part master still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
70 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.6 | ADM-R06 | Keep and harden Admin Body part master (do not rebuild) | ADM-R06.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Body part master; do not silently switch | Existing | Repertory | §7.1 | Body part master | Manage body parts | Admin Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | ADM-R06.02 | Body part master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Body part master still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
71 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.7 | ADM-R07 | Keep and harden Admin Intensity master (do not rebuild) | ADM-R07.01 | Regression: list / add / edit / (import-export if present) for Intensity master | Existing | Repertory | §7.1 | Intensity master | Manage intensity levels | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | Intensity master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Intensity master still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
72 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.7 | ADM-R07 | Keep and harden Admin Intensity master (do not rebuild) | ADM-R07.02 | ACL: only Admin (and permitted roles) can mutate Intensity master; Doctor is read-only consumer on Patient Board | Existing Improvement | Repertory | §7.1 | Intensity master | Manage intensity levels | Admin Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | ADM-R07.01 | Intensity master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Intensity master still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
73 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.7 | ADM-R07 | Keep and harden Admin Intensity master (do not rebuild) | ADM-R07.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Intensity master; do not silently switch | Existing | Repertory | §7.1 | Intensity master | Manage intensity levels | Admin Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | ADM-R07.02 | Intensity master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Intensity master still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
74 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.8 | ADM-R08 | Keep and harden Admin Remedy master (do not rebuild) | ADM-R08.01 | Regression: list / add / edit / (import-export if present) for Remedy master | Existing | Repertory | §7.1 | Remedy master | Manage the remedy library | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | Remedy master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Remedy master still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
75 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.8 | ADM-R08 | Keep and harden Admin Remedy master (do not rebuild) | ADM-R08.02 | ACL: only Admin (and permitted roles) can mutate Remedy master; Doctor is read-only consumer on Patient Board | Existing Improvement | Repertory | §7.1 | Remedy master | Manage the remedy library | Admin Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | ADM-R08.01 | Remedy master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Remedy master still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
76 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.8 | ADM-R08 | Keep and harden Admin Remedy master (do not rebuild) | ADM-R08.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Remedy master; do not silently switch | Existing | Repertory | §7.1 | Remedy master | Manage the remedy library | Admin Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | ADM-R08.02 | Remedy master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Remedy master still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
77 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.9 | ADM-R09 | Keep and harden Admin Remedy grade master (do not rebuild) | ADM-R09.01 | Regression: list / add / edit / (import-export if present) for Remedy grade master | Existing | Repertory | §7.1 | Remedy grade master | Manage remedy grading | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | Remedy grade master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Remedy grade master still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
78 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.9 | ADM-R09 | Keep and harden Admin Remedy grade master (do not rebuild) | ADM-R09.02 | ACL: only Admin (and permitted roles) can mutate Remedy grade master; Doctor is read-only consumer on Patient Board | Existing Improvement | Repertory | §7.1 | Remedy grade master | Manage remedy grading | Admin Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | ADM-R09.01 | Remedy grade master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Remedy grade master still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
79 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.9 | ADM-R09 | Keep and harden Admin Remedy grade master (do not rebuild) | ADM-R09.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Remedy grade master; do not silently switch | Existing | Repertory | §7.1 | Remedy grade master | Manage remedy grading | Admin Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | ADM-R09.02 | Remedy grade master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Remedy grade master still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
80 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.10 | ADM-M01 | Keep and harden Admin Author master (do not rebuild) | ADM-M01.01 | Regression: list / add / edit / (import-export if present) for Author master | Existing | Materia Medica | §7.1 | Author master | Manage materia medica authors | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | Author master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Author master still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
81 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.10 | ADM-M01 | Keep and harden Admin Author master (do not rebuild) | ADM-M01.02 | ACL: only Admin (and permitted roles) can mutate Author master; Doctor is read-only consumer on Patient Board | Existing Improvement | Materia Medica | §7.1 | Author master | Manage materia medica authors | Admin Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | ADM-M01.01 | Author master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Author master still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
82 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.10 | ADM-M01 | Keep and harden Admin Author master (do not rebuild) | ADM-M01.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Author master; do not silently switch | Existing | Materia Medica | §7.1 | Author master | Manage materia medica authors | Admin Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | ADM-M01.02 | Author master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Author master still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
83 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.11 | ADM-M02 | Keep and harden Admin Materia medica master (do not rebuild) | ADM-M02.01 | Regression: list / add / edit / (import-export if present) for Materia medica master | Existing | Materia Medica | §7.1 | Materia medica master | Manage the materia medica library | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | MM master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Materia medica master still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
84 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.11 | ADM-M02 | Keep and harden Admin Materia medica master (do not rebuild) | ADM-M02.02 | ACL: only Admin (and permitted roles) can mutate Materia medica master; Doctor is read-only consumer on Patient Board | Existing Improvement | Materia Medica | §7.1 | Materia medica master | Manage the materia medica library | Admin Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | ADM-M02.01 | MM master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Materia medica master still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
85 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.11 | ADM-M02 | Keep and harden Admin Materia medica master (do not rebuild) | ADM-M02.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Materia medica master; do not silently switch | Existing | Materia Medica | §7.1 | Materia medica master | Manage the materia medica library | Admin Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | ADM-M02.02 | MM master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Materia medica master still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
86 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.12 | ADM-M03 | Keep and harden Admin Materia medica heads (do not rebuild) | ADM-M03.01 | Regression: list / add / edit / (import-export if present) for Materia medica heads | Existing | Materia Medica | §7.1 | Materia medica heads | Manage chapter headings | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | MM heads live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Materia medica heads still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
87 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.12 | ADM-M03 | Keep and harden Admin Materia medica heads (do not rebuild) | ADM-M03.02 | ACL: only Admin (and permitted roles) can mutate Materia medica heads; Doctor is read-only consumer on Patient Board | Existing Improvement | Materia Medica | §7.1 | Materia medica heads | Manage chapter headings | Admin Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | ADM-M03.01 | MM heads live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Materia medica heads still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
88 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.12 | ADM-M03 | Keep and harden Admin Materia medica heads (do not rebuild) | ADM-M03.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Materia medica heads; do not silently switch | Existing | Materia Medica | §7.1 | Materia medica heads | Manage chapter headings | Admin Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | ADM-M03.02 | MM heads live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Materia medica heads still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
89 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.13 | ADM-M04 | Keep and harden Admin Materia medica remedies (do not rebuild) | ADM-M04.01 | Regression: list / add / edit / (import-export if present) for Materia medica remedies | Existing | Materia Medica | §7.1 | Materia medica remedies | View remedy-wise materia medica | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | Remedy-wise MM viewer live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Materia medica remedies still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
90 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.13 | ADM-M04 | Keep and harden Admin Materia medica remedies (do not rebuild) | ADM-M04.02 | ACL: only Admin (and permitted roles) can mutate Materia medica remedies; Doctor is read-only consumer on Patient Board | Existing Improvement | Materia Medica | §7.1 | Materia medica remedies | View remedy-wise materia medica | Admin Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | ADM-M04.01 | Remedy-wise MM viewer live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Materia medica remedies still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
91 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.13 | ADM-M04 | Keep and harden Admin Materia medica remedies (do not rebuild) | ADM-M04.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Materia medica remedies; do not silently switch | Existing | Materia Medica | §7.1 | Materia medica remedies | View remedy-wise materia medica | Admin Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | ADM-M04.02 | Remedy-wise MM viewer live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Materia medica remedies still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
92 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.14 | ADM-D01 | Keep and harden Admin Diagnosis system (do not rebuild) | ADM-D01.01 | Regression: list / add / edit / (import-export if present) for Diagnosis system | Existing | Diagnosis | §7.1 | Diagnosis system | Manage diagnosis systems | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | Diagnosis system CRUD live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Diagnosis system still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
93 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.14 | ADM-D01 | Keep and harden Admin Diagnosis system (do not rebuild) | ADM-D01.02 | ACL: only Admin (and permitted roles) can mutate Diagnosis system; Doctor is read-only consumer on Patient Board | Existing Improvement | Diagnosis | §7.1 | Diagnosis system | Manage diagnosis systems | Admin Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | ADM-D01.01 | Diagnosis system CRUD live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Diagnosis system still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
94 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.14 | ADM-D01 | Keep and harden Admin Diagnosis system (do not rebuild) | ADM-D01.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Diagnosis system; do not silently switch | Existing | Diagnosis | §7.1 | Diagnosis system | Manage diagnosis systems | Admin Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | ADM-D01.02 | Diagnosis system CRUD live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Diagnosis system still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
95 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.15 | ADM-D02 | Keep and harden Admin Diagnosis therapeutics (do not rebuild) | ADM-D02.01 | Regression: list / add / edit / (import-export if present) for Diagnosis therapeutics | Existing | Diagnosis | §7.1 | Diagnosis therapeutics | Manage therapeutics | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | Therapeutics details live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Diagnosis therapeutics still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
96 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.15 | ADM-D02 | Keep and harden Admin Diagnosis therapeutics (do not rebuild) | ADM-D02.02 | ACL: only Admin (and permitted roles) can mutate Diagnosis therapeutics; Doctor is read-only consumer on Patient Board | Existing Improvement | Diagnosis | §7.1 | Diagnosis therapeutics | Manage therapeutics | Admin Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | ADM-D02.01 | Therapeutics details live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Diagnosis therapeutics still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
97 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.15 | ADM-D02 | Keep and harden Admin Diagnosis therapeutics (do not rebuild) | ADM-D02.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Diagnosis therapeutics; do not silently switch | Existing | Diagnosis | §7.1 | Diagnosis therapeutics | Manage therapeutics | Admin Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | ADM-D02.02 | Therapeutics details live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Diagnosis therapeutics still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
98 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.16 | ADM-D03 | Keep and harden Admin Diagnosis conditions (do not rebuild) | ADM-D03.01 | Regression: list / add / edit / (import-export if present) for Diagnosis conditions | Existing | Diagnosis | §7.1 | Diagnosis conditions | Manage conditions and linked rubrics | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | Conditions + keyword→rubric live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Diagnosis conditions still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
99 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.16 | ADM-D03 | Keep and harden Admin Diagnosis conditions (do not rebuild) | ADM-D03.02 | ACL: only Admin (and permitted roles) can mutate Diagnosis conditions; Doctor is read-only consumer on Patient Board | Existing Improvement | Diagnosis | §7.1 | Diagnosis conditions | Manage conditions and linked rubrics | Admin Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | ADM-D03.01 | Conditions + keyword→rubric live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Diagnosis conditions still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
100 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.16 | ADM-D03 | Keep and harden Admin Diagnosis conditions (do not rebuild) | ADM-D03.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Diagnosis conditions; do not silently switch | Existing | Diagnosis | §7.1 | Diagnosis conditions | Manage conditions and linked rubrics | Admin Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | ADM-D03.02 | Conditions + keyword→rubric live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Diagnosis conditions still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
101 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.17 | ADM-A01 | Keep and harden Admin Drug system (do not rebuild) | ADM-A01.01 | Regression: list / add / edit / (import-export if present) for Drug system | Existing | Adverse Effect | §7.1 | Drug system | Manage conventional drug systems | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | Drug system CRUD live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Drug system still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
102 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.17 | ADM-A01 | Keep and harden Admin Drug system (do not rebuild) | ADM-A01.02 | ACL: only Admin (and permitted roles) can mutate Drug system; Doctor is read-only consumer on Patient Board | Existing Improvement | Adverse Effect | §7.1 | Drug system | Manage conventional drug systems | Admin Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | ADM-A01.01 | Drug system CRUD live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Drug system still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
103 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.17 | ADM-A01 | Keep and harden Admin Drug system (do not rebuild) | ADM-A01.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Drug system; do not silently switch | Existing | Adverse Effect | §7.1 | Drug system | Manage conventional drug systems | Admin Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | ADM-A01.02 | Drug system CRUD live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Drug system still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
104 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.18 | ADM-A02 | Keep and harden Admin Drug group (do not rebuild) | ADM-A02.01 | Regression: list / add / edit / (import-export if present) for Drug group | Existing | Adverse Effect | §7.1 | Drug group | Manage drug groups | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | Drug group CRUD live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Drug group still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
105 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.18 | ADM-A02 | Keep and harden Admin Drug group (do not rebuild) | ADM-A02.02 | ACL: only Admin (and permitted roles) can mutate Drug group; Doctor is read-only consumer on Patient Board | Existing Improvement | Adverse Effect | §7.1 | Drug group | Manage drug groups | Admin Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | ADM-A02.01 | Drug group CRUD live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Drug group still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
106 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.18 | ADM-A02 | Keep and harden Admin Drug group (do not rebuild) | ADM-A02.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Drug group; do not silently switch | Existing | Adverse Effect | §7.1 | Drug group | Manage drug groups | Admin Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | ADM-A02.02 | Drug group CRUD live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Drug group still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
107 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.19 | ADM-A03 | Keep and harden Admin Allopathic drug & side effects (do not rebuild) | ADM-A03.01 | Regression: list / add / edit / (import-export if present) for Allopathic drug & side effects | Existing | Adverse Effect | §7.1 | Allopathic drug & side effects | Manage drugs with side effects and adverse reactions | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | Allopathic drug + serious/other/adverse live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Allopathic drug & side effects still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
108 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.19 | ADM-A03 | Keep and harden Admin Allopathic drug & side effects (do not rebuild) | ADM-A03.02 | ACL: only Admin (and permitted roles) can mutate Allopathic drug & side effects; Doctor is read-only consumer on Patient Board | Existing Improvement | Adverse Effect | §7.1 | Allopathic drug & side effects | Manage drugs with side effects and adverse reactions | Admin Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | ADM-A03.01 | Allopathic drug + serious/other/adverse live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Allopathic drug & side effects still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
109 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.19 | ADM-A03 | Keep and harden Admin Allopathic drug & side effects (do not rebuild) | ADM-A03.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Allopathic drug & side effects; do not silently switch | Existing | Adverse Effect | §7.1 | Allopathic drug & side effects | Manage drugs with side effects and adverse reactions | Admin Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | ADM-A03.02 | Allopathic drug + serious/other/adverse live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Allopathic drug & side effects still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
110 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.20 | ADM-Q01 | Keep and harden Admin Question section, group & sub-group (do not rebuild) | ADM-Q01.01 | Regression: list / add / edit / (import-export if present) for Question section, group & sub-group | Existing | Clinical Questions | §7.1 | Question section, group & sub-group | Manage the clinical questionnaire structure | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | Existance / question group / subgroup CRUD live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Question section, group & sub-group still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
111 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.20 | ADM-Q01 | Keep and harden Admin Question section, group & sub-group (do not rebuild) | ADM-Q01.02 | ACL: only Admin (and permitted roles) can mutate Question section, group & sub-group; Doctor is read-only consumer on Patient Board | Existing Improvement | Clinical Questions | §7.1 | Question section, group & sub-group | Manage the clinical questionnaire structure | Admin Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | ADM-Q01.01 | Existance / question group / subgroup CRUD live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Question section, group & sub-group still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
112 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.20 | ADM-Q01 | Keep and harden Admin Question section, group & sub-group (do not rebuild) | ADM-Q01.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Question section, group & sub-group; do not silently switch | Existing | Clinical Questions | §7.1 | Question section, group & sub-group | Manage the clinical questionnaire structure | Admin Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | ADM-Q01.02 | Existance / question group / subgroup CRUD live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Question section, group & sub-group still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
113 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.21 | ADM-Q02 | Keep and harden Admin Clinical question mapping (do not rebuild) | ADM-Q02.01 | Regression: list / add / edit / (import-export if present) for Clinical question mapping | Existing | Clinical Questions | §7.1 | Clinical question mapping | Map questions to body parts and rubrics | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | Clinical questions mapped to body parts and rubrics live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Clinical question mapping still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
114 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.21 | ADM-Q02 | Keep and harden Admin Clinical question mapping (do not rebuild) | ADM-Q02.02 | ACL: only Admin (and permitted roles) can mutate Clinical question mapping; Doctor is read-only consumer on Patient Board | Existing Improvement | Clinical Questions | §7.1 | Clinical question mapping | Map questions to body parts and rubrics | Admin Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | ADM-Q02.01 | Clinical questions mapped to body parts and rubrics live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Clinical question mapping still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
115 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.21 | ADM-Q02 | Keep and harden Admin Clinical question mapping (do not rebuild) | ADM-Q02.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for Clinical question mapping; do not silently switch | Existing | Clinical Questions | §7.1 | Clinical question mapping | Map questions to body parts and rubrics | Admin Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | ADM-Q02.02 | Clinical questions mapped to body parts and rubrics live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | Clinical question mapping still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
116 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.22 | ADM-3D1 | Keep and harden Admin 3D mesh key master (do not rebuild) | ADM-3D1.01 | Regression: list / add / edit / (import-export if present) for 3D mesh key master | Existing | 3D Body | §7.1 | 3D mesh key master | Manage 3D model references | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | Mesh key master on .NET 8 live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | 3D mesh key master still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
117 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.22 | ADM-3D1 | Keep and harden Admin 3D mesh key master (do not rebuild) | ADM-3D1.02 | ACL: only Admin (and permitted roles) can mutate 3D mesh key master; Doctor is read-only consumer on Patient Board | Existing Improvement | 3D Body | §7.1 | 3D mesh key master | Manage 3D model references | Admin Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | ADM-3D1.01 | Mesh key master on .NET 8 live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | 3D mesh key master still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
118 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.22 | ADM-3D1 | Keep and harden Admin 3D mesh key master (do not rebuild) | ADM-3D1.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for 3D mesh key master; do not silently switch | Existing | 3D Body | §7.1 | 3D mesh key master | Manage 3D model references | Admin Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | ADM-3D1.02 | Mesh key master on .NET 8 live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | 3D mesh key master still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
119 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.23 | ADM-3D2 | Keep and harden Admin 3D section master (do not rebuild) | ADM-3D2.01 | Regression: list / add / edit / (import-export if present) for 3D section master | Existing | 3D Body | §7.1 | 3D section master | Manage 3D body sections | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | 3D section master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | 3D section master still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
120 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.23 | ADM-3D2 | Keep and harden Admin 3D section master (do not rebuild) | ADM-3D2.02 | ACL: only Admin (and permitted roles) can mutate 3D section master; Doctor is read-only consumer on Patient Board | Existing Improvement | 3D Body | §7.1 | 3D section master | Manage 3D body sections | Admin Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | ADM-3D2.01 | 3D section master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | 3D section master still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
121 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.23 | ADM-3D2 | Keep and harden Admin 3D section master (do not rebuild) | ADM-3D2.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for 3D section master; do not silently switch | Existing | 3D Body | §7.1 | 3D section master | Manage 3D body sections | Admin Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | ADM-3D2.02 | 3D section master live | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | 3D section master still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
122 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.24 | ADM-3D3 | Keep and harden Admin 3D hotspots (do not rebuild) | ADM-3D3.01 | Regression: list / add / edit / (import-export if present) for 3D hotspots | Existing | 3D Body | §7.1 | 3D hotspots | Manage clickable points on the 3D model | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | Hotspot master live; doctor viewer consumes them | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | 3D hotspots still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
123 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.24 | ADM-3D3 | Keep and harden Admin 3D hotspots (do not rebuild) | ADM-3D3.02 | ACL: only Admin (and permitted roles) can mutate 3D hotspots; Doctor is read-only consumer on Patient Board | Existing Improvement | 3D Body | §7.1 | 3D hotspots | Manage clickable points on the 3D model | Admin Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | ADM-3D3.01 | Hotspot master live; doctor viewer consumes them | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | 3D hotspots still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
124 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.24 | ADM-3D3 | Keep and harden Admin 3D hotspots (do not rebuild) | ADM-3D3.03 | Dual-API: confirm UI still hits the correct host (classic vs .NET 8) for 3D hotspots; do not silently switch | Existing | 3D Body | §7.1 | 3D hotspots | Manage clickable points on the 3D model | Admin Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | ADM-3D3.02 | Hotspot master live; doctor viewer consumes them | Regression pack + ACL + dual-API hygiene; Excel import/export remains where it already works | 3D hotspots still works after Phase 0 ACL; unauthorised role cannot mutate | Not Started
125 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.25 | ADM-B01 | Business Management — Doctor qualifications (existing, used later by credentialing) | ADM-B01.01 | Regression: qualifications list/add/edit | Existing | Business Management | §7.2 | Doctor qualifications | Manage the qualification list | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | Qualifications CRUD on newer API live; used by RegisterDoctor | Keep; credentialing Phase 8 will reference QualificationId | Qualification list still drives doctor registration | Not Started
126 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.25 | ADM-B01 | Business Management — Doctor qualifications (existing, used later by credentialing) | ADM-B01.02 | ACL on qualification APIs | Existing Improvement | Business Management | §7.2 | Doctor qualifications | Manage the qualification list | Admin Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | ADM-B01.01 | Qualifications CRUD on newer API live; used by RegisterDoctor | Keep; credentialing Phase 8 will reference QualificationId | Qualification list still drives doctor registration | Not Started
127 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.25 | ADM-B01 | Business Management — Doctor qualifications (existing, used later by credentialing) | ADM-B01.03 | Confirm UI uses newer API (not classic) for qualifications | Existing | Business Management | §7.2 | Doctor qualifications | Manage the qualification list | Admin Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | ADM-B01.02 | Qualifications CRUD on newer API live; used by RegisterDoctor | Keep; credentialing Phase 8 will reference QualificationId | Qualification list still drives doctor registration | Not Started
128 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.26 | ADM-B02 | Business Management — Lab & imaging test catalog (existing, used by eRx lab orders) | ADM-B02.01 | Regression: lab catalog CRUD and doctor order pick-list | Existing | Business Management | §7.2 | Lab & imaging test catalog | Manage the test catalogue | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | Labs & imaging CRUD live; Patient Board orders from this catalogue | Keep; eRx Phase 10 continues to use the same catalogue | Doctor can still order a lab from the catalogue | Not Started
129 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.26 | ADM-B02 | Business Management — Lab & imaging test catalog (existing, used by eRx lab orders) | ADM-B02.02 | ACL on catalog mutate | Existing Improvement | Business Management | §7.2 | Lab & imaging test catalog | Manage the test catalogue | Admin Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | ADM-B02.01 | Labs & imaging CRUD live; Patient Board orders from this catalogue | Keep; eRx Phase 10 continues to use the same catalogue | Doctor can still order a lab from the catalogue | Not Started
130 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.26 | ADM-B02 | Business Management — Lab & imaging test catalog (existing, used by eRx lab orders) | ADM-B02.03 | Confirm classic PatientLab APIs still read this catalogue | Existing | Business Management | §7.2 | Lab & imaging test catalog | Manage the test catalogue | Admin Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | ADM-B02.02 | Labs & imaging CRUD live; Patient Board orders from this catalogue | Keep; eRx Phase 10 continues to use the same catalogue | Doctor can still order a lab from the catalogue | Not Started
131 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.27 | ADM-B03 | Business Management — Subscription packages (existing S1 SaaS; later tied to Account ledger) | ADM-B03.01 | Regression: package list/add/edit; doctor Widgets still reads packages | Existing | Business Management | §7.2 | Subscription packages | Manage doctor subscription plans | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | Package CRUD live; Razorpay buy/renew partial (no webhook) | Do not overload PackageEntryDetail for consult/medicine money; Phase 6 ports payment verification | Admin can still create/edit packages; doctor still sees plan flags | Not Started
132 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.27 | ADM-B03 | Business Management — Subscription packages (existing S1 SaaS; later tied to Account ledger) | ADM-B03.02 | ACL on package mutate | Existing Improvement | Business Management | §7.2 | Subscription packages | Manage doctor subscription plans | Admin Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | ADM-B03.01 | Package CRUD live; Razorpay buy/renew partial (no webhook) | Do not overload PackageEntryDetail for consult/medicine money; Phase 6 ports payment verification | Admin can still create/edit packages; doctor still sees plan flags | Not Started
133 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.27 | ADM-B03 | Business Management — Subscription packages (existing S1 SaaS; later tied to Account ledger) | ADM-B03.03 | Note in code: PackageEntryDetail is S1 only — never reuse for S2 consult or S5 medicine | Existing | Business Management | §7.2 | Subscription packages | Manage doctor subscription plans | Admin Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | ADM-B03.02 | Package CRUD live; Razorpay buy/renew partial (no webhook) | Do not overload PackageEntryDetail for consult/medicine money; Phase 6 ports payment verification | Admin can still create/edit packages; doctor still sees plan flags | Not Started
134 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.28 | ADM-B04 | Business Management — Roles & menu permissions (existing DB, runtime ACL leftover) | ADM-B04.01 | No schema change unless Account/Pharmacy/Patient roles need new MenuMaster rows — seed those menus | Existing Improvement | Business Management | §7.2 | Roles & menu permissions | Control exactly what each role can access | Admin Portal | Database | No | Yes | Yes | No | No | No | P1 | S | — | Role CRUD screens live; runtime GetMenuByRole commented; no frontend route ACL | This is the product surface for SEC-04; complete wiring here | Changing a role’s menu immediately hides those routes after refresh | Not Started
135 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.28 | ADM-B04 | Business Management — Roles & menu permissions (existing DB, runtime ACL leftover) | ADM-B04.02 | Restore GetMenuByRole on .NET 8; seed menus for Account and (later) Pharmacy | Existing Improvement | Business Management | §7.2 | Roles & menu permissions | Control exactly what each role can access | Admin Portal | API | No | Yes | Yes | Yes | No | No | P1 | M | ADM-B04.01 | Role CRUD screens live; runtime GetMenuByRole commented; no frontend route ACL | This is the product surface for SEC-04; complete wiring here | Changing a role’s menu immediately hides those routes after refresh | Not Started
136 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.28 | ADM-B04 | Business Management — Roles & menu permissions (existing DB, runtime ACL leftover) | ADM-B04.03 | Admin role pages remain; frontend consumes menu API instead of hard-coded LayoutMenuData for domain items | Existing Improvement | Business Management | §7.2 | Roles & menu permissions | Control exactly what each role can access | Admin Portal | Web SPA | Yes | No | No | Yes | No | No | P1 | M | ADM-B04.02 | Role CRUD screens live; runtime GetMenuByRole commented; no frontend route ACL | This is the product surface for SEC-04; complete wiring here | Changing a role’s menu immediately hides those routes after refresh | Not Started
137 | 1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 1.28 | ADM-B04 | Business Management — Roles & menu permissions (existing DB, runtime ACL leftover) | ADM-B04.04 | QA: edit role menu → user of that role no longer sees the item | Regression | Business Management | §7.2 | Roles & menu permissions | Control exactly what each role can access | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P1 | S | ADM-B04.03 | Role CRUD screens live; runtime GetMenuByRole commented; no frontend route ACL | This is the product surface for SEC-04; complete wiring here | Changing a role’s menu immediately hides those routes after refresh | Not Started
138 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.1 | CLN-01 | Clinical workspace — single screen for the entire consultation | CLN-01.01 | UI: Patient Board header shows appointment, visit type, consult mode placeholders (wired in Phases 4 and 6) | Existing Improvement | Patient Board | §5.3 | Clinical workspace | Single screen for the entire consultation | Doctor Web Portal | Web SPA | Yes | No | No | No | No | No | P1 | S | — | PatientBoard.js (~13.5k) is the workspace; ~90% — missing payment/tele/eRx header status | Keep one screen; add header chips for payment, tele session, signed eRx (chips light up as later phases land) | Doctor still opens one board per patient; new chips do not break tabs | Not Started
139 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.1 | CLN-01 | Clinical workspace — single screen for the entire consultation | CLN-01.02 | Do not split the board into multiple apps; mobile doctor app will NOT get case-taking (PDF §3) | Existing | Patient Board | §5.3 | Clinical workspace | Single screen for the entire consultation | Doctor Web Portal | Architecture | No | No | No | No | No | No | P1 | S | CLN-01.01 | PatientBoard.js (~13.5k) is the workspace; ~90% — missing payment/tele/eRx header status | Keep one screen; add header chips for payment, tele session, signed eRx (chips light up as later phases land) | Doctor still opens one board per patient; new chips do not break tabs | Not Started
140 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.1 | CLN-01 | Clinical workspace — single screen for the entire consultation | CLN-01.03 | Regression: open case from dashboard still remounts via PatientBoardRoute | Regression | Patient Board | §5.3 | Clinical workspace | Single screen for the entire consultation | Doctor Web Portal | QA | Yes | No | No | No | No | No | P1 | S | CLN-01.02 | PatientBoard.js (~13.5k) is the workspace; ~90% — missing payment/tele/eRx header status | Keep one screen; add header chips for payment, tele session, signed eRx (chips light up as later phases land) | Doctor still opens one board per patient; new chips do not break tabs | Not Started
141 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.2 | CLN-02 | Manual case taking — structured case taking (keep) | CLN-02.01 | Regression: create case, add rubrics via manual path, repertorize | Existing | Patient Board | §5.3 | Manual case taking | Structured case taking | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | Classic case-taking tabs live | Regression only; do not rebuild | Manual case taking still saves/restores | Not Started
142 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.2 | CLN-02 | Manual case taking — structured case taking (keep) | CLN-02.02 | ACL: only treating doctor (not Reception) can run full case taking | Existing Improvement | Patient Board | §5.3 | Manual case taking | Structured case taking | Doctor Web Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | CLN-02.01 | Classic case-taking tabs live | Regression only; do not rebuild | Manual case taking still saves/restores | Not Started
143 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.2 | CLN-02 | Manual case taking — structured case taking (keep) | CLN-02.03 | Confirm clipboard/repertorization APIs still on the correct host | Existing | Patient Board | §5.3 | Manual case taking | Structured case taking | Doctor Web Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | CLN-02.02 | Classic case-taking tabs live | Regression only; do not rebuild | Manual case taking still saves/restores | Not Started
144 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.3 | CLN-03 | Body parts & intensity selection (keep) | CLN-03.01 | Regression: body part → rubrics; intensity chip | Existing | Patient Board | §5.3 | Body parts & intensity selection | Select affected areas and severity | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | Body Parts tab + intensity chips live | Regression; intensity master from Phase 1 still drives chips | Selecting a body part + intensity still adds rubrics | Not Started
145 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.3 | CLN-03 | Body parts & intensity selection (keep) | CLN-03.02 | ACL: doctor-only | Existing Improvement | Patient Board | §5.3 | Body parts & intensity selection | Select affected areas and severity | Doctor Web Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | CLN-03.01 | Body Parts tab + intensity chips live | Regression; intensity master from Phase 1 still drives chips | Selecting a body part + intensity still adds rubrics | Not Started
146 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.3 | CLN-03 | Body parts & intensity selection (keep) | CLN-03.03 | API host unchanged | Existing | Patient Board | §5.3 | Body parts & intensity selection | Select affected areas and severity | Doctor Web Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | CLN-03.02 | Body Parts tab + intensity chips live | Regression; intensity master from Phase 1 still drives chips | Selecting a body part + intensity still adds rubrics | Not Started
147 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.4 | CLN-04 | Clinical questions — guided questions by section, group and sub-group (keep) | CLN-04.01 | Regression: full question drill-down | Existing | Patient Board | §5.3 | Clinical questions | Guided questions by section, group and sub-group | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | Questions tab loads Existance taxonomy live | Regression | Section → group → subgroup → keywords → rubrics still works | Not Started
148 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.4 | CLN-04 | Clinical questions — guided questions by section, group and sub-group (keep) | CLN-04.02 | ACL doctor-only | Existing Improvement | Patient Board | §5.3 | Clinical questions | Guided questions by section, group and sub-group | Doctor Web Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | CLN-04.01 | Questions tab loads Existance taxonomy live | Regression | Section → group → subgroup → keywords → rubrics still works | Not Started
149 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.4 | CLN-04 | Clinical questions — guided questions by section, group and sub-group (keep) | CLN-04.03 | API host unchanged | Existing | Patient Board | §5.3 | Clinical questions | Guided questions by section, group and sub-group | Doctor Web Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | CLN-04.02 | Questions tab loads Existance taxonomy live | Regression | Section → group → subgroup → keywords → rubrics still works | Not Started
150 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.5 | CLN-05 | Diagnosis, therapeutics & pattern search (keep) | CLN-05.01 | Regression: diagnosis search + therapeutics | Existing | Patient Board | §5.3 | Diagnosis, therapeutics & pattern search | Search diagnoses and linked therapeutics | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | Clinical Pattern tab live (13 keyword tabs + therapeutics) | Regression | Diagnosis search still returns linked rubrics and therapeutics | Not Started
151 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.5 | CLN-05 | Diagnosis, therapeutics & pattern search (keep) | CLN-05.02 | ACL doctor-only | Existing Improvement | Patient Board | §5.3 | Diagnosis, therapeutics & pattern search | Search diagnoses and linked therapeutics | Doctor Web Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | CLN-05.01 | Clinical Pattern tab live (13 keyword tabs + therapeutics) | Regression | Diagnosis search still returns linked rubrics and therapeutics | Not Started
152 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.5 | CLN-05 | Diagnosis, therapeutics & pattern search (keep) | CLN-05.03 | API host unchanged | Existing | Patient Board | §5.3 | Diagnosis, therapeutics & pattern search | Search diagnoses and linked therapeutics | Doctor Web Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | CLN-05.02 | Clinical Pattern tab live (13 keyword tabs + therapeutics) | Regression | Diagnosis search still returns linked rubrics and therapeutics | Not Started
153 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.6 | CLN-06 | Repertory rubric search & selection (keep) | CLN-06.01 | Regression: tree + search + add to clipboard | Existing | Patient Board | §5.3 | Repertory rubric search & selection | Search and select from the full repertory | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | Repertory tree + search live | Regression; small UX polish allowed but not a rewrite | Search still adds to clipboard | Not Started
154 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.6 | CLN-06 | Repertory rubric search & selection (keep) | CLN-06.02 | ACL doctor-only | Existing Improvement | Patient Board | §5.3 | Repertory rubric search & selection | Search and select from the full repertory | Doctor Web Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | CLN-06.01 | Repertory tree + search live | Regression; small UX polish allowed but not a rewrite | Search still adds to clipboard | Not Started
155 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.6 | CLN-06 | Repertory rubric search & selection (keep) | CLN-06.03 | Confirm subsection search host (newer vs classic) documented | Existing | Patient Board | §5.3 | Repertory rubric search & selection | Search and select from the full repertory | Doctor Web Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | CLN-06.02 | Repertory tree + search live | Regression; small UX polish allowed but not a rewrite | Search still adds to clipboard | Not Started
156 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.7 | CLN-07 | Manage selected rubrics — review, edit and remove (remaining ~10%) | CLN-07.01 | No new table — clipboard already persisted via board backup / repertorization payload | Existing Improvement | Patient Board | §5.3 | Manage selected rubrics | Review, edit and remove selected rubrics | Doctor Web Portal | Database | No | Yes | Yes | No | No | No | P1 | S | — | Clipboard exists; confirm-delete / intensity-edit incomplete | Confirm delete; edit intensity on selected rubric; no accidental wipe | Doctor can remove one rubric without losing the rest | Not Started
157 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.7 | CLN-07 | Manage selected rubrics — review, edit and remove (remaining ~10%) | CLN-07.02 | If intensity-on-clipboard is client-only, persist it on backup payload | Existing Improvement | Patient Board | §5.3 | Manage selected rubrics | Review, edit and remove selected rubrics | Doctor Web Portal | API | No | Yes | Yes | Yes | No | No | P1 | M | CLN-07.01 | Clipboard exists; confirm-delete / intensity-edit incomplete | Confirm delete; edit intensity on selected rubric; no accidental wipe | Doctor can remove one rubric without losing the rest | Not Started
158 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.7 | CLN-07 | Manage selected rubrics — review, edit and remove (remaining ~10%) | CLN-07.03 | Clipboard UX: confirm delete; intensity edit; count badge | Existing Improvement | Patient Board | §5.3 | Manage selected rubrics | Review, edit and remove selected rubrics | Doctor Web Portal | Web SPA | Yes | No | No | Yes | No | No | P1 | M | CLN-07.02 | Clipboard exists; confirm-delete / intensity-edit incomplete | Confirm delete; edit intensity on selected rubric; no accidental wipe | Doctor can remove one rubric without losing the rest | Not Started
159 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.7 | CLN-07 | Manage selected rubrics — review, edit and remove (remaining ~10%) | CLN-07.04 | QA: remove, undo-not-required, backup restore still has remaining rubrics | Regression | Patient Board | §5.3 | Manage selected rubrics | Review, edit and remove selected rubrics | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P1 | S | CLN-07.03 | Clipboard exists; confirm-delete / intensity-edit incomplete | Confirm delete; edit intensity on selected rubric; no accidental wipe | Doctor can remove one rubric without losing the rest | Not Started
160 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.8 | CLN-08 | Audio case taking — record and receive suggested rubrics (keep engine; do not rebuild) | CLN-08.01 | Regression: record, poll, approve/reject suggested rubrics | Existing | Audio AI | §5.3 | Audio case taking | Record the consultation and receive suggested rubrics automatically | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P1 | S | — | Whisper + rubric engines + CaseTaking UI live on .NET 8 | Keep; follow existing AUDIO_CASE_TAKING_* docs; accuracy is the next task | Record/upload still produces suggested rubrics for approve/reject | Not Started
161 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.8 | CLN-08 | Audio case taking — record and receive suggested rubrics (keep engine; do not rebuild) | CLN-08.02 | Consent: audio consent continues to write AudioCaseConsentLog (later also ConsentRecord) | Existing Improvement | Audio AI | §5.3 | Audio case taking | Record the consultation and receive suggested rubrics automatically | Doctor Web Portal | Security | Yes | Yes | No | Yes | No | No | P1 | S | CLN-08.01 | Whisper + rubric engines + CaseTaking UI live on .NET 8 | Keep; follow existing AUDIO_CASE_TAKING_* docs; accuracy is the next task | Record/upload still produces suggested rubrics for approve/reject | Not Started
162 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.8 | CLN-08 | Audio case taking — record and receive suggested rubrics (keep engine; do not rebuild) | CLN-08.03 | Confirm audio queue/worker still healthy | Existing | Audio AI | §5.3 | Audio case taking | Record the consultation and receive suggested rubrics automatically | Doctor Web Portal | API hygiene | No | Yes | No | Yes | No | No | P1 | S | CLN-08.02 | Whisper + rubric engines + CaseTaking UI live on .NET 8 | Keep; follow existing AUDIO_CASE_TAKING_* docs; accuracy is the next task | Record/upload still produces suggested rubrics for approve/reject | Not Started
163 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.9 | CLN-09 | Improved rubric accuracy — enhanced accuracy rules for audio-based rubric suggestions | CLN-09.01 | Follow AUDIO_CASE_TAKING_* docs: accuracy rules, aliases, metaphors, benchmark | Existing Improvement | Audio AI | §5.3 | Improved rubric accuracy | Enhanced accuracy rules for audio-based rubric suggestions | Doctor Web Portal + Admin intelligence | Backend | No | Yes | No | No | No | No | P1 | L | — | Engine + admin metaphors/aliases exist; accuracy rules still in progress (~50%) | Complete accuracy rules per AUDIO_CASE_TAKING_AI_ENGINE docs; metaphor/alias QA | Benchmark set meets agreed accuracy gate before calling this done | Not Started
164 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.9 | CLN-09 | Improved rubric accuracy — enhanced accuracy rules for audio-based rubric suggestions | CLN-09.02 | Admin: metaphor/alias approve-reject remaining UX | Existing Improvement | Audio AI | §5.3 | Improved rubric accuracy | Enhanced accuracy rules for audio-based rubric suggestions | Doctor Web Portal + Admin intelligence | Web SPA | Yes | No | No | Yes | No | No | P1 | M | CLN-09.01 | Engine + admin metaphors/aliases exist; accuracy rules still in progress (~50%) | Complete accuracy rules per AUDIO_CASE_TAKING_AI_ENGINE docs; metaphor/alias QA | Benchmark set meets agreed accuracy gate before calling this done | Not Started
165 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.9 | CLN-09 | Improved rubric accuracy — enhanced accuracy rules for audio-based rubric suggestions | CLN-09.03 | QA: golden transcripts → expected rubric IDs within tolerance | Regression | Audio AI | §5.3 | Improved rubric accuracy | Enhanced accuracy rules for audio-based rubric suggestions | Doctor Web Portal + Admin intelligence | QA | No | Yes | No | No | No | No | P1 | M | CLN-09.02 | Engine + admin metaphors/aliases exist; accuracy rules still in progress (~50%) | Complete accuracy rules per AUDIO_CASE_TAKING_AI_ENGINE docs; metaphor/alias QA | Benchmark set meets agreed accuracy gate before calling this done | Not Started
166 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.10 | CLN-10 | Materia medica reference during consultation (remaining ~10%) | CLN-10.01 | No schema change | Existing Improvement | Patient Board | §5.3 | Materia medica reference | Browse materia medica during the consultation | Doctor Web Portal | Database | No | Yes | Yes | No | No | No | P2 | S | — | MM tab + repertorize differential accordion ~90% | Faster head navigation during case; do not rebuild MM masters | Doctor can open a remedy MM without leaving the board | Not Started
167 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.10 | CLN-10 | Materia medica reference during consultation (remaining ~10%) | CLN-10.02 | Existing MM APIs — add a lightweight get-by-remedy if chatty | Existing Improvement | Patient Board | §5.3 | Materia medica reference | Browse materia medica during the consultation | Doctor Web Portal | API | No | Yes | Yes | Yes | No | No | P2 | M | CLN-10.01 | MM tab + repertorize differential accordion ~90% | Faster head navigation during case; do not rebuild MM masters | Doctor can open a remedy MM without leaving the board | Not Started
168 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.10 | CLN-10 | Materia medica reference during consultation (remaining ~10%) | CLN-10.03 | MM tab: faster head navigation / keep place in case | Existing Improvement | Patient Board | §5.3 | Materia medica reference | Browse materia medica during the consultation | Doctor Web Portal | Web SPA | Yes | No | No | Yes | No | No | P2 | M | CLN-10.02 | MM tab + repertorize differential accordion ~90% | Faster head navigation during case; do not rebuild MM masters | Doctor can open a remedy MM without leaving the board | Not Started
169 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.10 | CLN-10 | Materia medica reference during consultation (remaining ~10%) | CLN-10.04 | QA: open MM for a repertorized remedy | Regression | Patient Board | §5.3 | Materia medica reference | Browse materia medica during the consultation | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | CLN-10.03 | MM tab + repertorize differential accordion ~90% | Faster head navigation during case; do not rebuild MM masters | Doctor can open a remedy MM without leaving the board | Not Started
170 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.11 | CLN-11 | Allopathic drug side-effect lookup (keep) | CLN-11.01 | Regression: search drug → side effects | Existing | Patient Board | §5.3 | Allopathic drug side-effect lookup | Check side effects of conventional medicines | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | Adverse Effect tab live | Regression | Lookup still shows serious/other/adverse | Not Started
171 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.11 | CLN-11 | Allopathic drug side-effect lookup (keep) | CLN-11.02 | ACL doctor-only | Existing Improvement | Patient Board | §5.3 | Allopathic drug side-effect lookup | Check side effects of conventional medicines | Doctor Web Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | CLN-11.01 | Adverse Effect tab live | Regression | Lookup still shows serious/other/adverse | Not Started
172 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.11 | CLN-11 | Allopathic drug side-effect lookup (keep) | CLN-11.03 | API host unchanged | Existing | Patient Board | §5.3 | Allopathic drug side-effect lookup | Check side effects of conventional medicines | Doctor Web Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | CLN-11.02 | Adverse Effect tab live | Regression | Lookup still shows serious/other/adverse | Not Started
173 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.12 | CLN-12 | Repertorization & elimination (remaining ~10%) | CLN-12.01 | No schema change | Existing Improvement | Patient Board | §5.3 | Repertorization & elimination | Full repertorization with elimination | Doctor Web Portal | Database | No | Yes | Yes | No | No | No | P1 | S | — | Common/uncommon/elimination live ~90% | Stability polish; Center of Gravity is a NEW panel on the same rubrics (next task) | Elimination still ranks remedies from selected rubrics | Not Started
174 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.12 | CLN-12 | Repertorization & elimination (remaining ~10%) | CLN-12.02 | Keep existing repertorization APIs; fix any known scoring edge cases | Existing Improvement | Patient Board | §5.3 | Repertorization & elimination | Full repertorization with elimination | Doctor Web Portal | API | No | Yes | Yes | Yes | No | No | P1 | M | CLN-12.01 | Common/uncommon/elimination live ~90% | Stability polish; Center of Gravity is a NEW panel on the same rubrics (next task) | Elimination still ranks remedies from selected rubrics | Not Started
175 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.12 | CLN-12 | Repertorization & elimination (remaining ~10%) | CLN-12.03 | Repertorize tab stability; then COG sits beside it | Existing Improvement | Patient Board | §5.3 | Repertorization & elimination | Full repertorization with elimination | Doctor Web Portal | Web SPA | Yes | No | No | Yes | No | No | P1 | M | CLN-12.02 | Common/uncommon/elimination live ~90% | Stability polish; Center of Gravity is a NEW panel on the same rubrics (next task) | Elimination still ranks remedies from selected rubrics | Not Started
176 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.12 | CLN-12 | Repertorization & elimination (remaining ~10%) | CLN-12.04 | QA: known case → expected top remedies | Regression | Patient Board | §5.3 | Repertorization & elimination | Full repertorization with elimination | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P1 | S | CLN-12.03 | Common/uncommon/elimination live ~90% | Stability polish; Center of Gravity is a NEW panel on the same rubrics (next task) | Elimination still ranks remedies from selected rubrics | Not Started
177 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.13 | CLN-13 | Center of Gravity — new analysis identifying the central remedy of the case, with reasoning shown | CLN-13.01 | No mandatory new table (algorithm on selected rubrics); optional CogRun log for support | New | Repertorization | §5.3 | Center of Gravity | New analysis identifying the central remedy of the case, with reasoning shown | Doctor Web Portal | Database | No | Yes | Yes | No | No | No | P1 | S | — | Does not exist | POST /api/Repertorization/CenterOfGravity from selected rubric ids + intensities; UI panel with explainability | COG returns ranked central remedies plus contribution reasons the doctor can read | Not Started
178 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.13 | CLN-13 | Center of Gravity — new analysis identifying the central remedy of the case, with reasoning shown | CLN-13.02 | POST /api/Repertorization/CenterOfGravity — input rubric ids + intensities; output ranked remedies + reasons | New | Repertorization | §5.3 | Center of Gravity | New analysis identifying the central remedy of the case, with reasoning shown | Doctor Web Portal | API | No | Yes | Yes | Yes | No | No | P1 | M | CLN-13.01 | Does not exist | POST /api/Repertorization/CenterOfGravity from selected rubric ids + intensities; UI panel with explainability | COG returns ranked central remedies plus contribution reasons the doctor can read | Not Started
179 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.13 | CLN-13 | Center of Gravity — new analysis identifying the central remedy of the case, with reasoning shown | CLN-13.03 | Patient Board → Repertorize tab → Center of Gravity sub-panel (toggle vs classic elimination) | New | Repertorization | §5.3 | Center of Gravity | New analysis identifying the central remedy of the case, with reasoning shown | Doctor Web Portal | Web SPA | Yes | No | No | Yes | No | No | P1 | M | CLN-13.02 | Does not exist | POST /api/Repertorization/CenterOfGravity from selected rubric ids + intensities; UI panel with explainability | COG returns ranked central remedies plus contribution reasons the doctor can read | Not Started
180 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.13 | CLN-13 | Center of Gravity — new analysis identifying the central remedy of the case, with reasoning shown | CLN-13.04 | QA: same clipboard as classic repertorize; COG reasons cite contributing rubrics; empty clipboard → clear empty state | Regression | Repertorization | §5.3 | Center of Gravity | New analysis identifying the central remedy of the case, with reasoning shown | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P1 | S | CLN-13.03 | Does not exist | POST /api/Repertorization/CenterOfGravity from selected rubric ids + intensities; UI panel with explainability | COG returns ranked central remedies plus contribution reasons the doctor can read | Not Started
181 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.14 | CLN-14 | Lab orders & lab entries (keep; later also sit on eRx) | CLN-14.01 | Regression: order lab from catalogue; enter result | Existing | Patient Board | §5.3 + §11 | Lab orders & lab entries | Order tests and record results / Tests ordered alongside the prescription | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | Lab order + result entry on prescription modal live | Keep; when eRx splits notes from Rx, labs stay on the prescription/eRx side | Order + result still save against the appointment | Not Started
182 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.14 | CLN-14 | Lab orders & lab entries (keep; later also sit on eRx) | CLN-14.02 | ACL doctor-only | Existing Improvement | Patient Board | §5.3 + §11 | Lab orders & lab entries | Order tests and record results / Tests ordered alongside the prescription | Doctor Web Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | CLN-14.01 | Lab order + result entry on prescription modal live | Keep; when eRx splits notes from Rx, labs stay on the prescription/eRx side | Order + result still save against the appointment | Not Started
183 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.14 | CLN-14 | Lab orders & lab entries (keep; later also sit on eRx) | CLN-14.03 | API: classic PatientLab still authoritative until ported | Existing | Patient Board | §5.3 + §11 | Lab orders & lab entries | Order tests and record results / Tests ordered alongside the prescription | Doctor Web Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | CLN-14.02 | Lab order + result entry on prescription modal live | Keep; when eRx splits notes from Rx, labs stay on the prescription/eRx side | Order + result still save against the appointment | Not Started
184 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.15 | CLN-15 | Appointment history notes (keep; split from eRx in Phase 10) | CLN-15.01 | Regression: add/list notes on a visit | Existing | Patient Board | §5.3 | Appointment history notes | Notes recorded against each visit | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P1 | S | — | AppointmentHistoryNote APIs live (classic); currently mixed into Rx modal tabs | Keep save/get; Phase 10 moves UX outside Rx modal and adds NoteType / IsErxExcluded | Notes still save against PatientAppId | Not Started
185 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.15 | CLN-15 | Appointment history notes (keep; split from eRx in Phase 10) | CLN-15.02 | ACL doctor-only | Existing Improvement | Patient Board | §5.3 | Appointment history notes | Notes recorded against each visit | Doctor Web Portal | Security | Yes | Yes | No | Yes | No | No | P1 | S | CLN-15.01 | AppointmentHistoryNote APIs live (classic); currently mixed into Rx modal tabs | Keep save/get; Phase 10 moves UX outside Rx modal and adds NoteType / IsErxExcluded | Notes still save against PatientAppId | Not Started
186 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.15 | CLN-15 | Appointment history notes (keep; split from eRx in Phase 10) | CLN-15.03 | Do not dual-write; classic notes stay until Phase 10 extends them | Existing | Patient Board | §5.3 | Appointment history notes | Notes recorded against each visit | Doctor Web Portal | API hygiene | No | Yes | No | Yes | No | No | P1 | S | CLN-15.02 | AppointmentHistoryNote APIs live (classic); currently mixed into Rx modal tabs | Keep save/get; Phase 10 moves UX outside Rx modal and adds NoteType / IsErxExcluded | Notes still save against PatientAppId | Not Started
187 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.16 | CLN-16 | Complaints & case details — wire Patient Board to existing SaveComplaints / SaveCaseDetails (~20% today) | CLN-16.01 | Use existing tables — no new schema unless fields are missing vs PDF | Existing Improvement | Patient Board | §5.3 | Complaints & case details | Capture and store complaints and case details | Doctor Web Portal | Database | No | Yes | Yes | No | No | No | P1 | S | — | Classic SaveComplaints / SaveCaseDetails APIs exist; Patient Board does not call them | Call the existing APIs from the board; Reception case-paper (Phase 5) uses a subset | Complaints and case details persist and reload on the board | Not Started
188 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.16 | CLN-16 | Complaints & case details — wire Patient Board to existing SaveComplaints / SaveCaseDetails (~20% today) | CLN-16.02 | Keep classic SaveComplaints / SaveCaseDetails; add GET if missing | Existing Improvement | Patient Board | §5.3 | Complaints & case details | Capture and store complaints and case details | Doctor Web Portal | API | No | Yes | Yes | Yes | No | No | P1 | M | CLN-16.01 | Classic SaveComplaints / SaveCaseDetails APIs exist; Patient Board does not call them | Call the existing APIs from the board; Reception case-paper (Phase 5) uses a subset | Complaints and case details persist and reload on the board | Not Started
189 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.16 | CLN-16 | Complaints & case details — wire Patient Board to existing SaveComplaints / SaveCaseDetails (~20% today) | CLN-16.03 | Patient Board: complaints + case details form that actually POSTs | Existing Improvement | Patient Board | §5.3 | Complaints & case details | Capture and store complaints and case details | Doctor Web Portal | Web SPA | Yes | No | No | Yes | No | No | P1 | M | CLN-16.02 | Classic SaveComplaints / SaveCaseDetails APIs exist; Patient Board does not call them | Call the existing APIs from the board; Reception case-paper (Phase 5) uses a subset | Complaints and case details persist and reload on the board | Not Started
190 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.16 | CLN-16 | Complaints & case details — wire Patient Board to existing SaveComplaints / SaveCaseDetails (~20% today) | CLN-16.04 | QA: save, reload, second doctor cannot read | Regression | Patient Board | §5.3 | Complaints & case details | Capture and store complaints and case details | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P1 | S | CLN-16.03 | Classic SaveComplaints / SaveCaseDetails APIs exist; Patient Board does not call them | Call the existing APIs from the board; Reception case-paper (Phase 5) uses a subset | Complaints and case details persist and reload on the board | Not Started
191 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.17 | CLN-17 | Patient back history — complete history of visits, notes, prescriptions and payments | CLN-17.01 | No new table — compose from Appointment + notes + Rx + (later) ConsultPayment | Existing Improvement | Patient Board | §5.3 | Patient back history | Complete history of visits, notes, prescriptions and payments | Doctor Web Portal | Database | No | Yes | Yes | No | No | No | P1 | S | — | History panel ~70%; no payment line (payments do not exist yet) | Timeline: visits, notes, eRx, labs; payment row added when Phase 6 lands (placeholder now) | Doctor sees chronological visits with notes and Rx; payment appears after Phase 6 | Not Started
192 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.17 | CLN-17 | Patient back history — complete history of visits, notes, prescriptions and payments | CLN-17.02 | GET patient timeline DTO including payment status when column exists | Existing Improvement | Patient Board | §5.3 | Patient back history | Complete history of visits, notes, prescriptions and payments | Doctor Web Portal | API | No | Yes | Yes | Yes | No | No | P1 | M | CLN-17.01 | History panel ~70%; no payment line (payments do not exist yet) | Timeline: visits, notes, eRx, labs; payment row added when Phase 6 lands (placeholder now) | Doctor sees chronological visits with notes and Rx; payment appears after Phase 6 | Not Started
193 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.17 | CLN-17 | Patient back history — complete history of visits, notes, prescriptions and payments | CLN-17.03 | History panel: date-ordered visits; open past eRx; payment badge placeholder | Existing Improvement | Patient Board | §5.3 | Patient back history | Complete history of visits, notes, prescriptions and payments | Doctor Web Portal | Web SPA | Yes | No | No | Yes | No | No | P1 | M | CLN-17.02 | History panel ~70%; no payment line (payments do not exist yet) | Timeline: visits, notes, eRx, labs; payment row added when Phase 6 lands (placeholder now) | Doctor sees chronological visits with notes and Rx; payment appears after Phase 6 | Not Started
194 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.17 | CLN-17 | Patient back history — complete history of visits, notes, prescriptions and payments | CLN-17.04 | QA: multi-visit patient; empty new patient | Regression | Patient Board | §5.3 | Patient back history | Complete history of visits, notes, prescriptions and payments | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P1 | S | CLN-17.03 | History panel ~70%; no payment line (payments do not exist yet) | Timeline: visits, notes, eRx, labs; payment row added when Phase 6 lands (placeholder now) | Doctor sees chronological visits with notes and Rx; payment appears after Phase 6 | Not Started
195 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.18 | CLN-18 | Export case data — download the full case in Excel or PDF | CLN-18.01 | Reuse ExportCasesToExcel; add PDF generation of the clinical case (doctor copy, includes notes) | Existing Improvement | Patient Board | §5.3 | Export case data | Download the full case in Excel or PDF | Doctor Web Portal | API | No | Yes | No | Yes | No | No | P1 | M | — | Newer ExportCasesToExcel exists; no Patient Board export UI; no PDF | Toolbar Excel + PDF using existing Excel API + new PDF renderer; exclude private notes from patient-facing PDF (eRx print is Phase 10) | Doctor downloads Excel and PDF of the case they own | Not Started
196 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.18 | CLN-18 | Export case data — download the full case in Excel or PDF | CLN-18.02 | Patient Board toolbar: Export Excel / Export PDF | New | Patient Board | §5.3 | Export case data | Download the full case in Excel or PDF | Doctor Web Portal | Web SPA | Yes | No | No | Yes | No | No | P1 | S | CLN-18.01 | Newer ExportCasesToExcel exists; no Patient Board export UI; no PDF | Toolbar Excel + PDF using existing Excel API + new PDF renderer; exclude private notes from patient-facing PDF (eRx print is Phase 10) | Doctor downloads Excel and PDF of the case they own | Not Started
197 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.18 | CLN-18 | Export case data — download the full case in Excel or PDF | CLN-18.03 | QA: export matches on-screen rubrics + Rx; unauthorised doctor 403 | Regression | Patient Board | §5.3 | Export case data | Download the full case in Excel or PDF | Doctor Web Portal | QA | Yes | Yes | No | No | No | No | P1 | S | CLN-18.02 | Newer ExportCasesToExcel exists; no Patient Board export UI; no PDF | Toolbar Excel + PDF using existing Excel API + new PDF renderer; exclude private notes from patient-facing PDF (eRx print is Phase 10) | Doctor downloads Excel and PDF of the case they own | Not Started
198 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.19 | CLN-19 | Session restore — continue exactly where the doctor left off, across multiple patients (keep) | CLN-19.01 | Regression: backup, restore, 5-session stack | Existing | Patient Board | §5.3 | Session restore | Continue exactly where the doctor left off, across multiple patients | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | Up to 5 in-memory sessions + DoctorPatientBoardBackup live | Regression; header stack remains | Kill browser, login, restore last work | Not Started
199 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.19 | CLN-19 | Session restore — continue exactly where the doctor left off, across multiple patients (keep) | CLN-19.02 | ACL: backup scoped to DoctorId | Existing Improvement | Patient Board | §5.3 | Session restore | Continue exactly where the doctor left off, across multiple patients | Doctor Web Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | CLN-19.01 | Up to 5 in-memory sessions + DoctorPatientBoardBackup live | Regression; header stack remains | Kill browser, login, restore last work | Not Started
200 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.19 | CLN-19 | Session restore — continue exactly where the doctor left off, across multiple patients (keep) | CLN-19.03 | API: PatientBoardBackup on .NET 8 unchanged | Existing | Patient Board | §5.3 | Session restore | Continue exactly where the doctor left off, across multiple patients | Doctor Web Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | CLN-19.02 | Up to 5 in-memory sessions + DoctorPatientBoardBackup live | Regression; header stack remains | Kill browser, login, restore last work | Not Started
201 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.20 | CLN-20 | 3D anatomy viewer — interactive 3D body model linked to rubric search (remaining ~50%) | CLN-20.01 | No new tables — Mesh/Section/Hotspot masters already exist | Existing Improvement | Anatomy | §5.3 | 3D anatomy viewer | Interactive 3D body model linked to rubric search | Doctor Web Portal | Database | No | Yes | Yes | No | No | No | P2 | S | — | three.js viewer + hotspot→search live; incomplete mesh coverage / UX | Complete GLB/hotspot coverage; mobile fallback later; admin 3D masters already in Phase 1 | Every admin hotspot on the shipped models opens the correct rubric search | Not Started
202 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.20 | CLN-20 | 3D anatomy viewer — interactive 3D body model linked to rubric search (remaining ~50%) | CLN-20.02 | Fix hotspot mapping gaps on newer threeDBodyPart APIs | Existing Improvement | Anatomy | §5.3 | 3D anatomy viewer | Interactive 3D body model linked to rubric search | Doctor Web Portal | API | No | Yes | Yes | Yes | No | No | P2 | M | CLN-20.01 | three.js viewer + hotspot→search live; incomplete mesh coverage / UX | Complete GLB/hotspot coverage; mobile fallback later; admin 3D masters already in Phase 1 | Every admin hotspot on the shipped models opens the correct rubric search | Not Started
203 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.20 | CLN-20 | 3D anatomy viewer — interactive 3D body model linked to rubric search (remaining ~50%) | CLN-20.03 | Viewer UX: incomplete regions, loading, fallback message | Existing Improvement | Anatomy | §5.3 | 3D anatomy viewer | Interactive 3D body model linked to rubric search | Doctor Web Portal | Web SPA | Yes | No | No | Yes | No | No | P2 | M | CLN-20.02 | three.js viewer + hotspot→search live; incomplete mesh coverage / UX | Complete GLB/hotspot coverage; mobile fallback later; admin 3D masters already in Phase 1 | Every admin hotspot on the shipped models opens the correct rubric search | Not Started
204 | 2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 2.20 | CLN-20 | 3D anatomy viewer — interactive 3D body model linked to rubric search (remaining ~50%) | CLN-20.04 | QA: click hotspot → subsection search results | Regression | Anatomy | §5.3 | 3D anatomy viewer | Interactive 3D body model linked to rubric search | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | CLN-20.03 | three.js viewer + hotspot→search live; incomplete mesh coverage / UX | Complete GLB/hotspot coverage; mobile fallback later; admin 3D masters already in Phase 1 | Every admin hotspot on the shipped models opens the correct rubric search | Not Started
205 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.1 | DOC-01 | Doctor home dashboard — complete overview of the working day (remaining ~30%) | DOC-01.01 | No new dashboard table | Existing Improvement | Doctor Dashboard | §5.1 | Doctor home dashboard | Complete overview of the working day | Doctor Web Portal | Database | No | Yes | Yes | No | No | No | P1 | S | — | Widgets + BestSellingProducts ~70%; missing online toggle, tele queue, payment badges, follow-up due | Extend, do not replace; later phases light up tele/payment chips | Doctor sees today’s buckets plus placeholders for tele/payment that become live in Phases 6 and 11 | Not Started
206 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.1 | DOC-01 | Doctor home dashboard — complete overview of the working day (remaining ~30%) | DOC-01.02 | Extend dashboard DTOs with paymentStatus / tele flags when columns exist (nullable until Phase 6/11) | Existing Improvement | Doctor Dashboard | §5.1 | Doctor home dashboard | Complete overview of the working day | Doctor Web Portal | API | No | Yes | Yes | Yes | No | No | P1 | M | DOC-01.01 | Widgets + BestSellingProducts ~70%; missing online toggle, tele queue, payment badges, follow-up due | Extend, do not replace; later phases light up tele/payment chips | Doctor sees today’s buckets plus placeholders for tele/payment that become live in Phases 6 and 11 | Not Started
207 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.1 | DOC-01 | Doctor home dashboard — complete overview of the working day (remaining ~30%) | DOC-01.03 | Dashboard chrome: keep counts; add slots for Online toggle, tele queue, unpaid badge | Existing Improvement | Doctor Dashboard | §5.1 | Doctor home dashboard | Complete overview of the working day | Doctor Web Portal | Web SPA | Yes | No | No | Yes | No | No | P1 | M | DOC-01.02 | Widgets + BestSellingProducts ~70%; missing online toggle, tele queue, payment badges, follow-up due | Extend, do not replace; later phases light up tele/payment chips | Doctor sees today’s buckets plus placeholders for tele/payment that become live in Phases 6 and 11 | Not Started
208 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.1 | DOC-01 | Doctor home dashboard — complete overview of the working day (remaining ~30%) | DOC-01.04 | QA: existing buckets still populate; reception still shares layout until Phase 5 reception chrome | Regression | Doctor Dashboard | §5.1 | Doctor home dashboard | Complete overview of the working day | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P1 | S | DOC-01.03 | Widgets + BestSellingProducts ~70%; missing online toggle, tele queue, payment badges, follow-up due | Extend, do not replace; later phases light up tele/payment chips | Doctor sees today’s buckets plus placeholders for tele/payment that become live in Phases 6 and 11 | Not Started
209 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.2 | DOC-02 | Patient counts & waiting list — live counts by status with quick actions (keep; extend paid/unpaid) | DOC-02.01 | Regression: each bucket count and click-through | Existing | Doctor Dashboard | §5.1 | Patient counts & waiting list | Live counts by status with quick actions | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P1 | S | — | Status buckets WAITING, WALK-IN, NOT ARRIVED, E-CONSULT, REMAINING, COMPLETED live | Keep; add CANCELLED in Phase 4; paid/unpaid badge in Phase 6 | Counts still match appointment list | Not Started
210 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.2 | DOC-02 | Patient counts & waiting list — live counts by status with quick actions (keep; extend paid/unpaid) | DOC-02.02 | Reception sharing this view is OK until Phase 5 splits chrome | Existing Improvement | Doctor Dashboard | §5.1 | Patient counts & waiting list | Live counts by status with quick actions | Doctor Web Portal | Security | Yes | Yes | No | Yes | No | No | P1 | S | DOC-02.01 | Status buckets WAITING, WALK-IN, NOT ARRIVED, E-CONSULT, REMAINING, COMPLETED live | Keep; add CANCELLED in Phase 4; paid/unpaid badge in Phase 6 | Counts still match appointment list | Not Started
211 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.2 | DOC-02 | Patient counts & waiting list — live counts by status with quick actions (keep; extend paid/unpaid) | DOC-02.03 | API: existing dashboard count endpoints | Existing | Doctor Dashboard | §5.1 | Patient counts & waiting list | Live counts by status with quick actions | Doctor Web Portal | API hygiene | No | Yes | No | Yes | No | No | P1 | S | DOC-02.02 | Status buckets WAITING, WALK-IN, NOT ARRIVED, E-CONSULT, REMAINING, COMPLETED live | Keep; add CANCELLED in Phase 4; paid/unpaid badge in Phase 6 | Counts still match appointment list | Not Started
212 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.3 | DOC-03 | Patient search, list & open case (remaining ~10%) | DOC-03.01 | Use existing Patient + Appointment — add DTO fields | Existing Improvement | Doctor Dashboard | §5.1 | Patient search, list & open case | Find any patient and open their case instantly | Doctor Web Portal | Database | No | Yes | Yes | No | No | No | P1 | S | — | Search/list/open ~90%; missing last visit, unpaid, family filters | Add last-visit column; unpaid/family after those modules exist | Search still opens Patient Board; last visit visible | Not Started
213 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.3 | DOC-03 | Patient search, list & open case (remaining ~10%) | DOC-03.02 | Search DTO includes lastVisitAt | Existing Improvement | Doctor Dashboard | §5.1 | Patient search, list & open case | Find any patient and open their case instantly | Doctor Web Portal | API | No | Yes | Yes | Yes | No | No | P1 | M | DOC-03.01 | Search/list/open ~90%; missing last visit, unpaid, family filters | Add last-visit column; unpaid/family after those modules exist | Search still opens Patient Board; last visit visible | Not Started
214 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.3 | DOC-03 | Patient search, list & open case (remaining ~10%) | DOC-03.03 | List columns: last visit; later payment/family | Existing Improvement | Doctor Dashboard | §5.1 | Patient search, list & open case | Find any patient and open their case instantly | Doctor Web Portal | Web SPA | Yes | No | No | Yes | No | No | P1 | M | DOC-03.02 | Search/list/open ~90%; missing last visit, unpaid, family filters | Add last-visit column; unpaid/family after those modules exist | Search still opens Patient Board; last visit visible | Not Started
215 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.3 | DOC-03 | Patient search, list & open case (remaining ~10%) | DOC-03.04 | QA: search by name/mobile; open case | Regression | Doctor Dashboard | §5.1 | Patient search, list & open case | Find any patient and open their case instantly | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P1 | S | DOC-03.03 | Search/list/open ~90%; missing last visit, unpaid, family filters | Add last-visit column; unpaid/family after those modules exist | Search still opens Patient Board; last visit visible | Not Started
216 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.4 | DOC-04 | Add new patient — register a patient in seconds (keep) | DOC-04.01 | Regression: add patient validation and save | Existing | Patients | §5.1 | Add new patient | Register a patient in seconds | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P1 | S | — | Create patient live | Regression; public self-registration is a different Patient identity in Phase 9 | Doctor can still create a clinic patient | Not Started
217 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.4 | DOC-04 | Add new patient — register a patient in seconds (keep) | DOC-04.02 | ACL: doctor/reception of that clinic only | Existing Improvement | Patients | §5.1 | Add new patient | Register a patient in seconds | Doctor Web Portal | Security | Yes | Yes | No | Yes | No | No | P1 | S | DOC-04.01 | Create patient live | Regression; public self-registration is a different Patient identity in Phase 9 | Doctor can still create a clinic patient | Not Started
218 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.4 | DOC-04 | Add new patient — register a patient in seconds (keep) | DOC-04.03 | API unchanged | Existing | Patients | §5.1 | Add new patient | Register a patient in seconds | Doctor Web Portal | API hygiene | No | Yes | No | Yes | No | No | P1 | S | DOC-04.02 | Create patient live | Regression; public self-registration is a different Patient identity in Phase 9 | Doctor can still create a clinic patient | Not Started
219 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.5 | DOC-05 | Import patients — bring existing patient records in bulk (keep) | DOC-05.01 | Regression: template + import + error rows | Existing | Patients | §5.1 | Import patients | Bring existing patient records in bulk | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | Import live | Regression | Import still creates patients for this doctor | Not Started
220 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.5 | DOC-05 | Import patients — bring existing patient records in bulk (keep) | DOC-05.02 | ACL doctor-only (or reception if already allowed) | Existing Improvement | Patients | §5.1 | Import patients | Bring existing patient records in bulk | Doctor Web Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | DOC-05.01 | Import live | Regression | Import still creates patients for this doctor | Not Started
221 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.5 | DOC-05 | Import patients — bring existing patient records in bulk (keep) | DOC-05.03 | API unchanged | Existing | Patients | §5.1 | Import patients | Bring existing patient records in bulk | Doctor Web Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | DOC-05.02 | Import live | Regression | Import still creates patients for this doctor | Not Started
222 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.6 | DOC-06 | Export patients — download patient data in Excel, CSV or PDF (keep) | DOC-06.01 | Audit current export formats; add PDF if only Excel/CSV exist today | Existing Improvement | Patients | §5.1 | Export patients | Download patient data in Excel, CSV or PDF | Doctor Web Portal | API | No | Yes | No | Yes | No | No | P2 | S | — | Export live (confirm PDF vs Excel/CSV in QA) | If PDF is missing, add it as Existing Improvement; do not skip the PDF wording in the PDF | Excel, CSV and PDF each download this doctor’s patients only | Not Started
223 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.6 | DOC-06 | Export patients — download patient data in Excel, CSV or PDF (keep) | DOC-06.02 | UI: Excel / CSV / PDF actions labelled as in the delivery document | Existing Improvement | Patients | §5.1 | Export patients | Download patient data in Excel, CSV or PDF | Doctor Web Portal | Web SPA | Yes | No | No | No | No | No | P2 | S | DOC-06.01 | Export live (confirm PDF vs Excel/CSV in QA) | If PDF is missing, add it as Existing Improvement; do not skip the PDF wording in the PDF | Excel, CSV and PDF each download this doctor’s patients only | Not Started
224 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.6 | DOC-06 | Export patients — download patient data in Excel, CSV or PDF (keep) | DOC-06.03 | QA: another doctor cannot export this list | Regression | Patients | §5.1 | Export patients | Download patient data in Excel, CSV or PDF | Doctor Web Portal | QA | Yes | Yes | No | No | No | No | P2 | S | DOC-06.02 | Export live (confirm PDF vs Excel/CSV in QA) | If PDF is missing, add it as Existing Improvement; do not skip the PDF wording in the PDF | Excel, CSV and PDF each download this doctor’s patients only | Not Started
225 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.7 | DOC-07 | Recent activity panel (keep) | DOC-07.01 | Regression: activity loads | Existing | Doctor Dashboard | §5.1 | Recent activity panel | Everything that happened recently, at a glance | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | Recent activity live | Regression; later include payment/tele events when those exist | Panel still lists recent actions | Not Started
226 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.7 | DOC-07 | Recent activity panel (keep) | DOC-07.02 | ACL scoped to doctor | Existing Improvement | Doctor Dashboard | §5.1 | Recent activity panel | Everything that happened recently, at a glance | Doctor Web Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | DOC-07.01 | Recent activity live | Regression; later include payment/tele events when those exist | Panel still lists recent actions | Not Started
227 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.7 | DOC-07 | Recent activity panel (keep) | DOC-07.03 | API unchanged | Existing | Doctor Dashboard | §5.1 | Recent activity panel | Everything that happened recently, at a glance | Doctor Web Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | DOC-07.02 | Recent activity live | Regression; later include payment/tele events when those exist | Panel still lists recent actions | Not Started
228 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.8 | DOC-08 | Patient statistics charts (keep; foundation for clinic performance in Phase 18) | DOC-08.01 | Regression: stats charts date range | Existing | Doctor Dashboard | §5.1 | Patient statistics charts | Visual practice statistics | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | GetPatientStats / GetPatientStatsCharts + ApexCharts live | Keep; clinic performance report extends this in Phase 18 | Charts still render for the doctor | Not Started
229 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.8 | DOC-08 | Patient statistics charts (keep; foundation for clinic performance in Phase 18) | DOC-08.02 | ACL doctor-only | Existing Improvement | Doctor Dashboard | §5.1 | Patient statistics charts | Visual practice statistics | Doctor Web Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | DOC-08.01 | GetPatientStats / GetPatientStatsCharts + ApexCharts live | Keep; clinic performance report extends this in Phase 18 | Charts still render for the doctor | Not Started
230 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.8 | DOC-08 | Patient statistics charts (keep; foundation for clinic performance in Phase 18) | DOC-08.03 | API unchanged | Existing | Doctor Dashboard | §5.1 | Patient statistics charts | Visual practice statistics | Doctor Web Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | DOC-08.02 | GetPatientStats / GetPatientStatsCharts + ApexCharts live | Keep; clinic performance report extends this in Phase 18 | Charts still render for the doctor | Not Started
231 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.9 | DOC-09 | Manage reception staff — add, edit and remove reception users (backend done, UI absent) | DOC-09.01 | No new API — authorise that the doctor owns the staff record on existing CRUD | Existing Improvement | Staff | §5.1 | Manage reception staff | Add, edit and remove reception users | Doctor Web Portal | API | No | Yes | No | Yes | No | No | P1 | S | — | .NET 8 api/ReceptionStaff CRUD exists; no SPA page | List/add/edit/disable at /doctor/reception-staff; doctor owns the staff record | Doctor can create a reception user who logs in to that DoctorId | Not Started
232 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.9 | DOC-09 | Manage reception staff — add, edit and remove reception users (backend done, UI absent) | DOC-09.02 | Build /doctor/reception-staff list, add, edit, disable pages; menu entry in doctor chrome | Existing Improvement | Staff | §5.1 | Manage reception staff | Add, edit and remove reception users | Doctor Web Portal | Web SPA | Yes | No | No | Yes | No | No | P1 | M | DOC-09.01 | .NET 8 api/ReceptionStaff CRUD exists; no SPA page | List/add/edit/disable at /doctor/reception-staff; doctor owns the staff record | Doctor can create a reception user who logs in to that DoctorId | Not Started
233 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.9 | DOC-09 | Manage reception staff — add, edit and remove reception users (backend done, UI absent) | DOC-09.03 | QA: reception user cannot manage other doctors’ staff; disable prevents login | Regression | Staff | §5.1 | Manage reception staff | Add, edit and remove reception users | Doctor Web Portal | QA | Yes | Yes | No | No | No | No | P1 | S | DOC-09.02 | .NET 8 api/ReceptionStaff CRUD exists; no SPA page | List/add/edit/disable at /doctor/reception-staff; doctor owns the staff record | Doctor can create a reception user who logs in to that DoctorId | Not Started
234 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.10 | DOC-10 | Doctor profile — clinic details, consultation fee, photo, qualifications, working hours, bank details | DOC-10.01 | Extend Doctor / add DoctorPayeeKyc fields (bank, PAN) used later by Account; ConsultFeeConfig may wait until Phase 6 — store fee on profile now if simpler | Existing Improvement | Doctor Profile | §5.1 | Doctor profile | Clinic details, consultation fee, photo, qualifications, working hours, bank details | Doctor Web Portal | Database | No | Yes | Yes | No | No | No | P0 | S | — | /profile is Velzon first_name only (~20%); credentials sit on Doctor entity; no fee/KYC UI | Real doctor profile: clinic, photo, qualifications, consult fee (feeds Phase 6), hours (feeds schedule), bank KYC (feeds Account payees) | Doctor can save clinic, photo, qualifications, fee, hours, bank details; verification status visible | Not Started
235 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.10 | DOC-10 | Doctor profile — clinic details, consultation fee, photo, qualifications, working hours, bank details | DOC-10.02 | GET/PUT /api/Profile/Me (doctor DTO); POST photo multipart; do not allow role escalation | Existing Improvement | Doctor Profile | §5.1 | Doctor profile | Clinic details, consultation fee, photo, qualifications, working hours, bank details | Doctor Web Portal | API | No | Yes | Yes | Yes | No | No | P0 | M | DOC-10.01 | /profile is Velzon first_name only (~20%); credentials sit on Doctor entity; no fee/KYC UI | Real doctor profile: clinic, photo, qualifications, consult fee (feeds Phase 6), hours (feeds schedule), bank KYC (feeds Account payees) | Doctor can save clinic, photo, qualifications, fee, hours, bank details; verification status visible | Not Started
236 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.10 | DOC-10 | Doctor profile — clinic details, consultation fee, photo, qualifications, working hours, bank details | DOC-10.03 | Replace Velzon /profile for doctor role with clinic/fee/photo/qualifications/hours/bank tabs | Existing Improvement | Doctor Profile | §5.1 | Doctor profile | Clinic details, consultation fee, photo, qualifications, working hours, bank details | Doctor Web Portal | Web SPA | Yes | No | No | Yes | No | No | P0 | M | DOC-10.02 | /profile is Velzon first_name only (~20%); credentials sit on Doctor entity; no fee/KYC UI | Real doctor profile: clinic, photo, qualifications, consult fee (feeds Phase 6), hours (feeds schedule), bank KYC (feeds Account payees) | Doctor can save clinic, photo, qualifications, fee, hours, bank details; verification status visible | Not Started
237 | 3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 3.10 | DOC-10 | Doctor profile — clinic details, consultation fee, photo, qualifications, working hours, bank details | DOC-10.04 | QA: reception cannot edit doctor bank details; photo displays on public profile later | Regression | Doctor Profile | §5.1 | Doctor profile | Clinic details, consultation fee, photo, qualifications, working hours, bank details | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P0 | S | DOC-10.03 | /profile is Velzon first_name only (~20%); credentials sit on Doctor entity; no fee/KYC UI | Real doctor profile: clinic, photo, qualifications, consult fee (feeds Phase 6), hours (feeds schedule), bank KYC (feeds Account payees) | Doctor can save clinic, photo, qualifications, fee, hours, bank details; verification status visible | Not Started
238 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.1 | APT-01 | Appointment list & waiting patients — full day view with live status (keep; later payment/tele) | APT-01.01 | Regression: day list, status colour, open patient | Existing | Appointments | §5.2 | Appointment list & waiting patients | Full day view with live status | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P1 | S | — | Day list + status live | Keep; reschedule/cancel/payment attach to this list | Day view still lists today’s appointments | Not Started
239 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.1 | APT-01 | Appointment list & waiting patients — full day view with live status (keep; later payment/tele) | APT-01.02 | ACL doctor/reception of that DoctorId | Existing Improvement | Appointments | §5.2 | Appointment list & waiting patients | Full day view with live status | Doctor Web Portal | Security | Yes | Yes | No | Yes | No | No | P1 | S | APT-01.01 | Day list + status live | Keep; reschedule/cancel/payment attach to this list | Day view still lists today’s appointments | Not Started
240 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.1 | APT-01 | Appointment list & waiting patients — full day view with live status (keep; later payment/tele) | APT-01.03 | API unchanged | Existing | Appointments | §5.2 | Appointment list & waiting patients | Full day view with live status | Doctor Web Portal | API hygiene | No | Yes | No | Yes | No | No | P1 | S | APT-01.02 | Day list + status live | Keep; reschedule/cancel/payment attach to this list | Day view still lists today’s appointments | Not Started
241 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.2 | APT-02 | Create new appointment — persist visit type, consultation mode and fee | APT-02.01 | DB: PatientAppointment.VisitType, ConsultMode; migrate existing rows VisitType=First (do not infer retrospectively) | Existing Improvement | Appointments | §5.2 | Create new appointment | Book with visit type, consultation mode and fee | Doctor Web Portal | Database | No | Yes | Yes | No | No | No | P0 | S | — | Create appointment ~90%; Formik modal has no VisitType / ConsultMode / fee | VisitType First/Follow-up; ConsultMode In-clinic / E-Consult; fee display from doctor profile / ConsultFeeConfig | New appointments persist visit type, mode and fee; filters/analytics can use them | Not Started
242 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.2 | APT-02 | Create new appointment — persist visit type, consultation mode and fee | APT-02.02 | API: create/update appointment accepts the new fields; PATCH VisitType | Existing Improvement | Appointments | §5.2 | Create new appointment | Book with visit type, consultation mode and fee | Doctor Web Portal | API | No | Yes | Yes | Yes | No | No | P0 | M | APT-02.01 | Create appointment ~90%; Formik modal has no VisitType / ConsultMode / fee | VisitType First/Follow-up; ConsultMode In-clinic / E-Consult; fee display from doctor profile / ConsultFeeConfig | New appointments persist visit type, mode and fee; filters/analytics can use them | Not Started
243 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.2 | APT-02 | Create new appointment — persist visit type, consultation mode and fee | APT-02.03 | Doctor/Reception new-appointment modal: visit type, consult mode, fee (placeholder until Phase 6 config) | Existing Improvement | Appointments | §5.2 | Create new appointment | Book with visit type, consultation mode and fee | Doctor Web Portal | Web SPA | Yes | No | No | Yes | No | No | P0 | M | APT-02.02 | Create appointment ~90%; Formik modal has no VisitType / ConsultMode / fee | VisitType First/Follow-up; ConsultMode In-clinic / E-Consult; fee display from doctor profile / ConsultFeeConfig | New appointments persist visit type, mode and fee; filters/analytics can use them | Not Started
244 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.2 | APT-02 | Create new appointment — persist visit type, consultation mode and fee | APT-02.04 | QA: staff-created appointments carry the same fields public booking will use in Phase 9 | Regression | Appointments | §5.2 | Create new appointment | Book with visit type, consultation mode and fee | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P0 | S | APT-02.03 | Create appointment ~90%; Formik modal has no VisitType / ConsultMode / fee | VisitType First/Follow-up; ConsultMode In-clinic / E-Consult; fee display from doctor profile / ConsultFeeConfig | New appointments persist visit type, mode and fee; filters/analytics can use them | Not Started
245 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.3 | APT-03 | Appointment status update — move patients through the visit stages (keep) | APT-03.01 | Regression: each status transition | Existing | Appointments | §5.2 | Appointment status update | Move patients through the visit stages | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P1 | S | — | Status transitions live | Keep; add CANCELLED in APT-06; do not reuse DeleteStatus as cancel | Status still updates and buckets refresh | Not Started
246 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.3 | APT-03 | Appointment status update — move patients through the visit stages (keep) | APT-03.02 | ACL doctor/reception | Existing Improvement | Appointments | §5.2 | Appointment status update | Move patients through the visit stages | Doctor Web Portal | Security | Yes | Yes | No | Yes | No | No | P1 | S | APT-03.01 | Status transitions live | Keep; add CANCELLED in APT-06; do not reuse DeleteStatus as cancel | Status still updates and buckets refresh | Not Started
247 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.3 | APT-03 | Appointment status update — move patients through the visit stages (keep) | APT-03.03 | API unchanged | Existing | Appointments | §5.2 | Appointment status update | Move patients through the visit stages | Doctor Web Portal | API hygiene | No | Yes | No | Yes | No | No | P1 | S | APT-03.02 | Status transitions live | Keep; add CANCELLED in APT-06; do not reuse DeleteStatus as cancel | Status still updates and buckets refresh | Not Started
248 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.4 | APT-04 | Appointment time update — adjust timings as the day runs (keep; distinct from formal reschedule) | APT-04.01 | Regression: UpdateAppointmentTime on dashboard | Existing | Appointments | §5.2 | Appointment time update | Adjust timings as the day runs | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P1 | S | — | UpdateAppointmentTime live — changes a time only; no audit/notify | Keep same-day time tweak; formal reschedule (old→new, notify, conflict) is APT-05 | Same-day time change still works; does not silently replace Reschedule | Not Started
249 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.4 | APT-04 | Appointment time update — adjust timings as the day runs (keep; distinct from formal reschedule) | APT-04.02 | Document in UI that Reschedule is the patient-notified path | Existing Improvement | Appointments | §5.2 | Appointment time update | Adjust timings as the day runs | Doctor Web Portal | Security | Yes | Yes | No | Yes | No | No | P1 | S | APT-04.01 | UpdateAppointmentTime live — changes a time only; no audit/notify | Keep same-day time tweak; formal reschedule (old→new, notify, conflict) is APT-05 | Same-day time change still works; does not silently replace Reschedule | Not Started
250 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.4 | APT-04 | Appointment time update — adjust timings as the day runs (keep; distinct from formal reschedule) | APT-04.03 | API: keep UpdateAppointmentTime; Reschedule wraps it | Existing | Appointments | §5.2 | Appointment time update | Adjust timings as the day runs | Doctor Web Portal | API hygiene | No | Yes | No | Yes | No | No | P1 | S | APT-04.02 | UpdateAppointmentTime live — changes a time only; no audit/notify | Keep same-day time tweak; formal reschedule (old→new, notify, conflict) is APT-05 | Same-day time change still works; does not silently replace Reschedule | Not Started
251 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.5 | APT-05 | Reschedule appointment — move to a new slot with automatic patient notification (NEW — not a rename of UpdateAppointmentTime) | APT-05.01 | DB: AppointmentChangeLog (PatientAppId, Action, OldValue, NewValue, ByUserId, ByRole, At) + indexes | New | Appointments | §5.2 + §2.3 + §6 | Reschedule appointment | Move to a new slot with automatic patient notification / Move to another slot without calling the clinic | Doctor Web + Reception + later Patient | Database | No | Yes | Yes | No | No | No | P0 | S | — | Time can be edited; no formal Reschedule (audit, notify, old→new confirm) | POST RescheduleAppointment; AppointmentChangeLog; conflict 409 with alternatives; SMS/WhatsApp fan-out (notify failure must not roll back) | Every reschedule is in the change log; patient notified; old slot released; reception uses the same API | Not Started
252 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.5 | APT-05 | Reschedule appointment — move to a new slot with automatic patient notification (NEW — not a rename of UpdateAppointmentTime) | APT-05.02 | API: POST /api/PatientAppointment/RescheduleAppointment — validate schedule, bookings, not in the past; 409 with alternatives; wrap UpdateAppointmentTime; GET ChangeLog/{id} | New | Appointments | §5.2 + §2.3 + §6 | Reschedule appointment | Move to a new slot with automatic patient notification / Move to another slot without calling the clinic | Doctor Web + Reception + later Patient | API | No | Yes | Yes | Yes | No | No | P0 | M | APT-05.01 | Time can be edited; no formal Reschedule (audit, notify, old→new confirm) | POST RescheduleAppointment; AppointmentChangeLog; conflict 409 with alternatives; SMS/WhatsApp fan-out (notify failure must not roll back) | Every reschedule is in the change log; patient notified; old slot released; reception uses the same API | Not Started
253 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.5 | APT-05 | Reschedule appointment — move to a new slot with automatic patient notification (NEW — not a rename of UpdateAppointmentTime) | APT-05.03 | UI: RescheduleModal shared by Doctor and Reception — old date/time + new slot picker; reason optional | New | Appointments | §5.2 + §2.3 + §6 | Reschedule appointment | Move to a new slot with automatic patient notification / Move to another slot without calling the clinic | Doctor Web + Reception + later Patient | Web SPA | Yes | No | No | Yes | No | No | P0 | M | APT-05.02 | Time can be edited; no formal Reschedule (audit, notify, old→new confirm) | POST RescheduleAppointment; AppointmentChangeLog; conflict 409 with alternatives; SMS/WhatsApp fan-out (notify failure must not roll back) | Every reschedule is in the change log; patient notified; old slot released; reception uses the same API | Not Started
254 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.5 | APT-05 | Reschedule appointment — move to a new slot with automatic patient notification (NEW — not a rename of UpdateAppointmentTime) | APT-05.04 | Notifications: SMS + WhatsApp + (later) push — old→new; must not block the transaction if notify fails | New Integration | Appointments | §5.2 + §2.3 + §6 | Reschedule appointment | Move to a new slot with automatic patient notification / Move to another slot without calling the clinic | Doctor Web + Reception + later Patient | Integration | No | Yes | No | Yes | No | Yes | P0 | M | APT-05.03 | Time can be edited; no formal Reschedule (audit, notify, old→new confirm) | POST RescheduleAppointment; AppointmentChangeLog; conflict 409 with alternatives; SMS/WhatsApp fan-out (notify failure must not roll back) | Every reschedule is in the change log; patient notified; old slot released; reception uses the same API | Not Started
255 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.5 | APT-05 | Reschedule appointment — move to a new slot with automatic patient notification (NEW — not a rename of UpdateAppointmentTime) | APT-05.05 | QA: slot taken → 409; patient already booked elsewhere; across a schedule change; reception authorised for own DoctorId only | Regression | Appointments | §5.2 + §2.3 + §6 | Reschedule appointment | Move to a new slot with automatic patient notification / Move to another slot without calling the clinic | Doctor Web + Reception + later Patient | QA | Yes | Yes | No | Yes | No | No | P0 | S | APT-05.04 | Time can be edited; no formal Reschedule (audit, notify, old→new confirm) | POST RescheduleAppointment; AppointmentChangeLog; conflict 409 with alternatives; SMS/WhatsApp fan-out (notify failure must not roll back) | Every reschedule is in the change log; patient notified; old slot released; reception uses the same API | Not Started
256 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.6 | APT-06 | Cancel appointment — reason, free the slot, trigger refund where applicable (NEW CANCELLED status — do NOT reuse DeleteStatus) | APT-06.01 | DB: add CANCELLED to status set; CancelReasonCode, CancelReasonText, CancelledBy, CancelledAt; DeleteStatus remains administrative | New | Appointments | §5.2 + §2.3 + §6 | Cancel appointment | Cancel with reason, free the slot, trigger refund where applicable / Cancel with reason, refund handled per policy | Doctor Web + Reception + later Patient | Database | No | Yes | Yes | No | No | No | P0 | S | — | No CANCELLED; DeleteStatus is soft-delete only | CANCELLED + reason fields; free slot; waitlist hook; if PAID evaluate refund policy (Phase 6/7) | Cancelled appointments leave active buckets; slot immediately bookable; refund path triggered rather than silently keeping money | Not Started
257 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.6 | APT-06 | Cancel appointment — reason, free the slot, trigger refund where applicable (NEW CANCELLED status — do NOT reuse DeleteStatus) | APT-06.02 | API: POST /api/PatientAppointment/CancelAppointment — reason required (enum; text if Other); free slot; offer waitlist stub; if PAID enqueue refund policy | New | Appointments | §5.2 + §2.3 + §6 | Cancel appointment | Cancel with reason, free the slot, trigger refund where applicable / Cancel with reason, refund handled per policy | Doctor Web + Reception + later Patient | API | No | Yes | Yes | Yes | No | No | P0 | M | APT-06.01 | No CANCELLED; DeleteStatus is soft-delete only | CANCELLED + reason fields; free slot; waitlist hook; if PAID evaluate refund policy (Phase 6/7) | Cancelled appointments leave active buckets; slot immediately bookable; refund path triggered rather than silently keeping money | Not Started
258 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.6 | APT-06 | Cancel appointment — reason, free the slot, trigger refund where applicable (NEW CANCELLED status — do NOT reuse DeleteStatus) | APT-06.03 | UI: CancelAppointmentModal shared by Doctor and Reception; dashboard Cancelled filter | New | Appointments | §5.2 + §2.3 + §6 | Cancel appointment | Cancel with reason, free the slot, trigger refund where applicable / Cancel with reason, refund handled per policy | Doctor Web + Reception + later Patient | Web SPA | Yes | No | No | Yes | No | No | P0 | M | APT-06.02 | No CANCELLED; DeleteStatus is soft-delete only | CANCELLED + reason fields; free slot; waitlist hook; if PAID evaluate refund policy (Phase 6/7) | Cancelled appointments leave active buckets; slot immediately bookable; refund path triggered rather than silently keeping money | Not Started
259 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.6 | APT-06 | Cancel appointment — reason, free the slot, trigger refund where applicable (NEW CANCELLED status — do NOT reuse DeleteStatus) | APT-06.04 | Waitlist worker stub: on cancel, offer freed slot (full waitlist capture is Phase 9 GST waitlist) | New Integration | Appointments | §5.2 + §2.3 + §6 | Cancel appointment | Cancel with reason, free the slot, trigger refund where applicable / Cancel with reason, refund handled per policy | Doctor Web + Reception + later Patient | Integration | No | Yes | No | Yes | No | Yes | P0 | M | APT-06.03 | No CANCELLED; DeleteStatus is soft-delete only | CANCELLED + reason fields; free slot; waitlist hook; if PAID evaluate refund policy (Phase 6/7) | Cancelled appointments leave active buckets; slot immediately bookable; refund path triggered rather than silently keeping money | Not Started
260 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.6 | APT-06 | Cancel appointment — reason, free the slot, trigger refund where applicable (NEW CANCELLED status — do NOT reuse DeleteStatus) | APT-06.05 | QA: reason mandatory; all three roles (later Patient) cancel with correct authorisation; freed slot bookable | Regression | Appointments | §5.2 + §2.3 + §6 | Cancel appointment | Cancel with reason, free the slot, trigger refund where applicable / Cancel with reason, refund handled per policy | Doctor Web + Reception + later Patient | QA | Yes | Yes | No | Yes | No | No | P0 | S | APT-06.04 | No CANCELLED; DeleteStatus is soft-delete only | CANCELLED + reason fields; free slot; waitlist hook; if PAID evaluate refund policy (Phase 6/7) | Cancelled appointments leave active buckets; slot immediately bookable; refund path triggered rather than silently keeping money | Not Started
261 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.7 | APT-07 | Daily schedule setup — define working days, hours and break times (promote modal to first-class screen) | APT-07.01 | Promote DailyScheduleSetupModal to /doctor/schedule; week grid; copy-day; reuse Get/SaveDailySchedule | Existing Improvement | Scheduling | §5.2 | Daily schedule setup | Define working days, hours and break times | Doctor Web Portal | Web SPA | Yes | No | No | Yes | No | No | P0 | M | — | DailyScheduleSetupModal + GetDailySchedule / SaveDailySchedule exist; not a first-class screen (draft marked 0%) | Promote to /doctor/schedule with week grid and copy-day; reuse existing APIs — do not rebuild | Public booking slots (Phase 9) respect the saved schedule | Not Started
262 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.7 | APT-07 | Daily schedule setup — define working days, hours and break times (promote modal to first-class screen) | APT-07.02 | No new API unless validation (breaks, overlapping hours) is missing — add server-side validation | Existing Improvement | Scheduling | §5.2 | Daily schedule setup | Define working days, hours and break times | Doctor Web Portal | API | No | Yes | No | Yes | No | No | P0 | S | APT-07.01 | DailyScheduleSetupModal + GetDailySchedule / SaveDailySchedule exist; not a first-class screen (draft marked 0%) | Promote to /doctor/schedule with week grid and copy-day; reuse existing APIs — do not rebuild | Public booking slots (Phase 9) respect the saved schedule | Not Started
263 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.7 | APT-07 | Daily schedule setup — define working days, hours and break times (promote modal to first-class screen) | APT-07.03 | QA: save week; public slot generator (Phase 9) uses this data; reception read-only is Phase 5 | Regression | Scheduling | §5.2 | Daily schedule setup | Define working days, hours and break times | Doctor Web Portal | QA | Yes | Yes | No | No | No | No | P0 | S | APT-07.02 | DailyScheduleSetupModal + GetDailySchedule / SaveDailySchedule exist; not a first-class screen (draft marked 0%) | Promote to /doctor/schedule with week grid and copy-day; reuse existing APIs — do not rebuild | Public booking slots (Phase 9) respect the saved schedule | Not Started
264 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.8 | APT-08 | Appointment slot grid — visual slot-by-slot view of the day (keep; public booking reuses this) | APT-08.01 | Regression: slot grid vs schedule | Existing | Scheduling | §5.2 | Appointment slot grid | Visual slot-by-slot view of the day | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P0 | S | — | Slot picker / grid live | Keep; Phase 9 public APIs reuse the same slot engine | Grid matches saved daily schedule | Not Started
265 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.8 | APT-08 | Appointment slot grid — visual slot-by-slot view of the day (keep; public booking reuses this) | APT-08.02 | ACL doctor/reception | Existing Improvement | Scheduling | §5.2 | Appointment slot grid | Visual slot-by-slot view of the day | Doctor Web Portal | Security | Yes | Yes | No | Yes | No | No | P0 | S | APT-08.01 | Slot picker / grid live | Keep; Phase 9 public APIs reuse the same slot engine | Grid matches saved daily schedule | Not Started
266 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.8 | APT-08 | Appointment slot grid — visual slot-by-slot view of the day (keep; public booking reuses this) | APT-08.03 | Document GetAppointmentSlots as the public-booking engine — do not fork a second slot calculator | Existing | Scheduling | §5.2 | Appointment slot grid | Visual slot-by-slot view of the day | Doctor Web Portal | API hygiene | No | Yes | No | Yes | No | No | P0 | S | APT-08.02 | Slot picker / grid live | Keep; Phase 9 public APIs reuse the same slot engine | Grid matches saved daily schedule | Not Started
267 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.9 | APT-09 | Consultation payment status on every appointment (schema now; values live in Phase 6) | APT-09.01 | DB: PatientAppointment.PaymentStatus, PaymentMethod, PayAtClinicAllowed; default UNPAID | New | Appointments | §5.2 + §9 | Consultation payment status | See paid, unpaid or pay-at-clinic on every appointment / Doctor, reception and patient all see the same payment status | Doctor Web Portal | Database | No | Yes | Yes | No | No | No | P0 | S | — | No PaymentStatus on appointment | Add PaymentStatus UNPAID / PENDING / PAID / FAILED / PAY_AT_CLINIC / REFUNDED; UI badge; source of truth is webhook in Phase 6 not the client screen | Every appointment row can show a payment badge; until Phase 6 all show UNPAID/PAY_AT_CLINIC as configured | Not Started
268 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.9 | APT-09 | Consultation payment status on every appointment (schema now; values live in Phase 6) | APT-09.02 | API: include PaymentStatus on all appointment DTOs (doctor, reception, later public/patient) | New | Appointments | §5.2 + §9 | Consultation payment status | See paid, unpaid or pay-at-clinic on every appointment / Doctor, reception and patient all see the same payment status | Doctor Web Portal | API | No | Yes | No | Yes | No | No | P0 | S | APT-09.01 | No PaymentStatus on appointment | Add PaymentStatus UNPAID / PENDING / PAID / FAILED / PAY_AT_CLINIC / REFUNDED; UI badge; source of truth is webhook in Phase 6 not the client screen | Every appointment row can show a payment badge; until Phase 6 all show UNPAID/PAY_AT_CLINIC as configured | Not Started
269 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.9 | APT-09 | Consultation payment status on every appointment (schema now; values live in Phase 6) | APT-09.03 | UI: Paid / Unpaid / Pay-at-clinic / Failed badges on doctor appointment list | New | Appointments | §5.2 + §9 | Consultation payment status | See paid, unpaid or pay-at-clinic on every appointment / Doctor, reception and patient all see the same payment status | Doctor Web Portal | Web SPA | Yes | No | No | No | No | No | P0 | S | APT-09.02 | No PaymentStatus on appointment | Add PaymentStatus UNPAID / PENDING / PAID / FAILED / PAY_AT_CLINIC / REFUNDED; UI badge; source of truth is webhook in Phase 6 not the client screen | Every appointment row can show a payment badge; until Phase 6 all show UNPAID/PAY_AT_CLINIC as configured | Not Started
270 | 4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 4.9 | APT-09 | Consultation payment status on every appointment (schema now; values live in Phase 6) | APT-09.04 | QA: same appointment shows the same badge on doctor and reception | Regression | Appointments | §5.2 + §9 | Consultation payment status | See paid, unpaid or pay-at-clinic on every appointment / Doctor, reception and patient all see the same payment status | Doctor Web Portal | QA | Yes | No | No | No | No | No | P0 | S | APT-09.03 | No PaymentStatus on appointment | Add PaymentStatus UNPAID / PENDING / PAID / FAILED / PAY_AT_CLINIC / REFUNDED; UI badge; source of truth is webhook in Phase 6 not the client screen | Every appointment row can show a payment badge; until Phase 6 all show UNPAID/PAY_AT_CLINIC as configured | Not Started
271 | 5 | Phase 5 — Reception portal (PDF §6) | 5.1 | REC-01 | Reception login — secure staff access (keep) | REC-01.01 | Regression: reception login with DoctorID claim | Existing | Reception | §6 | Reception login | Secure staff access | Reception Portal | QA | Yes | Yes | No | Yes | No | No | P1 | S | — | Reception logs in via Account; JWT includes DoctorID; uses doctor dashboard layout | Keep login; Phase 0 hashing applies; later dedicated reception chrome | Reception user still logs in and lands on front-desk home | Not Started
272 | 5 | Phase 5 — Reception portal (PDF §6) | 5.1 | REC-01 | Reception login — secure staff access (keep) | REC-01.02 | Disabled staff cannot login (after DOC-09) | Existing Improvement | Reception | §6 | Reception login | Secure staff access | Reception Portal | Security | Yes | Yes | No | Yes | No | No | P1 | S | REC-01.01 | Reception logs in via Account; JWT includes DoctorID; uses doctor dashboard layout | Keep login; Phase 0 hashing applies; later dedicated reception chrome | Reception user still logs in and lands on front-desk home | Not Started
273 | 5 | Phase 5 — Reception portal (PDF §6) | 5.1 | REC-01 | Reception login — secure staff access (keep) | REC-01.03 | Same Login API as doctor | Existing | Reception | §6 | Reception login | Secure staff access | Reception Portal | API hygiene | No | Yes | No | Yes | No | No | P1 | S | REC-01.02 | Reception logs in via Account; JWT includes DoctorID; uses doctor dashboard layout | Keep login; Phase 0 hashing applies; later dedicated reception chrome | Reception user still logs in and lands on front-desk home | Not Started
274 | 5 | Phase 5 — Reception portal (PDF §6) | 5.2 | REC-02 | Reception profile — manage own profile details (0% today) | REC-02.01 | Reuse Profile/Me with role=Reception DTO (no new table if UserMaster suffices) | New | Reception | §6 | Reception profile | Manage own profile details | Reception Portal | Database | No | Yes | Yes | No | No | No | P1 | S | — | No reception-specific profile; shared Velzon /profile | Name, mobile, attached doctor (read-only); cannot edit doctor bank/fee | Reception can update own name/mobile; cannot change DoctorId | Not Started
275 | 5 | Phase 5 — Reception portal (PDF §6) | 5.2 | REC-02 | Reception profile — manage own profile details (0% today) | REC-02.02 | GET/PUT profile fields allowed for reception; ignore clinic fee/bank | New | Reception | §6 | Reception profile | Manage own profile details | Reception Portal | API | No | Yes | Yes | Yes | No | No | P1 | M | REC-02.01 | No reception-specific profile; shared Velzon /profile | Name, mobile, attached doctor (read-only); cannot edit doctor bank/fee | Reception can update own name/mobile; cannot change DoctorId | Not Started
276 | 5 | Phase 5 — Reception portal (PDF §6) | 5.2 | REC-02 | Reception profile — manage own profile details (0% today) | REC-02.03 | /profile reception variant | New | Reception | §6 | Reception profile | Manage own profile details | Reception Portal | Web SPA | Yes | No | No | Yes | No | No | P1 | M | REC-02.02 | No reception-specific profile; shared Velzon /profile | Name, mobile, attached doctor (read-only); cannot edit doctor bank/fee | Reception can update own name/mobile; cannot change DoctorId | Not Started
277 | 5 | Phase 5 — Reception portal (PDF §6) | 5.2 | REC-02 | Reception profile — manage own profile details (0% today) | REC-02.04 | QA: cannot edit doctor qualifications or fee | Regression | Reception | §6 | Reception profile | Manage own profile details | Reception Portal | QA | Yes | Yes | No | Yes | No | No | P1 | S | REC-02.03 | No reception-specific profile; shared Velzon /profile | Name, mobile, attached doctor (read-only); cannot edit doctor bank/fee | Reception can update own name/mobile; cannot change DoctorId | Not Started
278 | 5 | Phase 5 — Reception portal (PDF §6) | 5.3 | REC-03 | Reception home dashboard — purpose-built front-desk dashboard (not only hidden doctor actions) | REC-03.01 | Route /reception (or role-based chrome on existing dashboard) hiding clinical tabs | Existing Improvement | Reception | §6 | Reception home dashboard | Purpose-built front-desk dashboard | Reception Portal | Web SPA | Yes | No | No | No | No | No | P1 | M | — | Same /doctordashboard with some clinical actions disabled ~90% | Reception-first chrome: queue, collect pay, case paper, no repertory/Rx; optional /reception home route | Reception never sees repertorize/audio/COG; sees queue and collect-pay | Not Started
279 | 5 | Phase 5 — Reception portal (PDF §6) | 5.3 | REC-03 | Reception home dashboard — purpose-built front-desk dashboard (not only hidden doctor actions) | REC-03.02 | Quick actions: new patient, new appointment, collect payment, case paper, schedule | Existing Improvement | Reception | §6 | Reception home dashboard | Purpose-built front-desk dashboard | Reception Portal | Web SPA | Yes | No | No | No | No | No | P1 | S | REC-03.01 | Same /doctordashboard with some clinical actions disabled ~90% | Reception-first chrome: queue, collect pay, case paper, no repertory/Rx; optional /reception home route | Reception never sees repertorize/audio/COG; sees queue and collect-pay | Not Started
280 | 5 | Phase 5 — Reception portal (PDF §6) | 5.3 | REC-03 | Reception home dashboard — purpose-built front-desk dashboard (not only hidden doctor actions) | REC-03.03 | QA: deep-link to Patient Board full clinical URL is 403 for reception | Regression | Reception | §6 | Reception home dashboard | Purpose-built front-desk dashboard | Reception Portal | QA | Yes | Yes | No | No | No | No | P1 | S | REC-03.02 | Same /doctordashboard with some clinical actions disabled ~90% | Reception-first chrome: queue, collect pay, case paper, no repertory/Rx; optional /reception home route | Reception never sees repertorize/audio/COG; sees queue and collect-pay | Not Started
281 | 5 | Phase 5 — Reception portal (PDF §6) | 5.4 | REC-04 | Create patient — register a walk-in patient quickly (keep) | REC-04.01 | Regression: reception create patient | Existing | Reception | §6 | Create patient | Register a walk-in patient quickly | Reception Portal | QA | Yes | Yes | No | Yes | No | No | P1 | S | — | Create patient live on shared dashboard | Keep on reception chrome | Walk-in patient created under the JWT DoctorId | Not Started
282 | 5 | Phase 5 — Reception portal (PDF §6) | 5.4 | REC-04 | Create patient — register a walk-in patient quickly (keep) | REC-04.02 | ACL: own doctor only | Existing Improvement | Reception | §6 | Create patient | Register a walk-in patient quickly | Reception Portal | Security | Yes | Yes | No | Yes | No | No | P1 | S | REC-04.01 | Create patient live on shared dashboard | Keep on reception chrome | Walk-in patient created under the JWT DoctorId | Not Started
283 | 5 | Phase 5 — Reception portal (PDF §6) | 5.4 | REC-04 | Create patient — register a walk-in patient quickly (keep) | REC-04.03 | Same create-patient API | Existing | Reception | §6 | Create patient | Register a walk-in patient quickly | Reception Portal | API hygiene | No | Yes | No | Yes | No | No | P1 | S | REC-04.02 | Create patient live on shared dashboard | Keep on reception chrome | Walk-in patient created under the JWT DoctorId | Not Started
284 | 5 | Phase 5 — Reception portal (PDF §6) | 5.5 | REC-05 | Patient search & list — find any patient instantly (keep) | REC-05.01 | Regression: search by name/mobile | Existing | Reception | §6 | Patient search & list | Find any patient instantly | Reception Portal | QA | Yes | Yes | No | Yes | No | No | P1 | S | — | Search live | Keep; no opening full clinical board | Search returns this doctor’s patients only | Not Started
285 | 5 | Phase 5 — Reception portal (PDF §6) | 5.5 | REC-05 | Patient search & list — find any patient instantly (keep) | REC-05.02 | Opening a row goes to case paper or appointment, not full repertory | Existing Improvement | Reception | §6 | Patient search & list | Find any patient instantly | Reception Portal | Security | Yes | Yes | No | Yes | No | No | P1 | S | REC-05.01 | Search live | Keep; no opening full clinical board | Search returns this doctor’s patients only | Not Started
286 | 5 | Phase 5 — Reception portal (PDF §6) | 5.5 | REC-05 | Patient search & list — find any patient instantly (keep) | REC-05.03 | API unchanged | Existing | Reception | §6 | Patient search & list | Find any patient instantly | Reception Portal | API hygiene | No | Yes | No | Yes | No | No | P1 | S | REC-05.02 | Search live | Keep; no opening full clinical board | Search returns this doctor’s patients only | Not Started
287 | 5 | Phase 5 — Reception portal (PDF §6) | 5.6 | REC-06 | Create & manage appointments — full appointment management (keep; plus reschedule/cancel from Phase 4) | REC-06.01 | Authorise Reception for Reschedule and Cancel for its own doctor's appointments only | New | Reception | §6 | Create & manage appointments | Full appointment management | Reception Portal | API + SPA | Yes | Yes | No | Yes | No | No | P0 | S | — | Create/status/time live; reschedule/cancel missing until Phase 4 APIs | Enable RescheduleAppointment and CancelAppointment for JWT DoctorId; isReceptionUser must not block | Reception acts only for its doctor; permission tests pass | Not Started
288 | 5 | Phase 5 — Reception portal (PDF §6) | 5.6 | REC-06 | Create & manage appointments — full appointment management (keep; plus reschedule/cancel from Phase 4) | REC-06.02 | Reception UI uses the same Reschedule/Cancel modals as doctor | New | Reception | §6 | Create & manage appointments | Full appointment management | Reception Portal | Web SPA | Yes | No | No | No | No | No | P0 | S | REC-06.01 | Create/status/time live; reschedule/cancel missing until Phase 4 APIs | Enable RescheduleAppointment and CancelAppointment for JWT DoctorId; isReceptionUser must not block | Reception acts only for its doctor; permission tests pass | Not Started
289 | 5 | Phase 5 — Reception portal (PDF §6) | 5.6 | REC-06 | Create & manage appointments — full appointment management (keep; plus reschedule/cancel from Phase 4) | REC-06.03 | QA: cannot cancel another clinic’s appointment | Regression | Reception | §6 | Create & manage appointments | Full appointment management | Reception Portal | QA | Yes | Yes | No | No | No | No | P0 | S | REC-06.02 | Create/status/time live; reschedule/cancel missing until Phase 4 APIs | Enable RescheduleAppointment and CancelAppointment for JWT DoctorId; isReceptionUser must not block | Reception acts only for its doctor; permission tests pass | Not Started
290 | 5 | Phase 5 — Reception portal (PDF §6) | 5.7 | REC-07 | New appointment — book on behalf of the patient (keep; same VisitType/ConsultMode/fee as APT-02) | REC-07.01 | Share the extended new-appointment modal with reception chrome | Existing Improvement | Reception | §6 | New appointment | Book on behalf of the patient | Reception Portal | Web SPA | Yes | No | No | No | No | No | P1 | S | — | New appointment modal live; fields incomplete until APT-02 | Same modal fields as doctor so public booking later matches staff-created rows | Reception-created appointments have visit type, mode, fee | Not Started
291 | 5 | Phase 5 — Reception portal (PDF §6) | 5.7 | REC-07 | New appointment — book on behalf of the patient (keep; same VisitType/ConsultMode/fee as APT-02) | REC-07.02 | QA: in-clinic vs E-Consult both creatable from reception | Regression | Reception | §6 | New appointment | Book on behalf of the patient | Reception Portal | QA | Yes | No | No | No | No | No | P1 | S | REC-07.01 | New appointment modal live; fields incomplete until APT-02 | Same modal fields as doctor so public booking later matches staff-created rows | Reception-created appointments have visit type, mode, fee | Not Started
292 | 5 | Phase 5 — Reception portal (PDF §6) | 5.8 | REC-08 | Waiting queue management — manage the live queue and call the next patient | REC-08.01 | No new table required if status+order suffice; optional QueuePosition | Existing Improvement | Reception | §6 | Waiting queue management | Manage the live queue and call the next patient | Reception Portal | Database | No | Yes | Yes | No | No | No | P1 | S | — | Status buckets ~60%; no dedicated queue UX / call-next | Dedicated queue: walk-in vs tele; payment state; Call next; notify patient (later push) | Reception can call next; status moves; patient can be notified when Phase 12 exists | Not Started
293 | 5 | Phase 5 — Reception portal (PDF §6) | 5.8 | REC-08 | Waiting queue management — manage the live queue and call the next patient | REC-08.02 | Optional CallNext API that sets status and timestamp | Existing Improvement | Reception | §6 | Waiting queue management | Manage the live queue and call the next patient | Reception Portal | API | No | Yes | Yes | Yes | No | No | P1 | M | REC-08.01 | Status buckets ~60%; no dedicated queue UX / call-next | Dedicated queue: walk-in vs tele; payment state; Call next; notify patient (later push) | Reception can call next; status moves; patient can be notified when Phase 12 exists | Not Started
294 | 5 | Phase 5 — Reception portal (PDF §6) | 5.8 | REC-08 | Waiting queue management — manage the live queue and call the next patient | REC-08.03 | Queue panel: order, wait time, paid/unpaid, Call next | Existing Improvement | Reception | §6 | Waiting queue management | Manage the live queue and call the next patient | Reception Portal | Web SPA | Yes | No | No | Yes | No | No | P1 | M | REC-08.02 | Status buckets ~60%; no dedicated queue UX / call-next | Dedicated queue: walk-in vs tele; payment state; Call next; notify patient (later push) | Reception can call next; status moves; patient can be notified when Phase 12 exists | Not Started
295 | 5 | Phase 5 — Reception portal (PDF §6) | 5.8 | REC-08 | Waiting queue management — manage the live queue and call the next patient | REC-08.04 | QA: two waiting patients; call next picks the right one | Regression | Reception | §6 | Waiting queue management | Manage the live queue and call the next patient | Reception Portal | QA | Yes | Yes | No | Yes | No | No | P1 | S | REC-08.03 | Status buckets ~60%; no dedicated queue UX / call-next | Dedicated queue: walk-in vs tele; payment state; Call next; notify patient (later push) | Reception can call next; status moves; patient can be notified when Phase 12 exists | Not Started
296 | 5 | Phase 5 — Reception portal (PDF §6) | 5.9 | REC-09 | Appointment status update (reception) — update as patients arrive and are seen (keep) | REC-09.01 | Regression: reception status update | Existing | Reception | §6 | Appointment status update | Update as patients arrive and are seen | Reception Portal | QA | Yes | Yes | No | Yes | No | No | P1 | S | — | Status update live | Keep on reception chrome | Arrived / seen transitions still work | Not Started
297 | 5 | Phase 5 — Reception portal (PDF §6) | 5.9 | REC-09 | Appointment status update (reception) — update as patients arrive and are seen (keep) | REC-09.02 | ACL own doctor | Existing Improvement | Reception | §6 | Appointment status update | Update as patients arrive and are seen | Reception Portal | Security | Yes | Yes | No | Yes | No | No | P1 | S | REC-09.01 | Status update live | Keep on reception chrome | Arrived / seen transitions still work | Not Started
298 | 5 | Phase 5 — Reception portal (PDF §6) | 5.9 | REC-09 | Appointment status update (reception) — update as patients arrive and are seen (keep) | REC-09.03 | Same status API as doctor | Existing | Reception | §6 | Appointment status update | Update as patients arrive and are seen | Reception Portal | API hygiene | No | Yes | No | Yes | No | No | P1 | S | REC-09.02 | Status update live | Keep on reception chrome | Arrived / seen transitions still work | Not Started
299 | 5 | Phase 5 — Reception portal (PDF §6) | 5.10 | REC-10 | Appointment time update (reception) — adjust timings through the day (keep) | REC-10.01 | Regression: reception UpdateAppointmentTime | Existing | Reception | §6 | Appointment time update | Adjust timings through the day | Reception Portal | QA | Yes | Yes | No | Yes | No | No | P2 | S | — | Time update live | Keep; formal reschedule remains REC-06 | Same-day time tweak from reception works | Not Started
300 | 5 | Phase 5 — Reception portal (PDF §6) | 5.10 | REC-10 | Appointment time update (reception) — adjust timings through the day (keep) | REC-10.02 | ACL own doctor | Existing Improvement | Reception | §6 | Appointment time update | Adjust timings through the day | Reception Portal | Security | Yes | Yes | No | Yes | No | No | P2 | S | REC-10.01 | Time update live | Keep; formal reschedule remains REC-06 | Same-day time tweak from reception works | Not Started
301 | 5 | Phase 5 — Reception portal (PDF §6) | 5.10 | REC-10 | Appointment time update (reception) — adjust timings through the day (keep) | REC-10.03 | Same API | Existing | Reception | §6 | Appointment time update | Adjust timings through the day | Reception Portal | API hygiene | No | Yes | No | Yes | No | No | P2 | S | REC-10.02 | Time update live | Keep; formal reschedule remains REC-06 | Same-day time tweak from reception works | Not Started
302 | 5 | Phase 5 — Reception portal (PDF §6) | 5.11 | REC-11 | View doctor schedule — see the doctor’s working schedule (read-only) | REC-11.01 | Frontend only over existing GetDailySchedule — /reception/schedule read-only | New | Reception | §6 | View doctor schedule | See the doctor’s working schedule | Reception Portal | Web SPA | Yes | No | No | Yes | No | No | P1 | S | — | GetDailySchedule exists; no reception view | Read-only /reception/schedule using DoctorID from JWT | Reception views hours; cannot edit clinical schedule unless authorised | Not Started
303 | 5 | Phase 5 — Reception portal (PDF §6) | 5.11 | REC-11 | View doctor schedule — see the doctor’s working schedule (read-only) | REC-11.02 | QA: edit buttons hidden; doctor can still edit on /doctor/schedule | Regression | Reception | §6 | View doctor schedule | See the doctor’s working schedule | Reception Portal | QA | Yes | No | No | No | No | No | P1 | S | REC-11.01 | GetDailySchedule exists; no reception view | Read-only /reception/schedule using DoctorID from JWT | Reception views hours; cannot edit clinical schedule unless authorised | Not Started
304 | 5 | Phase 5 — Reception portal (PDF §6) | 5.12 | REC-12 | Log case paper / chief complaint — record the reason for visit before the consultation | REC-12.01 | Reuse complaints table; add CreatedByRole=Reception | New | Reception | §6 | Log case paper / chief complaint | Record the reason for visit before the consultation | Reception Portal | Database | No | Yes | Yes | No | No | No | P1 | S | — | Missing; SaveComplaints exists but board is doctor-only | Restricted case-paper form (chief complaint only — no repertory/Rx); audit reception author | Chief complaint visible to doctor on Patient Board; reception cannot repertorize | Not Started
305 | 5 | Phase 5 — Reception portal (PDF §6) | 5.12 | REC-12 | Log case paper / chief complaint — record the reason for visit before the consultation | REC-12.02 | POST case-paper subset of SaveComplaints; GET on board | New | Reception | §6 | Log case paper / chief complaint | Record the reason for visit before the consultation | Reception Portal | API | No | Yes | Yes | Yes | No | No | P1 | M | REC-12.01 | Missing; SaveComplaints exists but board is doctor-only | Restricted case-paper form (chief complaint only — no repertory/Rx); audit reception author | Chief complaint visible to doctor on Patient Board; reception cannot repertorize | Not Started
306 | 5 | Phase 5 — Reception portal (PDF §6) | 5.12 | REC-12 | Log case paper / chief complaint — record the reason for visit before the consultation | REC-12.03 | /reception/case-paper or limited board | New | Reception | §6 | Log case paper / chief complaint | Record the reason for visit before the consultation | Reception Portal | Web SPA | Yes | No | No | Yes | No | No | P1 | M | REC-12.02 | Missing; SaveComplaints exists but board is doctor-only | Restricted case-paper form (chief complaint only — no repertory/Rx); audit reception author | Chief complaint visible to doctor on Patient Board; reception cannot repertorize | Not Started
307 | 5 | Phase 5 — Reception portal (PDF §6) | 5.12 | REC-12 | Log case paper / chief complaint — record the reason for visit before the consultation | REC-12.04 | QA: doctor sees CC; reception 403 on repertory APIs | Regression | Reception | §6 | Log case paper / chief complaint | Record the reason for visit before the consultation | Reception Portal | QA | Yes | Yes | No | Yes | No | No | P1 | S | REC-12.03 | Missing; SaveComplaints exists but board is doctor-only | Restricted case-paper form (chief complaint only — no repertory/Rx); audit reception author | Chief complaint visible to doctor on Patient Board; reception cannot repertorize | Not Started
308 | 5 | Phase 5 — Reception portal (PDF §6) | 5.13 | REC-13 | Collect consultation payment — cash, UPI, card or payment link and issue a receipt (API in Phase 6; UI shell now) | REC-13.01 | Specify receipt fields (amount, method, appointment, GST placeholder) for Phase 6 implementation | New | Reception | §6 + §9 | Collect consultation payment | Take cash, UPI, card or payment link and issue a receipt | Reception Portal | Design | Yes | No | No | No | No | No | P0 | S | — | Does not exist | UI modal ready; CollectAtReception API lands with payment spine in Phase 6 — do not fake a paid status here | Modal exists but cannot mark PAID until Phase 6 webhook/ledger path is live — or land UI in Phase 6 with PAY-06. Prefer implement fully in Phase 6; this task is the reception UX that Phase 6 must include | Not Started |  | Implement with PAY-02 in Phase 6; listed here so PDF §6 is not skipped in the Reception phase map
309 | 5 | Phase 5 — Reception portal (PDF §6) | 5.13 | REC-13 | Collect consultation payment — cash, UPI, card or payment link and issue a receipt (API in Phase 6; UI shell now) | REC-13.02 | Do not write PaymentStatus=PAID from the client — Account/webhook is source of truth (Phase 6) | New | Reception | §6 + §9 | Collect consultation payment | Take cash, UPI, card or payment link and issue a receipt | Reception Portal | Architecture | No | Yes | No | No | No | No | P0 | S | REC-13.01 | Does not exist | UI modal ready; CollectAtReception API lands with payment spine in Phase 6 — do not fake a paid status here | Modal exists but cannot mark PAID until Phase 6 webhook/ledger path is live — or land UI in Phase 6 with PAY-06. Prefer implement fully in Phase 6; this task is the reception UX that Phase 6 must include | Not Started |  | Implement with PAY-02 in Phase 6; listed here so PDF §6 is not skipped in the Reception phase map
310 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.1 | PAY-01 | Consultation fee configuration — each doctor’s fee set and displayed to patients | PAY-01.01 | DB: ConsultFeeConfig (DoctorId, InClinicFee, TeleFee, InstantSurcharge, Currency, PayAtClinicEnabled, EffectiveFrom) | New | Payments | §9 | Consultation fee configuration | Each doctor’s fee set and displayed to patients | Doctor profile + Public + Admin | Database | No | Yes | Yes | No | No | No | P0 | S | — | No ConsultFeeConfig; doctor profile work in DOC-10 may have stored a fee field | ConsultFeeConfig (InClinic, EConsult, optional Instant surcharge, PayAtClinicEnabled, GST flags) | Fee shown to patients matches what checkout charges; admin/doctor can update | Not Started
311 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.1 | PAY-01 | Consultation fee configuration — each doctor’s fee set and displayed to patients | PAY-01.02 | API: GET public fee; PUT doctor/admin; history of changes in audit | New | Payments | §9 | Consultation fee configuration | Each doctor’s fee set and displayed to patients | Doctor profile + Public + Admin | API | No | Yes | Yes | Yes | No | No | P0 | M | PAY-01.01 | No ConsultFeeConfig; doctor profile work in DOC-10 may have stored a fee field | ConsultFeeConfig (InClinic, EConsult, optional Instant surcharge, PayAtClinicEnabled, GST flags) | Fee shown to patients matches what checkout charges; admin/doctor can update | Not Started
312 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.1 | PAY-01 | Consultation fee configuration — each doctor’s fee set and displayed to patients | PAY-01.03 | Doctor profile fee tab + later public doctor card | New | Payments | §9 | Consultation fee configuration | Each doctor’s fee set and displayed to patients | Doctor profile + Public + Admin | Web SPA | Yes | No | No | Yes | No | No | P0 | M | PAY-01.02 | No ConsultFeeConfig; doctor profile work in DOC-10 may have stored a fee field | ConsultFeeConfig (InClinic, EConsult, optional Instant surcharge, PayAtClinicEnabled, GST flags) | Fee shown to patients matches what checkout charges; admin/doctor can update | Not Started
313 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.1 | PAY-01 | Consultation fee configuration — each doctor’s fee set and displayed to patients | PAY-01.04 | QA: changing fee does not alter already-created unpaid orders without a rule (document the rule) | Regression | Payments | §9 | Consultation fee configuration | Each doctor’s fee set and displayed to patients | Doctor profile + Public + Admin | QA | Yes | Yes | No | Yes | No | No | P0 | S | PAY-01.03 | No ConsultFeeConfig; doctor profile work in DOC-10 may have stored a fee field | ConsultFeeConfig (InClinic, EConsult, optional Instant surcharge, PayAtClinicEnabled, GST flags) | Fee shown to patients matches what checkout charges; admin/doctor can update | Not Started
314 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.2 | PAY-02 | Automatic payment verification — bank/webhook is source of truth, not the patient’s screen | PAY-02.01 | DB: PaymentOrder, PaymentEvent (raw webhook), idempotency key on payment_id | New | Payments | §9 | Automatic payment verification | Payments confirmed by the bank, not by the patient’s screen — nothing is lost if the app or browser closes | Shared | Database | No | Yes | Yes | No | No | No | P0 | M | — | Razorpay checkout for S1 subscription only; no webhook; no signature verify on server | Port Razorpay to .NET 8; keys in config; POST /api/Payments/Webhook/Razorpay anonymous + signature verify; PaymentOrder table | Kill browser after pay → webhook still marks PAID; client callback alone never marks PAID | Not Started
315 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.2 | PAY-02 | Automatic payment verification — bank/webhook is source of truth, not the patient’s screen | PAY-02.02 | Port Order/GenerateOrderId pattern to .NET 8; move keys to configuration; do not commit secrets | New Integration | Payments | §9 | Automatic payment verification | Payments confirmed by the bank, not by the patient’s screen — nothing is lost if the app or browser closes | Shared | API | No | Yes | No | Yes | No | Yes | P0 | L | PAY-02.01 | Razorpay checkout for S1 subscription only; no webhook; no signature verify on server | Port Razorpay to .NET 8; keys in config; POST /api/Payments/Webhook/Razorpay anonymous + signature verify; PaymentOrder table | Kill browser after pay → webhook still marks PAID; client callback alone never marks PAID | Not Started
316 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.2 | PAY-02 | Automatic payment verification — bank/webhook is source of truth, not the patient’s screen | PAY-02.03 | Webhook handler payment.captured / payment.failed; signature verify; never trust client-only success | New Integration | Payments | §9 | Automatic payment verification | Payments confirmed by the bank, not by the patient’s screen — nothing is lost if the app or browser closes | Shared | API | No | Yes | No | Yes | No | Yes | P0 | M | PAY-02.02 | Razorpay checkout for S1 subscription only; no webhook; no signature verify on server | Port Razorpay to .NET 8; keys in config; POST /api/Payments/Webhook/Razorpay anonymous + signature verify; PaymentOrder table | Kill browser after pay → webhook still marks PAID; client callback alone never marks PAID | Not Started
317 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.2 | PAY-02 | Automatic payment verification — bank/webhook is source of truth, not the patient’s screen | PAY-02.04 | QA: duplicate webhook; delayed webhook; failed capture; app closed mid-checkout | Regression | Payments | §9 | Automatic payment verification | Payments confirmed by the bank, not by the patient’s screen — nothing is lost if the app or browser closes | Shared | QA | No | Yes | No | No | No | Yes | P0 | M | PAY-02.03 | Razorpay checkout for S1 subscription only; no webhook; no signature verify on server | Port Razorpay to .NET 8; keys in config; POST /api/Payments/Webhook/Razorpay anonymous + signature verify; PaymentOrder table | Kill browser after pay → webhook still marks PAID; client callback alone never marks PAID | Not Started
318 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.3 | PAY-03 | Online consultation payment — patient pays by card, UPI, netbanking or wallet | PAY-03.01 | DB: ConsultPayment linked to PaymentOrder + PatientAppId — NOT PackageEntryDetail | New | Payments | §9 + §4 + §2.3 | Online consultation payment | Patient pays by card, UPI, netbanking or wallet / Pay the consultation fee at the time of booking / Pay the consultation fee inside the app | Public web + later Patient app | Database | No | Yes | Yes | No | No | No | P0 | S | — | Does not exist (only S1 SaaS) | CreateConsultOrder attached to PatientAppId; Razorpay Checkout; webhook sets PAID; do not overload PackageEntryDetail | Paid appointment unlocks tele queue rules; doctor sees PAID; Account sees ledger row (Phase 7) | Not Started
319 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.3 | PAY-03 | Online consultation payment — patient pays by card, UPI, netbanking or wallet | PAY-03.02 | API: CreateConsultOrder, Verify (optional), status by appointment; amount from ConsultFeeConfig | New | Payments | §9 + §4 + §2.3 | Online consultation payment | Patient pays by card, UPI, netbanking or wallet / Pay the consultation fee at the time of booking / Pay the consultation fee inside the app | Public web + later Patient app | API | No | Yes | Yes | Yes | No | No | P0 | M | PAY-03.01 | Does not exist (only S1 SaaS) | CreateConsultOrder attached to PatientAppId; Razorpay Checkout; webhook sets PAID; do not overload PackageEntryDetail | Paid appointment unlocks tele queue rules; doctor sees PAID; Account sees ledger row (Phase 7) | Not Started
320 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.3 | PAY-03 | Online consultation payment — patient pays by card, UPI, netbanking or wallet | PAY-03.03 | Public /book/pay/:bookingId using Razorpay pattern from Widgets.js but consult order API | New | Payments | §9 + §4 + §2.3 | Online consultation payment | Patient pays by card, UPI, netbanking or wallet / Pay the consultation fee at the time of booking / Pay the consultation fee inside the app | Public web + later Patient app | Web SPA | Yes | No | No | Yes | No | No | P0 | M | PAY-03.02 | Does not exist (only S1 SaaS) | CreateConsultOrder attached to PatientAppId; Razorpay Checkout; webhook sets PAID; do not overload PackageEntryDetail | Paid appointment unlocks tele queue rules; doctor sees PAID; Account sees ledger row (Phase 7) | Not Started
321 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.3 | PAY-03 | Online consultation payment — patient pays by card, UPI, netbanking or wallet | PAY-03.04 | Razorpay Checkout methods: card, UPI, netbanking, wallet as enabled on the account | New Integration | Payments | §9 + §4 + §2.3 | Online consultation payment | Patient pays by card, UPI, netbanking or wallet / Pay the consultation fee at the time of booking / Pay the consultation fee inside the app | Public web + later Patient app | Integration | No | Yes | No | Yes | No | Yes | P0 | M | PAY-03.03 | Does not exist (only S1 SaaS) | CreateConsultOrder attached to PatientAppId; Razorpay Checkout; webhook sets PAID; do not overload PackageEntryDetail | Paid appointment unlocks tele queue rules; doctor sees PAID; Account sees ledger row (Phase 7) | Not Started
322 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.3 | PAY-03 | Online consultation payment — patient pays by card, UPI, netbanking or wallet | PAY-03.05 | QA: success, failure, pending, double-click create order idempotent | Regression | Payments | §9 + §4 + §2.3 | Online consultation payment | Patient pays by card, UPI, netbanking or wallet / Pay the consultation fee at the time of booking / Pay the consultation fee inside the app | Public web + later Patient app | QA | Yes | Yes | No | Yes | No | No | P0 | S | PAY-03.04 | Does not exist (only S1 SaaS) | CreateConsultOrder attached to PatientAppId; Razorpay Checkout; webhook sets PAID; do not overload PackageEntryDetail | Paid appointment unlocks tele queue rules; doctor sees PAID; Account sees ledger row (Phase 7) | Not Started
323 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.4 | PAY-04 | Reception payment collection — cash, UPI, card or payment link with printed receipt | PAY-04.01 | Reuse PaymentOrder + ConsultPayment with Method=CASH/UPI_OFFLINE/CARD_POS/PAY_LINK | New | Payments | §9 + §6 | Reception payment collection | Cash, UPI, card or payment link with printed receipt | Reception Portal | Database | No | Yes | Yes | No | No | No | P0 | S | — | Does not exist | CollectAtReception writes ledger S3; print receipt; payment-link uses same Razorpay order as online | Cash still creates an immutable ledger row; receipt printable; status matches doctor list | Not Started
324 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.4 | PAY-04 | Reception payment collection — cash, UPI, card or payment link with printed receipt | PAY-04.02 | API: CollectAtReception; generate pay-link; print receipt payload | New | Payments | §9 + §6 | Reception payment collection | Cash, UPI, card or payment link with printed receipt | Reception Portal | API | No | Yes | Yes | Yes | No | No | P0 | M | PAY-04.01 | Does not exist | CollectAtReception writes ledger S3; print receipt; payment-link uses same Razorpay order as online | Cash still creates an immutable ledger row; receipt printable; status matches doctor list | Not Started
325 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.4 | PAY-04 | Reception payment collection — cash, UPI, card or payment link with printed receipt | PAY-04.03 | Reception collect modal: amount, method, GST placeholder, print receipt | New | Payments | §9 + §6 | Reception payment collection | Cash, UPI, card or payment link with printed receipt | Reception Portal | Web SPA | Yes | No | No | Yes | No | No | P0 | M | PAY-04.02 | Does not exist | CollectAtReception writes ledger S3; print receipt; payment-link uses same Razorpay order as online | Cash still creates an immutable ledger row; receipt printable; status matches doctor list | Not Started
326 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.4 | PAY-04 | Reception payment collection — cash, UPI, card or payment link with printed receipt | PAY-04.04 | Pay-link SMS/WhatsApp optional (Phase 12); must still ledger if notify fails | New Integration | Payments | §9 + §6 | Reception payment collection | Cash, UPI, card or payment link with printed receipt | Reception Portal | Integration | No | Yes | No | Yes | No | Yes | P0 | M | PAY-04.03 | Does not exist | CollectAtReception writes ledger S3; print receipt; payment-link uses same Razorpay order as online | Cash still creates an immutable ledger row; receipt printable; status matches doctor list | Not Started
327 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.4 | PAY-04 | Reception payment collection — cash, UPI, card or payment link with printed receipt | PAY-04.05 | QA: cash collection visible in clinic collection view after Phase 7; cannot mark PAID without this API | Regression | Payments | §9 + §6 | Reception payment collection | Cash, UPI, card or payment link with printed receipt | Reception Portal | QA | Yes | Yes | No | Yes | No | No | P0 | S | PAY-04.04 | Does not exist | CollectAtReception writes ledger S3; print receipt; payment-link uses same Razorpay order as online | Cash still creates an immutable ledger row; receipt printable; status matches doctor list | Not Started
328 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.5 | PAY-05 | Pay-at-clinic option — book now, pay at the clinic where the doctor allows it | PAY-05.01 | Honor PayAtClinicEnabled on public create-booking and checkout | New | Payments | §9 | Pay-at-clinic option | Book now, pay at the clinic where the doctor allows it | Public + Doctor + Reception | API | No | Yes | No | Yes | No | No | P1 | S | — | Does not exist | PayAtClinicEnabled on fee config; appointment PaymentStatus=PAY_AT_CLINIC; tele queue may still require PAID (policy) | If doctor disables pay-at-clinic, public checkout requires online pay | Not Started
329 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.5 | PAY-05 | Pay-at-clinic option — book now, pay at the clinic where the doctor allows it | PAY-05.02 | UI: public booking shows Pay at clinic vs Pay now; doctor list badge | New | Payments | §9 | Pay-at-clinic option | Book now, pay at the clinic where the doctor allows it | Public + Doctor + Reception | Web SPA | Yes | No | No | No | No | No | P1 | S | PAY-05.01 | Does not exist | PayAtClinicEnabled on fee config; appointment PaymentStatus=PAY_AT_CLINIC; tele queue may still require PAID (policy) | If doctor disables pay-at-clinic, public checkout requires online pay | Not Started
330 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.5 | PAY-05 | Pay-at-clinic option — book now, pay at the clinic where the doctor allows it | PAY-05.03 | QA: doctor flag off → pay-at-clinic hidden; reception can still collect | Regression | Payments | §9 | Pay-at-clinic option | Book now, pay at the clinic where the doctor allows it | Public + Doctor + Reception | QA | Yes | Yes | No | No | No | No | P1 | S | PAY-05.02 | Does not exist | PayAtClinicEnabled on fee config; appointment PaymentStatus=PAY_AT_CLINIC; tele queue may still require PAID (policy) | If doctor disables pay-at-clinic, public checkout requires online pay | Not Started
331 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.6 | PAY-06 | Doctor subscription payment — buy and renew subscription packages (complete remaining ~30%) | PAY-06.01 | Reuse PAY-02 webhook for S1 orders; link PackageEntryDetail as S1 only | Existing Improvement | Payments | §9 | Doctor subscription payment | Buy and renew subscription packages | Doctor Web Portal | API | No | Yes | No | No | No | Yes | P1 | M | — | Checkout works ~70%; no webhook, refund, invoice, GST, Account ledger | Same webhook spine; write S1 ledger; invoice; failed pay UX; PackageEntryDetail shape UNCHANGED | SaaS pay verified by webhook; doctor plan flags update without trusting client callback alone | Not Started
332 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.6 | PAY-06 | Doctor subscription payment — buy and renew subscription packages (complete remaining ~30%) | PAY-06.02 | Widgets.js: handle failed pay; show invoice when Phase 7 invoice exists | Existing Improvement | Payments | §9 | Doctor subscription payment | Buy and renew subscription packages | Doctor Web Portal | Web SPA | Yes | No | No | No | No | No | P1 | S | PAY-06.01 | Checkout works ~70%; no webhook, refund, invoice, GST, Account ledger | Same webhook spine; write S1 ledger; invoice; failed pay UX; PackageEntryDetail shape UNCHANGED | SaaS pay verified by webhook; doctor plan flags update without trusting client callback alone | Not Started
333 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.6 | PAY-06 | Doctor subscription payment — buy and renew subscription packages (complete remaining ~30%) | PAY-06.03 | QA: renew, fail, webhook delay, last-5-days warning still works | Regression | Payments | §9 | Doctor subscription payment | Buy and renew subscription packages | Doctor Web Portal | QA | Yes | Yes | No | No | No | No | P1 | S | PAY-06.02 | Checkout works ~70%; no webhook, refund, invoice, GST, Account ledger | Same webhook spine; write S1 ledger; invoice; failed pay UX; PackageEntryDetail shape UNCHANGED | SaaS pay verified by webhook; doctor plan flags update without trusting client callback alone | Not Started
334 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.7 | PAY-07 | Medicine payment — pay online or cash on delivery (API contract now; HomeoMeds Phase 14 implements orders) | PAY-07.01 | Extend PaymentOrder with Stream=CONSULT¦SUBSCRIPTION¦MEDICINE so Phase 14 can attach without schema rewrite | New | Payments | §9 + §12 | Medicine payment | Pay online or choose cash on delivery / Both options supported, with status tracking | Shared | Database | No | Yes | Yes | No | No | No | P1 | S | — | Does not exist | PaymentOrder.Stream=MEDICINE; COD_PENDING until pharmacy confirms collection; do not mix with consult money | A medicine PaymentOrder cannot be summarised as consult GMV | Not Started
335 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.7 | PAY-07 | Medicine payment — pay online or cash on delivery (API contract now; HomeoMeds Phase 14 implements orders) | PAY-07.02 | API stub: CreateMedicineOrder payment + COD status enum — implemented fully in Phase 14 | New | Payments | §9 + §12 | Medicine payment | Pay online or choose cash on delivery / Both options supported, with status tracking | Shared | API | No | Yes | No | Yes | No | No | P1 | S | PAY-07.01 | Does not exist | PaymentOrder.Stream=MEDICINE; COD_PENDING until pharmacy confirms collection; do not mix with consult money | A medicine PaymentOrder cannot be summarised as consult GMV | Not Started
336 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.7 | PAY-07 | Medicine payment — pay online or cash on delivery (API contract now; HomeoMeds Phase 14 implements orders) | PAY-07.03 | QA: stream isolation query (consult vs medicine totals differ) | Regression | Payments | §9 + §12 | Medicine payment | Pay online or choose cash on delivery / Both options supported, with status tracking | Shared | QA | No | Yes | No | No | No | No | P2 | S | PAY-07.02 | Does not exist | PaymentOrder.Stream=MEDICINE; COD_PENDING until pharmacy confirms collection; do not mix with consult money | A medicine PaymentOrder cannot be summarised as consult GMV | Not Started
337 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.8 | PAY-08 | Payment status everywhere — doctor, reception and patient all see the same payment status | PAY-08.01 | Single source: PaymentOrder/ConsultPayment → Appointment.PaymentStatus updated only by webhook or CollectAtReception | New | Payments | §9 | Payment status everywhere | Doctor, reception and patient all see the same payment status | All | API | No | Yes | No | No | No | No | P0 | M | — | No shared status | Single PaymentStatus on appointment/order; all DTOs read it; never a second client-only flag | Doctor list, reception queue, public booking confirmation, later patient app show identical status for the same id | Not Started
338 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.8 | PAY-08 | Payment status everywhere — doctor, reception and patient all see the same payment status | PAY-08.02 | Surface badges: doctor, reception; public confirmation page; patient app in Phase 16 consumes same API | New | Payments | §9 | Payment status everywhere | Doctor, reception and patient all see the same payment status | All | Web SPA | Yes | No | No | No | No | No | P0 | S | PAY-08.01 | No shared status | Single PaymentStatus on appointment/order; all DTOs read it; never a second client-only flag | Doctor list, reception queue, public booking confirmation, later patient app show identical status for the same id | Not Started
339 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.8 | PAY-08 | Payment status everywhere — doctor, reception and patient all see the same payment status | PAY-08.03 | QA: three roles, one appointment, same enum value | Regression | Payments | §9 | Payment status everywhere | Doctor, reception and patient all see the same payment status | All | QA | Yes | Yes | No | No | No | No | P0 | S | PAY-08.02 | No shared status | Single PaymentStatus on appointment/order; all DTOs read it; never a second client-only flag | Doctor list, reception queue, public booking confirmation, later patient app show identical status for the same id | Not Started
340 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.9 | PAY-09 | Refunds — processed and tracked against the original payment | PAY-09.01 | DB: Refund (PaymentOrderId, Amount, Reason, Status, GatewayRefundId, ByUserId, At) | New | Payments | §9 + §8 + §2.8 | Refunds | Processed and tracked against the original payment / Issue and track refunds | Account + Patient | Database | No | Yes | Yes | No | No | No | P0 | S | — | Does not exist | Refund entity against original PaymentOrder; Razorpay refund API; cancel-appointment hook; patient sees status | Refund cannot exceed captured amount; original payment remains visible; appointment status REFUNDED/partial as designed | Not Started
341 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.9 | PAY-09 | Refunds — processed and tracked against the original payment | PAY-09.02 | API: create refund (Account); webhook refund.processed; cancel-appointment policy engine (full/partial/none) | New | Payments | §9 + §8 + §2.8 | Refunds | Processed and tracked against the original payment / Issue and track refunds | Account + Patient | API | No | Yes | Yes | Yes | No | No | P0 | M | PAY-09.01 | Does not exist | Refund entity against original PaymentOrder; Razorpay refund API; cancel-appointment hook; patient sees status | Refund cannot exceed captured amount; original payment remains visible; appointment status REFUNDED/partial as designed | Not Started
342 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.9 | PAY-09 | Refunds — processed and tracked against the original payment | PAY-09.03 | Account refund screen in Phase 7; patient payments list in Phase 16 | New | Payments | §9 + §8 + §2.8 | Refunds | Processed and tracked against the original payment / Issue and track refunds | Account + Patient | Web SPA | Yes | No | No | Yes | No | No | P0 | M | PAY-09.02 | Does not exist | Refund entity against original PaymentOrder; Razorpay refund API; cancel-appointment hook; patient sees status | Refund cannot exceed captured amount; original payment remains visible; appointment status REFUNDED/partial as designed | Not Started
343 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.9 | PAY-09 | Refunds — processed and tracked against the original payment | PAY-09.04 | Razorpay refund API + webhook | New Integration | Payments | §9 + §8 + §2.8 | Refunds | Processed and tracked against the original payment / Issue and track refunds | Account + Patient | Integration | No | Yes | No | Yes | No | Yes | P0 | M | PAY-09.03 | Does not exist | Refund entity against original PaymentOrder; Razorpay refund API; cancel-appointment hook; patient sees status | Refund cannot exceed captured amount; original payment remains visible; appointment status REFUNDED/partial as designed | Not Started
344 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.9 | PAY-09 | Refunds — processed and tracked against the original payment | PAY-09.05 | QA: double refund blocked; cash collection refund is ledger-only per PRE-02 policy | Regression | Payments | §9 + §8 + §2.8 | Refunds | Processed and tracked against the original payment / Issue and track refunds | Account + Patient | QA | Yes | Yes | No | Yes | No | No | P0 | S | PAY-09.04 | Does not exist | Refund entity against original PaymentOrder; Razorpay refund API; cancel-appointment hook; patient sees status | Refund cannot exceed captured amount; original payment remains visible; appointment status REFUNDED/partial as designed | Not Started
345 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.10 | PAY-10 | Payment receipts & invoices — issued for every transaction | PAY-10.01 | DB: Invoice (Number, Series, Stream, PaymentOrderId, GstBreakup, PdfPath) | New | Payments | §9 + §8 | Payment receipts & invoices | Issued for every transaction / Invoice numbering and tax reporting | All | Database | No | Yes | Yes | No | No | No | P1 | S | — | No invoice entity | Invoice numbering series from PRE-02; PDF receipt; GST fields; email in Phase 12 | Every PAID consult/subscription/medicine has a retrievable receipt number | Not Started
346 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.10 | PAY-10 | Payment receipts & invoices — issued for every transaction | PAY-10.02 | API: get invoice by payment; generate PDF via SecureDocument | New | Payments | §9 + §8 | Payment receipts & invoices | Issued for every transaction / Invoice numbering and tax reporting | All | API | No | Yes | Yes | Yes | No | No | P1 | M | PAY-10.01 | No invoice entity | Invoice numbering series from PRE-02; PDF receipt; GST fields; email in Phase 12 | Every PAID consult/subscription/medicine has a retrievable receipt number | Not Started
347 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.10 | PAY-10 | Payment receipts & invoices — issued for every transaction | PAY-10.03 | Print/download on reception, doctor (subscription), later patient app | New | Payments | §9 + §8 | Payment receipts & invoices | Issued for every transaction / Invoice numbering and tax reporting | All | Web SPA | Yes | No | No | Yes | No | No | P1 | M | PAY-10.02 | No invoice entity | Invoice numbering series from PRE-02; PDF receipt; GST fields; email in Phase 12 | Every PAID consult/subscription/medicine has a retrievable receipt number | Not Started
348 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.10 | PAY-10 | Payment receipts & invoices — issued for every transaction | PAY-10.04 | QA: unique invoice numbers; cancelled invoice not reused | Regression | Payments | §9 + §8 | Payment receipts & invoices | Issued for every transaction / Invoice numbering and tax reporting | All | QA | Yes | Yes | No | Yes | No | No | P1 | S | PAY-10.03 | No invoice entity | Invoice numbering series from PRE-02; PDF receipt; GST fields; email in Phase 12 | Every PAID consult/subscription/medicine has a retrievable receipt number | Not Started
349 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.11 | PAY-11 | Complete payment audit trail — every transaction traceable end to end by Homeocentrum | PAY-11.01 | Persist raw webhook JSON; correlation id on Appointment and Ledger | New | Payments | §9 + §17 | Complete audit trail | Every transaction traceable end to end by Homeocentrum | Account | Database | No | Yes | Yes | No | No | No | P0 | S | — | No webhook store | PaymentEvent raw payloads + AuditEvent + OtpAudit for payouts; Account can reconstruct without Razorpay dashboard | Given a PatientAppId, Account retrieves order, events, invoice, refunds | Not Started
350 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.11 | PAY-11 | Complete payment audit trail — every transaction traceable end to end by Homeocentrum | PAY-11.02 | Account query API: trail by appointment / payment / doctor (Phase 7 UI) | New | Payments | §9 + §17 | Complete audit trail | Every transaction traceable end to end by Homeocentrum | Account | API | No | Yes | No | Yes | No | No | P0 | M | PAY-11.01 | No webhook store | PaymentEvent raw payloads + AuditEvent + OtpAudit for payouts; Account can reconstruct without Razorpay dashboard | Given a PatientAppId, Account retrieves order, events, invoice, refunds | Not Started
351 | 6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 6.11 | PAY-11 | Complete payment audit trail — every transaction traceable end to end by Homeocentrum | PAY-11.03 | QA: missing webhook still shows PENDING not PAID | Regression | Payments | §9 + §17 | Complete audit trail | Every transaction traceable end to end by Homeocentrum | Account | QA | No | Yes | No | No | No | No | P0 | S | PAY-11.02 | No webhook store | PaymentEvent raw payloads + AuditEvent + OtpAudit for payouts; Account can reconstruct without Razorpay dashboard | Given a PatientAppId, Account retrieves order, events, invoice, refunds | Not Started
352 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.1 | FIN-01 | Unified transaction ledger — every rupee that moves through the platform, in one record | FIN-01.01 | DB: LedgerEntry (Stream, Direction, Amount, Gst, Commission, EntityType, EntityId, PaymentOrderId, At) immutable | New | Account | §8 | Unified transaction ledger | Every rupee that moves through the platform, in one record | Account Portal | Database | No | Yes | Yes | No | No | No | P0 | S | — | Does not exist | Append-only LedgerEntry for S1–S7; filters; OTP audit link; Admin may view, Account owns movement | No money movement without a ledger row; rows are immutable | Not Started
353 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.1 | FIN-01 | Unified transaction ledger — every rupee that moves through the platform, in one record | FIN-01.02 | API: GET /account/ledger filters; export; write-only from payment/settlement services | New | Account | §8 | Unified transaction ledger | Every rupee that moves through the platform, in one record | Account Portal | API | No | Yes | Yes | Yes | No | No | P0 | M | FIN-01.01 | Does not exist | Append-only LedgerEntry for S1–S7; filters; OTP audit link; Admin may view, Account owns movement | No money movement without a ledger row; rows are immutable | Not Started
354 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.1 | FIN-01 | Unified transaction ledger — every rupee that moves through the platform, in one record | FIN-01.03 | /account/ledger UI — Account layout sidebar Finance | New | Account | §8 | Unified transaction ledger | Every rupee that moves through the platform, in one record | Account Portal | Web SPA | Yes | No | No | Yes | No | No | P0 | M | FIN-01.02 | Does not exist | Append-only LedgerEntry for S1–S7; filters; OTP audit link; Admin may view, Account owns movement | No money movement without a ledger row; rows are immutable | Not Started
355 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.1 | FIN-01 | Unified transaction ledger — every rupee that moves through the platform, in one record | FIN-01.04 | QA: consult pay writes S2; subscription writes S1; they never share one row | Regression | Account | §8 | Unified transaction ledger | Every rupee that moves through the platform, in one record | Account Portal | QA | Yes | Yes | No | Yes | No | No | P0 | S | FIN-01.03 | Does not exist | Append-only LedgerEntry for S1–S7; filters; OTP audit link; Admin may view, Account owns movement | No money movement without a ledger row; rows are immutable | Not Started
356 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.2 | FIN-02 | Consultation payment reconciliation — online payments and reception collections matched and verified | FIN-02.01 | Reuse ConsultPayment + Appointment; reconciliation query | New | Account | §8 + §7.2 + §16 | Consultation payment reconciliation | Online payments and reception collections matched and verified / Match every booking against every payment | Account + Admin | Database | No | Yes | Yes | No | No | No | P0 | S | — | Does not exist | Join booking ↔ payment ↔ appointment; KPI collected/pending/failed/refunded; CSV | Every paid booking has exactly one captured consult payment or an exception | Not Started
357 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.2 | FIN-02 | Consultation payment reconciliation — online payments and reception collections matched and verified | FIN-02.02 | GET Admin/Account reconciliation + aggregates | New | Account | §8 + §7.2 + §16 | Consultation payment reconciliation | Online payments and reception collections matched and verified / Match every booking against every payment | Account + Admin | API | No | Yes | Yes | Yes | No | No | P0 | M | FIN-02.01 | Does not exist | Join booking ↔ payment ↔ appointment; KPI collected/pending/failed/refunded; CSV | Every paid booking has exactly one captured consult payment or an exception | Not Started
358 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.2 | FIN-02 | Consultation payment reconciliation — online payments and reception collections matched and verified | FIN-02.03 | /account/consult-recon and /admin/consult-payments (same data, Account owns, Admin views) | New | Account | §8 + §7.2 + §16 | Consultation payment reconciliation | Online payments and reception collections matched and verified / Match every booking against every payment | Account + Admin | Web SPA | Yes | No | No | Yes | No | No | P0 | M | FIN-02.02 | Does not exist | Join booking ↔ payment ↔ appointment; KPI collected/pending/failed/refunded; CSV | Every paid booking has exactly one captured consult payment or an exception | Not Started
359 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.2 | FIN-02 | Consultation payment reconciliation — online payments and reception collections matched and verified | FIN-02.04 | QA: unmatched payment appears in exception queue not silent | Regression | Account | §8 + §7.2 + §16 | Consultation payment reconciliation | Online payments and reception collections matched and verified / Match every booking against every payment | Account + Admin | QA | Yes | Yes | No | Yes | No | No | P0 | S | FIN-02.03 | Does not exist | Join booking ↔ payment ↔ appointment; KPI collected/pending/failed/refunded; CSV | Every paid booking has exactly one captured consult payment or an exception | Not Started
360 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.3 | FIN-03 | Medicine ledger — medicine money tracked separately from consultation money | FIN-03.01 | LedgerEntry stream MEDICINE with SplitSeller/SplitPlatform/SplitDelivery | New | Account | §8 + §12 | Medicine ledger | Medicine money tracked separately from consultation money / Seller, platform and delivery shares recorded separately from consultation money | Account Portal | Database | No | Yes | Yes | No | No | No | P1 | S | — | Does not exist | /account/medicine-ledger; Stream=MEDICINE; seller/platform/delivery split columns; filled in Phase 14 | Medicine GMV query cannot include consult fees | Not Started
361 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.3 | FIN-03 | Medicine ledger — medicine money tracked separately from consultation money | FIN-03.02 | GET /account/medicine-ledger | New | Account | §8 + §12 | Medicine ledger | Medicine money tracked separately from consultation money / Seller, platform and delivery shares recorded separately from consultation money | Account Portal | API | No | Yes | Yes | Yes | No | No | P1 | M | FIN-03.01 | Does not exist | /account/medicine-ledger; Stream=MEDICINE; seller/platform/delivery split columns; filled in Phase 14 | Medicine GMV query cannot include consult fees | Not Started
362 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.3 | FIN-03 | Medicine ledger — medicine money tracked separately from consultation money | FIN-03.03 | /account/medicine-ledger UI (empty until HomeoMeds orders exist — still ship the screen) | New | Account | §8 + §12 | Medicine ledger | Medicine money tracked separately from consultation money / Seller, platform and delivery shares recorded separately from consultation money | Account Portal | Web SPA | Yes | No | No | Yes | No | No | P1 | M | FIN-03.02 | Does not exist | /account/medicine-ledger; Stream=MEDICINE; seller/platform/delivery split columns; filled in Phase 14 | Medicine GMV query cannot include consult fees | Not Started
363 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.3 | FIN-03 | Medicine ledger — medicine money tracked separately from consultation money | FIN-03.04 | QA: S2 consult row never appears on this screen | Regression | Account | §8 + §12 | Medicine ledger | Medicine money tracked separately from consultation money / Seller, platform and delivery shares recorded separately from consultation money | Account Portal | QA | Yes | Yes | No | Yes | No | No | P1 | S | FIN-03.03 | Does not exist | /account/medicine-ledger; Stream=MEDICINE; seller/platform/delivery split columns; filled in Phase 14 | Medicine GMV query cannot include consult fees | Not Started
364 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.4 | FIN-04 | Settlement runs — scheduled settlement of amounts due to doctors and pharmacies | FIN-04.01 | DB: SettlementRun, SettlementLine | New | Account | §8 + §16 | Settlement runs | Scheduled settlement of amounts due to doctors and pharmacies | Account Portal | Database | No | Yes | Yes | No | No | No | P0 | S | — | Does not exist | SettlementRun job T+N hold; net of commission/GST/refunds; pharmacies after Phase 14 | A settlement run is replayable and lists included transactions | Not Started
365 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.4 | FIN-04 | Settlement runs — scheduled settlement of amounts due to doctors and pharmacies | FIN-04.02 | API: create run (dry-run + commit); list; detail | New | Account | §8 + §16 | Settlement runs | Scheduled settlement of amounts due to doctors and pharmacies | Account Portal | API | No | Yes | Yes | Yes | No | No | P0 | M | FIN-04.01 | Does not exist | SettlementRun job T+N hold; net of commission/GST/refunds; pharmacies after Phase 14 | A settlement run is replayable and lists included transactions | Not Started
366 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.4 | FIN-04 | Settlement runs — scheduled settlement of amounts due to doctors and pharmacies | FIN-04.03 | /account/settlements | New | Account | §8 + §16 | Settlement runs | Scheduled settlement of amounts due to doctors and pharmacies | Account Portal | Web SPA | Yes | No | No | Yes | No | No | P0 | M | FIN-04.02 | Does not exist | SettlementRun job T+N hold; net of commission/GST/refunds; pharmacies after Phase 14 | A settlement run is replayable and lists included transactions | Not Started
367 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.4 | FIN-04 | Settlement runs — scheduled settlement of amounts due to doctors and pharmacies | FIN-04.04 | QA: hold days exclude too-new captures; refunds net out | Regression | Account | §8 + §16 | Settlement runs | Scheduled settlement of amounts due to doctors and pharmacies | Account Portal | QA | Yes | Yes | No | Yes | No | No | P0 | S | FIN-04.03 | Does not exist | SettlementRun job T+N hold; net of commission/GST/refunds; pharmacies after Phase 14 | A settlement run is replayable and lists included transactions | Not Started
368 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.5 | FIN-05 | Payout approval — payouts released only after OTP-verified approval | FIN-05.01 | DB: Payout (PayeeType Doctor¦Pharmacy, Amount, Status, SettlementRunId) | New | Account | §8 + §17 | Payout approval | Payouts released only after OTP-verified approval | Account Portal | Database | No | Yes | Yes | No | No | No | P0 | S | — | Does not exist | ApprovePayout requires SEC-07 OTP; Admin cannot approve; NEFT/file or gateway per PRE-01 | Payout without OTP fails; audit shows who approved | Not Started
369 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.5 | FIN-05 | Payout approval — payouts released only after OTP-verified approval | FIN-05.02 | API: ApprovePayout with OTP; reject | New | Account | §8 + §17 | Payout approval | Payouts released only after OTP-verified approval | Account Portal | API | No | Yes | Yes | Yes | No | No | P0 | M | FIN-05.01 | Does not exist | ApprovePayout requires SEC-07 OTP; Admin cannot approve; NEFT/file or gateway per PRE-01 | Payout without OTP fails; audit shows who approved | Not Started
370 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.5 | FIN-05 | Payout approval — payouts released only after OTP-verified approval | FIN-05.03 | /account/payouts | New | Account | §8 + §17 | Payout approval | Payouts released only after OTP-verified approval | Account Portal | Web SPA | Yes | No | No | Yes | No | No | P0 | M | FIN-05.02 | Does not exist | ApprovePayout requires SEC-07 OTP; Admin cannot approve; NEFT/file or gateway per PRE-01 | Payout without OTP fails; audit shows who approved | Not Started
371 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.5 | FIN-05 | Payout approval — payouts released only after OTP-verified approval | FIN-05.04 | Bank file / Razorpay payout adapter per PRE-01 | New Integration | Account | §8 + §17 | Payout approval | Payouts released only after OTP-verified approval | Account Portal | Integration | No | Yes | No | Yes | No | Yes | P0 | M | FIN-05.03 | Does not exist | ApprovePayout requires SEC-07 OTP; Admin cannot approve; NEFT/file or gateway per PRE-01 | Payout without OTP fails; audit shows who approved | Not Started
372 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.5 | FIN-05 | Payout approval — payouts released only after OTP-verified approval | FIN-05.05 | QA: Account role only; replay OTP; Admin 403 on approve | Regression | Account | §8 + §17 | Payout approval | Payouts released only after OTP-verified approval | Account Portal | QA | Yes | Yes | No | Yes | No | No | P0 | S | FIN-05.04 | Does not exist | ApprovePayout requires SEC-07 OTP; Admin cannot approve; NEFT/file or gateway per PRE-01 | Payout without OTP fails; audit shows who approved | Not Started
373 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.6 | FIN-06 | Refund processing — Account issues and tracks refunds (uses PAY-09) | FIN-06.01 | UI /account/refunds: original payment, amount, reason, status | New | Account | §8 | Refund processing | Issue and track refunds | Account Portal | Web SPA | Yes | No | No | Yes | No | No | P0 | M | — | Does not exist | /account/refunds UI on PAY-09 APIs; OTP if policy requires | Account can issue refund; patient status updates; ledger reverses | Not Started
374 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.6 | FIN-06 | Refund processing — Account issues and tracks refunds (uses PAY-09) | FIN-06.02 | Ledger reverse entries on successful refund | New | Account | §8 | Refund processing | Issue and track refunds | Account Portal | API | No | Yes | No | No | No | No | P0 | S | FIN-06.01 | Does not exist | /account/refunds UI on PAY-09 APIs; OTP if policy requires | Account can issue refund; patient status updates; ledger reverses | Not Started
375 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.6 | FIN-06 | Refund processing — Account issues and tracks refunds (uses PAY-09) | FIN-06.03 | QA: partial refund; full refund; cash-policy path | Regression | Account | §8 | Refund processing | Issue and track refunds | Account Portal | QA | Yes | Yes | No | No | No | No | P0 | S | FIN-06.02 | Does not exist | /account/refunds UI on PAY-09 APIs; OTP if policy requires | Account can issue refund; patient status updates; ledger reverses | Not Started
376 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.7 | FIN-07 | Payment exception handling — investigate and resolve every failed or disputed payment | FIN-07.01 | DB: PaymentException state machine | New | Account | §8 + §7.2 | Payment exception handling | Investigate and resolve every failed or disputed payment / Every failed or mismatched payment surfaced for action | Account + Admin | Database | No | Yes | Yes | No | No | No | P0 | S | — | Does not exist | Exception queue Failed/Partial/Webhook-mismatch/Refund-pending; retry/resolve with OTP on manual reconcile | Nothing failed is silent; resolve writes audit | Not Started
377 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.7 | FIN-07 | Payment exception handling — investigate and resolve every failed or disputed payment | FIN-07.02 | API: list/detail/retry/resolve; created by webhook mismatches | New | Account | §8 + §7.2 | Payment exception handling | Investigate and resolve every failed or disputed payment / Every failed or mismatched payment surfaced for action | Account + Admin | API | No | Yes | Yes | Yes | No | No | P0 | M | FIN-07.01 | Does not exist | Exception queue Failed/Partial/Webhook-mismatch/Refund-pending; retry/resolve with OTP on manual reconcile | Nothing failed is silent; resolve writes audit | Not Started
378 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.7 | FIN-07 | Payment exception handling — investigate and resolve every failed or disputed payment | FIN-07.03 | /account/exceptions and /admin/payment-exceptions (same queue) | New | Account | §8 + §7.2 | Payment exception handling | Investigate and resolve every failed or disputed payment / Every failed or mismatched payment surfaced for action | Account + Admin | Web SPA | Yes | No | No | Yes | No | No | P0 | M | FIN-07.02 | Does not exist | Exception queue Failed/Partial/Webhook-mismatch/Refund-pending; retry/resolve with OTP on manual reconcile | Nothing failed is silent; resolve writes audit | Not Started
379 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.7 | FIN-07 | Payment exception handling — investigate and resolve every failed or disputed payment | FIN-07.04 | QA: failed webhook creates exception; manual resolve requires Account role + OTP | Regression | Account | §8 + §7.2 | Payment exception handling | Investigate and resolve every failed or disputed payment / Every failed or mismatched payment surfaced for action | Account + Admin | QA | Yes | Yes | No | Yes | No | No | P0 | S | FIN-07.03 | Does not exist | Exception queue Failed/Partial/Webhook-mismatch/Refund-pending; retry/resolve with OTP on manual reconcile | Nothing failed is silent; resolve writes audit | Not Started
380 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.8 | FIN-08 | GST & invoice reports — invoice numbering and tax reporting | FIN-08.01 | Reuse Invoice; tax config table (GstRate, treatment flags) | New | Account | §8 + §16 | GST & invoice reports | Invoice numbering and tax reporting | Account Portal | Database | No | Yes | Yes | No | No | No | P1 | S | — | Does not exist | /account/tax export using Invoice table and PRE-02 GST treatment — configuration not hardcoded | Date-range GST report matches invoices issued | Not Started
381 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.8 | FIN-08 | GST & invoice reports — invoice numbering and tax reporting | FIN-08.02 | GET tax report + CSV | New | Account | §8 + §16 | GST & invoice reports | Invoice numbering and tax reporting | Account Portal | API | No | Yes | Yes | Yes | No | No | P1 | M | FIN-08.01 | Does not exist | /account/tax export using Invoice table and PRE-02 GST treatment — configuration not hardcoded | Date-range GST report matches invoices issued | Not Started
382 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.8 | FIN-08 | GST & invoice reports — invoice numbering and tax reporting | FIN-08.03 | /account/tax | New | Account | §8 + §16 | GST & invoice reports | Invoice numbering and tax reporting | Account Portal | Web SPA | Yes | No | No | Yes | No | No | P1 | M | FIN-08.02 | Does not exist | /account/tax export using Invoice table and PRE-02 GST treatment — configuration not hardcoded | Date-range GST report matches invoices issued | Not Started
383 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.8 | FIN-08 | GST & invoice reports — invoice numbering and tax reporting | FIN-08.04 | QA: rates come from config; changing rate does not rewrite old invoices | Regression | Account | §8 + §16 | GST & invoice reports | Invoice numbering and tax reporting | Account Portal | QA | Yes | Yes | No | Yes | No | No | P1 | S | FIN-08.03 | Does not exist | /account/tax export using Invoice table and PRE-02 GST treatment — configuration not hardcoded | Date-range GST report matches invoices issued | Not Started
384 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.9 | FIN-09 | Payee records — bank and KYC details for doctors and pharmacies | FIN-09.01 | DB: Payee (DoctorId/PharmacyId, Bank, PAN, KYC status) | New | Account | §8 | Payee records | Bank and KYC details for doctors and pharmacies | Account Portal | Database | No | Yes | Yes | No | No | No | P1 | S | — | Doctor bank fields added in DOC-10; no Account UI; no pharmacy | /account/payees; OTP on doctor KYC change (fraud); pharmacies after Phase 14 | Payout cannot run to a payee missing KYC | Not Started
385 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.9 | FIN-09 | Payee records — bank and KYC details for doctors and pharmacies | FIN-09.02 | API: list/update; OTP on bank change | New | Account | §8 | Payee records | Bank and KYC details for doctors and pharmacies | Account Portal | API | No | Yes | Yes | Yes | No | No | P1 | M | FIN-09.01 | Doctor bank fields added in DOC-10; no Account UI; no pharmacy | /account/payees; OTP on doctor KYC change (fraud); pharmacies after Phase 14 | Payout cannot run to a payee missing KYC | Not Started
386 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.9 | FIN-09 | Payee records — bank and KYC details for doctors and pharmacies | FIN-09.03 | /account/payees | New | Account | §8 | Payee records | Bank and KYC details for doctors and pharmacies | Account Portal | Web SPA | Yes | No | No | Yes | No | No | P1 | M | FIN-09.02 | Doctor bank fields added in DOC-10; no Account UI; no pharmacy | /account/payees; OTP on doctor KYC change (fraud); pharmacies after Phase 14 | Payout cannot run to a payee missing KYC | Not Started
387 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.9 | FIN-09 | Payee records — bank and KYC details for doctors and pharmacies | FIN-09.04 | QA: missing KYC blocks FIN-05 | Regression | Account | §8 | Payee records | Bank and KYC details for doctors and pharmacies | Account Portal | QA | Yes | Yes | No | Yes | No | No | P1 | S | FIN-09.03 | Doctor bank fields added in DOC-10; no Account UI; no pharmacy | /account/payees; OTP on doctor KYC change (fraud); pharmacies after Phase 14 | Payout cannot run to a payee missing KYC | Not Started
388 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.10 | FIN-10 | Clinic collection view — cash and UPI collected at reception, per clinic and per day | FIN-10.01 | Query ConsultPayment Method in CASH/UPI_OFFLINE grouped by DoctorId/date | New | Account | §8 | Clinic collection view | Cash and UPI collected at reception, per clinic and per day | Account Portal | Database | No | Yes | Yes | No | No | No | P1 | S | — | Does not exist | /account/clinic-collections from CollectAtReception rows; respect PRE-02 retain vs remit | Per clinic per day cash/UPI totals match reception receipts | Not Started
389 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.10 | FIN-10 | Clinic collection view — cash and UPI collected at reception, per clinic and per day | FIN-10.02 | GET clinic-collections | New | Account | §8 | Clinic collection view | Cash and UPI collected at reception, per clinic and per day | Account Portal | API | No | Yes | Yes | Yes | No | No | P1 | M | FIN-10.01 | Does not exist | /account/clinic-collections from CollectAtReception rows; respect PRE-02 retain vs remit | Per clinic per day cash/UPI totals match reception receipts | Not Started
390 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.10 | FIN-10 | Clinic collection view — cash and UPI collected at reception, per clinic and per day | FIN-10.03 | /account/clinic-collections | New | Account | §8 | Clinic collection view | Cash and UPI collected at reception, per clinic and per day | Account Portal | Web SPA | Yes | No | No | Yes | No | No | P1 | M | FIN-10.02 | Does not exist | /account/clinic-collections from CollectAtReception rows; respect PRE-02 retain vs remit | Per clinic per day cash/UPI totals match reception receipts | Not Started
391 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.10 | FIN-10 | Clinic collection view — cash and UPI collected at reception, per clinic and per day | FIN-10.04 | QA: online Razorpay consults do not appear as clinic cash | Regression | Account | §8 | Clinic collection view | Cash and UPI collected at reception, per clinic and per day | Account Portal | QA | Yes | Yes | No | Yes | No | No | P1 | S | FIN-10.03 | Does not exist | /account/clinic-collections from CollectAtReception rows; respect PRE-02 retain vs remit | Per clinic per day cash/UPI totals match reception receipts | Not Started
392 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.11 | FIN-11 | Separation of duties — Account controls money; Admin controls platform and clinical data | FIN-11.01 | Seed Account role menus: ledger, recon, medicine ledger, exceptions, settlements, payouts, refunds, tax, payees, clinic collections | New | Account | §8 | Separation of duties | The Account department controls money. Admin controls the platform and clinical data. Neither can perform the other’s role, which protects both. | Admin + Account | Configuration | Yes | Yes | Yes | No | No | No | P0 | M | — | Account role does not exist | Enforce in RBAC: Admin cannot ApprovePayout; Account cannot edit repertory/users’ clinical masters | Automated tests for both forbidden directions | Not Started
393 | 7 | Phase 7 — Account & finance department (PDF §8) | 7.11 | FIN-11 | Separation of duties — Account controls money; Admin controls platform and clinical data | FIN-11.02 | Negative tests: Admin POST ApprovePayout → 403; Account POST repertory section → 403 | Regression | Account | §8 | Separation of duties | The Account department controls money. Admin controls the platform and clinical data. Neither can perform the other’s role, which protects both. | Admin + Account | QA | No | Yes | No | Yes | No | No | P0 | S | FIN-11.01 | Account role does not exist | Enforce in RBAC: Admin cannot ApprovePayout; Account cannot edit repertory/users’ clinical masters | Automated tests for both forbidden directions | Not Started
394 | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.1 | TRU-01 | Doctor credentialing — doctors upload qualification and registration documents for review | TRU-01.01 | DB: DoctorVerification (Pending/Approved/Rejected/NeedsInfo), DoctorCredentialDocument | New | Trust | §13 + §7.2 | Doctor credentialing | Doctors upload qualification and registration documents for review | Doctor Web + Admin | Database | No | Yes | Yes | No | No | No | P0 | S | — | RegisterDoctor activates immediately; PassingUniversity/CertNo/QualificationId exist; no document store/queue | DoctorCredentialDocument + VerificationStatus Pending; do not auto-activate practice for public directory | New registrations sit in Pending with documents; existing doctors backfill per PRE-03 | Not Started
395 | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.1 | TRU-01 | Doctor credentialing — doctors upload qualification and registration documents for review | TRU-01.02 | API: upload documents; MyStatus; RegisterDoctor modified to VerificationStatus=Pending (not auto-practice) | New | Trust | §13 + §7.2 | Doctor credentialing | Doctors upload qualification and registration documents for review | Doctor Web + Admin | API | No | Yes | Yes | Yes | No | No | P0 | M | TRU-01.01 | RegisterDoctor activates immediately; PassingUniversity/CertNo/QualificationId exist; no document store/queue | DoctorCredentialDocument + VerificationStatus Pending; do not auto-activate practice for public directory | New registrations sit in Pending with documents; existing doctors backfill per PRE-03 | Not Started
396 | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.1 | TRU-01 | Doctor credentialing — doctors upload qualification and registration documents for review | TRU-01.03 | Doctor profile credentials tab + document upload | New | Trust | §13 + §7.2 | Doctor credentialing | Doctors upload qualification and registration documents for review | Doctor Web + Admin | Web SPA | Yes | No | No | Yes | No | No | P0 | M | TRU-01.02 | RegisterDoctor activates immediately; PassingUniversity/CertNo/QualificationId exist; no document store/queue | DoctorCredentialDocument + VerificationStatus Pending; do not auto-activate practice for public directory | New registrations sit in Pending with documents; existing doctors backfill per PRE-03 | Not Started
397 | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.1 | TRU-01 | Doctor credentialing — doctors upload qualification and registration documents for review | TRU-01.04 | QA: doctor without docs cannot appear in public directory (Phase 9) | Regression | Trust | §13 + §7.2 | Doctor credentialing | Doctors upload qualification and registration documents for review | Doctor Web + Admin | QA | Yes | Yes | No | Yes | No | No | P0 | S | TRU-01.03 | RegisterDoctor activates immediately; PassingUniversity/CertNo/QualificationId exist; no document store/queue | DoctorCredentialDocument + VerificationStatus Pending; do not auto-activate practice for public directory | New registrations sit in Pending with documents; existing doctors backfill per PRE-03 | Not Started
398 | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.2 | TRU-02 | Verification review — Admin approves, rejects or requests further information | TRU-02.01 | Reuse DoctorVerification | New | Trust | §13 + §7.2 | Verification review | Admin approves, rejects or requests more information before they can practise on the platform | Admin Portal | Database | No | Yes | Yes | No | No | No | P0 | S | — | Does not exist | /admin/doctor-credentialing list + detail; email notify doctor | Approve/reject/request-info all audited; doctor sees status | Not Started
399 | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.2 | TRU-02 | Verification review — Admin approves, rejects or requests further information | TRU-02.02 | API: Queue, {id}, Approve, Reject, RequestInfo | New | Trust | §13 + §7.2 | Verification review | Admin approves, rejects or requests more information before they can practise on the platform | Admin Portal | API | No | Yes | Yes | Yes | No | No | P0 | M | TRU-02.01 | Does not exist | /admin/doctor-credentialing list + detail; email notify doctor | Approve/reject/request-info all audited; doctor sees status | Not Started
400 | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.2 | TRU-02 | Verification review — Admin approves, rejects or requests further information | TRU-02.03 | /admin/doctor-credentialing and /:doctorId; verification column on users list | New | Trust | §13 + §7.2 | Verification review | Admin approves, rejects or requests more information before they can practise on the platform | Admin Portal | Web SPA | Yes | No | No | Yes | No | No | P0 | M | TRU-02.02 | Does not exist | /admin/doctor-credentialing list + detail; email notify doctor | Approve/reject/request-info all audited; doctor sees status | Not Started
401 | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.2 | TRU-02 | Verification review — Admin approves, rejects or requests further information | TRU-02.04 | Email notify (Phase 12 SMTP already used for activation) | New Integration | Trust | §13 + §7.2 | Verification review | Admin approves, rejects or requests more information before they can practise on the platform | Admin Portal | Integration | No | Yes | No | Yes | No | Yes | P0 | M | TRU-02.03 | Does not exist | /admin/doctor-credentialing list + detail; email notify doctor | Approve/reject/request-info all audited; doctor sees status | Not Started
402 | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.2 | TRU-02 | Verification review — Admin approves, rejects or requests further information | TRU-02.05 | QA: reject reason required; request-info reopens Pending | Regression | Trust | §13 + §7.2 | Verification review | Admin approves, rejects or requests more information before they can practise on the platform | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P0 | S | TRU-02.04 | Does not exist | /admin/doctor-credentialing list + detail; email notify doctor | Approve/reject/request-info all audited; doctor sees status | Not Started
403 | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.3 | TRU-03 | Verified badge — patients see which doctors have been verified | TRU-03.01 | Public doctor DTO includes isVerified | New | Trust | §13 + §2.2 | Verified badge / Credentials & verification | Patients see which doctors have been verified / Verified badge showing the doctor’s credentials are checked | Public + Patient app | API | No | Yes | No | Yes | No | No | P0 | S | — | Does not exist | Badge on public doctor card and profile from VerificationStatus=Approved | Unverified doctors never show a verified badge | Not Started
404 | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.3 | TRU-03 | Verified badge — patients see which doctors have been verified | TRU-03.02 | Badge component for website (Phase 9) and patient app (Phase 16) | New | Trust | §13 + §2.2 | Verified badge / Credentials & verification | Patients see which doctors have been verified / Verified badge showing the doctor’s credentials are checked | Public + Patient app | Web SPA | Yes | No | No | No | No | No | P0 | S | TRU-03.01 | Does not exist | Badge on public doctor card and profile from VerificationStatus=Approved | Unverified doctors never show a verified badge | Not Started
405 | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.3 | TRU-03 | Verified badge — patients see which doctors have been verified | TRU-03.03 | QA: pending doctor has no badge | Regression | Trust | §13 + §2.2 | Verified badge / Credentials & verification | Patients see which doctors have been verified / Verified badge showing the doctor’s credentials are checked | Public + Patient app | QA | Yes | No | No | No | No | No | P0 | S | TRU-03.02 | Does not exist | Badge on public doctor card and profile from VerificationStatus=Approved | Unverified doctors never show a verified badge | Not Started
406 | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.4 | TRU-04 | Practice gate — only verified doctors appear to patients and take paid consultations | TRU-04.01 | Public doctor list filter VerificationStatus=Approved | New | Trust | §13 | Practice gate | Only verified doctors appear to patients and take paid consultations | Public + Payments | API | No | Yes | No | Yes | No | No | P0 | S | — | Any activated doctor could theoretically be listed; no public list yet | Public search and CreateConsultOrder require Approved; own-clinic staff booking may still work per PRE-03 | Unverified doctor absent from /book; paid public consult blocked | Not Started
407 | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.4 | TRU-04 | Practice gate — only verified doctors appear to patients and take paid consultations | TRU-04.02 | CreateConsultOrder rejects unverified doctor for patient-originated bookings | New | Trust | §13 | Practice gate | Only verified doctors appear to patients and take paid consultations | Public + Payments | API | No | Yes | No | Yes | No | No | P0 | S | TRU-04.01 | Any activated doctor could theoretically be listed; no public list yet | Public search and CreateConsultOrder require Approved; own-clinic staff booking may still work per PRE-03 | Unverified doctor absent from /book; paid public consult blocked | Not Started
408 | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.4 | TRU-04 | Practice gate — only verified doctors appear to patients and take paid consultations | TRU-04.03 | QA: reception can still book own clinic patient for unverified doctor if PRE-03 allows | Regression | Trust | §13 | Practice gate | Only verified doctors appear to patients and take paid consultations | Public + Payments | QA | No | Yes | No | No | No | No | P0 | S | TRU-04.02 | Any activated doctor could theoretically be listed; no public list yet | Public search and CreateConsultOrder require Approved; own-clinic staff booking may still work per PRE-03 | Unverified doctor absent from /book; paid public consult blocked | Not Started
409 | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.5 | TRU-05 | Patient reviews — patients rate and review consultations | TRU-05.01 | DB: Review (PatientAppId, Rating, Text, Status, At) | New | Trust | §13 + §2.8 | Patient reviews / Write a review | Patients rate and review consultations / Rate and review the consultation | Patient + Public | Database | No | Yes | Yes | No | No | No | P1 | S | — | Does not exist | Review linked to PatientAppId; one review per visit; moderation flag optional | Review only after completed consult; doctor cannot write self-reviews | Not Started
410 | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.5 | TRU-05 | Patient reviews — patients rate and review consultations | TRU-05.02 | API: create (patient), list by doctor (public approved), doctor list own | New | Trust | §13 + §2.8 | Patient reviews / Write a review | Patients rate and review consultations / Rate and review the consultation | Patient + Public | API | No | Yes | Yes | Yes | No | No | P1 | M | TRU-05.01 | Does not exist | Review linked to PatientAppId; one review per visit; moderation flag optional | Review only after completed consult; doctor cannot write self-reviews | Not Started
411 | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.5 | TRU-05 | Patient reviews — patients rate and review consultations | TRU-05.03 | Public doctor profile reviews; patient app write flow Phase 16 | New | Trust | §13 + §2.8 | Patient reviews / Write a review | Patients rate and review consultations / Rate and review the consultation | Patient + Public | Web SPA | Yes | No | No | Yes | No | No | P1 | M | TRU-05.02 | Does not exist | Review linked to PatientAppId; one review per visit; moderation flag optional | Review only after completed consult; doctor cannot write self-reviews | Not Started
412 | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.5 | TRU-05 | Patient reviews — patients rate and review consultations | TRU-05.04 | QA: duplicate review blocked; incomplete visit blocked | Regression | Trust | §13 + §2.8 | Patient reviews / Write a review | Patients rate and review consultations / Rate and review the consultation | Patient + Public | QA | Yes | Yes | No | Yes | No | No | P1 | S | TRU-05.03 | Does not exist | Review linked to PatientAppId; one review per visit; moderation flag optional | Review only after completed consult; doctor cannot write self-reviews | Not Started
413 | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.6 | TRU-06 | Review appeal — doctors can appeal a review; patients manage reviews and raise an appeal | TRU-06.01 | DB: ReviewAppeal | New | Trust | §13 + §2.8 | Review appeal / My reviews & appeal | Doctors can appeal a review / Manage reviews and raise an appeal | Doctor + Patient + Admin | Database | No | Yes | Yes | No | No | No | P2 | S | — | Does not exist | Appeal entity; admin resolves; patient my-reviews list | Appealed review hidden or marked pending per policy; admin decision audited | Not Started
414 | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.6 | TRU-06 | Review appeal — doctors can appeal a review; patients manage reviews and raise an appeal | TRU-06.02 | API: doctor appeal; patient list/mine; admin resolve | New | Trust | §13 + §2.8 | Review appeal / My reviews & appeal | Doctors can appeal a review / Manage reviews and raise an appeal | Doctor + Patient + Admin | API | No | Yes | Yes | Yes | No | No | P2 | M | TRU-06.01 | Does not exist | Appeal entity; admin resolves; patient my-reviews list | Appealed review hidden or marked pending per policy; admin decision audited | Not Started
415 | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.6 | TRU-06 | Review appeal — doctors can appeal a review; patients manage reviews and raise an appeal | TRU-06.03 | Doctor dashboard my-reviews; admin queue | New | Trust | §13 + §2.8 | Review appeal / My reviews & appeal | Doctors can appeal a review / Manage reviews and raise an appeal | Doctor + Patient + Admin | Web SPA | Yes | No | No | Yes | No | No | P2 | M | TRU-06.02 | Does not exist | Appeal entity; admin resolves; patient my-reviews list | Appealed review hidden or marked pending per policy; admin decision audited | Not Started
416 | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.6 | TRU-06 | Review appeal — doctors can appeal a review; patients manage reviews and raise an appeal | TRU-06.04 | QA: only treating doctor of that visit can appeal | Regression | Trust | §13 + §2.8 | Review appeal / My reviews & appeal | Doctors can appeal a review / Manage reviews and raise an appeal | Doctor + Patient + Admin | QA | Yes | Yes | No | Yes | No | No | P2 | S | TRU-06.03 | Does not exist | Appeal entity; admin resolves; patient my-reviews list | Appealed review hidden or marked pending per policy; admin decision audited | Not Started
417 | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.7 | TRU-07 | Ranking transparency — patients are shown why doctors are ranked as they are | TRU-07.01 | Ranking config (weights) — not a black box hardcoded sort | New | Trust | §13 + §2.2 | Ranking transparency / Ranking explanation | Patients are shown why doctors are ranked as they are / Transparent explanation of why doctors appear in a given order | Public + Patient app | Database | No | Yes | Yes | No | No | No | P1 | S | — | Does not exist | Documented ranking factors (verified, availability, fee, reviews, experience) + explain API/UI | Each search result has an explain link that matches the sort order | Not Started
418 | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.7 | TRU-07 | Ranking transparency — patients are shown why doctors are ranked as they are | TRU-07.02 | GET doctors + GET ranking-explain/{doctorId} | New | Trust | §13 + §2.2 | Ranking transparency / Ranking explanation | Patients are shown why doctors are ranked as they are / Transparent explanation of why doctors appear in a given order | Public + Patient app | API | No | Yes | Yes | Yes | No | No | P1 | M | TRU-07.01 | Does not exist | Documented ranking factors (verified, availability, fee, reviews, experience) + explain API/UI | Each search result has an explain link that matches the sort order | Not Started
419 | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.7 | TRU-07 | Ranking transparency — patients are shown why doctors are ranked as they are | TRU-07.03 | Search results: Why this order? panel | New | Trust | §13 + §2.2 | Ranking transparency / Ranking explanation | Patients are shown why doctors are ranked as they are / Transparent explanation of why doctors appear in a given order | Public + Patient app | Web SPA | Yes | No | No | Yes | No | No | P1 | M | TRU-07.02 | Does not exist | Documented ranking factors (verified, availability, fee, reviews, experience) + explain API/UI | Each search result has an explain link that matches the sort order | Not Started
420 | 8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 8.7 | TRU-07 | Ranking transparency — patients are shown why doctors are ranked as they are | TRU-07.04 | QA: changing weights changes order and explanation together | Regression | Trust | §13 + §2.2 | Ranking transparency / Ranking explanation | Patients are shown why doctors are ranked as they are / Transparent explanation of why doctors appear in a given order | Public + Patient app | QA | Yes | Yes | No | Yes | No | No | P1 | S | TRU-07.03 | Does not exist | Documented ranking factors (verified, availability, fee, reviews, experience) + explain API/UI | Each search result has an explain link that matches the sort order | Not Started
421 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.1 | WEB-01 | Product home page — complete public website presenting the service | WEB-01.01 | No schema | Existing Improvement | Patient Website | §4 | Product home page | Complete public website presenting the service | Patient Website | Database | No | Yes | Yes | No | No | No | P1 | S | — | HomeoJobLanding ~50%; Velzon leftovers; CTAs incomplete for book/trust/apps | Book CTA, verified doctors, consult+SaaS pricing teaser, app download placeholders | Unauthenticated user can go Home → Book without calling the clinic | Not Started
422 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.1 | WEB-01 | Product home page — complete public website presenting the service | WEB-01.02 | Reuse public doctor/fee APIs when live | Existing Improvement | Patient Website | §4 | Product home page | Complete public website presenting the service | Patient Website | API | No | Yes | Yes | Yes | No | No | P1 | M | WEB-01.01 | HomeoJobLanding ~50%; Velzon leftovers; CTAs incomplete for book/trust/apps | Book CTA, verified doctors, consult+SaaS pricing teaser, app download placeholders | Unauthenticated user can go Home → Book without calling the clinic | Not Started
423 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.1 | WEB-01 | Product home page — complete public website presenting the service | WEB-01.03 | HomeLandingPage: book, verified doctors, pricing teaser, store badges; strip leftover job-board feel | Existing Improvement | Patient Website | §4 | Product home page | Complete public website presenting the service | Patient Website | Web SPA | Yes | No | No | Yes | No | No | P1 | M | WEB-01.02 | HomeoJobLanding ~50%; Velzon leftovers; CTAs incomplete for book/trust/apps | Book CTA, verified doctors, consult+SaaS pricing teaser, app download placeholders | Unauthenticated user can go Home → Book without calling the clinic | Not Started
424 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.1 | WEB-01 | Product home page — complete public website presenting the service | WEB-01.04 | QA: mobile viewport; deep link /book | Regression | Patient Website | §4 | Product home page | Complete public website presenting the service | Patient Website | QA | Yes | Yes | No | Yes | No | No | P1 | S | WEB-01.03 | HomeoJobLanding ~50%; Velzon leftovers; CTAs incomplete for book/trust/apps | Book CTA, verified doctors, consult+SaaS pricing teaser, app download placeholders | Unauthenticated user can go Home → Book without calling the clinic | Not Started
425 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.2 | WEB-02 | Consultation & subscription pricing — transparent pricing display | WEB-02.01 | Public doctor card shows in-clinic and tele fee | Existing Improvement | Patient Website | §4 | Consultation & subscription pricing | Transparent pricing display | Patient Website | Web SPA | Yes | No | No | Yes | No | No | P1 | S | — | SaaS package marketing /pricing exists; no consult fee display per doctor | Keep SaaS pricing; add consult fee on doctor cards from ConsultFeeConfig | Patient sees consult fee before booking; doctor SaaS pricing still shown for doctors buying plans | Not Started
426 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.2 | WEB-02 | Consultation & subscription pricing — transparent pricing display | WEB-02.02 | /pricing remains SaaS packages for doctors; label it clearly vs patient consult fees | Existing Improvement | Patient Website | §4 | Consultation & subscription pricing | Transparent pricing display | Patient Website | Web SPA | Yes | No | No | No | No | No | P1 | S | WEB-02.01 | SaaS package marketing /pricing exists; no consult fee display per doctor | Keep SaaS pricing; add consult fee on doctor cards from ConsultFeeConfig | Patient sees consult fee before booking; doctor SaaS pricing still shown for doctors buying plans | Not Started
427 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.2 | WEB-02 | Consultation & subscription pricing — transparent pricing display | WEB-02.03 | QA: fee matches checkout amount | Regression | Patient Website | §4 | Consultation & subscription pricing | Transparent pricing display | Patient Website | QA | Yes | No | No | No | No | No | P1 | S | WEB-02.02 | SaaS package marketing /pricing exists; no consult fee display per doctor | Keep SaaS pricing; add consult fee on doctor cards from ConsultFeeConfig | Patient sees consult fee before booking; doctor SaaS pricing still shown for doctors buying plans | Not Started
428 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.3 | WEB-03 | Doctor discovery — browse and search verified doctors | WEB-03.01 | Public doctor search indexes (from Doctor + verification + fee + schedule) | New | Patient Website | §4 + §2.2 | Doctor discovery | Browse and search verified doctors | Patient Website | Database | No | Yes | Yes | No | No | No | P0 | S | — | Does not exist as a patient product (marketing only) | /book search: name, condition, category; filters availability, fee, experience, language, location | Only verified doctors; ranking explanation available (TRU-07) | Not Started
429 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.3 | WEB-03 | Doctor discovery — browse and search verified doctors | WEB-03.02 | GET /api/Public/Doctors + filters + profile | New | Patient Website | §4 + §2.2 | Doctor discovery | Browse and search verified doctors | Patient Website | API | No | Yes | Yes | Yes | No | No | P0 | M | WEB-03.01 | Does not exist as a patient product (marketing only) | /book search: name, condition, category; filters availability, fee, experience, language, location | Only verified doctors; ranking explanation available (TRU-07) | Not Started
430 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.3 | WEB-03 | Doctor discovery — browse and search verified doctors | WEB-03.03 | /book list + filters + doctor profile page | New | Patient Website | §4 + §2.2 | Doctor discovery | Browse and search verified doctors | Patient Website | Web SPA | Yes | No | No | Yes | No | No | P0 | M | WEB-03.02 | Does not exist as a patient product (marketing only) | /book search: name, condition, category; filters availability, fee, experience, language, location | Only verified doctors; ranking explanation available (TRU-07) | Not Started
431 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.3 | WEB-03 | Doctor discovery — browse and search verified doctors | WEB-03.04 | QA: unverified excluded; filters combine; empty state | Regression | Patient Website | §4 + §2.2 | Doctor discovery | Browse and search verified doctors | Patient Website | QA | Yes | Yes | No | Yes | No | No | P0 | S | WEB-03.03 | Does not exist as a patient product (marketing only) | /book search: name, condition, category; filters availability, fee, experience, language, location | Only verified doctors; ranking explanation available (TRU-07) | Not Started
432 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.4 | WEB-04 | Self-service booking — book an appointment online without calling the clinic | WEB-04.01 | Reuse Patient + Appointment; BookingToken; PatientAuth OTP | New | Patient Website | §4 + §2.3 | Self-service booking | Book an appointment online without calling the clinic | Patient Website | Database | No | Yes | Yes | No | No | No | P0 | S | — | Staff-only appointments | Funnel /book/:id/slots → review+consent → create Patient+Appointment; OTP; rate-limit; respect schedule + unpaid hold policy PRE-03 | Slot no longer free after confirmed booking; consent written to ConsentRecord | Not Started
433 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.4 | WEB-04 | Self-service booking — book an appointment online without calling the clinic | WEB-04.02 | Public: Doctors/{id}/Slots, Create, {bookingToken}; POST PatientAuth RequestOtp/VerifyOtp | New | Patient Website | §4 + §2.3 | Self-service booking | Book an appointment online without calling the clinic | Patient Website | API | No | Yes | Yes | Yes | No | No | P0 | M | WEB-04.01 | Staff-only appointments | Funnel /book/:id/slots → review+consent → create Patient+Appointment; OTP; rate-limit; respect schedule + unpaid hold policy PRE-03 | Slot no longer free after confirmed booking; consent written to ConsentRecord | Not Started
434 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.4 | WEB-04 | Self-service booking — book an appointment online without calling the clinic | WEB-04.03 | /book/:doctorId/slots; /book/confirm; booking success | New | Patient Website | §4 + §2.3 | Self-service booking | Book an appointment online without calling the clinic | Patient Website | Web SPA | Yes | No | No | Yes | No | No | P0 | M | WEB-04.02 | Staff-only appointments | Funnel /book/:id/slots → review+consent → create Patient+Appointment; OTP; rate-limit; respect schedule + unpaid hold policy PRE-03 | Slot no longer free after confirmed booking; consent written to ConsentRecord | Not Started
435 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.4 | WEB-04 | Self-service booking — book an appointment online without calling the clinic | WEB-04.04 | QA: double-book same slot; hold expiry; OTP fail; consent required | Regression | Patient Website | §4 + §2.3 | Self-service booking | Book an appointment online without calling the clinic | Patient Website | QA | Yes | Yes | No | Yes | No | No | P0 | S | WEB-04.03 | Staff-only appointments | Funnel /book/:id/slots → review+consent → create Patient+Appointment; OTP; rate-limit; respect schedule + unpaid hold policy PRE-03 | Slot no longer free after confirmed booking; consent written to ConsentRecord | Not Started
436 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.5 | WEB-05 | Online consultation payment on website — pay the fee at the time of booking | WEB-05.01 | /book/pay/:bookingId + success/failure pages | New | Patient Website | §4 + §9 | Online consultation payment | Pay the consultation fee at the time of booking | Patient Website | Web SPA | Yes | No | No | Yes | No | Yes | P0 | M | — | Does not exist | Checkout uses PAY-03; success/fail pages; pay-at-clinic branch from PAY-05 | Closing the tab does not lose a captured payment (PAY-02) | Not Started
437 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.5 | WEB-05 | Online consultation payment on website — pay the fee at the time of booking | WEB-05.02 | QA: pay-at-clinic skip checkout; failed pay remains PENDING not PAID | Regression | Patient Website | §4 + §9 | Online consultation payment | Pay the consultation fee at the time of booking | Patient Website | QA | Yes | Yes | No | No | No | No | P0 | S | WEB-05.01 | Does not exist | Checkout uses PAY-03; success/fail pages; pay-at-clinic branch from PAY-05 | Closing the tab does not lose a captured payment (PAY-02) | Not Started
438 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.6 | WEB-06 | Contact & enquiry form — enquiries reach the admin team and are tracked | WEB-06.01 | Reuse EnquiryDetail; add Status/AssignedTo if missing | Existing Improvement | Patient Website | §4 + §15 | Contact & enquiry form | Enquiries reach the admin team and are tracked | Patient Website + Admin | Database | No | Yes | Yes | No | No | No | P1 | S | — | EnquiryDetail API exists; public form partial; admin inbox screen missing | Confirmation + enquiry id; /admin/enquiries inbox; optional convert to SupportTicket | Every website enquiry is visible to admin with status | Not Started
439 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.6 | WEB-06 | Contact & enquiry form — enquiries reach the admin team and are tracked | WEB-06.02 | Existing enquiry POST; admin list API if missing | Existing Improvement | Patient Website | §4 + §15 | Contact & enquiry form | Enquiries reach the admin team and are tracked | Patient Website + Admin | API | No | Yes | Yes | Yes | No | No | P1 | M | WEB-06.01 | EnquiryDetail API exists; public form partial; admin inbox screen missing | Confirmation + enquiry id; /admin/enquiries inbox; optional convert to SupportTicket | Every website enquiry is visible to admin with status | Not Started
440 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.6 | WEB-06 | Contact & enquiry form — enquiries reach the admin team and are tracked | WEB-06.03 | /contact confirmation; /admin/enquiries inbox (not Velzon mailbox) | Existing Improvement | Patient Website | §4 + §15 | Contact & enquiry form | Enquiries reach the admin team and are tracked | Patient Website + Admin | Web SPA | Yes | No | No | Yes | No | No | P1 | M | WEB-06.02 | EnquiryDetail API exists; public form partial; admin inbox screen missing | Confirmation + enquiry id; /admin/enquiries inbox; optional convert to SupportTicket | Every website enquiry is visible to admin with status | Not Started
441 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.6 | WEB-06 | Contact & enquiry form — enquiries reach the admin team and are tracked | WEB-06.04 | QA: guest submit → admin sees row | Regression | Patient Website | §4 + §15 | Contact & enquiry form | Enquiries reach the admin team and are tracked | Patient Website + Admin | QA | Yes | Yes | No | Yes | No | No | P1 | S | WEB-06.03 | EnquiryDetail API exists; public form partial; admin inbox screen missing | Confirmation + enquiry id; /admin/enquiries inbox; optional convert to SupportTicket | Every website enquiry is visible to admin with status | Not Started
442 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.7 | WEB-07 | Privacy policy — covering data protection, recording and pharmacy consent | WEB-07.01 | Replace /privacy content with signed legal copy; store PolicyVersion | Existing Improvement | Legal | §4 + §17 | Privacy policy | Covering data protection, recording and pharmacy consent | Patient Website | Web SPA | Yes | No | Yes | No | No | No | P0 | S | — | Privacy page partial; not DPDP/tele/pharmacy complete | Publish PRE-03 legal copy: DPDP, recording, pharmacy, data-rights, family/caregiver | Versioned policy; booking consent references this version | Not Started
443 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.7 | WEB-07 | Privacy policy — covering data protection, recording and pharmacy consent | WEB-07.02 | QA: booking consent shows policy version number | Regression | Legal | §4 + §17 | Privacy policy | Covering data protection, recording and pharmacy consent | Patient Website | QA | Yes | No | No | No | No | No | P0 | S | WEB-07.01 | Privacy page partial; not DPDP/tele/pharmacy complete | Publish PRE-03 legal copy: DPDP, recording, pharmacy, data-rights, family/caregiver | Versioned policy; booking consent references this version | Not Started
444 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.8 | WEB-08 | Terms of service — covering payments, refunds, telemedicine and medicine orders | WEB-08.01 | Replace /terms with signed copy; version stamp on booking/payment | Existing Improvement | Legal | §4 | Terms of service | Covering payments, refunds, telemedicine and medicine orders | Patient Website | Web SPA | Yes | No | Yes | No | No | No | P0 | S | — | Terms partial | Payments, refunds, telemedicine, HomeoMeds, codes-before-names | Checkout cannot complete without accepted terms version | Not Started
445 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.8 | WEB-08 | Terms of service — covering payments, refunds, telemedicine and medicine orders | WEB-08.02 | QA: terms checkbox required on confirm | Regression | Legal | §4 | Terms of service | Covering payments, refunds, telemedicine and medicine orders | Patient Website | QA | Yes | No | No | No | No | No | P0 | S | WEB-08.01 | Terms partial | Payments, refunds, telemedicine, HomeoMeds, codes-before-names | Checkout cannot complete without accepted terms version | Not Started
446 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.9 | WEB-09 | Doctor self-registration — doctors apply to join the platform online | WEB-09.01 | Documents via TRU-01 tables | Existing Improvement | Patient Website | §4 | Doctor self-registration | Doctors apply to join the platform online | Public | Database | No | Yes | Yes | No | No | No | P0 | S | — | RegisterDoctor ~90%; activates immediately; no document upload | Document upload; pending-verification message; TRU-01 status Pending | New doctor cannot take paid public consults until Approved | Not Started
447 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.9 | WEB-09 | Doctor self-registration — doctors apply to join the platform online | WEB-09.02 | RegisterDoctor sets Pending; does not auto-activate practice for directory | Existing Improvement | Patient Website | §4 | Doctor self-registration | Doctors apply to join the platform online | Public | API | No | Yes | Yes | Yes | No | No | P0 | M | WEB-09.01 | RegisterDoctor ~90%; activates immediately; no document upload | Document upload; pending-verification message; TRU-01 status Pending | New doctor cannot take paid public consults until Approved | Not Started
448 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.9 | WEB-09 | Doctor self-registration — doctors apply to join the platform online | WEB-09.03 | /register multipart docs; pending message; status page | Existing Improvement | Patient Website | §4 | Doctor self-registration | Doctors apply to join the platform online | Public | Web SPA | Yes | No | No | Yes | No | No | P0 | M | WEB-09.02 | RegisterDoctor ~90%; activates immediately; no document upload | Document upload; pending-verification message; TRU-01 status Pending | New doctor cannot take paid public consults until Approved | Not Started
449 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.9 | WEB-09 | Doctor self-registration — doctors apply to join the platform online | WEB-09.04 | QA: register → admin queue row | Regression | Patient Website | §4 | Doctor self-registration | Doctors apply to join the platform online | Public | QA | Yes | Yes | No | Yes | No | No | P0 | S | WEB-09.03 | RegisterDoctor ~90%; activates immediately; no document upload | Document upload; pending-verification message; TRU-01 status Pending | New doctor cannot take paid public consults until Approved | Not Started
450 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.10 | WEB-10 | Email activation — secure account activation by email link | WEB-10.01 | Activation token TTL if missing | Existing Improvement | Auth | §4 | Email activation | Secure account activation by email link | Public | Database | No | Yes | Yes | No | No | No | P1 | S | — | ActivateUser via /login?UserId= ~90%; align with verification; expiry/resend incomplete | Token expiry, resend, align with credentialing (activation ≠ verified practice) | Expired link fails; resend works; activated unverified still not in directory | Not Started
451 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.10 | WEB-10 | Email activation — secure account activation by email link | WEB-10.02 | Resend activation; do not treat activation as TRU-04 gate | Existing Improvement | Auth | §4 | Email activation | Secure account activation by email link | Public | API | No | Yes | Yes | Yes | No | No | P1 | M | WEB-10.01 | ActivateUser via /login?UserId= ~90%; align with verification; expiry/resend incomplete | Token expiry, resend, align with credentialing (activation ≠ verified practice) | Expired link fails; resend works; activated unverified still not in directory | Not Started
452 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.10 | WEB-10 | Email activation — secure account activation by email link | WEB-10.03 | Login activation query param UX + expiry copy | Existing Improvement | Auth | §4 | Email activation | Secure account activation by email link | Public | Web SPA | Yes | No | No | Yes | No | No | P1 | M | WEB-10.02 | ActivateUser via /login?UserId= ~90%; align with verification; expiry/resend incomplete | Token expiry, resend, align with credentialing (activation ≠ verified practice) | Expired link fails; resend works; activated unverified still not in directory | Not Started
453 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.10 | WEB-10 | Email activation — secure account activation by email link | WEB-10.04 | QA: used link, expired link, resend | Regression | Auth | §4 | Email activation | Secure account activation by email link | Public | QA | Yes | Yes | No | Yes | No | No | P1 | S | WEB-10.03 | ActivateUser via /login?UserId= ~90%; align with verification; expiry/resend incomplete | Token expiry, resend, align with credentialing (activation ≠ verified practice) | Expired link fails; resend works; activated unverified still not in directory | Not Started
454 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.11 | WEB-11 | Waitlist offer — get offered a slot when one is freed by a cancellation (patient website + later app) | WEB-11.01 | DB: BookingWaitlist | New | Booking | §2.3 | Waitlist offer | Get offered a slot when one is freed by a cancellation | Patient Website + App | Database | No | Yes | Yes | No | No | No | P2 | S | — | Cancel hook stub in Phase 4; no waitlist records | BookingWaitlist; on cancel, offer FIFO; timeout | Cancelled slot offered to waitlisted patient before returning to open search | Not Started
455 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.11 | WEB-11 | Waitlist offer — get offered a slot when one is freed by a cancellation (patient website + later app) | WEB-11.02 | API: join waitlist; worker on CancelAppointment | New | Booking | §2.3 | Waitlist offer | Get offered a slot when one is freed by a cancellation | Patient Website + App | API | No | Yes | Yes | Yes | No | No | P2 | M | WEB-11.01 | Cancel hook stub in Phase 4; no waitlist records | BookingWaitlist; on cancel, offer FIFO; timeout | Cancelled slot offered to waitlisted patient before returning to open search | Not Started
456 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.11 | WEB-11 | Waitlist offer — get offered a slot when one is freed by a cancellation (patient website + later app) | WEB-11.03 | Public waitlist CTA on full days | New | Booking | §2.3 | Waitlist offer | Get offered a slot when one is freed by a cancellation | Patient Website + App | Web SPA | Yes | No | No | Yes | No | No | P2 | M | WEB-11.02 | Cancel hook stub in Phase 4; no waitlist records | BookingWaitlist; on cancel, offer FIFO; timeout | Cancelled slot offered to waitlisted patient before returning to open search | Not Started
457 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.11 | WEB-11 | Waitlist offer — get offered a slot when one is freed by a cancellation (patient website + later app) | WEB-11.04 | Notify SMS/push when Phase 12 exists | New Integration | Booking | §2.3 | Waitlist offer | Get offered a slot when one is freed by a cancellation | Patient Website + App | Integration | No | Yes | No | Yes | No | Yes | P2 | M | WEB-11.03 | Cancel hook stub in Phase 4; no waitlist records | BookingWaitlist; on cancel, offer FIFO; timeout | Cancelled slot offered to waitlisted patient before returning to open search | Not Started
458 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.11 | WEB-11 | Waitlist offer — get offered a slot when one is freed by a cancellation (patient website + later app) | WEB-11.05 | QA: two waiters; first gets offer; expiry releases to second | Regression | Booking | §2.3 | Waitlist offer | Get offered a slot when one is freed by a cancellation | Patient Website + App | QA | Yes | Yes | No | Yes | No | No | P2 | S | WEB-11.04 | Cancel hook stub in Phase 4; no waitlist records | BookingWaitlist; on cancel, offer FIFO; timeout | Cancelled slot offered to waitlisted patient before returning to open search | Not Started
459 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.12 | WEB-12 | Health articles — educational content to build trust and engagement | WEB-12.01 | Public articles list/detail from existing blog/news APIs | Existing Improvement | Patient Website | §2.2 | Health articles | Educational content to build trust and engagement | Patient Website + App | Web SPA | Yes | No | No | Yes | No | No | P2 | S | — | Blog/news APIs on classic exist for marketing | Reuse blog/news as health articles on public site and later patient app; admin already has news/blog | Published articles appear on public site; draft does not | Not Started
460 | 9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 9.12 | WEB-12 | Health articles — educational content to build trust and engagement | WEB-12.02 | QA: unpublished hidden | Regression | Patient Website | §2.2 | Health articles | Educational content to build trust and engagement | Patient Website + App | QA | Yes | No | No | No | No | No | P2 | S | WEB-12.01 | Blog/news APIs on classic exist for marketing | Reuse blog/news as health articles on public site and later patient app; admin already has news/blog | Published articles appear on public site; draft does not | Not Started
461 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.1 | ERX-01 | Potency module — every remedy carries a defined potency from a managed list, no free text | ERX-01.01 | DB: PotencyMaster; PrescriptionRemedyDetail.PotencyId | New | eRx | §11 | Potency module | Every remedy carries a defined potency, selected from a managed list — no free text | Doctor Web + Admin | Database | No | Yes | Yes | No | No | No | P0 | S | — | Dose saved as empty free-text dose: '' | PotencyMaster CRUD; PotencyId on PrescriptionRemedyDetail; stop empty Dose | Cannot sign eRx with missing potency | Not Started
462 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.1 | ERX-01 | Potency module — every remedy carries a defined potency from a managed list, no free text | ERX-01.02 | API: potency DDL; extend SavePrescriptionDetail | New | eRx | §11 | Potency module | Every remedy carries a defined potency, selected from a managed list — no free text | Doctor Web + Admin | API | No | Yes | Yes | Yes | No | No | P0 | M | ERX-01.01 | Dose saved as empty free-text dose: '' | PotencyMaster CRUD; PotencyId on PrescriptionRemedyDetail; stop empty Dose | Cannot sign eRx with missing potency | Not Started
463 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.1 | ERX-01 | Potency module — every remedy carries a defined potency from a managed list, no free text | ERX-01.03 | Rx modal potency picker (6C, 30C, 200C, 1M…) | New | eRx | §11 | Potency module | Every remedy carries a defined potency, selected from a managed list — no free text | Doctor Web + Admin | Web SPA | Yes | No | No | Yes | No | No | P0 | M | ERX-01.02 | Dose saved as empty free-text dose: '' | PotencyMaster CRUD; PotencyId on PrescriptionRemedyDetail; stop empty Dose | Cannot sign eRx with missing potency | Not Started
464 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.1 | ERX-01 | Potency module — every remedy carries a defined potency from a managed list, no free text | ERX-01.04 | QA: free text potency rejected | Regression | eRx | §11 | Potency module | Every remedy carries a defined potency, selected from a managed list — no free text | Doctor Web + Admin | QA | Yes | Yes | No | Yes | No | No | P0 | S | ERX-01.03 | Dose saved as empty free-text dose: '' | PotencyMaster CRUD; PotencyId on PrescriptionRemedyDetail; stop empty Dose | Cannot sign eRx with missing potency | Not Started
465 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.2 | ERX-02 | Dosage details — frequency, duration and instructions recorded clearly | ERX-02.01 | DB: Frequency, Duration, Instructions on remedy line | New | eRx | §11 | Dosage details | Frequency, duration and instructions recorded clearly | Doctor Web Portal | Database | No | Yes | Yes | No | No | No | P0 | S | — | Unstructured/empty dose | Frequency, Duration, Instructions fields on each remedy line | Print/PDF shows frequency, duration, instructions | Not Started
466 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.2 | ERX-02 | Dosage details — frequency, duration and instructions recorded clearly | ERX-02.02 | Extend save/get Rx APIs | New | eRx | §11 | Dosage details | Frequency, duration and instructions recorded clearly | Doctor Web Portal | API | No | Yes | Yes | Yes | No | No | P0 | M | ERX-02.01 | Unstructured/empty dose | Frequency, Duration, Instructions fields on each remedy line | Print/PDF shows frequency, duration, instructions | Not Started
467 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.2 | ERX-02 | Dosage details — frequency, duration and instructions recorded clearly | ERX-02.03 | Rx row UI for the three fields | New | eRx | §11 | Dosage details | Frequency, duration and instructions recorded clearly | Doctor Web Portal | Web SPA | Yes | No | No | Yes | No | No | P0 | M | ERX-02.02 | Unstructured/empty dose | Frequency, Duration, Instructions fields on each remedy line | Print/PDF shows frequency, duration, instructions | Not Started
468 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.2 | ERX-02 | Dosage details — frequency, duration and instructions recorded clearly | ERX-02.04 | QA: all three persist and print | Regression | eRx | §11 | Dosage details | Frequency, duration and instructions recorded clearly | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P0 | S | ERX-02.03 | Unstructured/empty dose | Frequency, Duration, Instructions fields on each remedy line | Print/PDF shows frequency, duration, instructions | Not Started
469 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.3 | ERX-03 | Visit notes kept separate from the prescription — private clinical notes never appear on the prescription given to the patient or pharmacy | ERX-03.01 | Extend AppointmentHistoryNote with NoteType, IsErxExcluded | New | eRx | §11 + §5.3 | Visit notes kept separate from the prescription | The doctor’s private clinical notes never appear on the prescription given to the patient or pharmacy | Doctor Web Portal | Database | No | Yes | Yes | No | No | No | P0 | S | — | History notes mixed into Rx modal tabs | Visit Notes panel outside Rx; NoteType; IsErxExcluded; eRx print has remedies+labs only | Patient PDF and pharmacy payload contain zero private note text | Not Started
470 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.3 | ERX-03 | Visit notes kept separate from the prescription — private clinical notes never appear on the prescription given to the patient or pharmacy | ERX-03.02 | GET /api/Erx/ByAppointment/{id} returns snapshot without notes | New | eRx | §11 + §5.3 | Visit notes kept separate from the prescription | The doctor’s private clinical notes never appear on the prescription given to the patient or pharmacy | Doctor Web Portal | API | No | Yes | Yes | Yes | No | No | P0 | M | ERX-03.01 | History notes mixed into Rx modal tabs | Visit Notes panel outside Rx; NoteType; IsErxExcluded; eRx print has remedies+labs only | Patient PDF and pharmacy payload contain zero private note text | Not Started
471 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.3 | ERX-03 | Visit notes kept separate from the prescription — private clinical notes never appear on the prescription given to the patient or pharmacy | ERX-03.03 | Move History Notes out of Rx modal; note types Chief complaint / Follow-up / General | New | eRx | §11 + §5.3 | Visit notes kept separate from the prescription | The doctor’s private clinical notes never appear on the prescription given to the patient or pharmacy | Doctor Web Portal | Web SPA | Yes | No | No | Yes | No | No | P0 | M | ERX-03.02 | History notes mixed into Rx modal tabs | Visit Notes panel outside Rx; NoteType; IsErxExcluded; eRx print has remedies+labs only | Patient PDF and pharmacy payload contain zero private note text | Not Started
472 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.3 | ERX-03 | Visit notes kept separate from the prescription — private clinical notes never appear on the prescription given to the patient or pharmacy | ERX-03.04 | QA: print eRx vs export case PDF (doctor copy still has notes) | Regression | eRx | §11 + §5.3 | Visit notes kept separate from the prescription | The doctor’s private clinical notes never appear on the prescription given to the patient or pharmacy | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P0 | S | ERX-03.03 | History notes mixed into Rx modal tabs | Visit Notes panel outside Rx; NoteType; IsErxExcluded; eRx print has remedies+labs only | Patient PDF and pharmacy payload contain zero private note text | Not Started
473 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.4 | ERX-04 | Signed digital prescription — issued and locked once signed, so it cannot be altered afterwards | ERX-04.01 | DB: ErxSnapshot, ErxSnapshotItem (codes+names stored; patient API returns codes until pharmacy accept) | New | eRx | §11 + §2.5 + §5.3 | Signed digital prescription | Issued and locked once signed, so it cannot be altered afterwards / Official prescription issued by the doctor | Doctor Web | Database | No | Yes | Yes | No | No | No | P0 | S | — | SavePrescriptionDetail overwritable; no lock/sign | ErxSnapshot immutable on sign; subsequent edits create a new unsigned draft not a silent mutate | Signed snapshot hash stable; UI cannot edit locked lines | Not Started
474 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.4 | ERX-04 | Signed digital prescription — issued and locked once signed, so it cannot be altered afterwards | ERX-04.02 | API: SignErx; GetErx; reject mutate of signed snapshot | New | eRx | §11 + §2.5 + §5.3 | Signed digital prescription | Issued and locked once signed, so it cannot be altered afterwards / Official prescription issued by the doctor | Doctor Web | API | No | Yes | Yes | Yes | No | No | P0 | M | ERX-04.01 | SavePrescriptionDetail overwritable; no lock/sign | ErxSnapshot immutable on sign; subsequent edits create a new unsigned draft not a silent mutate | Signed snapshot hash stable; UI cannot edit locked lines | Not Started
475 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.4 | ERX-04 | Signed digital prescription — issued and locked once signed, so it cannot be altered afterwards | ERX-04.03 | Sign button; locked badge on board header | New | eRx | §11 + §2.5 + §5.3 | Signed digital prescription | Issued and locked once signed, so it cannot be altered afterwards / Official prescription issued by the doctor | Doctor Web | Web SPA | Yes | No | No | Yes | No | No | P0 | M | ERX-04.02 | SavePrescriptionDetail overwritable; no lock/sign | ErxSnapshot immutable on sign; subsequent edits create a new unsigned draft not a silent mutate | Signed snapshot hash stable; UI cannot edit locked lines | Not Started
476 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.4 | ERX-04 | Signed digital prescription — issued and locked once signed, so it cannot be altered afterwards | ERX-04.04 | QA: POST save after sign does not change snapshot | Regression | eRx | §11 + §2.5 + §5.3 | Signed digital prescription | Issued and locked once signed, so it cannot be altered afterwards / Official prescription issued by the doctor | Doctor Web | QA | Yes | Yes | No | Yes | No | No | P0 | S | ERX-04.03 | SavePrescriptionDetail overwritable; no lock/sign | ErxSnapshot immutable on sign; subsequent edits create a new unsigned draft not a silent mutate | Signed snapshot hash stable; UI cannot edit locked lines | Not Started
477 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.5 | ERX-05 | Prescription history — every prescription stored against the patient and visit | ERX-05.01 | GET history by patient; by appointment | New | eRx | §11 | Prescription history | Every prescription stored against the patient and visit | Doctor + Patient | API | No | Yes | No | Yes | No | No | P1 | S | — | Rx saved per appointment but no signed history product | List snapshots by PatientId; open past visit eRx | All signed eRx retrievable by patient and treating doctor | Not Started
478 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.5 | ERX-05 | Prescription history — every prescription stored against the patient and visit | ERX-05.02 | Doctor history panel lists signed eRx; patient timeline in Phase 16 | New | eRx | §11 | Prescription history | Every prescription stored against the patient and visit | Doctor + Patient | Web SPA | Yes | No | No | No | No | No | P1 | S | ERX-05.01 | Rx saved per appointment but no signed history product | List snapshots by PatientId; open past visit eRx | All signed eRx retrievable by patient and treating doctor | Not Started
479 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.5 | ERX-05 | Prescription history — every prescription stored against the patient and visit | ERX-05.03 | QA: another doctor 403 | Regression | eRx | §11 | Prescription history | Every prescription stored against the patient and visit | Doctor + Patient | QA | No | Yes | No | No | No | No | P1 | S | ERX-05.02 | Rx saved per appointment but no signed history product | List snapshots by PatientId; open past visit eRx | All signed eRx retrievable by patient and treating doctor | Not Started
480 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.6 | ERX-06 | Patient view of prescription in app — patient sees the prescription immediately (codes until pharmacy accept) | ERX-06.01 | Patient-authorised GET Erx; apply code protection ERX-08 | New | eRx | §11 + §2.5 | Patient view in app | Patient sees the prescription immediately in the app | Patient App + Website | API | No | Yes | No | Yes | No | No | P0 | S | — | No patient surface | Patient GET eRx by appointment; names redacted until Phase 14 accept; website optional view | Immediately after sign, patient API returns codes (or names if no HomeoMeds order required for in-clinic dispense policy — document) | Not Started
481 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.6 | ERX-06 | Patient view of prescription in app — patient sees the prescription immediately (codes until pharmacy accept) | ERX-06.02 | Web confirmation/records page can show the same payload before the app exists | New | eRx | §11 + §2.5 | Patient view in app | Patient sees the prescription immediately in the app | Patient App + Website | Web SPA | Yes | No | No | No | No | No | P0 | S | ERX-06.01 | No patient surface | Patient GET eRx by appointment; names redacted until Phase 14 accept; website optional view | Immediately after sign, patient API returns codes (or names if no HomeoMeds order required for in-clinic dispense policy — document) | Not Started
482 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.6 | ERX-06 | Patient view of prescription in app — patient sees the prescription immediately (codes until pharmacy accept) | ERX-06.03 | QA: doctor names vs patient codes differ until pharmacy OTP accept | Regression | eRx | §11 + §2.5 | Patient view in app | Patient sees the prescription immediately in the app | Patient App + Website | QA | No | Yes | No | No | No | No | P0 | S | ERX-06.02 | No patient surface | Patient GET eRx by appointment; names redacted until Phase 14 accept; website optional view | Immediately after sign, patient API returns codes (or names if no HomeoMeds order required for in-clinic dispense policy — document) | Not Started
483 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.7 | ERX-07 | Print & PDF — printable and downloadable prescription | ERX-07.01 | PDF renderer from ErxSnapshot; store via SEC-09 | New | eRx | §11 | Print & PDF | Printable and downloadable prescription | Doctor + Patient | API | No | Yes | No | Yes | No | No | P1 | M | — | No eRx PDF | Patient copy without notes; doctor copy may include letterhead; SecureDocument store | PDF matches signed snapshot; notes absent on patient copy | Not Started
484 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.7 | ERX-07 | Print & PDF — printable and downloadable prescription | ERX-07.02 | Print/Download on doctor board and later patient app | New | eRx | §11 | Print & PDF | Printable and downloadable prescription | Doctor + Patient | Web SPA | Yes | No | No | No | No | No | P1 | S | ERX-07.01 | No eRx PDF | Patient copy without notes; doctor copy may include letterhead; SecureDocument store | PDF matches signed snapshot; notes absent on patient copy | Not Started
485 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.7 | ERX-07 | Print & PDF — printable and downloadable prescription | ERX-07.03 | QA: notes leak test on patient PDF | Regression | eRx | §11 | Print & PDF | Printable and downloadable prescription | Doctor + Patient | QA | No | Yes | No | No | No | No | P1 | S | ERX-07.02 | No eRx PDF | Patient copy without notes; doctor copy may include letterhead; SecureDocument store | PDF matches signed snapshot; notes absent on patient copy | Not Started
486 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.8 | ERX-08 | Remedy code protection — patient sees remedy codes rather than names until a licensed pharmacy accepts the order | ERX-08.01 | Assign stable remedy codes on snapshot items | New | eRx | §11 | Remedy code protection | The patient sees remedy codes rather than remedy names until a licensed pharmacy accepts the order | Patient | API | No | Yes | Yes | No | No | No | P0 | M | — | Does not exist | Code map on snapshot items; patient serializer strips names; doctor always sees names | Patient JSON has no remedy name fields until PharmacyAccepted | Not Started
487 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.8 | ERX-08 | Remedy code protection — patient sees remedy codes rather than names until a licensed pharmacy accepts the order | ERX-08.02 | Patient serializer tests (contract tests) | Regression | eRx | §11 | Remedy code protection | The patient sees remedy codes rather than remedy names until a licensed pharmacy accepts the order | Patient | QA | No | Yes | No | No | No | No | P0 | S | ERX-08.01 | Does not exist | Code map on snapshot items; patient serializer strips names; doctor always sees names | Patient JSON has no remedy name fields until PharmacyAccepted | Not Started
488 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.9 | ERX-09 | Reveal on pharmacy acceptance — names and price revealed; payment QR or link generated (implemented with HomeoMeds; contract now) | ERX-09.01 | API contract: AcceptOrder(OTP) → reveal names; Quote → PayQR | New | eRx | §11 + §12 | Reveal on pharmacy acceptance | Once a pharmacy accepts and verifies by OTP, the remedy names and price are revealed and a payment QR or link is generated | Patient + Pharmacy | API | No | Yes | No | Yes | No | No | P0 | S | — | Does not exist | Flag PharmacyAccepted on order; patient GET starts returning names; CreateMedicine payment link; full UI in Phase 14 | Names appear only after OTP accept; QR/link only after quote | Not Started
489 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.9 | ERX-09 | Reveal on pharmacy acceptance — names and price revealed; payment QR or link generated (implemented with HomeoMeds; contract now) | ERX-09.02 | Implement fully with MED-* in Phase 14 — do not reveal names from doctor sign alone | New | eRx | §11 + §12 | Reveal on pharmacy acceptance | Once a pharmacy accepts and verifies by OTP, the remedy names and price are revealed and a payment QR or link is generated | Patient + Pharmacy | Architecture | No | Yes | No | No | No | No | P0 | S | ERX-09.01 | Does not exist | Flag PharmacyAccepted on order; patient GET starts returning names; CreateMedicine payment link; full UI in Phase 14 | Names appear only after OTP accept; QR/link only after quote | Not Started
490 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.10 | ERX-10 | Repeat prescription / refill — patient requests; doctor approves or rejects from the mobile app (inbox on web too) | ERX-10.01 | DB: RefillRequest | New | eRx | §11 + §3 + §2.7 | Repeat prescription / refill | Patient requests a refill; doctor approves or rejects from the mobile app | Patient + Doctor mobile + Doctor web | Database | No | Yes | Yes | No | No | No | P1 | S | — | Does not exist | RefillRequest against ErxSnapshot; doctor inbox; no case-taking on mobile | Reject/approve audited; approved refill creates a new order draft not an editable old snapshot | Not Started
491 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.10 | ERX-10 | Repeat prescription / refill — patient requests; doctor approves or rejects from the mobile app (inbox on web too) | ERX-10.02 | API: patient request; doctor inbox; approve/reject | New | eRx | §11 + §3 + §2.7 | Repeat prescription / refill | Patient requests a refill; doctor approves or rejects from the mobile app | Patient + Doctor mobile + Doctor web | API | No | Yes | Yes | Yes | No | No | P1 | M | ERX-10.01 | Does not exist | RefillRequest against ErxSnapshot; doctor inbox; no case-taking on mobile | Reject/approve audited; approved refill creates a new order draft not an editable old snapshot | Not Started
492 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.10 | ERX-10 | Repeat prescription / refill — patient requests; doctor approves or rejects from the mobile app (inbox on web too) | ERX-10.03 | Doctor web inbox; doctor app in Phase 17; patient app in Phase 16 | New | eRx | §11 + §3 + §2.7 | Repeat prescription / refill | Patient requests a refill; doctor approves or rejects from the mobile app | Patient + Doctor mobile + Doctor web | Web SPA | Yes | No | No | Yes | No | No | P1 | M | ERX-10.02 | Does not exist | RefillRequest against ErxSnapshot; doctor inbox; no case-taking on mobile | Reject/approve audited; approved refill creates a new order draft not an editable old snapshot | Not Started
493 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.10 | ERX-10 | Repeat prescription / refill — patient requests; doctor approves or rejects from the mobile app (inbox on web too) | ERX-10.04 | QA: cannot refill unsigned/locked-expired per policy | Regression | eRx | §11 + §3 + §2.7 | Repeat prescription / refill | Patient requests a refill; doctor approves or rejects from the mobile app | Patient + Doctor mobile + Doctor web | QA | Yes | Yes | No | Yes | No | No | P1 | S | ERX-10.03 | Does not exist | RefillRequest against ErxSnapshot; doctor inbox; no case-taking on mobile | Reject/approve audited; approved refill creates a new order draft not an editable old snapshot | Not Started
494 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.11 | ERX-11 | Lab orders alongside the prescription (keep existing labs on eRx snapshot) | ERX-11.01 | Copy lab orders into ErxSnapshot on sign | Existing Improvement | eRx | §11 | Lab orders | Tests ordered alongside the prescription | Doctor Web | API | No | Yes | No | No | No | No | P1 | S | — | Labs on Rx modal live | Include lab orders in signed snapshot; still not on private notes | Signed eRx PDF lists labs; results stay clinical-side | Not Started
495 | 10 | Phase 10 — Digital prescription / eRx (PDF §11) | 10.11 | ERX-11 | Lab orders alongside the prescription (keep existing labs on eRx snapshot) | ERX-11.02 | QA: labs visible on eRx; result values not required on patient copy | Regression | eRx | §11 | Lab orders | Tests ordered alongside the prescription | Doctor Web | QA | No | Yes | No | No | No | No | P1 | S | ERX-11.01 | Labs on Rx modal live | Include lab orders in signed snapshot; still not on private notes | Signed eRx PDF lists labs; results stay clinical-side | Not Started
496 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.1 | TEL-01 | Doctor availability — online or offline status and working hours | TEL-01.01 | DB: TeleAvailability (Online/Offline, LastHeartbeat) | New | Telemedicine | §10 + §3 | Doctor availability | Doctor sets online or offline status and working hours | Doctor Web + Doctor App | Database | No | Yes | Yes | No | No | No | P0 | S | — | E-CONSULT status + WhatsApp video stub only; no availability | TeleAvailability + heartbeat; working hours reuse daily schedule | Offline doctor cannot be offered instant consult | Not Started
497 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.1 | TEL-01 | Doctor availability — online or offline status and working hours | TEL-01.02 | API: SET/GET availability; public GET by doctorId | New | Telemedicine | §10 + §3 | Doctor availability | Doctor sets online or offline status and working hours | Doctor Web + Doctor App | API | No | Yes | Yes | Yes | No | No | P0 | M | TEL-01.01 | E-CONSULT status + WhatsApp video stub only; no availability | TeleAvailability + heartbeat; working hours reuse daily schedule | Offline doctor cannot be offered instant consult | Not Started
498 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.1 | TEL-01 | Doctor availability — online or offline status and working hours | TEL-01.03 | Dashboard toggle Online for teleconsult | New | Telemedicine | §10 + §3 | Doctor availability | Doctor sets online or offline status and working hours | Doctor Web + Doctor App | Web SPA | Yes | No | No | Yes | No | No | P0 | M | TEL-01.02 | E-CONSULT status + WhatsApp video stub only; no availability | TeleAvailability + heartbeat; working hours reuse daily schedule | Offline doctor cannot be offered instant consult | Not Started
499 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.1 | TEL-01 | Doctor availability — online or offline status and working hours | TEL-01.04 | QA: heartbeat expiry sets offline | Regression | Telemedicine | §10 + §3 | Doctor availability | Doctor sets online or offline status and working hours | Doctor Web + Doctor App | QA | Yes | Yes | No | Yes | No | No | P0 | S | TEL-01.03 | E-CONSULT status + WhatsApp video stub only; no availability | TeleAvailability + heartbeat; working hours reuse daily schedule | Offline doctor cannot be offered instant consult | Not Started
500 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.2 | TEL-02 | Telemedicine waiting queue — who is waiting, how long, whether they have paid | TEL-02.01 | Queue query on E-CONSULT + PaymentStatus + join time | New | Telemedicine | §10 + §3 | Telemedicine waiting queue | Doctor sees who is waiting, for how long, and whether they have paid | Doctor Web + App | Database | No | Yes | Yes | No | No | No | P0 | S | — | E-CONSULT list only | Queue by doctor + Online + paid/confirmed; wait time; Join | Unpaid patients do not join if policy requires PAID | Not Started
501 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.2 | TEL-02 | Telemedicine waiting queue — who is waiting, how long, whether they have paid | TEL-02.02 | GET Tele/Queue; POST start session | New | Telemedicine | §10 + §3 | Telemedicine waiting queue | Doctor sees who is waiting, for how long, and whether they have paid | Doctor Web + App | API | No | Yes | Yes | Yes | No | No | P0 | M | TEL-02.01 | E-CONSULT list only | Queue by doctor + Online + paid/confirmed; wait time; Join | Unpaid patients do not join if policy requires PAID | Not Started
502 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.2 | TEL-02 | Telemedicine waiting queue — who is waiting, how long, whether they have paid | TEL-02.03 | Dedicated Tele queue on dashboard (beyond E-CONSULT list) | New | Telemedicine | §10 + §3 | Telemedicine waiting queue | Doctor sees who is waiting, for how long, and whether they have paid | Doctor Web + App | Web SPA | Yes | No | No | Yes | No | No | P0 | M | TEL-02.02 | E-CONSULT list only | Queue by doctor + Online + paid/confirmed; wait time; Join | Unpaid patients do not join if policy requires PAID | Not Started
503 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.2 | TEL-02 | Telemedicine waiting queue — who is waiting, how long, whether they have paid | TEL-02.04 | SignalR/poll | New Integration | Telemedicine | §10 + §3 | Telemedicine waiting queue | Doctor sees who is waiting, for how long, and whether they have paid | Doctor Web + App | Integration | No | Yes | No | Yes | No | Yes | P0 | M | TEL-02.03 | E-CONSULT list only | Queue by doctor + Online + paid/confirmed; wait time; Join | Unpaid patients do not join if policy requires PAID | Not Started
504 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.2 | TEL-02 | Telemedicine waiting queue — who is waiting, how long, whether they have paid | TEL-02.05 | QA: wait time increases; paid badge matches PAY-08 | Regression | Telemedicine | §10 + §3 | Telemedicine waiting queue | Doctor sees who is waiting, for how long, and whether they have paid | Doctor Web + App | QA | Yes | Yes | No | Yes | No | No | P0 | S | TEL-02.04 | E-CONSULT list only | Queue by doctor + Online + paid/confirmed; wait time; Join | Unpaid patients do not join if policy requires PAID | Not Started
505 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.3 | TEL-03 | Video consultation in browser — doctor consults directly from the web portal | TEL-03.01 | DB: TeleSession (PatientAppId, RoomId, Status) | New | Telemedicine | §10 | Video consultation in browser | Doctor consults directly from the web portal | Doctor Web Portal | Database | No | Yes | Yes | No | No | No | P0 | S | — | SweetAlert WhatsApp stub | /teleconsult/:sessionId in-browser video; replace stub; vendor from PRE-03 | Doctor and patient in same room linked to PatientAppId | Not Started
506 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.3 | TEL-03 | Video consultation in browser — doctor consults directly from the web portal | TEL-03.02 | API: create/end session; vendor tokens | New | Telemedicine | §10 | Video consultation in browser | Doctor consults directly from the web portal | Doctor Web Portal | API | No | Yes | Yes | Yes | No | No | P0 | M | TEL-03.01 | SweetAlert WhatsApp stub | /teleconsult/:sessionId in-browser video; replace stub; vendor from PRE-03 | Doctor and patient in same room linked to PatientAppId | Not Started
507 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.3 | TEL-03 | Video consultation in browser — doctor consults directly from the web portal | TEL-03.03 | Full-page video room mute/end | New | Telemedicine | §10 | Video consultation in browser | Doctor consults directly from the web portal | Doctor Web Portal | Web SPA | Yes | No | No | Yes | No | No | P0 | M | TEL-03.02 | SweetAlert WhatsApp stub | /teleconsult/:sessionId in-browser video; replace stub; vendor from PRE-03 | Doctor and patient in same room linked to PatientAppId | Not Started
508 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.3 | TEL-03 | Video consultation in browser — doctor consults directly from the web portal | TEL-03.04 | Video SDK (Agora/Twilio/Daily) | New Integration | Telemedicine | §10 | Video consultation in browser | Doctor consults directly from the web portal | Doctor Web Portal | Integration | No | Yes | No | Yes | No | Yes | P0 | M | TEL-03.03 | SweetAlert WhatsApp stub | /teleconsult/:sessionId in-browser video; replace stub; vendor from PRE-03 | Doctor and patient in same room linked to PatientAppId | Not Started
509 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.3 | TEL-03 | Video consultation in browser — doctor consults directly from the web portal | TEL-03.05 | QA: replace WhatsApp alert; session ends write timestamp | Regression | Telemedicine | §10 | Video consultation in browser | Doctor consults directly from the web portal | Doctor Web Portal | QA | Yes | Yes | No | Yes | No | No | P0 | S | TEL-03.04 | SweetAlert WhatsApp stub | /teleconsult/:sessionId in-browser video; replace stub; vendor from PRE-03 | Doctor and patient in same room linked to PatientAppId | Not Started
510 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.4 | TEL-04 | Video consultation on mobile — doctor and patient both consult from the app (apps in 16–17; same session tokens) | TEL-04.01 | Token API must be client-agnostic (web and mobile) | New | Telemedicine | §10 + §2.4 + §3 | Video consultation on mobile | Doctor and patient both consult from the app / Face-to-face consultation from home / Start the video or audio consultation from the phone | Patient App + Doctor App | API | No | Yes | No | Yes | Yes | No | P0 | S | — | No apps | Same TeleSession tokens; mobile join implemented in Phases 16–17 against this API | Web doctor + mobile patient in one session | Not Started
511 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.4 | TEL-04 | Video consultation on mobile — doctor and patient both consult from the app (apps in 16–17; same session tokens) | TEL-04.02 | Contract tests: token TTL, room id = session id | Regression | Telemedicine | §10 + §2.4 + §3 | Video consultation on mobile | Doctor and patient both consult from the app / Face-to-face consultation from home / Start the video or audio consultation from the phone | Patient App + Doctor App | QA | No | Yes | No | No | No | No | P0 | S | TEL-04.01 | No apps | Same TeleSession tokens; mobile join implemented in Phases 16–17 against this API | Web doctor + mobile patient in one session | Not Started
512 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.5 | TEL-05 | Device check — camera, microphone and connection tested before joining | TEL-05.01 | Shared device-check component (web); mobile equivalent in Phase 16 | New | Telemedicine | §10 + §2.4 | Device check | Camera, microphone and connection tested before joining | Doctor Web + Patient | Web SPA | Yes | No | No | No | No | No | P1 | M | — | Does not exist | Pre-join device/network check UI; block join on hard fail with guidance | User sees camera/mic/network result before entering the room | Not Started
513 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.5 | TEL-05 | Device check — camera, microphone and connection tested before joining | TEL-05.02 | QA: deny camera permission → clear guidance | Regression | Telemedicine | §10 + §2.4 | Device check | Camera, microphone and connection tested before joining | Doctor Web + Patient | QA | Yes | No | No | No | No | No | P1 | S | TEL-05.01 | Does not exist | Pre-join device/network check UI; block join on hard fail with guidance | User sees camera/mic/network result before entering the room | Not Started
514 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.6 | TEL-06 | Waiting room — patient waits with live status until the doctor joins | TEL-06.01 | Session status events | New | Telemedicine | §10 + §2.4 | Waiting room | Patient waits with live status / Wait with live status until the doctor joins | Patient | Database | No | Yes | Yes | No | No | No | P1 | S | — | Does not exist | Waiting room page: position, doctor online, paid, estimated wait | Status updates without refresh (poll/SignalR) | Not Started
515 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.6 | TEL-06 | Waiting room — patient waits with live status until the doctor joins | TEL-06.02 | GET session status for patient token | New | Telemedicine | §10 + §2.4 | Waiting room | Patient waits with live status / Wait with live status until the doctor joins | Patient | API | No | Yes | Yes | Yes | No | No | P1 | M | TEL-06.01 | Does not exist | Waiting room page: position, doctor online, paid, estimated wait | Status updates without refresh (poll/SignalR) | Not Started
516 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.6 | TEL-06 | Waiting room — patient waits with live status until the doctor joins | TEL-06.03 | Waiting room UI on web (and app later) | New | Telemedicine | §10 + §2.4 | Waiting room | Patient waits with live status / Wait with live status until the doctor joins | Patient | Web SPA | Yes | No | No | Yes | No | No | P1 | M | TEL-06.02 | Does not exist | Waiting room page: position, doctor online, paid, estimated wait | Status updates without refresh (poll/SignalR) | Not Started
517 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.6 | TEL-06 | Waiting room — patient waits with live status until the doctor joins | TEL-06.04 | QA: doctor join transitions patient into the call | Regression | Telemedicine | §10 + §2.4 | Waiting room | Patient waits with live status / Wait with live status until the doctor joins | Patient | QA | Yes | Yes | No | Yes | No | No | P1 | S | TEL-06.03 | Does not exist | Waiting room page: position, doctor online, paid, estimated wait | Status updates without refresh (poll/SignalR) | Not Started
518 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.7 | TEL-07 | Recording consent — consent captured before the consultation; no recording without it | TEL-07.01 | Write ConsentRecord TeleRecording; TeleConsentLog events | New | Telemedicine | §10 + §2.4 + §17 | Recording consent | Consent captured before the consultation; no recording without it / Explicit consent requested before any recording | Patient + Doctor | Database | No | Yes | Yes | No | No | No | P0 | S | — | AudioCaseConsentLog only for audio case taking | ConsentRecord type TeleRecording; block record if declined; both sides see status | Recording pipeline cannot start if consent denied | Not Started
519 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.7 | TEL-07 | Recording consent — consent captured before the consultation; no recording without it | TEL-07.02 | API: capture consent; session.recordAllowed | New | Telemedicine | §10 + §2.4 + §17 | Recording consent | Consent captured before the consultation; no recording without it / Explicit consent requested before any recording | Patient + Doctor | API | No | Yes | Yes | Yes | No | No | P0 | M | TEL-07.01 | AudioCaseConsentLog only for audio case taking | ConsentRecord type TeleRecording; block record if declined; both sides see status | Recording pipeline cannot start if consent denied | Not Started
520 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.7 | TEL-07 | Recording consent — consent captured before the consultation; no recording without it | TEL-07.03 | Pre-join modal both sides | New | Telemedicine | §10 + §2.4 + §17 | Recording consent | Consent captured before the consultation; no recording without it / Explicit consent requested before any recording | Patient + Doctor | Web SPA | Yes | No | No | Yes | No | No | P0 | M | TEL-07.02 | AudioCaseConsentLog only for audio case taking | ConsentRecord type TeleRecording; block record if declined; both sides see status | Recording pipeline cannot start if consent denied | Not Started
521 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.7 | TEL-07 | Recording consent — consent captured before the consultation; no recording without it | TEL-07.04 | QA: decline → no record; audit row still written | Regression | Telemedicine | §10 + §2.4 + §17 | Recording consent | Consent captured before the consultation; no recording without it / Explicit consent requested before any recording | Patient + Doctor | QA | Yes | Yes | No | Yes | No | No | P0 | S | TEL-07.03 | AudioCaseConsentLog only for audio case taking | ConsentRecord type TeleRecording; block record if declined; both sides see status | Recording pipeline cannot start if consent denied | Not Started
522 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.8 | TEL-08 | Rejoin after dropped call — either side can rejoin the same consultation | TEL-08.01 | API: Rejoin issues token if Status=Active | New | Telemedicine | §10 + §2.4 | Rejoin after dropped call | Either side can rejoin the same consultation / Rejoin the same consultation if the connection drops | Doctor + Patient | API | No | Yes | No | Yes | No | No | P0 | S | — | Does not exist | Session Active until End; rejoin tokens; dashboard Rejoin | Drop and rejoin same PatientAppId session; End prevents rejoin | Not Started
523 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.8 | TEL-08 | Rejoin after dropped call — either side can rejoin the same consultation | TEL-08.02 | UI Rejoin on doctor dashboard and patient waiting/call fail | New | Telemedicine | §10 + §2.4 | Rejoin after dropped call | Either side can rejoin the same consultation / Rejoin the same consultation if the connection drops | Doctor + Patient | Web SPA | Yes | No | No | No | No | No | P0 | S | TEL-08.01 | Does not exist | Session Active until End; rejoin tokens; dashboard Rejoin | Drop and rejoin same PatientAppId session; End prevents rejoin | Not Started
524 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.8 | TEL-08 | Rejoin after dropped call — either side can rejoin the same consultation | TEL-08.03 | QA: after End, rejoin 409 | Regression | Telemedicine | §10 + §2.4 | Rejoin after dropped call | Either side can rejoin the same consultation / Rejoin the same consultation if the connection drops | Doctor + Patient | QA | No | Yes | No | No | No | No | P0 | S | TEL-08.02 | Does not exist | Session Active until End; rejoin tokens; dashboard Rejoin | Drop and rejoin same PatientAppId session; End prevents rejoin | Not Started
525 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.9 | TEL-09 | Join failure handling — clear fallback if the call cannot connect, with options to retry | TEL-09.01 | Standardise join error codes; log TeleSessionEvent | New | Telemedicine | §10 + §2.4 | Join failure handling / Fallback & join failure handling | Clear fallback if the call cannot connect / Clear guidance if the call fails, with options to retry | Doctor + Patient | API | No | Yes | No | No | No | No | P1 | S | — | Does not exist | Error codes; retry; support ticket deep link later; do not silently fail | Every join failure has a user-visible next action | Not Started
526 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.9 | TEL-09 | Join failure handling — clear fallback if the call cannot connect, with options to retry | TEL-09.02 | Fallback UI: retry, rejoin, contact support | New | Telemedicine | §10 + §2.4 | Join failure handling / Fallback & join failure handling | Clear fallback if the call cannot connect / Clear guidance if the call fails, with options to retry | Doctor + Patient | Web SPA | Yes | No | No | No | No | No | P1 | S | TEL-09.01 | Does not exist | Error codes; retry; support ticket deep link later; do not silently fail | Every join failure has a user-visible next action | Not Started
527 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.9 | TEL-09 | Join failure handling — clear fallback if the call cannot connect, with options to retry | TEL-09.03 | QA: simulated token fail | Regression | Telemedicine | §10 + §2.4 | Join failure handling / Fallback & join failure handling | Clear fallback if the call cannot connect / Clear guidance if the call fails, with options to retry | Doctor + Patient | QA | Yes | No | No | No | No | No | P1 | S | TEL-09.02 | Does not exist | Error codes; retry; support ticket deep link later; do not silently fail | Every join failure has a user-visible next action | Not Started
528 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.10 | TEL-10 | Case-linked chat — chat attached to the consultation record, not a loose message thread | TEL-10.01 | DB: TeleChatMessage (SessionId, PatientAppId, Body, At) | New | Telemedicine | §10 + §2.4 | Case-linked chat | Chat attached to the consultation record / Chat tied to the consultation, not a loose message thread | Doctor + Patient | Database | No | Yes | Yes | No | No | No | P1 | S | — | Does not exist | Messages keyed by TeleSession/PatientAppId; retained with the case | Chat not visible on a different appointment | Not Started
529 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.10 | TEL-10 | Case-linked chat — chat attached to the consultation record, not a loose message thread | TEL-10.02 | API: post/list; doctor and patient only | New | Telemedicine | §10 + §2.4 | Case-linked chat | Chat attached to the consultation record / Chat tied to the consultation, not a loose message thread | Doctor + Patient | API | No | Yes | Yes | Yes | No | No | P1 | M | TEL-10.01 | Does not exist | Messages keyed by TeleSession/PatientAppId; retained with the case | Chat not visible on a different appointment | Not Started
530 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.10 | TEL-10 | Case-linked chat — chat attached to the consultation record, not a loose message thread | TEL-10.03 | In-room chat panel | New | Telemedicine | §10 + §2.4 | Case-linked chat | Chat attached to the consultation record / Chat tied to the consultation, not a loose message thread | Doctor + Patient | Web SPA | Yes | No | No | Yes | No | No | P1 | M | TEL-10.02 | Does not exist | Messages keyed by TeleSession/PatientAppId; retained with the case | Chat not visible on a different appointment | Not Started
531 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.10 | TEL-10 | Case-linked chat — chat attached to the consultation record, not a loose message thread | TEL-10.04 | QA: IDOR other session 403 | Regression | Telemedicine | §10 + §2.4 | Case-linked chat | Chat attached to the consultation record / Chat tied to the consultation, not a loose message thread | Doctor + Patient | QA | Yes | Yes | No | Yes | No | No | P1 | S | TEL-10.03 | Does not exist | Messages keyed by TeleSession/PatientAppId; retained with the case | Chat not visible on a different appointment | Not Started
532 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.11 | TEL-11 | Consultation summary — issued to the patient at the end of the call | TEL-11.01 | DB: ConsultationSummary (PatientAppId, Text, At) | New | Telemedicine | §10 + §2.4 | Consultation summary | Issued to the patient at the end of the call / Written summary available immediately after the call | Patient + Doctor | Database | No | Yes | Yes | No | No | No | P1 | S | — | Does not exist | Doctor submits summary (not private notes); patient sees immediately; may share eRx id | Summary available without waiting for signed eRx if doctor issues it first | Not Started
533 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.11 | TEL-11 | Consultation summary — issued to the patient at the end of the call | TEL-11.02 | API: doctor PUT; patient GET | New | Telemedicine | §10 + §2.4 | Consultation summary | Issued to the patient at the end of the call / Written summary available immediately after the call | Patient + Doctor | API | No | Yes | Yes | Yes | No | No | P1 | M | TEL-11.01 | Does not exist | Doctor submits summary (not private notes); patient sees immediately; may share eRx id | Summary available without waiting for signed eRx if doctor issues it first | Not Started
534 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.11 | TEL-11 | Consultation summary — issued to the patient at the end of the call | TEL-11.03 | Post-call summary form; patient view | New | Telemedicine | §10 + §2.4 | Consultation summary | Issued to the patient at the end of the call / Written summary available immediately after the call | Patient + Doctor | Web SPA | Yes | No | No | Yes | No | No | P1 | M | TEL-11.02 | Does not exist | Doctor submits summary (not private notes); patient sees immediately; may share eRx id | Summary available without waiting for signed eRx if doctor issues it first | Not Started
535 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.11 | TEL-11 | Consultation summary — issued to the patient at the end of the call | TEL-11.04 | QA: private notes not copied into summary by default | Regression | Telemedicine | §10 + §2.4 | Consultation summary | Issued to the patient at the end of the call / Written summary available immediately after the call | Patient + Doctor | QA | Yes | Yes | No | Yes | No | No | P1 | S | TEL-11.03 | Does not exist | Doctor submits summary (not private notes); patient sees immediately; may share eRx id | Summary available without waiting for signed eRx if doctor issues it first | Not Started
536 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.12 | TEL-12 | Instant consultation — patient requests an immediate consultation with an available doctor | TEL-12.01 | DB: InstantConsultRequest, DoctorOffer | New | Telemedicine | §10 + §2.3 | Instant consultation / Instant consult request / Queue & doctor offer | Patient can request an immediate consultation with an available doctor / See position in queue and accept an offered doctor | Patient + Doctor | Database | No | Yes | Yes | No | No | No | P1 | S | — | Does not exist | Instant request pool; offer doctor; patient accepts; optional surcharge from fee config | Offline doctors never offered; patient can decline an offered doctor | Not Started
537 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.12 | TEL-12 | Instant consultation — patient requests an immediate consultation with an available doctor | TEL-12.02 | API: request, match, offer, accept, queue position | New | Telemedicine | §10 + §2.3 | Instant consultation / Instant consult request / Queue & doctor offer | Patient can request an immediate consultation with an available doctor / See position in queue and accept an offered doctor | Patient + Doctor | API | No | Yes | Yes | Yes | No | No | P1 | M | TEL-12.01 | Does not exist | Instant request pool; offer doctor; patient accepts; optional surcharge from fee config | Offline doctors never offered; patient can decline an offered doctor | Not Started
538 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.12 | TEL-12 | Instant consultation — patient requests an immediate consultation with an available doctor | TEL-12.03 | Patient instant CTA; doctor offer banner | New | Telemedicine | §10 + §2.3 | Instant consultation / Instant consult request / Queue & doctor offer | Patient can request an immediate consultation with an available doctor / See position in queue and accept an offered doctor | Patient + Doctor | Web SPA | Yes | No | No | Yes | No | No | P1 | M | TEL-12.02 | Does not exist | Instant request pool; offer doctor; patient accepts; optional surcharge from fee config | Offline doctors never offered; patient can decline an offered doctor | Not Started
539 | 11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 11.12 | TEL-12 | Instant consultation — patient requests an immediate consultation with an available doctor | TEL-12.04 | QA: no online doctor → empty state; surcharge on checkout | Regression | Telemedicine | §10 + §2.3 | Instant consultation / Instant consult request / Queue & doctor offer | Patient can request an immediate consultation with an available doctor / See position in queue and accept an offered doctor | Patient + Doctor | QA | Yes | Yes | No | Yes | No | No | P1 | S | TEL-12.03 | Does not exist | Instant request pool; offer doctor; patient accepts; optional surcharge from fee config | Offline doctors never offered; patient can decline an offered doctor | Not Started
540 | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.1 | COM-01 | SMS — appointment confirmation, registration confirmation, doctor-unavailable, OTP, reschedule and cancellation | COM-01.01 | DB: SmsTemplate, SmsMessageLog; Patient.SmsOptOut | New | Notifications | §14 | SMS | Appointment confirmation, registration confirmation, doctor-unavailable notice, OTP, reschedule and cancellation alerts | Shared | Database | No | Yes | Yes | No | No | No | P0 | S | — | No SMS provider; WhatsApp exists separately | SmsProvider + templates + DLT; event hooks; DND/opt-out on Patient | Each listed event can send SMS; notify failure does not roll back the business transaction | Not Started
541 | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.1 | COM-01 | SMS — appointment confirmation, registration confirmation, doctor-unavailable, OTP, reschedule and cancellation | COM-01.02 | API: Templates CRUD; Send; History; event worker | New | Notifications | §14 | SMS | Appointment confirmation, registration confirmation, doctor-unavailable notice, OTP, reschedule and cancellation alerts | Shared | API | No | Yes | Yes | Yes | No | No | P0 | M | COM-01.01 | No SMS provider; WhatsApp exists separately | SmsProvider + templates + DLT; event hooks; DND/opt-out on Patient | Each listed event can send SMS; notify failure does not roll back the business transaction | Not Started
542 | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.1 | COM-01 | SMS — appointment confirmation, registration confirmation, doctor-unavailable, OTP, reschedule and cancellation | COM-01.03 | Doctor /doctor/sms enable-per-event; admin templates | New | Notifications | §14 | SMS | Appointment confirmation, registration confirmation, doctor-unavailable notice, OTP, reschedule and cancellation alerts | Shared | Web SPA | Yes | No | No | Yes | No | No | P0 | M | COM-01.02 | No SMS provider; WhatsApp exists separately | SmsProvider + templates + DLT; event hooks; DND/opt-out on Patient | Each listed event can send SMS; notify failure does not roll back the business transaction | Not Started
543 | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.1 | COM-01 | SMS — appointment confirmation, registration confirmation, doctor-unavailable, OTP, reschedule and cancellation | COM-01.04 | MSG91/Twilio/etc. from PRE-03 | New Integration | Notifications | §14 | SMS | Appointment confirmation, registration confirmation, doctor-unavailable notice, OTP, reschedule and cancellation alerts | Shared | Integration | No | Yes | No | Yes | No | Yes | P0 | M | COM-01.03 | No SMS provider; WhatsApp exists separately | SmsProvider + templates + DLT; event hooks; DND/opt-out on Patient | Each listed event can send SMS; notify failure does not roll back the business transaction | Not Started
544 | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.1 | COM-01 | SMS — appointment confirmation, registration confirmation, doctor-unavailable, OTP, reschedule and cancellation | COM-01.05 | QA: OTP SMS; reschedule old→new; cancel; doctor unavailable; opt-out honored | Regression | Notifications | §14 | SMS | Appointment confirmation, registration confirmation, doctor-unavailable notice, OTP, reschedule and cancellation alerts | Shared | QA | Yes | Yes | No | Yes | No | No | P0 | S | COM-01.04 | No SMS provider; WhatsApp exists separately | SmsProvider + templates + DLT; event hooks; DND/opt-out on Patient | Each listed event can send SMS; notify failure does not roll back the business transaction | Not Started
545 | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.2 | COM-02 | WhatsApp — templates, offers, health tips and bulk messaging with delivery reports and opt-out (complete remaining ~50%) | COM-02.01 | Extend WhatsApp log if delivery receipts not stored | Existing Improvement | Notifications | §14 | WhatsApp | Templates, offers, health tips and bulk messaging to patients, with delivery reports and opt-out | Doctor Web | Database | No | Yes | Yes | No | No | No | P1 | S | — | Meta Cloud send/templates/campaigns live; bulk/opt-in/analytics incomplete | Finish bulk queue UX, template approval states, delivery reports, opt-out | Bulk campaign shows delivered/failed; opted-out patients excluded | Not Started
546 | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.2 | COM-02 | WhatsApp — templates, offers, health tips and bulk messaging with delivery reports and opt-out (complete remaining ~50%) | COM-02.02 | Finish bulk worker + receipt webhook | Existing Improvement | Notifications | §14 | WhatsApp | Templates, offers, health tips and bulk messaging to patients, with delivery reports and opt-out | Doctor Web | API | No | Yes | Yes | Yes | No | No | P1 | M | COM-02.01 | Meta Cloud send/templates/campaigns live; bulk/opt-in/analytics incomplete | Finish bulk queue UX, template approval states, delivery reports, opt-out | Bulk campaign shows delivered/failed; opted-out patients excluded | Not Started
547 | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.2 | COM-02 | WhatsApp — templates, offers, health tips and bulk messaging with delivery reports and opt-out (complete remaining ~50%) | COM-02.03 | WhatsAppModal: campaign status, failures, opt-out | Existing Improvement | Notifications | §14 | WhatsApp | Templates, offers, health tips and bulk messaging to patients, with delivery reports and opt-out | Doctor Web | Web SPA | Yes | No | No | Yes | No | No | P1 | M | COM-02.02 | Meta Cloud send/templates/campaigns live; bulk/opt-in/analytics incomplete | Finish bulk queue UX, template approval states, delivery reports, opt-out | Bulk campaign shows delivered/failed; opted-out patients excluded | Not Started
548 | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.2 | COM-02 | WhatsApp — templates, offers, health tips and bulk messaging with delivery reports and opt-out (complete remaining ~50%) | COM-02.04 | QA: opt-in required; template rejected state | Regression | Notifications | §14 | WhatsApp | Templates, offers, health tips and bulk messaging to patients, with delivery reports and opt-out | Doctor Web | QA | Yes | Yes | No | Yes | No | No | P1 | S | COM-02.03 | Meta Cloud send/templates/campaigns live; bulk/opt-in/analytics incomplete | Finish bulk queue UX, template approval states, delivery reports, opt-out | Bulk campaign shows delivered/failed; opted-out patients excluded | Not Started
549 | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.3 | COM-03 | Push notifications — booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests | COM-03.01 | DB: DeviceToken, AppNotification | New | Notifications | §14 + §2.9 + §3 | Push notifications | Booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests / Patient waiting, new booking, reschedule, cancellation, refill request, payment received | Patient App + Doctor App | Database | No | Yes | Yes | No | No | No | P0 | S | — | Does not exist | DeviceToken + FCM/APNs; event fan-out; apps register tokens in Phases 16–17 | Each listed event has a template; unregister on logout | Not Started
550 | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.3 | COM-03 | Push notifications — booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests | COM-03.02 | API: Devices/Register; Notifications/Send; list | New | Notifications | §14 + §2.9 + §3 | Push notifications | Booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests / Patient waiting, new booking, reschedule, cancellation, refill request, payment received | Patient App + Doctor App | API | No | Yes | Yes | Yes | No | No | P0 | M | COM-03.01 | Does not exist | DeviceToken + FCM/APNs; event fan-out; apps register tokens in Phases 16–17 | Each listed event has a template; unregister on logout | Not Started
551 | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.3 | COM-03 | Push notifications — booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests | COM-03.03 | Server event hooks (apps consume in 16–17) | New | Notifications | §14 + §2.9 + §3 | Push notifications | Booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests / Patient waiting, new booking, reschedule, cancellation, refill request, payment received | Patient App + Doctor App | Web SPA | Yes | No | No | Yes | No | No | P0 | M | COM-03.02 | Does not exist | DeviceToken + FCM/APNs; event fan-out; apps register tokens in Phases 16–17 | Each listed event has a template; unregister on logout | Not Started
552 | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.3 | COM-03 | Push notifications — booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests | COM-03.04 | FCM + APNs | New Integration | Notifications | §14 + §2.9 + §3 | Push notifications | Booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests / Patient waiting, new booking, reschedule, cancellation, refill request, payment received | Patient App + Doctor App | Integration | No | Yes | No | Yes | No | Yes | P0 | M | COM-03.03 | Does not exist | DeviceToken + FCM/APNs; event fan-out; apps register tokens in Phases 16–17 | Each listed event has a template; unregister on logout | Not Started
553 | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.3 | COM-03 | Push notifications — booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests | COM-03.05 | QA: doctor and patient payloads isolated; token refresh | Regression | Notifications | §14 + §2.9 + §3 | Push notifications | Booking confirmed, payment received, doctor ready, prescription issued, order updates, refill requests / Patient waiting, new booking, reschedule, cancellation, refill request, payment received | Patient App + Doctor App | QA | Yes | Yes | No | Yes | No | No | P0 | S | COM-03.04 | Does not exist | DeviceToken + FCM/APNs; event fan-out; apps register tokens in Phases 16–17 | Each listed event has a template; unregister on logout | Not Started
554 | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.4 | COM-04 | Email — registration, activation, password reset, invoices and receipts | COM-04.01 | EmailMessageLog if missing | Existing Improvement | Notifications | §14 | Email | Registration, activation, password reset, invoices and receipts | Shared | Database | No | Yes | Yes | No | No | No | P1 | S | — | SMTP used for activation/forgot (plaintext issue fixed in Phase 0); no invoice email | Template emails for listed events; invoice PDF attach via SEC-09 | Each listed event has an email; bounce logged | Not Started
555 | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.4 | COM-04 | Email — registration, activation, password reset, invoices and receipts | COM-04.02 | Send invoice/receipt email on PAID; keep activation/reset | Existing Improvement | Notifications | §14 | Email | Registration, activation, password reset, invoices and receipts | Shared | API | No | Yes | Yes | Yes | No | No | P1 | M | COM-04.01 | SMTP used for activation/forgot (plaintext issue fixed in Phase 0); no invoice email | Template emails for listed events; invoice PDF attach via SEC-09 | Each listed event has an email; bounce logged | Not Started
556 | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.4 | COM-04 | Email — registration, activation, password reset, invoices and receipts | COM-04.03 | No new public page — transactional only | Existing Improvement | Notifications | §14 | Email | Registration, activation, password reset, invoices and receipts | Shared | Web SPA | Yes | No | No | Yes | No | No | P1 | M | COM-04.02 | SMTP used for activation/forgot (plaintext issue fixed in Phase 0); no invoice email | Template emails for listed events; invoice PDF attach via SEC-09 | Each listed event has an email; bounce logged | Not Started
557 | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.4 | COM-04 | Email — registration, activation, password reset, invoices and receipts | COM-04.04 | QA: reset still has no plaintext password; invoice attached | Regression | Notifications | §14 | Email | Registration, activation, password reset, invoices and receipts | Shared | QA | Yes | Yes | No | Yes | No | No | P1 | S | COM-04.03 | SMTP used for activation/forgot (plaintext issue fixed in Phase 0); no invoice email | Template emails for listed events; invoice PDF attach via SEC-09 | Each listed event has an email; bounce logged | Not Started
558 | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.5 | COM-05 | In-app notification centre — all alerts collected in one place for patients and doctors | COM-05.01 | Reuse AppNotification | New | Notifications | §14 + §2.8 | In-app notification centre / Notifications centre | All alerts collected in one place for patients and doctors / All alerts in one place | Patient App + Doctor Web/App | Database | No | Yes | Yes | No | No | No | P1 | S | — | Does not exist (Velzon notification demo is not product) | AppNotification inbox; mark read; do not use Velzon demo notifications | Same events as push appear in-app if push is denied | Not Started
559 | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.5 | COM-05 | In-app notification centre — all alerts collected in one place for patients and doctors | COM-05.02 | GET/PATCH notifications | New | Notifications | §14 + §2.8 | In-app notification centre / Notifications centre | All alerts collected in one place for patients and doctors / All alerts in one place | Patient App + Doctor Web/App | API | No | Yes | Yes | Yes | No | No | P1 | M | COM-05.01 | Does not exist (Velzon notification demo is not product) | AppNotification inbox; mark read; do not use Velzon demo notifications | Same events as push appear in-app if push is denied | Not Started
560 | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.5 | COM-05 | In-app notification centre — all alerts collected in one place for patients and doctors | COM-05.03 | Doctor web bell; patient/doctor app centres in 16–17 | New | Notifications | §14 + §2.8 | In-app notification centre / Notifications centre | All alerts collected in one place for patients and doctors / All alerts in one place | Patient App + Doctor Web/App | Web SPA | Yes | No | No | Yes | No | No | P1 | M | COM-05.02 | Does not exist (Velzon notification demo is not product) | AppNotification inbox; mark read; do not use Velzon demo notifications | Same events as push appear in-app if push is denied | Not Started
561 | 12 | Phase 12 — Communication & notifications (PDF §14) | 12.5 | COM-05 | In-app notification centre — all alerts collected in one place for patients and doctors | COM-05.04 | QA: mark read; empty state; not Velzon demo route | Regression | Notifications | §14 + §2.8 | In-app notification centre / Notifications centre | All alerts collected in one place for patients and doctors / All alerts in one place | Patient App + Doctor Web/App | QA | Yes | Yes | No | Yes | No | No | P1 | S | COM-05.03 | Does not exist (Velzon notification demo is not product) | AppNotification inbox; mark read; do not use Velzon demo notifications | Same events as push appear in-app if push is denied | Not Started
562 | 13 | Phase 13 — Support & help desk (PDF §15) | 13.1 | SUP-01 | Patient support tickets — patients raise issues from the app and track them | SUP-01.01 | DB: SupportTicket, SupportTicketMessage, SupportTicketAttachment | New | Support | §15 + §2.9 | Patient support tickets / Help centre & support tickets | Patients raise issues from the app and track them to resolution | Patient App + Admin | Database | No | Yes | Yes | No | No | No | P1 | S | — | Does not exist; EnquiryDetail is not tickets; Velzon tickets demo ignore | SupportTicket reporter=Patient; status track; not Enquiry, not Velzon /apps-tickets-* | Patient sees status changes; cannot see other patients’ tickets | Not Started
563 | 13 | Phase 13 — Support & help desk (PDF §15) | 13.1 | SUP-01 | Patient support tickets — patients raise issues from the app and track them | SUP-01.02 | API: create/list/mine for patient | New | Support | §15 + §2.9 | Patient support tickets / Help centre & support tickets | Patients raise issues from the app and track them to resolution | Patient App + Admin | API | No | Yes | Yes | Yes | No | No | P1 | M | SUP-01.01 | Does not exist; EnquiryDetail is not tickets; Velzon tickets demo ignore | SupportTicket reporter=Patient; status track; not Enquiry, not Velzon /apps-tickets-* | Patient sees status changes; cannot see other patients’ tickets | Not Started
564 | 13 | Phase 13 — Support & help desk (PDF §15) | 13.1 | SUP-01 | Patient support tickets — patients raise issues from the app and track them | SUP-01.03 | Patient app screens in Phase 16; web help optional | New | Support | §15 + §2.9 | Patient support tickets / Help centre & support tickets | Patients raise issues from the app and track them to resolution | Patient App + Admin | Web SPA | Yes | No | No | Yes | No | No | P1 | M | SUP-01.02 | Does not exist; EnquiryDetail is not tickets; Velzon tickets demo ignore | SupportTicket reporter=Patient; status track; not Enquiry, not Velzon /apps-tickets-* | Patient sees status changes; cannot see other patients’ tickets | Not Started
565 | 13 | Phase 13 — Support & help desk (PDF §15) | 13.1 | SUP-01 | Patient support tickets — patients raise issues from the app and track them | SUP-01.04 | QA: IDOR; attachment via SEC-09 | Regression | Support | §15 + §2.9 | Patient support tickets / Help centre & support tickets | Patients raise issues from the app and track them to resolution | Patient App + Admin | QA | Yes | Yes | No | Yes | No | No | P1 | S | SUP-01.03 | Does not exist; EnquiryDetail is not tickets; Velzon tickets demo ignore | SupportTicket reporter=Patient; status track; not Enquiry, not Velzon /apps-tickets-* | Patient sees status changes; cannot see other patients’ tickets | Not Started
566 | 13 | Phase 13 — Support & help desk (PDF §15) | 13.2 | SUP-02 | Doctor support tickets — doctors raise issues from the portal | SUP-02.01 | Reuse SupportTicket with ReporterRole=Doctor | New | Support | §15 | Doctor support tickets | Doctors raise issues from the portal | Doctor Web + Admin | API | No | Yes | No | Yes | No | No | P1 | S | — | Does not exist | Same ticket tables; reporter=Doctor | Doctor portal has Raise issue; tracks to resolution | Not Started
567 | 13 | Phase 13 — Support & help desk (PDF §15) | 13.2 | SUP-02 | Doctor support tickets — doctors raise issues from the portal | SUP-02.02 | /doctor/support list/create/detail | New | Support | §15 | Doctor support tickets | Doctors raise issues from the portal | Doctor Web + Admin | Web SPA | Yes | No | No | No | No | No | P1 | M | SUP-02.01 | Does not exist | Same ticket tables; reporter=Doctor | Doctor portal has Raise issue; tracks to resolution | Not Started
568 | 13 | Phase 13 — Support & help desk (PDF §15) | 13.2 | SUP-02 | Doctor support tickets — doctors raise issues from the portal | SUP-02.03 | QA: doctor cannot see another doctor’s tickets | Regression | Support | §15 | Doctor support tickets | Doctors raise issues from the portal | Doctor Web + Admin | QA | Yes | Yes | No | No | No | No | P1 | S | SUP-02.02 | Does not exist | Same ticket tables; reporter=Doctor | Doctor portal has Raise issue; tracks to resolution | Not Started
569 | 13 | Phase 13 — Support & help desk (PDF §15) | 13.3 | SUP-03 | Admin issue queue — all issues in one queue with priority, assignment and status | SUP-03.01 | Extend ticket with Priority, Assignee, SLA | New | Support | §15 + §7.2 | Admin issue queue / Support ticket queue | All issues in one queue with priority, assignment and status / All patient and doctor issues in one queue with assignment and resolution | Admin Portal | Database | No | Yes | Yes | No | No | No | P1 | S | — | Does not exist | /admin/support-tickets; SLA timestamps; assign | Patient and doctor tickets in one queue; assignable | Not Started
570 | 13 | Phase 13 — Support & help desk (PDF §15) | 13.3 | SUP-03 | Admin issue queue — all issues in one queue with priority, assignment and status | SUP-03.02 | Admin list/filter/assign/status | New | Support | §15 + §7.2 | Admin issue queue / Support ticket queue | All issues in one queue with priority, assignment and status / All patient and doctor issues in one queue with assignment and resolution | Admin Portal | API | No | Yes | Yes | Yes | No | No | P1 | M | SUP-03.01 | Does not exist | /admin/support-tickets; SLA timestamps; assign | Patient and doctor tickets in one queue; assignable | Not Started
571 | 13 | Phase 13 — Support & help desk (PDF §15) | 13.3 | SUP-03 | Admin issue queue — all issues in one queue with priority, assignment and status | SUP-03.03 | /admin/support-tickets and /:id | New | Support | §15 + §7.2 | Admin issue queue / Support ticket queue | All issues in one queue with priority, assignment and status / All patient and doctor issues in one queue with assignment and resolution | Admin Portal | Web SPA | Yes | No | No | Yes | No | No | P1 | M | SUP-03.02 | Does not exist | /admin/support-tickets; SLA timestamps; assign | Patient and doctor tickets in one queue; assignable | Not Started
572 | 13 | Phase 13 — Support & help desk (PDF §15) | 13.3 | SUP-03 | Admin issue queue — all issues in one queue with priority, assignment and status | SUP-03.04 | QA: not using Velzon ticket pages | Regression | Support | §15 + §7.2 | Admin issue queue / Support ticket queue | All issues in one queue with priority, assignment and status / All patient and doctor issues in one queue with assignment and resolution | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P1 | S | SUP-03.03 | Does not exist | /admin/support-tickets; SLA timestamps; assign | Patient and doctor tickets in one queue; assignable | Not Started
573 | 13 | Phase 13 — Support & help desk (PDF §15) | 13.4 | SUP-04 | Ticket conversation — full message thread with attachments | SUP-04.01 | API: messages CRUD + attachment | New | Support | §15 | Ticket conversation | Full message thread with attachments | Admin + Doctor + Patient | API | No | Yes | No | Yes | No | No | P1 | M | — | Does not exist | Threaded messages + SEC-09 attachments | Both sides see the same thread order | Not Started
574 | 13 | Phase 13 — Support & help desk (PDF §15) | 13.4 | SUP-04 | Ticket conversation — full message thread with attachments | SUP-04.02 | Detail UI thread | New | Support | §15 | Ticket conversation | Full message thread with attachments | Admin + Doctor + Patient | Web SPA | Yes | No | No | No | No | No | P1 | M | SUP-04.01 | Does not exist | Threaded messages + SEC-09 attachments | Both sides see the same thread order | Not Started
575 | 13 | Phase 13 — Support & help desk (PDF §15) | 13.4 | SUP-04 | Ticket conversation — full message thread with attachments | SUP-04.03 | QA: attachment unauthorised download 403 | Regression | Support | §15 | Ticket conversation | Full message thread with attachments | Admin + Doctor + Patient | QA | No | Yes | No | No | No | No | P1 | S | SUP-04.02 | Does not exist | Threaded messages + SEC-09 attachments | Both sides see the same thread order | Not Started
576 | 13 | Phase 13 — Support & help desk (PDF §15) | 13.5 | SUP-05 | Enquiry management — website enquiries tracked (ties WEB-06) | SUP-05.01 | Admin enquiry inbox SLA fields | Existing Improvement | Support | §15 + §4 | Enquiry management | Website enquiries reach the admin team and are tracked | Admin Portal | Web SPA | Yes | No | No | Yes | No | No | P1 | S | — | API exists; inbox missing | Complete WEB-06 admin inbox if not already; convert enquiry → ticket optional | No enquiry is only in email | Not Started
577 | 13 | Phase 13 — Support & help desk (PDF §15) | 13.5 | SUP-05 | Enquiry management — website enquiries tracked (ties WEB-06) | SUP-05.02 | QA: convert to ticket keeps original enquiry id | Regression | Support | §15 + §4 | Enquiry management | Website enquiries reach the admin team and are tracked | Admin Portal | QA | Yes | No | No | No | No | No | P1 | S | SUP-05.01 | API exists; inbox missing | Complete WEB-06 admin inbox if not already; convert enquiry → ticket optional | No enquiry is only in email | Not Started
578 | 13 | Phase 13 — Support & help desk (PDF §15) | 13.6 | SUP-06 | Help centre — self-service help content for patients | SUP-06.01 | HelpArticle table or reuse blog category=help | New | Support | §15 + §2.9 | Help centre | Self-service help content for patients | Patient Website + App | Database | No | Yes | Yes | No | No | No | P2 | S | — | Does not exist | CMS articles or static help; searchable | Patient can open help without raising a ticket | Not Started
579 | 13 | Phase 13 — Support & help desk (PDF §15) | 13.6 | SUP-06 | Help centre — self-service help content for patients | SUP-06.02 | Public GET help articles | New | Support | §15 + §2.9 | Help centre | Self-service help content for patients | Patient Website + App | API | No | Yes | Yes | Yes | No | No | P2 | M | SUP-06.01 | Does not exist | CMS articles or static help; searchable | Patient can open help without raising a ticket | Not Started
580 | 13 | Phase 13 — Support & help desk (PDF §15) | 13.6 | SUP-06 | Help centre — self-service help content for patients | SUP-06.03 | Help centre list/detail | New | Support | §15 + §2.9 | Help centre | Self-service help content for patients | Patient Website + App | Web SPA | Yes | No | No | Yes | No | No | P2 | M | SUP-06.02 | Does not exist | CMS articles or static help; searchable | Patient can open help without raising a ticket | Not Started
581 | 13 | Phase 13 — Support & help desk (PDF §15) | 13.6 | SUP-06 | Help centre — self-service help content for patients | SUP-06.04 | QA: unpublished hidden | Regression | Support | §15 + §2.9 | Help centre | Self-service help content for patients | Patient Website + App | QA | Yes | Yes | No | Yes | No | No | P2 | S | SUP-06.03 | Does not exist | CMS articles or static help; searchable | Patient can open help without raising a ticket | Not Started
582 | 13 | Phase 13 — Support & help desk (PDF §15) | 13.7 | SUP-07 | Assisted booking — help for patients who need support booking | SUP-07.01 | Flag BookingChannel=Assisted; AssistedRequest ticket type | New | Support | §15 + §2.9 | Assisted booking | Support for patients who need help booking / Help for patients who need support booking | Support + Reception + Patient | Database | No | Yes | Yes | No | No | No | P2 | S | — | Does not exist | Staff (admin/support/reception) can complete public booking on behalf of a patient with audit; patient app CTA to request assistance | Assisted booking appears in audit as staff-created; patient still owns the appointment | Not Started
583 | 13 | Phase 13 — Support & help desk (PDF §15) | 13.7 | SUP-07 | Assisted booking — help for patients who need support booking | SUP-07.02 | API: request assistance; staff completes WEB-04 create on behalf | New | Support | §15 + §2.9 | Assisted booking | Support for patients who need help booking / Help for patients who need support booking | Support + Reception + Patient | API | No | Yes | Yes | Yes | No | No | P2 | M | SUP-07.01 | Does not exist | Staff (admin/support/reception) can complete public booking on behalf of a patient with audit; patient app CTA to request assistance | Assisted booking appears in audit as staff-created; patient still owns the appointment | Not Started
584 | 13 | Phase 13 — Support & help desk (PDF §15) | 13.7 | SUP-07 | Assisted booking — help for patients who need support booking | SUP-07.03 | Patient CTA; admin/reception assisted-book wizard | New | Support | §15 + §2.9 | Assisted booking | Support for patients who need help booking / Help for patients who need support booking | Support + Reception + Patient | Web SPA | Yes | No | No | Yes | No | No | P2 | M | SUP-07.02 | Does not exist | Staff (admin/support/reception) can complete public booking on behalf of a patient with audit; patient app CTA to request assistance | Assisted booking appears in audit as staff-created; patient still owns the appointment | Not Started
585 | 13 | Phase 13 — Support & help desk (PDF §15) | 13.7 | SUP-07 | Assisted booking — help for patients who need support booking | SUP-07.04 | QA: consent still captured; payment still Homeocentrum | Regression | Support | §15 + §2.9 | Assisted booking | Support for patients who need help booking / Help for patients who need support booking | Support + Reception + Patient | QA | Yes | Yes | No | Yes | No | No | P2 | S | SUP-07.03 | Does not exist | Staff (admin/support/reception) can complete public booking on behalf of a patient with audit; patient app CTA to request assistance | Assisted booking appears in audit as staff-created; patient still owns the appointment | Not Started
586 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.1 | MED-01 | Pharmacy partner onboarding — licensed premises, licence records, activation checklist | MED-01.01 | DB: PharmacyPartner, PharmacyLicence, activation checklist fields | New | HomeoMeds | §12 + §7.2 | Pharmacy partner onboarding / Pharmacy partner management | Licensed premises registered with licence records and an activation checklist / Onboard and activate licensed pharmacies | Pharmacy + Admin | Database | No | Yes | Yes | No | No | No | P0 | S | — | Does not exist | PharmacyPartner + licences; admin activation; pharmacy console login | Unactivated pharmacy cannot receive orders | Not Started
587 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.1 | MED-01 | Pharmacy partner onboarding — licensed premises, licence records, activation checklist | MED-01.02 | API: onboard, admin activate, pharmacy login role | New | HomeoMeds | §12 + §7.2 | Pharmacy partner onboarding / Pharmacy partner management | Licensed premises registered with licence records and an activation checklist / Onboard and activate licensed pharmacies | Pharmacy + Admin | API | No | Yes | Yes | Yes | No | No | P0 | M | MED-01.01 | Does not exist | PharmacyPartner + licences; admin activation; pharmacy console login | Unactivated pharmacy cannot receive orders | Not Started
588 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.1 | MED-01 | Pharmacy partner onboarding — licensed premises, licence records, activation checklist | MED-01.03 | /pharmacy/onboard; /admin pharmacy partners | New | HomeoMeds | §12 + §7.2 | Pharmacy partner onboarding / Pharmacy partner management | Licensed premises registered with licence records and an activation checklist / Onboard and activate licensed pharmacies | Pharmacy + Admin | Web SPA | Yes | No | No | Yes | No | No | P0 | M | MED-01.02 | Does not exist | PharmacyPartner + licences; admin activation; pharmacy console login | Unactivated pharmacy cannot receive orders | Not Started
589 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.1 | MED-01 | Pharmacy partner onboarding — licensed premises, licence records, activation checklist | MED-01.04 | QA: checklist incomplete blocks activate | Regression | HomeoMeds | §12 + §7.2 | Pharmacy partner onboarding / Pharmacy partner management | Licensed premises registered with licence records and an activation checklist / Onboard and activate licensed pharmacies | Pharmacy + Admin | QA | Yes | Yes | No | Yes | No | No | P0 | S | MED-01.03 | Does not exist | PharmacyPartner + licences; admin activation; pharmacy console login | Unactivated pharmacy cannot receive orders | Not Started
590 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.2 | MED-02 | Licence gating — expired or suspended licences blocked automatically from receiving orders | MED-02.01 | Job: mark licence expired/suspended; exclude from routing | New | HomeoMeds | §12 | Licence gating | Pharmacies with expired or suspended licences are blocked automatically from receiving orders | Backend | Backend | No | Yes | Yes | No | No | No | P0 | M | — | Does not exist | Scheduler; routing skip; banner on pharmacy console | Expired licence receives zero new orders the next minute | Not Started
591 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.2 | MED-02 | Licence gating — expired or suspended licences blocked automatically from receiving orders | MED-02.02 | Pharmacy console status banner | New | HomeoMeds | §12 | Licence gating | Pharmacies with expired or suspended licences are blocked automatically from receiving orders | Backend | Web SPA | Yes | No | No | No | No | No | P0 | S | MED-02.01 | Does not exist | Scheduler; routing skip; banner on pharmacy console | Expired licence receives zero new orders the next minute | Not Started
592 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.2 | MED-02 | Licence gating — expired or suspended licences blocked automatically from receiving orders | MED-02.03 | QA: expire a licence in test → order not offered | Regression | HomeoMeds | §12 | Licence gating | Pharmacies with expired or suspended licences are blocked automatically from receiving orders | Backend | QA | No | Yes | No | No | No | No | P0 | S | MED-02.02 | Does not exist | Scheduler; routing skip; banner on pharmacy console | Expired licence receives zero new orders the next minute | Not Started
593 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.3 | MED-03 | Fulfilment consent & pharmacy selection — patient chooses the seller and consents before the prescription is shared | MED-03.01 | Consent + selected PharmacyPartnerId on MedicineOrder | New | HomeoMeds | §12 + §2.7 | Fulfilment consent & pharmacy selection | The patient chooses the seller and consents before the prescription is shared | Patient | Database | No | Yes | Yes | No | No | No | P0 | S | — | Does not exist | ConsentRecord PharmacyShare; patient picks from routed sellers; share only after consent | No pharmacy sees names until patient consents and seller is selected (codes still protected until accept+OTP) | Not Started
594 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.3 | MED-03 | Fulfilment consent & pharmacy selection — patient chooses the seller and consents before the prescription is shared | MED-03.02 | API: list sellers; select; grant consent | New | HomeoMeds | §12 + §2.7 | Fulfilment consent & pharmacy selection | The patient chooses the seller and consents before the prescription is shared | Patient | API | No | Yes | Yes | Yes | No | No | P0 | M | MED-03.01 | Does not exist | ConsentRecord PharmacyShare; patient picks from routed sellers; share only after consent | No pharmacy sees names until patient consents and seller is selected (codes still protected until accept+OTP) | Not Started
595 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.3 | MED-03 | Fulfilment consent & pharmacy selection — patient chooses the seller and consents before the prescription is shared | MED-03.03 | Patient pharmacy pick UI (web optional + app Phase 16) | New | HomeoMeds | §12 + §2.7 | Fulfilment consent & pharmacy selection | The patient chooses the seller and consents before the prescription is shared | Patient | Web SPA | Yes | No | No | Yes | No | No | P0 | M | MED-03.02 | Does not exist | ConsentRecord PharmacyShare; patient picks from routed sellers; share only after consent | No pharmacy sees names until patient consents and seller is selected (codes still protected until accept+OTP) | Not Started
596 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.3 | MED-03 | Fulfilment consent & pharmacy selection — patient chooses the seller and consents before the prescription is shared | MED-03.04 | QA: without consent, handoff API 403 | Regression | HomeoMeds | §12 + §2.7 | Fulfilment consent & pharmacy selection | The patient chooses the seller and consents before the prescription is shared | Patient | QA | Yes | Yes | No | Yes | No | No | P0 | S | MED-03.03 | Does not exist | ConsentRecord PharmacyShare; patient picks from routed sellers; share only after consent | No pharmacy sees names until patient consents and seller is selected (codes still protected until accept+OTP) | Not Started
597 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.4 | MED-04 | Prescription handoff — signed prescription becomes the order directly — no re-entry, no transcription errors | MED-04.01 | DB: MedicineOrder, MedicineOrderItem from ErxSnapshot | New | HomeoMeds | §12 + §2.7 | Prescription handoff / Order start | The signed prescription becomes the order directly — no re-entry, no transcription errors / Start an order directly from the prescription | Patient + Pharmacy | Database | No | Yes | Yes | No | No | No | P0 | S | — | Does not exist | MedicineOrder copied from ErxSnapshot items (codes); pharmacy never types remedies | Order lines == snapshot lines; pharmacy cannot add a different remedy | Not Started
598 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.4 | MED-04 | Prescription handoff — signed prescription becomes the order directly — no re-entry, no transcription errors | MED-04.02 | API: POST order from ErxId | New | HomeoMeds | §12 + §2.7 | Prescription handoff / Order start | The signed prescription becomes the order directly — no re-entry, no transcription errors / Start an order directly from the prescription | Patient + Pharmacy | API | No | Yes | Yes | Yes | No | No | P0 | M | MED-04.01 | Does not exist | MedicineOrder copied from ErxSnapshot items (codes); pharmacy never types remedies | Order lines == snapshot lines; pharmacy cannot add a different remedy | Not Started
599 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.4 | MED-04 | Prescription handoff — signed prescription becomes the order directly — no re-entry, no transcription errors | MED-04.03 | Order start from patient eRx screen | New | HomeoMeds | §12 + §2.7 | Prescription handoff / Order start | The signed prescription becomes the order directly — no re-entry, no transcription errors / Start an order directly from the prescription | Patient + Pharmacy | Web SPA | Yes | No | No | Yes | No | No | P0 | M | MED-04.02 | Does not exist | MedicineOrder copied from ErxSnapshot items (codes); pharmacy never types remedies | Order lines == snapshot lines; pharmacy cannot add a different remedy | Not Started
600 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.4 | MED-04 | Prescription handoff — signed prescription becomes the order directly — no re-entry, no transcription errors | MED-04.04 | QA: line count mismatch fails sign-off | Regression | HomeoMeds | §12 + §2.7 | Prescription handoff / Order start | The signed prescription becomes the order directly — no re-entry, no transcription errors / Start an order directly from the prescription | Patient + Pharmacy | QA | Yes | Yes | No | Yes | No | No | P0 | S | MED-04.03 | Does not exist | MedicineOrder copied from ErxSnapshot items (codes); pharmacy never types remedies | Order lines == snapshot lines; pharmacy cannot add a different remedy | Not Started
601 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.5 | MED-05 | Rule-based seller routing — licence validity, service area, working hours and capacity | MED-05.01 | DB: SellerRoutingRule (area, hours, capacity) | New | HomeoMeds | §12 | Rule-based seller routing | Orders routed by licence validity, service area, working hours and capacity | Backend | Database | No | Yes | Yes | No | No | No | P0 | S | — | Does not exist | SellerRoutingRule engine | Out-of-area pharmacy never listed | Not Started
602 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.5 | MED-05 | Rule-based seller routing — licence validity, service area, working hours and capacity | MED-05.02 | Routing service used by seller list API | New | HomeoMeds | §12 | Rule-based seller routing | Orders routed by licence validity, service area, working hours and capacity | Backend | API | No | Yes | Yes | Yes | No | No | P0 | M | MED-05.01 | Does not exist | SellerRoutingRule engine | Out-of-area pharmacy never listed | Not Started
603 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.5 | MED-05 | Rule-based seller routing — licence validity, service area, working hours and capacity | MED-05.03 | Admin/pharmacy hours and area config UI | New | HomeoMeds | §12 | Rule-based seller routing | Orders routed by licence validity, service area, working hours and capacity | Backend | Web SPA | Yes | No | No | Yes | No | No | P0 | M | MED-05.02 | Does not exist | SellerRoutingRule engine | Out-of-area pharmacy never listed | Not Started
604 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.5 | MED-05 | Rule-based seller routing — licence validity, service area, working hours and capacity | MED-05.04 | QA: capacity full excluded; hours closed excluded | Regression | HomeoMeds | §12 | Rule-based seller routing | Orders routed by licence validity, service area, working hours and capacity | Backend | QA | Yes | Yes | No | Yes | No | No | P0 | S | MED-05.03 | Does not exist | SellerRoutingRule engine | Out-of-area pharmacy never listed | Not Started
605 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.6 | MED-06 | Manual stock confirmation — pharmacy confirms availability — no live inventory integration required | MED-06.01 | Accept payload includes stock confirmation; reject reason OUT_OF_STOCK | New | HomeoMeds | §12 | Manual stock confirmation | The pharmacy confirms availability — no live inventory integration required | Pharmacy console | API | No | Yes | No | Yes | No | No | P0 | S | — | Does not exist | Accept/reject with stock flag; do not build inventory master | Reject for out-of-stock routes to next seller or exception queue | Not Started
606 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.6 | MED-06 | Manual stock confirmation — pharmacy confirms availability — no live inventory integration required | MED-06.02 | Pharmacy UI confirm availability | New | HomeoMeds | §12 | Manual stock confirmation | The pharmacy confirms availability — no live inventory integration required | Pharmacy console | Web SPA | Yes | No | No | No | No | No | P0 | S | MED-06.01 | Does not exist | Accept/reject with stock flag; do not build inventory master | Reject for out-of-stock routes to next seller or exception queue | Not Started
607 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.6 | MED-06 | Manual stock confirmation — pharmacy confirms availability — no live inventory integration required | MED-06.03 | QA: no inventory SKU table required | Regression | HomeoMeds | §12 | Manual stock confirmation | The pharmacy confirms availability — no live inventory integration required | Pharmacy console | QA | No | Yes | No | No | No | No | P0 | S | MED-06.02 | Does not exist | Accept/reject with stock flag; do not build inventory master | Reject for out-of-stock routes to next seller or exception queue | Not Started
608 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.7 | MED-07 | Pharmacy console — accept or reject, enter price quote, mark ready and dispatched | MED-07.01 | Order status machine: Offered/Accepted/Rejected/Quoted/Paid/Ready/Dispatched/Delivered | New | HomeoMeds | §12 | Pharmacy console | Accept or reject orders, enter the price quote, mark ready and dispatched | Pharmacy console | Database | No | Yes | Yes | No | No | No | P0 | S | — | Does not exist | /pharmacy/orders list+detail; OTP accept (SEC-07); quote; ready; dispatched | OTP required on accept; status visible to patient | Not Started
609 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.7 | MED-07 | Pharmacy console — accept or reject, enter price quote, mark ready and dispatched | MED-07.02 | API: accept(OTP), reject, quote, ready, dispatch | New | HomeoMeds | §12 | Pharmacy console | Accept or reject orders, enter the price quote, mark ready and dispatched | Pharmacy console | API | No | Yes | Yes | Yes | No | No | P0 | M | MED-07.01 | Does not exist | /pharmacy/orders list+detail; OTP accept (SEC-07); quote; ready; dispatched | OTP required on accept; status visible to patient | Not Started
610 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.7 | MED-07 | Pharmacy console — accept or reject, enter price quote, mark ready and dispatched | MED-07.03 | /pharmacy/orders and detail | New | HomeoMeds | §12 | Pharmacy console | Accept or reject orders, enter the price quote, mark ready and dispatched | Pharmacy console | Web SPA | Yes | No | No | Yes | No | No | P0 | M | MED-07.02 | Does not exist | /pharmacy/orders list+detail; OTP accept (SEC-07); quote; ready; dispatched | OTP required on accept; status visible to patient | Not Started
611 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.7 | MED-07 | Pharmacy console — accept or reject, enter price quote, mark ready and dispatched | MED-07.04 | OTP on accept | New Integration | HomeoMeds | §12 | Pharmacy console | Accept or reject orders, enter the price quote, mark ready and dispatched | Pharmacy console | Integration | No | Yes | No | Yes | No | Yes | P0 | M | MED-07.03 | Does not exist | /pharmacy/orders list+detail; OTP accept (SEC-07); quote; ready; dispatched | OTP required on accept; status visible to patient | Not Started
612 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.7 | MED-07 | Pharmacy console — accept or reject, enter price quote, mark ready and dispatched | MED-07.05 | QA: accept without OTP fails; names still hidden to patient until accept succeeds | Regression | HomeoMeds | §12 | Pharmacy console | Accept or reject orders, enter the price quote, mark ready and dispatched | Pharmacy console | QA | Yes | Yes | No | Yes | No | No | P0 | S | MED-07.04 | Does not exist | /pharmacy/orders list+detail; OTP accept (SEC-07); quote; ready; dispatched | OTP required on accept; status visible to patient | Not Started
613 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.8 | MED-08 | Quote before payment — the patient always sees the price before paying | MED-08.01 | DB: MedicineQuote | New | HomeoMeds | §12 + §2.7 | Quote before payment / Pharmacy selection & quote | The patient always sees the price before paying / Choose a licensed pharmacy and see the price before paying | Patient | Database | No | Yes | Yes | No | No | No | P0 | S | — | Does not exist | MedicineQuote; patient must confirm quote; then PAY-07 | Payment API rejects if quote not accepted by patient | Not Started
614 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.8 | MED-08 | Quote before payment — the patient always sees the price before paying | MED-08.02 | API: quote, patient accept quote, then create medicine payment | New | HomeoMeds | §12 + §2.7 | Quote before payment / Pharmacy selection & quote | The patient always sees the price before paying / Choose a licensed pharmacy and see the price before paying | Patient | API | No | Yes | Yes | Yes | No | No | P0 | M | MED-08.01 | Does not exist | MedicineQuote; patient must confirm quote; then PAY-07 | Payment API rejects if quote not accepted by patient | Not Started
615 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.8 | MED-08 | Quote before payment — the patient always sees the price before paying | MED-08.03 | Patient quote screen | New | HomeoMeds | §12 + §2.7 | Quote before payment / Pharmacy selection & quote | The patient always sees the price before paying / Choose a licensed pharmacy and see the price before paying | Patient | Web SPA | Yes | No | No | Yes | No | No | P0 | M | MED-08.02 | Does not exist | MedicineQuote; patient must confirm quote; then PAY-07 | Payment API rejects if quote not accepted by patient | Not Started
616 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.8 | MED-08 | Quote before payment — the patient always sees the price before paying | MED-08.04 | QA: price change after quote invalidates old quote | Regression | HomeoMeds | §12 + §2.7 | Quote before payment / Pharmacy selection & quote | The patient always sees the price before paying / Choose a licensed pharmacy and see the price before paying | Patient | QA | Yes | Yes | No | Yes | No | No | P0 | S | MED-08.03 | Does not exist | MedicineQuote; patient must confirm quote; then PAY-07 | Payment API rejects if quote not accepted by patient | Not Started
617 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.9 | MED-09 | Payment or cash on delivery — both options, with status tracking | MED-09.01 | Wire PAY-07 CreateMedicineOrder; COD status enum | New | HomeoMeds | §12 + §9 | Payment or cash on delivery | Both options supported, with status tracking | Patient | API | No | Yes | No | Yes | No | Yes | P0 | M | — | Stream MEDICINE stub in Phase 6 | Online pay via PAY-02; COD_PENDING until pharmacy confirms collection | COD does not mark Stream MEDICINE as captured until collection confirmed | Not Started
618 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.9 | MED-09 | Payment or cash on delivery — both options, with status tracking | MED-09.02 | Patient pay vs COD UI | New | HomeoMeds | §12 + §9 | Payment or cash on delivery | Both options supported, with status tracking | Patient | Web SPA | Yes | No | No | No | Yes | No | P0 | M | MED-09.01 | Stream MEDICINE stub in Phase 6 | Online pay via PAY-02; COD_PENDING until pharmacy confirms collection | COD does not mark Stream MEDICINE as captured until collection confirmed | Not Started
619 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.9 | MED-09 | Payment or cash on delivery — both options, with status tracking | MED-09.03 | QA: COD vs prepaid ledger split | Regression | HomeoMeds | §12 + §9 | Payment or cash on delivery | Both options supported, with status tracking | Patient | QA | No | Yes | No | No | No | No | P0 | S | MED-09.02 | Stream MEDICINE stub in Phase 6 | Online pay via PAY-02; COD_PENDING until pharmacy confirms collection | COD does not mark Stream MEDICINE as captured until collection confirmed | Not Started
620 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.10 | MED-10 | Order tracking — live status for the patient at every stage | MED-10.01 | DB: MedicineOrderEvent | New | HomeoMeds | §12 + §2.7 | Order tracking | Live status for the patient at every stage / Live status from accepted to delivered | Patient | Database | No | Yes | Yes | No | No | No | P1 | S | — | Does not exist | Status timeline events; push updates COM-03 | Every status change visible; never silent skip | Not Started
621 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.10 | MED-10 | Order tracking — live status for the patient at every stage | MED-10.02 | GET tracking by order id (patient) | New | HomeoMeds | §12 + §2.7 | Order tracking | Live status for the patient at every stage / Live status from accepted to delivered | Patient | API | No | Yes | Yes | Yes | No | No | P1 | M | MED-10.01 | Does not exist | Status timeline events; push updates COM-03 | Every status change visible; never silent skip | Not Started
622 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.10 | MED-10 | Order tracking — live status for the patient at every stage | MED-10.03 | Tracking UI | New | HomeoMeds | §12 + §2.7 | Order tracking | Live status for the patient at every stage / Live status from accepted to delivered | Patient | Web SPA | Yes | No | No | Yes | No | No | P1 | M | MED-10.02 | Does not exist | Status timeline events; push updates COM-03 | Every status change visible; never silent skip | Not Started
623 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.10 | MED-10 | Order tracking — live status for the patient at every stage | MED-10.04 | Push on status change | New Integration | HomeoMeds | §12 + §2.7 | Order tracking | Live status for the patient at every stage / Live status from accepted to delivered | Patient | Integration | No | Yes | No | Yes | No | Yes | P1 | M | MED-10.03 | Does not exist | Status timeline events; push updates COM-03 | Every status change visible; never silent skip | Not Started
624 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.10 | MED-10 | Order tracking — live status for the patient at every stage | MED-10.05 | QA: dispatched without ready is invalid transition | Regression | HomeoMeds | §12 + §2.7 | Order tracking | Live status for the patient at every stage / Live status from accepted to delivered | Patient | QA | Yes | Yes | No | Yes | No | No | P1 | S | MED-10.04 | Does not exist | Status timeline events; push updates COM-03 | Every status change visible; never silent skip | Not Started
625 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.11 | MED-11 | Medicine ledger shares — seller, platform and delivery recorded (FIN-03 live fill) | MED-11.01 | On captured medicine payment write three-share ledger lines | New | HomeoMeds | §12 + §8 | Medicine ledger | Seller, platform and delivery shares recorded separately from consultation money | Account | API | No | Yes | Yes | No | No | No | P0 | M | — | Empty medicine ledger screen from Phase 7 | On pay/COD collect, write SplitSeller/Platform/Delivery from config | Account medicine ledger shows real rows after first order | Not Started
626 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.11 | MED-11 | Medicine ledger shares — seller, platform and delivery recorded (FIN-03 live fill) | MED-11.02 | QA: consult GMV unchanged by a medicine order | Regression | HomeoMeds | §12 + §8 | Medicine ledger | Seller, platform and delivery shares recorded separately from consultation money | Account | QA | No | Yes | No | No | No | No | P0 | S | MED-11.01 | Empty medicine ledger screen from Phase 7 | On pay/COD collect, write SplitSeller/Platform/Delivery from config | Account medicine ledger shows real rows after first order | Not Started
627 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.12 | MED-12 | Order exception queue — stuck, rejected or failed orders always surfaced — never silent | MED-12.01 | Exception rows for medicine orders | New | HomeoMeds | §12 | Order exception queue | Stuck, rejected or failed orders are always surfaced to the operations team — never silent | Admin + Account | Database | No | Yes | Yes | No | No | No | P0 | S | — | Does not exist | HomeoMeds exception queue; SLA; never drop | Rejected-by-all-sellers appears in queue within worker SLA | Not Started
628 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.12 | MED-12 | Order exception queue — stuck, rejected or failed orders always surfaced — never silent | MED-12.02 | Admin/ops list/detail/retry re-route | New | HomeoMeds | §12 | Order exception queue | Stuck, rejected or failed orders are always surfaced to the operations team — never silent | Admin + Account | API | No | Yes | Yes | Yes | No | No | P0 | M | MED-12.01 | Does not exist | HomeoMeds exception queue; SLA; never drop | Rejected-by-all-sellers appears in queue within worker SLA | Not Started
629 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.12 | MED-12 | Order exception queue — stuck, rejected or failed orders always surfaced — never silent | MED-12.03 | /admin/homemeds-exceptions | New | HomeoMeds | §12 | Order exception queue | Stuck, rejected or failed orders are always surfaced to the operations team — never silent | Admin + Account | Web SPA | Yes | No | No | Yes | No | No | P0 | M | MED-12.02 | Does not exist | HomeoMeds exception queue; SLA; never drop | Rejected-by-all-sellers appears in queue within worker SLA | Not Started
630 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.12 | MED-12 | Order exception queue — stuck, rejected or failed orders always surfaced — never silent | MED-12.04 | QA: silent discard impossible (metric + queue) | Regression | HomeoMeds | §12 | Order exception queue | Stuck, rejected or failed orders are always surfaced to the operations team — never silent | Admin + Account | QA | Yes | Yes | No | Yes | No | No | P0 | S | MED-12.03 | Does not exist | HomeoMeds exception queue; SLA; never drop | Rejected-by-all-sellers appears in queue within worker SLA | Not Started
631 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.13 | MED-13 | OTP-based control — key actions verified by OTP so Homeocentrum can monitor and trace every transaction | MED-13.01 | Bind OTP actions: PharmacyAccept, (optional) QuoteLock, Payout already FIN-05 | New | HomeoMeds | §12 + §17 | OTP-based control | Key actions verified by OTP so Homeocentrum can monitor and trace every transaction | Pharmacy + Account | API | No | Yes | No | Yes | No | No | P0 | S | — | SEC-07 infrastructure exists | OTP on pharmacy accept (and other high-risk); OtpAudit queryable | Accept without OTP fails; audit lists the action | Not Started
632 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.13 | MED-13 | OTP-based control — key actions verified by OTP so Homeocentrum can monitor and trace every transaction | MED-13.02 | QA: Account OTP audit shows pharmacy accept | Regression | HomeoMeds | §12 + §17 | OTP-based control | Key actions verified by OTP so Homeocentrum can monitor and trace every transaction | Pharmacy + Account | QA | No | Yes | No | No | No | No | P0 | S | MED-13.01 | SEC-07 infrastructure exists | OTP on pharmacy accept (and other high-risk); OtpAudit queryable | Accept without OTP fails; audit lists the action | Not Started
633 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.14 | MED-14 | Refill orders — repeat orders raised from an existing prescription | MED-14.01 | On doctor approve, clone order from snapshot; patient one-tap | New | HomeoMeds | §12 + §2.7 + §11 | Refill orders / Order detail & refill | Repeat orders raised from an existing prescription / Full order history and one-tap refill request | Patient + Doctor | API | No | Yes | No | Yes | No | No | P1 | M | — | ERX-10 refill request exists | Approved refill creates a new MedicineOrder from the same snapshot; one-tap patient | Refill does not mutate the original signed snapshot | Not Started
634 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.14 | MED-14 | Refill orders — repeat orders raised from an existing prescription | MED-14.02 | Patient order detail + refill CTA | New | HomeoMeds | §12 + §2.7 + §11 | Refill orders / Order detail & refill | Repeat orders raised from an existing prescription / Full order history and one-tap refill request | Patient + Doctor | Web SPA | Yes | No | No | No | Yes | No | P1 | S | MED-14.01 | ERX-10 refill request exists | Approved refill creates a new MedicineOrder from the same snapshot; one-tap patient | Refill does not mutate the original signed snapshot | Not Started
635 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.14 | MED-14 | Refill orders — repeat orders raised from an existing prescription | MED-14.03 | QA: original eRx unchanged | Regression | HomeoMeds | §12 + §2.7 + §11 | Refill orders / Order detail & refill | Repeat orders raised from an existing prescription / Full order history and one-tap refill request | Patient + Doctor | QA | No | Yes | No | No | No | No | P1 | S | MED-14.02 | ERX-10 refill request exists | Approved refill creates a new MedicineOrder from the same snapshot; one-tap patient | Refill does not mutate the original signed snapshot | Not Started
636 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.15 | MED-15 | Order review & consent (patient) — confirm and consent before the prescription is shared | MED-15.01 | Patient review screen before handoff | New | HomeoMeds | §2.7 | Order review & consent | Confirm and consent before the prescription is shared | Patient | Web SPA | Yes | No | No | Yes | Yes | No | P0 | M | — | Covered by MED-03; explicit review screen still required | Review screen listing codes (not names) + pharmacy + consent checkbox | Share does not occur until review confirmed | Not Started
637 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.15 | MED-15 | Order review & consent (patient) — confirm and consent before the prescription is shared | MED-15.02 | QA: back button does not share | Regression | HomeoMeds | §2.7 | Order review & consent | Confirm and consent before the prescription is shared | Patient | QA | Yes | No | No | No | No | No | P0 | S | MED-15.01 | Covered by MED-03; explicit review screen still required | Review screen listing codes (not names) + pharmacy + consent checkbox | Share does not occur until review confirmed | Not Started
638 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.16 | MED-16 | Medicines tab — all medicine orders in one place (API now; app UI in Phase 16) | MED-16.01 | GET /api/Patient/MedicineOrders | New | HomeoMeds | §2.7 | Medicines tab | All medicine orders in one place | Patient | API | No | Yes | No | Yes | No | No | P1 | S | — | Does not exist | GET my orders; website optional list; app tab Phase 16 | Patient sees all orders for their PatientId only | Not Started
639 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.16 | MED-16 | Medicines tab — all medicine orders in one place (API now; app UI in Phase 16) | MED-16.02 | Optional web list; mobile tab later | New | HomeoMeds | §2.7 | Medicines tab | All medicine orders in one place | Patient | Web SPA | Yes | No | No | No | No | No | P1 | S | MED-16.01 | Does not exist | GET my orders; website optional list; app tab Phase 16 | Patient sees all orders for their PatientId only | Not Started
640 | 14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 14.16 | MED-16 | Medicines tab — all medicine orders in one place (API now; app UI in Phase 16) | MED-16.03 | QA: IDOR other patient 403 | Regression | HomeoMeds | §2.7 | Medicines tab | All medicine orders in one place | Patient | QA | No | Yes | No | No | No | No | P1 | S | MED-16.02 | Does not exist | GET my orders; website optional list; app tab Phase 16 | Patient sees all orders for their PatientId only | Not Started
641 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.1 | CON-01 | Family members — add family members under one account | CON-01.01 | DB: FamilyMember | New | Patient identity | §2.1 | Family members | Add family members under one account | Patient App (API now) | Database | No | Yes | Yes | No | No | No | P0 | S | — | Does not exist | FamilyMember under Patient account; bookings can be for a member | Member has own PatientId or MemberId linked; records isolated correctly | Not Started
642 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.1 | CON-01 | Family members — add family members under one account | CON-01.02 | API: CRUD family; book-as-member | New | Patient identity | §2.1 | Family members | Add family members under one account | Patient App (API now) | API | No | Yes | Yes | Yes | No | No | P0 | M | CON-01.01 | Does not exist | FamilyMember under Patient account; bookings can be for a member | Member has own PatientId or MemberId linked; records isolated correctly | Not Started
643 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.1 | CON-01 | Family members — add family members under one account | CON-01.03 | Consumed in Phase 16 | New | Patient identity | §2.1 | Family members | Add family members under one account | Patient App (API now) | Web SPA | Yes | No | No | Yes | No | No | P0 | M | CON-01.02 | Does not exist | FamilyMember under Patient account; bookings can be for a member | Member has own PatientId or MemberId linked; records isolated correctly | Not Started
644 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.1 | CON-01 | Family members — add family members under one account | CON-01.04 | QA: adult consent rules for minors documented | Regression | Patient identity | §2.1 | Family members | Add family members under one account | Patient App (API now) | QA | Yes | Yes | No | Yes | No | No | P0 | S | CON-01.03 | Does not exist | FamilyMember under Patient account; bookings can be for a member | Member has own PatientId or MemberId linked; records isolated correctly | Not Started
645 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.2 | CON-02 | Caregiver authorization — let a family member book and manage on their behalf | CON-02.01 | DB: CaregiverAuth | New | Patient identity | §2.1 | Caregiver authorization | Let a family member book and manage on their behalf | Patient App (API now) | Database | No | Yes | Yes | No | No | No | P0 | S | — | Does not exist | CaregiverAuth with scopes; OTP; withdrawable via consent centre | Caregiver cannot exceed granted scopes; withdrawal immediate | Not Started
646 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.2 | CON-02 | Caregiver authorization — let a family member book and manage on their behalf | CON-02.02 | API: grant/revoke/list; booking authorisation check | New | Patient identity | §2.1 | Caregiver authorization | Let a family member book and manage on their behalf | Patient App (API now) | API | No | Yes | Yes | Yes | No | No | P0 | M | CON-02.01 | Does not exist | CaregiverAuth with scopes; OTP; withdrawable via consent centre | Caregiver cannot exceed granted scopes; withdrawal immediate | Not Started
647 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.2 | CON-02 | Caregiver authorization — let a family member book and manage on their behalf | CON-02.03 | Consumed in Phase 16 | New | Patient identity | §2.1 | Caregiver authorization | Let a family member book and manage on their behalf | Patient App (API now) | Web SPA | Yes | No | No | Yes | No | No | P0 | M | CON-02.02 | Does not exist | CaregiverAuth with scopes; OTP; withdrawable via consent centre | Caregiver cannot exceed granted scopes; withdrawal immediate | Not Started
648 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.2 | CON-02 | Caregiver authorization — let a family member book and manage on their behalf | CON-02.04 | OTP on grant | New Integration | Patient identity | §2.1 | Caregiver authorization | Let a family member book and manage on their behalf | Patient App (API now) | Integration | No | Yes | No | Yes | No | Yes | P0 | M | CON-02.03 | Does not exist | CaregiverAuth with scopes; OTP; withdrawable via consent centre | Caregiver cannot exceed granted scopes; withdrawal immediate | Not Started
649 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.2 | CON-02 | Caregiver authorization — let a family member book and manage on their behalf | CON-02.05 | QA: revoked token cannot book | Regression | Patient identity | §2.1 | Caregiver authorization | Let a family member book and manage on their behalf | Patient App (API now) | QA | Yes | Yes | No | Yes | No | No | P0 | S | CON-02.04 | Does not exist | CaregiverAuth with scopes; OTP; withdrawable via consent centre | Caregiver cannot exceed granted scopes; withdrawal immediate | Not Started
650 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.3 | CON-03 | Records timeline + consultation note + document upload APIs | CON-03.01 | Reuse appointments + summary + eRx + SecureDocument | New | Patient records | §2.5 | Records timeline / Consultation note / Document upload | Complete visit history in date order / Doctor’s notes for each visit / Upload reports, scans and previous prescriptions | Patient App (API now) | Database | No | Yes | Yes | No | No | No | P0 | S | — | Doctor history exists; no patient timeline; no patient upload | Patient timeline DTO (visits, summary, eRx codes, labs); consultation note = TEL-11 summary not private notes; uploads via SEC-09 | Private doctor notes never in patient timeline; uploads listed | Not Started
651 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.3 | CON-03 | Records timeline + consultation note + document upload APIs | CON-03.02 | GET timeline; GET consultation note (summary); POST documents | New | Patient records | §2.5 | Records timeline / Consultation note / Document upload | Complete visit history in date order / Doctor’s notes for each visit / Upload reports, scans and previous prescriptions | Patient App (API now) | API | No | Yes | Yes | Yes | No | No | P0 | M | CON-03.01 | Doctor history exists; no patient timeline; no patient upload | Patient timeline DTO (visits, summary, eRx codes, labs); consultation note = TEL-11 summary not private notes; uploads via SEC-09 | Private doctor notes never in patient timeline; uploads listed | Not Started
652 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.3 | CON-03 | Records timeline + consultation note + document upload APIs | CON-03.03 | Consumed in Phase 16 | New | Patient records | §2.5 | Records timeline / Consultation note / Document upload | Complete visit history in date order / Doctor’s notes for each visit / Upload reports, scans and previous prescriptions | Patient App (API now) | Web SPA | Yes | No | No | Yes | No | No | P0 | M | CON-03.02 | Doctor history exists; no patient timeline; no patient upload | Patient timeline DTO (visits, summary, eRx codes, labs); consultation note = TEL-11 summary not private notes; uploads via SEC-09 | Private doctor notes never in patient timeline; uploads listed | Not Started
653 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.3 | CON-03 | Records timeline + consultation note + document upload APIs | CON-03.04 | QA: notes leak test on timeline JSON | Regression | Patient records | §2.5 | Records timeline / Consultation note / Document upload | Complete visit history in date order / Doctor’s notes for each visit / Upload reports, scans and previous prescriptions | Patient App (API now) | QA | Yes | Yes | No | Yes | No | No | P0 | S | CON-03.03 | Doctor history exists; no patient timeline; no patient upload | Patient timeline DTO (visits, summary, eRx codes, labs); consultation note = TEL-11 summary not private notes; uploads via SEC-09 | Private doctor notes never in patient timeline; uploads listed | Not Started
654 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.4 | CON-04 | Follow-up plan & tasks — clear next steps after each consultation | CON-04.01 | DB: FollowUpPlan, FollowUpTask | New | Continuity | §2.6 | Follow-up plan & tasks | Clear next steps after each consultation | Doctor Web + Patient | Database | No | Yes | Yes | No | No | No | P1 | S | — | Does not exist (follow-up option in notes does not save) | FollowUpTask created by doctor; patient sees tasks | Tasks persist against PatientAppId; due dates drive Phase 18 follow-up analysis | Not Started
655 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.4 | CON-04 | Follow-up plan & tasks — clear next steps after each consultation | CON-04.02 | API: doctor set; patient list/complete | New | Continuity | §2.6 | Follow-up plan & tasks | Clear next steps after each consultation | Doctor Web + Patient | API | No | Yes | Yes | Yes | No | No | P1 | M | CON-04.01 | Does not exist (follow-up option in notes does not save) | FollowUpTask created by doctor; patient sees tasks | Tasks persist against PatientAppId; due dates drive Phase 18 follow-up analysis | Not Started
656 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.4 | CON-04 | Follow-up plan & tasks — clear next steps after each consultation | CON-04.03 | Doctor board follow-up panel; app in Phase 16 | New | Continuity | §2.6 | Follow-up plan & tasks | Clear next steps after each consultation | Doctor Web + Patient | Web SPA | Yes | No | No | Yes | No | No | P1 | M | CON-04.02 | Does not exist (follow-up option in notes does not save) | FollowUpTask created by doctor; patient sees tasks | Tasks persist against PatientAppId; due dates drive Phase 18 follow-up analysis | Not Started
657 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.4 | CON-04 | Follow-up plan & tasks — clear next steps after each consultation | CON-04.04 | QA: overdue flag | Regression | Continuity | §2.6 | Follow-up plan & tasks | Clear next steps after each consultation | Doctor Web + Patient | QA | Yes | Yes | No | Yes | No | No | P1 | S | CON-04.03 | Does not exist (follow-up option in notes does not save) | FollowUpTask created by doctor; patient sees tasks | Tasks persist against PatientAppId; due dates drive Phase 18 follow-up analysis | Not Started
658 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.5 | CON-05 | Symptom diary — record symptoms between visits | CON-05.01 | DB: SymptomDiary | New | Continuity | §2.6 | Symptom diary | Record symptoms between visits | Patient App (API now) | Database | No | Yes | Yes | No | No | No | P1 | S | — | Does not exist | SymptomDiary entries; doctor can read on board | Entries dated; treating doctor can read; other doctors 403 | Not Started
659 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.5 | CON-05 | Symptom diary — record symptoms between visits | CON-05.02 | API: patient CRUD; doctor GET by patient | New | Continuity | §2.6 | Symptom diary | Record symptoms between visits | Patient App (API now) | API | No | Yes | Yes | Yes | No | No | P1 | M | CON-05.01 | Does not exist | SymptomDiary entries; doctor can read on board | Entries dated; treating doctor can read; other doctors 403 | Not Started
660 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.5 | CON-05 | Symptom diary — record symptoms between visits | CON-05.03 | Doctor board read-only; app write Phase 16 | New | Continuity | §2.6 | Symptom diary | Record symptoms between visits | Patient App (API now) | Web SPA | Yes | No | No | Yes | No | No | P1 | M | CON-05.02 | Does not exist | SymptomDiary entries; doctor can read on board | Entries dated; treating doctor can read; other doctors 403 | Not Started
661 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.5 | CON-05 | Symptom diary — record symptoms between visits | CON-05.04 | QA: IDOR | Regression | Continuity | §2.6 | Symptom diary | Record symptoms between visits | Patient App (API now) | QA | Yes | Yes | No | Yes | No | No | P1 | S | CON-05.03 | Does not exist | SymptomDiary entries; doctor can read on board | Entries dated; treating doctor can read; other doctors 403 | Not Started
662 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.6 | CON-06 | Progress tracking — see improvement over time across visits | CON-06.01 | Derived API from diary + appointments | New | Continuity | §2.6 | Progress tracking | See improvement over time across visits | Patient + Doctor | Database | No | Yes | Yes | No | No | No | P2 | S | — | Does not exist | Progress series from diary + visit outcomes; not a fake chart | Empty state for new patients; series uses real diary/visit data | Not Started
663 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.6 | CON-06 | Progress tracking — see improvement over time across visits | CON-06.02 | GET progress series | New | Continuity | §2.6 | Progress tracking | See improvement over time across visits | Patient + Doctor | API | No | Yes | Yes | Yes | No | No | P2 | M | CON-06.01 | Does not exist | Progress series from diary + visit outcomes; not a fake chart | Empty state for new patients; series uses real diary/visit data | Not Started
664 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.6 | CON-06 | Progress tracking — see improvement over time across visits | CON-06.03 | Consumed in Phase 16 | New | Continuity | §2.6 | Progress tracking | See improvement over time across visits | Patient + Doctor | Web SPA | Yes | No | No | Yes | No | No | P2 | M | CON-06.02 | Does not exist | Progress series from diary + visit outcomes; not a fake chart | Empty state for new patients; series uses real diary/visit data | Not Started
665 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.6 | CON-06 | Progress tracking — see improvement over time across visits | CON-06.04 | QA: no dummy numbers | Regression | Continuity | §2.6 | Progress tracking | See improvement over time across visits | Patient + Doctor | QA | Yes | Yes | No | Yes | No | No | P2 | S | CON-06.03 | Does not exist | Progress series from diary + visit outcomes; not a fake chart | Empty state for new patients; series uses real diary/visit data | Not Started
666 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.7 | CON-07 | Consent centre & data rights — view, manage and withdraw consents; request data | CON-07.01 | Reuse ConsentRecord; DataRequest table | New | Privacy | §17 + §2.8 | Consent centre & data rights | Patients can view, manage and withdraw consent / View, manage and withdraw consents; request data | Patient App (API now) | Database | No | Yes | Yes | No | No | No | P0 | S | — | ConsentRecord from Phase 0 | Patient list/withdraw; data export request (DPDP); deletion request workflow | Withdraw tele-recording prevents future recording; export request ticketed | Not Started
667 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.7 | CON-07 | Consent centre & data rights — view, manage and withdraw consents; request data | CON-07.02 | API: list/withdraw; request export/delete | New | Privacy | §17 + §2.8 | Consent centre & data rights | Patients can view, manage and withdraw consent / View, manage and withdraw consents; request data | Patient App (API now) | API | No | Yes | Yes | Yes | No | No | P0 | M | CON-07.01 | ConsentRecord from Phase 0 | Patient list/withdraw; data export request (DPDP); deletion request workflow | Withdraw tele-recording prevents future recording; export request ticketed | Not Started
668 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.7 | CON-07 | Consent centre & data rights — view, manage and withdraw consents; request data | CON-07.03 | Consumed in Phase 16 | New | Privacy | §17 + §2.8 | Consent centre & data rights | Patients can view, manage and withdraw consent / View, manage and withdraw consents; request data | Patient App (API now) | Web SPA | Yes | No | No | Yes | No | No | P0 | M | CON-07.02 | ConsentRecord from Phase 0 | Patient list/withdraw; data export request (DPDP); deletion request workflow | Withdraw tele-recording prevents future recording; export request ticketed | Not Started
669 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.7 | CON-07 | Consent centre & data rights — view, manage and withdraw consents; request data | CON-07.04 | QA: withdraw marketing stops WhatsApp/SMS offers | Regression | Privacy | §17 + §2.8 | Consent centre & data rights | Patients can view, manage and withdraw consent / View, manage and withdraw consents; request data | Patient App (API now) | QA | Yes | Yes | No | Yes | No | No | P0 | S | CON-07.03 | ConsentRecord from Phase 0 | Patient list/withdraw; data export request (DPDP); deletion request workflow | Withdraw tele-recording prevents future recording; export request ticketed | Not Started
670 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.8 | CON-08 | Patient payments & refunds read model | CON-08.01 | GET /api/Patient/Payments | New | Patient money | §2.8 | Payments & refunds | Full payment history and refund status | Patient App (API now) | API | No | Yes | No | Yes | No | No | P1 | M | — | Ledger exists for Account | Patient-safe DTO of own consult+medicine payments and refunds — no other patients, no commission internals | Patient sees status matching PAY-08; no Account-only fields leaked | Not Started
671 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.8 | CON-08 | Patient payments & refunds read model | CON-08.02 | QA: commission/GST internal lines hidden | Regression | Patient money | §2.8 | Payments & refunds | Full payment history and refund status | Patient App (API now) | QA | No | Yes | No | No | No | No | P1 | S | CON-08.01 | Ledger exists for Account | Patient-safe DTO of own consult+medicine payments and refunds — no other patients, no commission internals | Patient sees status matching PAY-08; no Account-only fields leaked | Not Started
672 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.9 | CON-09 | Physical clinic appointment — book an in-person visit as well as online | CON-09.01 | Public/patient create booking accepts ConsultMode=In-clinic; uses in-clinic fee | Existing Improvement | Booking | §2.9 + §5.2 | Physical clinic appointment | Book an in-person visit as well as online | Patient | API | No | Yes | No | Yes | No | No | P1 | S | — | ConsultMode added in APT-02; public booking in WEB-04 | Ensure public/patient booking supports In-clinic as first-class, not tele-only | Patient can book in-clinic slot where doctor offers it | Not Started
673 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.9 | CON-09 | Physical clinic appointment — book an in-person visit as well as online | CON-09.02 | QA: in-clinic does not require device check/video | Regression | Booking | §2.9 + §5.2 | Physical clinic appointment | Book an in-person visit as well as online | Patient | QA | No | Yes | No | No | No | No | P1 | S | CON-09.01 | ConsultMode added in APT-02; public booking in WEB-04 | Ensure public/patient booking supports In-clinic as first-class, not tele-only | Patient can book in-clinic slot where doctor offers it | Not Started
674 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.10 | CON-10 | Patient profile setup API — name, age, gender, contact and health basics | CON-10.01 | Extend Patient with health-basics JSON/columns | New | Patient identity | §2.1 | Profile setup | Name, age, gender, contact and health basics | Patient App (API now) | Database | No | Yes | Yes | No | No | No | P0 | S | — | Clinic-created Patient exists; no self-serve profile product | Patient profile fields + health basics; used by OTP-verified patient token | Profile required before first paid booking (or soft-gate documented) | Not Started
675 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.10 | CON-10 | Patient profile setup API — name, age, gender, contact and health basics | CON-10.02 | GET/PUT /api/Patient/Profile | New | Patient identity | §2.1 | Profile setup | Name, age, gender, contact and health basics | Patient App (API now) | API | No | Yes | Yes | Yes | No | No | P0 | M | CON-10.01 | Clinic-created Patient exists; no self-serve profile product | Patient profile fields + health basics; used by OTP-verified patient token | Profile required before first paid booking (or soft-gate documented) | Not Started
676 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.10 | CON-10 | Patient profile setup API — name, age, gender, contact and health basics | CON-10.03 | Consumed in Phase 16 | New | Patient identity | §2.1 | Profile setup | Name, age, gender, contact and health basics | Patient App (API now) | Web SPA | Yes | No | No | Yes | No | No | P0 | M | CON-10.02 | Clinic-created Patient exists; no self-serve profile product | Patient profile fields + health basics; used by OTP-verified patient token | Profile required before first paid booking (or soft-gate documented) | Not Started
677 | 15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 15.10 | CON-10 | Patient profile setup API — name, age, gender, contact and health basics | CON-10.04 | QA: cannot escalate to doctor role via profile PUT | Regression | Patient identity | §2.1 | Profile setup | Name, age, gender, contact and health basics | Patient App (API now) | QA | Yes | Yes | No | Yes | No | No | P0 | S | CON-10.03 | Clinic-created Patient exists; no self-serve profile product | Patient profile fields + health basics; used by OTP-verified patient token | Profile required before first paid booking (or soft-gate documented) | Not Started
678 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.1 | PAT-01 | Patient app — language selection on first open | PAT-01.01 | UI: Language selection screens (empty, loading, error, offline) | New | Patient Mobile | §2.1 | Language selection | Choose preferred language on first open | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | — | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Choose preferred language on first open | Not Started
679 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.1 | PAT-01 | Patient app — language selection on first open | PAT-01.02 | Wire to the Phase 8–15 API for: Language selection | New | Patient Mobile | §2.1 | Language selection | Choose preferred language on first open | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-01.01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Choose preferred language on first open | Not Started
680 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.1 | PAT-01 | Patient app — language selection on first open | PAT-01.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.1 | Language selection | Choose preferred language on first open | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-01.02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Choose preferred language on first open | Not Started
681 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.1 | PAT-01 | Patient app — language selection on first open | PAT-01.04 | QA both platforms: Language selection matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.1 | Language selection | Choose preferred language on first open | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-01.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Choose preferred language on first open | Not Started
682 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.2 | PAT-02 | Patient app — welcome and introduction | PAT-02.01 | UI: Welcome & introduction screens (empty, loading, error, offline) | New | Patient Mobile | §2.1 | Welcome & introduction | Guided introduction to the app | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | — | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Guided introduction to the app | Not Started
683 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.2 | PAT-02 | Patient app — welcome and introduction | PAT-02.02 | Wire to the Phase 8–15 API for: Welcome & introduction | New | Patient Mobile | §2.1 | Welcome & introduction | Guided introduction to the app | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-02.01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Guided introduction to the app | Not Started
684 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.2 | PAT-02 | Patient app — welcome and introduction | PAT-02.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.1 | Welcome & introduction | Guided introduction to the app | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-02.02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Guided introduction to the app | Not Started
685 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.2 | PAT-02 | Patient app — welcome and introduction | PAT-02.04 | QA both platforms: Welcome & introduction matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.1 | Welcome & introduction | Guided introduction to the app | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-02.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Guided introduction to the app | Not Started
686 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.3 | PAT-03 | Patient app — mobile number + OTP login (PatientAuth) | PAT-03.01 | UI: Mobile number + OTP login screens (empty, loading, error, offline) | New | Patient Mobile | §2.1 | Mobile number + OTP login | Secure sign-in with no password to remember | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | WEB-04 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Secure sign-in with no password to remember | Not Started
687 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.3 | PAT-03 | Patient app — mobile number + OTP login (PatientAuth) | PAT-03.02 | Wire to the Phase 8–15 API for: Mobile number + OTP login | New | Patient Mobile | §2.1 | Mobile number + OTP login | Secure sign-in with no password to remember | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-03.01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Secure sign-in with no password to remember | Not Started
688 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.3 | PAT-03 | Patient app — mobile number + OTP login (PatientAuth) | PAT-03.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.1 | Mobile number + OTP login | Secure sign-in with no password to remember | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-03.02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Secure sign-in with no password to remember | Not Started
689 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.3 | PAT-03 | Patient app — mobile number + OTP login (PatientAuth) | PAT-03.04 | QA both platforms: Mobile number + OTP login matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.1 | Mobile number + OTP login | Secure sign-in with no password to remember | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-03.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Secure sign-in with no password to remember | Not Started
690 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.4 | PAT-04 | Patient app — profile setup | PAT-04.01 | UI: Profile setup screens (empty, loading, error, offline) | New | Patient Mobile | §2.1 | Profile setup | Name, age, gender, contact and health basics | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | CON-10 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Name, age, gender, contact and health basics | Not Started
691 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.4 | PAT-04 | Patient app — profile setup | PAT-04.02 | Wire to the Phase 8–15 API for: Profile setup | New | Patient Mobile | §2.1 | Profile setup | Name, age, gender, contact and health basics | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-04.01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Name, age, gender, contact and health basics | Not Started
692 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.4 | PAT-04 | Patient app — profile setup | PAT-04.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.1 | Profile setup | Name, age, gender, contact and health basics | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-04.02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Name, age, gender, contact and health basics | Not Started
693 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.4 | PAT-04 | Patient app — profile setup | PAT-04.04 | QA both platforms: Profile setup matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.1 | Profile setup | Name, age, gender, contact and health basics | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-04.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Name, age, gender, contact and health basics | Not Started
694 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.5 | PAT-05 | Patient app — privacy consent before data stored | PAT-05.01 | UI: Privacy consent screens (empty, loading, error, offline) | New | Patient Mobile | §2.1 | Privacy consent | Clear consent before any personal data is stored | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | SEC-06 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Clear consent before any personal data is stored | Not Started
695 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.5 | PAT-05 | Patient app — privacy consent before data stored | PAT-05.02 | Wire to the Phase 8–15 API for: Privacy consent | New | Patient Mobile | §2.1 | Privacy consent | Clear consent before any personal data is stored | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-05.01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Clear consent before any personal data is stored | Not Started
696 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.5 | PAT-05 | Patient app — privacy consent before data stored | PAT-05.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.1 | Privacy consent | Clear consent before any personal data is stored | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-05.02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Clear consent before any personal data is stored | Not Started
697 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.5 | PAT-05 | Patient app — privacy consent before data stored | PAT-05.04 | QA both platforms: Privacy consent matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.1 | Privacy consent | Clear consent before any personal data is stored | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-05.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Clear consent before any personal data is stored | Not Started
698 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.6 | PAT-06 | Patient app — family members | PAT-06.01 | UI: Family members screens (empty, loading, error, offline) | New | Patient Mobile | §2.1 | Family members | Add family members under one account | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | CON-01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Add family members under one account | Not Started
699 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.6 | PAT-06 | Patient app — family members | PAT-06.02 | Wire to the Phase 8–15 API for: Family members | New | Patient Mobile | §2.1 | Family members | Add family members under one account | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-06.01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Add family members under one account | Not Started
700 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.6 | PAT-06 | Patient app — family members | PAT-06.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.1 | Family members | Add family members under one account | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-06.02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Add family members under one account | Not Started
701 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.6 | PAT-06 | Patient app — family members | PAT-06.04 | QA both platforms: Family members matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.1 | Family members | Add family members under one account | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-06.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Add family members under one account | Not Started
702 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.7 | PAT-07 | Patient app — caregiver authorization | PAT-07.01 | UI: Caregiver authorization screens (empty, loading, error, offline) | New | Patient Mobile | §2.1 | Caregiver authorization | Let a family member book and manage on their behalf | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | CON-02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Let a family member book and manage on their behalf | Not Started
703 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.7 | PAT-07 | Patient app — caregiver authorization | PAT-07.02 | Wire to the Phase 8–15 API for: Caregiver authorization | New | Patient Mobile | §2.1 | Caregiver authorization | Let a family member book and manage on their behalf | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-07.01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Let a family member book and manage on their behalf | Not Started
704 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.7 | PAT-07 | Patient app — caregiver authorization | PAT-07.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.1 | Caregiver authorization | Let a family member book and manage on their behalf | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-07.02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Let a family member book and manage on their behalf | Not Started
705 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.7 | PAT-07 | Patient app — caregiver authorization | PAT-07.04 | QA both platforms: Caregiver authorization matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.1 | Caregiver authorization | Let a family member book and manage on their behalf | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-07.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Let a family member book and manage on their behalf | Not Started
706 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.8 | PAT-08 | Patient app — home dashboard | PAT-08.01 | UI: Home dashboard screens (empty, loading, error, offline) | New | Patient Mobile | §2.2 | Home dashboard | Personalised home with upcoming visits and quick actions | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | — | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Personalised home with upcoming visits and quick actions | Not Started
707 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.8 | PAT-08 | Patient app — home dashboard | PAT-08.02 | Wire to the Phase 8–15 API for: Home dashboard | New | Patient Mobile | §2.2 | Home dashboard | Personalised home with upcoming visits and quick actions | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-08.01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Personalised home with upcoming visits and quick actions | Not Started
708 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.8 | PAT-08 | Patient app — home dashboard | PAT-08.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.2 | Home dashboard | Personalised home with upcoming visits and quick actions | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-08.02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Personalised home with upcoming visits and quick actions | Not Started
709 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.8 | PAT-08 | Patient app — home dashboard | PAT-08.04 | QA both platforms: Home dashboard matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.2 | Home dashboard | Personalised home with upcoming visits and quick actions | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-08.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Personalised home with upcoming visits and quick actions | Not Started
710 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.9 | PAT-09 | Patient app — search and care categories | PAT-09.01 | UI: Search & care categories screens (empty, loading, error, offline) | New | Patient Mobile | §2.2 | Search & care categories | Search by name, condition or category of care | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | WEB-03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Search by name, condition or category of care | Not Started
711 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.9 | PAT-09 | Patient app — search and care categories | PAT-09.02 | Wire to the Phase 8–15 API for: Search & care categories | New | Patient Mobile | §2.2 | Search & care categories | Search by name, condition or category of care | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-09.01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Search by name, condition or category of care | Not Started
712 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.9 | PAT-09 | Patient app — search and care categories | PAT-09.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.2 | Search & care categories | Search by name, condition or category of care | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-09.02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Search by name, condition or category of care | Not Started
713 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.9 | PAT-09 | Patient app — search and care categories | PAT-09.04 | QA both platforms: Search & care categories matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.2 | Search & care categories | Search by name, condition or category of care | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-09.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Search by name, condition or category of care | Not Started
714 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.10 | PAT-10 | Patient app — search results | PAT-10.01 | UI: Search results screens (empty, loading, error, offline) | New | Patient Mobile | §2.2 | Search results | Clear list of available doctors | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | WEB-03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Clear list of available doctors | Not Started
715 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.10 | PAT-10 | Patient app — search results | PAT-10.02 | Wire to the Phase 8–15 API for: Search results | New | Patient Mobile | §2.2 | Search results | Clear list of available doctors | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-10.01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Clear list of available doctors | Not Started
716 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.10 | PAT-10 | Patient app — search results | PAT-10.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.2 | Search results | Clear list of available doctors | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-10.02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Clear list of available doctors | Not Started
717 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.10 | PAT-10 | Patient app — search results | PAT-10.04 | QA both platforms: Search results matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.2 | Search results | Clear list of available doctors | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-10.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Clear list of available doctors | Not Started
718 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.11 | PAT-11 | Patient app — discovery filters | PAT-11.01 | UI: Filters screens (empty, loading, error, offline) | New | Patient Mobile | §2.2 | Filters | Narrow by availability, fee, experience, language and location | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | WEB-03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Narrow by availability, fee, experience, language and location | Not Started
719 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.11 | PAT-11 | Patient app — discovery filters | PAT-11.02 | Wire to the Phase 8–15 API for: Filters | New | Patient Mobile | §2.2 | Filters | Narrow by availability, fee, experience, language and location | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-11.01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Narrow by availability, fee, experience, language and location | Not Started
720 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.11 | PAT-11 | Patient app — discovery filters | PAT-11.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.2 | Filters | Narrow by availability, fee, experience, language and location | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-11.02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Narrow by availability, fee, experience, language and location | Not Started
721 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.11 | PAT-11 | Patient app — discovery filters | PAT-11.04 | QA both platforms: Filters matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.2 | Filters | Narrow by availability, fee, experience, language and location | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-11.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Narrow by availability, fee, experience, language and location | Not Started
722 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.12 | PAT-12 | Patient app — doctor profile | PAT-12.01 | UI: Doctor profile screens (empty, loading, error, offline) | New | Patient Mobile | §2.2 | Doctor profile | Full profile with qualifications, experience and consultation fee | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | WEB-03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Full profile with qualifications, experience and consultation fee | Not Started
723 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.12 | PAT-12 | Patient app — doctor profile | PAT-12.02 | Wire to the Phase 8–15 API for: Doctor profile | New | Patient Mobile | §2.2 | Doctor profile | Full profile with qualifications, experience and consultation fee | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-12.01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Full profile with qualifications, experience and consultation fee | Not Started
724 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.12 | PAT-12 | Patient app — doctor profile | PAT-12.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.2 | Doctor profile | Full profile with qualifications, experience and consultation fee | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-12.02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Full profile with qualifications, experience and consultation fee | Not Started
725 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.12 | PAT-12 | Patient app — doctor profile | PAT-12.04 | QA both platforms: Doctor profile matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.2 | Doctor profile | Full profile with qualifications, experience and consultation fee | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-12.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Full profile with qualifications, experience and consultation fee | Not Started
726 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.13 | PAT-13 | Patient app — verified badge on doctor | PAT-13.01 | UI: Credentials & verification screens (empty, loading, error, offline) | New | Patient Mobile | §2.2 | Credentials & verification | Verified badge showing the doctor’s credentials are checked | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | TRU-03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Verified badge showing the doctor’s credentials are checked | Not Started
727 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.13 | PAT-13 | Patient app — verified badge on doctor | PAT-13.02 | Wire to the Phase 8–15 API for: Credentials & verification | New | Patient Mobile | §2.2 | Credentials & verification | Verified badge showing the doctor’s credentials are checked | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-13.01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Verified badge showing the doctor’s credentials are checked | Not Started
728 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.13 | PAT-13 | Patient app — verified badge on doctor | PAT-13.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.2 | Credentials & verification | Verified badge showing the doctor’s credentials are checked | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-13.02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Verified badge showing the doctor’s credentials are checked | Not Started
729 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.13 | PAT-13 | Patient app — verified badge on doctor | PAT-13.04 | QA both platforms: Credentials & verification matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.2 | Credentials & verification | Verified badge showing the doctor’s credentials are checked | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-13.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Verified badge showing the doctor’s credentials are checked | Not Started
730 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.14 | PAT-14 | Patient app — ranking explanation | PAT-14.01 | UI: Ranking explanation screens (empty, loading, error, offline) | New | Patient Mobile | §2.2 | Ranking explanation | Transparent explanation of why doctors appear in a given order | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | TRU-07 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Transparent explanation of why doctors appear in a given order | Not Started
731 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.14 | PAT-14 | Patient app — ranking explanation | PAT-14.02 | Wire to the Phase 8–15 API for: Ranking explanation | New | Patient Mobile | §2.2 | Ranking explanation | Transparent explanation of why doctors appear in a given order | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-14.01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Transparent explanation of why doctors appear in a given order | Not Started
732 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.14 | PAT-14 | Patient app — ranking explanation | PAT-14.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.2 | Ranking explanation | Transparent explanation of why doctors appear in a given order | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-14.02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Transparent explanation of why doctors appear in a given order | Not Started
733 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.14 | PAT-14 | Patient app — ranking explanation | PAT-14.04 | QA both platforms: Ranking explanation matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.2 | Ranking explanation | Transparent explanation of why doctors appear in a given order | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-14.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Transparent explanation of why doctors appear in a given order | Not Started
734 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.15 | PAT-15 | Patient app — health articles | PAT-15.01 | UI: Health articles screens (empty, loading, error, offline) | New | Patient Mobile | §2.2 | Health articles | Educational content to build trust and engagement | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | WEB-12 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Educational content to build trust and engagement | Not Started
735 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.15 | PAT-15 | Patient app — health articles | PAT-15.02 | Wire to the Phase 8–15 API for: Health articles | New | Patient Mobile | §2.2 | Health articles | Educational content to build trust and engagement | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-15.01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Educational content to build trust and engagement | Not Started
736 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.15 | PAT-15 | Patient app — health articles | PAT-15.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.2 | Health articles | Educational content to build trust and engagement | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-15.02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Educational content to build trust and engagement | Not Started
737 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.15 | PAT-15 | Patient app — health articles | PAT-15.04 | QA both platforms: Health articles matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.2 | Health articles | Educational content to build trust and engagement | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-15.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Educational content to build trust and engagement | Not Started
738 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.16 | PAT-16 | Patient app — slot picker | PAT-16.01 | UI: Slot picker screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Slot picker | See real available time slots and choose one | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | APT-08 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: See real available time slots and choose one | Not Started
739 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.16 | PAT-16 | Patient app — slot picker | PAT-16.02 | Wire to the Phase 8–15 API for: Slot picker | New | Patient Mobile | §2.3 | Slot picker | See real available time slots and choose one | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-16.01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: See real available time slots and choose one | Not Started
740 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.16 | PAT-16 | Patient app — slot picker | PAT-16.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Slot picker | See real available time slots and choose one | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-16.02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: See real available time slots and choose one | Not Started
741 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.16 | PAT-16 | Patient app — slot picker | PAT-16.04 | QA both platforms: Slot picker matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Slot picker | See real available time slots and choose one | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-16.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: See real available time slots and choose one | Not Started
742 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.17 | PAT-17 | Patient app — booking review and consent | PAT-17.01 | UI: Booking review & consent screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Booking review & consent | Confirm details and consent before booking | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | WEB-04 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Confirm details and consent before booking | Not Started
743 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.17 | PAT-17 | Patient app — booking review and consent | PAT-17.02 | Wire to the Phase 8–15 API for: Booking review & consent | New | Patient Mobile | §2.3 | Booking review & consent | Confirm details and consent before booking | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-17.01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Confirm details and consent before booking | Not Started
744 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.17 | PAT-17 | Patient app — booking review and consent | PAT-17.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Booking review & consent | Confirm details and consent before booking | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-17.02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Confirm details and consent before booking | Not Started
745 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.17 | PAT-17 | Patient app — booking review and consent | PAT-17.04 | QA both platforms: Booking review & consent matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Booking review & consent | Confirm details and consent before booking | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-17.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Confirm details and consent before booking | Not Started
746 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.18 | PAT-18 | Patient app — checkout | PAT-18.01 | UI: Checkout screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Checkout | Pay the consultation fee inside the app | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | PAY-03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Pay the consultation fee inside the app | Not Started
747 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.18 | PAT-18 | Patient app — checkout | PAT-18.02 | Wire to the Phase 8–15 API for: Checkout | New | Patient Mobile | §2.3 | Checkout | Pay the consultation fee inside the app | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-18.01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Pay the consultation fee inside the app | Not Started
748 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.18 | PAT-18 | Patient app — checkout | PAT-18.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Checkout | Pay the consultation fee inside the app | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-18.02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Pay the consultation fee inside the app | Not Started
749 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.18 | PAT-18 | Patient app — checkout | PAT-18.04 | QA both platforms: Checkout matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Checkout | Pay the consultation fee inside the app | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-18.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Pay the consultation fee inside the app | Not Started
750 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.19 | PAT-19 | Patient app — payment status | PAT-19.01 | UI: Payment status screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Payment status | Immediate confirmation of paid, pending or failed | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | PAY-08 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Immediate confirmation of paid, pending or failed | Not Started
751 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.19 | PAT-19 | Patient app — payment status | PAT-19.02 | Wire to the Phase 8–15 API for: Payment status | New | Patient Mobile | §2.3 | Payment status | Immediate confirmation of paid, pending or failed | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-19.01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Immediate confirmation of paid, pending or failed | Not Started
752 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.19 | PAT-19 | Patient app — payment status | PAT-19.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Payment status | Immediate confirmation of paid, pending or failed | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-19.02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Immediate confirmation of paid, pending or failed | Not Started
753 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.19 | PAT-19 | Patient app — payment status | PAT-19.04 | QA both platforms: Payment status matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Payment status | Immediate confirmation of paid, pending or failed | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-19.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Immediate confirmation of paid, pending or failed | Not Started
754 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.20 | PAT-20 | Patient app — appointment detail | PAT-20.01 | UI: Appointment detail screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Appointment detail | Full booking details in one place | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | — | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Full booking details in one place | Not Started
755 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.20 | PAT-20 | Patient app — appointment detail | PAT-20.02 | Wire to the Phase 8–15 API for: Appointment detail | New | Patient Mobile | §2.3 | Appointment detail | Full booking details in one place | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-20.01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Full booking details in one place | Not Started
756 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.20 | PAT-20 | Patient app — appointment detail | PAT-20.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Appointment detail | Full booking details in one place | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-20.02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Full booking details in one place | Not Started
757 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.20 | PAT-20 | Patient app — appointment detail | PAT-20.04 | QA both platforms: Appointment detail matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Appointment detail | Full booking details in one place | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-20.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Full booking details in one place | Not Started
758 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.21 | PAT-21 | Patient app — reschedule | PAT-21.01 | UI: Reschedule appointment screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Reschedule appointment | Move to another slot without calling the clinic | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | APT-05 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Move to another slot without calling the clinic | Not Started
759 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.21 | PAT-21 | Patient app — reschedule | PAT-21.02 | Wire to the Phase 8–15 API for: Reschedule appointment | New | Patient Mobile | §2.3 | Reschedule appointment | Move to another slot without calling the clinic | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-21.01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Move to another slot without calling the clinic | Not Started
760 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.21 | PAT-21 | Patient app — reschedule | PAT-21.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Reschedule appointment | Move to another slot without calling the clinic | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-21.02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Move to another slot without calling the clinic | Not Started
761 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.21 | PAT-21 | Patient app — reschedule | PAT-21.04 | QA both platforms: Reschedule appointment matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Reschedule appointment | Move to another slot without calling the clinic | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-21.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Move to another slot without calling the clinic | Not Started
762 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.22 | PAT-22 | Patient app — cancel | PAT-22.01 | UI: Cancel appointment screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Cancel appointment | Cancel with reason, refund handled per policy | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | APT-06 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Cancel with reason, refund handled per policy | Not Started
763 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.22 | PAT-22 | Patient app — cancel | PAT-22.02 | Wire to the Phase 8–15 API for: Cancel appointment | New | Patient Mobile | §2.3 | Cancel appointment | Cancel with reason, refund handled per policy | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-22.01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Cancel with reason, refund handled per policy | Not Started
764 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.22 | PAT-22 | Patient app — cancel | PAT-22.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Cancel appointment | Cancel with reason, refund handled per policy | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-22.02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Cancel with reason, refund handled per policy | Not Started
765 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.22 | PAT-22 | Patient app — cancel | PAT-22.04 | QA both platforms: Cancel appointment matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Cancel appointment | Cancel with reason, refund handled per policy | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-22.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Cancel with reason, refund handled per policy | Not Started
766 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.23 | PAT-23 | Patient app — waitlist offer | PAT-23.01 | UI: Waitlist offer screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Waitlist offer | Get offered a slot when one is freed by a cancellation | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | WEB-11 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Get offered a slot when one is freed by a cancellation | Not Started
767 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.23 | PAT-23 | Patient app — waitlist offer | PAT-23.02 | Wire to the Phase 8–15 API for: Waitlist offer | New | Patient Mobile | §2.3 | Waitlist offer | Get offered a slot when one is freed by a cancellation | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-23.01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Get offered a slot when one is freed by a cancellation | Not Started
768 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.23 | PAT-23 | Patient app — waitlist offer | PAT-23.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Waitlist offer | Get offered a slot when one is freed by a cancellation | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-23.02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Get offered a slot when one is freed by a cancellation | Not Started
769 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.23 | PAT-23 | Patient app — waitlist offer | PAT-23.04 | QA both platforms: Waitlist offer matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Waitlist offer | Get offered a slot when one is freed by a cancellation | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-23.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Get offered a slot when one is freed by a cancellation | Not Started
770 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.24 | PAT-24 | Patient app — instant consult request | PAT-24.01 | UI: Instant consult request screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Instant consult request | Request an immediate consultation with an available doctor | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | TEL-12 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Request an immediate consultation with an available doctor | Not Started
771 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.24 | PAT-24 | Patient app — instant consult request | PAT-24.02 | Wire to the Phase 8–15 API for: Instant consult request | New | Patient Mobile | §2.3 | Instant consult request | Request an immediate consultation with an available doctor | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-24.01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Request an immediate consultation with an available doctor | Not Started
772 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.24 | PAT-24 | Patient app — instant consult request | PAT-24.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Instant consult request | Request an immediate consultation with an available doctor | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-24.02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Request an immediate consultation with an available doctor | Not Started
773 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.24 | PAT-24 | Patient app — instant consult request | PAT-24.04 | QA both platforms: Instant consult request matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Instant consult request | Request an immediate consultation with an available doctor | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-24.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Request an immediate consultation with an available doctor | Not Started
774 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.25 | PAT-25 | Patient app — queue and doctor offer | PAT-25.01 | UI: Queue & doctor offer screens (empty, loading, error, offline) | New | Patient Mobile | §2.3 | Queue & doctor offer | See position in queue and accept an offered doctor | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | TEL-12 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: See position in queue and accept an offered doctor | Not Started
775 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.25 | PAT-25 | Patient app — queue and doctor offer | PAT-25.02 | Wire to the Phase 8–15 API for: Queue & doctor offer | New | Patient Mobile | §2.3 | Queue & doctor offer | See position in queue and accept an offered doctor | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-25.01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: See position in queue and accept an offered doctor | Not Started
776 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.25 | PAT-25 | Patient app — queue and doctor offer | PAT-25.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.3 | Queue & doctor offer | See position in queue and accept an offered doctor | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-25.02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: See position in queue and accept an offered doctor | Not Started
777 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.25 | PAT-25 | Patient app — queue and doctor offer | PAT-25.04 | QA both platforms: Queue & doctor offer matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.3 | Queue & doctor offer | See position in queue and accept an offered doctor | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-25.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: See position in queue and accept an offered doctor | Not Started
778 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.26 | PAT-26 | Patient app — device check | PAT-26.01 | UI: Device check screens (empty, loading, error, offline) | New | Patient Mobile | §2.4 | Device check | Camera, microphone and network checked before the call | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | TEL-05 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Camera, microphone and network checked before the call | Not Started
779 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.26 | PAT-26 | Patient app — device check | PAT-26.02 | Wire to the Phase 8–15 API for: Device check | New | Patient Mobile | §2.4 | Device check | Camera, microphone and network checked before the call | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-26.01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Camera, microphone and network checked before the call | Not Started
780 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.26 | PAT-26 | Patient app — device check | PAT-26.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.4 | Device check | Camera, microphone and network checked before the call | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-26.02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Camera, microphone and network checked before the call | Not Started
781 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.26 | PAT-26 | Patient app — device check | PAT-26.04 | QA both platforms: Device check matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.4 | Device check | Camera, microphone and network checked before the call | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-26.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Camera, microphone and network checked before the call | Not Started
782 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.27 | PAT-27 | Patient app — waiting room | PAT-27.01 | UI: Waiting room screens (empty, loading, error, offline) | New | Patient Mobile | §2.4 | Waiting room | Wait with live status until the doctor joins | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | TEL-06 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Wait with live status until the doctor joins | Not Started
783 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.27 | PAT-27 | Patient app — waiting room | PAT-27.02 | Wire to the Phase 8–15 API for: Waiting room | New | Patient Mobile | §2.4 | Waiting room | Wait with live status until the doctor joins | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-27.01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Wait with live status until the doctor joins | Not Started
784 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.27 | PAT-27 | Patient app — waiting room | PAT-27.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.4 | Waiting room | Wait with live status until the doctor joins | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-27.02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Wait with live status until the doctor joins | Not Started
785 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.27 | PAT-27 | Patient app — waiting room | PAT-27.04 | QA both platforms: Waiting room matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.4 | Waiting room | Wait with live status until the doctor joins | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-27.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Wait with live status until the doctor joins | Not Started
786 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.28 | PAT-28 | Patient app — live video | PAT-28.01 | UI: Live video consultation screens (empty, loading, error, offline) | New | Patient Mobile | §2.4 | Live video consultation | Face-to-face consultation from home | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | TEL-04 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Face-to-face consultation from home | Not Started
787 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.28 | PAT-28 | Patient app — live video | PAT-28.02 | Wire to the Phase 8–15 API for: Live video consultation | New | Patient Mobile | §2.4 | Live video consultation | Face-to-face consultation from home | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-28.01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Face-to-face consultation from home | Not Started
788 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.28 | PAT-28 | Patient app — live video | PAT-28.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.4 | Live video consultation | Face-to-face consultation from home | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-28.02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Face-to-face consultation from home | Not Started
789 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.28 | PAT-28 | Patient app — live video | PAT-28.04 | QA both platforms: Live video consultation matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.4 | Live video consultation | Face-to-face consultation from home | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-28.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Face-to-face consultation from home | Not Started
790 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.29 | PAT-29 | Patient app — recording consent | PAT-29.01 | UI: Recording consent screens (empty, loading, error, offline) | New | Patient Mobile | §2.4 | Recording consent | Explicit consent requested before any recording | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | TEL-07 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Explicit consent requested before any recording | Not Started
791 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.29 | PAT-29 | Patient app — recording consent | PAT-29.02 | Wire to the Phase 8–15 API for: Recording consent | New | Patient Mobile | §2.4 | Recording consent | Explicit consent requested before any recording | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-29.01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Explicit consent requested before any recording | Not Started
792 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.29 | PAT-29 | Patient app — recording consent | PAT-29.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.4 | Recording consent | Explicit consent requested before any recording | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-29.02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Explicit consent requested before any recording | Not Started
793 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.29 | PAT-29 | Patient app — recording consent | PAT-29.04 | QA both platforms: Recording consent matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.4 | Recording consent | Explicit consent requested before any recording | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-29.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Explicit consent requested before any recording | Not Started
794 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.30 | PAT-30 | Patient app — join failure fallback | PAT-30.01 | UI: Fallback & join failure handling screens (empty, loading, error, offline) | New | Patient Mobile | §2.4 | Fallback & join failure handling | Clear guidance if the call fails, with options to retry | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | TEL-09 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Clear guidance if the call fails, with options to retry | Not Started
795 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.30 | PAT-30 | Patient app — join failure fallback | PAT-30.02 | Wire to the Phase 8–15 API for: Fallback & join failure handling | New | Patient Mobile | §2.4 | Fallback & join failure handling | Clear guidance if the call fails, with options to retry | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-30.01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Clear guidance if the call fails, with options to retry | Not Started
796 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.30 | PAT-30 | Patient app — join failure fallback | PAT-30.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.4 | Fallback & join failure handling | Clear guidance if the call fails, with options to retry | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-30.02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Clear guidance if the call fails, with options to retry | Not Started
797 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.30 | PAT-30 | Patient app — join failure fallback | PAT-30.04 | QA both platforms: Fallback & join failure handling matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.4 | Fallback & join failure handling | Clear guidance if the call fails, with options to retry | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-30.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Clear guidance if the call fails, with options to retry | Not Started
798 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.31 | PAT-31 | Patient app — case-linked chat | PAT-31.01 | UI: Case-linked chat screens (empty, loading, error, offline) | New | Patient Mobile | §2.4 | Case-linked chat | Chat tied to the consultation, not a loose message thread | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | TEL-10 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Chat tied to the consultation, not a loose message thread | Not Started
799 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.31 | PAT-31 | Patient app — case-linked chat | PAT-31.02 | Wire to the Phase 8–15 API for: Case-linked chat | New | Patient Mobile | §2.4 | Case-linked chat | Chat tied to the consultation, not a loose message thread | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-31.01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Chat tied to the consultation, not a loose message thread | Not Started
800 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.31 | PAT-31 | Patient app — case-linked chat | PAT-31.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.4 | Case-linked chat | Chat tied to the consultation, not a loose message thread | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-31.02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Chat tied to the consultation, not a loose message thread | Not Started
801 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.31 | PAT-31 | Patient app — case-linked chat | PAT-31.04 | QA both platforms: Case-linked chat matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.4 | Case-linked chat | Chat tied to the consultation, not a loose message thread | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-31.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Chat tied to the consultation, not a loose message thread | Not Started
802 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.32 | PAT-32 | Patient app — consultation summary | PAT-32.01 | UI: Consultation summary screens (empty, loading, error, offline) | New | Patient Mobile | §2.4 | Consultation summary | Written summary available immediately after the call | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | TEL-11 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Written summary available immediately after the call | Not Started
803 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.32 | PAT-32 | Patient app — consultation summary | PAT-32.02 | Wire to the Phase 8–15 API for: Consultation summary | New | Patient Mobile | §2.4 | Consultation summary | Written summary available immediately after the call | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-32.01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Written summary available immediately after the call | Not Started
804 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.32 | PAT-32 | Patient app — consultation summary | PAT-32.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.4 | Consultation summary | Written summary available immediately after the call | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-32.02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Written summary available immediately after the call | Not Started
805 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.32 | PAT-32 | Patient app — consultation summary | PAT-32.04 | QA both platforms: Consultation summary matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.4 | Consultation summary | Written summary available immediately after the call | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-32.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Written summary available immediately after the call | Not Started
806 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.33 | PAT-33 | Patient app — rejoin | PAT-33.01 | UI: Rejoin after dropped call screens (empty, loading, error, offline) | New | Patient Mobile | §2.4 | Rejoin after dropped call | Rejoin the same consultation if the connection drops | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | TEL-08 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Rejoin the same consultation if the connection drops | Not Started
807 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.33 | PAT-33 | Patient app — rejoin | PAT-33.02 | Wire to the Phase 8–15 API for: Rejoin after dropped call | New | Patient Mobile | §2.4 | Rejoin after dropped call | Rejoin the same consultation if the connection drops | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-33.01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Rejoin the same consultation if the connection drops | Not Started
808 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.33 | PAT-33 | Patient app — rejoin | PAT-33.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.4 | Rejoin after dropped call | Rejoin the same consultation if the connection drops | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-33.02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Rejoin the same consultation if the connection drops | Not Started
809 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.33 | PAT-33 | Patient app — rejoin | PAT-33.04 | QA both platforms: Rejoin after dropped call matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.4 | Rejoin after dropped call | Rejoin the same consultation if the connection drops | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-33.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Rejoin the same consultation if the connection drops | Not Started
810 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.34 | PAT-34 | Patient app — records timeline | PAT-34.01 | UI: Records timeline screens (empty, loading, error, offline) | New | Patient Mobile | §2.5 | Records timeline | Complete visit history in date order | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | CON-03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Complete visit history in date order | Not Started
811 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.34 | PAT-34 | Patient app — records timeline | PAT-34.02 | Wire to the Phase 8–15 API for: Records timeline | New | Patient Mobile | §2.5 | Records timeline | Complete visit history in date order | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-34.01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Complete visit history in date order | Not Started
812 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.34 | PAT-34 | Patient app — records timeline | PAT-34.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.5 | Records timeline | Complete visit history in date order | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-34.02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Complete visit history in date order | Not Started
813 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.34 | PAT-34 | Patient app — records timeline | PAT-34.04 | QA both platforms: Records timeline matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.5 | Records timeline | Complete visit history in date order | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-34.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Complete visit history in date order | Not Started
814 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.35 | PAT-35 | Patient app — consultation note (summary, not private notes) | PAT-35.01 | UI: Consultation note screens (empty, loading, error, offline) | New | Patient Mobile | §2.5 | Consultation note | Doctor’s notes for each visit | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | CON-03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Doctor’s notes for each visit | Not Started
815 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.35 | PAT-35 | Patient app — consultation note (summary, not private notes) | PAT-35.02 | Wire to the Phase 8–15 API for: Consultation note | New | Patient Mobile | §2.5 | Consultation note | Doctor’s notes for each visit | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-35.01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Doctor’s notes for each visit | Not Started
816 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.35 | PAT-35 | Patient app — consultation note (summary, not private notes) | PAT-35.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.5 | Consultation note | Doctor’s notes for each visit | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-35.02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Doctor’s notes for each visit | Not Started
817 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.35 | PAT-35 | Patient app — consultation note (summary, not private notes) | PAT-35.04 | QA both platforms: Consultation note matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.5 | Consultation note | Doctor’s notes for each visit | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-35.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Doctor’s notes for each visit | Not Started
818 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.36 | PAT-36 | Patient app — signed eRx (codes until pharmacy accept) | PAT-36.01 | UI: Signed digital prescription screens (empty, loading, error, offline) | New | Patient Mobile | §2.5 | Signed digital prescription | Official prescription issued by the doctor | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | ERX-06 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Official prescription issued by the doctor | Not Started
819 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.36 | PAT-36 | Patient app — signed eRx (codes until pharmacy accept) | PAT-36.02 | Wire to the Phase 8–15 API for: Signed digital prescription | New | Patient Mobile | §2.5 | Signed digital prescription | Official prescription issued by the doctor | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-36.01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Official prescription issued by the doctor | Not Started
820 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.36 | PAT-36 | Patient app — signed eRx (codes until pharmacy accept) | PAT-36.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.5 | Signed digital prescription | Official prescription issued by the doctor | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-36.02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Official prescription issued by the doctor | Not Started
821 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.36 | PAT-36 | Patient app — signed eRx (codes until pharmacy accept) | PAT-36.04 | QA both platforms: Signed digital prescription matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.5 | Signed digital prescription | Official prescription issued by the doctor | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-36.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Official prescription issued by the doctor | Not Started
822 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.37 | PAT-37 | Patient app — document upload | PAT-37.01 | UI: Document upload screens (empty, loading, error, offline) | New | Patient Mobile | §2.5 | Document upload | Upload reports, scans and previous prescriptions | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | CON-03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Upload reports, scans and previous prescriptions | Not Started
823 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.37 | PAT-37 | Patient app — document upload | PAT-37.02 | Wire to the Phase 8–15 API for: Document upload | New | Patient Mobile | §2.5 | Document upload | Upload reports, scans and previous prescriptions | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-37.01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Upload reports, scans and previous prescriptions | Not Started
824 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.37 | PAT-37 | Patient app — document upload | PAT-37.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.5 | Document upload | Upload reports, scans and previous prescriptions | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-37.02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Upload reports, scans and previous prescriptions | Not Started
825 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.37 | PAT-37 | Patient app — document upload | PAT-37.04 | QA both platforms: Document upload matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.5 | Document upload | Upload reports, scans and previous prescriptions | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-37.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Upload reports, scans and previous prescriptions | Not Started
826 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.38 | PAT-38 | Patient app — follow-up plan and tasks | PAT-38.01 | UI: Follow-up plan & tasks screens (empty, loading, error, offline) | New | Patient Mobile | §2.6 | Follow-up plan & tasks | Clear next steps after each consultation | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | CON-04 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Clear next steps after each consultation | Not Started
827 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.38 | PAT-38 | Patient app — follow-up plan and tasks | PAT-38.02 | Wire to the Phase 8–15 API for: Follow-up plan & tasks | New | Patient Mobile | §2.6 | Follow-up plan & tasks | Clear next steps after each consultation | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-38.01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Clear next steps after each consultation | Not Started
828 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.38 | PAT-38 | Patient app — follow-up plan and tasks | PAT-38.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.6 | Follow-up plan & tasks | Clear next steps after each consultation | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-38.02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Clear next steps after each consultation | Not Started
829 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.38 | PAT-38 | Patient app — follow-up plan and tasks | PAT-38.04 | QA both platforms: Follow-up plan & tasks matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.6 | Follow-up plan & tasks | Clear next steps after each consultation | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-38.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Clear next steps after each consultation | Not Started
830 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.39 | PAT-39 | Patient app — symptom diary | PAT-39.01 | UI: Symptom diary screens (empty, loading, error, offline) | New | Patient Mobile | §2.6 | Symptom diary | Record symptoms between visits | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | CON-05 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Record symptoms between visits | Not Started
831 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.39 | PAT-39 | Patient app — symptom diary | PAT-39.02 | Wire to the Phase 8–15 API for: Symptom diary | New | Patient Mobile | §2.6 | Symptom diary | Record symptoms between visits | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-39.01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Record symptoms between visits | Not Started
832 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.39 | PAT-39 | Patient app — symptom diary | PAT-39.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.6 | Symptom diary | Record symptoms between visits | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-39.02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Record symptoms between visits | Not Started
833 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.39 | PAT-39 | Patient app — symptom diary | PAT-39.04 | QA both platforms: Symptom diary matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.6 | Symptom diary | Record symptoms between visits | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-39.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Record symptoms between visits | Not Started
834 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.40 | PAT-40 | Patient app — progress tracking | PAT-40.01 | UI: Progress tracking screens (empty, loading, error, offline) | New | Patient Mobile | §2.6 | Progress tracking | See improvement over time across visits | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | CON-06 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: See improvement over time across visits | Not Started
835 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.40 | PAT-40 | Patient app — progress tracking | PAT-40.02 | Wire to the Phase 8–15 API for: Progress tracking | New | Patient Mobile | §2.6 | Progress tracking | See improvement over time across visits | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-40.01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: See improvement over time across visits | Not Started
836 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.40 | PAT-40 | Patient app — progress tracking | PAT-40.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.6 | Progress tracking | See improvement over time across visits | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-40.02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: See improvement over time across visits | Not Started
837 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.40 | PAT-40 | Patient app — progress tracking | PAT-40.04 | QA both platforms: Progress tracking matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.6 | Progress tracking | See improvement over time across visits | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-40.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: See improvement over time across visits | Not Started
838 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.41 | PAT-41 | Patient app — medicines tab | PAT-41.01 | UI: Medicines tab screens (empty, loading, error, offline) | New | Patient Mobile | §2.7 | Medicines tab | All medicine orders in one place | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | MED-16 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: All medicine orders in one place | Not Started
839 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.41 | PAT-41 | Patient app — medicines tab | PAT-41.02 | Wire to the Phase 8–15 API for: Medicines tab | New | Patient Mobile | §2.7 | Medicines tab | All medicine orders in one place | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-41.01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: All medicine orders in one place | Not Started
840 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.41 | PAT-41 | Patient app — medicines tab | PAT-41.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.7 | Medicines tab | All medicine orders in one place | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-41.02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: All medicine orders in one place | Not Started
841 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.41 | PAT-41 | Patient app — medicines tab | PAT-41.04 | QA both platforms: Medicines tab matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.7 | Medicines tab | All medicine orders in one place | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-41.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: All medicine orders in one place | Not Started
842 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.42 | PAT-42 | Patient app — start HomeoMeds order from eRx | PAT-42.01 | UI: Order start screens (empty, loading, error, offline) | New | Patient Mobile | §2.7 | Order start | Start an order directly from the prescription | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | MED-04 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Start an order directly from the prescription | Not Started
843 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.42 | PAT-42 | Patient app — start HomeoMeds order from eRx | PAT-42.02 | Wire to the Phase 8–15 API for: Order start | New | Patient Mobile | §2.7 | Order start | Start an order directly from the prescription | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-42.01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Start an order directly from the prescription | Not Started
844 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.42 | PAT-42 | Patient app — start HomeoMeds order from eRx | PAT-42.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.7 | Order start | Start an order directly from the prescription | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-42.02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Start an order directly from the prescription | Not Started
845 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.42 | PAT-42 | Patient app — start HomeoMeds order from eRx | PAT-42.04 | QA both platforms: Order start matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.7 | Order start | Start an order directly from the prescription | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-42.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Start an order directly from the prescription | Not Started
846 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.43 | PAT-43 | Patient app — pharmacy selection and quote | PAT-43.01 | UI: Pharmacy selection & quote screens (empty, loading, error, offline) | New | Patient Mobile | §2.7 | Pharmacy selection & quote | Choose a licensed pharmacy and see the price before paying | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | MED-08 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Choose a licensed pharmacy and see the price before paying | Not Started
847 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.43 | PAT-43 | Patient app — pharmacy selection and quote | PAT-43.02 | Wire to the Phase 8–15 API for: Pharmacy selection & quote | New | Patient Mobile | §2.7 | Pharmacy selection & quote | Choose a licensed pharmacy and see the price before paying | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-43.01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Choose a licensed pharmacy and see the price before paying | Not Started
848 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.43 | PAT-43 | Patient app — pharmacy selection and quote | PAT-43.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.7 | Pharmacy selection & quote | Choose a licensed pharmacy and see the price before paying | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-43.02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Choose a licensed pharmacy and see the price before paying | Not Started
849 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.43 | PAT-43 | Patient app — pharmacy selection and quote | PAT-43.04 | QA both platforms: Pharmacy selection & quote matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.7 | Pharmacy selection & quote | Choose a licensed pharmacy and see the price before paying | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-43.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Choose a licensed pharmacy and see the price before paying | Not Started
850 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.44 | PAT-44 | Patient app — order review and consent | PAT-44.01 | UI: Order review & consent screens (empty, loading, error, offline) | New | Patient Mobile | §2.7 | Order review & consent | Confirm and consent before the prescription is shared | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | MED-15 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Confirm and consent before the prescription is shared | Not Started
851 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.44 | PAT-44 | Patient app — order review and consent | PAT-44.02 | Wire to the Phase 8–15 API for: Order review & consent | New | Patient Mobile | §2.7 | Order review & consent | Confirm and consent before the prescription is shared | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-44.01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Confirm and consent before the prescription is shared | Not Started
852 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.44 | PAT-44 | Patient app — order review and consent | PAT-44.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.7 | Order review & consent | Confirm and consent before the prescription is shared | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-44.02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Confirm and consent before the prescription is shared | Not Started
853 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.44 | PAT-44 | Patient app — order review and consent | PAT-44.04 | QA both platforms: Order review & consent matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.7 | Order review & consent | Confirm and consent before the prescription is shared | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-44.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Confirm and consent before the prescription is shared | Not Started
854 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.45 | PAT-45 | Patient app — order tracking | PAT-45.01 | UI: Order tracking screens (empty, loading, error, offline) | New | Patient Mobile | §2.7 | Order tracking | Live status from accepted to delivered | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | MED-10 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Live status from accepted to delivered | Not Started
855 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.45 | PAT-45 | Patient app — order tracking | PAT-45.02 | Wire to the Phase 8–15 API for: Order tracking | New | Patient Mobile | §2.7 | Order tracking | Live status from accepted to delivered | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-45.01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Live status from accepted to delivered | Not Started
856 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.45 | PAT-45 | Patient app — order tracking | PAT-45.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.7 | Order tracking | Live status from accepted to delivered | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-45.02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Live status from accepted to delivered | Not Started
857 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.45 | PAT-45 | Patient app — order tracking | PAT-45.04 | QA both platforms: Order tracking matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.7 | Order tracking | Live status from accepted to delivered | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-45.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Live status from accepted to delivered | Not Started
858 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.46 | PAT-46 | Patient app — order detail and refill | PAT-46.01 | UI: Order detail & refill screens (empty, loading, error, offline) | New | Patient Mobile | §2.7 | Order detail & refill | Full order history and one-tap refill request | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | MED-14 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Full order history and one-tap refill request | Not Started
859 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.46 | PAT-46 | Patient app — order detail and refill | PAT-46.02 | Wire to the Phase 8–15 API for: Order detail & refill | New | Patient Mobile | §2.7 | Order detail & refill | Full order history and one-tap refill request | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-46.01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Full order history and one-tap refill request | Not Started
860 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.46 | PAT-46 | Patient app — order detail and refill | PAT-46.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.7 | Order detail & refill | Full order history and one-tap refill request | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-46.02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Full order history and one-tap refill request | Not Started
861 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.46 | PAT-46 | Patient app — order detail and refill | PAT-46.04 | QA both platforms: Order detail & refill matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.7 | Order detail & refill | Full order history and one-tap refill request | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-46.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Full order history and one-tap refill request | Not Started
862 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.47 | PAT-47 | Patient app — write a review | PAT-47.01 | UI: Write a review screens (empty, loading, error, offline) | New | Patient Mobile | §2.8 | Write a review | Rate and review the consultation | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | TRU-05 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Rate and review the consultation | Not Started
863 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.47 | PAT-47 | Patient app — write a review | PAT-47.02 | Wire to the Phase 8–15 API for: Write a review | New | Patient Mobile | §2.8 | Write a review | Rate and review the consultation | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-47.01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Rate and review the consultation | Not Started
864 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.47 | PAT-47 | Patient app — write a review | PAT-47.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.8 | Write a review | Rate and review the consultation | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-47.02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Rate and review the consultation | Not Started
865 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.47 | PAT-47 | Patient app — write a review | PAT-47.04 | QA both platforms: Write a review matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.8 | Write a review | Rate and review the consultation | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-47.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Rate and review the consultation | Not Started
866 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.48 | PAT-48 | Patient app — my reviews and appeal | PAT-48.01 | UI: My reviews & appeal screens (empty, loading, error, offline) | New | Patient Mobile | §2.8 | My reviews & appeal | Manage reviews and raise an appeal | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | TRU-06 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Manage reviews and raise an appeal | Not Started
867 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.48 | PAT-48 | Patient app — my reviews and appeal | PAT-48.02 | Wire to the Phase 8–15 API for: My reviews & appeal | New | Patient Mobile | §2.8 | My reviews & appeal | Manage reviews and raise an appeal | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-48.01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Manage reviews and raise an appeal | Not Started
868 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.48 | PAT-48 | Patient app — my reviews and appeal | PAT-48.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.8 | My reviews & appeal | Manage reviews and raise an appeal | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-48.02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Manage reviews and raise an appeal | Not Started
869 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.48 | PAT-48 | Patient app — my reviews and appeal | PAT-48.04 | QA both platforms: My reviews & appeal matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.8 | My reviews & appeal | Manage reviews and raise an appeal | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-48.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Manage reviews and raise an appeal | Not Started
870 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.49 | PAT-49 | Patient app — payments and refunds | PAT-49.01 | UI: Payments & refunds screens (empty, loading, error, offline) | New | Patient Mobile | §2.8 | Payments & refunds | Full payment history and refund status | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | CON-08 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Full payment history and refund status | Not Started
871 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.49 | PAT-49 | Patient app — payments and refunds | PAT-49.02 | Wire to the Phase 8–15 API for: Payments & refunds | New | Patient Mobile | §2.8 | Payments & refunds | Full payment history and refund status | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-49.01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Full payment history and refund status | Not Started
872 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.49 | PAT-49 | Patient app — payments and refunds | PAT-49.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.8 | Payments & refunds | Full payment history and refund status | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-49.02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Full payment history and refund status | Not Started
873 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.49 | PAT-49 | Patient app — payments and refunds | PAT-49.04 | QA both platforms: Payments & refunds matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.8 | Payments & refunds | Full payment history and refund status | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-49.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Full payment history and refund status | Not Started
874 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.50 | PAT-50 | Patient app — profile and settings | PAT-50.01 | UI: Profile & settings screens (empty, loading, error, offline) | New | Patient Mobile | §2.8 | Profile & settings | Manage personal details and preferences | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | CON-10 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Manage personal details and preferences | Not Started
875 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.50 | PAT-50 | Patient app — profile and settings | PAT-50.02 | Wire to the Phase 8–15 API for: Profile & settings | New | Patient Mobile | §2.8 | Profile & settings | Manage personal details and preferences | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-50.01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Manage personal details and preferences | Not Started
876 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.50 | PAT-50 | Patient app — profile and settings | PAT-50.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.8 | Profile & settings | Manage personal details and preferences | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-50.02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Manage personal details and preferences | Not Started
877 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.50 | PAT-50 | Patient app — profile and settings | PAT-50.04 | QA both platforms: Profile & settings matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.8 | Profile & settings | Manage personal details and preferences | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-50.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Manage personal details and preferences | Not Started
878 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.51 | PAT-51 | Patient app — consent centre and data rights | PAT-51.01 | UI: Consent centre & data rights screens (empty, loading, error, offline) | New | Patient Mobile | §2.8 | Consent centre & data rights | View, manage and withdraw consents; request data | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | CON-07 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: View, manage and withdraw consents; request data | Not Started
879 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.51 | PAT-51 | Patient app — consent centre and data rights | PAT-51.02 | Wire to the Phase 8–15 API for: Consent centre & data rights | New | Patient Mobile | §2.8 | Consent centre & data rights | View, manage and withdraw consents; request data | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-51.01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: View, manage and withdraw consents; request data | Not Started
880 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.51 | PAT-51 | Patient app — consent centre and data rights | PAT-51.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.8 | Consent centre & data rights | View, manage and withdraw consents; request data | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-51.02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: View, manage and withdraw consents; request data | Not Started
881 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.51 | PAT-51 | Patient app — consent centre and data rights | PAT-51.04 | QA both platforms: Consent centre & data rights matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.8 | Consent centre & data rights | View, manage and withdraw consents; request data | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-51.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: View, manage and withdraw consents; request data | Not Started
882 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.52 | PAT-52 | Patient app — notifications centre | PAT-52.01 | UI: Notifications centre screens (empty, loading, error, offline) | New | Patient Mobile | §2.8 | Notifications centre | All alerts in one place | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | COM-05 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: All alerts in one place | Not Started
883 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.52 | PAT-52 | Patient app — notifications centre | PAT-52.02 | Wire to the Phase 8–15 API for: Notifications centre | New | Patient Mobile | §2.8 | Notifications centre | All alerts in one place | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-52.01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: All alerts in one place | Not Started
884 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.52 | PAT-52 | Patient app — notifications centre | PAT-52.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.8 | Notifications centre | All alerts in one place | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-52.02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: All alerts in one place | Not Started
885 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.52 | PAT-52 | Patient app — notifications centre | PAT-52.04 | QA both platforms: Notifications centre matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.8 | Notifications centre | All alerts in one place | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-52.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: All alerts in one place | Not Started
886 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.53 | PAT-53 | Patient app — help centre and tickets | PAT-53.01 | UI: Help centre & support tickets screens (empty, loading, error, offline) | New | Patient Mobile | §2.9 | Help centre & support tickets | Raise an issue and track it to resolution | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | SUP-01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Raise an issue and track it to resolution | Not Started
887 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.53 | PAT-53 | Patient app — help centre and tickets | PAT-53.02 | Wire to the Phase 8–15 API for: Help centre & support tickets | New | Patient Mobile | §2.9 | Help centre & support tickets | Raise an issue and track it to resolution | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-53.01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Raise an issue and track it to resolution | Not Started
888 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.53 | PAT-53 | Patient app — help centre and tickets | PAT-53.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.9 | Help centre & support tickets | Raise an issue and track it to resolution | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-53.02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Raise an issue and track it to resolution | Not Started
889 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.53 | PAT-53 | Patient app — help centre and tickets | PAT-53.04 | QA both platforms: Help centre & support tickets matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.9 | Help centre & support tickets | Raise an issue and track it to resolution | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-53.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Raise an issue and track it to resolution | Not Started
890 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.54 | PAT-54 | Patient app — physical clinic booking | PAT-54.01 | UI: Physical clinic appointment screens (empty, loading, error, offline) | New | Patient Mobile | §2.9 | Physical clinic appointment | Book an in-person visit as well as online | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | CON-09 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Book an in-person visit as well as online | Not Started
891 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.54 | PAT-54 | Patient app — physical clinic booking | PAT-54.02 | Wire to the Phase 8–15 API for: Physical clinic appointment | New | Patient Mobile | §2.9 | Physical clinic appointment | Book an in-person visit as well as online | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-54.01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Book an in-person visit as well as online | Not Started
892 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.54 | PAT-54 | Patient app — physical clinic booking | PAT-54.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.9 | Physical clinic appointment | Book an in-person visit as well as online | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-54.02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Book an in-person visit as well as online | Not Started
893 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.54 | PAT-54 | Patient app — physical clinic booking | PAT-54.04 | QA both platforms: Physical clinic appointment matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.9 | Physical clinic appointment | Book an in-person visit as well as online | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-54.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Book an in-person visit as well as online | Not Started
894 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.55 | PAT-55 | Patient app — assisted booking request | PAT-55.01 | UI: Assisted booking screens (empty, loading, error, offline) | New | Patient Mobile | §2.9 | Assisted booking | Help for patients who need support booking | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | SUP-07 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Help for patients who need support booking | Not Started
895 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.55 | PAT-55 | Patient app — assisted booking request | PAT-55.02 | Wire to the Phase 8–15 API for: Assisted booking | New | Patient Mobile | §2.9 | Assisted booking | Help for patients who need support booking | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-55.01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Help for patients who need support booking | Not Started
896 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.55 | PAT-55 | Patient app — assisted booking request | PAT-55.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.9 | Assisted booking | Help for patients who need support booking | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-55.02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Help for patients who need support booking | Not Started
897 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.55 | PAT-55 | Patient app — assisted booking request | PAT-55.04 | QA both platforms: Assisted booking matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.9 | Assisted booking | Help for patients who need support booking | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-55.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Help for patients who need support booking | Not Started
898 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.56 | PAT-56 | Patient app — low-data mode | PAT-56.01 | UI: Low-data mode screens (empty, loading, error, offline) | New | Patient Mobile | §2.9 | Low-data mode | Works on slow or limited connections | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | — | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Works on slow or limited connections | Not Started
899 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.56 | PAT-56 | Patient app — low-data mode | PAT-56.02 | Wire to the Phase 8–15 API for: Low-data mode | New | Patient Mobile | §2.9 | Low-data mode | Works on slow or limited connections | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-56.01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Works on slow or limited connections | Not Started
900 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.56 | PAT-56 | Patient app — low-data mode | PAT-56.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.9 | Low-data mode | Works on slow or limited connections | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-56.02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Works on slow or limited connections | Not Started
901 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.56 | PAT-56 | Patient app — low-data mode | PAT-56.04 | QA both platforms: Low-data mode matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.9 | Low-data mode | Works on slow or limited connections | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-56.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Works on slow or limited connections | Not Started
902 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.57 | PAT-57 | Patient app — push notifications | PAT-57.01 | UI: Push notifications screens (empty, loading, error, offline) | New | Patient Mobile | §2.9 | Push notifications | Booking confirmations, reminders, doctor ready, prescription issued, order updates | Patient Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | COM-03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Booking confirmations, reminders, doctor ready, prescription issued, order updates | Not Started
903 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.57 | PAT-57 | Patient app — push notifications | PAT-57.02 | Wire to the Phase 8–15 API for: Push notifications | New | Patient Mobile | §2.9 | Push notifications | Booking confirmations, reminders, doctor ready, prescription issued, order updates | Patient Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | PAT-57.01 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Booking confirmations, reminders, doctor ready, prescription issued, order updates | Not Started
904 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.57 | PAT-57 | Patient app — push notifications | PAT-57.03 | Low-data assets where applicable; accessibility labels | New | Patient Mobile | §2.9 | Push notifications | Booking confirmations, reminders, doctor ready, prescription issued, order updates | Patient Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | PAT-57.02 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Booking confirmations, reminders, doctor ready, prescription issued, order updates | Not Started
905 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.57 | PAT-57 | Patient app — push notifications | PAT-57.04 | QA both platforms: Push notifications matches website/API status; no local fake paid/signed state | Regression | Patient Mobile | §2.9 | Push notifications | Booking confirmations, reminders, doctor ready, prescription issued, order updates | Patient Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | PAT-57.03 | No patient app in repos | Native/RN screens on existing APIs; iOS and Android parity | iOS and Android: Booking confirmations, reminders, doctor ready, prescription issued, order updates | Not Started
906 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.58 | PAT-58 | Patient app — iOS and Android store release, device matrix, and parity QA | PAT-58.01 | CI: iOS + Android release builds; env pointing to .NET 8 | New | Patient Mobile | §2 + §18 | Patient mobile app iOS and Android | iOS and Android — onboarding, discovery, booking, payment, video consultation, records, prescriptions, follow-up, medicines, reviews, support, notifications | Patient Mobile App | Mobile | No | No | No | No | Yes | No | P0 | L | — | No app | Store builds; crash-free join; feature parity checklist against every §2 row | Parity matrix signed: every §2 feature works on both OS | Not Started
907 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.58 | PAT-58 | Patient app — iOS and Android store release, device matrix, and parity QA | PAT-58.02 | Parity QA spreadsheet: each PAT-01..57 on both OS | Regression | Patient Mobile | §2 + §18 | Patient mobile app iOS and Android | iOS and Android — onboarding, discovery, booking, payment, video consultation, records, prescriptions, follow-up, medicines, reviews, support, notifications | Patient Mobile App | QA | No | No | No | No | Yes | No | P0 | L | PAT-58.01 | No app | Store builds; crash-free join; feature parity checklist against every §2 row | Parity matrix signed: every §2 feature works on both OS | Not Started
908 | 16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 16.58 | PAT-58 | Patient app — iOS and Android store release, device matrix, and parity QA | PAT-58.03 | Crashlytics/Sentry equivalent for patient app | New Integration | Patient Mobile | §2 + §18 | Patient mobile app iOS and Android | iOS and Android — onboarding, discovery, booking, payment, video consultation, records, prescriptions, follow-up, medicines, reviews, support, notifications | Patient Mobile App | Mobile | No | No | No | No | Yes | Yes | P0 | S | PAT-58.02 | No app | Store builds; crash-free join; feature parity checklist against every §2 row | Parity matrix signed: every §2 feature works on both OS | Not Started
909 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.1 | DMO-01 | Doctor app — login & identity (same login and same account as the web portal) | DMO-01.01 | Login screen (password or OTP-to-registered mobile) | New | Doctor Mobile | §3 | Login & identity | Same login and same account as the web portal | Doctor Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P0 | M | — | No doctor app | Same Account login + DoctorId; bind device; no separate doctor identity | Web and app show the same queue for the same DoctorId | Not Started
910 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.1 | DMO-01 | Doctor app — login & identity (same login and same account as the web portal) | DMO-01.02 | Call same Login API; store JWT securely (Keychain/Keystore) | New | Doctor Mobile | §3 | Login & identity | Same login and same account as the web portal | Doctor Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P0 | M | DMO-01.01 | No doctor app | Same Account login + DoctorId; bind device; no separate doctor identity | Web and app show the same queue for the same DoctorId | Not Started
911 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.1 | DMO-01 | Doctor app — login & identity (same login and same account as the web portal) | DMO-01.03 | Expired session → re-login; no case-taking entry point | New | Doctor Mobile | §3 | Login & identity | Same login and same account as the web portal | Doctor Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P0 | S | DMO-01.02 | No doctor app | Same Account login + DoctorId; bind device; no separate doctor identity | Web and app show the same queue for the same DoctorId | Not Started
912 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.1 | DMO-01 | Doctor app — login & identity (same login and same account as the web portal) | DMO-01.04 | QA: same DoctorId as web; reception accounts must not open doctor clinical actions | Regression | Doctor Mobile | §3 | Login & identity | Same login and same account as the web portal | Doctor Mobile App | QA | Yes | No | No | Yes | Yes | No | P0 | S | DMO-01.03 | No doctor app | Same Account login + DoctorId; bind device; no separate doctor identity | Web and app show the same queue for the same DoctorId | Not Started
913 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.2 | DMO-02 | Doctor app — first-run onboarding (guided setup, number confirmation and permissions) | DMO-02.01 | Onboarding screens | New | Doctor Mobile | §3 | First-run onboarding | Guided setup, number confirmation and permissions | Doctor Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | — | No app | Confirm registered mobile; permission primer | Onboarding cannot be skipped past permission explanation for mic/camera/push | Not Started
914 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.2 | DMO-02 | Doctor app — first-run onboarding (guided setup, number confirmation and permissions) | DMO-02.02 | Confirm number against profile | New | Doctor Mobile | §3 | First-run onboarding | Guided setup, number confirmation and permissions | Doctor Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | DMO-02.01 | No app | Confirm registered mobile; permission primer | Onboarding cannot be skipped past permission explanation for mic/camera/push | Not Started
915 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.2 | DMO-02 | Doctor app — first-run onboarding (guided setup, number confirmation and permissions) | DMO-02.03 | Skip vs required steps documented | New | Doctor Mobile | §3 | First-run onboarding | Guided setup, number confirmation and permissions | Doctor Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | DMO-02.02 | No app | Confirm registered mobile; permission primer | Onboarding cannot be skipped past permission explanation for mic/camera/push | Not Started
916 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.2 | DMO-02 | Doctor app — first-run onboarding (guided setup, number confirmation and permissions) | DMO-02.04 | QA: number mismatch blocked | Regression | Doctor Mobile | §3 | First-run onboarding | Guided setup, number confirmation and permissions | Doctor Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | DMO-02.03 | No app | Confirm registered mobile; permission primer | Onboarding cannot be skipped past permission explanation for mic/camera/push | Not Started
917 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.3 | DMO-03 | Doctor app — notification permissions (push, microphone and camera handled properly) | DMO-03.01 | Permission primer + settings CTA | New | Doctor Mobile | §3 | Notification permissions | Push, microphone and camera permissions handled properly | Doctor Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P0 | M | — | No app | OS permission flows; settings deep link if denied | Denied camera still allows queue viewing; join explains why it cannot start | Not Started
918 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.3 | DMO-03 | Doctor app — notification permissions (push, microphone and camera handled properly) | DMO-03.02 | Register FCM/APNs token (COM-03) | New | Doctor Mobile | §3 | Notification permissions | Push, microphone and camera permissions handled properly | Doctor Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P0 | M | DMO-03.01 | No app | OS permission flows; settings deep link if denied | Denied camera still allows queue viewing; join explains why it cannot start | Not Started
919 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.3 | DMO-03 | Doctor app — notification permissions (push, microphone and camera handled properly) | DMO-03.03 | Denied-state UX | New | Doctor Mobile | §3 | Notification permissions | Push, microphone and camera permissions handled properly | Doctor Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P0 | S | DMO-03.02 | No app | OS permission flows; settings deep link if denied | Denied camera still allows queue viewing; join explains why it cannot start | Not Started
920 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.3 | DMO-03 | Doctor app — notification permissions (push, microphone and camera handled properly) | DMO-03.04 | QA: deny each permission independently | Regression | Doctor Mobile | §3 | Notification permissions | Push, microphone and camera permissions handled properly | Doctor Mobile App | QA | Yes | No | No | Yes | Yes | No | P0 | S | DMO-03.03 | No app | OS permission flows; settings deep link if denied | Denied camera still allows queue viewing; join explains why it cannot start | Not Started
921 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.4 | DMO-04 | Doctor app — today’s queue & schedule (the full day at a glance) | DMO-04.01 | TodayQueue screen | New | Doctor Mobile | §3 | Today’s queue & schedule | The full day at a glance | Doctor Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P0 | M | — | No app | Appointment list APIs; payment + tele flags; no Patient Board | Matches web dashboard buckets for today | Not Started
922 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.4 | DMO-04 | Doctor app — today’s queue & schedule (the full day at a glance) | DMO-04.02 | Existing appointment list APIs | New | Doctor Mobile | §3 | Today’s queue & schedule | The full day at a glance | Doctor Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P0 | M | DMO-04.01 | No app | Appointment list APIs; payment + tele flags; no Patient Board | Matches web dashboard buckets for today | Not Started
923 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.4 | DMO-04 | Doctor app — today’s queue & schedule (the full day at a glance) | DMO-04.03 | Pull-to-refresh; empty Sunday | New | Doctor Mobile | §3 | Today’s queue & schedule | The full day at a glance | Doctor Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P0 | S | DMO-04.02 | No app | Appointment list APIs; payment + tele flags; no Patient Board | Matches web dashboard buckets for today | Not Started
924 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.4 | DMO-04 | Doctor app — today’s queue & schedule (the full day at a glance) | DMO-04.04 | QA: parity with web counts | Regression | Doctor Mobile | §3 | Today’s queue & schedule | The full day at a glance | Doctor Mobile App | QA | Yes | No | No | Yes | Yes | No | P0 | S | DMO-04.03 | No app | Appointment list APIs; payment + tele flags; no Patient Board | Matches web dashboard buckets for today | Not Started
925 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.5 | DMO-05 | Doctor app — availability toggle (go online or offline, set working hours) | DMO-05.01 | Availability + hours screens | New | Doctor Mobile | §3 | Availability toggle | Go online or offline, set working hours | Doctor Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P0 | M | — | No app | Same TeleAvailability + schedule APIs as web | Toggle on app updates web and patient instant matching | Not Started
926 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.5 | DMO-05 | Doctor app — availability toggle (go online or offline, set working hours) | DMO-05.02 | TEL-01 + APT-07 APIs (hours read/edit policy: edit hours may stay web-only if product decides — PDF says set working hours so include) | New | Doctor Mobile | §3 | Availability toggle | Go online or offline, set working hours | Doctor Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P0 | M | DMO-05.01 | No app | Same TeleAvailability + schedule APIs as web | Toggle on app updates web and patient instant matching | Not Started
927 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.5 | DMO-05 | Doctor app — availability toggle (go online or offline, set working hours) | DMO-05.03 | Offline banner | New | Doctor Mobile | §3 | Availability toggle | Go online or offline, set working hours | Doctor Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P0 | S | DMO-05.02 | No app | Same TeleAvailability + schedule APIs as web | Toggle on app updates web and patient instant matching | Not Started
928 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.5 | DMO-05 | Doctor app — availability toggle (go online or offline, set working hours) | DMO-05.04 | QA: web and app status match within heartbeat | Regression | Doctor Mobile | §3 | Availability toggle | Go online or offline, set working hours | Doctor Mobile App | QA | Yes | No | No | Yes | Yes | No | P0 | S | DMO-05.03 | No app | Same TeleAvailability + schedule APIs as web | Toggle on app updates web and patient instant matching | Not Started
929 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.6 | DMO-06 | Doctor app — push notifications (waiting, booking, reschedule, cancellation, refill, payment received) | DMO-06.01 | Notification handling + deep links into queue/refill/join | New | Doctor Mobile | §3 | Push notifications | Patient waiting, new booking, reschedule, cancellation, refill request, payment received | Doctor Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P0 | M | — | No app | Consume COM-03 doctor templates | Each listed event delivers a push when permission granted | Not Started
930 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.6 | DMO-06 | Doctor app — push notifications (waiting, booking, reschedule, cancellation, refill, payment received) | DMO-06.02 | Device register | New | Doctor Mobile | §3 | Push notifications | Patient waiting, new booking, reschedule, cancellation, refill request, payment received | Doctor Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P0 | M | DMO-06.01 | No app | Consume COM-03 doctor templates | Each listed event delivers a push when permission granted | Not Started
931 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.6 | DMO-06 | Doctor app — push notifications (waiting, booking, reschedule, cancellation, refill, payment received) | DMO-06.03 | Foreground in-app banner | New | Doctor Mobile | §3 | Push notifications | Patient waiting, new booking, reschedule, cancellation, refill request, payment received | Doctor Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P0 | S | DMO-06.02 | No app | Consume COM-03 doctor templates | Each listed event delivers a push when permission granted | Not Started
932 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.6 | DMO-06 | Doctor app — push notifications (waiting, booking, reschedule, cancellation, refill, payment received) | DMO-06.04 | QA: each event type deep link | Regression | Doctor Mobile | §3 | Push notifications | Patient waiting, new booking, reschedule, cancellation, refill request, payment received | Doctor Mobile App | QA | Yes | No | No | Yes | Yes | No | P0 | S | DMO-06.03 | No app | Consume COM-03 doctor templates | Each listed event delivers a push when permission granted | Not Started
933 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.7 | DMO-07 | Doctor app — patient context card (name, age, chief complaint and last visit) — NO case-taking | DMO-07.01 | PatientCard read-only | New | Doctor Mobile | §3 | Patient context card | Name, age, chief complaint and last visit before joining | Doctor Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P0 | M | — | No app; PDF: detailed case-taking stays on the web portal | Read-only card; explicitly no repertory/audio/Rx compose | No path to Patient Board clinical tools from the app | Not Started
934 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.7 | DMO-07 | Doctor app — patient context card (name, age, chief complaint and last visit) — NO case-taking | DMO-07.02 | Context API (name, age, CC, last visit, payment, tele) | New | Doctor Mobile | §3 | Patient context card | Name, age, chief complaint and last visit before joining | Doctor Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P0 | M | DMO-07.01 | No app; PDF: detailed case-taking stays on the web portal | Read-only card; explicitly no repertory/audio/Rx compose | No path to Patient Board clinical tools from the app | Not Started
935 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.7 | DMO-07 | Doctor app — patient context card (name, age, chief complaint and last visit) — NO case-taking | DMO-07.03 | Do not ship case-taking tabs | New | Doctor Mobile | §3 | Patient context card | Name, age, chief complaint and last visit before joining | Doctor Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P0 | S | DMO-07.02 | No app; PDF: detailed case-taking stays on the web portal | Read-only card; explicitly no repertory/audio/Rx compose | No path to Patient Board clinical tools from the app | Not Started
936 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.7 | DMO-07 | Doctor app — patient context card (name, age, chief complaint and last visit) — NO case-taking | DMO-07.04 | QA: repertory endpoints never called from app | Regression | Doctor Mobile | §3 | Patient context card | Name, age, chief complaint and last visit before joining | Doctor Mobile App | QA | Yes | No | No | Yes | Yes | No | P0 | S | DMO-07.03 | No app; PDF: detailed case-taking stays on the web portal | Read-only card; explicitly no repertory/audio/Rx compose | No path to Patient Board clinical tools from the app | Not Started
937 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.8 | DMO-08 | Doctor app — join consultation (video or audio from the phone) | DMO-08.01 | VideoRoom | New | Doctor Mobile | §3 | Join consultation | Start the video or audio consultation from the phone | Doctor Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P0 | M | — | No app | Same session tokens as TEL-03/04 | Join same room as web patient or mobile patient | Not Started
938 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.8 | DMO-08 | Doctor app — join consultation (video or audio from the phone) | DMO-08.02 | Tele session tokens | New | Doctor Mobile | §3 | Join consultation | Start the video or audio consultation from the phone | Doctor Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P0 | M | DMO-08.01 | No app | Same session tokens as TEL-03/04 | Join same room as web patient or mobile patient | Not Started
939 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.8 | DMO-08 | Doctor app — join consultation (video or audio from the phone) | DMO-08.03 | Audio-only fallback | New | Doctor Mobile | §3 | Join consultation | Start the video or audio consultation from the phone | Doctor Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P0 | S | DMO-08.02 | No app | Same session tokens as TEL-03/04 | Join same room as web patient or mobile patient | Not Started
940 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.8 | DMO-08 | Doctor app — join consultation (video or audio from the phone) | DMO-08.04 | QA: web patient + app doctor | Regression | Doctor Mobile | §3 | Join consultation | Start the video or audio consultation from the phone | Doctor Mobile App | QA | Yes | No | No | Yes | Yes | No | P0 | S | DMO-08.03 | No app | Same session tokens as TEL-03/04 | Join same room as web patient or mobile patient | Not Started
941 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.9 | DMO-09 | Doctor app — refill approval (approve or reject repeat prescription requests) | DMO-09.01 | RefillInbox + RefillDetail | New | Doctor Mobile | §3 + §11 | Refill approval | Approve or reject repeat prescription requests | Doctor Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P0 | M | — | No app | ERX-10 inbox; approve only — Patient Board remains web | Approve/reject from phone writes the same RefillRequest as web | Not Started
942 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.9 | DMO-09 | Doctor app — refill approval (approve or reject repeat prescription requests) | DMO-09.02 | Approve/Reject APIs | New | Doctor Mobile | §3 + §11 | Refill approval | Approve or reject repeat prescription requests | Doctor Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P0 | M | DMO-09.01 | No app | ERX-10 inbox; approve only — Patient Board remains web | Approve/reject from phone writes the same RefillRequest as web | Not Started
943 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.9 | DMO-09 | Doctor app — refill approval (approve or reject repeat prescription requests) | DMO-09.03 | Show codes vs names per policy (doctor sees names) | New | Doctor Mobile | §3 + §11 | Refill approval | Approve or reject repeat prescription requests | Doctor Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P0 | S | DMO-09.02 | No app | ERX-10 inbox; approve only — Patient Board remains web | Approve/reject from phone writes the same RefillRequest as web | Not Started
944 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.9 | DMO-09 | Doctor app — refill approval (approve or reject repeat prescription requests) | DMO-09.04 | QA: reject reason; cannot edit snapshot | Regression | Doctor Mobile | §3 + §11 | Refill approval | Approve or reject repeat prescription requests | Doctor Mobile App | QA | Yes | No | No | Yes | Yes | No | P0 | S | DMO-09.03 | No app | ERX-10 inbox; approve only — Patient Board remains web | Approve/reject from phone writes the same RefillRequest as web | Not Started
945 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.10 | DMO-10 | Doctor app — earnings summary (today, this week, this month, with payout status) | DMO-10.01 | Earnings screens | New | Doctor Mobile | §3 + §16 | Earnings summary | Today, this week and this month, with payout status | Doctor Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | — | No app | Account ledger read model for this DoctorId — not a second money system | Figures match Account settlement for that doctor | Not Started
946 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.10 | DMO-10 | Doctor app — earnings summary (today, this week, this month, with payout status) | DMO-10.02 | GET Earnings/Summary | New | Doctor Mobile | §3 + §16 | Earnings summary | Today, this week and this month, with payout status | Doctor Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | DMO-10.01 | No app | Account ledger read model for this DoctorId — not a second money system | Figures match Account settlement for that doctor | Not Started
947 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.10 | DMO-10 | Doctor app — earnings summary (today, this week, this month, with payout status) | DMO-10.03 | Empty first week | New | Doctor Mobile | §3 + §16 | Earnings summary | Today, this week and this month, with payout status | Doctor Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | DMO-10.02 | No app | Account ledger read model for this DoctorId — not a second money system | Figures match Account settlement for that doctor | Not Started
948 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.10 | DMO-10 | Doctor app — earnings summary (today, this week, this month, with payout status) | DMO-10.04 | QA: matches /account figures ± rounding | Regression | Doctor Mobile | §3 + §16 | Earnings summary | Today, this week and this month, with payout status | Doctor Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | DMO-10.03 | No app | Account ledger read model for this DoctorId — not a second money system | Figures match Account settlement for that doctor | Not Started
949 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.11 | DMO-11 | Doctor app — offline handling (weak connection or expired session) | DMO-11.01 | Offline/error screens | New | Doctor Mobile | §3 | Offline handling | Clear behaviour on weak connection or expired session | Doctor Mobile App | Mobile UI | Yes | No | No | No | Yes | No | P1 | M | — | No app | Queued actions policy (do not fake join); session expiry uses SEC-03 | Expired JWT cannot join video; user is told to re-login | Not Started
950 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.11 | DMO-11 | Doctor app — offline handling (weak connection or expired session) | DMO-11.02 | 401 interceptor → logout API | New | Doctor Mobile | §3 | Offline handling | Clear behaviour on weak connection or expired session | Doctor Mobile App | Mobile client | Yes | No | No | Yes | Yes | No | P1 | M | DMO-11.01 | No app | Queued actions policy (do not fake join); session expiry uses SEC-03 | Expired JWT cannot join video; user is told to re-login | Not Started
951 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.11 | DMO-11 | Doctor app — offline handling (weak connection or expired session) | DMO-11.03 | No silent retry of payments | New | Doctor Mobile | §3 | Offline handling | Clear behaviour on weak connection or expired session | Doctor Mobile App | Mobile UX | Yes | No | No | No | Yes | No | P1 | S | DMO-11.02 | No app | Queued actions policy (do not fake join); session expiry uses SEC-03 | Expired JWT cannot join video; user is told to re-login | Not Started
952 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.11 | DMO-11 | Doctor app — offline handling (weak connection or expired session) | DMO-11.04 | QA: airplane mode on join | Regression | Doctor Mobile | §3 | Offline handling | Clear behaviour on weak connection or expired session | Doctor Mobile App | QA | Yes | No | No | Yes | Yes | No | P1 | S | DMO-11.03 | No app | Queued actions policy (do not fake join); session expiry uses SEC-03 | Expired JWT cannot join video; user is told to re-login | Not Started
953 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.12 | DMO-12 | Doctor app — reliability monitoring (failures reported automatically) | DMO-12.01 | Integrate Crashlytics/Sentry; map to doctorId hashed | New Integration | Doctor Mobile | §3 | Reliability monitoring | Failures are reported automatically, not left to a phone call | Doctor Mobile App | Mobile | No | No | No | No | Yes | Yes | P1 | S | — | No app | Crash/error SDK; join failures also as TeleSessionEvent | A forced crash appears in the monitoring tool within SLA | Not Started
954 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.12 | DMO-12 | Doctor app — reliability monitoring (failures reported automatically) | DMO-12.02 | QA: simulated crash + join fail event | Regression | Doctor Mobile | §3 | Reliability monitoring | Failures are reported automatically, not left to a phone call | Doctor Mobile App | QA | No | No | No | No | Yes | No | P1 | S | DMO-12.01 | No app | Crash/error SDK; join failures also as TeleSessionEvent | A forced crash appears in the monitoring tool within SLA | Not Started
955 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.13 | DMO-13 | Doctor app — iOS and Android parity QA (queue, availability, notifications, context, video, refill, earnings) | DMO-13.01 | Release builds both OS | New | Doctor Mobile | §3 + §18 | Doctor mobile app iOS and Android | iOS and Android — queue, availability, notifications, patient context, video consultation, refill approval, earnings | Doctor Mobile App | Mobile | No | No | No | No | Yes | No | P0 | L | — | No app | Parity checklist for every §3 row on both OS | Parity matrix signed | Not Started
956 | 17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 17.13 | DMO-13 | Doctor app — iOS and Android parity QA (queue, availability, notifications, context, video, refill, earnings) | DMO-13.02 | Parity QA DMO-01..12 both OS | Regression | Doctor Mobile | §3 + §18 | Doctor mobile app iOS and Android | iOS and Android — queue, availability, notifications, patient context, video consultation, refill approval, earnings | Doctor Mobile App | QA | No | No | No | No | Yes | No | P0 | L | DMO-13.01 | No app | Parity checklist for every §3 row on both OS | Parity matrix signed | Not Started
957 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.1 | RPT-01 | Admin overview dashboard — platform-wide activity at a glance (replace Velzon ecommerce) | RPT-01.01 | No ecommerce tables | Existing Improvement | Reports | §16 + §7.2 | Admin overview dashboard / Admin dashboard | Platform-wide activity at a glance / Live overview of the whole platform | Admin Portal | Database | No | Yes | Yes | No | No | No | P0 | S | — | Velzon ecommerce dashboard 0% product; login lands /dashboard | True /admin/dashboard KPIs: doctors, credentialing, bookings, GMV, failed payments, tickets, HomeoMeds exceptions; redirect /dashboard away from StoreVisits | Admin home is product KPIs, not Velzon Revenue/StoreVisits | Not Started
958 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.1 | RPT-01 | Admin overview dashboard — platform-wide activity at a glance (replace Velzon ecommerce) | RPT-01.02 | GET /api/AdminDashboard/Overview | Existing Improvement | Reports | §16 + §7.2 | Admin overview dashboard / Admin dashboard | Platform-wide activity at a glance / Live overview of the whole platform | Admin Portal | API | No | Yes | Yes | Yes | No | No | P0 | M | RPT-01.01 | Velzon ecommerce dashboard 0% product; login lands /dashboard | True /admin/dashboard KPIs: doctors, credentialing, bookings, GMV, failed payments, tickets, HomeoMeds exceptions; redirect /dashboard away from StoreVisits | Admin home is product KPIs, not Velzon Revenue/StoreVisits | Not Started
959 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.1 | RPT-01 | Admin overview dashboard — platform-wide activity at a glance (replace Velzon ecommerce) | RPT-01.03 | Replace pages/Admin/Dashboard; getHomeDashboardPath → /admin/dashboard | Existing Improvement | Reports | §16 + §7.2 | Admin overview dashboard / Admin dashboard | Platform-wide activity at a glance / Live overview of the whole platform | Admin Portal | Web SPA | Yes | No | No | Yes | No | No | P0 | M | RPT-01.02 | Velzon ecommerce dashboard 0% product; login lands /dashboard | True /admin/dashboard KPIs: doctors, credentialing, bookings, GMV, failed payments, tickets, HomeoMeds exceptions; redirect /dashboard away from StoreVisits | Admin home is product KPIs, not Velzon Revenue/StoreVisits | Not Started
960 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.1 | RPT-01 | Admin overview dashboard — platform-wide activity at a glance (replace Velzon ecommerce) | RPT-01.04 | QA: login as admin never shows fake store visits | Regression | Reports | §16 + §7.2 | Admin overview dashboard / Admin dashboard | Platform-wide activity at a glance / Live overview of the whole platform | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P0 | S | RPT-01.03 | Velzon ecommerce dashboard 0% product; login lands /dashboard | True /admin/dashboard KPIs: doctors, credentialing, bookings, GMV, failed payments, tickets, HomeoMeds exceptions; redirect /dashboard away from StoreVisits | Admin home is product KPIs, not Velzon Revenue/StoreVisits | Not Started
961 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.2 | RPT-02 | Doctor practice statistics — patient and consultation trends (extend existing charts) | RPT-02.01 | No new warehouse required for v1 | Existing Improvement | Reports | §16 + §5.1 | Doctor practice statistics | Patient and consultation trends | Doctor Web | Database | No | Yes | Yes | No | No | No | P1 | S | — | Patient stats charts live | Keep as foundation; ensure visit type/mode included after APT-02 | Trends include first vs follow-up when VisitType exists | Not Started
962 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.2 | RPT-02 | Doctor practice statistics — patient and consultation trends (extend existing charts) | RPT-02.02 | Extend GetPatientStatsCharts with VisitType/ConsultMode | Existing Improvement | Reports | §16 + §5.1 | Doctor practice statistics | Patient and consultation trends | Doctor Web | API | No | Yes | Yes | Yes | No | No | P1 | M | RPT-02.01 | Patient stats charts live | Keep as foundation; ensure visit type/mode included after APT-02 | Trends include first vs follow-up when VisitType exists | Not Started
963 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.2 | RPT-02 | Doctor practice statistics — patient and consultation trends (extend existing charts) | RPT-02.03 | Dashboard charts consume new series | Existing Improvement | Reports | §16 + §5.1 | Doctor practice statistics | Patient and consultation trends | Doctor Web | Web SPA | Yes | No | No | Yes | No | No | P1 | M | RPT-02.02 | Patient stats charts live | Keep as foundation; ensure visit type/mode included after APT-02 | Trends include first vs follow-up when VisitType exists | Not Started
964 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.2 | RPT-02 | Doctor practice statistics — patient and consultation trends (extend existing charts) | RPT-02.04 | QA: empty new clinic | Regression | Reports | §16 + §5.1 | Doctor practice statistics | Patient and consultation trends | Doctor Web | QA | Yes | Yes | No | Yes | No | No | P1 | S | RPT-02.03 | Patient stats charts live | Keep as foundation; ensure visit type/mode included after APT-02 | Trends include first vs follow-up when VisitType exists | Not Started
965 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.3 | RPT-03 | Follow-up analysis — due/overdue patients and follow-up conversion | RPT-03.01 | Queries on VisitType + FollowUpTask | New | Reports | §16 | Follow-up analysis | Which patients are due or overdue for follow-up, and follow-up conversion | Doctor Web | Database | No | Yes | Yes | No | No | No | P1 | S | — | Does not exist; follow-up option in notes does not save | /doctor/follow-up-analysis from VisitType + CON-04 tasks | Due list and conversion first-visit → follow-up are real counts | Not Started
966 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.3 | RPT-03 | Follow-up analysis — due/overdue patients and follow-up conversion | RPT-03.02 | GET FollowUpDue, FollowUpSummary | New | Reports | §16 | Follow-up analysis | Which patients are due or overdue for follow-up, and follow-up conversion | Doctor Web | API | No | Yes | Yes | Yes | No | No | P1 | M | RPT-03.01 | Does not exist; follow-up option in notes does not save | /doctor/follow-up-analysis from VisitType + CON-04 tasks | Due list and conversion first-visit → follow-up are real counts | Not Started
967 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.3 | RPT-03 | Follow-up analysis — due/overdue patients and follow-up conversion | RPT-03.03 | /doctor/follow-up-analysis | New | Reports | §16 | Follow-up analysis | Which patients are due or overdue for follow-up, and follow-up conversion | Doctor Web | Web SPA | Yes | No | No | Yes | No | No | P1 | M | RPT-03.02 | Does not exist; follow-up option in notes does not save | /doctor/follow-up-analysis from VisitType + CON-04 tasks | Due list and conversion first-visit → follow-up are real counts | Not Started
968 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.3 | RPT-03 | Follow-up analysis — due/overdue patients and follow-up conversion | RPT-03.04 | QA: overdue vs due buckets | Regression | Reports | §16 | Follow-up analysis | Which patients are due or overdue for follow-up, and follow-up conversion | Doctor Web | QA | Yes | Yes | No | Yes | No | No | P1 | S | RPT-03.03 | Does not exist; follow-up option in notes does not save | /doctor/follow-up-analysis from VisitType + CON-04 tasks | Due list and conversion first-visit → follow-up are real counts | Not Started
969 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.4 | RPT-04 | Clinic performance analysis — appointments, slot utilisation, no-shows, cancellations, waiting time and revenue | RPT-04.01 | Aggregate APIs beyond GetPatientStatsCharts | New | Reports | §16 | Clinic performance analysis | Appointments, slot utilisation, no-shows, cancellations, waiting time and revenue | Doctor Web | Database | No | Yes | Yes | No | No | No | P1 | S | — | Does not exist | /doctor/clinic-performance including payment collected and tele duration if timed | Each KPI has a definition note on the screen (no silent formula) | Not Started
970 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.4 | RPT-04 | Clinic performance analysis — appointments, slot utilisation, no-shows, cancellations, waiting time and revenue | RPT-04.02 | GET ClinicPerformance | New | Reports | §16 | Clinic performance analysis | Appointments, slot utilisation, no-shows, cancellations, waiting time and revenue | Doctor Web | API | No | Yes | Yes | Yes | No | No | P1 | M | RPT-04.01 | Does not exist | /doctor/clinic-performance including payment collected and tele duration if timed | Each KPI has a definition note on the screen (no silent formula) | Not Started
971 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.4 | RPT-04 | Clinic performance analysis — appointments, slot utilisation, no-shows, cancellations, waiting time and revenue | RPT-04.03 | /doctor/clinic-performance | New | Reports | §16 | Clinic performance analysis | Appointments, slot utilisation, no-shows, cancellations, waiting time and revenue | Doctor Web | Web SPA | Yes | No | No | Yes | No | No | P1 | M | RPT-04.02 | Does not exist | /doctor/clinic-performance including payment collected and tele duration if timed | Each KPI has a definition note on the screen (no silent formula) | Not Started
972 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.4 | RPT-04 | Clinic performance analysis — appointments, slot utilisation, no-shows, cancellations, waiting time and revenue | RPT-04.04 | QA: cancelled excluded from completed; revenue uses ledger not client | Regression | Reports | §16 | Clinic performance analysis | Appointments, slot utilisation, no-shows, cancellations, waiting time and revenue | Doctor Web | QA | Yes | Yes | No | Yes | No | No | P1 | S | RPT-04.03 | Does not exist | /doctor/clinic-performance including payment collected and tele duration if timed | Each KPI has a definition note on the screen (no silent formula) | Not Started
973 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.5 | RPT-05 | Payment reconciliation report — bookings matched against payments | RPT-05.01 | CSV/PDF export of FIN-02 query | New | Reports | §16 + §7.2 | Payment reconciliation report / Consult booking & payment reconciliation | Bookings matched against payments / Match every booking against every payment | Admin + Account | API | No | Yes | No | Yes | No | No | P1 | S | — | FIN-02 built the queue; this is the report/export | Exportable report from the same reconciliation query | CSV totals match on-screen KPIs | Not Started
974 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.5 | RPT-05 | Payment reconciliation report — bookings matched against payments | RPT-05.02 | Report UI on admin/account recon screens | New | Reports | §16 + §7.2 | Payment reconciliation report / Consult booking & payment reconciliation | Bookings matched against payments / Match every booking against every payment | Admin + Account | Web SPA | Yes | No | No | No | No | No | P1 | S | RPT-05.01 | FIN-02 built the queue; this is the report/export | Exportable report from the same reconciliation query | CSV totals match on-screen KPIs | Not Started
975 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.5 | RPT-05 | Payment reconciliation report — bookings matched against payments | RPT-05.03 | QA: unmatched rows included | Regression | Reports | §16 + §7.2 | Payment reconciliation report / Consult booking & payment reconciliation | Bookings matched against payments / Match every booking against every payment | Admin + Account | QA | Yes | No | No | No | No | No | P1 | S | RPT-05.02 | FIN-02 built the queue; this is the report/export | Exportable report from the same reconciliation query | CSV totals match on-screen KPIs | Not Started
976 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.6 | RPT-06 | Settlement & payout reports — amounts due and paid to doctors and pharmacies | RPT-06.01 | Export settlement runs + payout register | New | Reports | §16 + §8 | Settlement & payout reports | Amounts due and paid to doctors and pharmacies | Account | API | No | Yes | No | Yes | No | No | P1 | S | — | FIN-04/05 exist as ops screens | Formal report/export of runs and payouts | Paid vs due columns reconcile to ledger | Not Started
977 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.6 | RPT-06 | Settlement & payout reports — amounts due and paid to doctors and pharmacies | RPT-06.02 | Report UI | New | Reports | §16 + §8 | Settlement & payout reports | Amounts due and paid to doctors and pharmacies | Account | Web SPA | Yes | No | No | No | No | No | P1 | S | RPT-06.01 | FIN-04/05 exist as ops screens | Formal report/export of runs and payouts | Paid vs due columns reconcile to ledger | Not Started
978 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.6 | RPT-06 | Settlement & payout reports — amounts due and paid to doctors and pharmacies | RPT-06.03 | QA: pharmacy lines appear only after HomeoMeds | Regression | Reports | §16 + §8 | Settlement & payout reports | Amounts due and paid to doctors and pharmacies | Account | QA | Yes | No | No | No | No | No | P1 | S | RPT-06.02 | FIN-04/05 exist as ops screens | Formal report/export of runs and payouts | Paid vs due columns reconcile to ledger | Not Started
979 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.7 | RPT-07 | GST & invoice reports (reporting surface of FIN-08) | RPT-07.01 | Confirm CA format; implement export if not already in FIN-08 | New | Reports | §16 + §8 | GST & invoice reports | Tax reporting | Account | API | No | Yes | No | No | No | No | P1 | M | — | FIN-08 built tax screen | Confirm report pack (GSTR-style export as agreed with CA) — configuration | Invoice list export matches FIN-08 | Not Started
980 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.7 | RPT-07 | GST & invoice reports (reporting surface of FIN-08) | RPT-07.02 | QA: number series gaps flagged | Regression | Reports | §16 + §8 | GST & invoice reports | Tax reporting | Account | QA | No | Yes | No | No | No | No | P1 | S | RPT-07.01 | FIN-08 built tax screen | Confirm report pack (GSTR-style export as agreed with CA) — configuration | Invoice list export matches FIN-08 | Not Started
981 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.8 | RPT-08 | Doctor earnings summary — daily, weekly and monthly earnings with payout status (web + same API as DMO-10) | RPT-08.01 | Reuse earnings API | New | Reports | §16 + §3 | Doctor earnings summary | Daily, weekly and monthly earnings with payout status | Doctor Web + App | Database | No | Yes | Yes | No | No | No | P1 | S | — | Does not exist | Web earnings page using same API as doctor app | Web and app match | Not Started
982 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.8 | RPT-08 | Doctor earnings summary — daily, weekly and monthly earnings with payout status (web + same API as DMO-10) | RPT-08.02 | GET Earnings/Summary already for app — add if missing date buckets | New | Reports | §16 + §3 | Doctor earnings summary | Daily, weekly and monthly earnings with payout status | Doctor Web + App | API | No | Yes | Yes | Yes | No | No | P1 | M | RPT-08.01 | Does not exist | Web earnings page using same API as doctor app | Web and app match | Not Started
983 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.8 | RPT-08 | Doctor earnings summary — daily, weekly and monthly earnings with payout status (web + same API as DMO-10) | RPT-08.03 | /doctor/earnings | New | Reports | §16 + §3 | Doctor earnings summary | Daily, weekly and monthly earnings with payout status | Doctor Web + App | Web SPA | Yes | No | No | Yes | No | No | P1 | M | RPT-08.02 | Does not exist | Web earnings page using same API as doctor app | Web and app match | Not Started
984 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.8 | RPT-08 | Doctor earnings summary — daily, weekly and monthly earnings with payout status (web + same API as DMO-10) | RPT-08.04 | QA: payout pending vs paid | Regression | Reports | §16 + §3 | Doctor earnings summary | Daily, weekly and monthly earnings with payout status | Doctor Web + App | QA | Yes | Yes | No | Yes | No | No | P1 | S | RPT-08.03 | Does not exist | Web earnings page using same API as doctor app | Web and app match | Not Started
985 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.9 | RPT-09 | Medicine order reports — order volumes, fulfilment and exceptions | RPT-09.01 | Aggregates on MedicineOrder | New | Reports | §16 + §12 | Medicine order reports | Order volumes, fulfilment and exceptions | Admin + Account | Database | No | Yes | Yes | No | No | No | P1 | S | — | Does not exist | Volumes, SLA, exception counts from HomeoMeds | Exception count matches MED-12 queue | Not Started
986 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.9 | RPT-09 | Medicine order reports — order volumes, fulfilment and exceptions | RPT-09.02 | GET medicine order report | New | Reports | §16 + §12 | Medicine order reports | Order volumes, fulfilment and exceptions | Admin + Account | API | No | Yes | Yes | Yes | No | No | P1 | M | RPT-09.01 | Does not exist | Volumes, SLA, exception counts from HomeoMeds | Exception count matches MED-12 queue | Not Started
987 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.9 | RPT-09 | Medicine order reports — order volumes, fulfilment and exceptions | RPT-09.03 | Admin/account report page | New | Reports | §16 + §12 | Medicine order reports | Order volumes, fulfilment and exceptions | Admin + Account | Web SPA | Yes | No | No | Yes | No | No | P1 | M | RPT-09.02 | Does not exist | Volumes, SLA, exception counts from HomeoMeds | Exception count matches MED-12 queue | Not Started
988 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.9 | RPT-09 | Medicine order reports — order volumes, fulfilment and exceptions | RPT-09.04 | QA: cancelled orders not counted as delivered | Regression | Reports | §16 + §12 | Medicine order reports | Order volumes, fulfilment and exceptions | Admin + Account | QA | Yes | Yes | No | Yes | No | No | P1 | S | RPT-09.03 | Does not exist | Volumes, SLA, exception counts from HomeoMeds | Exception count matches MED-12 queue | Not Started
989 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.10 | RPT-10 | Platform users remaining 20% — import, export and activation control | RPT-10.01 | VerificationStatus on user/doctor list DTO | Existing Improvement | Admin | §7.2 | Platform users | Manage all users with import, export and activation control | Admin Portal | Database | No | Yes | Yes | No | No | No | P1 | S | — | List/Add/Edit live; Import/Export buttons dead; no verification column | Wire Import/Export; verification column; activate/lock; link credentialing | Import/Export work; unverified visible; lock prevents login | Not Started
990 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.10 | RPT-10 | Platform users remaining 20% — import, export and activation control | RPT-10.02 | User import/export APIs if missing | Existing Improvement | Admin | §7.2 | Platform users | Manage all users with import, export and activation control | Admin Portal | API | No | Yes | Yes | Yes | No | No | P1 | M | RPT-10.01 | List/Add/Edit live; Import/Export buttons dead; no verification column | Wire Import/Export; verification column; activate/lock; link credentialing | Import/Export work; unverified visible; lock prevents login | Not Started
991 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.10 | RPT-10 | Platform users remaining 20% — import, export and activation control | RPT-10.03 | ListUser.js wire dead buttons; verification column | Existing Improvement | Admin | §7.2 | Platform users | Manage all users with import, export and activation control | Admin Portal | Web SPA | Yes | No | No | Yes | No | No | P1 | M | RPT-10.02 | List/Add/Edit live; Import/Export buttons dead; no verification column | Wire Import/Export; verification column; activate/lock; link credentialing | Import/Export work; unverified visible; lock prevents login | Not Started
992 | 18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 18.10 | RPT-10 | Platform users remaining 20% — import, export and activation control | RPT-10.04 | QA: export contains only permitted fields | Regression | Admin | §7.2 | Platform users | Manage all users with import, export and activation control | Admin Portal | QA | Yes | Yes | No | Yes | No | No | P1 | S | RPT-10.03 | List/Add/Edit live; Import/Export buttons dead; no verification column | Wire Import/Export; verification column; activate/lock; link credentialing | Import/Export work; unverified visible; lock prevents login | Not Started
993 | 19 | Phase 19 — Cross-surface QA, NFR, delivery summary gate (PDF §1 + §18) | 19.1 | QA-01 | One ecosystem proof — patient, appointment, prescription and payment created anywhere are visible everywhere | QA-01.01 | E2E: Reception creates patient+appt → Doctor board → sign eRx → Patient app sees codes → Pharmacy accept OTP → patient sees names+pay → Account ledger S2 and S5 | Regression | QA | §1 + §18 | One connected ecosystem | A patient, an appointment, a prescription and a payment created anywhere in the system are visible everywhere else | All | QA | Yes | Yes | No | No | Yes | No | P0 | L | — | Surfaces were built in phases | End-to-end scripts covering all six user types | Signed E2E pack: 6 roles, no dual ledgers, no dual appointments | Not Started
994 | 19 | Phase 19 — Cross-surface QA, NFR, delivery summary gate (PDF §1 + §18) | 19.1 | QA-01 | One ecosystem proof — patient, appointment, prescription and payment created anywhere are visible everywhere | QA-01.02 | E2E: Patient app books+pays tele → doctor app join → summary+eRx → refill on doctor app | Regression | QA | §1 + §18 | One connected ecosystem | A patient, an appointment, a prescription and a payment created anywhere in the system are visible everywhere else | All | QA | No | No | No | No | Yes | No | P0 | L | QA-01.01 | Surfaces were built in phases | End-to-end scripts covering all six user types | Signed E2E pack: 6 roles, no dual ledgers, no dual appointments | Not Started
995 | 19 | Phase 19 — Cross-surface QA, NFR, delivery summary gate (PDF §1 + §18) | 19.1 | QA-01 | One ecosystem proof — patient, appointment, prescription and payment created anywhere are visible everywhere | QA-01.03 | Negative: Admin cannot payout; Account cannot edit repertory | Regression | QA | §1 + §18 | One connected ecosystem | A patient, an appointment, a prescription and a payment created anywhere in the system are visible everywhere else | All | QA | No | Yes | No | No | No | No | P0 | S | QA-01.02 | Surfaces were built in phases | End-to-end scripts covering all six user types | Signed E2E pack: 6 roles, no dual ledgers, no dual appointments | Not Started
996 | 19 | Phase 19 — Cross-surface QA, NFR, delivery summary gate (PDF §1 + §18) | 19.2 | QA-02 | Delivery summary gate — every area in PDF §18 signed off | QA-02.01 | Traceability review: 01_PDF_Coverage every row has Main Task ID and final Status | Regression | QA | §18 | Summary of delivery | All features listed in this document are included in the delivery scope. | Programme | QA | No | No | No | No | No | No | P0 | M | — | This register is the scope | Walk the coverage sheet; zero PDF rows with Status≠Done unless formally deferred with client sign | Coverage sheet 100% mapped; deferred items have written client sign | Not Started
997 | 19 | Phase 19 — Cross-surface QA, NFR, delivery summary gate (PDF §1 + §18) | 19.2 | QA-02 | Delivery summary gate — every area in PDF §18 signed off | QA-02.02 | Do not ship Velzon demo tickets/KYC/ecommerce as product | Regression | QA | §18 | Summary of delivery | All features listed in this document are included in the delivery scope. | Programme | QA | Yes | No | No | No | No | No | P0 | S | QA-02.01 | This register is the scope | Walk the coverage sheet; zero PDF rows with Status≠Done unless formally deferred with client sign | Coverage sheet 100% mapped; deferred items have written client sign | Not Started
998 | 19 | Phase 19 — Cross-surface QA, NFR, delivery summary gate (PDF §1 + §18) | 19.3 | NFR-01 | NFR — performance, low-data, reliability, secrets, dual-API freeze | NFR-01.01 | Rotate API secrets; keys in config/KeyVault; directory browsing remains off | Existing Modification | NFR | §2.9 + §3 + §17 | Low-data mode / Reliability monitoring / Secure login | Works on slow connections; failures reported automatically; credentials protected | All | Security | No | Yes | No | No | No | No | P0 | M | — | Known risks: plaintext passwords (fixed P0), secrets in appsettings, dual API drift | Rotate secrets; no new third API; patient low-data verified; doctor reliability SDK live | Load test on booking+webhook; secrets not in git; dual-API map documented | Not Started
999 | 19 | Phase 19 — Cross-surface QA, NFR, delivery summary gate (PDF §1 + §18) | 19.3 | NFR-01 | NFR — performance, low-data, reliability, secrets, dual-API freeze | NFR-01.02 | Performance: slot lock under concurrent public booking | Regression | NFR | §2.9 + §3 + §17 | Low-data mode / Reliability monitoring / Secure login | Works on slow connections; failures reported automatically; credentials protected | All | QA | No | Yes | No | No | No | No | P0 | M | NFR-01.01 | Known risks: plaintext passwords (fixed P0), secrets in appsettings, dual API drift | Rotate secrets; no new third API; patient low-data verified; doctor reliability SDK live | Load test on booking+webhook; secrets not in git; dual-API map documented | Not Started
1000 | 19 | Phase 19 — Cross-surface QA, NFR, delivery summary gate (PDF §1 + §18) | 19.3 | NFR-01 | NFR — performance, low-data, reliability, secrets, dual-API freeze | NFR-01.03 | Patient low-data mode QA on 2G profile | Regression | NFR | §2.9 + §3 + §17 | Low-data mode / Reliability monitoring / Secure login | Works on slow connections; failures reported automatically; credentials protected | All | QA | No | No | No | No | Yes | No | P0 | S | NFR-01.02 | Known risks: plaintext passwords (fixed P0), secrets in appsettings, dual API drift | Rotate secrets; no new third API; patient low-data verified; doctor reliability SDK live | Load test on booking+webhook; secrets not in git; dual-API map documented | Not Started

## 04_Dashboard
COUNTS FOR PLANNING — source = generated tasks (not live Status). Refresh by re-running the generator after edits to the Python source.
By phase |  |  | By work type
Phase | Phase name | Sub tasks | Work Type | Sub tasks
PRE | PRE — Client gates (must sign before Phase 6 money spine) | 11 | New | 488
0 | Phase 0 — Foundation: one ecosystem, identity, security (PDF §1 + §17) | 41 | Regression | 227
1 | Phase 1 — Admin clinical knowledge masters (PDF §7.1) — keep live, do not rebuild | 85 | Existing Improvement | 145
2 | Phase 2 — Doctor clinical workspace (PDF §5.3) — complete the existing heart of the product | 67 | Existing | 103
3 | Phase 3 — Doctor dashboard & daily operations (PDF §5.1) | 33 | New Integration | 19
4 | Phase 4 — Appointments & scheduling (PDF §5.2) — product completeness before public booking | 33 | Client Decision | 9
5 | Phase 5 — Reception portal (PDF §6) | 39 | Existing Modification | 6
6 | Phase 6 — Payment system (PDF §9) — Homeocentrum holds every rupee | 42 | Configuration | 2
7 | Phase 7 — Account & finance department (PDF §8) | 42 | Data Migration | 1
8 | Phase 8 — Trust & verification (PDF §13) — gate public doctor discovery | 27
9 | Phase 9 — Patient website (PDF §4) — public discovery, booking, payment | 40 | By application surface
10 | Phase 10 — Digital prescription / eRx (PDF §11) | 35 | Surface | Sub tasks
11 | Phase 11 — Telemedicine / video consultation (PDF §10) | 44 | Patient Mobile App | 231
12 | Phase 12 — Communication & notifications (PDF §14) | 22 | Doctor Web Portal | 136
13 | Phase 13 — Support & help desk (PDF §15) | 24 | Admin Portal | 104
14 | Phase 14 — HomeoMeds online medicine delivery (PDF §12) | 55 | Doctor Mobile App | 48
15 | Phase 15 — Patient continuity APIs (PDF §2.5–2.8) — build before mobile UI | 37 | Reception Portal | 44
16 | Phase 16 — Patient mobile app iOS & Android (PDF §2) — consumes Phases 8–15 APIs | 231 | Shared | 43
17 | Phase 17 — Doctor mobile app iOS & Android (PDF §3) — no case-taking on phone | 48 | Account Portal | 32
18 | Phase 18 — Reports & analytics (PDF §16) — after data exists | 36 | Patient | 29
19 | Phase 19 — Cross-surface QA, NFR, delivery summary gate (PDF §1 + §18) | 8 | Patient App (API now) | 27
|  |  | Doctor Web | 22
|  |  | Patient Website | 21
|  |  | Patient + Doctor | 19
|  |  | All | 17
|  |  | Doctor + Patient | 16
|  |  | Admin + Account | 13
|  |  | Doctor Web + Admin | 11
|  |  | Patient Website + App | 11
|  |  | Doctor Web + Reception + later Patient | 10
|  |  | Account | 10
|  |  | Doctor Web + App | 9
|  |  | Account + Admin | 8
|  |  | Public | 8
|  |  | Pharmacy console | 8
|  |  | Public + Patient app | 7
|  |  | Patient App + Doctor App | 7
|  |  | Backend | 7
|  |  | Patient + Pharmacy | 6
|  |  | Doctor Web + Patient | 6
|  |  | Public web + later Patient app | 5
|  |  | Account + Patient | 5
|  |  | All web + later mobile | 4
|  |  | Admin / Doctor / Reception web | 4
|  |  | Admin / All web | 4
|  |  | Doctor profile + Public + Admin | 4
|  |  | Patient + Public | 4
|  |  | Doctor + Patient + Admin | 4
|  |  | Patient Website + Admin | 4
|  |  | Patient + Doctor mobile + Doctor web | 4
|  |  | Doctor Web + Doctor App | 4
|  |  | Patient App + Doctor Web/App | 4
|  |  | Patient App + Admin | 4
|  |  | Support + Reception + Patient | 4
|  |  | Pharmacy + Admin | 4
|  |  | Account / Gateway | 3
|  |  | Account / Reception | 3
|  |  | API | 3
|  |  | Doctor Web Portal + Admin intelligence | 3
|  |  | Public + Doctor + Reception | 3
|  |  | Public + Payments | 3
|  |  | Patient App + Website | 3
|  |  | Admin + Doctor + Patient | 3
|  |  | Pharmacy + Account | 2
|  |  | Programme | 2

## 05_Screen_API_DB
Implementation index — screens, APIs and tables the sequential register implements. Design sign-off still required on exact paths.
NEW / CHANGED SCREENS
Area | Items
Admin | KPI home · Credentialing queue/detail · Users import/export · Consult recon · Payment exceptions · Support tickets · Enquiries inbox · Pharmacy activation · HomeoMeds exceptions · Help articles
Account | Ledger · Consult recon · Medicine ledger · Exceptions · Settlements · Payouts · Refunds · Tax · Payees · Clinic collections
Doctor web | Real profile · Schedule · Reception staff · Reschedule/Cancel modals · Follow-up analysis · Clinic performance · Earnings · SMS templates · Tele room · COG panel · eRx sign · Visit notes split · Support
Reception | Reception home/queue · Profile · Read-only schedule · Case paper · Collect payment
Public website | Home CTAs · /book · slots · confirm · pay · doctor profile · articles · privacy/terms · register docs
Pharmacy | Onboard · Order inbox · Order detail (OTP accept, quote, dispatch)
Patient app | Every PAT-01..57 screen in PDF §2
Doctor app | Every DMO-01..12 screen in PDF §3 — no case-taking
PROPOSED APIs (target contracts)
Area | Items
Auth / profile | Logout · Forgot/Reset/ChangePassword · Profile/Me · Profile/Photo · PatientAuth RequestOtp/VerifyOtp
Credentialing | Queue · {id} · Approve · Reject · RequestInfo · Documents · MyStatus · RegisterDoctor (modify)
Payments | Orders · Webhook/Razorpay · ConsultOrder · CollectAtReception · Exceptions · Refunds · Invoices · Earnings/Summary
Ledger | Ledger · MedicineLedger · Settlements · ApprovePayout (OTP) · Payees · ClinicCollections
Public booking | Doctors · Profile · Slots · Create · Waitlist · InstantConsult
Appointments | RescheduleAppointment · CancelAppointment · ChangeLog · VisitType PATCH
eRx | PotencyMaster · SignErx · Erx/ByAppointment · Export PDF · RefillInbox · Approve/Reject
Telemedicine | Availability · Queue · Sessions · End · Rejoin · Consent · Chat · Summary
HomeoMeds | Onboard · Licence · Sellers · Orders · Accept OTP · Quote · Pay · Status · Exceptions · Refill
Support / comms | SupportTicket · SMS Templates/Send · Devices/Register · Notifications
Continuity | Family · Caregiver · Timeline · Diary · FollowUp · Consents · Patient Payments
NEW / MODIFIED TABLES
Area | Items
Modified existing | UserMaster (hash) · Doctor (fee/KYC/verification) · Patient · PatientAppointment (VisitType, ConsultMode, PaymentStatus, CANCELLED) · AppointmentHistoryNote (NoteType) · PrescriptionRemedyDetail (PotencyId) · Role/Menu · EnquiryDetail · UserLoginStatus · PackageEntryDetail UNCHANGED shape
Trust / identity | DoctorVerification · DoctorCredentialDocument · FamilyMember · CaregiverAuth · ConsentRecord · Review · ReviewAppeal
Money | PaymentOrder · PaymentEvent · LedgerEntry · ConsultPayment · ConsultFeeConfig · PaymentException · SettlementRun · Payout · Refund · Invoice · Payee
Control | OtpChallenge · OtpAuditLog · PasswordResetToken · AuditEvent · SecureDocument
Clinical / eRx / tele | PotencyMaster · ErxSnapshot · ErxSnapshotItem · RefillRequest · TeleAvailability · TeleSession · TeleChatMessage · ConsultationSummary · FollowUpTask · SymptomDiary
HomeoMeds | PharmacyPartner · PharmacyLicence · SellerRoutingRule · MedicineOrder · MedicineOrderItem · MedicineQuote · MedicineOrderEvent
Messaging / support | SmsTemplate · SmsMessageLog · DeviceToken · AppNotification · SupportTicket · SupportTicketMessage · HelpArticle